## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 64f65ea6-078a-4b7b-bd96-ef12f5e2f8a3 |  | checklist | W |  |  |  |  | Yes | Woods - Grafton Install QA Checklist | 20047161-9836-4243-a4d7-80f28d4f1075
checkpoint-group | f3d408dc-948d-4085-8da1-8bda54114f32 |  | section | Pre-start
checkpoint-status | c8d05fe5-ec28-4917-a50c-dc5d29705f63 |  | checkpoint | Openings Correct
checkpoint-status | f694bbf0-240e-4525-801e-ca7adfc9543f |  | checkpoint | Area Tidy
checkpoint-status | 830d9bad-0da1-4034-887d-61a9819c91a4 |  | checkpoint | Water Proofing / Flashing Tape installed
checkpoint-group | 4348e6f5-f408-4da7-bb77-68c84d39d7e9 |  | section | Install
checkpoint-status | 0b04e9f9-78f4-4545-9832-bbb255a84c28 |  | checkpoint | Correct Packing
checkpoint-status | 30f79605-263d-49c6-a230-82dd292cee5f |  | checkpoint | Frame Installed Correctly / As per SD’s
checkpoint-status | a65e1a50-d426-43da-a49c-8cc81b5bf503 |  | checkpoint | Fixings as per SD's / Overseal Complete
checkpoint-status | 4ccdd101-6023-4e02-aefd-d658e437fbc1 |  | checkpoint | Seals and PEF Rod Completed
checkpoint-status | 8b67c5b2-bd60-4387-a7e1-0ecab2be67cb |  | checkpoint | Seal between 6mm & 20mm Wide
checkpoint-status | 94db30c8-c893-40c8-9bf6-65338510fe37 |  | checkpoint | Sub Sill End Dams sealed correctly
checkpoint-status | c391fd9c-3fe8-4b4f-8f28-dbf1103cec9f |  | checkpoint | Head & External Flashings Installed
checkpoint-status | 1490a0f7-bcfc-4d9b-9295-3eae13eb55d5 |  | checkpoint | Hardware Installed and Operational
checkpoint-status | e1e7ff09-c332-4ae1-9f9f-0fd933544db1 |  | checkpoint | Manifestation Strips N/A
checkpoint-group | e8ddd385-d4a6-4f66-b2dd-fd3ecbedf49e |  | section | Glazing
checkpoint-status | a43f9681-f631-4b03-9709-035386defaad |  | checkpoint | Glass Defect Free
checkpoint-status | fd68c266-b2c6-4b5a-94f6-caaaf8e550f7 |  | checkpoint | Back Pan - Clean Cavitiy - Backpan QA if installed on site
checkpoint-status | 33f7ae68-33b2-47e3-9cb8-ae2266af2b1a |  | checkpoint | Glass Type - Installed Correctly
checkpoint-status | df6ac5c2-9823-41f1-8cb6-c73e65a15a77 |  | checkpoint | Glass Installed - Correct Orientation
checkpoint-status | 2237d2e8-bc28-473a-bf46-f1f4513dbe72 |  | checkpoint | Wedge - Complete
checkpoint-group | cb2b6054-e193-4fb0-80ab-0fef1d493792 |  | section | Handover
checkpoint-status | 5239a585-5194-48f6-9d7b-8dfb7af75262 |  | checkpoint | Defects List Completed
checkpoint-status | 46ee65b3-d52b-44ba-b064-ab8716fc81f3 |  | checkpoint | Area Clean and Tidy
checkpoint-status | 04757274-f54d-4178-8908-48c61d8d3e9b |  | checkpoint | Window opening Functional
checkpoint-status | 7e0bb2b9-37d5-4fe2-a983-4e3ccc0dc41c |  | checkpoint | Doors Operational
checkpoint-status | 6b57082a-a4f0-4b99-96b3-aed32c15b224 |  | checkpoint | Handover Keys
checkpoint-status | 187be866-5472-4c7a-96f3-c76dfc0c9336 |  | checkpoint | Please find pictures attached
checkpoint-group | f11636d2-5fc8-46d5-ac72-326c48829803 |  | section | Client Signoff
checkpoint-status | 192cded3-8b7b-4c4f-9aca-7b85fc510fef |  | checkpoint | SIGNED
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | c891559e-4614-4fb4-9a63-872ed22592c2
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | H&S Week Starting: |  |  |  |  | Yes | Add Weekly H&S Checklist | 3efe68fe-fa2f-4031-84c4-aae7d467c3be
checkpoint-status |  |  | checkpoint | Task Analysis/JSA
checkpoint-status |  |  | checkpoint | Toolbox Minutes
checkpoint-status |  |  | checkpoint | Hot Works Permits/Confined Spaces/Working at heights
checkpoint-status |  |  | checkpoint | Site Safety Inspection Checklists
checkpoint-status |  |  | checkpoint | Hazard ID
checkpoint-status |  |  | checkpoint | Accident/Incident/Near Miss Investigation Report
checkpoint-status |  |  | checkpoint | Notice/Record of Serious Harm Accident
checkpoint-status |  |  | checkpoint | Additional Heath & Safety Documentation
checklist-sectioned |  |  | checklist | Item Install QA |  |  |  |  | Yes | Add Item Install QA Checklist | 4dfd150c-6ebf-423b-86b9-e76d868e019b
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Opening correct, rebates, drip grooves
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Building wrap correctly installed
checkpoint-status |  |  | checkpoint | Flashing tape correctly installed
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Correct packings and sufficient at fixings
checkpoint-status |  |  | checkpoint | Reveal material correct size (TWT) and undamaged
checkpoint-status |  |  | checkpoint | Reveal grooves correct size and location for linings
checkpoint-status |  |  | checkpoint | Frame installed correctly
checkpoint-status |  |  | checkpoint | Head flashing installed
checkpoint-status |  |  | checkpoint | Openings correct and operational
checkpoint-status |  |  | checkpoint | Sealants and air seals installed correctly with Perf rod
checkpoint-status |  |  | checkpoint | Hardware installed and operational
checkpoint-status |  |  | checkpoint | Manifestation installed
checkpoint-status |  |  | checkpoint | Glazing completed correct to specification including wedging
checkpoint-group |  |  | section | Handover / Signoff
checkpoint-status |  |  | checkpoint | Item inspected and damage free
checkpoint-status |  |  | checkpoint | Area and item left clean and tidy
checkpoint-status |  |  | checkpoint | Protection tapes and films installed
checkpoint-status |  |  | checkpoint | Item inspected, all elements checked, correct, functioning and approved
checkpoint-status |  |  | checkpoint | Windows left clean
checkpoint-status |  |  | checkpoint | Window openers, etc commmissioned
checkpoint-status |  |  | checkpoint | Remidial list completed
checkpoint-status |  |  | checkpoint | Handover keys
holdpoint |  |  | signoff | Request approval