## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN | itp |  |  |  |  | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN Rev 1
section | Preliminaries
checkpoint | 1.01 - PQE
label | Material Test Method Requirement - Has all preseal repairs been completed?
label | Reference Documents - Insert Layer Acceptance ITP No
label | Material Acceptance Criteria (Method) - Workpack closeout record
label | Material Test Frequency - Prior to sealing commencing
label | Target Criteria - All underlying layers meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - SE / CE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - PQE
label | Material Test Method Requirement - Bitumen Sprayer
label | Reference Documents - TNZ P3
label | Material Acceptance Criteria (Method) - Certification provided
label | Material Test Frequency - Prior to starting
label | Target Criteria - Current E/2 Certificate
label | Action Point Records Required - Certificate Sheet
label | Responsibility - SE / CE / PM / PQE
section | Chip Seal Application
checkpoint | 2.01 - PQE
label | Material Test Method Requirement - Seal Design
label | Reference Documents - INSERT SEAL DESIGN
label | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
label | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
label | Target Criteria - Meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - PQE / CE / PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Field
label | Material Test Method Requirement - GO/NO GO Survey
label | Reference Documents - Downer survay sealing Go/NO GO , road science Zeus app & Downer Iris app.
label | Material Acceptance Criteria (Method) - Downers Procedures
label | Material Test Frequency - prior to sealing on each site
label | Target Criteria - Pass on GO/NO GO , Marginal &discussion with contract manager or approval from Rehab manager
label | Action Point Records Required - Hold Point
label | Responsibility - PQE / CE / PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - PQE / CE / PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Field
label | Material Test Method Requirement - Pre-seal Inspection
label | Reference Documents - TNZ P3:1995.7
label | Material Acceptance Criteria (Method) - Downers Procedures
label | Material Test Frequency - 100% of Surface Prior to sealing
label | Target Criteria - The surface shall then be swept clean of loose aggregate, dust, dirt and other deleterious matter.
label | ○ Street Furniture and Start and End poitns have been taped and/or masked for overspray
label | ○ Line marking tags are in place.
label | Action Point Records Required - Hold Point
label | Responsibility - PQE / CE / PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Field
label | Material Test Method Requirement - Road temp
label | Reference Documents - TNZ P3:1995.18
label | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
label | Material Test Frequency - Once per day of sealing prior to sealing commencing
label | Target Criteria - Air temp >10°C
label | Action Point Records Required - Spray Sheet
label | Responsibility - SE / CE / PM
checkpoint | 2.06 - Field
label | Material Test Method Requirement - Application Rate
label | Reference Documents - TNZ P3 : 1995.18
label | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
label | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
label | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
label | Action Point Records Required - Spray Sheet
label | Responsibility - SE / CE / PM
checkpoint | 2.07 - Field
label | Material Test Method Requirement - Chip spread rate
label | Reference Documents - TNZ P3: 1995.21
label | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
label | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
label | Target Criteria - Visual checks meets seal design requirements
label | Action Point Records Required - Witness Point/Spray sheet
label | Responsibility - SE / CE / PM
checkpoint | 2.08 - Field
label | Material Test Method Requirement - Rolling Checks
label | Reference Documents - TNZ P3: 1995.22
label | Material Acceptance Criteria (Method) - Sealing Record
label | Material Test Frequency - for each sealing site per day
label | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
label | Action Point Records Required - Witness Point/Spray sheet
label | Responsibility - SE / CE / PM
checkpoint | 2.09 - Field
label | Material Test Method Requirement - Post-seal Inspection
label | Reference Documents - TNZ P3: 1995
label | Material Acceptance Criteria (Method) - Engineers Inspection
label | Material Test Frequency - 100% of Site After sealing (within 5 days)
label | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
label | ○ Line marking has been reinstated
label | ○ All excess chip has been removed from site
label | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
label | Action Point Records Required - Hold Point
label | Responsibility - SE / CE / PM / ER
holdpoint | AUTHORITY HOLDPOINT
section | Post Completion
checkpoint | 3.01 - Field
label | Material Test Method Requirement - Asbuilt and RAMM Data
label | Reference Documents - RAMM update sheet
label | Material Acceptance Criteria (Method) - See Asset Management Information Plan
label | Material Test Frequency - After works complete
label | Target Criteria - RAMM sheet 100% complete and accurate.
label | Action Point Records Required - RAMM Asset Update Sheet
label | Responsibility - PQE / CE / PM / ER