## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN | itp |  |  |  |  | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN Rev 1
section | Subgrade
checkpoint | 1.01 - Field
label | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
label | Reference Documents - RITS Table 3-20
label | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
label | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
label | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
label | Target Criteria - Confirm design assumptions - Scalar reaches minimum 7 blows/300mm
label | Action Point Records Required - Test Record
label | Responsibility - QA / SE / PE
checkpoint | 1.02 - Field
label | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
label | Reference Documents - RITS Table 3-21
label | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
label | Material Test Frequency - In centre of undercut or trench Minimum of 1 test per undercut location
label | Target Criteria - CIV ≥ 15 or CBR of 20
label | Action Point Records Required - Test Record
label | Responsibility - QA / SE / PE
checkpoint | 1.03 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24
label | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
label | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
label | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
label | Target Criteria - +0mm/-30m from design or nominated level
label | ○ No more than 15mm deviation from a 3m straight edge
label | Action Point Records Required - Survey record
label | Responsibility - QA / SE / PE
checkpoint | 1.04 - Field
label | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
label | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
label | Material Acceptance Criteria (Method) - Manufacturer installation instructions
label | Material Test Frequency - 100% of Surface
label | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
label | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
label | Action Point Records Required - Site Record
label | Responsibility - QA / SE / PE
checkpoint | 1.05 - PQE
label | Material Test Method Requirement - Is the layer closed out?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - 100% of Surface Prior to placement of material
label | Target Criteria - PQE Approval
label | ○ All testing record & reviewed as compliant.
label | Available Documents:
label | ○ Test records
label | ○ Survey records
label | ○ Hold Point Records
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
section | Subbase
checkpoint | 2.01 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing link
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Field
label | Material Test Method Requirement - Plateau Density Test
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
label | Target Criteria - N/A
label | Action Point Records Required - Hold Point, Test Record
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Field
label | Material Test Method Requirement - Clegg Hammer
label | Reference Documents - RITS Table 3-21
label | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
label | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
label | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
label | Target Criteria - CIV ≥ 25
label | Action Point Records Required - Test Record
label | Responsibility - QA / SE / PE
checkpoint | 2.04 - Field
label | Material Test Method Requirement - Compaction NDM Back Scatter
label | Reference Documents - RITS Table 3-22
label | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
label | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
label | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
label | Target Criteria - Mean ≥ 95 % MDD
label | ○ Minimum ≥ 92% MDD
label | Action Point Records Required - Test Record
label | Responsibility - QA / SE / PE
checkpoint | 2.05 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24
label | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
label | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
label | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
label | Target Criteria - +5mm/-25m from design or nominated level
label | ○ No more than 15mm deviation from a 3m straight edge
label | Action Point Records Required - Survey record
label | Responsibility - QA / SE / PE
checkpoint | 2.06 - PQE
label | Material Test Method Requirement - Is the layer closed out?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - 100% of Surface Prior to placement of material
label | Target Criteria - PQE Approval
label | ○ All testing record & reviewed as compliant.
label | Available Documents:
label | ○ Test records
label | ○ Survey records
label | ○ Hold Point Records
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
section | Membrane or First Coat Seal
checkpoint | 3.01 - PQE
label | Material Test Method Requirement - Seal Design
label | Reference Documents - INSERT SEAL DESIGN
label | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
label | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
label | Target Criteria - Meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE / ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02 - PQE
label | Material Test Method Requirement - Bitumen Sprayer
label | Reference Documents - TNZ P3
label | Material Acceptance Criteria (Method) - Certification provided
label | Material Test Frequency - Prior to starting
label | Target Criteria - Current E/2 Certificate
label | Action Point Records Required - Certificate Sheet
label | Responsibility - SE / PE / PM / PQE / Era
checkpoint | 3.03 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Field
label | Material Test Method Requirement - Preseal Inspection
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 100% of Surface Prior to sealing of surface
label | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
label | Action Point Records Required - Test Record
label | Responsibility - FM /QA / SE / PE
checkpoint | 3.05 - Field
label | Material Test Method Requirement - Degree of Saturaton
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
label | Target Criteria - < 80 % Completed Max 48hrs before sealing
label | Action Point Records Required - Test Record
label | Responsibility - QA / SE / PE
checkpoint | 3.06 - Field
label | Material Test Method Requirement - GO/NO GO Survey
label | Reference Documents - Downers processes
label | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
label | Material Test Frequency - Prior to sealing on each site
label | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
label | Action Point Records Required - Survey record
label | Responsibility - QA / SE / PE
checkpoint | 3.07 - Field
label | Material Test Method Requirement - Road temp
label | Reference Documents - TNZ P3:1995.18
label | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
label | Material Test Frequency - Once per day of sealing prior to sealing commencing
label | Target Criteria - Air temp >10°C
label | Action Point Records Required - Spray sheet
label | Responsibility - QA / SE / PE
checkpoint | 3.08 - Field
label | Material Test Method Requirement - Application Rate
label | Reference Documents - TNZ P/3 : 1995.18
label | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
label | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
label | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
label | Action Point Records Required - Spray Sheet
label | Responsibility - QA / SE / PE
checkpoint | 3.09 - Field
label | Material Test Method Requirement - Chip spread rate
label | Reference Documents - TNZ P3: 1995.21
label | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
label | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
label | Target Criteria - Visual checks meets seal design requirements
label | Action Point Records Required - Witness Point/Spray sheet
label | Responsibility - QA / SE / PE
checkpoint | 3.10 - Field
label | Material Test Method Requirement - Rolling Checks
label | Reference Documents - TNZ P3: 1995.22
label | Material Acceptance Criteria (Method) - Sealing Record
label | Material Test Frequency - for each sealing site per day
label | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
label | Action Point Records Required - Witness Point/Spray sheet
label | Responsibility - QA / SE / PE
checkpoint | 3.11 - Field
label | Material Test Method Requirement - Post Seal Inspection
label | Reference Documents - TNZ P3: 1995
label | Material Acceptance Criteria (Method) - Engineers Inspection
label | Material Test Frequency - After sealing
label | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
label | Action Point Records Required - Witness Point
label | Responsibility - QA / SE / PE
section | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
checkpoint | 4.01 - PQE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
label | Material Acceptance Criteria (Method) - Approved Treatment Design
label | Material Test Frequency - Prior to paving works commencing
label | Target Criteria - Treatment Design validation
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Lab
label | Material Test Method Requirement - In-situ mat density calibration cores
label | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
label | Material Acceptance Criteria (Method) - ASTM D5361
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Characteristic value - mix design air void +3% -2%
label | Action Point Records Required - Hold Point
label | Responsibility - SE / PE / PM / PQE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Lab
label | Material Test Method Requirement - Grading (Particle Size Distribution)
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Tolerance from nominated JMF grading as per
label | ○ NZTA M10 Table 5.3
label | ○ NZTA M27 Table 5.3
label | ○ TNZ P/11 Table 7.1
label | Action Point Records Required - Test record
label | Responsibility - SE / PE / PM / PQE
checkpoint | 4.04 - Lab
label | Material Test Method Requirement - Binder content
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D2172
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Tolerance on JMF
label | ○ Individual ±0.5 (All)
label | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
label | ○ Rolling Average of 3 ±0.4% (PA)
label | Action Point Records Required - Test record
label | Responsibility - SE / PE / PM / PQE
checkpoint | 4.05 - Lab
label | Material Test Method Requirement - Air Voids
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D3203-22
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - As specified for each mix type
label | Action Point Records Required - Test record
label | Responsibility - SE / PE / PM / PQE
checkpoint | 4.06 - Lab
label | Material Test Method Requirement - Maximum Theoretical Specific Gravity
label | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
label | Material Acceptance Criteria (Method) - ASTM D2041
label | Material Test Frequency - One test per 900 t of asphalt plant production
label | Target Criteria - Report Value
label | Action Point Records Required - Test record
label | Responsibility - SE / PE / PM / PQE
checkpoint | 4.07 - Field
label | Material Test Method Requirement - Load Locate
label | Reference Documents - Downer Procedures
label | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
label | – Truck ID/Rego/Driver
label | – Depart Plant Time
label | – Arrive Site Time
label | – AC Temp on Arrival
label | – Ground Temp on Arrival
label | – Tonnage
label | – Run Width
label | – Estimated Run Length
label | – Calculated Area
label | – Calculated Average Depth
label | Material Test Frequency - Every Load
label | Target Criteria - All data is collected
label | Action Point Records Required - QA Sheet
label | Responsibility - QA / SE / PE
checkpoint | 4.08 - Field
label | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
label | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
label | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
label | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
label | ○ 1 test per 100m per layer length (min 3 / Construction lot)
label | Target Criteria - Mat: Mean air voids JMF +3,-2
label | ○ Join: Mean air voids JMF +5,-2
label | Action Point Records Required - Test record
label | Responsibility - QA / SE / PE
checkpoint | 4.09 - Field
label | Material Test Method Requirement - Surface Level- Stringline checks for validation
label | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2 Downer Procedures
label | Material Acceptance Criteria (Method) - NZTA M/10
label | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
label | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
label | Target Criteria - +15mm/-5mm from design or nominated level
label | ○ No more than 8mm deviaton from a 3m straight edge
label | Action Point Records Required - Survey record
label | Responsibility - QA / SE / PE
checkpoint | 4.10 - Field
label | Material Test Method Requirement - Post Surfacing Inspection
label | Reference Documents - CCA Procedures
label | Material Acceptance Criteria (Method) - Contract Specifications
label | Material Test Frequency - 100% of site After surfacing (within 5 days)
label | Target Criteria - Line marking has been reinstated
label | ○ All excess material has been removed from site
label | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
label | Action Point Records Required - Hold Point
label | Responsibility - QA / SE / PE
holdpoint | AUTHORITY HOLDPOINT
section | Post Construction
checkpoint | 5.01 - PQE
label | Material Test Method Requirement - Asbuilt and RAMM Data
label | Reference Documents - RAMM Update sheet
label | Material Acceptance Criteria (Method) - Asset Management Information Plan
label | Material Test Frequency - After works complete
label | Target Criteria - RAMM sheet 100% complete and accurate .
label | Action Point Records Required - RAMM Asset Update sheet
label | Responsibility - site engineer / Project Engineer/PQE
checkpoint | 5.02 - Lab
label | Material Test Method Requirement - High speed Rutting & NAASRA - Road Roughness
label | Reference Documents - CCA DOC
label | Material Acceptance Criteria (Method) - Laser Profilometer Survey
label | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
label | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
label | Target Criteria - High Speed Rutting: > 5mm Report to Designer
label | ○ NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value
label | Action Point Records Required - Test Record
label | Responsibility - site engineer / Project Engineer/PQE