## Seal Construction ITP (hidden)
REHAB SEALING INSPECTION TESTING PLAN
Item No | Material Type | Typical Use | Item ID | PQE, Supplier or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | LINK |  |  | NOTES
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptiance Criteria (Method) | Material Test Frequency* | Target Criteria |  | Action Point | Responsibility
1 | Preliminaries | Compliance | 1.01 | PQE | Has the underlying layer been tested and results accepted | Insert Layer Acceptance ITP No | Workpack closeout record | Prior to sealing commencing | All underlying layers meets project requirements |  | Hold Point | PQE
|  |  | 1.02 | PQE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate | Site Engineer/Project Engineer
2 | Membrane Application | For Compliance | 2.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | Site Engineer/PQE/Project Engineer
|  |  | 2.02 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PQE
|  |  | 2.04 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | Site Engineer/Project Engineer
|  |  | 2.05 | Field | Application Rate | TNZ P4 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray sheet
3 | Chip Seal Application | For Compliance | 3.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | Site Engineer/Project Engineer
|  |  | 3.02 |  | GO/NO GO Survey | Downer survay sealing Go/NO GO , road science Zeus app & Downer Iris app. | Pass on GO/NO GO , Marginal &discussion with contract manager or approval from Rehab manager | prior to sealing on each site |  |  | Hold Point | Site Engineer/Project Engineer
|  |  | 3.03 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PQE
|  | On Site Testing | 3.04 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray Sheet | Site Engineer/Project Engineer
|  |  | 3.05 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet
|  |  | 3.06 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet
|  |  | 3.07 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet
|  |  | 3.08 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Inspection Sheet | Site Engineer/PQE/Project Engineer
4 | Post Completion |  | 4.01 | Field | Asbuilt and RAMM Data | RAMM update sheet | See Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update Sheet | Site Engineer/Project Engineer

## SAC Rehab ITP
| Site Name | Pine ave | [6 empty] | Development Date:
| Carriageway width (m) | 8 |  |  | Target CBR value for subgrade | 3 |  |  | Role | Name |  | Acronym
| Surfacing Type | Chipseal |  |  | Scala - Minimum blows per 100mm | n/a |  |  | Foreman |  |  | FM
| Kerb and Channel | Yes |  |  | Scala - Minimum blows per 300mm | 7 |  |  | Quality Technician |  |  | QA
| ESA (Million ESA) | 0.44 |  |  | Clegg - Minimum CIV value | n/a |  |  | Site Engineer |  |  | SE
|  | From design report |  |  | Material used for Subbase | WHAP65 |  |  | Site Supervisor |  |  | SS
| Does design align with RITs standards | No |  |  | Target MDD value for subbase |  |  |  | Project Engineer |  |  | PE
| Theoretical max deflection on Basecourse (mm) | 1.83 |  |  | Material used for Basecourse | TNZ AP40 |  |  | Project Manager |  |  | PM
[5 empty] | Target MDD value for basecourse |  |  |  | Pavement Quality Engineer |  |  | PQE
[9 empty] | Engineers Representative |  |  | ER
STRUCTURAL REHAB INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Subgrade |  | 1.01 | Field | Scala Penetrometer Cohesive soils only | RITS Table 3-20 | NZS 4402.6.5.2:1988 | 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Confirm design assumptions - Scalar reaches minimum 7 blows/300mm |  | Test Record | QA / SE / PE
|  |  | 1.02 | Field | Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | In centre of undercut or trench Minimum of 1 test per undercut location | CIV ≥ 15 or CBR of 20 |  | Test Record | QA / SE / PE
|  |  | 1.03 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 1.04 | Field | Tenser Triaxial Geogrid and Geofabric (cloth) installation | Tensar construction sequence CS_TriAx/30.04.08 | Manufracture installation instructions | 100% of Surface | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. |  | Site Record | QA / SE / PE
|  | Compliance | 1.05 | PQE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | SE / PE / PM / PQE
2 | Subbase | Compliance | 2.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  |  | 2.02 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | N/A |  | Hold Point Test Record | SE / PE / PM / PQE
|  |  | 2.03 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | CIV ≥ 25 |  | Test Record | QA / SE / PE
|  |  | 2.04 | Field | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 95 % MDD Minimum ≥ 92% MDD |  | Test Record | QA / SE / PE
|  |  | 2.05 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  | Compliance | 2.06 | PQE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | SE / PE / PM / PQE
3 | Membrane or First Coat Seal | Compliance | 3.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | SE / PE / PM / PQE / ER
|  | Compliance | 3.02 | PQE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | SE / PE / PM / PQE / ER
|  | Compliance | 3.03 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  |  | 3.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | FM /QA / SE / PE
|  |  | 3.05 | Field | Degree of Saturaton | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 set of 5 per 1000m² - then 1 per 200m² | < 80 % Completed Max 48hrs before sealing |  | Test Record | QA / SE / PE
|  |  | 3.06 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  | Survey record | QA / SE / PE
|  |  | 3.07 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | QA / SE / PE
|  |  | 3.08 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE / PE
|  |  | 3.09 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | QA / SE / PE
|  |  | 3.1 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | QA / SE / PE
|  |  | 3.11 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | QA / SE / PE
4 | DG and AC Mixes NZTA M10:2020 SMA Mixes NZTA M27:2020 PA Mixes TNZ P/11 | Compliance | 4.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation |  | Hold Point | SE / PE / PM / PQE
|  | Production Testing and Cores | 4.02 | Lab | In-situ mat density calibration cores | NZTA M10:2020 9.9.1 NZTA M27:2020 9.9.1 | ASTM D5361 | One test per 900 t of asphalt plant production | Characteristic value - mix design air void +3% -2% |  | Hold Point | SE / PE / PM / PQE
|  |  | 4.03 | Lab | Grading (Particle Size Distribution) | NZTA M10: 2020 Table 5.2 NZTA M27:2020 Table 5.2 TNZ P/11:2007 Table 7.1 | NZS 4407:2015 test 3.8 |  | Tolerance from nominated JMF grading as per NZTA M10 Table 5.3 NZTA M27 Table 5.3 TNZ P/11 Table 7.1 |  | Test record | SE / PE / PM / PQE
|  |  | 4.04 | Lab | Binder content |  | ASTM D2172 |  | Tolerance on JMF Individual ±0.5 (All) Rolling Average of 3 ±0.3% (DG, AC, SMA) Rolling Average of 3 ±0.4% (PA) |  |  | SE / PE / PM / PQE
|  |  | 4.05 | Lab | Air Voids |  | ASTM D3203-22 |  | As specified for each mix type |  |  | SE / PE / PM / PQE
|  |  | 4.06 | Lab | Maximum Theoratical Specific Gravity |  | ASTM D2041 |  | Report Value |  |  | SE / PE / PM / PQE
|  |  | 4.07 | Field | Load Locate | Downer Procedures | Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Every Load | All data is collected |  | QA Sheet | QA / SE / PE
|  |  | 4.08 | Field | NDM Density Testing On-Site Mat and Joint | NZTA M10:2020 9.9.1 and 9.9.2 NZTA M27:2020 9.9.1 and 9.9.2 | ASTM D2950 ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 |  | Test record | QA / SE / PE
|  |  | 4.09 | Field | Surface Level- Stringline checks for validation | NZTA M10:2020 10.2 NZTA M27: 2020 10.2 Downer Procedures | NZTA M/10 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +15mm/-5mm from design or nominated level No more than 8mm deviaton from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 4.1 | Field | Post Surfacing Inspection | CCA Procedures | Contract Specifications | 100% of site After surfacing (within 5 days) | Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers |  | Hold Point | QA / SE / PE
5 | Post Construction | Compliance | 5.01 | PQE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | site engineer / Project Engineer/PQE
|  | Compliance | 5.02 | Lab | High speed Rutting & NAASRA - Road Roughness | CCA DOC | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths | High Speed Rutting: > 5mm Report to Designer NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value |  | Test Record | site engineer / Project Engineer/PQE

## Rehab ITP
| Site Name | Pine ave | [6 empty] | Development Date:
| Carriageway width (m) | 8 |  |  | Target CBR value for subgrade | 3 |  |  | Role | Name |  | Acronym
| Surfacing Type | Chipseal |  |  | Scala - Minimum blows per 100mm | n/a |  |  | Foreman |  |  | FM
| Kerb and Channel | Yes |  |  | Scala - Minimum blows per 300mm | 7 |  |  | Quality Technician |  |  | QA
| ESA (Million ESA) | 0.44 |  |  | Clegg - Minimum CIV value | n/a |  |  | Site Engineer |  |  | SE
|  | From design report |  |  | Material used for Subbase | WHAP65 |  |  | Site Supervisor |  |  | SS
| Does design align with RITs standards | No |  |  | Target MDD value for subbase |  | from lab report |  | Project Engineer |  |  | PE
| Theoretical max deflection on Basecourse (mm) | 1.83 |  |  | Material used for Basecourse | TNZ AP40 |  |  | Project Manager |  |  | PM
[5 empty] | Target MDD value for basecourse |  | from lab report |  | Pavement Quality Engineer |  |  | PQE
[9 empty] | Engineers Representative |  |  | ER
GRANULAR REHAB INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Subgrade |  | 1.01 | Field | Scala Penetrometer Cohesive soils only | RITS Table 3-20 | NZS 4402.6.5.2:1988 | 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Confirm design assumptions - Scalar reaches minimum 7 blows/300mm |  | Test Record | QA / SE / PE
|  |  | 1.02 | Field | Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | In centre of undercut or trench Minimum of 1 test per undercut location | CIV ≥ 15 or CBR of 20 |  | Test Record | QA / SE / PE
|  |  | 1.03 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 1.04 | Field | Tenser Triaxial Geogrid and Geofabric (cloth) installation | Tensar construction sequence CS_TriAx/30.04.08 | Manufracture installation instructions | 100% of Surface | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. |  | Site Record | QA / SE / PE
|  | Compliance | 1.05 | PQE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | SE / PE / PM / PQE
2 | Subbase | Compliance | 2.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  |  | 2.02 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | N/A |  | Hold Point Test Record | SE / PE / PM / PQE
|  |  | 2.03 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | CIV ≥ 25 |  | Test Record | QA / SE / PE
|  |  | 2.04 | Field | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 95 % MDD Minimum ≥ 92% MDD |  | Test Record | QA / SE / PE
|  |  | 2.05 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  | Compliance | 2.06 | PQE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | SE / PE / PM / PQE
3 | Basecourse | Compliance | 3.01 | PQE | Has the material used in this layer been formally accepted for use? | See PQE | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  | Stabilisation Delete if Not Required | 3.02 | Field | Cement application Mat test | TNZ B/5:2008 | TNZ B/5:2008 | 1 test per 400m² (minimum 1 per run) | ±0.50kg/m² of specified rate |  | Stabilisation QA sheet | QA / SE / PE
|  | Stabilisation Delete if Not Required | 3.03 | Field | Stabilisation Depth | TNZ B/5:2008 | TNZ B/5:2008 | 2 test per 400m² (minimum 1 per run) | Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer |  | Stabilisation QA sheet | QA / SE / PE
|  |  | 3.04 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per site | N/A |  | Test Record | SE / PE / PM / PQE
|  |  | 3.05 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | CIV ≥ 40 |  | Test Record | QA / SE / PE
|  |  | 3.06 | Lab | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 98 % MDD Minimum ≥ 95% MDD |  | Test Record | QA / SE / PE
|  |  | 3.07 | Lab | Benkelmen Beam Deflection Testing | RITS Table 3-23 | RITS 3.8.3.5 ASTM D5874-16 | 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Max deflection allowed: 1.83mm From design report - due to non-RITs compliant Subgrade CBR |  | Test Record | QA / SE / PE
|  |  | 3.08 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +10mm/-0mm from design or nominated level No more than 12mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 3.09 | Field | Visual Inspection of Basecourse Surface | TNZ B/02: 2005 7.8 | TNZ B/02: 2005 7.8 | 100% of Surface Prior to sealing of surface | Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface) |  | Hold Point | SE / PE / PM / PQE / ER
|  | Compliance | 3.1 | PQE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to sealing of surface | Engineers Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | SE / PE / PM / PQE / ER
4 | Membrane or First Coat Seal | Compliance |  | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | SE / PE / PM / PQE / ER
|  | Compliance |  | PQE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | SE / PE / PM / PQE / ER
|  | Compliance |  | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  |  |  | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | FM /QA / SE / PE
|  |  |  | Field | Degree of Saturaton | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 set of 5 per 1000m² - then 1 per 200m² | < 80 % Completed Max 48hrs before sealing |  | Test Record | QA / SE / PE
|  |  |  | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  | Survey record | QA / SE / PE
|  |  |  | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | QA / SE / PE
|  |  |  | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE / PE
|  |  |  | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | QA / SE / PE
|  |  |  | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | QA / SE / PE
|  |  |  | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose Line marking has been reinstated All excess chip has been removed from site All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers. |  | Hold Point | QA / SE / PE
5 | Post Construction | Compliance | 5.01 | PQE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | site engineer / Project Engineer/PQE
|  | Compliance | 5.02 | Lab | High speed Rutting & NAASRA - Road Roughness | CCA DOC | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths | High Speed Rutting: > 5mm Report to Designer NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value |  | Test Record | site engineer / Project Engineer/PQE

## Asphalt ITP
| Site Name | Pine ave | [6 empty] | Development Date:
| Carriageway width (m) | 8 |  |  | Surface pre-treatment type |  |  |  | Role | Name |  | Acronym
| Surfacing Type | AC |  |  | Milling depth |  |  |  | Foreman |  |  | FM
| Kerb and Channel | Yes |  |  | Target area |  |  |  | Quality Technician |  |  | QA
| Target area |  |  |  | Target tonnage |  |  |  | Site Engineer |  |  | SE
| Layer depth minimum thickness | [7 empty] | Site Supervisor |  |  | SS
| Mean Profile Thickness | [7 empty] | Project Engineer |  |  | PE
| Mix specific density | [7 empty] | Project Manager |  |  | PM
| JMF Air void target | [7 empty] | Pavement Quality Engineer |  |  | PQE
[9 empty] | Engineers Representative |  |  | ER
ASPHALT SURFACE RENEWAL INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Milling |  | 1.01 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 NZTA M10:2020 10.1 | String line or GPS rover | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +10mm/-0mm from design or nominated level No more than 8mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 1.02 | Field | Surface Inspection | NZTA M10:2020 9.2 | Visual Inspection | 100% of Surface Prior to paving | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. |  | Hold Point | QA / SE / PE
|  |  | 1.03 | Field | Does the surface pre-treatment meet project requirments? | NZTA M27:2020 9.3 NZTA M10:2020 9.2 NZTA SP-M-032 | Design requirements Visual confirmation after milling NZTA SP-M-032: Step 4 Bond and Seal | 100% of Surface Prior to paving | Is the suggested surface pre-treatment still suitable after inspectiing the milled surface? |  | Hold Point | SE / PE / PM / PQE / ER
2 | Surface pre-treatment Membrane or Chipseal | Compliance | 2.01 | PQE | Seal Design | NZTA M27:2020 9.3 NZTA M10:2020 9.2 NZTA SP-M-032 | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | SE / PE / PM / PQE / ER
|  | Compliance | 2.02 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | SE / PE / PM / PQE
|  |  | 2.03 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | FM /QA / SE / PE
|  |  | 2.04 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | QA / SE / PE
|  |  | 2.05 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE / PE
|  |  | 2.06 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | QA / SE / PE
|  |  | 2.07 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | QA / SE / PE
3 | DG and AC Mixes NZTA M10:2020 SMA Mixes NZTA M27:2020 PA Mixes TNZ P/11 | Compliance | 3.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines | Approved Treatment Design | Prior to paving works commencing | Treatment Design validation |  | Hold Point | SE / PE / PM / PQE
|  | Production Testing and Cores | 3.02 | Lab | In-situ mat density calibration cores | NZTA M10:2020 9.9.1 NZTA M27:2020 9.9.1 | ASTM D5361 | One test per 900 t of asphalt plant production | Characteristic value - mix design air void +3% -2% |  | Hold Point | SE / PE / PM / PQE
|  |  | 3.03 | Lab | Grading (Particle Size Distribution) | NZTA M10: 2020 Table 5.2 NZTA M27:2020 Table 5.2 TNZ P/11:2007 Table 7.1 | NZS 4407:2015 test 3.8 |  | Tolerance from nominated JMF grading as per NZTA M10 Table 5.3 NZTA M27 Table 5.3 TNZ P/11 Table 7.1 |  | Test record | SE / PE / PM / PQE
|  |  | 3.04 | Lab | Binder content |  | ASTM D2172 |  | Tolerance on JMF Individual ±0.5 (All) Rolling Average of 3 ±0.3% (DG, AC, SMA) Rolling Average of 3 ±0.4% (PA) |  |  | SE / PE / PM / PQE
|  |  | 3.05 | Lab | Air Voids |  | ASTM D3203-22 |  | As specified for each mix type |  |  | SE / PE / PM / PQE
|  |  | 3.06 | Lab | Maximum Theoratical Specific Gravity |  | ASTM D2041 |  | Report Value |  |  | SE / PE / PM / PQE
|  |  | 3.07 | Field | Load Locate | Downer Procedures | Each load can be indentified to a location. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Every Load | All data is collected |  | QA Sheet | QA / SE / PE
|  |  | 3.08 | Field | NDM Density Testing On-Site Mat and Joint | NZTA M10:2020 9.9.1 and 9.9.2 NZTA M27:2020 9.9.1 and 9.9.2 | ASTM D2950 ASTM D5361 | 1 test per 300m² per layer (Min 8 / Construction lot) 1 test per 100m per layer length (min 3 / Construction lot) | Mat: Mean air voids JMF +3,-2 Join: Mean air voids JMF +5,-2 |  | Test record | QA / SE / PE
|  |  | 3.09 | Field | Surface Level- Stringline checks for validation | NZTA M10:2020 10.2 NZTA M27: 2020 10.2 Downer Procedures | NZTA M/10 | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal | +10mm/-0mm from design or nominated level No more than 8mm deviation from a 3m straight edge |  | Survey record | QA / SE / PE
|  |  | 3.1 | Field | Post Surfacing Inspection | CCA Procedures | Contract Specifications | 100% of site After surfacing (within 5 days) | Line marking has been reinstated All excess material has been removed from site All CPs are clear from filter fabric and any excess material removed from on top service covers |  | Hold Point | QA / SE / PE
4 | Post Construction | Compliance | 4.01 | PQE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | SE / PE / PM / PQE
|  | Compliance | 4.02 | Lab | High speed Rutting & NAASRA - Road Roughness | CCA DOC | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths | High Speed Rutting: > 5mm Report to Designer NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value |  | Test Record | SE / PE / PM / PQE

## Chipseal Renewal ITP
| Site Name | [7 empty] | Development Date:
| Carriageway width (m) | 8 |  |  | Binder (Emulsion or Cut Back) |  |  |  | Role | Name |  | Acronym
| Treatment area length (m) |  |  |  | PMB (Yes/No) |  |  |  | Foreman |  |  | FM
| Treatment area (m²) |  |  |  | Hot spread rate |  |  |  | Quality Technician |  |  | QA
| Treatment |  |  |  | Estimated Binder qty | 0 | ltr |  | Site Engineer |  |  | SE
[5 empty] | Chip source |  | Quarry Name |  | Site Supervisor |  |  | SS
| Fabric (Yes/No) |  |  |  | Chip spread rate |  | m²/t |  | Contract Engineer |  |  | CE
[5 empty] | Estimated Chip Qty | 0 | t |  | Project Manager |  |  | PM
[9 empty] | Pavement Quality Engineer |  |  | PQE
[9 empty] | Engineers Representative |  |  | ER
CHIPSEAL RENEWAL INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Preliminaries | Compliance | 1.01 | PQE | Has all preseal repairs been completed? | Insert Layer Acceptance ITP No | Workpack closeout record | Prior to sealing commencing | All underlying layers meets project requirements |  | Hold Point | SE / CE / PM / PQE
|  |  | 1.02 | PQE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | SE / CE / PM / PQE
2 | Chip Seal Application | For Compliance | 2.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | PQE / CE / PM
|  |  | 2.02 | Field | GO/NO GO Survey | Downer survay sealing Go/NO GO , road science Zeus app & Downer Iris app. | Downers Procedures | prior to sealing on each site | Pass on GO/NO GO , Marginal &discussion with contract manager or approval from Rehab manager |  | Hold Point | PQE / CE / PM
|  |  | 2.03 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PQE / CE / PM
|  | On Site Testing | 2.04 | Field | Pre-seal Inspection | TNZ P3:1995.7 | Downers Procedures | 100% of Surface Prior to sealing | The surface shall then be swept clean of loose aggregate, dust, dirt and other deleterious matter. Street Furniture and Start and End poitns have been taped and/or masked for overspray Line marking tags are in place. |  | Hold Point | PQE / CE / PM
|  |  | 2.05 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray Sheet | SE / CE / PM
|  |  | 2.06 | Field | Application Rate | TNZ P3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | SE / CE / PM
|  |  | 2.07 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | SE / CE / PM
|  |  | 2.08 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | SE / CE / PM
|  |  | 2.09 | Field | Post-seal Inspection | TNZ P3: 1995 | Engineers Inspection | 100% of Site After sealing (within 5 days) | The chip is embedded, uniformily placed and chipseal is fit for purpose Line marking has been reinstated All excess chip has been removed from site All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers. |  | Hold Point | SE / CE / PM / ER
3 | Post Completion |  | 3.01 | Field | Asbuilt and RAMM Data | RAMM update sheet | See Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update Sheet | PQE / CE / PM / ER

## Seal Material Acceptance ITP (hidden)
WPK# : |  | INSPECTION AND TEST PLAN TEMPLATE - Sealing
Item No | Material Type | Typical Use | Item ID | For Information or Compliance | Material Properties Required for Acceptability for Permanent Works | [5 empty] | Check |  |  | Completed/Checked | NOTES
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptiance Criteria (Method) | Material Test Frequency* |  | Target Criteria |  | Action Point | Responsibility
1 | Binder | Binder Testing | 1.01 | For Compliance | Bitumen used to manufacture binder | Specification C0213.3.2 Specification C0213.3.3 Specification CO213.3.4 | TNZ M/1 Table 1 Tests | Once initially then as directed by the Designer |  | Meets project requirements |  | Test Report | Sealing PE
|  |  | 1.02 |  | Blended binder |  | Testing to be nominated by manufacturer | Repeat as per manufacturer's requirements |  | Meets project requirements |  | Test Report | Sealing PE
|  |  | 1.03 |  | Bituminous binder test results | Specification C0213.3.3 | TNZ M/1 Table 1 Tests shall be submitted to the Designer | Prior to sealing commencing (Minimum 1 week prior to application) |  | Meets project requirements |  | Hold Point | CPS
|  |  | 1.04 |  | Polymer additive | Specification C0213.3.5 | Full technical details and specification shall submitted to Designer for approval | Prior to sealing commencing (Minimum 1 week prior to application) |  | Meets project requirements |  | Hold Point | CPS
2 | Sealing Chip | Sealing Chip Source Testing | 2.01 | For Compliance | Crushing Resistance | Specification C0213.3.1 TNZ M6:2011 Clause 3.2 | NZS 4407: Test 3.10 | Three initially per grade of chip from Quarry stockpile then repeat once per 10,000m 3 used or per annum, whichever is lesser |  | Not more than 10% fines at 230kN |  | Test Report | Sealing PE
|  |  | 2.02 |  | Weathering Quality Index | Specification C0213.3.1 TNZ M6:2011 Clause 3.3 | NZS 4407: Test 3.11 |  |  | AA or BA |  | Test Report | Sealing PE
|  |  | 2.03 |  | Weak Particles Test | Specification C0213.3.1 TNZ M6:2011 Clause 3.4 | AS 1141.32 The Weak Particles Test |  |  | Max. 1% unsound particles |  | Test Report | Sealing PE
|  |  | 2.04 |  | Polished Stone Value (for wearing course only) | Specification C0213.3.1 TNZ M6:2011 Clause 3.5 | BS EN 1097 Part 8 |  |  | Not required : Refer to RFI-003648 |  | N/A | N/A
|  |  | 2.05 |  | Sealing chip - Source property test results | Specification C0213.3.2 | Approved Material Acceptance | Prior to sealing commencing (Minimum 1 week prior to application) |  | Material meets project requirements |  | Hold Point | CPS
|  | Sealing Chip Production Testing | 2.06 | For Compliance | Cleanness Value for Grade 2, Grade 3 & Grade 4 | Specification C0213.3.1 TNZ M6:2011 Clause 4.1.1 | NZS 4407 : Test 3.9 | Three initially per grade of chip from Quarry stockpile then repeat as follows: 1 test per < 100m3 2 test per 100-500m3 or 3 test per >500m3 |  | Grade 3 : 87 Minimum Grade 4 : 85 Minimum |  | Test Report | Sealing PE
|  |  | 2.07 |  | Size and Shape for Grade 2, Grade 3 & Grade 4 | Specification C0213.3.1 TNZ M6:2011 Clause 4.1.2 | NZS 4407 : Test 3.13 The Size & Shape of Aggregate |  |  | TNZ M6 : Table 3 |  | Test Report | Sealing PE
|  |  | 2.08 |  | Cleanness Value for Grade 5 & Grade 6 | Specification C0213.3.1 TNZ M6:2011 Clause 4.2.3 | NZS 4407 : Test 3.9 | Three initially and repeat once per 500m3 used |  | Grade 5 : Report Only Grade 6 : Report Only |  | Test Report | Sealing PE
|  |  | 2.09 |  | Particle Size Distribution for Grade 5 & Grade 6 | Specification C0213.3.1 TNZ M6:2011 Clause 4.2.2 | NZS 4407: Test 3.8.2 |  |  | TNZ M6 : Table 4 |  | Test Report | Sealing PE
3 | Chipseal | Seal Design | 3.01 | For Compliance | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) |  | Meets project requirements |  | Hold Point | CPS
|  |  | 3.02 |  | Bitumen Sprayer | TNZ P3 | Certification | Prior to starting |  | Current E/2 Certificate |  | Record | Sealing PE
|  |  | 3.03 |  | Construction Trial Chip Bedding In | Specification C0213.3.4 | Trial design seal coats shall be undertaken to vertify constructability of seal layers and to confirm a rolling strategy to be adopted for each chipseal layer | Prior to sealing commencing |  | Meets project requirements |  | Hold Point | CPS
4 | Construction | For Compliance | 4.01 | Field | Has the underlying layer been tested and results accepted | Insert Layer Acceptance ITP No |  | Prior to sealing commencing |  | All underlying layers meets project requirements |  | Hold Point | CPS
|  |  | 4.02 |  | Degree of Saturation (DOS) | TNZ B/2: 2005 Clause 12 RFI-003243 |  | 1 set of 5 per 1,000m2 then 1 per 200m2 |  | < 60% completed a maximum 48 hours before application of prime coat |  | Hold Point | Pavement PE (Hi-lab)
|  |  | 4.03 |  | Joint Preseal Inspection |  | Has the prime coat cured and surface ready to seal | Prior to sealing commencing |  | Surface is ready to seal |  | Hold Point | CPS
|  | On Site Testing | 4.04 |  | Application Rate | Specification C0213.5.3 | Sealing Record | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling |  | As per approved seal design |  | Spray sheet | Sealing PE
|  |  | 4.05 |  | Chip spread rate | Specification C0213.5.4 TNZ P3: 1995 | Chipsealing in New Zealand | 1 test per Grade of Chip per 2,000m2 |  | As per Chipping guide |  | Visual | Sealing PE
|  |  | 4.06 |  | Rolling Checks | Specification CO213.5.4 TNZ P3: 1995 | Approved Methodology | Per site |  | Sufficient rolling to be carried out in accordance with Construction Trial and Rolling methodology |  | Record | Sealing PE
|  |  | 4.07 |  | NAASRA - Road Roughness (Wearing Course only) | Specifcation CO213.5.6 | Laser Profilometer Survey | All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths |  | Shall not exceed 70 counts/km as a 95th percentile value |  | Record | Sealing PE
|  |  | 4.08 |  | High speed Rutting & NAASRA - Road Roughness | Specification CO213.5.6 & CO213.5.7 | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths |  | High Speed Rutting: > 5mm Report to Designer NAASRA reading: For information |  | Record | Sealing PE
|  |  | 4.09 |  | Post Seal Inspection | Specification CO213.5.4 TNZ P3: 1995 | Engineers Inspection | After sealing |  | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Record | Sealing PE
Completed By |  |  |  |  | Reviewed By | [8 empty] | Template Revision | Date
Job Position: Pavement Quality Engineer |  |  |  |  | Job Description: |  |  |  | This ITP has been created using the Project Specific Specifications as referenced above.
[9 empty] | The Aconex reference for this document is WEXHS-24PG-ITP-CP-00024 |  |  |  |  | 2
Name and surname: Suraj lamichhane |  |  |  |  | Name and Surname: |  |  |  | Any site specific additions to this ITP will be added in the appropriate section and reapproved
[14 empty] | 1 | 2020-06-05
Signature: |  |  |  |  | Signature:
A
Date: 22/07/2019 |  |  |  |  | Date: