## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP - Basecourse |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
0 | Draft for Approval | 2022-12-22 |  | Gabriel Cirne |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Reviewed | 2023-07-13 |  | Emil |  | Comments by BBO |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
[10 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement & Surfacing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By | Comments
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
2.01 | Basecourse aggregate
2.01.01 | Basecourse CBR | (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and; (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%. | TNZ M/4: 2006 | IANZ Lab Reports | 10,000m3 | HP | ENG
2.01.02 | Running Course Material Approval | The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter. The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED) | TNZ B/02: 2005 - 10.2 | IANZ Lab Reports | 1 test every stockpile | HP | ENG
2.01.03 | Basecourse MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer. | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 1 test per material type | H | PE | Items included, subdivision from item "Sub-base Production Property Test Sampling"
2.01.04 | Crushing Resistance | The crushing resistance shall not be less than 130kN when the aggregate is tested | NZS 4407: 1991 Test 3.10. | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
2.01.05 | Weathering Resistance | The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested | NZS 4407: 1991 Test 3.11 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
2.01.06 | Particle Size Distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006. | TNZ M/4: 2006 | IANZ Lab Reports | 0 to 400m³ - 2 tests 400 to 1,500m³ - 3 tests 1,500 to 4,000m³ - 4 tests >4,000m³ - 1 test for each additional 1,000m³ | HP | ENG
2.01.07 | Sand Equivalent | The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test. If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above). The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6 | TNZ M/4: 2006, 4.2.1.1 | IANZ Lab Reports |  | HP | ENG
2.01.08 | Liquid Limit | The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2. | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.09 | Plasticity Index | The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4 | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.10 | Clay Index | The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5. | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.11 | Accelerated Weathering Testing | If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis The levels of smectite clay minerals are not classified as “abundant” | In accordance with NZTA Standard Specification T20 Draft Specification | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
2.01.12 | Repeat Load Triaxial Test | In accordance with NZTA T15 | NZTA T15 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
2.01.13 | Broken Face Content | The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407 : 1991, Test 3.14 Broken Face Test. | TNZ M/4: 2006, 4.2.2 | IANZ Lab Reports | 1 Test per Source | HP | ENG