## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP - Subbase |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval | 2023-04-04 |  | Gabriel |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2023-04-18 |  | Emil |  | Review A reviewed by the BBO engineer, some changes were made and resent for approval. DN1205-BBO-GCO-0051 (14/04/2023) |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
C | Draft for Approval | 2023-05-01 |  | Emil |  | Review B reviewed by the BBO engineer, some changes were made and resent for approval. DN1205-BBO-GCO-0055 (26/04/2023) |  |  |  | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Sub-base
Pavement & Surfacing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
5.01 | General Materials
5.01.01 | Sampling and testing | For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site. | PS - 7.2.4 | IANZ Lab Reports | five working days prior to delivery of the material to site. | HP | ENG
5.01.02 | Sampling and testing | Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer. Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use. The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.” Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply. | NZTA B/6 item 5 | Lab reports | Prior to Works start, per source | HP | ENG
5.02 | Sub-base aggregate
5.02.01 | Sub-base MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 1 test per material type | H | PE
5.02.02 | Cement for sub-base stabilisation | Cement for stabilisation shall meet the requirements of NZTA B6. | PS - 7.3.2 PS - 7.2.6 | Datasheets | Prior to Use | H | PE
5.02.05 | Crushing Resistance | The crushing resistance shall not be less than 130kN when the aggregate is tested | NZS 4407: 1991 Test 3.10. | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
5.02.06 | Weathering Resistance | The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested | NZS 4407: 1991 Test 3.11 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
5.02.07 | Particle size distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. | NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving | IANZ Lab Reports | 0 to 400m³ - 2 tests 400 to 1,500m³ - 3 tests 1,500 to 4,000m³ - 4 tests >4,000m³ - 1 test for each additional 1,000m³ | HP | ENG
5.02.08 | Sand Equivalent | The sand equivalent shall not be less than 25 when the aggregate is tested | NZS 4407: 1991 Test 3.6 (Wet Method) | IANZ Lab Reports |  | HP | ENG
5.02.09 | Liquid Limit | Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL). | NZS 4402 Test 2.2 NZS4407:2015 Test 3.2. | IANZ Lab Reports |  | HP | ENG
5.02.10 | Plasticity Index | Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested | NZS 4407 Test 3.4 | IANZ Lab Reports |  | HP | ENG
5.02.11 | Clay Index | Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested | NZS 4407 Test 3.5 | IANZ Lab Reports |  | HP | ENG
5.02.12 | Proportion of Broken Rock | In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces | PS - 7.2.2 | IANZ Lab Reports | 1 Test per source of the coarse aggregate. Additional samples if source is changed | HP | ENG
5.02.13 | Organic Matter | It shall be free of organic matter | PS - 7.2.2 | Photos | Continuous | I | SE/PE
5.02.14 | Accelerated Weathering Testing | If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis The levels of smectite clay minerals are not classified as “abundant” | In accordance with NZTA Standard Specification T20 Draft Specification | Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
5.02.15 | Repeat Load Triaxial Test | In accordance with NZTA T15 | NZTA T15 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
5.02.16 | Unconfined Compressive Strength (UCS) | Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives. | PS - Table No. 7.2 | IANZ Lab Reports | 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed. | HP | ENG
5.02.17 | Indirect Tensile Strength (ITS) | In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents. | NZTA T/19 - Table A7.4 | IANZ Lab Reports | 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed. | HP | ENG