## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004A – Asphaltic Planing | itp |  |  |  | Yes | ITP004A – Asphaltic Planing
section | 1. Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex.
label | Reference Documents - Current Revisions in Aconex
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer / Site Supervisor
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Minimum of one working cold planning machine onsite meeting the requirements of Project Specification.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.3
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer / Site Supervisor
checkpoint | 1.4 - Weather Conditions
label | Frequency - Prior to commencing works
label | Acceptance Criteria - When significant rain or weather events are forecasted that will prevent satisfactory completion of the works, works will not be undertaken.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. CL 11.5.2, 13.6.3 & 14.15.4.1
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer / Site Supervisor
section | 2. Asphaltic Planing
checkpoint | 2.1 - Set-out of area to be profiled
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Planing areas and depths are as shown on the Drawings and to be confirmed on site by the Principal’s Design Consultant. Updated profiling areas and depths for SP1 patching works are as per DCWC Mgt-GCOR-001362 and DCWC Mgt- PMA-000144.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint | 2.2 - Profiled Surface
label | Frequency - During profiling
label | Acceptance Criteria - The surface texture depth of the planed surface must be as agreed with the Principal’s Design Consultant, must be of the order of 3 mm to 6 mm and must be of a consistent appearance.
label | ○ No point on the planed surface must lie more than 6 mm below a 3 m straightedge placed on the planed surface in any direction.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer / Site Supervisor
checkpoint | 2.3 - Profiled Edges
label | Frequency - After completion of profiling
label | Acceptance Criteria - Where the cold planing equipment leaves edges along the perimeter of the excavation which are broken/chipped at the surface the Contractor must cut the edges.
label | ○ The cut must be straight and parallel to the perimeter of the excavation and must remove all chipped and broken edges to provide a clean face between vertical and 45º using an approved method.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer / Site Supervisor
checkpoint | 2.4 - Cleaning of profiled surface and removal of profiled materials
label | Frequency - During and after completion of profiling
label | Acceptance Criteria - Once the profiling is complete, the sweeping and cleaning of the profiled surface will commence.
label | ○ All loose materials and dust to be removed and the profiled surface shall be clean prior to any subsequent works.
label | ○ Disposal of profilings is to be as per CEMP.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
checkpoint | 2.5 - Inspection of Profiled Surface
label | Frequency - After completion of profiling
label | Acceptance Criteria - Once swept and cleaned, the profiled surface will be assessed by the Prinicpal’s Design Consultant for cleanliness as well as delamination, cracking and other issues likely to impact performance.
label | ○ An assessment will be made in conjunction with the Prinicpal’s Design Consultant whether any additional profiling is required and whether it can be undertaken in consideration of the circumstances of the shift.
label | ○ Note that a minimum of 30mm of existing asphalt is to be retained to avoid disturbing the underlying existing granular pavement.
label | ○ Photos and/or records will be taken to record any areas of concern and document what actions were undertaken.
label | Reference Documents - AECOM – MAPMP 2.0 DP1 Spec. Cl 12.4.1, 12.4.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed, Photos/GIS Markup
label | HP
label | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP