## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  | Yes | DG-QA-TP018 Inspection and Test Plan (ITP) | 970f6a1d-5474-4bfc-89c1-99f4afc5306d
checkpoint-group |  |  | section | Consent Conditions 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Appoint contact person for Councils monitoring officer.
label | 82c83786-d7d1-5a8e-8424-50578c481c85 |  | note | Inspection Point: Quality Control Activity - /
label | 7441c0bd-d7ad-5802-a967-2df772a5f694 |  | note | Acceptance Criteria - Prior to works
label | 1323c44d-7d9c-521d-a680-75d86856f3f3 |  | note | Verifying Document - /
label | 203ecac3-2f99-5da0-b495-e21f5eb69f66 |  | note | Frequency - Once
label | ff9ee02b-f7af-5957-a44a-3f48c5133d77 |  | note | Inspection Type (Visual, other) - Hold Point
label | 2ca33e78-a89a-5398-823f-aac4356e9665 |  | note | Inspection: Key - CH
label | dff32f22-6cd0-5e90-82a9-ae8e334a3b05 |  | note | Inspection: By (Role Key) - Consent Holder
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Appoint ecologist
label | 5aaf89b6-9fef-5ae9-a4da-3fd983e70ee2 |  | note | Inspection Point: Quality Control Activity - /
label | 29888df2-418f-5618-92ba-39b8e066cc2b |  | note | Acceptance Criteria - Prior to works
label | 313448fe-773e-5c90-9948-f144b142049b |  | note | Verifying Document - /
label | 95e5a147-14c4-5d3b-89b4-2c137f17975f |  | note | Frequency - Once
label | 966a22aa-ad07-51a9-882d-f802469bbc6d |  | note | Inspection Type (Visual, other) - Hold Point
label | 247c9220-a044-5743-b6e0-b2dc1ac70dd2 |  | note | Inspection: Key - CH
label | 792b28fa-1ad2-56d3-b879-a2309e0de963 |  | note | Inspection: By (Role Key) - Consent Holder
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Advise council montoring officer of contact people (Rep, Principal Contractor, Ecologist)
label | 3763e547-186f-518c-a5a2-60be435a41ce |  | note | Inspection Point: Quality Control Activity - /
label | a6a3e379-04d2-56c8-8c59-20fda579455f |  | note | Acceptance Criteria - Prior to works. (ongoing, and within one day of changes
label | 381cca76-0c98-54df-bb5f-98870ddac806 |  | note | Verifying Document - /
label | 67f8e478-223e-5362-9229-e4034dbbfb75 |  | note | Frequency - Once
label | f21b20f0-4d4f-59af-976b-d1d614f87973 |  | note | Inspection Type (Visual, other) - Hold Point
label | a4ac963c-2e25-5554-b797-e71281ce8cdb |  | note | Inspection: Key - CH
label | 9c122957-7582-50bc-a4f3-b19ae3d2eeb6 |  | note | Inspection: By (Role Key) - Consent Holder
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Advise monitoring officer of works commencing
label | 089e9d11-cdc0-5c68-9839-af9edd04c401 |  | note | Inspection Point: Quality Control Activity - /
label | 4dbe8fc6-e2a0-56e3-83cb-56e801e811ff |  | note | Acceptance Criteria - 10 working days prior to works. (and when sediment control measures placed and 24hrs prior to measures being removed
label | 06473ecc-648f-5b7b-b1dd-c8fa43d983d7 |  | note | Verifying Document - /
label | 3e01b2b0-53c1-538a-a7ef-5703efb2f15b |  | note | Frequency - Once
label | eb8b08a4-31ea-5203-86f8-8ba0ae62e8c8 |  | note | Inspection Type (Visual, other) - Hold Point
label | c937fb93-de09-5b1c-a2cb-22506cccaf84 |  | note | Inspection: Key - CH + C
label | 5190171f-e2dd-5c9c-9943-9ab0fb44f887 |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Site meeting between principal contractor, ecologist, monotoring officer, iwi officer
label | baf29d09-8b98-5273-823b-3c69785b0555 |  | note | Inspection Point: Quality Control Activity - /
label | 8d084724-eda1-5c92-94fc-bbb9dcab30f0 |  | note | Acceptance Criteria - Prior to works
label | a9a47e2e-d608-508a-a233-121c5f1a888c |  | note | Verifying Document - /
label | 9b1cf043-a5de-5bbb-87da-d5badfe74570 |  | note | Frequency - Once
label | 0199c3a4-e995-5ed4-93f1-9c3a76167213 |  | note | Inspection Type (Visual, other) - Hold Point
label | fd1a700d-08a3-5515-a787-258c7b76fb91 |  | note | Inspection: Key - CH + C
label | 1767650f-3c48-520c-ba3c-91489d12f7da |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Iwi monitor to be appointed, and forward evidence of this to monitoring officer
label | 774c20f4-0d25-58cb-b1e6-98cd6585897e |  | note | Inspection Point: Quality Control Activity - /
label | ee3e55b9-863f-5bd7-81b8-b5d0d23ff866 |  | note | Acceptance Criteria - 10 working days prior to works.
label | 625f0169-e483-5593-8d52-1277697f8ced |  | note | Verifying Document - /
label | 334768f2-c3be-5bcb-8a5b-d872ccba8d4d |  | note | Frequency - Once
label | ab70496c-5b84-56f8-9072-c0f39dccbd1a |  | note | Inspection Type (Visual, other) - Hold Point
label | 8d670f3c-40b5-50fd-a3df-b90c54b57eea |  | note | Inspection: Key - CH
label | e07f15ac-e53b-5746-af26-610cf6f80327 |  | note | Inspection: By (Role Key) - Consent Holder
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Prepare construction management plan, traffic management plan and spill management plan - see conditions for requirements
label | 356c33bd-82e6-596e-8179-ceda00bfaabb |  | note | Inspection Point: Quality Control Activity - Engineer to inspect plans
label | 3d7032b2-742f-58d9-8d5c-420643b9ca68 |  | note | Acceptance Criteria - 15 working days prior to works
label | 9aec4d8f-fef1-593d-b607-96ad0d4cb479 |  | note | Verifying Document - /
label | a7fd992c-4f03-5b49-a416-345770c71560 |  | note | Frequency - Once
label | 98795e9c-dd31-5c0b-aea0-3f34b36afb22 |  | note | Inspection Type (Visual, other) - Hold Point
label | feb191c1-30db-5a26-a246-5425009548bc |  | note | Inspection: Key - CH + C
label | 6a85444a-d245-56ea-a9e1-381e100f93d0 |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Penguin management plan submitted to council
label | 6618e399-de01-599e-a3cb-23d4a0ba8c51 |  | note | Inspection Point: Quality Control Activity - Engineer to inspect plans
label | 651a3e7e-aab4-5716-87d0-26c40cbc0a93 |  | note | Acceptance Criteria - 15 working days prior to works
label | fa2519bf-41fc-582e-9847-2ff71c2068f7 |  | note | Verifying Document - /
label | 1792583b-448d-5388-a6fd-a2d1b558686f |  | note | Frequency - Once
label | 5c1befe4-31d6-5546-ad05-86b1aecad11b |  | note | Inspection Type (Visual, other) - Hold Point
label | 84e41546-510f-561a-96eb-f712bc02d9d7 |  | note | Inspection: Key - CH
label | 2c190425-9adb-5fbe-b34f-ac9bced93961 |  | note | Inspection: By (Role Key) - Consent Holder
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Lizard management by Ecologist 2-10 days prior to vegetation removal in specific areas
label | 45ef99eb-3c69-540a-918a-d2fe6b1495c1 |  | note | Inspection Point: Quality Control Activity - /
label | febe8be4-1cac-549d-a798-c06d20c01db0 |  | note | Acceptance Criteria - 2-10 days prior to vegetation clearance in specific areas
label | f8bf7fc8-6d67-5f55-af20-b18bbd159d32 |  | note | Verifying Document - /
label | bd197c5c-cb5a-5f47-9994-24e303bfa40b |  | note | Frequency - Once
label | 3b03726e-0d59-5f39-98bb-14de1ab62091 |  | note | Inspection Type (Visual, other) - Hold Point
label | 1f5a0171-e576-5e11-9ee3-e907590ceb17 |  | note | Inspection: Key - CH + C
label | cfe3bc4d-e50b-5b75-b755-fd1819b374da |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.10 - Clean machinery prior to arrival on site
label | dea2f959-c343-51bb-85b1-c37bb7d3ca20 |  | note | Inspection Point: Quality Control Activity - /
label | a69c3dde-9ef8-57db-bfb7-33d38743e945 |  | note | Acceptance Criteria - Prior to arrival on site
label | c5eb88cd-c579-5863-8deb-c64cc9ea7865 |  | note | Verifying Document - /
label | 7603ffa7-0ac9-5325-8c11-e9c8db31a64e |  | note | Frequency - Once
label | 1516c92a-032f-57d9-8040-94f478393117 |  | note | Inspection Type (Visual, other) - Hold Point
label | d5f187f8-8095-50c6-9f65-a1c74e3c75ce |  | note | Inspection: Key - C
label | 245f643f-df6f-58f2-bd90-d1b020b1bb79 |  | note | Inspection: By (Role Key) - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.11 - Access routes (on foot) identified to works areas to avoid vegetation
label | cdae7729-6f06-5967-bf4f-36c4744cca9a |  | note | Inspection Point: Quality Control Activity - /
label | 26f07a50-0fda-51d5-bc04-73bd729d306f |  | note | Acceptance Criteria - Identified on-site prior to works impacting estuary vegetation
label | 4a2a3799-8207-55fe-923c-9a66f3e6e28d |  | note | Verifying Document - /
label | d8b40ac1-2351-55d9-ac5b-792063371c6f |  | note | Frequency - Once
label | 98fc9777-3900-5e78-8db7-05daa356ea0f |  | note | Inspection Type (Visual, other) - Hold Point
label | 12549f38-0b5d-59b3-bd3c-be2a1d516d71 |  | note | Inspection: Key - C
label | 7e18b355-5930-5469-a95e-88121fe599d8 |  | note | Inspection: By (Role Key) - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.12 - Erect notices at each end of works site prior to works commencing
label | 8af3afcc-0ce9-5372-92e4-7f83516bfecc |  | note | Inspection Point: Quality Control Activity - /
label | 4fe2afe2-19f2-5d94-9415-38785680cba7 |  | note | Acceptance Criteria - 2 working days prior to works (minimum)
label | 8b6af839-1f7a-5aa9-a63a-82db695d352e |  | note | Verifying Document - /
label | eb38f93d-8eb1-54c4-9545-b6b3f46b690c |  | note | Frequency - Once
label | 58ccb15e-e3a3-5b9c-902a-7139fbf90747 |  | note | Inspection Type (Visual, other) - Hold Point
label | 218c22bf-776f-55a9-b408-b29d1ae8b7d0 |  | note | Inspection: Key - CH + C
label | f00c6f5e-13d6-5ae9-a22a-610071d951e0 |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.13 - Provide written notice to neighbours prior to works commencing
label | cb326401-ff93-5dd2-a0bf-2fd0d0fb080e |  | note | Inspection Point: Quality Control Activity - /
label | f8076e9b-7d7b-5b03-9f2f-e35442d7ab05 |  | note | Acceptance Criteria - 2 working days prior to works (minimum)
label | b36d77ff-9761-5f67-9b8b-ce09e7dac621 |  | note | Verifying Document - /
label | 74fdf8d9-f7b4-5036-b3cb-16dd6194c500 |  | note | Frequency - Once
label | fe630f0a-52b3-56ff-a6f2-cbea595b6e8e |  | note | Inspection Type (Visual, other) - Hold Point
label | 05d9f7a3-7a90-5e43-843f-8bb7eeb48554 |  | note | Inspection: Key - CH + C
label | 4d8ca7de-f72b-560f-9746-3b374fc2605f |  | note | Inspection: By (Role Key) - Consent Holder + Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Safety 2.0
checkpoint-status |  |  | checkpoint | 2.1 - Traffic Management
label | 7588c1c2-4725-5ec6-b7e3-41e253531a62 |  | note | Inspection Point: Quality Control Activity - Traffic Management to be set up daily before work can commence.
label | 03569ff7-db85-5e4a-8767-39de350f1b5b |  | note | Acceptance Criteria - Traffic Management set up by qualified STMS according to approved plan
label | a1914867-f536-56b6-8769-3587d97ea190 |  | note | Verifying Document - Approved TMP
label | 99415ba4-9242-5112-b2ca-b3fcf4ac60ee |  | note | Frequency - Daily
label | e5c5356b-b9ba-5ce7-bbe3-0cda59a28e24 |  | note | Inspection Type (Visual, other) - Hold Point
label | a7f3f116-6681-522e-b4ac-75b82ed63fe0 |  | note | Inspection: Key - C
label | d30f4382-0eb6-56f0-89fd-2c49f8608cf5 |  | note | Inspection: By (Role Key) - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Locate services
label | 8b86e7ed-e7bc-536f-8944-99fde5428218 |  | note | Inspection Point: Quality Control Activity - /
label | 8b6e7594-6787-53c3-9d27-15dd6e72ceb1 |  | note | Acceptance Criteria - Services located by Delta, Chorus and TDC prior to commencing works.
label | ef55a1a1-617e-5245-886e-65c92c390098 |  | note | Verifying Document - /
label | aed1e5be-8742-5d38-b165-969e7a4f1349 |  | note | Frequency - Once
label | b94759c9-fec9-5a07-94f8-16efbd680f77 |  | note | Inspection Type (Visual, other) - Verification
label | ded45ddf-7d6f-57ee-9056-55f349c4ce3c |  | note | Inspection: Key - C
label | c6a7b561-dc06-536f-aa82-3d217de754e1 |  | note | Inspection: By (Role Key) - Contractor
checkpoint-group |  |  | section | Road Widening
checkpoint-status |  |  | checkpoint | 4.4 - Compaction of basecoursde (Field Dry Density)
label | f82c931f-8d7d-5f72-afd9-dce8010e1329 |  | note | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 7.6
label | e36bbec7-8071-524b-8107-394f0ee04da8 |  | note | Acceptance Criteria - ≥ 98% ave at MDD. ≥ 95% min
label | e438fb45-3fe6-5a69-bb9e-422ae82839f8 |  | note | Verifying Document - Inspection
label | f015821f-63ed-56fd-b567-757a96c9487e |  | note | Frequency - 1 lot ( 5 tests)
label | 121af36f-d7ca-5f86-9cc6-fe1bc13d925e |  | note | Inspection Type (Visual, other) - Hold Point
label | ae7355bb-c8f8-5b7e-9ff8-99605ff45d65 |  | note | Inspection: Key - SC
label | d6b83a7d-9f59-5ae6-ad53-4ff8ae700117 |  | note | Inspection: By (Role Key) - Sels Civil
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Saturation
label | fbb79fa9-f598-53a0-b489-d3c54d102cda |  | note | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 12
label | edb0d9ff-1f42-56c3-bdbf-35d9ba983213 |  | note | Acceptance Criteria - Less than 80%
label | daf23936-4e9e-5c1e-becd-219f3b928157 |  | note | Verifying Document - Inspection
label | f25614e2-a10f-51c9-b6eb-c273a749ab23 |  | note | Frequency - 1 per 110m²
label | 60b85720-38e1-5dcb-9979-0289d4a180a3 |  | note | Inspection Type (Visual, other) - Hold Point
label | b107d325-8224-53ce-afb9-036326dac98b |  | note | Inspection: Key - SC
label | 7c30eac3-5f8d-5023-9e0e-ace72d9a6745 |  | note | Inspection: By (Role Key) - Sels Civil
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 - Pre Seal Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Estuary Side Prep
checkpoint-status |  |  | checkpoint | 4.4 - Compaction of basecoursde (Field Dry Density)
label | 3a405596-9c63-5945-ae40-17b938507769 |  | note | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 7.6
label | 3ef6991f-cbab-5aa3-8c1d-f6e56464f5f7 |  | note | Acceptance Criteria - ≥ 98% ave at MDD. ≥ 95% min
label | 198f37d2-580b-5504-b0d9-d30ede32edf2 |  | note | Verifying Document - Inspection
label | ced1d87e-a3ac-50fe-a95f-bf14f79aec7c |  | note | Frequency - 1 lot ( 5 tests)
label | 254a748d-ebf8-5294-9eb4-868bb7bb0712 |  | note | Inspection Type (Visual, other) - Hold Point
label | 3d6df650-f67b-513f-ba12-e801804e06be |  | note | Inspection: Key - SC
label | 52bc1db1-2d9b-5088-8192-c516873effb0 |  | note | Inspection: By (Role Key) - Sels Civil
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Saturation
label | 1eede0a0-70d5-505c-8769-1feccee7fdeb |  | note | Inspection Point: Quality Control Activity - NDM as per TNZ B/02 clause 12
label | 1b0285c6-7e31-56ea-95f6-0dfbe0fc7e6a |  | note | Acceptance Criteria - Less than 80%
label | 5657d329-bb1d-5640-85d0-bdc6eb284f5b |  | note | Verifying Document - Inspection
label | 9126322a-ac4c-5a33-ad96-7a6adf5035cf |  | note | Frequency - 1 per 110m²
label | 2eb06ebb-d928-5163-bf28-95546fdcda00 |  | note | Inspection Type (Visual, other) - Hold Point
label | 5477bc8a-f56a-5839-a0be-515dcc522709 |  | note | Inspection: Key - SC
label | 6bf70fe4-a575-55f6-8807-91be3526631e |  | note | Inspection: By (Role Key) - Sels Civil
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 - Pre Seal Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Basecourse 4.1
checkpoint-status |  |  | checkpoint | 4.1.1 - Sand Equivalent
label | 375b5300-652d-5e6a-97fa-3e793bb66e4b |  | note | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | d2a18436-9a3b-54d9-a244-ef84a667b4b5 |  | note | Acceptance Criteria - ≥ 40
label | d59aae74-06df-541d-bd88-dee50ea31d52 |  | note | Verifying Document - Council / Engineer to approve materials
label | eeda0a10-be6a-5657-96c1-0ec5b1cd6c1f |  | note | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | 28521fec-47de-551a-982d-a63396c03c26 |  | note | Inspection Type (Visual, other) - Hold Point
label | 6e003490-7fe2-57aa-a8f1-726dda3446b3 |  | note | Inspection: Key - WSP / TDC
label | 3ef5088d-7812-5309-bedd-0e1f9762bf25 |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.2 - Clay Index
label | b3a779b5-b1bd-5bf9-b3ed-567f05f7efa9 |  | note | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | fc8f85ac-c272-5bbb-bcf0-cc89a3db4f10 |  | note | Acceptance Criteria - ≤ 3 passing 75um
label | 176328e1-82cd-5025-8292-f0d2189015d7 |  | note | Verifying Document - Council / Engineer to approve materials
label | 2baa80f0-1f45-53ec-b1c4-e600d7507524 |  | note | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | 3abb0b0d-4786-5df6-841c-ec6fe57fe1a0 |  | note | Inspection: Key - WSP / TDC
label | 603ed08f-8865-572a-b640-c053aed2fb41 |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.4 - Broken Face Content
label | a8298bef-4bf9-5aab-8e62-8d284cf7ed2e |  | note | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | e01777b4-96d8-5702-8b95-bb1bd4e4d01f |  | note | Acceptance Criteria - 70% with 2 broken faces
label | ac2bd050-e47a-5a29-a9f0-9133c6f40cf5 |  | note | Verifying Document - Council / Engineer to approve materials
label | 6d291460-712a-5dbb-9c9f-e5292fb9f7cd |  | note | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | 6e4fc42b-218e-55fd-b568-cbf3145dabc8 |  | note | Inspection: Key - WSP / TDC
label | b62bbf9f-640e-5b94-9a53-9e50471954a2 |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1.5 - Particle Size Distribution
label | 82731ba0-34d0-51b6-a1e7-1de386a18896 |  | note | Inspection Point: Quality Control Activity - As per NZS 4407:2015
label | cdc27594-a1aa-5179-8862-5bfa8f49622f |  | note | Acceptance Criteria - To be within envelope limits
label | 40d7e74a-39ec-5ed4-b43a-144a704575e4 |  | note | Verifying Document - Council / Engineer to approve materials
label | 18f93d37-56ec-5c5e-a098-11b714e53f5e |  | note | Frequency - 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1
label | 21759808-7b9e-5ade-83e8-d6b08d2f5ec3 |  | note | Inspection: Key - WSP / TDC
label | eae47b2a-484a-5c8b-941b-7387ee0e799e |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Footpath
checkpoint-status |  |  | checkpoint | Riwaka Gold material being used for the footpath
label | c18633a1-2375-53d3-8abb-13e19dd85a4f |  | note | Inspection Type (Visual, other) - Visual
label | a5af5ec6-4c75-5d04-b52a-f0fb25488234 |  | note | Inspection: Key - WSP / TDC
label | 222184e5-2435-5c0d-a016-2177367d94f2 |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Asphaltic Concrete 8.0
checkpoint-status |  |  | checkpoint | 8.1 - Surface shape on completion
label | ec3ab4a0-9f55-5bef-b8f7-464b8091f84d |  | note | Inspection Point: Quality Control Activity - 3 metre straight edge
label | 869b579a-aea0-547f-a56b-af3078392936 |  | note | Acceptance Criteria - Maximum 5mm
label | d87aeae9-de9c-5903-91f7-85dc56a912f5 |  | note | Verifying Document - Visual
label | 00aaeab2-f75b-583b-8395-828e80a113a0 |  | note | Frequency - /
label | e1601cc4-3d6d-55db-8c7f-a5e64dc7d83d |  | note | Inspection Type (Visual, other) - Hold Point
label | 91fcc141-cd90-5c7a-915d-607837a59deb |  | note | Inspection: Key - CS
label | eca876a4-b49c-5434-a946-992898ad8774 |  | note | Inspection: By (Role Key) - Construction Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - Depth
label | bcf7bab8-8e7f-5234-b76d-39647b7a04cb |  | note | Inspection Point: Quality Control Activity - Ruler measurement
label | c794933a-2e7a-51d9-9181-6886869d711f |  | note | Acceptance Criteria - -0mm +5mm
label | 5ca29dab-c6b1-58f7-b7f5-351935a04307 |  | note | Verifying Document - Visual
label | f4f808ec-e9bd-5eee-96fd-147729c22eef |  | note | Frequency - /
label | 457d8825-bb4a-527c-9018-91e38370e89e |  | note | Inspection Type (Visual, other) - Hold Point
label | f00269b3-2e16-5454-b0f5-4b3375ebeaf1 |  | note | Inspection: Key - CS
label | 4a75aa8d-f3df-5be1-91eb-51565752ef2e |  | note | Inspection: By (Role Key) - Construction Supervisor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Boardwalk 9.0
checkpoint-status |  |  | checkpoint | 9.1 - Refer to DRG 5-G3445.40
label | 41baa70d-3d78-5505-8a43-1f8affe4b31b |  | note | Inspection Point: Quality Control Activity - /
label | 7dcb2a0d-c2fb-5672-aea1-158d46e15b73 |  | note | Acceptance Criteria - Built to plan
label | 19164efa-9e78-5c67-a967-4e8324f17b3d |  | note | Verifying Document - Inspection
label | 74403c1a-7c2a-5685-92cb-6af1956d7658 |  | note | Frequency - When Required
label | 3bd7399b-fce6-51a8-af89-3435635a1248 |  | note | Inspection Type (Visual, other) - Hold Point
label | 9eb6d58d-6c5c-5a44-b408-eeba90d95dbd |  | note | Inspection: Key - WSP / TDC
label | d1073d9f-b530-5602-ac6c-392c8ffc6993 |  | note | Inspection: By (Role Key) - WSP / TDC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Post set out
label | 1ae64678-12a1-5523-a32c-43d3352c6eca |  | note | Inspection Point: Quality Control Activity - Ruler measurement / and stringline
label | cadcb7d1-c0f5-5107-9cf9-ec82dc450b32 |  | note | Acceptance Criteria - Spacing and alignment
label | de599642-1337-58ed-ba3a-edbeb4212d9e |  | note | Verifying Document - inspection
label | c5a19132-13c1-570c-b995-a6ff1ca9c695 |  | note | Frequency - prior to comencement of driving piles
label | e1d28d70-bb53-5d0d-ba47-85afe528cb47 |  | note | Inspection Type (Visual, other) - Hold point
label | 1bddc7d7-e77e-5de3-9cc8-aa2a0feebf3a |  | note | Inspection: Key - WSP
label | 5b95eb0d-8509-57bc-a912-f00100547121 |  | note | Inspection: By (Role Key) - WSP / C
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Depth of piles
label | 6a0f7597-e9f3-56ed-b2b7-00678c6182d3 |  | note | Inspection Point: Quality Control Activity - Pre marked on Piles
label | 8799e3fa-d20a-551e-ab7a-caac67ed6aaa |  | note | Acceptance Criteria - Minimum 2.5m
label | e5ee194c-a6b7-56ed-89ad-f16b46734d95 |  | note | Verifying Document - measuremnt on piles
label | d9f17d3d-58e1-5388-876a-95eac856bb42 |  | note | Frequency - all
label | 5d05233e-6307-5955-ab47-faea1e79153c |  | note | Inspection Type (Visual, other) - Visual
label | 65f31e92-69e1-58f5-a6c4-800fefbd9ac2 |  | note | Inspection: Key - WSP
label | 228f55cf-f48d-5a8c-a740-35819d5ddd29 |  | note | Inspection: By (Role Key) - WSP / C
checkpoint-status |  |  | checkpoint | 9.4 - Resistance
label | dde67136-0349-5641-b2c9-b76ddb7102aa |  | note | Acceptance Criteria - 60kN
label | a3bdf68a-bff8-5181-916b-646a96833e29 |  | note | Verifying Document - Blows of driver record
label | d1b5cc6b-56f1-5e63-9630-dbc21438d700 |  | note | Frequency - all
label | b3a6d76f-e348-5edf-81c5-9db25fcf6bb0 |  | note | Inspection Type (Visual, other) - visual
label | 1594c111-227d-5ef4-9e87-d5a16b820f32 |  | note | Inspection: Key - WSP
label | e9980cde-af42-5711-ad9c-dfaeb3a50138 |  | note | Inspection: By (Role Key) - construction Supervisor