## Table 1
Levels Suspended Drainage Checklist Levels Suspended Drainage Checklist
Hot Water Unit Checklist
Vents Checklist
Storm Water Grates Checklist
type | name |  | values
checklist In-Ground Stormwater Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint | Pipework installation
checkpoint | Pipework checked for correct invert levels & gradients
checkpoint | Pits checked for correct invert levels & finished floor levels
checkpoint Ensure correct locations of pits.
checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checklist In-Ground Sewer Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint | Pipework installation
checkpoint | Pipework checked for correct invert levels & gradients
checkpoint | Book inspection with VBA for in-ground drainage.
checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint | Test sewer
checklist In-Ground Pits/Pumps/Tanks Checklist
checkpoint | Sewer pump well
checkpoint | Storwater pump well
checkpoint | Stormwater pits
checkpoint | Grease interceptor trap
checkpoint | Conduits rain to IFC location
checkpoint | Torpedo tanks
checkpoint | Stormwater detention system
checklist Penetrations Checklist
checkpoint | All works to be set our as per approved IFC drawings.
checkpoint | Fire collar installation
checkpoint | Cast in drains
checkpoint | Photos of collar end labelling referencing fire matrix if required
checklist Suspended Stormwater Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint | Pipework installation
checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint | Smoke seal penetrations
checkpoint | Fire collars installed if necessary
checklist Suspended Sewer Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
checkpoint | Pipework installation
checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint | Smoke seal penetrations
checkpoint | Fire collars installed if necessary
checkpoint | Test sewer
checklist Other Areas Suspended Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
checkpoint | Pipework installation
checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint | Smoke seal penetrations
checkpoint | Fire collars installed if necessary
checklist Corridor Checklist
checkpoint | Rainwater
checkpoint | Hot Water
checkpoint | Hot Water Lagged
checkpoint | Cold Water
checkpoint | Test Hot Water
checkpoint | Test Cold Water
checkpoint | Test Rain Water
checkpoint | Fire Caulking (Corridor to Apt)
checkpoint | Cold Water Meter Manifold
checklist Suspended Copper Works Checklist
checkpoint | Pipework installed - domestic hot/cold/rain water
checkpoint | Smoke seal penetrations
checkpoint | Tested
checkpoint | Fire rated if necessary
checklist Gas Works Checklist
checkpoint | Gas Meter set up (Ground floor only)
checkpoint | Gas Riser room pipe installation
checkpoint | Pipe anchor/slide guides
checkpoint | Smoke sealed
checkpoint | Gas tested
checkpoint | Fire rated
checklist In-Ground Pits/Pumps/Tanks Checklist
checkpoint | Sewer pump well
checkpoint | Storwater pump well
checkpoint | Stormwater pits
checkpoint | Grease interceptor trap
checkpoint | Conduits rain to IFC location
checkpoint | Torpedo tanks
checkpoint | Stormwater detention system
checklist Basement Pumps/Tanks/Booster Pump Checklist
checkpoint checkpoint | Domestic cold water booster pump Domestic cold water break tank
checkpoint checkpoint | Rainwater pump set Rainwater tanks
checkpoint checkpoint checkpoint | Sewer pump board installed Stormwater pump board installed Suspended Pollutant trap
checkpoint checkpoint | Diversion valve OSD tank (if applicable)
checkpoint checkpoint | Smoke sealed Tested
checkpoint | Fire rated if necessary
checkpoint | Water meter assembly
checklist Rough In Checklist
checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint | For other areas includes female/male/DDA bathroom, kitchen
checkpoint | High Level Rough In
checkpoint | Wall Set Out
checkpoint | Wall Rough In
checkpoint | Waste Rollovers
checkpoint | Gas
checkpoint | Test Water
checklist Levels Suspended Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes female/male/DDA bathroom, kitchen
checkpoint | Pipework installation
checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint | Smoke seal penetrations
checkpoint | Fire collars installed if necessary
checklist Other Areas Fit Off Checklist
section Kitchen/Butler's Pantry Fit Off
checkpoint | Kitchen Mini Stops
checkpoint | Kitchen Sink Waste
checkpoint | Kitchen Sink Mixer
checkpoint | Kitchen Dishwasher
checkpoint | Kitchen Cooktop
section Female Bathroom Fit Off
checkpoint | Bathroom Shower Mixer
checkpoint | Bathroom Shower Rail/Rose
checkpoint | Bathroom Basin
checkpoint | Bathroom Basin Mixer
checkpoint | Bathroom Bottle Trap
checkpoint | Bathroom Toilet
checkpoint | Bathroom Urinal
section Male Bathroom Fit Off
checkpoint | Bathroom Shower Mixer
checkpoint | Bathroom Shower Rail/Rose
checkpoint | Bathroom Basin
checkpoint | Bathroom Basin Mixer
checkpoint | Bathroom Bottle Trap
checkpoint | Bathroom Toilet
checkpoint | Bathroom Urinal
section DDA Bathroom Fit Off
checkpoint | Bathroom Shower Mixer
checkpoint | Bathroom Shower Rail/Rose
checkpoint | Bathroom Basin
checkpoint | Bathroom Basin Mixer
checkpoint | Bathroom Bottle Trap
checkpoint | Bathroom Toilet
checkpoint | Bathroom Urinal
checklist Commissioning Checklist
checkpoint | Includes female/male/DDA bathroom, kitchen
checkpoint | Test Hot Water Temperature
checkpoint | Test Waste for leaks
checkpoint | Run Cycle on Dishwasher
checklist Hot Water Unit Checklist
checkpoint | Hot water unit installation
checkpoint | Copper works installation
checkpoint | Smoke sealed
checkpoint | Fire rated
checkpoint | Tested
checklist Vents Checklist
checkpoint | Vents installed
checkpoint | Smoke sealed
checkpoint | Fire rated
checkpoint | Tested
checklist Storm Water Grates Checklist
checkpoint | Grates installed
checkpoint | Smoke sealed
checkpoint | Fire rated
checkpoint | Tested
checklist Apartment Suspended Drainage Checklist
checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
checkpoint | Pipework installation
checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint | Smoke seal penetrations
checkpoint | Fire collars installed if necessary
checklist Apartment Fit Off Checklist
section Laundry Fit Off
checkpoint | Laundry Trough
checkpoint | Laundry Trough Mixer
checkpoint | Laundry Trough Mini Stops
checkpoint | Laundry Trough Waste
section Kitchen Fit Off
checkpoint | Kitchen Mini Stops
checkpoint | Kitchen Sink Waste
checkpoint | Kitchen Sink Mixer
checkpoint | Kitchen Dishwasher
checkpoint | Kitchen Cooktop
section Bathroom Fit Off
checkpoint | Bathroom Shower Mixer
checkpoint | Bathroom Shower Rail/Rose
checkpoint | Bathroom Basin
checkpoint | Bathroom Basin Mixer
checkpoint | Bathroom Bottle Trap
checkpoint | Bathroom Toilet
checkpoint | Bathroom Urinal
Folder Structure
Site QA
Checklists
In-Ground
Sewer Stormwater
Pits / Pumps / Tanks
In-Ground Sewer Drainage Checklist
In-Ground Stormwater Drainage Checklist In-Ground Pits/Pumps/Tanks Checklist
Penetrations
B3 B2 B1
Ground Level 1
Level 2
Level 3
Level 4
Level 5
Level 6
Level 7 Roof
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
POUR 1 AND POUR 2
Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist Penetrations Checklist
Suspended Drainage
B2 B1
Ground
FULL LEVEL FULL LEVEL
Apartment G.01 = G.09
break down into each apartment Levels Suspended Drainage Checklist
Level 1
Apartment 1.01 - G.09
break down into each apartment Apartment Suspended Drainage Checklist
Level 2
Apartment 2.01 - 2.09
break down into each apartment Apartment Suspended Drainage Checklist
Level 3
Apartment 3.01 - 3.09
break down into each apartment Apartment Suspended Drainage Checklist
Level 4
Apartment 4.01 - 4.09
break down into each apartment Apartment Suspended Drainage Checklist
Level 5
Apartment 5.01 - 5.05
break down into each apartment Apartment Suspended Drainage Checklist
Level 6
Apartment 6.01 - 6.05
break down into each apartment Apartment Suspended Drainage Checklist
Level 7
Apartment 7.01 - 7.05
break down into each apartment Apartment Suspended Drainage Checklist
Roof
Basement Suspended Copper Works
B2 B1
Rough In
Ground
Suspended Copper Works Checklist Suspended Copper Works Checklist
Apartment G.01 = G.09 break down into each apartment Rough In Checklist
Level 1
Apartment 1.01 - G.09
break down into each apartment Rough In Checklist
Level 2
Apartment 2.01 - 2.09
break down into each apartment Rough In Checklist
Level 3
Apartment 3.01 - 3.09
break down into each apartment Rough In Checklist
Level 4
Apartment 4.01 - 4.09
break down into each apartment Rough In Checklist
Level 5
Apartment 5.01 - 5.05
break down into each apartment Rough In Checklist
Level 6
Apartment 6.01 - 6.05
break down into each apartment Rough In Checklist
Level 7
Apartment 7.01 - 7.05
break down into each apartment Rough In Checklist
Roof
Corridor
Ground Level 1
Level 2
Level 3
Level 4
Level 5
Level 6
Level 7
Corridor Checklist Corridor Checklist Corridor Checklist Corridor Checklist Corridor Checklist Corridor Checklist Corridor Checklist Corridor Checklist
Fit Off
Ground
Apartment G.01 = G.09
break down into each apartment Apartment Fit Off Checklist
Level 1
Apartment 1.01 - G.09
break down into each apartment Apartment Fit Off Checklist
Level 2
Apartment 2.01 - 2.09
break down into each apartment Apartment Fit Off Checklist
Level 3
Apartment 3.01 - 3.09
break down into each apartment Apartment Fit Off Checklist
Level 4
Apartment 4.01 - 4.09
break down into each apartment Apartment Fit Off Checklist
Level 5
Apartment 5.01 - 5.05
break down into each apartment Apartment Fit Off Checklist
Level 6
Apartment 6.01 - 6.05
break down into each apartment Apartment Fit Off Checklist
Level 7
Apartment 7.01 - 7.05
break down into each apartment Apartment Fit Off Checklist
Roof
Commissioning
Ground
Apartment G.01 = G.09
break down into each apartment Commissioning Checklist
Level 1
Apartment 1.01 - G.09
break down into each apartment Commissioning Checklist
Level 2
Apartment 2.01 - 2.09
break down into each apartment Commissioning Checklist
Level 3
Apartment 3.01 - 3.09
break down into each apartment Commissioning Checklist
Level 4
Apartment 4.01 - 4.09
break down into each apartment Commissioning Checklist
Level 5
Apartment 5.01 - 5.05
break down into each apartment Commissioning Checklist
Level 6
Apartment 6.01 - 6.05
break down into each apartment Commissioning Checklist
Level 7
Apartment 7.01 - 7.05
break down into each apartment Commissioning Checklist
Roof
Roof Works
Hot Water Units Vents
Stormwater Grates