## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
DTM-ITP-007- Concrete - Kerb, Footpaths & Islands
| Scope |  |  | Kerb, Footpath and Islands
Rows
|  | Kerb, Footpath and Islands | dynamic | Kerb, Footpath and Islands
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Submission & Approval of Concrete Mix Design |  | 1.3 - Submission & Approval of Concrete Mix Design
|  | 2.1 - Setting Out |  | 2.1 - Setting Out
|  | 2.2 - Excavation Permit |  | 2.2 - Excavation Permit
|  | 2.3 - Excavation |  | 2.3 - Excavation
|  | 2.4 - Bedding |  | 2.4 - Bedding
|  | 2.5 - Formwork |  | 2.5 - Formwork
|  | 2.6 - Reinforcement |  | 2.6 - Reinforcement
|  | 2.7 - Sampling Strength and Consistency |  | 2.7 - Sampling Strength and Consistency
|  | 2.8 - Concrete Placement |  | 2.8 - Concrete Placement
|  | 2.9 - Record location of each batch |  | 2.9 - Record location of each batch
|  | 2.10 - Surface Finish |  | 2.10 - Surface Finish
|  | 2.11 - Pram Crossings |  | 2.11 - Pram Crossings
|  | 2.12 - Driveways - Acommodation Works |  | 2.12 - Driveways - Acommodation Works
|  | 2.13 - Joints |  | 2.13 - Joints
|  | 2.14 - Protection of concrete |  | 2.14 - Protection of concrete
|  | 2.15 - Curing |  | 2.15 - Curing
|  | 3.1 - Tolerances |  | 3.1 - Tolerances
|  | 3.2 - Backfilling |  | 3.2 - Backfilling
|  | 3.3 - Compressive Strength Conformance |  | 3.3 - Compressive Strength Conformance
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Print Name: | QAV - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Position: | QAV - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Work Completed On: | Work Completed On: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
DTM-ITP-009- Traffic Signals
| Scope |  |  | Traffic Signals
Rows
|  | Traffic Signals | dynamic | Traffic Signals
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Ensure correct materials are being used |  | 1.3 - Ensure correct materials are being used
|  | 1.4 - Pre-installation |  | 1.4 - Pre-installation
|  | 1.5 - Set Out |  | 1.5 - Set Out
|  | 1.6 - Proving Services |  | 1.6 - Proving Services
|  | 1.7 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets |  | 1.7 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets
|  | 1.8 - Boring proposal |  | 1.8 - Boring proposal
|  | 1.9 - Submission of Mix Design |  | 1.9 - Submission of Mix Design
|  | 2.1 - Excavation/Boring & Trenching |  | 2.1 - Excavation/Boring & Trenching
|  | 2.2 - Installation of Conduits |  | 2.2 - Installation of Conduits
|  | 2.3 - Installation of Draw Cords |  | 2.3 - Installation of Draw Cords
|  | 2.4 - Back Fill of Trenches - Open Trench |  | 2.4 - Back Fill of Trenches - Open Trench
|  | 2.5 - Back Fill of Trenches - Inspection (Open Trench) |  | 2.5 - Back Fill of Trenches - Inspection (Open Trench)
|  | 2.6 - Back Fill of Trenches - Grout & Inspection (Direction Bore Trench) |  | 2.6 - Back Fill of Trenches - Grout & Inspection (Direction Bore Trench)
|  | 2.7 - Compaction |  | 2.7 - Compaction
|  | 2.8 - Installation of marker tape |  | 2.8 - Installation of marker tape
|  | 2.9 - Cable Pits & Pit Lids |  | 2.9 - Cable Pits & Pit Lids
|  | 2.10 - Asbestos Removal |  | 2.10 - Asbestos Removal
|  | 2.11 - Pit Lid Surrounds |  | 2.11 - Pit Lid Surrounds
|  | 3.1 - Determine footing required at location |  | 3.1 - Determine footing required at location
|  | 3.2 - Excavation Levels |  | 3.2 - Excavation Levels
|  | 3.3 - Rag Bolt Assembly |  | 3.3 - Rag Bolt Assembly
|  | 3.4 - Pre-pour inspection |  | 3.4 - Pre-pour inspection
|  | 3.5 - Pouring of concrete - foundations |  | 3.5 - Pouring of concrete - foundations
|  | 3.6 - Sampling and Concrete Testing |  | 3.6 - Sampling and Concrete Testing
|  | 3.7 - Standing of Pedestals and Poles |  | 3.7 - Standing of Pedestals and Poles
|  | 3.8 - Post pour Inspection |  | 3.8 - Post pour Inspection
|  | 4.1 - Hardware Installation |  | 4.1 - Hardware Installation
|  | 4.2 - Lantern Mounting Height |  | 4.2 - Lantern Mounting Height
|  | 4.3 - Lantern Mounting Locations and Allignment |  | 4.3 - Lantern Mounting Locations and Allignment
|  | 4.4 - Target Boards, Visors and Louvres |  | 4.4 - Target Boards, Visors and Louvres
|  | 4.5 - Installation of Pedestrian Push Buttons |  | 4.5 - Installation of Pedestrian Push Buttons
|  | 4.6 - Non-Commissioned Lanterns |  | 4.6 - Non-Commissioned Lanterns
|  | 4.7 - Inspection |  | 4.7 - Inspection
|  | 4.8 - ITS Installation |  | 4.8 - ITS Installation
|  | 5.1 - Point of Supply |  | 5.1 - Point of Supply
|  | 5.2 - Connection of Traffic Signal Controller |  | 5.2 - Connection of Traffic Signal Controller
|  | 5.3 - Site Cabling |  | 5.3 - Site Cabling
|  | 5.4 - Installation of Detector Loops |  | 5.4 - Installation of Detector Loops
|  | 6.1 - Testing of Electrical Works/PreCommisioning |  | 6.1 - Testing of Electrical Works/PreCommisioning
|  | 6.2 - Provision of Power |  | 6.2 - Provision of Power
|  | 6.2 - Traffic Signal Controller Installation |  | 6.2 - Traffic Signal Controller Installation
|  | 6.2 - As-constructed drawings |  | 6.2 - As-constructed drawings
|  | 6.3 - Comissioning |  | 6.3 - Comissioning
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Print Name: | QAV - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Position: | QAV - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Work Completed On: | Work Completed On: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
DTM-ITP-013- Retaining Wall Backfill
| Scope |  |  | Retaining Wall Backfill
Rows
|  | Retaining Wall Backfill | dynamic | Retaining Wall Backfill
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 2.1 - Survey Set-Out |  | 2.1 - Survey Set-Out
|  | 2.2 - Excavation Permit |  | 2.2 - Excavation Permit
|  | 2.3 - Placing Fill |  | 2.3 - Placing Fill
|  | 2.4 - Groundwater |  | 2.4 - Groundwater
|  | 2.5 - Fill Placement next to Structures |  | 2.5 - Fill Placement next to Structures
|  | 2.6 - Compaction of Fill next to Structures |  | 2.6 - Compaction of Fill next to Structures
|  | 2.7 - Topsoiling (Behind Wall) |  | 2.7 - Topsoiling (Behind Wall)
|  | 2.8 - Landscape Works (Behind Wall) |  | 2.8 - Landscape Works (Behind Wall)
|  | 3.1 - Proof Rolling |  | 3.1 - Proof Rolling
|  | 3.2 - Materials Property Testing |  | 3.2 - Materials Property Testing
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Print Name: | QAV - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Position: | QAV - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Work Completed On: | Work Completed On: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
DTM-ITP-014- Water Main Relocation
| Scope |  |  | Water Main Relocation
Rows
|  | Water Main Relocation | dynamic | Water Main Relocation
Columns
|  | 1.1 - Obtain the TasWater Engineering Design Approval |  | 1.1 - Obtain the TasWater Engineering Design Approval
|  | 1.2 - Pre job-start meeting with TasWater |  | 1.2 - Pre job-start meeting with TasWater
|  | 1.3 - Apply for and obtain permit to construct |  | 1.3 - Apply for and obtain permit to construct
|  | 1.4 - Preparation and submission of construction management plan |  | 1.4 - Preparation and submission of construction management plan
|  | 1.5 - Request and schedule booking for a witness pressure test with TasWater |  | 1.5 - Request and schedule booking for a witness pressure test with TasWater
|  | 1.6 - Request and schedule the isolation and cuttover to new infrastructure |  | 1.6 - Request and schedule the isolation and cuttover to new infrastructure
|  | 1.7 - Check for correct documentation |  | 1.7 - Check for correct documentation
|  | 1.8 - Implementation of all measures and controls |  | 1.8 - Implementation of all measures and controls
|  | 2.1 - Survey Set-Out |  | 2.1 - Survey Set-Out
|  | 2.2 - Excavation Permit |  | 2.2 - Excavation Permit
|  | 2.3 - Vacuum excavation of trench |  | 2.3 - Vacuum excavation of trench
|  | 2.4 - Installation of pipework (including new property connection). |  | 2.4 - Installation of pipework (including new property connection).
|  | 2.5 - Installation of thrust blocks (temporary and permanent) |  | 2.5 - Installation of thrust blocks (temporary and permanent)
|  | 2.6 - TasWater Inspection |  | 2.6 - TasWater Inspection
|  | 2.7 - Back-fill of trench for purpose of pressure testing |  | 2.7 - Back-fill of trench for purpose of pressure testing
|  | 2.8 - Removal of old section of water main |  | 2.8 - Removal of old section of water main
|  | 3.1 - Pressure Testing of new pipework |  | 3.1 - Pressure Testing of new pipework
|  | 3.2 - Cut-Over |  | 3.2 - Cut-Over
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Print Name: | QAV - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Position: | QAV - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Work Completed On: | Work Completed On: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction