## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-004 - Earthworks Cut | itp |  |  |  | Yes | ITP-004 - Earthworks Cut | 46bb3171-5048-4e01-ba74-7b262ae04ed8
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | b9b05130-21d0-59f5-81b8-3a1a66ee3588 |  | note | Method/Description - Document Review
label | cca29099-c6de-57fd-ae2f-5ea7651289fd |  | note | Test frequency - Prior to personal starting
label | 4905a6bb-47b9-5612-ae3f-f47e06a3b0f0 |  | note | Constructor - H
label | 1f5798a0-6591-5954-918a-aee49800be2c |  | note | Verifying Records - signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | 24af5ac5-dc0f-5572-9f8f-f968599806a2 |  | note | Method/Description - Document Review
label | d029f256-64c1-5d38-8894-c6b955988ec4 |  | note | Test frequency - Prior to starting
label | 9ccc7c7c-c593-53c9-9870-a2b85c4ac74e |  | note | Constructor - H
label | 72f7fbe8-8bd4-59ac-ac7e-03030dbfa37b |  | note | Verifying Records - IFC drawings or written approval from PAB
checkpoint-status |  |  | checkpoint | 1.03 - Approved SCWMP
label | 0f4c9061-2d18-5631-8ae0-0ec860083288 |  | note | Method/Description - Document Review
label | a327f40c-0cc6-5dcc-a5dd-6af44d88cad3 |  | note | Test frequency - Once prior to works commencing
label | e23ce9b7-d559-5ade-84ab-75a9ecf1e255 |  | note | Constructor - H
label | 3080528e-d0ce-5ac5-86cf-2503bbfaeec7 |  | note | Verifying Records - Approved SCWMP
checkpoint-group |  |  | section | 2.0 During Construction
checkpoint-status |  |  | checkpoint | 2.01 - Set out extents
label | 103bcb86-e5f6-5c01-af96-35bd1d9e7fee |  | note | Method/Description - Survey/visual
label | 262daded-4c81-56e9-8f2d-3e49f5dff431 |  | note | Test frequency - Prior to Commencement
label | 1ea47dec-8e81-5dcb-a913-446cacda69f8 |  | note | Constructor - H
label | deb203b7-5718-5616-9630-a1d5c9b53cb4 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports
checkpoint-status |  |  | checkpoint | 2.02 - Verify Machine Control
label | 1eb179e8-4c86-5fa2-9225-acc058072e50 |  | note | Method/Description - Survey/visual
label | ff8ab6ca-fe21-580e-91cd-305bc4ec1caa |  | note | Test frequency - Daily
label | 0bd6ade8-f046-5723-bd0b-cff871f84ada |  | note | Constructor - W
label | 81b1d103-1a86-5f80-98b9-ade368456739 |  | note | Verifying Records - Plant Pre Starts
checkpoint-status |  |  | checkpoint | 2.03 - Assess Crest detail
label | f3ac45c9-18de-5552-a055-bfe70ec804e4 |  | note | Method/Description - Hand augers/ slope assess
label | b75a31c8-d7b1-5a3f-9647-11984d4d8ef7 |  | note | Test frequency - Prior to Excavation
label | d2943094-13b2-5e7a-a39e-0717e6228ecc |  | note | Constructor - H
label | 5cbe8ddb-a41b-53d1-8cde-c352d85b9596 |  | note | Designer - H
label | bafc3aed-08c4-5976-9598-1264d363e6e2 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04.01 - Install crest detail: Soil Nailing
label | adac4e33-95b4-5458-9ce8-697f3b3b7dbc |  | note | Method/Description - Visual Inspection
label | d9512120-644e-57a0-b43a-c5e04cd770db |  | note | Test frequency - Prior to cutting rock slope
label | 84f258ea-3834-54e0-8cbd-ed1f3850922c |  | note | Constructor - H
label | a3a10b54-2402-59ce-bb85-8f6c786ccc34 |  | note | Designer - H
label | 8aa35759-d24a-5aaa-a711-b1cb733df60c |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04.02 - Install crest detail: Erosion Matting
label | d57b4711-e40c-53cf-8d1b-f0876f8d9957 |  | note | Method/Description - Visual Inspection
label | 95465785-0b13-5703-9136-61773491d56b |  | note | Test frequency - Prior to cutting rock slope
label | 93f1b126-b28e-5388-a0bc-f4e064b993de |  | note | Constructor - H
label | c5badbe0-bac7-5e2b-93aa-25331a045951 |  | note | Designer - W
label | 5778f670-eae3-5fd7-bc03-4203a0c7e7ca |  | note | Verifying Records - Sub Contractor QA Records
checkpoint-status |  |  | checkpoint | 2.05 - Cut Face inspection: Cut Face inspection
label | acfa0d9c-0bcd-515d-a750-0c97ef4b5f5a |  | note | Method/Description - Survey check by construction team, visual inspection by designer.
label | 31f04f6c-d015-5817-98c6-d1fe5971b4ce |  | note | Test frequency - 100m2 or maximum 5m vertical cut
label | 41ae2613-b497-5a9d-a029-654d7e2bd51d |  | note | Constructor - H
label | 59fc9c46-102d-5bb7-a357-2a09a166aedf |  | note | Verifying Records - Earthworks Cut Checklist, Survey record, As-built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Cut Face inspection: Cut face material verification - Geo mapping
label | 4d6bb129-d861-5f8e-81d3-dc1f94ac6fee |  | note | Method/Description - Geo inspection and face mapping
label | a8b16777-a627-5be9-9840-c87648cdc4cf |  | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | f226a919-790e-56f6-8c3b-36bbcf89b915 |  | note | Constructor - H
label | 056b5fad-0b37-52be-a52d-471442da127d |  | note | Designer - H
label | 5b8b5c68-2bae-5e3c-824e-c2b2f5d84c39 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Install Rock Drape: Set out drape anchorages
label | 5183685a-f9a1-54de-b5a8-55d252383bd4 |  | note | Method/Description - Geo walk over
label | 2265fabb-5f12-543f-974b-43bbd5ab3478 |  | note | Test frequency - Prior to drilling
label | 8fb6da51-6d90-5d71-8c95-1facf5504a92 |  | note | Constructor - H
label | b3d8e1dc-497b-5d87-acbe-02ca013aa778 |  | note | Designer - H
label | 0cdcf132-3e26-5085-8ea2-a1f512f388e8 |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.08 - Install Rock Drape: Install anchors
label | c5eb9fb5-a4ec-5c94-b7dc-4604772bf060 |  | note | Method/Description - Drill and grout records. Stressing records.
label | dfa0837c-37da-5a6d-8c65-32929a1f1296 |  | note | Test frequency - During construction and at end
label | 6ae8403c-b05a-5a44-b2a3-25561d0b3959 |  | note | Constructor - H
label | 8258a11a-e5cc-52de-97d0-f25ba8a92110 |  | note | Designer - H
label | ebacc7f3-1f60-5c72-8025-72696e0ca23a |  | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.09 - Install Rock Drape: Install Drapes
label | fc21ffbb-bd96-598a-96b1-6db9e1946805 |  | note | Method/Description - Visual inspection
label | 8072ffbf-0279-5439-9379-5d52e34ff66b |  | note | Test frequency - During construction and at end
label | de624760-9f81-522a-9b58-c0003f7f368e |  | note | Constructor - H
label | bdff8204-3322-5084-8aab-73333ca33573 |  | note | Designer - H
label | 4cf2dc7d-1a23-5873-981a-c1c24b4001d4 |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - Install Rock Bolts
label | 87b32ff1-a65e-5141-bc7f-05d8afa61fe4 |  | note | Method/Description - Drill and grout records. Stressing records.
label | c40dcf3d-f43c-5a07-92ef-f797e8f4187b |  | note | Test frequency - During construction and at end
label | 2c83b556-60d1-58ed-ae76-55188c239b0f |  | note | Constructor - H
label | 4d079ed6-1e69-5da2-ac1b-b1da20dea177 |  | note | Designer - H
label | 9ee04451-2404-5d7e-90b8-340826f2ec8a |  | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Catch Ditch Inspection
label | 00e58ffe-037b-545d-bace-5b883e0647b3 |  | note | Method/Description - Visual inspection
label | 750aae21-4e55-55ee-95d8-d2214481286c |  | note | Test frequency - During construction and at end
label | 38c24efb-1c17-5bfc-8867-5830c39a3cdb |  | note | Constructor - W
label | 1b2daf5e-43d3-523f-9929-d91a9a0cbfdc |  | note | Designer - H
label | 49901b71-e92f-5910-92b8-f91214a6bb2b |  | note | Verifying Records - EarthworksCut Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.01 - Rock Fall Test
label | 01881ecd-5f95-53d8-9234-8808dd9fbc0a |  | note | Method/Description - Visual inspection
label | f6e238b7-83bb-57db-8393-f9fd6e598922 |  | note | Test frequency - After catch ditch is formed at each rock cutting site
label | 20517f6f-4dc0-53d7-b6cc-bda6897dc3a5 |  | note | Constructor - H
label | b50f0b20-1e92-5d53-b575-7fa220612f21 |  | note | Designer - H
label | c8176c17-9c21-5b7c-830f-603325d44830 |  | note | Verifying Records - Designer assessment Memo
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.02 - Survey As-builts
label | 96e8f962-2b54-5686-b51d-3c930ba3629b |  | note | Method/Description - Survey As-built
label | adec30b1-222c-5cca-9b84-a8fff78f3ce7 |  | note | Test frequency - During construction and at end
label | 696c0ab2-add1-5162-a27c-a6be042143f9 |  | note | Constructor - H
label | d0445372-fb8a-58cc-a492-62a96ba38b50 |  | note | Verifying Records - Digital file
checkpoint-status |  |  | checkpoint | 3.03 - Monitoring Data
label | a4a65e69-72d3-54bd-bff7-c79b0236a9e3 |  | note | Method/Description - Visual inspection and review of monitoring data review.
label | 849a4e4b-61b2-5118-bf7b-39abb9f6c1c8 |  | note | Test frequency - End of construction
label | 3bcde90b-3f05-5b5a-b4d3-04605f0478fa |  | note | Constructor - H
label | 3e6bdc87-1ffa-51a4-b7e2-789510c68974 |  | note | Designer - H
label | 5204e30e-6e3d-59f7-8aaa-6c8263b29352 |  | note | Verifying Records - Digital file
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Red Line Mark Ups
label | ba02192f-3b0c-5b84-a1cd-58a1b7a4a369 |  | note | Method/Description - Red Pen Mark up
label | b040b799-4cd0-5bc0-984a-70a0dc98eace |  | note | Test frequency - End of construction
label | cdedf424-4590-5f49-a9f5-e4f800f21a12 |  | note | Constructor - H
label | 8c2ed140-05e6-564e-84d1-1868fec32d9d |  | note | Designer - W
label | ed08f1da-48e6-5d19-83b3-e1012293eca4 |  | note | Verifying Records - Red Pen mark ups
checkpoint-group |  |  | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint-status |  |  | checkpoint | ITP Close-Out by
label | 8daf5f14-6013-5009-b236-3638f2c275a6 |  | note | Site Engineer/Project Engineer
label | 8bd05865-687b-56e2-91f9-d1b0d8ddae3e |  | note | Zone Manager Approval
label | 71e00a12-d4ba-542a-b192-34ec02325679 |  | note | Construction Manager Approval
label | 1469c7f4-a2de-515e-be40-4a582d94c73a |  | note | Quality Manager Approval
date | 7eb7055c-3586-51f9-9375-bb33d9b0c07a |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | ITP-014 - Fill 14 Rev 3 | itp |  |  |  | Yes | ITP-014 - Fill 14 Rev 3 | 4c6f4dd4-7e6b-43b4-8142-d2c861e040ad
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - CWP
label | e089dd61-1536-5853-b386-da5ac012a822 |  | note | Method/Description - Document Review
label | 39acd8e3-3204-52a1-8063-8a84de727505 |  | note | Test frequency - Prior to personal starting
label | fb74a4ec-b970-5a82-9438-0371ff2c4f60 |  | note | Contractor - H
label | 24e19b5d-b714-51a0-871e-2fc4077a520b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.03 - IFC's specification
label | 4257e64a-85d4-58d9-ac5c-ff666a5cfb32 |  | note | Method/Description - Document Review
label | 5230702f-d278-5658-a1d3-b49fa06541f8 |  | note | Test frequency - Prior to works commencing
label | 7f1cfa8a-1324-5bbe-8e81-b61f3faa9861 |  | note | Contractor - H
label | 29646630-3fb9-533d-b171-9e4cf8f44811 |  | note | Designer - H
label | a31745d4-ff53-5865-bb8f-f5113a7501f3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - IFC drawings
label | 306054e1-5f7e-5a9e-9293-a2d5c4f460ea |  | note | Method/Description - Document Review
label | 9fef44a4-1c56-50e4-bd9c-758c6a3e91de |  | note | Test frequency - Prior to works commencing
label | ede6e919-9c31-590b-a63f-de014264a326 |  | note | Contractor - H
label | 17e771b9-78be-537c-9d0f-a2ce791868cf |  | note | Designer - H
label | 815c58e5-413d-52ba-841c-7c25c85b51cc |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Approved earthworks model
label | 01ed7ab8-e726-5289-baf1-a02abb6ed932 |  | note | Method/Description - Document Review
label | 14c5379d-7ee1-5304-9c5b-3f018a80d31d |  | note | Test frequency - Every new Earthworks Model and prior to work commencing
label | dbbf0570-b9dd-5c71-832a-19a7885904a3 |  | note | Contractor - H
label | 36c8e97f-e357-50b5-b7a8-7c1a3cc5021a |  | note | Designer - H
label | 20908a2c-eb88-5181-b450-52efe7c43b5a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.06 - Approval of stockpile location
label | 9b76d029-9a17-5010-a234-f64302f8b71f |  | note | Method/Description - Document Review & Approval
label | 197af4fe-a59b-500d-8df5-16c49792cc02 |  | note | Test frequency - Prior to works commencing
label | ca87598a-5c60-504a-b9b2-2a1df578b983 |  | note | Contractor - H
label | cd0c588b-b973-51b0-a4b7-2e2e82094b69 |  | note | Designer - H
label | 170dea46-b59b-5c8f-8531-5e621947838d |  | note | Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.07 - Installation of prefabricated vertical drains sequence and method
label | 85400be2-a428-5805-98bc-800258186bf2 |  | note | Method/Description - Document Review & Approval
label | 8c3e6ade-519a-5f6a-a625-19f8909ed9ab |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | 847212ec-70ca-50f2-9431-e056b4149ae6 |  | note | Contractor - H
label | 4aae23c8-b4ce-5f8a-bfcf-369ed9d8b142 |  | note | Designer - H
label | 1dc449ba-d1b8-5c9f-82b2-fd308a2413d4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - CWP approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.08 - PVD sample
label | 0eee56b4-55ac-5546-b040-654ba8683847 |  | note | Method/Description - Approval
label | 80081bcd-1079-5c4a-8387-329e87e5628a |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | c611e8e2-079a-55d5-988e-8cd0d0803aa6 |  | note | Contractor - H
label | a7cf3122-eea5-5164-aabe-66226997eb8a |  | note | Designer - H
label | 638c7a7f-872e-50ac-a2d3-e8032f4695e4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - PVD sample approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material
label | fe3d3893-9b75-5b64-a04e-1d86acb4c29b |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 3495b883-135d-5188-a0d3-d10d9d52de1d |  | note | Test frequency - 1 Per 20,000m3 (Structural Fill)
label | 67342cb9-e379-5628-a679-ce5a8db057c2 |  | note | Contractor - H
label | a28c4d46-5800-5e2f-874f-026ddf166bf7 |  | note | Designer - R
label | 43f46eb8-2a53-5e14-bb91-3c6e4f968bc8 |  | note | Lab - I
label | 08e9d96a-e0bb-5542-8746-18d30c8a2f2d |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.02 - Atterberg limits test for Structural Fill Material
label | 8efac5e3-3f65-5738-b1ef-ec1292709d9b |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 69535725-4c0e-5f33-8524-84264d367b24 |  | note | Test frequency - 2 Per 20,000m3 (Structural Fill)
label | a7c3cdf6-e207-5b7c-94c0-021fa86c896c |  | note | Contractor - H
label | 589c06d6-31ed-5107-8627-2f07da1e5e18 |  | note | Designer - R
label | 5a220030-7b33-59f4-a579-fbbdf4a7dcc2 |  | note | Lab - I
label | 0ffef775-f465-53b4-a18c-cb1c8b8f6766 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
label | 69d19818-b469-529b-9ef7-aff4c821fe86 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | b785a442-961b-5b94-8af8-151734794fbd |  | note | Test frequency - 1 test per 20,000m3
label | 9dc921ba-1c25-579d-91bb-dc10a63c0afb |  | note | Contractor - H
label | 8c71261a-99b2-5147-b6ef-5ae27e292320 |  | note | Designer - R
label | 84d35f5f-7d9c-5a6e-8f30-54288b08faf8 |  | note | Lab - I
label | 7a182bf3-cccc-5a7c-8f91-8121237d9a3c |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
label | c59817c9-50be-57fa-8a32-5c7c76032d5e |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 76ac39ed-9b7a-59a0-b5ac-3bb48e1f216e |  | note | Test frequency - 1 test per 20,000m3
label | 6933c107-6455-5372-9895-8562ca47e33a |  | note | Contractor - H
label | 75fb34ac-acdf-5390-bec7-ea6b8ccb8b3e |  | note | Designer - H
label | b84d75df-09d6-5625-82b4-5dcc25d460ea |  | note | Lab - I
label | bf3fd3b6-0a3a-54e8-82d2-93b93a3b84bb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Drainage blanket
label | 5f61ab54-103f-57e4-b3d5-36ed0ad1c60e |  | note | Method/Description - Designer Approval
label | 05a674f2-7e45-5ea9-bc15-ba0ac76a05cf |  | note | Test frequency - Once Prior to commence
label | decef77c-f13e-5384-af72-010f0e562add |  | note | Contractor - H
label | 550c5d7f-12c3-57f0-8220-b741f2afe396 |  | note | Designer - R
label | eed25f06-ee66-51fe-8fcd-4c2230e42877 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.06 - 40/20 drainage material
label | 2aad36c5-3178-5d0c-b563-cea580cd6ca9 |  | note | Method/Description - Designer Approval
label | 1bb11428-cc48-5cb8-9500-5416e5d302a9 |  | note | Test frequency - Once Prior to commence
label | 70f7244d-d97b-57fa-ba1f-11ca991144e6 |  | note | Contractor - H
label | 93dcab24-a726-5715-a574-d685ab37c873 |  | note | Designer - R
label | 69f55381-5238-5045-8214-2b52b33454b8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.07 - High Strength Geo Cloth
label | cc42d98a-b6e1-545c-a3e8-a8f0711fb4d7 |  | note | Method/Description - Designer Approval
label | ba53d346-cff1-5f5f-9c68-4435402ee6e1 |  | note | Test frequency - Once Prior to commence
label | 1811fe65-9427-59db-889b-58dc829be190 |  | note | Contractor - H
label | d39fbbec-30d7-5c3f-8345-7aca5985147a |  | note | Designer - R
label | de6d87a0-7015-588a-ae4a-9848e89f27f4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint-status |  |  | checkpoint | 2.08 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | 4fe0414f-4239-55ef-a22c-522af0dbe57a |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 9af2b779-18d4-5639-b763-35fc911342e9 |  | note | Test frequency - Source approval 3 no. tests
label | 84bc0c4c-e53d-5bdd-8ea2-8e0f713d599f |  | note | Contractor - H
label | be7c19d5-d59b-577a-b17e-1340b30702ae |  | note | Designer - R
label | 92b1ceab-f0f3-5745-9dd7-568ee317fc8f |  | note | Lab - I
label | ed72e9b7-06b2-5fef-8081-5fd20bbf7445 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.09 - Particle size distribution (PSD) Test for GAP 65 material
label | 6df844d5-c6e5-5b50-bc97-f066190d8d5f |  | note | Method/Description - NZS 4402:1986, Test 2.8
label | 2024b29f-6e6e-5046-a5b1-d068b202c155 |  | note | Test frequency - Source approval 3 no. tests then every 2000m3.
label | 81dd4ea6-c9f3-535b-b8a4-e25de9ca5bc7 |  | note | Contractor - H
label | da3423e1-4912-559a-a70a-22c67be079e6 |  | note | Designer - H
label | 34e401da-14b0-5355-909b-1fab55def249 |  | note | Lab - I
label | ffc35911-fefb-5f3c-81d9-9f1138519e2a |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Permeability test for GAP 65 material
label | abb288ed-94c4-565a-bcbe-80a7a9498f05 |  | note | Method/Description - ASTM D5084 - 16a
label | 667c33d2-16ea-59ad-b248-0140ab162dae |  | note | Test frequency - Source approval 3 no. tests
label | 8a353e9d-0b0c-5277-bc4c-19a6ae765ccd |  | note | Contractor - H
label | 3461238d-3066-5158-86e0-f70bf1338b73 |  | note | Designer - H
label | e5afa4ec-f602-5c85-b1f6-4e9dc54888f5 |  | note | Lab - I
label | ccbdcac9-77d7-502c-b0c6-8af78eb7f154 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Material approval of prefabricated vertical drains (PVD). The PVDs shall consist of a continuous plastic drainage core wrapped in a non-woven geotextile material. The geotextile wrap shall be tight around the core and shall be securely seamed in a manner that will not introduce any new materials nor present an obstruction that will impede flow in the channels of the core. PVDs shall be produced by a manufacturer with an in-place quality control program which is monitored by an independent third party testing organization.
label | 3e8c1bb0-c1ab-5fb5-89b8-3ef7172e6251 |  | note | Method/Description - Document Review & Approval
label | fd487ad6-02d2-5418-bd50-438713622a49 |  | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
label | 22746887-54ff-51c8-82f9-880c730c907a |  | note | Contractor - H
label | e094b828-fa6e-514d-9556-53061f6e13e2 |  | note | Designer - H
label | 983be9dc-0e75-51d3-9080-11838c3f6709 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material approval, Material test certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Delivery of prefabricated vertical drains (PVD)
label | c4d0f25b-c01c-55f0-ac5d-da60e709be1c |  | note | Method/Description - Inspection
label | e91f0f77-e1e1-5a3e-b754-e0fd3b4c509c |  | note | Test frequency - Each delivery
label | 37198f97-9691-5687-98f1-5de475b20e13 |  | note | Contractor - H
label | d3b190cb-bdc8-58a7-94dc-e8757bfd86a6 |  | note | Designer - R
label | def2bcb4-5b54-58c2-bd1e-b67895b50ca0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Product name and identification
label | 69194214-b8dd-5492-a6fd-adf96ae38b13 |  | note | ○ Date of manufacture
label | 39120593-16c7-526d-a9c0-756e3d8a250e |  | note | ○ Lot or control numbers
label | b68aedef-2480-53fc-a83c-ba6abb04e1da |  | note | ○ Name and address of producer/supplier
label | 210d1a1d-b0d4-511c-9de2-9ca121ad46ab |  | note | ○ Manufacturer’s certificate
label | 202807af-e5b8-5897-89f7-974afbafb89a |  | note | ○ Material Delivery Inspection Checklist
checkpoint-status |  |  | checkpoint | 2.13 - Visual inspection - separation geotextiles, basal reinforcement
label | 1bd88497-d9fb-5902-84bb-cfdc5803aee2 |  | note | Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration.
label | 71eb19da-0af6-507b-98b1-2e074189508e |  | note | Test frequency - Check each lot (1 roll)
label | d2cc6a8e-ea17-5dd1-81ee-362bb5e76a6d |  | note | Contractor - H
label | e39e4363-a496-551a-9b40-bb8b6c8098b8 |  | note | Designer - H
label | 3ab53a30-a262-5f5d-99ad-0793e7430328 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.1 Pre-filling
checkpoint-status |  |  | checkpoint | 3.1.1 - The installation trail of prefabricated vertical drains (PVD) shall be conducted.
label | 97f9bb0b-efa0-5e7e-9a39-524fca722d8e |  | note | Method/Description - Inspection
label | e775fc77-3d94-5aba-bd13-e6f88a90f925 |  | note | Test frequency - Prior to Commencement
label | 1661fe29-029e-5561-bc4e-c6cbcc706096 |  | note | Contractor - H
label | e6cebe15-0755-5252-bb65-539748cf44ec |  | note | Designer - H
label | 6dcf5206-64ff-5c45-bdad-5893da52433e |  | note | Verifying Records Checklists, Test and Supplier Certificates - PVD installation trial approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.2 - Set out extents of fill and check against design
label | 25cac1dc-aace-5742-9749-f1f60709f72b |  | note | Method/Description - Survey/visual
label | 325250a9-1fea-53ba-a6fd-3f9cc2992dcb |  | note | Test frequency - Prior to Commencement
label | 3e4fec7a-f0c0-5fef-84b4-d44b36b4a27c |  | note | Contractor - W
label | c69a12d2-db03-5683-9bc5-9bc4c008074f |  | note | Verifying Records Checklists, Test and Supplier Certificates -
checkpoint-status |  |  | checkpoint | 3.1.3 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | 361d3fcd-5761-5969-b127-8f78ac70eec6 |  | note | Method/Description - Survey/visual
label | 32a28ac9-03ff-5114-a365-62d5b468379f |  | note | Test frequency - Prior to Commencement
label | 94fb3fe3-284e-5f1f-b1b3-c7a605682912 |  | note | Contractor - W
label | 19deee23-2985-533c-91d5-1b2ba15f919a |  | note | Verifying Records Checklists, Test and Supplier Certificates -
checkpoint-status |  |  | checkpoint | 3.1.4 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots.
label | 1a348236-b66a-5bd4-8e38-49fb771503d0 |  | note | Method/Description - Survey/visual
label | dd07b0db-1b64-5554-996c-13f88aeb70ce |  | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas
label | 4cefef70-d70b-5f2f-bd0a-9dd8aaf9a7af |  | note | Contractor - H
label | 434a115a-1bb4-50fa-b482-55f18e55ab9e |  | note | Designer - H
label | 2300c56a-cfa5-5688-8427-01c065d552f5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Lead
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.5 - Designer witness of in-situ subgrade prior to filling
label | bd8a8c5f-6389-5d13-8c98-1be5295a12aa |  | note | Method/Description - Inspection
label | 33e3c142-ebd8-576e-b307-69c7f771e120 |  | note | Test frequency - 100% subgrade inspection
label | 79406ac8-c103-5021-a391-bcd811ea7178 |  | note | Contractor - H
label | 9706c16a-b806-557f-b718-5a5485afc829 |  | note | Designer - H
label | 1c2b0ef5-892e-57c8-bcdd-b0cb4f179983 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.6 - Undercuts Inspection
label | 1c92114b-c3a2-5ff5-bf14-380ce17efb4e |  | note | Method/Description - Visual inspection
label | 8cc3f98a-7992-5c34-a970-aa9b90fd9d6c |  | note | Test frequency - 100% of works area
label | 9d38d27f-ca7d-590b-8db5-af470db6d917 |  | note | Contractor - H
label | 80624815-64ab-54b6-b308-94b8f8f55539 |  | note | Designer - H
label | dba31996-79a8-5d7d-bd7e-c377ccdaa919 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.7 - When required Undercuts (cut-to-fill operations)
label | 573f101f-9c92-5dd6-9ac1-23ee73f3074d |  | note | Method/Description - Visual inspection
label | ebc841ad-eda4-51ef-9e98-314cc1ecac4e |  | note | Test frequency - Prior to Filling
label | 631ebf2c-da87-5e05-bb1c-8398efa8f066 |  | note | Contractor - H
label | d751f6fa-d6dc-5441-b9f7-98fd09470c69 |  | note | Designer - H
label | 816cda5f-7d1d-5433-ac80-6adf6a0a143f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.8 - Piles
label | 9e292be0-218c-5ad6-83fc-39a460da28ec |  | note | Method/Description - Inspection
label | 89558d2d-a6af-598b-afac-4fd569abfea0 |  | note | Test frequency - Ongoing
label | bb1043b4-a984-5987-9ffb-3b2344f37241 |  | note | Contractor - W
label | 812ce363-a49f-5498-88ac-1455a3fd3dfa |  | note | Designer - R
label | f4e19a1d-9781-59ef-990b-14e71c021e0b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
checkpoint-status |  |  | checkpoint | 3.1.9 - Installation of prefabricated vertical drains (PVD). PVDs shall be installed after the sand blanket is placed and before the installation of high strength geotextile (basal reinforcement) and the embankment fill. The proposed locations of the PVDs shall be marked out in accordance with the Drawings.
label | 02772269-8cd9-5812-8490-49c9fb5ea26c |  | note | Method/Description - Inspection
label | fcaa78c8-eaec-5af0-8068-8694c820285b |  | note | Test frequency - Each installation of vertical drains
label | 064360f2-54db-57e9-a4aa-8667c2c68884 |  | note | Contractor - I
label | 920d3cd9-9abb-5771-bb1d-9879caee64c9 |  | note | Designer - I
label | a828426c-18b1-5d81-bc8e-0ef079211b3a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Vertical drains Installation Checklist
checkpoint-status |  |  | checkpoint | 3.1.10 - Basal reinforcement installation
label | 22501e99-b98a-533e-bab5-2dec0e3e01c4 |  | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
label | b9f3449b-b28c-52de-9d81-d6feb598e690 |  | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
label | 78056acd-72a3-5086-ad48-99da7b326ea6 |  | note | Contractor - H
label | 5fd9e1e3-4c81-584e-a6df-82f98dacffa5 |  | note | Designer - H
label | 8d7c27b1-582a-5788-9d77-b4341a49eb13 |  | note | Verifying Records Checklists, Test and Supplier Certificates -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.11 - Drainage blanket installation
label | e66d49e0-6a2c-5dba-86c0-571245b0190e |  | note | Method/Description - Visual inspection
label | 468681a3-e2b8-5559-9dcc-66c5968da39a |  | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
label | 3101edb3-e15e-5a0e-a8cf-2ef9b2b70ee0 |  | note | Contractor - H
label | 29893417-818a-5baa-ac98-58662688a3fa |  | note | Designer - H
label | 32daacef-533c-5bd3-9312-0d9c1ac5f204 |  | note | Verifying Records Checklists, Test and Supplier Certificates -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.12 - Monitoring Instrumentation
label | e2a4e63a-4b09-5aad-aed8-1a1637c9a195 |  | note | Method/Description - Survey/ data logging
label | beb620e3-0d13-5345-aa39-e51abca915bd |  | note | Test frequency - Ongoing
label | 7414e67b-d4c9-5f2c-b4d3-7c1f33df2da0 |  | note | Contractor - W
label | a5ad977e-4b9c-5ca9-bdc7-db37e3b8fd20 |  | note | Designer - R
label | 07952f33-9b11-5337-b4e0-37461539d0f9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
checkpoint-group |  |  | section | 3.2 Fill construction
checkpoint-status |  |  | checkpoint | 3.2.1 - Filling for the first 5m of Fill
label | 0d8da633-65bb-599a-b6c0-b002435afb62 |  | note | Method/Description - Visual inspection
label | 58eb5e2e-840a-56ce-a71b-42f823542139 |  | note | Test frequency - Daily
label | ede1dd0c-957e-5d6e-97ee-f9f01f364642 |  | note | Contractor - H
label | 9d95cad0-2ece-5f3c-b427-9aa1b730f5ce |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report/ UAV Scan
checkpoint-status |  |  | checkpoint | 3.2.2 - Hold filling operations for a period of two months
label | ff990dcf-077e-5fb4-ac6f-76f0372a01fa |  | note | Method/Description - Monitoring data records
label | 1b93eb8f-b083-5cdf-bd41-030dfd2360cf |  | note | Test frequency - Daily
label | 6f94c824-74cd-5099-8ca0-cdefa294f20b |  | note | Contractor - H
label | dea990f0-55b6-5065-9874-9039d72c47df |  | note | Designer - H
label | 1e53fcf8-4ab0-5c2a-8d99-45583015dbd8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP-012 - Concrete Culvert | itp |  |  |  | Yes | ITP-017 - Concrete Culvert 17 | 4f45d31a-7812-407a-96f9-09c844036807
checkpoint-group |  |  | section | 1.1.0 Pre-construction approvals
checkpoint-status |  |  | checkpoint | 1.1.1 - Construction Environmental Management Plan
label | 9228b49e-5aee-50d3-942b-513a1e401c62 |  | note | Method/Description - Document Review
label | 5377f383-17ff-587f-8f81-1473fcf043e6 |  | note | Test frequency - Prior to work starting
label | ec45cb7e-6dfa-5859-baa1-f3d73975ea0a |  | note | Contractor - H
label | 75e814f9-98ac-5a60-b5b6-2b847c137ed4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint-status |  |  | checkpoint | 1.1.2 - Construction Work Plan
label | 87ecf765-4293-5159-912e-f58d4aa9e29c |  | note | Method/Description - Document Review
label | 43582105-9874-562e-a056-f5fef5f7bebe |  | note | Test frequency - Prior to work starting
label | 577042e6-c79f-572f-a20c-2060ec37af0f |  | note | Contractor - H
label | 5c2d71bc-4f66-5599-8f1f-c89960790661 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.1.3 - IANZ accredited testing organisation
label | d73622e4-339e-57f0-8976-0951e2f36dba |  | note | Method/Description - Document Review
label | 0cfa570d-3e93-5252-968e-96862152a449 |  | note | Test frequency - Once prior to works commencing
label | b5ef69a8-7b63-5c04-a0db-11432dc931b5 |  | note | Contractor - H
label | 57277e7f-aec3-5eaa-ba65-bfc85d2bf0ee |  | note | Designer - H
label | 49551789-7e21-5026-b6bf-2296c8af16ad |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.4 - IFC's specification
label | a2b1b20e-abef-5ee8-bf13-ba4a3c21c1ad |  | note | Method/Description - Document Review
label | f5842c77-6e5a-5e98-aeec-edf052fa72a2 |  | note | Test frequency - Once prior to works commencing
label | a7b08a26-79f9-585e-9f62-84ec09d1c8c0 |  | note | Contractor - H
label | da4d491c-8d62-5680-9df1-96017b9bf004 |  | note | Designer - H
label | fb143926-042d-58fc-8ca4-eec66f248683 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.5 - IFC drawings
label | d02bfaf1-7299-5414-b0e0-98744319620b |  | note | Method/Description - Document Review
label | fec2408c-f0cd-5a7f-a5b7-0b1e81716e06 |  | note | Test frequency - Once prior to works commencing
label | f9724dbf-bbef-5a78-a688-caa65e6b1b06 |  | note | Contractor - H
label | f09a0e65-2f7a-594b-aee0-d5908c89cdd7 |  | note | Designer - H
label | 25fe20b3-1c16-5164-820f-b435da814784 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.6 - Approved Drainage Strings
label | 859362a7-67dc-5889-b3ca-caf93ee2434c |  | note | Method/Description - Document Review
label | 50b400a9-6b28-55ac-bcf7-162f72351b1f |  | note | Test frequency - Every new Drainage Line and prior to work commencing
label | 7219ff0f-4965-5490-b4b6-c12ceb794f6a |  | note | Contractor - H
label | 86b0c31e-7352-5b3d-9ad9-97b67ae08f6c |  | note | Designer - H
label | 49771ed7-1726-5648-b0a6-189e97078026 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.7 - Approval of stockpile location
label | 642f99c1-08c7-506b-8db2-2883f207768e |  | note | Method/Description - Document Review & Approval
label | d546ad01-1270-5ac6-a636-f549e73d0c2b |  | note | Test frequency - Prior to works commencing
label | 37a316ed-bb20-5d4e-a168-6bf6c2b76503 |  | note | Contractor - H
label | 78dd2113-9c68-5c3b-8803-a60c3627460d |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 1.2.0 Material compliance
checkpoint-status |  |  | checkpoint | 1.2.1 - Materials Approval- pipes and fittings
label | 52bd9155-494f-50d7-9d15-f147933cb9e2 |  | note | Method/Description - Material Submittal to DSR review
label | 8f9fee52-df73-5037-ae6e-15486c792166 |  | note | Test frequency - Prior to works commencing
label | 0bbd4002-a9a9-5e67-95ad-5336d271823e |  | note | Contractor - H
label | d45cc9dd-3a9c-5658-8ee3-f4f279645b18 |  | note | Designer - H
label | b3a4b655-16ee-5511-9857-d63a707641ea |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.2 - Materials Delivery- pipes and fittings
label | cc85ecff-a0a9-5dff-9f0d-62f3ed39471f |  | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | fb6948fc-a24a-5291-ba8d-40f8b19a9977 |  | note | Test frequency - Each delivery to site
label | 36a9fc4a-073f-5fb2-b911-50585553b5ad |  | note | Contractor - H
label | 16b99f2f-7550-5378-9ea1-c0e18cdd3938 |  | note | Designer - R
label | a8b26609-a72c-5441-8fea-d0a3727e055e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint-status |  |  | checkpoint | 1.2.3 - Materials Approval – pre-cast Concrete Manhole units and wingwalls
label | 6127b00d-50de-50be-92d7-9842234e7627 |  | note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
label | 21e84d09-0dd6-5311-b066-688534eeca4b |  | note | Test frequency - Prior to works commencing
label | 97cbce36-4cb4-5ede-8b72-da68dbed02b2 |  | note | Contractor - H
label | cc179de9-a7a0-51e4-9176-705d7e1bf48a |  | note | Designer - H
label | a002bb78-6be2-584f-bf16-fab19d6b0b3b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.4 - Materials Delivery – pre-cast Concrete Manhole units and wingwalls
label | 86342b20-ceb0-5782-9c67-c639fa47c4a5 |  | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | be977e92-5547-5fe0-9598-a70a11a6f493 |  | note | Test frequency - Each delivery to site
label | 9bbea42a-4985-5447-908b-4be23dfb7261 |  | note | Contractor - H
label | ff97a6ad-39fc-54d3-aabe-d8225f1a9a24 |  | note | Designer - R
label | de9a1911-a267-57cb-91b1-39f1b813891e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint-status |  |  | checkpoint | 1.2.5 - Materials Delivery – Lids and Grates for Manholes
label | 65f1536e-47d5-5d9f-8ba7-43e351273f6e |  | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
label | 2cd7c8dd-710e-5143-9509-543b9368f5c6 |  | note | Test frequency - Each delivery to site
label | 1dcc800b-9f9b-54b4-8b5d-162fe72c0b8f |  | note | Contractor - H
label | 6a1f3567-b35c-5172-9d6e-8edf6b5b96b6 |  | note | Designer - R
label | 8cd22a33-3a32-512c-bf5b-3748f591d44a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
checkpoint-status |  |  | checkpoint | 1.2.6 - Materials Approval – Weathering Index for Bedding, Haunch Material AP20 aggregate
label | 83436569-fa71-5144-aa61-2d89e282a663 |  | note | Method/Description - Weathering Index test
label | 7bc3ed3a-3ca9-5c2d-8836-200c464ab9a1 |  | note | Test frequency - Two tests per source 4 weeks before use in the works
label | 8582ab00-843f-5371-aa75-07b417e65dd8 |  | note | Contractor - H
label | 4203cd20-24ce-53a7-8d67-07d728e562cf |  | note | Designer - R
label | efc084eb-7a7a-5c1d-b8bd-15648d90c3a1 |  | note | Lab - I
label | 70aaf10c-a346-5aab-bc91-41112d8f53c5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
checkpoint-status |  |  | checkpoint | 1.2.7 - Materials Approval – Crushing Resistance for Bedding, Haunch Material AP20 aggregate
label | 25d5cdf5-53b6-5069-84f3-df1fea371e38 |  | note | Method/Description - Crushing Resistance test
label | 8b0e5de7-e311-520a-bdcd-31fa19e427c1 |  | note | Test frequency - Two tests per source 4 weeks before use in the works
label | 339a17bb-ac56-58dd-a213-d1b3beff7630 |  | note | Contractor - H
label | ef21b36e-4f63-56e5-bfe9-ffc1742911d7 |  | note | Designer - R
label | ea842e33-c074-55d0-a5a1-08194f2d3d06 |  | note | Lab - I
label | 0cae91a1-d7d5-57a7-8c8a-56833eb9a809 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
checkpoint-status |  |  | checkpoint | 1.2.8 - Materials Delivery – Grading for Bedding, Haunch Material AP20 aggregate
label | bc5f7429-197c-5f43-806c-a083bff36ec1 |  | note | Method/Description - Grading Testing Inspection the new Delivery and review the Dockets and test certificates
label | b5443b02-cb36-54f0-9d3f-a5b2b509e24f |  | note | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
label | 58ec9069-dae4-53b2-8ce5-75fd90b44de2 |  | note | Contractor - H
label | c5407b9f-e654-5447-9d66-8661bac1269a |  | note | Designer - R
label | e04ed7d5-504d-50fd-85d2-6fe379953ae2 |  | note | Lab - I
label | 4a5e922c-0e9d-582b-bb3b-85672a1431bc |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
checkpoint-status |  |  | checkpoint | 1.2.9 - Materials Approval – Maximum Dry Density for Bedding, Haunching AP20 Aggregate
label | cd4baa4b-91f6-5c0a-ace9-cd6ee27b175b |  | note | Method/Description - Standard MDD Test
label | a6a8d166-d53c-573f-881f-05defcc1407c |  | note | Test frequency - 3 no. tests per source with minimum 5 points
label | 86b62a4d-06ff-5f12-ba8b-67ba02bd1470 |  | note | Contractor - H
label | 0c0daa9c-346a-540f-8493-22ce36bc0266 |  | note | Designer - R
label | 078c2dc3-2c7c-51db-a567-9c6a6ae74c88 |  | note | Lab - I
label | 344073d1-f3ef-5f45-a097-fe1bba1fef63 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 1.2.10 - Materials - Structural Fill for Overlay Zones (AP65)
label | 8fedcc53-0875-509b-8b60-6a5c450f37ab |  | note | Method/Description - As Per MMA-CON-CMA-ITP-31067
label | f8e2b0f3-9dc2-55d4-a121-8319ba8be70e |  | note | Test frequency - As Per MMA-CON-CMA-ITP-31067
label | 7d87816f-8a30-5fc6-b191-8cfe4b067382 |  | note | Contractor - H
label | 4c70234c-da14-5be1-9585-3a68fe8d4284 |  | note | Designer - R
label | 04c98a3e-da02-5b42-85c7-7a839f249836 |  | note | Lab - I
label | 530fc226-ce63-512c-97b3-7742c4f04065 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
checkpoint-status |  |  | checkpoint | 1.2.11 - Material Approval – Rip Rap
label | f29bbd4a-58c3-518b-bfa2-dd9bb2369659 |  | note | Method/Description - Test
label | 579e6197-b2f2-51a9-9cb6-349506b7c731 |  | note | Test frequency - Prior to works commencing
label | 650c2dc0-f9a1-5372-894f-2f502109c62f |  | note | Contractor - H
label | ec637ec8-7e7c-56b7-a74a-8fb29f7243b7 |  | note | Designer - R
label | cf22aa9f-e7dd-56ac-ae42-3228ffeae010 |  | note | Lab - I
label | 5b87d090-3971-51fa-b9e4-8d9550c84264 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.12 - Materials Delivery – Weathering Index of a Coarse Aggregate for Rip Rap
label | 76d76450-aa41-57a2-b65a-f7469001594c |  | note | Method/Description - Weathering Index test
label | 5dd95292-dc1f-5a31-8582-e3dc1b982f05 |  | note | Test frequency - One test per 1000 m3
label | 2299bdab-318f-599f-beb9-fab2b24ab1d5 |  | note | Contractor - H
label | c29c1dd3-e6f5-5924-a8ba-2fb0916a57fb |  | note | Designer - R
label | 084e7d2d-a7dd-5dde-8c31-521cde127c0c |  | note | Lab - I
label | f1ef77e9-68e0-5c4d-b0a6-bebefce552d3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
checkpoint-status |  |  | checkpoint | 1.2.13 - Materials Approval – Crushing Resistance of Coarse Aggregate for Rip Rap
label | ace74ae8-bb30-53f5-9cba-38fc3b840177 |  | note | Method/Description - Crushing Resistance test
label | e9c655c2-b83d-50d2-abd6-988cecfd500b |  | note | Test frequency - One test per 1000 m3
label | 09add22f-c38c-5c33-9d65-33561b80bb8b |  | note | Contractor - H
label | 12b6174a-ab9a-5ac6-9414-4752329ddf76 |  | note | Designer - R
label | 77130f70-ebb3-59c4-9470-ebc25bde8cf0 |  | note | Lab - I
label | 56c5d09e-4671-54e3-ab99-ec26663198ae |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
checkpoint-status |  |  | checkpoint | 1.2.14 - Materials Approval – Solid Density of Aggregate for Rip Rap
label | 16241c37-b56e-5992-aa1b-aacff7797c63 |  | note | Method/Description - Solid Density of Aggregate test
label | b3fe0262-8281-51bb-bd7a-2eb3aa0706f3 |  | note | Test frequency - One test per 1000 m3
label | 35389f48-0b1f-5623-aa22-cb338b069eb3 |  | note | Contractor - H
label | 6b4b9f0f-ccf2-5407-b7a7-bc629d4eb14e |  | note | Designer - R
label | ce520bfb-c4bb-56db-ac5e-b62d82e4c5a7 |  | note | Lab - I
label | 04712e61-9d90-5cf9-81ad-dea279d7b4f7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Solid Density of Aggregate test Report
checkpoint-status |  |  | checkpoint | 1.2.15 - Materials Delivery – Grading for Rip Rap
label | 418d53d7-b473-5e55-9394-69829ce1f519 |  | note | Method/Description - Grading Testing
label | ad12a285-38e9-5200-875f-2de03a60615c |  | note | Test frequency - 1 per 500 m3
label | 324efc51-a05f-5244-9a3a-89ff808d6bdb |  | note | Contractor - H
label | 5a691c0b-f3a1-542f-9d48-0b8b9f0e2bb1 |  | note | Designer - R
label | 93cf2d6e-d631-5297-be5b-7cccebca74df |  | note | Lab - I
label | ab37d86c-5690-5391-b799-11d45f798d9e |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
checkpoint-status |  |  | checkpoint | 1.2.16 - Materials Approval –Point Load Strength for Rip Rap
label | a60cabeb-6df7-5495-84a9-1dc7d01b2c3d |  | note | Method/Description - Point Load Strength test
label | 78605a8d-9ff1-5c4a-bbf1-0edfd45b279d |  | note | Test frequency - One test per 1000 m3
label | 3a2784c2-123b-5657-aad3-25765a771a21 |  | note | Contractor - H
label | bdfc2831-7f77-5018-adc1-7bc743b52b93 |  | note | Designer - R
label | f5ce3993-0879-5921-af5a-678877962c29 |  | note | Lab - I
label | 603d2c75-6a46-5f90-8006-4e818479e54e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Point Load Strength test Report
checkpoint-status |  |  | checkpoint | 1.2.17 - Materials Delivery – UCS Rock for Rip Rap
label | a0050bb9-62a2-5f6e-bcf5-ef037ba1c3d1 |  | note | Method/Description - UCS Rock Test
label | c05cef0c-ff14-55de-96a3-417ee73d3832 |  | note | Test frequency - One test per 1000 m3
label | 748ed59f-a8cb-531a-a778-4854e6f862be |  | note | Contractor - H
label | e35fa1c1-981f-5fe1-82e9-0828acba424f |  | note | Designer - R
label | fbf26c5a-2355-5b59-8623-32c70741ba18 |  | note | Lab - I
label | 2d562601-9907-5560-afa8-bb69b85a94c6 |  | note | Verifying Records Checklists, Test and Supplier Certificates - UCS Rock Test Report
checkpoint-group |  |  | section | 1.3.0 Geosynthetics
checkpoint-status |  |  | checkpoint | 1.3.1 - Designer Visual inspection of the bottom of the excavation
label | 0db1dd08-cf25-5a83-98fb-b78beabf6e34 |  | note | Method/Description - Inspection
label | a4c984cd-ae01-5139-99e9-e5b98c37dd16 |  | note | Test frequency - Check each lot
label | 268892fb-2c5d-5ce1-ad2d-f8e82d79373f |  | note | Contractor - H
label | 88b4001b-385e-57ac-9181-fece7ee10919 |  | note | Designer - H
label | 3b6dabf8-b6a7-5b7e-a02f-ab02d1ccc8ae |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Daily Site Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3.2 - Geotextiles
label | 2ff86310-02b0-5683-be3b-65387d1ae0e0 |  | note | Method/Description - Inspection
label | 85c3a159-0f78-536a-971c-759c0364cb62 |  | note | Test frequency - Ongoing
label | 0c3c90a2-c72c-5b90-a571-de290875c9ae |  | note | Contractor - H
label | 6261776d-24d8-543f-a2b8-6d3a56fd1e4d |  | note | Designer - W
label | ad6c9d91-dcfe-5123-9922-d9c2d3e1687e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Manufactures Certificate
checkpoint-group |  |  | section | 2.1.0 Trench Excavation
checkpoint-status |  |  | checkpoint | 2.1.1 - Trench Subgrade
label | 847e7178-d71f-5f9a-8147-da80203f137c |  | note | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2:1988 for non-cohesive materials. Table 18
label | 45a647cb-092a-5069-a13c-23fbaee0f119 |  | note | ○ The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3.
label | 70b28c97-0316-5492-9fda-120649e4d15d |  | note | Test frequency - 2 nos. Dynamic Cone Penetrometer tests / 5m of trench, 1 per ancillary structure
label | f9b21d77-9275-5be5-bc34-7bbdfc68b456 |  | note | Contractor - H
label | 72bc675b-d854-517d-8eb5-e36777048a7d |  | note | Designer - W
label | 5c45e531-83d5-53a4-ab3e-51126cdad3e0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Dynamic Cone Penetrometer Test Report
checkpoint-status |  |  | checkpoint | 2.1.2 - Trench Benching
label | ea4b4f01-db21-5042-aa47-a6bffcb6519a |  | note | Method/Description - 1.5m benches to be constructed starting from rock face
label | e3e0e14b-b1f3-5841-838e-ff78e88bb891 |  | note | Test frequency - Daily
label | 85cc4c53-0690-5d9f-8dda-8c730a8a3309 |  | note | Contractor - H
label | 6945ba66-2aef-5448-b240-0f6c8238fe9d |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
checkpoint-group |  |  | section | 2.2.0 Pipe Bedding and Construction
checkpoint-status |  |  | checkpoint | 2.2.1 - Construction of embedment side zones using AP20
label | 3a7ba378-3987-5b74-8f07-b83588c52669 |  | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991;
label | 33deb3de-4a1a-5a03-8e66-8127f4ea16af |  | note | Test frequency - Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift
label | 919547bb-70d0-5ccf-b4dd-321aeb76e91c |  | note | Contractor - W
label | 0b9d354a-383a-59b4-bd63-18093e708e72 |  | note | Designer - W
label | d1570523-4240-5e8c-8472-5d3a389c01d6 |  | note | Lab - I
label | ba0ecf47-244f-5440-b923-0f52e5fd3c52 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 2.2.2 - Construction of Overlay Zone
label | 69b3b9a8-f078-5dbb-9f5e-9c813035422f |  | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength
label | 9e012799-ff14-5a55-aefa-01c479d91ba7 |  | note | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
label | a1c7c260-c6b0-5a2c-9435-7ca233679ef8 |  | note | Contractor - W
label | 943df5af-0820-5d7d-9e21-bdb41665cadb |  | note | Designer - W
label | 37d8da41-ddd1-5515-888a-c20a8228259f |  | note | Lab - I
label | fe7b455b-e6bb-5d65-a5ed-1aa67681411c |  | note | Verifying Records Checklists, Test and Supplier Certificates - NDM Test Report
checkpoint-status |  |  | checkpoint | 2.2.3 - Construction of pipe
label | 5495e333-1841-5d58-a491-9d43276c9772 |  | note | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
label | 2c330310-90ff-58e2-966d-39f47fe9b707 |  | note | Test frequency - Review every 10m and witness every 25m
label | 63264f0b-8b4c-562c-8ba5-74f0d41f691f |  | note | Contractor - W
label | 150709ef-07d4-5761-94ab-46be48debe81 |  | note | Designer - W
label | 2cb52ef5-085e-528a-ab3b-fd0f482a608d |  | note | Lab - I
label | a9ac0eb5-2063-5928-815d-ac0a351654aa |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.4 - Construction of Wingwalls
label | 63e31e78-1cb6-5685-a317-de149d6ba04a |  | note | Method/Description - Wingwalls shall be constructed on a compacted, 150 mm layer of AP65 granular material. Jointing between the connecting pipe and the back of the wingwall shall be completed using mass concrete.
label | 23794daf-fd71-5587-ae40-508d5f86f8fb |  | note | ○ Visual inspection of joints between pipe and wingwall
label | b3f0c1c6-cede-5fe4-8db2-a2f7618ad84f |  | note | Test frequency - Each Wingwall
label | a64fac22-c168-52a8-8e9c-17a8ca99a408 |  | note | Contractor - W
label | 95dcca66-7830-5bcc-8e0b-c1fa1340f6df |  | note | Designer - W
label | a7c398a7-c4e2-55e8-89f5-9fbbcb7152a9 |  | note | Lab - I
label | e71736b2-6383-5e48-8937-ae2a8056a9bf |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Check sheet
checkpoint-status |  |  | checkpoint | 2.2.5 - Construction of Antiseep Collars
label | 4c99c008-fdb2-5621-8d69-e78e5f9ee706 |  | note | Method/Description - Antiseep collars to be embedded 200mm horizontally into side of trench and 400mm below base of trench. To be located every second pipe joint. The collars shall be constructed using 25 MPa concrete.
label | 85ddf569-907e-56ec-8b62-49a94a82b8c8 |  | note | Test frequency - Each Anti Seep Collar
label | 60bb4a34-1198-5817-a955-75899b32e8f7 |  | note | Contractor - W
label | dc501a93-a067-500b-b7b2-b712ae7708fd |  | note | Designer - H
label | 6e4341db-cdb0-5dfb-b7ec-d0d4d9996949 |  | note | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Check sheet, Concrete Dockets, Concrete Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.6 - Construction of Cut Off Toes
label | 427d8625-88da-5823-8de8-4f5aadec412b |  | note | Method/Description - Cut off Toe to be embedded 1m (or note 4) from top of wingwall base, to be constructed as per IFC Drawings
label | ca58d884-f8f0-5b9d-9796-e3ee82da142a |  | note | Test frequency - Cut Off Toe
label | 1d881238-7e12-5496-aa65-5a99f5277924 |  | note | Contractor - W
label | d1641998-47dd-5bb3-9217-e0d77c23c526 |  | note | Designer - H
label | a122cb44-bda1-5576-86aa-cd11a610b441 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Check sheet, Detail Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.7 - Construction of Inlet/Outlet Channels
label | 45ed5101-68a7-5e22-a22f-f5825168438d |  | note | Method/Description - DSR to inspect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
label | 5afe2323-d6f6-5caf-b559-8b73dba33b0e |  | note | Test frequency - Each Channels
label | c0b813fb-a9aa-5f37-aae5-84685b21bd6e |  | note | Contractor - W
label | 1e47230d-026c-5f7d-9395-bc17239f19f5 |  | note | Designer - W
label | 3086fc60-1d3c-57a8-a396-5bfc16171ca0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
checkpoint-status |  |  | checkpoint | 2.2.8 - Fish Passage
label | a09e9033-37fe-59f4-805b-6df53e475682 |  | note | Method/Description - 25% embedment depth with meandering low flow path from void filled riprap. Spat ropes for CU-17
label | 5661c784-7c55-55e6-963d-25c98bc02011 |  | note | Test frequency - Review every 10m and witness every 25m
label | 3abb2b58-3dab-5492-85a0-92faafcb0ecc |  | note | Contractor - W
label | 58acd012-3564-52bb-8c5f-829e197eeb19 |  | note | Designer - W
label | b3639ecc-1436-532c-98be-e037658ce66b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
checkpoint-status |  |  | checkpoint | 2.2.9 - Construction of Safety Rail
label | 3e635c4d-68d4-5c4e-ad17-6fdfcc89400f |  | note | Method/Description - Constructed as per IFC Drawings
label | eeccdb52-2237-5e3e-a86f-4cd66649a4c6 |  | note | Test frequency - Each Fence
label | 4cd7c820-cb60-52e5-ba17-3960a61db922 |  | note | Contractor - W
label | f527a4c2-cae9-57f6-a5a6-84009edc69f3 |  | note | Designer - W
label | 94535d2b-004f-5af0-8369-14420763c9a4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey/as-builts
label | 40494747-1472-5bb5-97a8-aec6c59a584d |  | note | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
label | d0bc6e8a-5d57-5205-96ec-3b694ce97faf |  | note | Test frequency - Every 100m
label | b7b8a638-6e8e-54a2-a65d-1745e26dfbf9 |  | note | Contractor - H
label | dce60108-fd2f-58a4-a4b9-29f1c2f24a17 |  | note | Designer - R
label | 56259f04-79c5-52f0-aeac-f4d4376e7aa7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Survey As-built Data
checkpoint-status |  |  | checkpoint | 3.2 - Post Construction CCTV inspection
label | 95f0d49c-e324-5e35-baf4-fa86f7683f68 |  | note | Method/Description - Check conformance with the specification and assess the asset condition post construction
label | 643a8dbb-4725-5eca-8ad5-5559c1234b0a |  | note | Test frequency - For all pipelines > 225 mm Diameter
label | 45a53d30-beb9-5f86-9463-33c05271ac0e |  | note | ○ At completion of trench backfill of minimum 5 m fill prior to final surfacing
label | 9fa72698-7372-5ff0-bf78-8761ee087785 |  | note | Contractor - H
label | ad14c004-5c03-5329-98e8-cd1f97967c30 |  | note | Designer - R
label | 6b831f80-8582-55ad-b922-6aa4926f093e |  | note | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard
checkpoint-group |  |  | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint-status |  |  | checkpoint | ITP Close-Out by
label | a57f4b42-7ec8-5415-9f65-ce1d2e335413 |  | note | Site Engineer/Project Engineer
label | ff8f41d9-1fe9-5988-adb9-7e759afebebf |  | note | Zone Manager Approval
label | b1b07624-6b73-5228-a07f-2293c17788af |  | note | Construction Manager Approval
label | 0e4133ec-0e60-5fd8-b55d-a9be9b10ab3d |  | note | Quality Manager Approval
date | 5750c7ec-09a8-5539-9a20-022691aefd0c |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | ITP - Earthworks Cut 12 Rev 1 | itp |  |  |  | Yes | ITP - Earthworks Cut 12 Rev 1 | 504f9bd1-0a5e-410e-a314-ff6476425dfc
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | 3efe6b64-0cae-5f56-91bd-8b053d6de10e |  | note | Method/Description - Document Review
label | 56d95657-bc0c-5a4b-b493-d5d5b454d783 |  | note | Test frequency - Prior to personal starting
label | d9b1c55d-c388-5f0c-afc7-2298eb608508 |  | note | Contractor - H
label | a874ef3f-0686-5233-ab40-53f345ff2862 |  | note | Designer - H
label | b582bfc2-90ee-5ddd-aafe-873ad3a95a5a |  | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | ffd8d6db-0dde-58af-9f5b-b9f306450bc7 |  | note | Method/Description - Document Review
label | bfba68a1-ca80-530c-8f55-81e25f916eee |  | note | Test frequency - Prior to starting
label | c6d27184-2a15-51f9-bfc8-0f7d0ad05211 |  | note | Contractor - H
label | fc92d2f3-e27d-51c9-9935-89166ef2627c |  | note | Designer - H
label | f5c2d42d-10d5-5e42-8e13-a2c408fee1e1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Approved SCWMP
label | b1092132-339a-5159-86b7-34f096569c4d |  | note | Method/Description - Document Review
label | 76a1f0d1-29c8-5dc3-8213-abbaaa6c458b |  | note | Test frequency - Once prior to works commencing
label | e80831aa-a0f8-5ae7-8950-d657efac192a |  | note | Contractor - H
label | 869d78eb-ddf9-5cc5-956d-1aa1991e99d5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint-status |  |  | checkpoint | 1.04 - Investigation nail testing (Pre-construction)
label | 3f4df789-9220-575b-bb17-1409a14820ba |  | note | Method/Description - Test
label | c2ce1e29-ad95-5752-8ded-a4a4da270140 |  | note | Test frequency - Pre-construction
label | 2692082b-52ae-5ed0-9e77-066d18c9f87c |  | note | Contractor - H
label | 5666f0a2-bd9f-5331-b33d-69d0c7136d67 |  | note | Designer - H
label | b2716bc7-2b2b-5c63-a20f-d4da916588b8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
label | 9aaebe36-fec7-5e87-ba8c-bc904afbd061 |  | note | Method/Description - Approval
label | 2056cce0-f4da-56da-b4ac-a6306e91a59a |  | note | Test frequency - Prior to commencing
label | ca819f3d-b27c-5448-a4f6-365ba626636d |  | note | Contractor - H
label | 94de48b4-0802-55ae-951f-7b7453686504 |  | note | Designer - H
label | 7bc3829b-189e-59d8-8519-0854822be3ae |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Headworks
label | 818682a9-dd56-5f6d-88bf-a6cf6c88a74b |  | note | Method/Description - Submit
label | 778e1366-9e9a-5206-973b-30f25c9cedb1 |  | note | Test frequency - Prior to commencing
label | 3a707d86-7ad1-5d63-bf2c-c08a45fe5f7d |  | note | Contractor - H
label | f2f0b058-d477-5677-8ea6-23f5842fc60e |  | note | Designer - H
label | 829fdb22-4a08-5104-b9c1-6f0c7d90cada |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Drapery Mesh
label | c9253dcb-0539-5e78-b054-3dfe0ead24af |  | note | Method/Description - Submit
label | a583f7a9-5565-59b0-aea8-72a46b299822 |  | note | Test frequency - Prior to commencing
label | d8bf1fdf-adcb-58b6-b757-c0ef52a63e5d |  | note | Contractor - H
label | 6a93acb3-8306-5593-af84-e1501f32c4d3 |  | note | Designer - H
label | 8ce2853a-a572-52bf-ba91-02d368a19858 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Steel Wire Ropes
label | 325ba659-cd11-564e-adcb-38d6662c24aa |  | note | Method/Description - Submit
label | f6f04053-9c17-550e-9d91-f980f4108af0 |  | note | Test frequency - Prior to commencing
label | fd811330-6392-5d3b-a31f-4fd438aad467 |  | note | Contractor - H
label | 3ec32774-e468-51eb-b1e1-c9c324284826 |  | note | Designer - H
label | 6b344dc9-04e7-5af3-907e-8fadb450bff6 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Wire Rope Fittings
label | e5bdb7ce-52c3-5164-bf09-f9b930e01459 |  | note | Method/Description - Submit
label | 0cf5c283-b69f-5aeb-80c8-f0cd813ff775 |  | note | Test frequency - Prior to commencing
label | 36084907-a7bc-5845-9934-0327e291a235 |  | note | Contractor - H
label | 4b9d6ee1-02a2-56e2-84be-53ae90216560 |  | note | Designer - H
label | 4a1bc91e-4af8-5cd3-8520-0ad7ac0a1ee2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Delivery of all rock drapery system components
label | 2b176abd-8d22-5fbc-bdc6-45ec1ce7900b |  | note | Method/Description - Visual
label | 4e301c2d-fe9d-5a4e-bc7e-a095676464cf |  | note | Test frequency - each delivery
label | a92ec3d7-da46-5e43-8b5b-aa345efedd1b |  | note | Contractor - H
label | 7a3199c3-5288-5986-bc39-0052c607bd13 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents
label | e106bd1f-4306-5870-b3d2-667c2a24fa5a |  | note | Method/Description - Survey/visual
label | 049b5c38-ee48-5188-a825-af3aaecb776c |  | note | Test frequency - Prior to Commencement
label | 72769698-5b7a-5e02-9331-c0202e9a9b88 |  | note | Contractor - H
label | 78770c6e-ba0d-5f1e-a043-e42182eb29aa |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
checkpoint-status |  |  | checkpoint | 3.02 - Verify Machine Control
label | 87a7806c-676c-5cbd-90e0-11a548d3b85e |  | note | Method/Description - Survey/visual
label | 06efc53a-344e-56a9-a597-3e676c00533a |  | note | Test frequency - Daily
label | 7b41747a-82b6-573d-9b8c-8fe086847088 |  | note | Contractor - W
label | bb8e2174-714d-5cf2-a2bb-1244a5d70269 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
checkpoint-status |  |  | checkpoint | 3.03 - Assess Crest detail
label | f67aa20f-f2f5-5033-923d-2e406e883d55 |  | note | Method/Description - Hand augers/ slope assess/Window Samples
label | 2a6a6d79-8f3f-51b5-bf89-c2889c129a44 |  | note | Test frequency - Prior to Excavation
label | bb61d5cf-a574-5343-9064-275999803d35 |  | note | Contractor - H
label | c892e452-9e76-50b4-866a-131190ddc367 |  | note | Designer - H
label | 6f112e26-4ce3-5ba1-b908-db74ecc0ff60 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Install crest detail - Soil Nailing
label | dd599ae3-a242-54b1-bc9e-d9999c14b2e1 |  | note | Method/Description - Visual Inspection
label | ceb63161-3852-56ad-9be3-dc2eaf00cb1f |  | note | Test frequency - Prior to cutting rock slope
label | ec72dbc6-ebae-50c9-bcb2-4cc55f1ab03c |  | note | Contractor - H
label | 96c552d5-88e8-59e4-850e-4d0c54067ce2 |  | note | Designer - H
label | 9b7cf0b4-383b-55a0-95b1-cb6e5c011808 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Install crest detail - Erosion Matting
label | 9474781f-06fd-56e4-a7c5-befb7c2105d6 |  | note | Method/Description - Visual Inspection
label | c9d975e8-c720-5f8c-9967-9b5c4cd716fe |  | note | Test frequency - Prior to cutting rock slope
label | a40d6db2-2903-59f1-baa3-26467f66e916 |  | note | Contractor - H
label | 8f0633ec-555e-5739-b7de-3cb73df0a505 |  | note | Designer - W
label | 0fd75df9-1d0a-56cf-a92f-9b178441431b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
checkpoint-status |  |  | checkpoint | 3.06 - Install Rock Fall Protection
label | 02afa65e-e8c4-54d7-b7f8-12c8ea3fb152 |  | note | Method/Description - Visual Inspection
label | b3d247aa-dcac-5a03-a5f1-b23ad4236296 |  | note | Test frequency - Prior to cutting rock slope
label | 1fe5f770-2540-5f71-8f9c-9d1d5a4dbace |  | note | Contractor - H
label | 8ac0bc2b-c8ee-5c53-89e0-243694841347 |  | note | Designer - H
label | 5b0b0f48-d268-5ad1-8a3f-0331bd62e55c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
label | 7ef0006b-ac0c-572d-a530-b00272e07578 |  | note | Method/Description - Survey check by construction team, visual inspection by designer.
label | 78351530-3306-51d8-9e36-40dc3580daac |  | note | Test frequency - 100m2 or maximum 5m vertical cut
label | 58ace8aa-7a56-5d41-a1dc-a7ffec549a6f |  | note | Contractor - H
label | 2f21b288-1034-57c3-8b21-d943bba0c1ab |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
checkpoint-status |  |  | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
label | f1d39dc9-4ce8-5e57-8f57-c2c27aebe7ac |  | note | Method/Description - Geo inspection and face mapping
label | ffcdeba8-7195-5d45-851f-13b523f68050 |  | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | 105202e6-8b08-5cb8-bca3-eb2d393a0f7f |  | note | Contractor - H
label | 2b1199e8-aa29-5e36-9a02-ee5ccfd8d791 |  | note | Designer - H
label | 4c2fa667-ce75-5130-885a-7655db44f92f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
label | 680268c3-3fe8-532f-9c49-4989df86452c |  | note | Method/Description - Geo walk over
label | b6f2952a-2fe0-58b0-887e-a2e336c28419 |  | note | Test frequency - Prior to drilling
label | 828188e2-af4a-55e2-b4a9-227ccf06c3bb |  | note | Contractor - H
label | 447a7f1f-1210-55d2-991c-e61f54fffbd0 |  | note | Designer - I
label | 1ce4f5b1-a6ac-5798-b8db-b1c1a821bef8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.10 - Install Rock Drape - Install anchors
label | 90e8b3f4-c92d-50e9-b1a7-3082fa9f90bd |  | note | Method/Description - Drill and grout records. Stressing records.
label | edd662e4-1b9a-5246-8257-b3492b94e908 |  | note | Test frequency - During construction and at end
label | d4371f53-7f78-5745-858d-d644f95c31d8 |  | note | Contractor - H
label | 81bb9c2c-11d2-5e18-ad8b-57de5bd843ad |  | note | Designer - I
label | 069c774e-7920-51e4-885b-0b2202351ca1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.11 - Install Rock Bolts
label | e1c22199-934d-5036-a747-074bf893429d |  | note | Method/Description - Drill and grout records. Stressing records.
label | c090af7a-cdb7-5e61-b4cc-b148c10778be |  | note | Test frequency - During construction and at end
label | bc8aca19-9fe7-552b-9e1e-d7394d3bdd58 |  | note | Contractor - H
label | fba800f4-210a-5d11-acc7-d3319e99f901 |  | note | Designer - I
label | 4316e0a9-8a3e-5fe5-be29-7a9e2a763464 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
checkpoint-status |  |  | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
label | b4e11c60-1242-57b8-bff0-b6dc684811e1 |  | note | Method/Description - Visual inspection
label | a77e8a32-4ff1-5ca7-9408-ece86918e143 |  | note | Test frequency - During construction and at end
label | cd91ed5c-beaf-5e80-bcdf-c26a05401e57 |  | note | Contractor - H
label | 9d905484-5974-5f03-9eb8-f0f6a40de14b |  | note | Designer - H
label | 95ec2e35-cabc-5187-82ba-269d95e3cb30 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Production nail acceptance tests
label | 2671a527-cbc9-54fe-8c2b-67c05fc7165f |  | note | Method/Description - Test
label | fe2d9c26-623d-5c67-8fb7-400ac43e4dbf |  | note | Test frequency - At Completion
label | f7ea9e21-ee7d-5e75-bf16-1d76858570ac |  | note | Contractor - H
label | f4338cf7-27bc-5c67-a468-1dc78bd2f98b |  | note | Designer - W
label | 8807d8e9-07ff-56bd-8f48-cd0a243331d9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
label | 6462b49b-cce3-57a5-9300-98f2a334fa25 |  | note | Method/Description - Test
label | a74d7e1b-59e7-5759-a923-2abdd3cab414 |  | note | Test frequency - At Completion
label | e4c9dd82-60f6-5476-81d8-1f5ad42c6779 |  | note | Contractor - H
label | 26b4afb6-a4f7-56a8-a20e-e66a4e28d31c |  | note | Designer - W
label | 47c6ae03-c613-5493-8c67-8252d324f4a0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.15 - Catch Ditch Inspection
label | ef010779-5d60-58db-80d6-94fed44e9677 |  | note | Method/Description - Visual inspection
label | 457f6c5b-084f-5378-abe8-06f172f26160 |  | note | Test frequency - During construction and at end
label | c773fbb2-432b-5bfb-ab7e-3216eab28511 |  | note | Contractor - W
label | 116167d6-660e-5b7e-ae4b-d721318708d6 |  | note | Designer - I
label | 8c3519ae-c7cc-5e51-b390-6ce00a86c61e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Throughout construction period prior to road opening
label | b2f5804b-eebc-5e0e-b806-f93835a69ea7 |  | note | Method/Description - Monitor
label | cc2474d5-1d10-5d48-a1c8-35ddf04d515c |  | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
label | 2cef5515-6aa1-5265-beea-d049c52adb9d |  | note | Contractor - H
label | 5c30ce6b-c9e3-52aa-811f-99ad3fe48a68 |  | note | Designer - H
label | 522850e2-1ec2-5392-b29e-850e4ae23c3f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Red Line Mark Up Drawings
label | bf52eade-eccc-56aa-91fb-0251acc214d2 |  | note | Method/Description - Submit
label | fcf86572-73f9-5631-b937-2515e81c22ab |  | note | Test frequency - At Completion
label | 2a3da0e6-0a6f-5b2e-870f-4120a58a8550 |  | note | Contractor - H
label | e0c36a09-33f8-5e55-ac50-06101691701a |  | note | Designer - R
label | 9abe176d-9fe6-55fd-823a-fd38554839de |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
checkpoint-status |  |  | checkpoint | 4.03 - Operation and maintenance report
label | d61801bf-268f-53bb-b851-955fae9b9f6a |  | note | Method/Description - Submit
label | 9b7241be-5cd2-5016-a00f-3de723a0e749 |  | note | Test frequency - At Completion
label | 303c4980-8a96-5596-bdb9-b11cd795babc |  | note | Contractor - H
label | 2e65953f-db31-5613-873d-9c11fc01212c |  | note | Designer - R
label | 069b5355-3572-5c43-afd2-1aa16abe76d1 |  | note | Client - R
label | 92b8c26f-d011-5257-90bc-3ffe802905a7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
checkpoint-status |  |  | checkpoint | 4.04 - Final Handover Package
label | 48452e55-2798-57b5-abe3-35913521b644 |  | note | Method/Description - Submit
label | 9be7946d-4d71-559c-a26a-eec294827515 |  | note | Test frequency - At Completion
label | 558d0b33-24eb-56eb-8b64-8ddf77c40bfe |  | note | Contractor - H
label | 43fb7a75-2b1f-5d47-8da8-dd0a47bfa5f1 |  | note | Designer - R
label | 873c2aa2-186e-5ea7-8750-62416f26f0d3 |  | note | Client - R
label | d9a6db20-64fe-5288-a650-d5ade0882c72 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
checklist-sectioned |  |  | checklist | ITP-011 - Fill 15 | itp |  |  |  | Yes | ITP-011 - Fill 15 | 56cfed4c-fc80-4fa7-9f5f-38e8f24799d6
checkpoint-group |  |  | section | 1.1.0 Pre-construction Approvals
checkpoint-status |  |  | checkpoint | 1.1.1 - Construction Environmental Management Plan
label | 50034a9b-c7fd-5d4a-ac48-4a40acfd5153 |  | note | Method/Description - Document Review
label | ca266398-4518-5357-8549-a06a9b788e3f |  | note | Test frequency - Prior to work starting
label | f0e3afb8-6790-5be9-a0f8-80f3ec578b99 |  | note | Contractor - H
label | ba562c65-bc6c-522d-9f17-2f2b27639032 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
checkpoint-status |  |  | checkpoint | 1.1.2 - Construction Work Plan
label | 07bf01a9-825c-5fdc-b175-9ae5c8ca892f |  | note | Method/Description - Document Review
label | 9b7eeef0-c1e4-56e5-b431-7adfa97d42a0 |  | note | Test frequency - Prior to personal starting
label | 35ee3d69-2c98-5c1e-85f0-9f0593f4aa04 |  | note | Contractor - H
label | ae769efa-75b8-536c-860e-dbb95892bf82 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.1.3 - IANZ accredited testing organisation
label | dc14c63e-01e6-5479-9e93-4f506f8ac28d |  | note | Method/Description - Document Review
label | be91758d-b187-54a6-9a01-4dc6ce1f1c07 |  | note | Test frequency - Once prior to works commencing
label | 4eb99b6d-d70c-571b-b090-cec6be83195e |  | note | Contractor - H
label | 67fdb9b4-4c51-5187-b60f-def6158133b7 |  | note | Designer - H
label | 4b926d1e-7dc3-59f3-a856-b730cdafc0c1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.4 - IFC's specification
label | 2450ca51-e036-508c-b9f4-8d0a3dbd04a8 |  | note | Method/Description - Document Review
label | ecf481fe-aa10-5f6c-9eeb-33e0dc2a64a3 |  | note | Test frequency - Once prior to works commencing
label | 20b4c479-3a6d-5812-9a25-7374d89f6fdb |  | note | Contractor - H
label | 9f9cade3-9e8b-5b6d-834e-672f2279b41e |  | note | Designer - H
label | 86591545-de2f-5cef-8092-31f351edb218 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.5 - IFC drawings
label | d8ddcaa6-3582-5415-81c3-661c617f6746 |  | note | Method/Description - Document Review
label | 83b2c398-5712-59c6-a5db-35bfd54ccb56 |  | note | Test frequency - Once prior to works commencing
label | 5c4b541e-c631-5927-992e-7794c26099b2 |  | note | Contractor - H
label | 3bcfe335-1b32-5b01-a8c3-d3124621f671 |  | note | Designer - H
label | e7cf6945-0b86-53c6-a8bd-15cd5969fe82 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.6 - Approved earthworks model
label | dbdd446d-910f-5404-aff5-101f91ddd9e3 |  | note | Method/Description - Document Review
label | a52bbb2b-cdd1-5db8-9599-2bb2aff2ebe5 |  | note | Test frequency - Every new Earthworks Model and prior to work commencing
label | 3604447a-d645-5d16-85c1-4d0ce474b5bf |  | note | Contractor - H
label | da4ad63a-38af-5b42-8c77-10e66b0f0fb6 |  | note | Designer - H
label | 6d2e6e99-3707-508d-a97d-0d75889b5c9a |  | note | Verifying Records Checklists, Test and Supplier Certificates - ?
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.7 - Approval of stockpile location
label | 1b3a81d4-0e09-5121-9c26-788f157b3581 |  | note | Method/Description - Document Review & Approval
label | 326eba61-a9dc-5712-b9ca-9966dc847b73 |  | note | Test frequency - Prior to works commencing
label | b25e1244-930e-50ab-bb58-0e00d83a8336 |  | note | Contractor - H
label | 0fe42e9c-25ef-5976-a855-5eb2a06e11c0 |  | note | Designer - H
label | d6e67424-952f-5384-bec9-25ef44e9b841 |  | note | Verifying Records Checklists, Test and Supplier Certificates - ?
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 1.2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 1.2.1 - Structural fill
label | 5fc7058d-46da-5dfd-a86d-1732f318088c |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | cc0df67d-b45e-5269-b280-818b498dd30f |  | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | caf36ebc-9909-584e-aef0-edd566e89c93 |  | note | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
label | cec78310-376b-52e9-b854-ce279b2cbb61 |  | note | Test frequency - 1 test per 20,000m³
label | 06e6a241-3136-5004-8427-a080f041cd13 |  | note | Contractor - H
label | 617c7773-2781-5469-bfc5-843c1ba862da |  | note | Designer - W
label | d698a9e7-51a5-5ed3-bdf9-c793b6b02760 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.2 - Buttress Fill
label | 6e842e6a-54ff-59d3-9470-fb4a5205080a |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | 45ecceae-e84d-57d2-a88e-f8bdab0ad1ff |  | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | 1f04baf1-07ca-5358-88c2-91c150c5d2bf |  | note | Test frequency - 1 test per 20,000m3
label | 0a900ba6-1f79-5556-9fcd-ecd98196d97d |  | note | Contractor - H
label | f92a7750-3e4e-5d0a-a3a9-a900b540ce28 |  | note | Designer - W
label | 670aa45d-4889-5e43-b84a-e1249e99e5d2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.3 - GAP 65
label | 9c740a6e-8cdb-52a6-9d62-8e429ce97fd9 |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.3
label | 67480ea2-8248-598c-823e-7344fffeb339 |  | note | • NZS 4402 Supplement No 1:1998 - Test 3.8.1 Determination of the particle size distribution Standard method by wet sieving
label | be8cc692-0330-558a-b852-0ea7a4214757 |  | note | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
label | e6bea317-9c5a-5276-8c06-2e25199693e4 |  | note | Test frequency - Determination of the dry density/water content - 3 tests per source.
label | c694db45-500d-57b6-90c3-0997b8a422df |  | note | • PSD - 3 no. tests per source + 1 test per 2,000m3.
label | 75054765-b58d-5321-b86b-3576953a5afa |  | note | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
label | bd06ccbb-640f-559d-9286-017191331ada |  | note | Contractor - H
label | 9bb7105e-96e5-5b5b-b5a9-c3e8c81a4c45 |  | note | Designer - W
label | c5bcb335-c9c1-5f34-bdff-091d90a12925 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.4 - GAP 65
label | b95347ff-aa0e-5115-af84-f66859e6c3bd |  | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
label | c1f243d8-d504-571f-8662-93d4b1b08273 |  | note | Test frequency - 3 no. tests per source and 1 test per 2000m3
label | 1c4c2757-5579-5847-82e5-8f21a5255178 |  | note | Contractor - H
label | 8ef58d5b-1336-52d3-91e5-f42d49851d85 |  | note | Designer - W
label | 5609d593-aac0-5012-8424-f895ca3aa213 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.5 - Cement stabilised structural fill
label | 23fe0fbd-c79a-5fd2-bfc0-a2888cef20ea |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | ef52621c-cc35-5389-9836-fc2ac990b949 |  | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | 76bde9e1-5a97-5375-98cf-727ab48a46aa |  | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | a4fae4c5-76c9-5f65-bc55-8e3b5b2f4a2b |  | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | b9c041f6-1aa6-539d-87ac-4f9364055105 |  | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
label | 85a13705-1cdb-5924-9a3a-f225b9fabdd2 |  | note | • UCS - 3 no. tests per source at adopted cement ratio.
label | 17d9408c-e7c0-5a2d-90b9-7d0912274a11 |  | note | Contractor - H
label | e93eefa6-9f30-5c6d-9395-ef2bea0b7640 |  | note | Designer - W
label | bf1b304c-f40d-58ad-a6cf-d83763cf48e7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.6 - MSE Fill
label | c924383a-bf1e-57a6-97ab-b7327c09ef88 |  | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
label | 4bf57aed-417b-5982-8772-317488d061c6 |  | note | Test frequency - 3 no. tests per source and 1 test per 2500m3
label | 4a95af0c-5716-5bf3-8137-06135e0403f7 |  | note | Contractor - H
label | 86686b7e-b0c1-5e3b-8575-9804afd8440f |  | note | Designer - W
label | b83b7c0a-9874-5bbc-89d6-b929b0828073 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.8 - Cement stabilised GAP 65
label | e8758f56-a0ce-5fd0-813e-4b7520f917a5 |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | 7be8c2e0-eadc-5384-ad7d-c5109ece7686 |  | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
label | 29d3a139-27f9-5be9-9860-dfbf27d5f1c9 |  | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
label | aeeba150-74c3-5372-8492-c67b72ecb26c |  | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | 3312b536-d2c2-5662-91f2-640a460737e0 |  | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | 9a133854-2b1a-5cf6-a81e-b33e01e4cdff |  | note | • PSD - 3 no. tests per source + 1 test per 2,000 m3
label | 4a64f4f3-3f6e-5fc2-b3f9-39b5564623c6 |  | note | • UCS - 3 no. tests per source at adopted cement ratio.
label | 3890c8ee-7f55-5734-bb14-8ac156315037 |  | note | Contractor - H
label | c3c19303-7fa6-5e2e-aab1-6e88c6ed3e80 |  | note | Designer - W
label | 222c3b85-555a-5189-93d0-137c0f28e710 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-status |  |  | checkpoint | 1.2.9 - Cement stabilised structural fill
label | ce1a64af-ba5d-5af2-9c4a-bd52d9c04c5d |  | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | d390698d-822c-582c-b0f0-2c1a57a3b314 |  | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | e42c1b44-e183-5f1d-b8ec-594f650831e0 |  | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | 7312d13e-7a47-59fc-810b-63332e2a420a |  | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | 3f5d2f30-e252-5ec0-b102-00e15489ebf4 |  | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
label | 9f298b74-ab69-52d8-9b49-094ec559f3fb |  | note | • UCS - 3 no. tests per source at adopted cement ratio.
label | 11a054a6-eb72-57a0-ade8-885820346df2 |  | note | Contractor - H
label | 89b7c534-a19b-5331-8ec4-61780cdf09ef |  | note | Designer - W
label | 3a63962c-0f91-5111-9c75-5e5db315b837 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint-group |  |  | section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
checkpoint-status |  |  | checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
label | dfc6d86c-a7d0-549d-8103-ebfbc43d72b9 |  | note | Method/Description - Document Review
label | 3f49e66f-27b3-5db3-b4c7-01ae780c9357 |  | note | Test frequency - Check each lot (1 roll)
label | 3dcf9eaf-134d-5b8b-b37c-d452438c3c81 |  | note | Contractor - H
label | 6a00fbbb-96b0-571a-844c-dc0fdbfc4520 |  | note | Designer - W
label | 977b0cb2-fab5-597f-ad3d-fcb59fcf2fa1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint-status |  |  | checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
label | 6b312682-20dd-5521-a652-4a804adb6c19 |  | note | Method/Description - Document Review
label | 27d5b2fa-0b8c-5a08-970c-9d355b1461ca |  | note | Test frequency - 1 test per production batch
label | 90077b3b-9ade-5198-aea3-b92e7a44febe |  | note | Contractor - H
label | 9fe05ba0-e3d1-5689-abd2-9f043b9dcff1 |  | note | Designer - W
label | 5acde8d0-aa95-5250-bfab-031799620b49 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint-status |  |  | checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
label | 7edba1c7-cfc6-5c26-9ac6-8a370dbd5f8f |  | note | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
label | 70b3561c-9dae-5efe-ad2e-218ddbe437cb |  | note | Test frequency - Check each lot (1 roll)
label | dc30d6c0-16d2-52b2-a254-58e7f99e486e |  | note | Contractor - H
label | cff40156-97da-5a03-b246-2ecb3e6845b5 |  | note | Designer - W
label | b2445143-698f-575b-9370-ce13a1387c07 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
checkpoint-status |  |  | checkpoint | 1.3.4 - Visual inspection - geogrids
label | a6fa02d3-5d52-5402-a62a-291db157f256 |  | note | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
label | 7af6b0af-0b4b-52e4-9c62-24c8b4e50d74 |  | note | Test frequency - Check each lot (1 roll)
label | f9a1cdca-dba7-50cf-9e52-bbd393bc9711 |  | note | Contractor - H
label | de95b5aa-14ff-5c6f-95ba-fd9685ca48ad |  | note | Designer - W
label | d8e9db36-8fb2-50b3-aea1-8439359b718f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
checkpoint-group |  |  | section | 1.4.0 Monitoring - Pre-construction
checkpoint-status |  |  | checkpoint | 1.4.1 - Monitoring prior to preload
label | 4e4ad618-ec23-5ca0-ab5e-a1237938ffd1 |  | note | Method/Description - Baseline readings
label | 057ae6a7-fec6-5698-85ae-f7f142d42112 |  | note | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
label | c5f36bfe-9cf2-546e-bad0-d56637147e4c |  | note | Contractor - H
label | 1b6b515d-d125-5456-9c97-3c1e434b5a2c |  | note | Designer - H
label | 096e062b-f92d-5bff-bb7c-915e2808986d |  | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.1.0 Pre-filling
checkpoint-status |  |  | checkpoint | 2.1.1 - Set out extents of fill and check against design
label | 1056ca91-1289-58de-922b-0e500e9fcfff |  | note | Method/Description - Survey/visual
label | 7b79e7d6-a31a-5931-bd63-9a1dd80f8e9e |  | note | Test frequency - Prior to Commencement
label | 50ac7331-e74c-5514-97e2-9cab71b1f8e2 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.1.2 - Vegetation Clearance
label | e3e61131-c40d-5470-a93c-090e828e4830 |  | note | Method/Description - Survey/visual
label | 40e89c54-9b20-5897-855a-227d098f02fc |  | note | Test frequency - Fill area foot print
label | 610d68e9-9738-5b5c-920f-9ab0b99e6e3f |  | note | Contractor - H
label | 40ee3f69-74ac-54fe-8a49-a9c419d5bec0 |  | note | Designer - W
label | 5f2ced3b-2e57-58bb-b07b-88b49adfa8c7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet Designer site report (where advise given)
checkpoint-status |  |  | checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
label | 0c7fa32b-93be-5b2c-86b8-e0c3a56c0203 |  | note | Method/Description - Visual inspection
label | 4832ef5e-f47d-59e9-9a4c-bda04d23df25 |  | note | Test frequency - Prior to Filling
label | dc11d2b9-4407-54a9-88b9-33f592567cbb |  | note | Contractor - H
label | 29e6c598-5b25-5aa2-beeb-530dd25eac36 |  | note | Designer - H
label | bf8b4fed-9c9b-52b3-b994-a42be9f71a1b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.5 - General Undercuts
label | ac514d07-ddf0-592a-9153-4b5f546ab61d |  | note | Method/Description - Visual inspection
label | 41dcbadf-ec3e-5ec3-84e6-400a3e26dc92 |  | note | Test frequency - Prior to Filling
label | a9e77516-a4c9-5340-aee7-d28fb19d4c46 |  | note | Contractor - I
label | 7ac43eb5-b116-58fd-9178-36a0750aa2a8 |  | note | Designer - I
label | f0c579ef-ad83-53bc-97fc-53c6d8a96f31 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint-status |  |  | checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
label | 3480f777-a904-56eb-b9a4-d79f2b8c6219 |  | note | Method/Description - Visual inspection
label | 06520e0f-6a06-5bd0-a4d5-4a8b37a31a13 |  | note | Test frequency - Prior to Filling
label | 1f3264c8-20f1-5c43-ab5f-d35d7b96716e |  | note | Contractor - H
label | ab67a8df-28ab-5ae8-896b-013dd1bc9f9a |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.7 - Basal reinforcement installation
label | ee8adac9-fea8-542c-a789-b01a47493bca |  | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
label | c662db2d-fab3-5b38-b749-9e849f6ea002 |  | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
label | 84f5833c-b83f-58ea-bc82-75e82a408384 |  | note | Contractor - H
label | 5067dfdf-d82a-54b2-8fc7-a37183507390 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.8 - Drainage blanket installation
label | bf44088c-6a88-5529-a4cd-fa2d06cccbba |  | note | Method/Description - Visual inspection
label | 0a5f93b0-2ea9-5639-a053-77137316c762 |  | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
label | c2db837e-4a44-5d64-9d6e-7e5e937c4872 |  | note | Contractor - H
label | f0c2daf9-4a2e-5221-a69f-8912915cd473 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.9 - Construction of wick drains
label | eed9ab96-9869-5901-9c98-73d791d28672 |  | note | Method/Description - Visual inspection and subcontractor record review
label | 0dd722de-cdb6-58d0-b1f1-8c1fb2be2a69 |  | note | Test frequency - During wick drain construction
label | 17596efd-2352-5432-9700-9e4d831de1d3 |  | note | Contractor - I
label | 6cd7e87c-a2bd-5455-ae74-ad01f88c9c21 |  | note | Designer - W
label | 7a4c5c42-e10c-5dfe-b933-747f38f45850 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
checkpoint-status |  |  | checkpoint | 2.1.10 - Sub soil drainage
label | 42ccfbf3-d7c8-5861-8695-87ef965970d0 |  | note | Method/Description - Inspection
label | 3f6da756-e5f2-56f8-b4f6-cb3a297f7a5e |  | note | Test frequency - During subsoil construction
label | 4e5a0339-543f-5332-92ca-06f701caa96a |  | note | Contractor - I
label | c42fb20e-057b-5948-a395-7a9c068ca1f4 |  | note | Designer - I
label | 74c8065b-cd85-5891-a6fc-9f12d70d5128 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint-status |  |  | checkpoint | 2.1.11 - Monitoring Equipment
label | 6b9bea36-81df-5467-b603-75cead2f7917 |  | note | Method/Description - Survey/ data logging
label | bfccd6c5-e006-5bd0-915b-9f1becba6486 |  | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | abf886e1-f802-519f-a7f1-802dca3eb53d |  | note | Contractor - W
label | 0454222b-e3bc-5f84-823b-bacf51f4567f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
checkpoint-group |  |  | section | 2.2.0 Fill Construction
checkpoint-status |  |  | checkpoint | 2.2.1 - Filling operations
label | 1e4eee05-2b8b-5f7e-a4ad-75a8996d96ca |  | note | Method/Description - Visual inspection
label | 0d9b7c2e-1f76-5e9b-9b34-987cbad8a792 |  | note | Test frequency - Daily
label | f5b59f25-1b02-5c93-abd6-bc4790a820d3 |  | note | Contractor - W
label | 10a7a72d-399a-50e4-912a-938f130c7865 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.2 - Filling operations
label | 590f413c-bc5c-501f-9230-21d41c7b9ae8 |  | note | Method/Description - Survey/visual
label | f09d59de-6754-51dc-bec3-c047c0a6951d |  | note | Test frequency - Daily
label | 1580519a-7ac8-5084-9aa6-a7d0bf1036bf |  | note | Contractor - W
label | 23fa558f-48fd-518e-bad3-d13dc474fb25 |  | note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint-status |  |  | checkpoint | 2.2.3 - Insitu fill testing
label | ec20bb4c-a3d2-5065-a7fc-ccbb753ba82b |  | note | Method/Description - Plateau Test
label | a453c1a3-24d7-5eaf-8a06-5ac243dbeb4b |  | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone,
label | 124fbdf9-52dc-5ff3-84c6-6fc5cf11502c |  | note | • Buttress Fill - 1 test per material type per earthworks zone
label | f0c0fca8-2726-598a-beed-31f8461f1af3 |  | note | • GAP65 - 1 test per material type per structure / location
label | d4efdf89-480c-5aa7-80a1-444e361aed7b |  | note | • Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | ee686f5a-7f8d-5631-bbf4-a4cc05909ece |  | note | Contractor - W
label | 61833c91-188c-5c25-8c44-70fec08dc8a5 |  | note | Designer - W
label | f4b6f81b-bb5a-5bb0-850c-0cc72ba47c9d |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.4 - Insitu fill testing
label | fe14da24-958a-5b46-9de0-6ea0dfc8194d |  | note | Method/Description - In situ moisture content and density
label | 5b0cc25b-0198-57a4-96b8-f7aedf5e4bdc |  | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
label | 3b5133b0-010c-5881-a1e8-5c20acdf6578 |  | note | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
label | 31c10d01-6a27-5b09-ba92-7d533d7d96e2 |  | note | • GAP65 - 4 tests per lift per structure
label | b95fa105-1813-5254-82fa-76d19ad6a362 |  | note | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label | 5eb78135-4bbc-52f3-a53a-94582587602c |  | note | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | 1da394e1-1f8b-57d8-9229-00c507273604 |  | note | Contractor - W
label | 2d842370-226b-5726-93ec-9ad07c0c106c |  | note | Designer - R
label | 052d651a-6597-5ca1-a7b2-12188636fab2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.5 - Insitu fill testing
label | ffe420a6-fa5e-5bd3-b6a5-db05ea076886 |  | note | Method/Description - Undrained shear Strength
label | 12f930a3-afd3-5cd4-a47a-aaf3eb346a33 |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2
label | d25a3467-ec32-5c9d-a55e-383c0a71567c |  | note | • Buttress Fill - 1 Test per layer per 2000m2
label | 1635b668-6837-5e3d-a324-fad5ee830c8b |  | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | 283ac3a3-2e88-5042-82a5-6988c1b4c8e9 |  | note | Contractor - W
label | ae593c0e-dadc-56ce-a786-a4cf8aa09216 |  | note | Designer - R
label | 703e8fbb-92b2-557c-9f05-380b2439272a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.6 - Pavement Subgrade Fill Testing
label | cc647bff-19fc-50e3-8464-a62cdaa5f4e2 |  | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | 50ab74b6-3db2-5da6-be8c-0764f24d0f39 |  | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
label | a669c3db-1caf-5be6-9e9a-fcf790db4faa |  | note | Contractor - W
label | cc7eae38-0c01-5b0f-86f1-5127d4ebc492 |  | note | Designer - R
label | bc577fb3-7c22-5f3d-aa96-cb1fedcbbdad |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.7 - Pavement Subgrade Fill Testing
label | b2390827-462b-5793-91ae-2865fccef62b |  | note | Method/Description - Scala Penetrometer Surcharged Fills
label | 6fc16cd9-d17f-57f9-b8e8-b0591bcaa905 |  | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
label | 16b66314-a0aa-57d3-a05d-894fe995c16f |  | note | Contractor - W
label | 664b35cc-d550-5ee2-b9fe-db2b478a84e0 |  | note | Designer - R
label | 65d32115-8f52-592a-88a8-b6ad84eec55e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.8 - Pavement Subgrade Fill Testing
label | 01e3215c-e556-534b-a474-d5fa358c39d1 |  | note | Method/Description - Benkelman beam and FWD Testing
label | 453fb531-f452-5b5b-9aed-aa2e53ca6026 |  | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
label | a572348a-90b7-5565-ab36-52514901a76c |  | note | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
label | 3134ec51-bfe1-5848-aab8-c6d362e75a81 |  | note | Contractor - W
label | 0f8e517d-537c-5544-a591-34539a8f0986 |  | note | Designer - R
label | 79a00819-98d5-5246-ae99-7eb67a88926c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.9 - Pavement Subgrade Fill Testing
label | 24a5717e-2919-5200-998b-997057ae1e1a |  | note | Method/Description - Laboratory Soaked CBR
label | 1e4936b9-f357-57ff-b0c0-d98c2efc11b2 |  | note | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
label | faf65416-3d56-58f3-85c1-015bebae8f29 |  | note | Contractor - W
label | 8c6a3b80-1ba7-5bc3-81e0-d7bf5fda7642 |  | note | Designer - R
label | 06f4e76b-e9c6-50ed-a167-d8eae77752f0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
label | af89f5a8-465b-5698-adec-10be03ae82a0 |  | note | Method/Description - Summarise, interpret and review test records
label | 865041c7-878d-543a-846a-bbbbf75a23d5 |  | note | Test frequency - Every test result
label | a1854082-b9a5-599f-8a19-6a14e0b975c2 |  | note | Contractor - H
label | 45e89e15-d49c-5fc0-a970-04f92ecdbf1e |  | note | Designer - H
label | 8d8677ca-8b07-5302-b8b4-773fb9064aaf |  | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.11 - Failed test result and remedial approval
label | 978410f7-d492-5c3f-8469-f4a587881556 |  | note | Method/Description - Review and approval of remedial action
label | da02a4e1-161d-5232-9191-1a3866fed6a4 |  | note | Test frequency - Every failed test and prior to remedial works
label | 33cf084f-b57d-5e9f-bae4-3d31aa60290c |  | note | Contractor - H
label | eb9c6464-4c79-5082-b888-caa806c04c9e |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.12 - Insitu Fill Testing
label | 82d4cdc0-3ec4-590f-bc86-5f7ca1bf3219 |  | note | Method/Description - Undrained shear Strength
label | 22c5d558-a834-51b9-8b4a-934507e56f7f |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2
label | 2e832840-edc7-5ff5-9a03-7ef3dc05c5a3 |  | note | • Buttress Fill - 1 Test per layer per 2000m2
label | eece1da6-06bd-53e9-b2c9-cbb2a26f5e7c |  | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | e8ee7147-d185-53a8-a85a-441af5ae2501 |  | note | Contractor - W
label | 1cdec2cd-06d6-5f86-8dbc-cbc21614f28f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-group |  |  | section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
checkpoint-status |  |  | checkpoint | 2.3.1 - Visual inspection for rate of filling
label | 10c4545e-de25-5a5c-a168-4f21293bd73f |  | note | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
label | 4f07bd8e-166d-5735-a1d8-267d811adfb3 |  | note | Test frequency - To be monitored daily
label | 7806a283-7d1f-5d25-bb18-147fa620e32f |  | note | Contractor - H
label | 065fbfb0-056f-5dfa-a5f8-32eff8f25091 |  | note | Designer - W
checkpoint-status |  |  | checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
label | f2efcc47-ad20-52d1-9262-78af7d76a26f |  | note | Method/Description - Review data and TARP levels before releasing HOLD.
label | 818092fa-e6cf-50c9-beae-ce0f8b8ff080 |  | note | Test frequency - Before releasing hold periods and allowing filling to continue.
label | 366a83f9-ed1d-59b6-a51d-d91de90b554d |  | note | Contractor - H
label | d1f0ba82-7efe-5dcb-b6fc-1fbdf8798d13 |  | note | Designer - H
label | 970d389c-1bce-51c8-8bd4-a427b9b4d60e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3.3 - Removal of preload/surcharge
label | 426f1f25-f038-5105-ae0b-f9faff0a44e5 |  | note | Method/Description - Assessment of monitoring and instrumentation data
label | d822bd21-2701-5001-9dd5-d8f220626730 |  | note | Test frequency - After completion of proposed hold period
label | 5e007f41-66e9-542d-aa89-517a5c49edca |  | note | Contractor - H
label | e6c88f6a-d0ac-54a6-8221-9f476f4bd4ac |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.4.0 Monitoring
checkpoint-status |  |  | checkpoint | 2.4.1 - During earth filling/preloading/surcharging
label | 0508c0c1-3b68-5298-ab26-971a6c8cdd4d |  | note | Method/Description - Monitoring during earth filling/preloading/surcharging
label | ac6e85aa-d9b7-56a1-b2d4-9ed493d69c5e |  | note | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
label | 7b43fb96-5a3d-5665-861f-a1c7fd890290 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.4.2 - During preload or surcharge hold period
label | ec8a779d-8d2d-594b-907c-c8f6dd8e0c8a |  | note | Method/Description - Monitoring during preloading or surcharge hold period
label | d60d1926-e190-5341-9c8b-a189abfec7ad |  | note | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
label | 678f212b-8a42-5868-a84c-12b6fbed5944 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.4.3 - At surcharge removal or hold period release
label | 1c573b88-3078-5933-91db-1c442ee4743d |  | note | Method/Description - Monitoring at surcharge removal or hold period release
label | 4c9e8f91-f39a-572f-a85a-6505d660fd59 |  | note | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
label | 7a325fb4-0492-5d84-bdd5-f0cbfe83eff1 |  | note | Contractor - W
checkpoint-group |  |  | section | 2.5.0 Monitoring reports
checkpoint-status |  |  | checkpoint | 2.5.1 - Preliminary inspection/monitoring report
label | b08d460d-bc6d-5fba-b22b-ad6393e8bc26 |  | note | Method/Description - Summary of site inspection / observation / measurement
label | 16ce8cc1-eecb-5edc-ae6b-8e98181bffa8 |  | note | Test frequency - Within one working day of site inspection/observation/measurement
label | 2967dff5-eddc-54d8-926c-341b575369c9 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.5.2 - Inspection/ monitoring report
label | 9f48fe2d-8360-5dda-a43f-e4871c95e452 |  | note | Report - Full and certified results
label | 3dfc2134-58ee-5b80-88dd-5c8590d4f4a6 |  | note | Frequency/timing - Within five working days of reading the particular instrument
label | 4e48e42a-eaec-50aa-90db-eb341fc3afc4 |  | note | Owner - Construction Team and Geotechnical Technician
label | 8b2b65f7-137a-56db-b113-5b69bccfff7b |  | note | Distribution - Geotechnical Engineer, Geotechnical Lead
checkpoint-status |  |  | checkpoint | 2.5.3 - Pre surcharge removal report
label | ff8beb86-d12f-5560-8246-a1c80f7c0678 |  | note | Report - Comparison between monitored results and baseline design predictions in both table and graphical format. Provide approval to remove surcharge.
label | a7d4b419-c260-5cf8-96f5-a4e0b22aa619 |  | note | Frequency/timing - Prior to surcharge removal at each fill
label | e60d8ccf-98e9-5478-985a-87c124c23c05 |  | note | Owner - Geotechnical Engineer (with Geotechnical Lead approval)
label | 6a7e8fcd-a899-5703-8f66-c8f396c9dd6e |  | note | Distribution - Design Manager, Construction Manager
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.2 - Survey As-builts
label | 5da60d60-bdd0-5bfe-b0e7-868735364dd0 |  | note | Test frequency - During construction and at end
label | 2b08a453-1ed5-568f-9545-ce3745e7ef82 |  | note | Contractor - H
label | cff27b27-0d6d-53c6-8a51-7394f8cc638a |  | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint-status |  |  | checkpoint | 3.3 - As-builts
label | 8d12136b-99b7-56a6-b8e8-423c4f932c01 |  | note | Method/Description - Mark up of construction drawings to reflect completed works
label | b5546a51-57d1-5cf1-9ae4-55734aedefc3 |  | note | Test frequency - End of Construction or after completion of preload/surcharge works
label | 79a814d3-c269-50a3-8459-acaec7673abd |  | note | Contractor - H
label | 3dd1ce46-19e3-55b4-9cd6-a7d70d14373c |  | note | Designer - H
label | 4110ec92-8b1c-5466-a377-9bccbb7254f0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint-status |  |  | checkpoint | ITP Close-Out by
label | 37d3795c-51da-5d7f-ad97-0fb503cf9c4f |  | note | Site Engineer/Project Engineer
label | 7726aa8f-f137-5131-9ccb-a0d7cb3915d0 |  | note | Zone Manager Approval
label | 9ee3c4da-5bab-5d55-ba41-2d8efd8d318b |  | note | Construction Manager Approval
label | c4b083ec-831a-54d2-ad43-5c7405c973ff |  | note | Quality Manager Approval
date | 8093829e-d2ee-5a87-9383-b08bc5ebef17 |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | ITP - Earthworks Cut 10 Rev 1 | itp |  |  |  | Yes | ITP - Earthworks Cut 10 Rev 1 | 60d4c5de-1912-4bec-920b-028b36e391da
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | bc48be59-51d4-56fc-b21d-7a6cb32fcbb5 |  | note | Method/Description - Document Review
label | dc0a6241-08f5-5c95-960a-d5199205bd29 |  | note | Test frequency - Prior to personal starting
label | 7c42040d-74de-5270-b68b-c1618021f0e1 |  | note | Contractor - H
label | 80550d88-1d7f-5a42-9ba4-9e6c647bf9bb |  | note | Designer - H
label | a797a1da-89a8-50fb-ab97-d5078decec53 |  | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | bc16f5f6-413b-51b4-8db1-afe7fd453105 |  | note | Method/Description - Document Review
label | 3d2aeafb-ab58-50b2-a8b9-32eeae3f32b6 |  | note | Test frequency - Prior to starting
label | 39ebb796-c4ac-576f-accf-8e47210028e4 |  | note | Contractor - H
label | 5b02bdf0-5912-5b65-9208-f8c1e4a2f866 |  | note | Designer - H
label | 7fcc791b-9643-54dd-99d2-d144648ea7fa |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Approved SCWMP
label | eeb04c0d-9228-58fc-81ab-814eaff9ad7e |  | note | Method/Description - Document Review
label | 68794616-9729-53eb-9736-d3d07a7198b0 |  | note | Test frequency - Once prior to works commencing
label | f069ea47-c3ce-5ebc-98a9-b33acf4dce0a |  | note | Contractor - H
label | 2217b11f-b651-5ef6-abfe-21507bdc77fb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint-status |  |  | checkpoint | 1.04 - Investigation testing (Pre-construction)
label | ea26347c-2af2-517c-832f-7bc7df459ac2 |  | note | Method/Description - Test
label | 8ebaedae-4203-553a-b1db-684bd02b5413 |  | note | Test frequency - Pre-construction
label | 90e847ae-1e62-5a4e-9d90-3d50b8a16068 |  | note | Contractor - H
label | b2d2e9e0-28de-511b-94f8-92e2b757890d |  | note | Designer - H
label | 0b107e6b-f491-5fbc-b744-969075a018cb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
label | b29182e6-ce13-521b-975d-f05d3a4ed441 |  | note | Method/Description - Approval
label | 98439c06-c1b1-50ee-b46e-2d678c7891d1 |  | note | Test frequency - Prior to commencing
label | ca107507-23a3-5fb3-a917-b15510ae1661 |  | note | Contractor - H
label | b1cb9936-c0fd-5ad6-94cc-681fd50c37a3 |  | note | Designer - H
label | 2cbf214c-1a23-50ca-8a13-30126135f510 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Headworks
label | caacb4c2-e2af-5c5f-966f-446a419bdb90 |  | note | Method/Description - Submit
label | e6c64625-15c9-569b-91f3-457de9310719 |  | note | Test frequency - Prior to commencing
label | e2c45304-13c7-5e6f-90ef-4849fb4c07f0 |  | note | Contractor - H
label | 3323592f-f20f-5c36-9fd2-c8f57c65f5e2 |  | note | Designer - H
label | 1c2cf481-15f2-5917-ab5f-c5c1df96591c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Grout
label | 2ddf9aac-ab29-5b48-a266-c8920c391f0f |  | note | Method/Description - Submit
label | a1069b04-92e8-5b54-9a75-907e1515f459 |  | note | Test frequency - Prior to commencing
label | b0f8e3c3-5180-5637-8e1b-2bfbde201efc |  | note | Contractor - H
label | a8237714-3a0c-5e47-8678-c0f6edd847c1 |  | note | Designer - H
label | 98bd1ae0-b97c-530d-a23f-442ae1599340 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Drapery Mesh
label | 2043331d-4e02-5ece-806f-9b046f12bb4d |  | note | Method/Description - Submit
label | ee5eb793-3804-5db7-8799-1527cceefac5 |  | note | Test frequency - Prior to commencing
label | 658b2b4b-f9e9-593a-aec8-02d04986b78e |  | note | Contractor - H
label | 2aa2134a-8bb2-543d-8534-56d66d96f99b |  | note | Designer - H
label | 9c0103f8-a314-5fc3-99a0-09d91e972638 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Steel Wire Ropes
label | c222faba-076b-5ef9-9206-7f46eee888aa |  | note | Method/Description - Submit
label | e1cf51d9-487e-5e40-ad8f-ef6f0f6ed23f |  | note | Test frequency - Prior to commencing
label | 5c5383cb-755e-5a80-99f0-8abc151ca831 |  | note | Contractor - H
label | dff4e656-7f6e-5f03-bed9-3babed98a051 |  | note | Designer - H
label | 247f70b2-d0d4-5909-b444-81de3eb54825 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Wire Rope Fittings
label | a64d4fba-6142-598d-a820-54614c22b38f |  | note | Method/Description - Submit
label | c23bc1ae-8e3f-509f-9d51-2bb55d7f6418 |  | note | Test frequency - Prior to commencing
label | fa39926a-48bb-5d65-b91b-4dae4ad64cce |  | note | Contractor - H
label | 77304c76-b859-5f5c-8773-454838e20149 |  | note | Designer - H
label | bd29d91d-c1ce-50f3-8b51-7eb339840f02 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Delivery of all rock drapery system components
label | 30cb1773-68a4-54e2-bbcb-2e1fb0987ded |  | note | Method/Description - Visual
label | 8ca37bc3-5f0b-5fb6-bd1e-ae05a5c8671c |  | note | Test frequency - each delivery
label | b6e1c79a-2b55-5507-80d9-72a27aa4ea79 |  | note | Contractor - H
label | 7026e32b-94ac-5e4a-8b4a-d5bd0f2aaa12 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents
label | d6756d55-6134-5739-993a-77ebccd3b557 |  | note | Method/Description - Survey/visual
label | 48d9c281-149a-5151-95f4-698240731b96 |  | note | Test frequency - Prior to Commencement
label | 4bd37f01-e1de-528a-ae6f-8b5ebe3a3ce4 |  | note | Contractor - H
label | 36357efa-9810-56b4-8445-9f7b034509b5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
checkpoint-status |  |  | checkpoint | 3.02 - Verify Machine Control
label | 11c8c659-be31-5bee-a305-af616377bbe9 |  | note | Method/Description - Survey/visual
label | 567910c2-704b-5c77-8bf3-948b742202cb |  | note | Test frequency - Daily
label | 169b49e4-68ce-571a-92c4-3da3a085f1d5 |  | note | Contractor - W
label | bf065234-73f4-5fbf-a31e-a43a64c25caf |  | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
checkpoint-status |  |  | checkpoint | 3.03 - Assess Crest detail
label | d724ec64-4a7f-5c12-8cf1-cb4d39b9b3d5 |  | note | Method/Description - Hand augers/ slope assess/Window Samples
label | 7fe631f2-4690-5dc5-8265-81a3fee74f0a |  | note | Test frequency - Prior to Excavation
label | 2f744cc2-0493-5c8e-a26e-a0611772f549 |  | note | Contractor - H
label | 311e340e-f363-5d8c-923f-7b2c12fc2abe |  | note | Designer - H
label | 8565cf56-b4f1-53ce-834b-2558b850c840 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Install crest detail - Soil Nailing
label | dbeb6aa0-2509-5992-aa06-e3eb68fbad0f |  | note | Method/Description - Visual Inspection
label | 73ba9fa3-0be6-5fdd-a45e-d2e85f4ad512 |  | note | Test frequency - Prior to cutting rock slope
label | 0a069931-8c38-51ce-876c-ca95ad696eb9 |  | note | Contractor - H
label | fa86e6e2-0840-5c5d-a248-5b3f8d6bed22 |  | note | Designer - H
label | 5c055a2e-d963-593a-9470-5dd11276c074 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Install crest detail - Erosion Matting
label | a0dc14e4-7a45-55ea-bd6a-0e756dbffefe |  | note | Method/Description - Visual Inspection
label | f9bcf0bf-54b2-558e-be72-ccaa0f4ec009 |  | note | Test frequency - Prior to cutting rock slope
label | e1d62ee2-e516-5b83-8290-0942e1e2bff6 |  | note | Contractor - H
label | d525aafa-4931-516d-98db-29fdc014b49d |  | note | Designer - W
label | c68a8a4e-b6af-569d-9c18-1abe607ff29c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
checkpoint-status |  |  | checkpoint | 3.06 - Install Rock Fall Protection
label | ce3f94e2-b6c6-5064-9dec-c3925caba8f1 |  | note | Method/Description - Visual Inspection
label | 65ccdd21-0290-5baf-994e-d6fedc21086d |  | note | Test frequency - Prior to cutting rock slope
label | f81f6583-0fb2-59e7-9a9c-5c251bbe9f51 |  | note | Contractor - H
label | c1f83483-110d-5d12-aa71-501c7e9710ff |  | note | Designer - H
label | 26bcfd9e-f2df-5ec0-89fe-2bb2d8a209d3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
label | ab0107bd-47bc-548f-9be0-0962f33b20ea |  | note | Method/Description - Survey check by construction team, visual inspection by designer.
label | 30cf4955-7959-5dc8-aadb-68ac4a615cfd |  | note | Test frequency - 100m2 or maximum 5m vertical cut
label | 32dccfc6-8b78-5974-8a87-d7f7149ce8e4 |  | note | Contractor - H
label | 8d765b57-f1a2-5c8b-adec-2c849667e6a7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
checkpoint-status |  |  | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
label | de65aaa7-f253-5fd4-a707-c06a0fe48e13 |  | note | Method/Description - Geo inspection and face mapping
label | 44080c6b-a0bb-59b1-9e51-070947693f1e |  | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | 167377c7-9603-548e-ac33-108b6fccad22 |  | note | Contractor - H
label | 05c39219-b111-592c-84ce-08db95400085 |  | note | Designer - H
label | 38c35d7e-4527-5422-9d6e-442b94bb881b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
label | bbe89ff4-e5c0-5761-b20c-56af651b86ab |  | note | Method/Description - Geo walk over
label | b56caee0-030e-51e4-b4cc-bb19d0701d87 |  | note | Test frequency - Prior to drilling
label | e7798dc6-55d3-5e7a-a901-f228d2198fe5 |  | note | Contractor - H
label | b28c1acf-8222-51dc-811f-7a0af3cb20c6 |  | note | Designer - I
label | 6514984a-1bce-528f-9f0a-dfa9564e1f09 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.10 - Install Rock Drape - Install anchors
label | 0867b240-7ac3-5d85-8357-58a4165f24b3 |  | note | Method/Description - Drill and grout records. Stressing records.
label | 6a68e547-ce55-50ac-8a9e-e6abda03ad42 |  | note | Test frequency - During construction and at end
label | 82e98677-e901-5710-962b-899c3416ae25 |  | note | Contractor - H
label | b4ebf5f9-01a4-522c-b4f7-9e49fccb9491 |  | note | Designer - I
label | 180fa315-5040-58ee-9abc-495cb5f943c1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.11 - Install Rock Bolts
label | 6950d28c-b7ad-552e-b3ce-b7ae395241d9 |  | note | Method/Description - Drill and grout records. Stressing records.
label | 65be1cfd-bff7-519d-b19a-2dc5a00f8fcc |  | note | Test frequency - During construction and at end
label | fa476613-9f3d-5dff-af3d-d7b8b201f97d |  | note | Contractor - H
label | c5249786-eb84-52c6-97c2-5a728849d713 |  | note | Designer - I
label | d7811f68-4817-5ce6-aa4e-8a0175875c10 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
checkpoint-status |  |  | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
label | d37957f8-af67-54fe-9dfa-05654a4064e1 |  | note | Method/Description - Visual inspection
label | 903c96bc-0a29-5d80-a17e-7a4234fd04f2 |  | note | Test frequency - During construction and at end
label | 88cc6d7e-c60e-5151-a779-7f4423f9dd6e |  | note | Contractor - H
label | 573d6107-e166-52dc-81bf-56c22e95716c |  | note | Designer - H
label | dd246132-a20a-598d-b0d9-5307ef6d7e0a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Production nail acceptance tests
label | 063e759f-d207-50ac-a156-71e0d6536ba1 |  | note | Method/Description - Test
label | 9e78a5ab-6e70-52a8-89b9-2fd74cff39fe |  | note | Test frequency - At Completion
label | 547b6478-a091-5734-b750-bfe6d9216e62 |  | note | Contractor - H
label | 53d51e2d-892d-5f18-ab4a-7606f93e9ad2 |  | note | Designer - W
label | 99f330d7-3913-5de9-9a07-ed7415c7931f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
label | ba2564ac-5a67-54dc-ace6-dccf2135dd58 |  | note | Method/Description - Test
label | 1492d707-b4a4-5bf8-9dfd-623ca88ef711 |  | note | Test frequency - At Completion
label | edcbcb33-6400-5d42-b32a-9c619f425866 |  | note | Contractor - H
label | b357e6c0-6487-5a5c-bd81-b26f06dd44cc |  | note | Designer - W
label | 643b3edd-725c-5027-9152-6480eec66be2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.15 - Catch Ditch Inspection
label | e1df5724-8dde-5ca6-baed-6653236a9d84 |  | note | Method/Description - Visual inspection
label | adbd8ec3-cd96-50d8-abc8-9f9b6cbe684f |  | note | Test frequency - During construction and at end
label | c310cfe2-0203-597c-8190-0f82442c175f |  | note | Contractor - W
label | f3eefe7d-4082-5338-8485-60d33d680e0e |  | note | Designer - I
label | 7addafad-14ef-5c21-8c85-6aa6f47879e6 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Throughout construction period prior to road opening
label | e587f083-cf5b-5612-b3d4-c63a37476462 |  | note | Method/Description - Monitor
label | 055d9e05-b296-559d-a78f-04d733932121 |  | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
label | 59570868-cb1b-5195-8856-a2dd4cb65fae |  | note | Contractor - H
label | a47a72c3-5612-58b0-86d3-2825f6f8160e |  | note | Designer - H
label | 9e00c7d4-adde-5450-9b0f-5eac4f84e78e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Red Line Mark Up Drawings
label | b97c3437-d842-5f3a-b53d-995594dc84bd |  | note | Method/Description - Submit
label | e3f02c82-98e2-50dc-8829-7d38a8bf2d63 |  | note | Test frequency - At Completion
label | c302beeb-9096-5042-8195-29e7b3d0796d |  | note | Contractor - H
label | 2da5465e-6715-5ecf-9eeb-edfed38638b6 |  | note | Designer - R
label | eacfc4f6-5364-5c00-8b3b-5fce3ac23ff3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
checkpoint-status |  |  | checkpoint | 4.03 - Operation and maintenance report
label | e840c5a0-cba9-505f-ac09-dda1b691da53 |  | note | Method/Description - Submit
label | d08c5825-98d6-540e-ad04-20ff9e0ba7f5 |  | note | Test frequency - At Completion
label | bda34d95-cb97-5812-9c75-e7801a3561d8 |  | note | Contractor - H
label | 12b07137-0306-5cf9-8fea-4dec86993b57 |  | note | Designer - R
label | 4a85c651-09b9-5f67-8c37-496562268e86 |  | note | Client - R
label | 21c1bcf2-76be-504f-8bd5-ea358e17ba13 |  | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
checkpoint-status |  |  | checkpoint | 4.04 - Final Handover Package
label | ce6ef1e6-8b6c-5de2-a841-d3c2041784ed |  | note | Method/Description - Submit
label | 0a02195f-9d74-5b77-b17b-7ebc0d5c04b2 |  | note | Test frequency - At Completion
label | f826b970-e166-5f89-9e18-b56274ec617f |  | note | Contractor - H
label | cc7a9247-ee97-5cbc-aba2-9388c24af2fd |  | note | Designer - R
label | 399da181-4075-53d1-9d05-62ee6e41e7db |  | note | Client - R
label | 46eea58d-5e20-56f7-aaf6-c87db6654af1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
checklist-sectioned |  |  | checklist | ITP-007 - Palisade Wall | itp |  |  |  | Yes | ITP-007 - Palisade Wall | 63c265bf-a546-41bc-8096-2c75d35bd3ce
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | ae17a6c1-46a2-550f-989f-9c932990bb19 |  | note | Method/Description - Document Review
label | bcd1878c-ec81-58b9-b27a-1f802258dcde |  | note | Test frequency - Prior to personal starting
label | b63f2dfe-8c01-55a8-9c21-3762471f75d1 |  | note | Constructor - H
label | ce694c1d-838d-5da9-9777-74c831c7d166 |  | note | Verifying Records - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | a12e9e8f-e5cf-5a64-933c-a4ab68b11a93 |  | note | Method/Description - Document Review
label | 275d9a3d-2ef2-5e00-807f-739d546ebe33 |  | note | Test frequency - Prior to starting
label | 9fe09329-56f4-554e-8897-4b3f05a26fa7 |  | note | Constructor - H
label | 54d14091-8a8f-5126-8232-9e3f864b7a16 |  | note | Verifying Records - IFC drawings or written approval from PAB
checkpoint-group |  |  | section | 2.0 During Construction
checkpoint-status |  |  | checkpoint | 2.01 - Survey Set Out
label | 574e2092-3e1b-5a23-ae41-33a3395a9869 |  | note | Method/Description - Survey/visual
label | 7a8b15bf-ee6b-5822-835c-2ffe380d46ea |  | note | Test frequency - Prior to Commencement
label | 845b40b2-6634-50cd-ad20-b6bbbd52089e |  | note | Constructor - H
label | 42070937-0609-57f0-85d4-49af8090564e |  | note | CPS - R
checkpoint-status |  |  | checkpoint | 2.02 - Steel Material Classification
label | 49c343d1-8d3a-5617-a759-6b9b03da12cc |  | note | Method/Description - Document review
label | 0bdcf704-3dc5-5dfd-9758-e40b18ea2d29 |  | note | Test frequency - Prior to commencement
label | c7124f4c-1414-5dd2-9fca-81711b642836 |  | note | Constructor - H
label | 86f81fb8-5615-5ff7-acb6-502340cdcfc6 |  | note | Verifying Records - Mill Certificates
checkpoint-status |  |  | checkpoint | 2.03 - Splicing Piles
label | 609e5639-a411-5e65-9a85-5ce1ed07efbf |  | note | Method/Description - Document review
label | 836aa4ef-df37-5c4a-8191-4a0a04bc45ee |  | note | Test frequency - Prior to welding or splicing
label | 8fe8c025-d7b7-5981-a308-af506c729cbd |  | note | Constructor - H
label | 2fa338d5-2aff-5cdf-a924-be7931f73c66 |  | note | CPS - I
label | b074dcca-8e55-52f2-9580-fdff20d1232f |  | note | Designer - H
label | 50117185-46ad-5617-9629-7b0c8d66a701 |  | note | Verifying Records - Mark Up As Built Drawings
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Piling Auguring
label | a58d2e99-2732-540a-9e33-b1d86b9debb3 |  | note | Method/Description - Visual/measure
label | 25c77358-f9bb-5079-bd8d-d7b241f6ac49 |  | note | Test frequency - Daily during piling operations
label | a8e165a6-e92c-5566-9166-966a2cde014b |  | note | Constructor - H
label | b0c4c133-5a4d-51c7-8759-e095a769fb40 |  | note | CPS - R
label | ee118550-7f3d-5f53-9949-57f2eb6af069 |  | note | Verifying Records - Piling Log
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Pre pour inspection
label | cd890e0a-16d7-5db5-992d-7ee3e7e785bb |  | note | Method/Description - Visual/measure Document review
label | 74516db5-2926-57b9-8cc1-d714a10c2dad |  | note | Test frequency - Prior to concrete pour
label | 57e77e17-00ea-50fb-92d3-b7dbbe2fd458 |  | note | Constructor - H
label | 74c8cbca-d8c9-500a-bc95-1227dbe83612 |  | note | CPS - H
label | d7d31a2f-df96-55da-99ce-5a6184ad75b2 |  | note | Verifying Records - Pile Pre Pour Checksheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Concrete supply
label | c102baee-d0fc-5c70-b55e-c0354af76818 |  | note | Method/Description - Supply docket review
label | 4ca7503f-abd8-5867-8ac6-19b7b07c2cca |  | note | Test frequency - During pour
label | 9620206b-292f-5f63-b82a-73a8d94d872a |  | note | Constructor - H
label | e0c82c1c-6bb6-5431-b9a9-62c18e1f808b |  | note | Verifying Records - Concrete Delivery Dockets and Test Results
checkpoint-status |  |  | checkpoint | 2.07 - Concrete Testing
label | efac2b73-5a69-54fb-aa30-8f562bec462d |  | note | Method/Description - Test
label | 454b7948-da88-53f4-9b2f-1ee141cda8ef |  | note | Test frequency - Each pour
label | 9e5051a7-aa92-56b3-b603-008d66dcfacf |  | note | Constructor - W/R
label | 5faeca59-31fa-508a-9a82-09c77ba029c3 |  | note | CPS - R
label | a6c78e55-806f-5458-ab23-6c2bca1e4f30 |  | note | Verifying Records - Test Results
checkpoint-status |  |  | checkpoint | 2.08 - Concrete Finish
label | 6218332a-e90d-53ba-a680-c2f5fabdfc1d |  | note | Method/Description - Visual Inspection
label | 2cf52b54-ad8d-59c0-a3e3-6ccd940ceadc |  | note | Test frequency - At the completion of the pour
label | c172a534-6452-5363-8ab4-4d5409225e3a |  | note | Constructor - I
label | 1733cb90-9297-57a7-8abc-2a487cd2f169 |  | note | CPS - I
label | fa1fa30b-1dd0-5b3b-b4c2-8f5ef1c0ebca |  | note | Verifying Records - Pile Pre Pour Checksheet
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.01 - Survey As-builts
label | d99d2f77-4932-5a67-9f6d-0352ee5513ed |  | note | Method/Description - Survey As-built
label | 51362fa7-a13c-5063-b8fd-296c51d5d96a |  | note | Test frequency - During construction and at end
label | 1410dcdb-57c7-5baf-a8ef-46ae33e8422b |  | note | Constructor - H
label | 663ee1a2-3f4e-575b-96c4-a8d2ebfc9dd7 |  | note | Verifying Records - Digital file
checkpoint-status |  |  | checkpoint | 3.02 - Red Line Mark Ups
label | c7075f55-1638-552b-a729-62475546a564 |  | note | Method/Description - Red Pen Mark up
label | 56e64a3e-3b7f-55ca-a720-88be66b549d0 |  | note | Test frequency - End of construction
label | bce71672-cac8-54a0-90ce-2675fb082c98 |  | note | Constructor - H
label | 0bbfadc7-18fc-5c80-83a3-a240ab238006 |  | note | CPS - R
label | 0ffdead6-9ba0-56ee-9a13-ca3dcd9ee36f |  | note | Verifying Records - Red Pen mark ups
checkpoint-group |  |  | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint-status |  |  | checkpoint | ITP Close-Out by
label | 1def2dee-d138-50e5-be5d-74064ede6d0c |  | note | Site Engineer/Project Engineer
label | 5555477f-fc70-5205-9277-4d8f264c7cb3 |  | note | Zone Manager Approval
label | 485e9ce9-6db1-52fd-aee4-ec60ad1fa8d6 |  | note | Construction Manager Approval
label | 756de4a5-a1b2-5d22-bc48-ab326e39aa73 |  | note | Quality Manager Approval
date | 7c9edf51-2630-5d7b-af4c-a635560f280f |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | ITP-006 - Temporary Culverts Installation | itp |  |  |  | Yes | ITP-006 - Temporary Culverts Installation | 8c4ff351-f39f-4e7c-92b9-860dcb97d380
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Confirm CWP Signed off
label | 8bcca5d2-2976-5a23-b405-c6d60403e2c7 |  | note | Method/Description - Document Review
label | 596fcf40-f136-57c5-b157-a2026b0750f5 |  | note | Test frequency - Prior to Work
label | 914272b8-2591-57ba-8b32-66cbde1c092d |  | note | Contractor - H
label | ce7bd977-6308-5ba0-8caa-bcb8124f28fe |  | note | Hynds - H
label | 5cd0f26c-3486-5983-a10b-64ebfe083bb7 |  | note | Client - H
label | a70b1538-7ab2-5367-b91b-fbad9a2c2b0b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
label | 34056558-ffa0-5201-9cbe-64991ed1eee5 |  | note | Method/Description - Document Review
label | 960eba53-f532-5268-8712-6315c1f919c3 |  | note | Test frequency - Prior to Work
label | 476a2b2a-cca6-5fe4-9472-b248f2e1ecc0 |  | note | Contractor - H
label | 5d933087-1e33-57c8-9f59-ea2d8a93b731 |  | note | Hynds - H
label | 08ecf120-7547-5d3e-9034-0795223f7415 |  | note | Client - H
label | 2c0d4747-0a14-50bd-9c2d-5f8abe5c4780 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Confirm Design is in place
label | 3fa3020d-d5fa-595b-8997-cbc3df6ab9a2 |  | note | Method/Description - Document Review
label | b55513d7-aff4-5d1b-b59f-448213c77dd9 |  | note | Test frequency - Prior to Work
label | 270616d9-4f18-5544-8286-f403e79e2939 |  | note | Contractor - H
label | ace7769b-523d-51fd-822e-b72ceeef6121 |  | note | Hynds - R
label | f29e2e19-05a2-5629-a09d-20cc11a5c036 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.04 - Complete Permit To Dig
label | af02e228-acc9-54cf-9a3e-36242cec0f72 |  | note | Method/Description - Document Production
label | 1f54f34e-5794-5d1a-bd82-926f0c86727c |  | note | Test frequency - Prior to all Excavation works
label | 6d47b75e-8b10-57e6-bbef-dc38a33cad7a |  | note | Contractor - H
label | 6150d923-7e62-5da7-ba68-907c67f93212 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
checkpoint-status |  |  | checkpoint | 1.05 - Survey
label | 9730b2b4-d46c-5e42-a1ae-692deef46d6e |  | note | Method/Description - Record inlet and outlet heights for the stream diversion. Mark out scope of works
label | 4d07a43d-8960-5c0e-b316-015a3e30f74a |  | note | Test frequency - Prior to Work
label | 5309efbf-ad8b-5a9a-99a7-38d6467979c8 |  | note | Contractor - H
label | 152f6c24-ecfe-5867-8f14-ad95ef1b88f1 |  | note | Hynds - R
label | 223ffcb4-c380-5273-b0c5-44d06cace32f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Survey Heights, Survey Mark-out
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - PKS pipe (1400mm, 900mm & 800mm)
label | b06cb1e0-db13-5f81-b7cc-421395cfedb4 |  | note | Method/Description - Document Review
label | 2de5d1f6-0b15-552b-9ae9-c60845cc3631 |  | note | Test frequency - All PKS pipes
label | 271ef182-0804-5ac6-a12d-4e5c7b25e43c |  | note | Contractor - R
label | 1e0c9aea-6f5a-5eea-b0d1-05f17118606e |  | note | Lab - H
label | dc5630ab-1c5c-564d-88fd-b67809ac8e65 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - PKS pipe fittings
label | f932ecbc-b8ee-5dd0-9a4c-7c567961ab1a |  | note | Method/Description - Document Review
label | dfbe90df-f533-5e42-a64b-e3f461674ef4 |  | note | Test frequency - All Fittings
label | 83fd9542-eb46-5a0c-b6a9-0b911ecdc1d5 |  | note | Contractor - R
label | c374d92e-68f5-52a4-97cd-cc5468747a9c |  | note | Lab - H
label | 603d3e25-09ff-5064-8c8c-ee2ec0a80ccb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Subsoil Pipe
label | 1e2c4e12-4456-54ca-98ce-23e9afca0bd4 |  | note | Method/Description - Ensure Pipes are ordered as per drawing
label | df6de802-7bb9-50a9-8aa6-8d422b96aba7 |  | note | Test frequency - All Subsoils
label | 37113ea6-9d63-5b69-9d08-41fe777895f4 |  | note | Contractor - R, I
label | a0d873da-bb0f-51c7-8c75-c371e5c812a7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.05 - Geotextile
label | 6abcee02-d71e-5353-9406-568821dc632d |  | note | Method/Description - Document Review
label | 232e368e-b197-5f21-8168-2b48ba57e51b |  | note | Test frequency - All Geotextiles
label | b11614e8-3f0a-56f2-86b2-de669b5e7fc2 |  | note | Contractor - R, I
label | 7b82b63b-2b35-561f-940e-4592ea2aa393 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.06 - Drainage aggregate
label | df6c7a2a-83f2-5829-9495-8dd85be80236 |  | note | Method/Description - Laboratory Testing
label | cdaaf44a-989d-5b0f-ae69-7240c3d030b4 |  | note | Test frequency - Embedment material
label | f58b17e0-177b-551c-9062-be0282493020 |  | note | Contractor - R
label | c099be62-f1b1-54bc-9c86-bc290562861e |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Crushing Resistance Test, Confirmation of Material acceptance from Designers
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Trench for PKS
label | 3977f772-33d4-57e6-90b8-2feb495543bd |  | note | Method/Description - Inspection
label | e8a5eb11-0157-5a7a-8fba-cdf5b9fdcb59 |  | note | Test frequency - Prior to BIDIM installation
label | 0d032c5e-9f49-589e-b2cb-52b52f4b433f |  | note | Contractor - I
label | 20752364-a489-58c8-bc4f-5a04546530b4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.02 - Insitu subgrade (foundation) Compliance
label | a8c0c653-f9d9-5249-9319-bfd0314824ee |  | note | Method/Description - Inspection
label | d3ba65cc-f58a-5014-9287-8ada3d77f468 |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | 4c222a4a-3879-512c-b4f2-6f94eba25e25 |  | note | Contractor - I
label | 70fbe8e1-f018-5077-8251-bae2e11936cb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
label | ebe45091-9fd6-522b-a2be-340c1bc986f1 |  | note | Method/Description - Inspection
label | bead50f6-cbb5-5b7e-8a8e-80b8190fa3e1 |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | 84d60d6e-d840-5b67-bb17-03d3c2d37533 |  | note | Contractor - I
label | f2c15657-8d2f-5f98-98ec-3739dee09921 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.04 - Install Bedding Material
label | 3052fcf5-adac-5953-94fe-08aee1b89c9a |  | note | Method/Description - Inspection
label | 8aa7b042-497a-5f83-84fc-56f7c3d1d02c |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | 9067b1fc-854b-53f7-bc24-12544cbb1ada |  | note | Contractor - I
label | 6f7a9cd3-1457-536c-84c2-a59272032605 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.05 - Survey pick up location and heights
label | 040d3231-b354-5c54-9ce1-8a3565693a52 |  | note | Method/Description - Survey pick up
label | fa1e1bdc-a7c8-51c8-b34b-c0d3cebcc5bf |  | note | Test frequency - Picked up location minimum every 100m
label | aefefd22-5e33-55cb-9e46-25743eaee2a0 |  | note | Contractor - H
label | 02914537-456f-5a3a-9ef0-03e65e99b61b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
checkpoint-status |  |  | checkpoint | 3.06 - Install PKS pipe
label | abf8ce50-12bd-500e-aeb4-df6600783a89 |  | note | Method/Description - Inspection
label | 244d6350-dbfb-57e3-9156-80d9806181ee |  | note | Test frequency - Checksheet filled in for every 100m section of drainage. Hynds inspection once at start of Works.
label | d6a34e46-217e-5e8e-9213-f8842cf24615 |  | note | Contractor - W, I
label | 7e620971-3b53-5329-af4f-f37450836102 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.07 - Install side support embedment material
label | 440be4b5-d534-50ef-a6c7-4f0b0b8d06e6 |  | note | Method/Description - Inspection
label | 879f454b-bd86-5b94-9a4b-775d230bda64 |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | 0ec9c69b-8080-55dc-b629-314ab5f88c15 |  | note | Contractor - I
label | b06f40dd-10f8-5f79-a209-6ebfc55208f4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.08 - Install overlay embedment material
label | 5daa1abf-1d51-5d22-8d25-b2778c9e14b2 |  | note | Method/Description - Inspection
label | 950c6c35-8e94-5d5c-b0af-42f73473c9a3 |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | a3f368f2-6f89-531e-af54-4dab17c427e8 |  | note | Contractor - I
label | b25648b8-be95-5d7a-9ead-06d5d13d43ad |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.09 - Wrap Geotextile
label | f880db3f-6fba-5897-a26e-fd6c967d1fd4 |  | note | Method/Description - Inspection
label | 1121fef9-fb6a-55e0-adc3-52a93be20d8e |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | 6fb29771-c5bd-5ccd-8242-6062b1db58bd |  | note | Contractor - I
label | 28e60a39-7acf-5806-b945-d43365d7222b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.10 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
label | dbd0b7a1-a2be-5ec2-b340-53cdc03d5b30 |  | note | Method/Description - Inspection
label | a81c3316-cd58-54b0-9aca-a135186dd12e |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | f748059f-174f-5691-9e36-6d688ef30e5c |  | note | Contractor - I
label | 5100807d-70d9-515d-94c7-ce73b075e195 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.11 - Spat Rope installation
label | 26fb15df-8f1c-5fc2-9927-977c0216bfd3 |  | note | Method/Description - Inspection
label | f389ccce-38c8-5466-a680-6cef979a2879 |  | note | Test frequency - Checksheet filled in for every 100m section of drainage
label | a3039d5f-16f3-5594-96cd-ad67855d4841 |  | note | Contractor - I
label | a32cb2d9-99d4-54bd-9179-a784e4a84c0c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint-status |  |  | checkpoint | 3.12 - Construct inlet and Outlet structures
label | 0debb97a-37cf-5e40-91c1-af9269a59654 |  | note | Method/Description - Inspection
label | 96c1baf3-ef5a-5846-9dab-4d01f267ad65 |  | note | Contractor - I
label | a831b8a8-7715-514c-b650-4b7b6359cbc0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Install culvert screen to catch debris
label | 4ab8e6dd-0aab-5add-b907-365591572736 |  | note | Method/Description - Inspection
label | 799d5670-42e5-56fe-abe7-2f3c64b5f83e |  | note | Test frequency - N/A
label | fee25ee8-e98b-522e-bb8c-9cd932df95ad |  | note | Contractor - I
checkpoint-status |  |  | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
label | d1d19c64-3d49-5249-b158-ed8c6fe54809 |  | note | Method/Description - Maintenance and Inspection Report Completed
label | d71fd21d-0ecc-5b3a-a2c5-bb49a68bac7f |  | note | Test frequency - All Temporary culverts
label | 79b5c7e6-7a1a-52ef-9bcd-2c261e157190 |  | note | Contractor - I
label | ddbff481-7bcf-56e2-802d-cec814301f0d |  | note | Hynds - R
label | 10203b48-48b9-5a03-b653-dfd45f5dc6ea |  | note | Verifying Records Checklists, Test and Supplier Certificates - Maintenance and Inspection Report including As Built Plan & Photographs
checklist-sectioned |  |  | checklist | ITP - Earthworks Cut 11 Rev 1 | itp |  |  |  | Yes | ITP - Earthworks Cut 11 Rev 1 | 923ba6b4-2e70-48f0-a850-7a114a16ca88
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | b1fad7ff-803a-5ccc-b08e-3b08fe1b815e |  | note | Method/Description - Document Review
label | 4f82afcf-2cb3-5178-bdef-5b8636599910 |  | note | Test frequency - Prior to personal starting
label | 477bfc6d-e1b2-59f6-91fa-b5b729c7fb26 |  | note | Contractor - H
label | fc53c781-f93f-5a8a-8af2-150459cde80e |  | note | Designer - H
label | 4669ba5a-f722-55d4-88da-a7c8ee26b0c4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | 7414cd06-bfd4-5b08-8d9c-868882f1f7c6 |  | note | Method/Description - Document Review
label | df232622-82aa-5c8b-a064-bab6a9ac5128 |  | note | Test frequency - Prior to starting
label | 5c031128-5597-5328-ad19-aaaad5b47d11 |  | note | Contractor - H
label | e808207a-ec6a-5faf-b001-52cce87cfc1d |  | note | Designer - H
label | 856e1b23-4389-5c76-81a3-79952ddaf593 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Approved SCWMP
label | 8302d758-3507-51c7-bd74-3fec1fca8ec9 |  | note | Method/Description - Document Review
label | 2fa7a5c0-9c3c-5968-9c3d-c460cfb90f98 |  | note | Test frequency - Once prior to works commencing
label | 8984bc8b-322e-56cd-84f3-0b3f390fff7d |  | note | Contractor - H
label | 1d52618e-7d5c-5fcb-81cf-4b6f4cf08183 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint-status |  |  | checkpoint | 1.04 - Investigation testing (Pre-construction)
label | acb1b279-f036-5da2-a737-22110f1915e7 |  | note | Method/Description - Test
label | 44cfdd2c-83ec-5966-bc4b-03a1d86ff765 |  | note | Test frequency - Pre-construction
label | 9081dcad-a9eb-5219-a16a-6e66b01bfe8c |  | note | Contractor - H
label | b345e757-6a76-5429-bdf4-513eafc3f085 |  | note | Designer - H
label | 271f2d58-979d-5cb5-9c52-91f520d57b2c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
label | ca6f43b8-9627-5249-ac3a-7305be9de7ed |  | note | Method/Description - Approval
label | 5c644dff-933a-5303-be66-5d1dc457643d |  | note | Test frequency - Prior to commencing
label | 5ab56e3e-572e-5589-a779-91794d6a8f3a |  | note | Contractor - H
label | cce6611a-8d3c-5ad5-b38f-f63fd4c364bb |  | note | Designer - H
label | 1a88f3cb-fb91-5e16-9dec-f83d12be280b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Headworks
label | d9de3895-65d3-5102-9c12-f6cbe933a946 |  | note | Method/Description - Submit
label | a54b1b4a-b37b-586f-8a52-a59b0e3b6b45 |  | note | Test frequency - Prior to commencing
label | 9420614b-c948-599a-b388-0c00c2f6d975 |  | note | Contractor - H
label | ae5bb703-3a51-5555-ba0b-3cdea91e7c34 |  | note | Designer - H
label | 3be8ddbe-17f7-5542-b701-a14a414ba984 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Grout
label | 4a770ebe-19e6-5c27-8934-c6cdfafea7f2 |  | note | Method/Description - Submit
label | 8705f591-481d-5c5f-ac71-36307f1e3849 |  | note | Test frequency - Prior to commencing
label | 16b7000c-65c1-5474-9720-6c422c7c742a |  | note | Contractor - H
label | bc0b3552-4452-5d37-a664-1c8f76e47c3b |  | note | Designer - H
label | 4a11efe0-1eea-52d0-a966-bbc29bb1a3a0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Drapery Mesh
label | acd84c6d-7554-583c-ac9d-75cba1301815 |  | note | Method/Description - Submit
label | 681f141f-b4ea-500a-914c-0a354544fff4 |  | note | Test frequency - Prior to commencing
label | 04a39f40-71eb-54d0-8306-4145b014d292 |  | note | Contractor - H
label | 34a77a80-27df-5e08-8c36-d2d1766240bf |  | note | Designer - H
label | 4a9d731e-8a58-5e33-b68a-f1a186a350d1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Steel Wire Ropes
label | 3c1b16ad-367e-5955-b0eb-ff8929f2ca71 |  | note | Method/Description - Submit
label | 3266bd59-f3e7-513a-8f67-2b97573bc11d |  | note | Test frequency - Prior to commencing
label | 464b5fb2-74d5-5bad-8a35-87c94bb02f73 |  | note | Contractor - H
label | 07410b86-7042-5a21-9404-87a223af013e |  | note | Designer - H
label | cc8b2eb4-b347-5003-a896-beffe655bbe6 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Wire Rope Fittings
label | 106f13da-3692-56c2-ab2b-55339fd12add |  | note | Method/Description - Submit
label | bccfcd0d-fee1-56cc-9046-b749b1a4a7f6 |  | note | Test frequency - Prior to commencing
label | 98bd4566-9caf-5297-b1e0-b392ec747ae4 |  | note | Contractor - H
label | 86d7c5e5-f969-5ce7-b561-16d2c84f11d9 |  | note | Designer - H
label | a415d7d2-cb44-5a57-8ee3-5620fed597c5 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Delivery of all rock drapery system components
label | 988ad208-1991-53ea-9e22-52194473970b |  | note | Method/Description - Visual
label | 7367c886-66da-5c98-bb24-84e42834d071 |  | note | Test frequency - each delivery
label | e65c8cab-bb0f-54e5-a8e7-b9d1c1e3643b |  | note | Contractor - H
label | 98e02821-4d13-5a72-8867-d446ccb95ac2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents
label | 49cd5c1e-60bc-5f82-a464-c6e0f2b7d2e4 |  | note | Method/Description - Survey/visual
label | 8fd8400d-40ab-5fa1-a4a5-911f2da2a6de |  | note | Test frequency - Prior to Commencement
label | 2483fe1a-04aa-56b5-8d38-44e41150008f |  | note | Contractor - H
label | 54e6359e-a127-5298-b127-d24b16dbf314 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
checkpoint-status |  |  | checkpoint | 3.02 - Verify Machine Control
label | 75ba54b3-be2d-5f79-a5bc-5d777d4da1d5 |  | note | Method/Description - Survey/visual
label | 7057cfed-7cb0-5096-b32b-5146720b38c5 |  | note | Test frequency - Daily
label | c04e23a6-f2a9-5a31-9d60-f02093f7fbd7 |  | note | Contractor - W
label | 193da519-1119-5eaf-9b24-a9daf8b62723 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
checkpoint-status |  |  | checkpoint | 3.03 - Assess Crest detail
label | 0e1f3103-223a-5bd1-a5c2-3e0887e92c18 |  | note | Method/Description - Hand augers/ slope assess/Window Samples
label | 40f432c3-865f-57eb-9480-2b866436de34 |  | note | Test frequency - Prior to Excavation
label | eee1da58-0e15-5ce8-9080-b12b6b5e369c |  | note | Contractor - H
label | 6b462512-412e-5e21-9186-2bc6fcb4402a |  | note | Designer - H
label | c9a6d1ea-20c6-5127-95cb-7b7b3b8989a1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Install crest detail - Soil Nailing
label | bd5f6714-437c-5e0b-8fa0-2ac1abb95130 |  | note | Method/Description - Visual Inspection
label | 09bd57a7-386e-54ea-8aea-eb89ae180256 |  | note | Test frequency - Prior to cutting rock slope
label | 47308621-5616-569f-8467-12109682e986 |  | note | Contractor - H
label | 5ba23382-806e-576f-9e66-d665079a48c4 |  | note | Designer - H
label | 1e6ec9af-863a-56a8-b01b-07653c1016a0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Install crest detail - Erosion Matting
label | 56fa8d6b-ff1b-50bc-ba83-87d3e4e74c0a |  | note | Method/Description - Visual Inspection
label | f591bc59-356f-5fb3-8495-b834eaeb9571 |  | note | Test frequency - Prior to cutting rock slope
label | 16d26ec6-8894-5b24-a272-ade1f595619c |  | note | Contractor - H
label | 54c900c2-b267-578c-b3d1-1f4a6c28b5e5 |  | note | Designer - W
label | 8c744a2b-2505-5585-a998-9fb4b689b3dc |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
checkpoint-status |  |  | checkpoint | 3.06 - Install Rock Fall Protection
label | ea4cb283-b495-579e-baf8-4271b0d30dfd |  | note | Method/Description - Visual Inspection
label | a674cd62-4918-58e0-b211-e2995f85d3d2 |  | note | Test frequency - Prior to cutting rock slope
label | ef52c3d5-3cef-5eb7-8830-13f5aa3832de |  | note | Contractor - H
label | 3edd6dbc-3f15-59d3-91d7-50b27d5a8db3 |  | note | Designer - H
label | 96245b6d-0b21-582d-a684-28ddfba09100 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
label | 4bc41b04-010c-567b-b5a3-5e423813fdd7 |  | note | Method/Description - Survey check by construction team, visual inspection by designer.
label | 75f8e66b-fa38-51ed-a727-d4e3df0842db |  | note | Test frequency - 100m2 or maximum 5m vertical cut
label | 20d1d63c-34a5-51c5-96f8-cd5bcde77f5e |  | note | Contractor - H
label | 6f77a6b0-a4ab-54d1-9071-3c5112fa9551 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
checkpoint-status |  |  | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
label | 537f4c6d-7354-5888-8cd4-20c5992041c4 |  | note | Method/Description - Geo inspection and face mapping
label | 5601228e-f9d1-5341-bcd0-d4be9e7d2f25 |  | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | d958c49d-aab8-53fe-91ca-ed57d41e11d7 |  | note | Contractor - H
label | d414aeb5-c69a-5fd9-aeae-6cbe2b711898 |  | note | Designer - H
label | b20dd8cc-529a-557c-8f0f-3c2dfbf6d988 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
label | c7d53db2-e394-53ca-af70-3dd26c659092 |  | note | Method/Description - Geo walk over
label | 5608c886-1c2b-5c96-a9e4-2903b884aab0 |  | note | Test frequency - Prior to drilling
label | 6f1302dd-c012-512b-bc95-607a2d33c64f |  | note | Contractor - H
label | cb0d9175-8427-5480-b122-f9fb089251eb |  | note | Designer - I
label | 6060d47a-0fdf-51b3-8c9e-02d0b9ec0e10 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.10 - Install Rock Drape - Install anchors
label | 27be02ff-ed41-5ae7-9005-275aa0aa64ed |  | note | Method/Description - Drill and grout records. Stressing records.
label | d945a3b2-c620-54ac-a922-8a5070b921d2 |  | note | Test frequency - During construction and at end
label | 8e6327c7-ac9f-5e0c-b4cd-f0f0619f2c59 |  | note | Contractor - H
label | ca733476-b29c-5587-8443-f3efd8b15d6e |  | note | Designer - I
label | 5e333f46-cd10-5082-8f46-e9e69c3664df |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
checkpoint-status |  |  | checkpoint | 3.11 - Install Rock Bolts
label | c350baa5-ff11-5131-9afc-26a5d5a36913 |  | note | Method/Description - Drill and grout records. Stressing records.
label | 148250f7-0f3a-53da-8e53-f1f037f2bfad |  | note | Test frequency - During construction and at end
label | 1ca6b708-0311-5960-bb83-065267ef316e |  | note | Contractor - H
label | 29a5a25f-a94e-5ab7-b8d8-b1a96f6b97f8 |  | note | Designer - I
label | 972ed810-2c08-5f16-8142-850443ee8ef7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
checkpoint-status |  |  | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
label | 23811254-3126-518a-b5be-52d3a0f38975 |  | note | Method/Description - Visual inspection
label | b8416c23-dc9d-5221-9455-201a0f193fab |  | note | Test frequency - During construction and at end
label | d2dfdf2b-78aa-56a3-b4b9-2fdd54c60688 |  | note | Contractor - H
label | e539b1e1-f155-5080-ace3-2b173d13d54c |  | note | Designer - H
label | c65d67f4-ebc6-57f8-a5c8-46c0cbea90fa |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Production nail acceptance tests
label | ad3791a9-5701-5f4e-a992-9e3a83362044 |  | note | Method/Description - Test
label | 6ab205da-96ce-571f-98bc-01e88d7e6d6d |  | note | Test frequency - At Completion
label | 0fabf57d-cf44-59d8-bc64-e29bd882d222 |  | note | Contractor - H
label | 8e339fc2-cfc8-521e-acd8-1daacdd978e2 |  | note | Designer - W
label | 1c6ed97e-7a3a-5b9a-a09a-d7a252afe358 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
label | 709895e6-45da-5aae-afb3-5e34093e26dc |  | note | Method/Description - Test
label | b2c8f36f-51aa-56d7-87b9-70cb9bbff5d9 |  | note | Test frequency - At Completion
label | 94b101c3-9207-5216-8279-f080112ad4dd |  | note | Contractor - H
label | feebd5e9-b22d-57cb-86f6-17a3b934734e |  | note | Designer - W
label | 1489c9d4-5f23-52e2-ad0a-6bdd6596ff7b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
checkpoint-status |  |  | checkpoint | 3.15 - Catch Ditch Inspection
label | 3ccf1c46-1927-5aa3-9c46-9d03592b571c |  | note | Method/Description - Visual inspection
label | 37479323-9a9e-5f99-8ae8-1790884d2960 |  | note | Test frequency - During construction and at end
label | 49046ca7-dd7e-5db5-9858-7a74bf1199ba |  | note | Contractor - W
label | a80f656a-a39d-5c07-941f-49d7b2657fb3 |  | note | Designer - I
label | 5e3f2a42-8a79-59ca-acc4-1d727bf6aebb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Throughout construction period prior to road opening
label | 89173973-a9e7-5c1c-a2c2-3f9f94544d8c |  | note | Method/Description - Monitor
label | f1d1b15f-b628-53ae-9b89-7f213ceba39c |  | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
label | 70c05cd3-6064-5a80-9bbc-dec525798450 |  | note | Contractor - H
label | 08c3d0bf-a1c4-547c-8892-4a2e766e11a9 |  | note | Designer - H
label | afc5c1a9-481b-521c-a78f-b29dfc05b253 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Red Line Mark Up Drawings
label | 0e4e143a-586f-57b0-a93b-bb161f194936 |  | note | Method/Description - Submit
label | d4cd4b5c-b538-5063-8453-5d789a3296a0 |  | note | Test frequency - At Completion
label | 232ba076-fe42-5073-9541-fcf35a3d56f8 |  | note | Contractor - H
label | d6b22be6-3cc6-5995-ab19-7d14eaffa301 |  | note | Designer - R
label | 94e9bb2e-c40b-5e0e-b41d-8dd39a542c04 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
checkpoint-status |  |  | checkpoint | 4.03 - Operation and maintenance report
label | d9db6970-c2a7-5ad7-9935-26f2a7560e87 |  | note | Method/Description - Submit
label | 04165cb4-b18f-5f44-937a-19c3fd6fbf8a |  | note | Test frequency - At Completion
label | 1282451b-59fe-5a7c-9dcc-91015835a4c3 |  | note | Contractor - H
label | 75292e76-3431-59b5-954c-a4de7ab28c72 |  | note | Designer - R
label | bdaf33fb-87c3-50cb-a1fb-db2b88ad2acb |  | note | Client - R
label | 776511f7-6a04-55c3-a70a-df7ad701ad28 |  | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
checkpoint-status |  |  | checkpoint | 4.04 - Final Handover Package
label | afa7a847-29b9-591c-8c8d-216dc16fe10c |  | note | Method/Description - Submit
label | 06b2cb67-a71c-512a-87de-a950c359f8ae |  | note | Test frequency - At Completion
label | fbe6a94a-920e-5a3b-908c-88b77ccd6cb3 |  | note | Contractor - H
label | 32d9d3d3-fbcf-5f38-8f70-4f777f2f583a |  | note | Designer - R
label | db1a03b0-e403-5962-b6f4-78d6f0bf21a0 |  | note | Client - R
label | 61137bd5-866e-5fb8-888d-97b6e2bf7547 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
checklist-sectioned |  |  | checklist | ITP-003 - Subsoil Drainage Install | itp |  |  |  | Yes | ITP-003 - Subsoil Drainage Install | a8522bb4-ee4b-4459-b361-a9f54ede29bc
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Confirm Method Statement Signed off
label | 411bd5c4-b550-5426-8642-6e9d38cedd5a |  | note | Method/Description - Document Review
label | f6ff0115-1f4c-5d65-84e0-4a72c28bf9ca |  | note | Test frequency - Prior to Work, Once
label | b9764723-8ab4-5c67-9161-c65c2a44bca2 |  | note | Contractor - H
label | a3fc211d-6b84-5b39-a13a-b983ebbf904c |  | note | Designer - H
label | 7e6343fc-ee4e-526f-9ad7-299d1c34eb9b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
label | 420fd7b7-423b-5959-993b-c73d42531c56 |  | note | Method/Description - Document Review
label | c0e5bc45-3814-5ff4-8b3b-a565b622cff6 |  | note | Test frequency - Prior to Work, Once
label | 8bc82449-2207-5d7a-96f3-793f9ca06ac7 |  | note | Contractor - H
label | ee6e2cd8-d98a-5e50-8c59-1804da061700 |  | note | Designer - H
label | d9d381ec-bfa8-5bee-899c-969666ee4ecb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.03 - Confirm IFC Design is in place
label | 5cbb18ad-918d-5405-baf8-81fe5da2b49a |  | note | Method/Description - Document Review
label | 44f5de07-bec1-5e35-9c1d-3dbfd9464002 |  | note | Test frequency - Prior to Work, Once
label | 3e53d722-fa25-56af-a398-678a5682fc0e |  | note | Designer - H
label | 52e4814e-6fe0-54f8-8f1f-0538178473a1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings Issued
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - Complete Permit To Dig
label | 6c102f09-b37e-5afb-9f26-f77c2b9aaf0b |  | note | Method/Description - Document Production
label | 7fa5eb99-b91d-5ad4-a556-531062f8850e |  | note | Test frequency - All Excavation works
label | e699e163-c0cf-5681-8f18-b79553cb4f80 |  | note | Contractor - H
label | 22edda1f-88cd-53b8-aea5-1fcfe52e7623 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Order Subsoil Pipes
label | af305bec-6dca-5765-b4f2-db988afa71b5 |  | note | Method/Description - Ensure Pipes are ordered as per drawing
label | 58b89afa-b730-5c29-8e64-326ba59444aa |  | note | Test frequency - All Subsoils
label | aaf13ecc-db2a-5c90-b8f9-81bdf5689aee |  | note | Contractor - R, I
label | 4c61e2ae-16c6-515a-ae67-2009a7fad8cd |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Material Complaince Certifcate/Data Sheets, Material Delivery Inspection Checksheet
checkpoint-status |  |  | checkpoint | 2.02 - Order Geotextile Material
label | 89d6f497-7bfc-594c-8eb7-f5bf197f03de |  | note | Method/Description - Document Review
label | ed503d8c-d3ee-56a7-95a4-7d45becbd6f0 |  | note | Test frequency - All Geotextiles
label | 6dab2856-732b-5149-bb06-32b809f5eebd |  | note | Contractor - R, I
label | f6b1b5ff-c92c-5653-ab33-115f67ed0fb4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Complaince Certifcate/Data Sheets, Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.03 - Order Subsoil Drainage Backfill Material
label | 622bff40-4a90-54e1-ac66-8edb6738428f |  | note | Method/Description - Laboratory Testing
label | c03b408a-b9c9-5dde-a71e-959b63c50f10 |  | note | Test frequency - All Material
label | 6e3b59f8-2e8a-5963-b6e3-3d0ed4beccf3 |  | note | Contractor - R
label | fffe0c0f-4766-5f30-bcb7-3d94a3257e7b |  | note | Designer - H
label | 06f57223-d4a2-5114-841e-5138808b0dbf |  | note | Lab - R
label | 31c62d6a-1468-5b2c-a597-e96682946414 |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Permeability Test Results, Crushing Resistance Test, RFI - Confirmation of Material acceptance from Designers
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Order FarmBoss Pipes (Temporary Drainage)
label | 30bbcc20-5408-5d2e-bbb9-6a5cc69851f3 |  | note | Method/Description - Document Review, Material Delivery Inspection
label | 097d041c-1f47-517b-ba4d-56ce9da6c904 |  | note | Test frequency - All Pipe
label | 54e4c6d4-86dc-5dc4-8573-38697687ca70 |  | note | Contractor - R, I
label | b2774fba-4484-5c97-9af9-b270674f6e74 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Delivery Inspection Checksheet
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Clearing and Stripping of Area
label | 54a0b372-b788-5f8c-8fd7-89a9b8adf917 |  | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
label | 7eba61e1-a678-5b88-9a49-d2db0087350f |  | note | Method/Description - Removal of Organic Material
label | bdb87169-5d7d-5d33-8552-99ef9253825d |  | note | Test frequency - All areas. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 8d14f524-c053-58df-8c51-56f43d393668 |  | note | Contractor - I
label | cce81a3b-409a-51fc-9e95-83e31b1880d2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.02 - Formation Level Inspection
label | f3036a5d-b13c-5a63-88a3-3ad0e220544f |  | note | Method/Description - Visual
label | 73ba8bc8-6bab-599d-880a-2e0ac03881d2 |  | note | Test frequency - At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid.
label | c5c8c29f-0e83-5d1a-bd36-890b925bcb8a |  | note | Contractor - H
label | 12b260a7-1688-5966-a01b-82021a9ef5d8 |  | note | Designer - H
label | 908813d1-8520-5971-8f63-9195c1247d12 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
label | b0109de6-b404-5c76-83d0-ee683c2dfc73 |  | note | Method/Description - Inspection
label | 8a80bde1-54b6-543b-b6c2-cda6cba54adf |  | note | Test frequency - All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 24ab384e-d96a-5aee-8fd9-df1dbc3afed3 |  | note | Contractor - H
label | ebdc72b7-9bbb-5a3d-a0bd-4a4bcb2818a5 |  | note | Designer - R
label | 21353ae2-3c95-5f46-a40e-3f9a08d0b24a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.04 - Install Bedding Material for Subsoil
label | b1b5b860-f0e8-59d4-8346-be74e228a313 |  | note | Method/Description - Inspection
label | 1932a309-a32e-55fc-93d9-935909f265bb |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | b5aa431b-d802-58d1-9bbb-f308f7575c4f |  | note | Contractor - I
label | 9d45cff1-e3db-556c-af76-eccfe60a67a3 |  | note | Designer - R
label | a401c1cf-1d25-578f-a88d-dddeb91d97c4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.05 - Install Main Gully Subsoil
label | d93d3077-04f3-546b-b3be-ac4b4e79bcd9 |  | note | Method/Description - Inspection
label | 674c2c76-db0e-5354-9d19-d1bba290b267 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 70ae588f-5643-5ac0-b22f-66abfa02029d |  | note | Contractor - I
label | 6726ff69-0b15-5532-9c98-d9bc9e2801b3 |  | note | Designer - I
label | def36970-6afd-5238-9837-484c1143cf7b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.06 - Install 450mm FarmBoss (temporary Additional Drainage)
label | 8b8f3e16-dd01-5675-92a4-435fab8755d0 |  | note | Method/Description - Inspection
label | 8fbebcb2-31f7-5f10-b82e-ddee47f53f77 |  | note | Test frequency - All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 6dfe1a21-1962-5a75-b326-ae092497b44c |  | note | Contractor - I
label | aed160f8-f5ac-58c1-a9fd-a2328f4a380a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.07 - Install Backfill Material
label | b4e7f7da-0ff1-5759-9d07-6a0864cfeec3 |  | note | Method/Description - Inspection
label | 4b40a2a4-a5b6-5991-bf26-b9638cf60226 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 95d1b2f7-f730-57c0-9193-1e90daff09ff |  | note | Contractor - I
label | a058d4fd-902f-543e-a36c-8526c32e317e |  | note | Designer - R
label | 41c9c328-47f6-593f-8583-164ac40798a2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.08 - Install Vertical Subsoils and Connections
label | 70d540f5-3674-5eb4-9939-8a266b433505 |  | note | Method/Description - Inspection
label | 3025783b-2ad7-52b3-b7d8-46663eff93c3 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 593fd4d7-8d4c-5b1a-854f-d31948c4321e |  | note | Contractor - I
label | b0b52af5-2717-5265-adcb-6f49bfc656a4 |  | note | Designer - R
label | 026816eb-1786-5f1e-961b-799c1ca2c9aa |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.09 - Install Additional Vertical Subsoils
label | f73c7e64-4c1d-577d-8897-de04a5088be1 |  | note | Method/Description - Inspection
label | b698bbae-bbee-51e0-a8d4-9e6765faddd9 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 4bbb6a7d-4a4e-55e4-a0cd-1800f317b7d1 |  | note | Contractor - I
label | e6260eb6-b8f2-5558-8c53-26626c1ca0a2 |  | note | Designer - R
label | da5d75ec-f13e-5505-ba75-0d4508d09075 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs, As built, Formal correspondence
checkpoint-status |  |  | checkpoint | 3.10 - Wrap Geotextile
label | b951fc49-e9bb-5569-a949-395e600ee30a |  | note | Method/Description - Inspection
label | 1c01c10c-9fa7-58ab-8b6b-3fb8505c1baa |  | note | Test frequency - All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 8a4e6575-67ed-5e13-9a2a-850167260611 |  | note | Contractor - I
label | e073d395-68ca-51a8-8020-9c1788f97bb9 |  | note | Designer - R
label | f54484f6-89d0-5be0-90bd-3c34df2a0802 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
label | 14bcfb28-8ee2-59d4-98f6-b3db43730e62 |  | note | Method/Description - Inspection
label | 1860d7b7-3a54-5c3c-85ba-ecb2572989b9 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | dfea8ab4-fa9e-50fa-b290-3ce40295a690 |  | note | Contractor - I
label | d31434ef-14ff-5ac1-8c82-8d3cddfb7331 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 3.12 - Construct Outlet structures
label | 5339cc5e-3443-5fec-bdd4-21e0f10d5a58 |  | note | Method/Description - Inspection
label | 668a31e4-9a76-5145-8e78-0956646d97a8 |  | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | 78b9c36b-690c-5484-b0a6-77e3f0dc8fcc |  | note | Contractor - I
label | d6830253-1bb1-55e1-9676-884360d4f7bc |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Completion of works
label | f02a4548-7e0b-51e6-a9f6-074e47f3d4c0 |  | note | Method/Description - Inspection
label | 5cd33b37-6710-54c6-ad63-77e8e0294792 |  | note | Test frequency - All Subsoils
label | a0972601-b0f8-5893-800a-3405c5695e7f |  | note | Contractor - I
label | a7e369d4-7517-5cb4-953c-c8ee47bd25ca |  | note | Designer - R
label | 3d4b2ee6-962e-5c38-9871-4f195c3114c3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint-status |  |  | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
label | cb221f93-58c1-52bc-8de9-adf7abe7dea6 |  | note | Method/Description - Maintenance and Inspection Report Completed
label | d7776e28-748f-5c55-bf04-2ececb274d93 |  | note | Test frequency - All Subsoils
label | d00a9801-7a1c-5d96-9a3b-1d01d832ceaf |  | note | Contractor - I
label | 92feb325-2ac3-5e68-a22c-4ee3742ece37 |  | note | Designer - R
label | 5ef0b631-7bc9-56bc-b929-46845b742467 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As Built Plan, Redline markup
checklist-sectioned |  |  | checklist | ITP - Fill 14 Bored Piles | itp |  |  |  | Yes | ITP - Fill 14 Bored Piles | c40449f2-a55f-4b76-9f4e-e19cbe38c2df
checkpoint-group |  |  | section | 1.1.0 Pre-construction approvals
checkpoint-status |  |  | checkpoint | 1.1.1 - Construction Environmental Management Plan
label | 61f29001-2f6b-5f44-89ee-d3b6c75a68c3 |  | note | Method/Description - Document Review
label | 1979e6b6-2b49-5aab-a971-55eb8ec20d46 |  | note | Test frequency - Prior to work starting
label | 542bdc72-8916-5c27-9f28-b39a18838a6e |  | note | Contractor - H
label | 55483e7d-69c6-525e-a54c-5057482cf97f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint-status |  |  | checkpoint | 1.1.2 - Construction Work Plan
label | 7e2b4418-314b-5306-b852-0e4e8ebc5a50 |  | note | Method/Description - Document Review
label | e8e1bed6-d40a-5654-8031-a3e78ea8fb19 |  | note | Test frequency - Prior to work starting
label | a31a4aec-69e1-5557-9d93-1d36e6eae9a4 |  | note | Contractor - H
label | ed40b710-a115-5a72-be30-2b3aa015cb9f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.1.3 - IANZ accredited testing organisation
label | a0c6841f-08e1-5aab-8422-463014b24441 |  | note | Method/Description - Document Review
label | 7955328a-9d87-521b-8490-bc968db8e258 |  | note | Test frequency - Once prior to works commencing
label | ec5fdf51-9b3e-5d73-8111-94b406304b45 |  | note | Contractor - H
label | d0cf77e1-01be-5dfc-8714-1d5ca8f01a0d |  | note | Designer - H
label | b7437ca6-4dd4-583b-b6a7-135edcb68c09 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.4 - IFC drawings
label | d92449ef-a0e2-57b9-ba4c-0ef09385e607 |  | note | Method/Description - Document Review
label | adef6486-4c99-5e70-bf30-db4a260e3350 |  | note | Test frequency - Once prior to works commencing
label | 1bb47dfe-220b-53f5-acb7-f57a3786599c |  | note | Contractor - H
label | c5038424-94de-503b-a6d5-a0cee48147f5 |  | note | Designer - H
label | 9394898e-12e1-53a6-a288-6ce480077786 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.5 - Survey Set Out
label | 89b1451d-6032-5004-ad56-d50d10a1da2d |  | note | Method/Description - Survey Set Out
label | 19afcdaf-ebb2-5ee7-8a54-c780b1bf4329 |  | note | Test frequency - Prior to work starting
label | 10693596-1e59-58a5-bdfc-1ea2f43cac45 |  | note | Contractor - H
label | 2c5cbfcb-b67a-5693-94f6-f65e009615e3 |  | note | Designer - W
checkpoint-status |  |  | checkpoint | 1.1.6 - Piling Platform
label | 123101ef-c100-51d0-8864-da9ac1295cda |  | note | Method/Description - Temporary Works Design Engineer to sign off permit to load prior to loading
label | 84d51347-9381-5962-b1ef-520ae16a07d3 |  | note | Test frequency - Prior to works commencing
label | 83f82ca9-6b2c-552a-be05-aa15582e7ff9 |  | note | Contractor - H
label | ddc1f0b2-79e2-56b9-a123-fbb0e7d8c8ff |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Load
checkpoint-status |  |  | checkpoint | 1.1.7 - Method statement and piling programme
label | bf779b64-86ce-5d67-a9fa-c4bc5bc49546 |  | note | Method/Description - Document Review
label | 740302f8-2624-506c-9d2b-3d0aab501916 |  | note | Test frequency - At least 1 week prior to work starting
label | 35917cb2-238b-5625-a3b2-526c61c44dac |  | note | Contractor - H
label | ff98f96d-5c76-5cc2-ab40-cc31f3e01460 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1.8 - Piling supervision
label | 7433a21a-8085-568b-a6ee-2eca876e0a49 |  | note | Method/Description - Nomination
label | 9a563578-bf0e-5e15-a3da-b3df15c9360e |  | note | Test frequency - Before construction and as necessary until the end of works.
label | ad5daf7b-e249-52fa-b4a4-cd93dac11087 |  | note | Contractor - H
label | efd0317d-2630-5f8a-81ae-c8d302a5a62f |  | note | Designer - W
checkpoint-status |  |  | checkpoint | 1.1.9 - Observation
label | 210e898e-ec94-503d-8632-89ae8e068efc |  | note | Method/Description - Contractor to provide adequate notice to enable DSR inspections
label | 794890df-a9e1-50bd-80da-db0266d6eaa2 |  | note | Test frequency - Daily during works
label | 705e9a5a-190f-5494-9709-fed5821feb54 |  | note | Contractor - W
label | c36d910e-1336-5133-b7c0-e60b9a76429d |  | note | Designer - W
checkpoint-status |  |  | checkpoint | 1.1.10 - Tremie check
label | 19ac1f51-a21f-5f49-b25a-a9d2d422855a |  | note | Method/Description - Confirmation of tremie sizing as outlined in section 2.1.5.2 of the specification.
label | 29b8670f-b6a5-568a-aa15-7fcfa7ee91e6 |  | note | Test frequency - Once prior to works commencing
label | 2894aacd-7fa9-55dc-a24e-c88a1582d48a |  | note | Contractor - H
label | 4ff67e2d-67d0-582e-87ca-9a340aad4c9d |  | note | Designer - W
label | fe747f01-0a46-5e2c-a367-ef3d708d8f2c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Record
checkpoint-status |  |  | checkpoint | 1.1.11 - Design of temporary casing
label | f9033219-e97a-556f-a9c0-aa9efef5c441 |  | note | Method/Description - Contractor to complete detailed design of temporary casings
label | c0307b7e-179a-512b-a284-ce910aed44a3 |  | note | Test frequency - Once prior to works commencing
label | 6102ec7f-db98-598c-a226-440d95c8251e |  | note | Contractor - H
label | e28a844e-26a4-50d0-b2e6-83e38df40ce6 |  | note | Designer - W
label | 0163946d-ab1c-5072-99de-f4721af2f050 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Record
checkpoint-group |  |  | section | 1.2.0 Material compliance
checkpoint-status |  |  | checkpoint | 1.2.1 - Concrete Mix Design
label | cf2648d0-6b87-5ce4-b8b8-1d3056a62246 |  | note | Method/Description - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 1 week prior to placing concrete and approved before placing concrete
label | 784a5273-6bac-5abe-8bb5-d89827971949 |  | note | Test frequency - Prior to commencement
label | 0aa927b5-4394-5714-8115-cf509b018f72 |  | note | Contractor - H
label | 1df17266-2625-53bd-8b62-0d8f8eb4036f |  | note | Designer - H
label | e75e3944-7847-51a4-b7be-c0f97bfb7542 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Mix Design Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.2 - Steel Reinforcement
label | 026db90b-3cf1-5d38-9422-b7eb53d1afa8 |  | note | Method/Description - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | f82df01f-6a5e-5434-93ea-d10acb7a27bb |  | note | Test frequency - Prior to ordering steel
label | 55186262-1c98-5e23-9be7-89901af2d985 |  | note | Contractor - H
label | a606cafa-bb69-5e0c-9c10-aaff2ea67011 |  | note | Designer - W?
label | eb21abb0-a29c-5168-9558-21ad6f0b90ba |  | note | Verifying Records Checklists, Test and Supplier Certificates - Mill Certificates, Detail Sheets
checkpoint-status |  |  | checkpoint | 1.2.3 - Welding of Reinforcement
label | c66861a3-8187-5b7b-bddb-ab4ba160dd4f |  | note | Method/Description - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | cbeba099-6de1-57f0-9082-d4acd05e3ac8 |  | note | Test frequency - Prior to welding or splicing
label | cb48a9f1-34ae-5bc4-b0db-6b963baf4d23 |  | note | Contractor - H
label | 0942976b-6654-55b2-82f7-355f8f978c42 |  | note | Designer - H
label | cce9ce8d-89d8-5ddb-82d2-6b08fabd5d05 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.4 - Welding of Reinforcement
label | 6b2f537f-f13c-5bd0-ae12-ecac410b0c1e |  | note | Method/Description - 100% Visual Scanning of all welds
label | e3104864-ddab-54a7-81be-dd81f128505f |  | note | ○ 100% Visual Inspection
label | 4227338d-84f0-5668-98b9-5646c15de346 |  | note | ○ 10% magnetic particle or liquid penetrant
label | 34e0972a-e00f-52d9-ba4a-97a653933e68 |  | note | ○ 10% radiography or ultrasonics
label | 802bc5e1-ff2b-594b-af26-22a542622511 |  | note | Test frequency - Each Weld
label | 269fcb9f-d7a1-5f17-82d8-86945d5a2211 |  | note | Contractor - H
label | ad057760-ba2f-5992-ac93-d5f145482b7a |  | note | Designer - W
label | 180ede67-7f2d-567b-9c92-58a37a63cb9e |  | note | Lab - I
label | 2cc856a7-52dc-54f4-a3f8-c0c4e5c22850 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Weld Inspection Report
checkpoint-status |  |  | checkpoint | 1.2.5 - On-Site Bending of Reinforcement
label | e015a632-52fb-57ce-913c-cea81e7d9b7b |  | note | Method/Description - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | a9652896-3b1a-5b20-8921-063950d0576f |  | note | Test frequency - Prior to cutting or bending onsite
label | 249fa559-c356-5e19-b5bd-00b4516e4612 |  | note | Contractor - H
label | a81f906e-f877-515f-b27c-c1e4835f201a |  | note | Designer - H
label | 518f5f73-dceb-5f88-86a5-f9fb48661e7a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.6 - Storage of pile casings
label | 6a32837c-260a-57a8-9e58-aaad559d2421 |  | note | Method/Description - Pile casings shall be stacked on suitable supports on firm ground
label | 67217de3-3fd4-597d-bca1-799705667ba4 |  | note | Test frequency - Prior to commencement
label | 69d905f7-3cfa-531e-9bcf-eb0f54a4a9ba |  | note | Contractor - H
label | 7c3bd17e-a93a-5ec4-b725-380e09bf3c8e |  | note | Designer - H
label | 84bdca34-9ccd-59bc-a741-1d1b4acac040 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2.7 - Concreting placement methodology
label | a0e8d5f4-7e51-53f1-9e49-b23fab9ec3fa |  | note | Method/Description - The concreting methodology shall be reviewed in advance by the Engineer, who will require to be satisfied that the method of placing and the concrete mix design will result in concrete fully compacted in place, possessing the specified strength and having the necessary density, integrity and durability.
label | 23068f9a-838b-537d-bb2f-45d3f1a08ea8 |  | note | Test frequency - Prior to commencement
label | 6a8946f7-0c11-580f-85f1-6813b0e6cd6f |  | note | Contractor - H
label | 05e0fe15-3130-5624-8978-e0f1ade310fe |  | note | Designer - H
label | 7807e1f7-1165-5cbd-a2e5-15dd2278c17b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.1.0 Drilling
checkpoint-status |  |  | checkpoint | 2.1.0 - Installation/Removal of Temporary Casing
label | e5e39352-4182-503d-85fd-bcd423e45289 |  | note | Method/Description - Vibe temporary casing to rock level, Extract Casing immediately following concrete pour.
label | 616bfc43-385b-594f-8043-b9ca36835132 |  | note | ○ Sufficient quanitity of concrete to be mainted with in the casing during removal to ensure external pressures are exceeded
label | c272e1ff-9b7d-594d-be3d-7dddc43f7cd9 |  | note | Test frequency - Each Pile
label | 8f764521-a207-570a-af61-ee189f8db68d |  | note | Contractor - H
label | 9c5d7dfc-80d5-5885-9b7c-b1b28f92fe16 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-status |  |  | checkpoint | 2.1.1 - Drill Rig Set Up
label | 434d24a1-dc97-5915-a8e6-8279e2b4d15d |  | note | Method/Description - Check drilling performance, verticality and position. Drilling equipment must be capable of drilling into inclined rock surface
label | 03b63dcf-b96f-523a-8c92-226e3274d14b |  | note | Test frequency - Each Pile
label | 64dd3aff-8ba9-5a1e-a122-086fcf86097a |  | note | Contractor - W
label | c887d275-828b-5a52-8404-182dcd99a816 |  | note | Designer - W
label | d962cd1d-9fe4-5a3b-aae0-6897fa07103e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-status |  |  | checkpoint | 2.1.2 - Pile Bore and Condition Log
label | 163a9a8d-f94e-5161-b0a2-e1c688932e7d |  | note | Method/Description - Inspect pile bore condition, pile depth, rock socket length, toe level and ground water level.
label | a42bbf65-5257-5d86-98d7-d6b328558640 |  | note | ○ No Pile shall be left open for greater then 24 hrs; pile borehole to be checked and cleaned if open more than 12 hrs; Concreting shall be done on the same day
label | e9e2b6ac-8ef0-5e17-a079-6e307e243b14 |  | note | Test frequency - Each Pile
label | 5cf1ba70-4ca5-50d8-b785-2a1fafe1ca62 |  | note | Contractor - H
label | 6244beaf-9f4e-52d4-b6cc-ea64738d8c7f |  | note | Designer - W
label | 34a02caa-42bb-5e57-8a56-e0842d7f6822 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-status |  |  | checkpoint | 2.1.3 - Rock Socket
label | 3d595554-70b4-5e40-af15-5d5d629a5ee7 |  | note | Method/Description - Each bored pile excavation shall be inspected by a Geotechnical Site Representative to ensure that the material at the base of the pile complies with the design requirements (i.e. founded in Mt Messenger Formation rock). The pile construction record shall be signed by the Geotechnical Site Representative to say the inspection has taken place and that the founding stratum meets the design requirements.
label | d845e343-678a-52dc-a8b5-4617ab235da7 |  | note | Test frequency - Each Pile
label | 46cf72c9-65a0-578d-8a08-331f7361b13c |  | note | Contractor - H
label | d1f18c3c-e1a3-5d86-ada3-99b70a57bfc1 |  | note | Designer - W
label | e8368c44-2223-56b7-8c71-30e0f99e1846 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-status |  |  | checkpoint | 2.1.4 - Cleaness of Pile Base
label | 8b196130-a19e-560c-95cf-24262d3e3b0c |  | note | Method/Description - All loose material to be removed from the bore using appropriate methods. Details of cleaning equipment to be submitted to the DSR at least 7 days prior to use onsite
label | a4cbabe9-4cad-5567-bf55-bc29a739c242 |  | note | Test frequency - Each Pile
label | 512ff111-3def-58e6-86ff-381f3912d327 |  | note | Contractor - H
label | 27c9ff9e-5bd3-5039-b777-bc234ee4752c |  | note | Designer - H
label | b01cab69-f2ad-5820-b74e-2472fc7cdf53 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI Bored Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.5 - Base Hardness
label | 45b5d5d6-1444-52ca-9926-9795f9a3aeb3 |  | note | Method/Description - Base Hardness Test to be undertaken immediately prior to placement of reinforecemnt cage.
label | 3c2f88fa-1cdd-5e2e-a1fa-3a0e72445dc9 |  | note | Test frequency - Each Pile
label | 3030d30d-d51d-562c-8501-6c75dbcf48c7 |  | note | Contractor - H
label | 1c0ee038-80d1-5f03-a769-1053e03f664e |  | note | Designer - H
label | 761cf2dd-50cb-5fd3-ac39-e2eea04f9819 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.6 - Pile bore
label | e2f98442-b168-5276-9077-42fcf8749b95 |  | note | Method/Description - Observation of geotechnical conditions encountered and confirmation of key design assumptions. Contractor to inform designer at least 1 day in advance where pile observations will be required.
label | 5fb71b29-3a53-5269-acc5-ace0fbf004b6 |  | note | Test frequency - Each Pile
label | 5705d8f2-0dba-5d5d-a7a9-a625e88bb700 |  | note | Contractor - H
label | da560292-0aba-5859-a830-25ac50c11dd9 |  | note | Designer - H
label | b967f971-f311-5a6b-a9a5-e3cb409faba8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.2.0 Construction of Pile
checkpoint-status |  |  | checkpoint | 2.2.1 - Reinforcement Cage
label | 3c731cbe-39ca-5139-8216-38c01d483ad5 |  | note | Method/Description - Visual Inspection to check supply and installation of reinforcement cage.
label | 7d63756e-20b0-52b9-b489-56280ae54cd1 |  | note | ○ Confirm cages have been supplied as per detail sheets.
label | 2f93728d-97fd-5b2b-bf7a-ac6f9bd2e70f |  | note | ○ Confirm Grade, Size, spacing, lap lengths and weld postions are as per IFC drawings
label | 48efa758-33f1-51cb-8dbe-2b9b7f5666f7 |  | note | Test frequency - Each Pile
label | 70406586-1a84-5dbe-b8b5-774991f960b5 |  | note | Contractor - H
label | 412683d6-1ce3-5b24-8c92-5767d73ed4f9 |  | note | Designer - H
label | a306dfb9-721b-5d91-b3bc-26505cf333dc |  | note | Verifying Records Checklists, Test and Supplier Certificates - Detail Sheets, Bored Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.2 - Pre Pour Inspection
label | 3f349e28-a76e-5812-8860-09ada24ed9ff |  | note | Method/Description - DSR to inspect and sign off each pile prior to concreting
label | ae4caaa6-798b-5fae-9a52-7c641bb869c5 |  | note | ○ Visual check of socket cleanliness inf dry
label | e352a3f2-9fc6-5726-beef-651ba6fb2c32 |  | note | Test frequency - Each Pile
label | 6e03debc-e7ff-5657-9f1f-85f112946a08 |  | note | Contractor - H
label | 7b568c6d-527c-5b59-8aad-7671a3ff215e |  | note | Designer - H
label | 35fbf134-f0f0-544f-941a-a2c7f41fb7ed |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.3 - Concrete Supply
label | 39881190-3486-55cc-9f6b-19374001d32b |  | note | Method/Description - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | c1feb23d-cd6a-5746-a9e6-e54a78b3c4d9 |  | note | ○ Concrete dockets checked for correct mix and concrete site testing undertaken.
label | 12b9a291-63bb-520d-8904-c9a9612b6edd |  | note | ○ One set of 3 cylinders to be taken for each set of poured piles
label | 97cdcd82-77b9-5c78-a065-feefe0dcb7bc |  | note | ○ Onsite Slump Test
label | 3f606efa-957c-55e4-988f-1d61d500049c |  | note | Test frequency - Each Delivery
label | 5b2ea29c-9a96-5fe2-bbc7-baef22f64cf8 |  | note | Contractor - H
label | 0cf20d9d-6ac9-52dd-9455-17200684d567 |  | note | Designer - W
label | 2b14a1e4-f409-5140-8490-4362e553291f |  | note | Lab - I
label | 958d0b06-9920-5dfc-831d-c564e53ef9f4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Concrete Dockets, Bored Pile Record, Concrete Test Results
checkpoint-status |  |  | checkpoint | 2.2.4 - Concrete Placement - Placing concrete under water
label | 28bd2adf-8d09-5ea7-9e5e-91cf91e35aa4 |  | note | Method/Description - Should either:
label | 9856054c-6a2b-5919-9994-9a2c516db30f |  | note | ○ the depth of water at the base of the pile at the commencement of concrete placement exceed 75 mm; or
label | 123b8409-bacd-55c4-af35-681ce6d067ad |  | note | ○ the inflow of water exceeds 200 mm of bore depth per hour; or
label | cf7460d8-a7e2-57a1-afe7-e814ff44e602 |  | note | ○ the use of drilling fluid prove necessary to maintain excavation stability,then concrete shall be placed using a tremie and a methodology that meets the appropriate requirements which are stipulated in this specification and the recommendations that are described in the publication “Recommended Practice Tremie Concrete for Deep Foundations (CIA, 2012) and/or Guide to Tremie Concrete for Deep Foundations (EFFC/DFI, 2018)”.
label | 3250e8de-d24a-57e1-abd2-ae658b514e7a |  | note | Test frequency - Each Pile
label | 8fd14542-ec25-53c1-a980-22df7ae05931 |  | note | Contractor - H
label | dfd826d3-5841-5e53-817e-a29d8c4285c7 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.5 - Concrete Placement - Dry Pour
label | 7958f68e-2be6-5ff0-94d5-b38ad8245f3c |  | note | Method/Description - Concrete height to be no greater than 10m.
label | e2d07f19-c240-52db-95a1-744c8cc11fe3 |  | note | ○ Concreting of piles shall be carried out continuously so no segregation occurs.
label | 637eccd8-0fbb-5dd4-b54f-3a2d8e94d4ef |  | note | ○ No concrete shall be placed when there is any danger of adverse weather causing damage to plastic or partially set concrete due to movement of pile casings.
label | c5e05f60-2a69-57a4-b033-cab785fa1dda |  | note | Test frequency - Each Pile
label | ffb29a09-e17e-5ada-b4d4-d20a65a76053 |  | note | Contractor - H
label | fe1e1c0e-4637-59aa-a0bf-99296cd10d0f |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2.6 - Post Pour Inspection
label | 73c4a54a-ce54-5e8a-966b-db36f18ddb0a |  | note | Method/Description - Complete Survey of Wet concrete level to ensure pile is poured to correct height
label | ae71bbe5-2943-5f17-bfa7-02f59e51c623 |  | note | ○ Confirm finish is as per IFC Drawings
label | 3445d5a7-2b6e-5b57-96d9-fdf065f2248c |  | note | ○ Record of pile length
label | bc67c0cd-6512-588f-a363-13d84944907e |  | note | Test frequency - Each Pile
label | c589a28c-f998-53de-b8a1-bffe9f99cb9f |  | note | Contractor - H
label | 27dd3a5f-97ae-59cf-be50-15b51bd3ac65 |  | note | Designer - W
label | 2ed9b603-8fd4-5a0d-b595-e09ecb835857 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-status |  |  | checkpoint | 2.2.7 - Reinforcement cage support during installation
label | b2bf07e7-de59-591b-9adf-4ce60bc5088b |  | note | Method/Description - Reinforcement cage to be adequately supported at all times during construction
label | 30da34d1-27d4-588d-b2cb-065452302ae9 |  | note | Test frequency - Each Pile
label | b2aba53b-c1af-54d3-8fc7-dd77303cb667 |  | note | Contractor - H
label | b215a48f-b1ec-5de8-a4ca-0f156e543c16 |  | note | Designer - W
label | a47030ba-4e72-5ac7-8006-dbab43d6a1e0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey/as-builts
label | 0be11f26-6501-5401-af5a-485caa5a6fca |  | note | Method/Description - Survey final position and top R.L. of each pile, produce As-Built drawings including stated measurements of pile lengths; record bedrock level
label | e7230960-6281-5419-babc-742bc3b0e56b |  | note | Test frequency - Each Pile
label | 476d5ccf-f296-5076-a37b-991ab9817b50 |  | note | Contractor - H
label | dad7c6c1-2120-58d6-81cd-c89890d69515 |  | note | Designer - R
label | 51811888-795b-5aaa-9b66-8897a27cdde8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
checkpoint-status |  |  | checkpoint | 3.2 - Red-Line As-built
label | b5be7e63-e421-5979-9242-19ba72e10a18 |  | note | Method/Description - Draewings updated to reflect any changes during construction
label | 28c6a7d4-4e5f-5dcb-980b-9d81776d456e |  | note | ○ Any RFI's and NCR's noted on drawings and closed out prior to drawing re-issue
label | d29fc432-22f9-5d01-9c44-ad341f8b5ea6 |  | note | Test frequency - On Completion of Works
label | 81e3220b-ff4c-5cd3-88d5-9901367a1cd8 |  | note | Contractor - H
label | 7ed51bf0-b157-5800-9d29-a1c74d781ebe |  | note | Designer - R
label | 3419a46e-9ba6-50d9-83ac-d6712b6d1019 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red-Line As-Built
checklist-sectioned |  |  | checklist | ITP-009 - Geotechnical Equipment Installation Rev 2 | itp |  |  |  | Yes | ITP-009 - Geotechnical Equipment Installation Rev 2 | deba3ec5-36d6-489e-888b-4d2fe8dcd74b
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Construction Environmental Management Plan
label | c1781c39-6cac-5686-bf54-d6edb8e4135b |  | note | Method/Description - Document Review
label | d179a05e-3643-5bc1-a50d-a3081f64eb5d |  | note | Test frequency - Prior to personnel starting
label | 09cac770-3cd8-52a3-8bc5-2e8a80f8cafc |  | note | Contractor - H
label | c9edf3ba-d9d5-5c74-81bb-44dd40ee758e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - Construction Work Plan
label | 4e0b4904-362c-544d-a719-519af9756510 |  | note | Method/Description - Document Review
label | 68d92397-5cc2-5989-980a-c1b77fa042d9 |  | note | Test frequency - Prior to work starting
label | 996f184d-097a-5a25-b169-b2d8603b4679 |  | note | Contractor - H
label | 5021dd96-64a1-550f-abbc-15231c330cd0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.03 - IFC's specification
label | 75236a7c-b6a6-5779-acfd-5a519a419c98 |  | note | Method/Description - Document Review
label | d571d8ab-9eda-5b36-ab0d-87d643deb4cc |  | note | Test frequency - Once prior to works commencing
label | 67804dd6-5d72-5463-9386-41204f75d563 |  | note | Contractor - H
label | e7d5e4d6-4f1f-54e6-9527-013ad9dff627 |  | note | Designer - H
label | 2f3480f7-88d4-5e28-b4eb-52e475865867 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.04 - IFC drawings
label | 570dcf66-8dcf-5ff0-a2ab-37d011c8b838 |  | note | Method/Description - Document Review
label | 4f6d9c99-2ee3-5e87-ae50-79704bd5e962 |  | note | Test frequency - Once prior to works commencing
label | f3b9d3d1-e7e4-5dc6-af7f-93e427e7c2fd |  | note | Contractor - H
label | 736e6f7e-2203-5986-9b6c-ce8718951ced |  | note | Designer - H
label | 102d6008-12ee-5103-a889-cf3c4060e1a4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.05 - Approved setout locations of instrumentations
label | 1206e3f9-55f0-5149-b537-d0cb066f8a02 |  | note | Method/Description - Designer Confirmation
label | 234615fe-858e-5b91-84b6-936b7919e60b |  | note | Test frequency - Once for every fill site prior to work commencing
label | 4da0b8e2-90de-5038-a64d-46d5bab7e7ca |  | note | Contractor - H
label | 087d1f16-fa33-5b3f-871f-0bc2341b77e6 |  | note | Designer - H
label | 94210d6e-d13c-5b52-a77a-cfd32be10b92 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Written Confirmation from Designeer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.06 - Method Statements Approval
label | 58043e0d-7a7c-5d6b-b0cb-2a5cb8308248 |  | note | Method/Description - Document Review
label | 28484890-c6bd-57aa-a072-f138cd85aad8 |  | note | Test frequency - Prior to installation of instrumentation
label | 84f1f6ba-afbe-56d4-b668-c6badf80a7ab |  | note | Contractor - H
label | 0d9b24a0-379f-5029-8b3b-a9dce4fb710d |  | note | Designer - H
label | b89bb69c-dd07-50f3-9c05-2adf405273ab |  | note | Verifying Records Checklists, Test and Supplier Certificates - Method Statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.07 - Calibration of Read Out Equipment
label | 5ce63ece-0744-5b28-8663-673fa4ec1110 |  | note | Method/Description - Document Review
label | 15a52ad9-a3d0-55a7-9e72-8b6f88f00fbb |  | note | Test frequency - Prior to starting
label | 90e5d4a7-3752-58ea-ba82-fda72e3a8599 |  | note | Contractor - H
label | 1d0cd476-aa76-5660-b4ca-c6e7df0b0dff |  | note | Lab - I
label | 4dea238d-d690-5ab4-9b25-df4fa7049db2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Calibration Certificate
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Vibrating Wire Piezometer manufacturer specification
label | 8508f579-26f6-5f9b-ab9d-ed5b0788bdab |  | note | Method/Description - Document Review
label | e2832465-6268-5839-a4ec-ae1f5f07a2e1 |  | note | Test frequency - Once
label | 247fa4c5-f5b6-5c18-ae09-0393c9d95ff6 |  | note | Designer - H
label | 83268092-d390-516d-9f97-e3d207dddff9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Vibrating Wire Piezometer calibration
label | b7f5e511-5b4c-523e-98f3-9186391fa4a1 |  | note | Method/Description - Document review of manufacturer's calibration certificate of piezometer
label | fd59376a-761f-529a-b44c-0563362362cc |  | note | Test frequency - Delivery and acceptance of piezometer material; prior to installation
label | a55a6cf7-0e6a-5223-b682-9188a30e3f05 |  | note | Designer - H
label | 9197808e-38e8-56aa-b5d1-141467cac314 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Extensometer manufacturer specification
label | 9bd24c8f-a7ad-56b6-aa41-95a90caf0ae4 |  | note | Method/Description - Document Review
label | 7adb8326-68d5-5a2e-905f-7abd3abe33fa |  | note | Test frequency - Once
label | 7b10df48-62e5-5e4c-b46a-9ee89ab0f16a |  | note | Designer - H
label | 7aecb46d-b871-5133-ba74-0800c6d852fb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - Inclinometer manufacturer specification
label | 61c5fa70-bf23-5469-ac68-32ed9196b1df |  | note | Method/Description - Document Review
label | a8c594f8-15a5-5f7f-ab2a-0b605b319f00 |  | note | Test frequency - Once
label | 4f4b3d8a-936d-55c9-b24f-1c47c5d15527 |  | note | Designer - H
label | e0a9a8b1-3235-57bb-9522-feee8457c568 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Inclinometer casing material
label | 8d049a49-da62-5946-8522-3ef97ebf2e26 |  | note | Method/Description - Inspection of Inclinometer Casing Materials
label | 197696da-5ff4-5fc2-a53c-3efe9fd19852 |  | note | Test frequency - After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation.
label | b541f439-cf8c-5c76-ab19-e156a625e233 |  | note | Installer - I
label | 51a32b4f-53df-507b-882e-d3af5dfe1dd6 |  | note | Contractor - W
label | d57118d9-7694-56ad-9862-2a885a9c809f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint-status |  |  | checkpoint | 2.06 - Inclinometer grouting materials
label | 786b931c-3c88-5ecd-a3fd-19727c3c31c7 |  | note | Method/Description - Review & approval of approved grout mix
label | f1b8de27-97da-5ca9-883d-dddb212c54c2 |  | note | Test frequency - Prior to Equipment Installation
label | 1cb33d54-ad44-5e27-a7db-8487d8dd5b73 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Inclinometer materials
label | e2fd1a81-73c7-565d-b853-c3111cd40f20 |  | note | Method/Description - Inspection of Inclinometer Measuring Equipment
label | 0a2a2ef6-b16b-542c-94d1-90837bbb9950 |  | note | Test frequency - After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation.
label | 273c8ca0-7b83-5e92-af35-22612739ccea |  | note | Installer - I
label | 348eb6b4-ef01-59c4-a5dd-6542c1578102 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.08 - Rod and Plate Settlement Markers
label | f1767a56-98cd-5161-b485-5858026a6851 |  | note | Method/Description - Inspection of Settlement Plate Materials
label | 726e8b24-7574-53c7-9215-d1d151994374 |  | note | Test frequency - After Delivery and acceptance of Settlement Plate Materials; Prior to Installation.
label | 3cf9b493-b1e0-5d9d-a648-c37d96e8394f |  | note | Installer - I
label | 5a063c6f-4079-5503-8288-efc6fa7dd4e9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.09 - Surface settlement marker material
label | 31e46699-57c0-56a7-8109-4cccd4ab8ee3 |  | note | Method/Description - Inspection of Surface Settlement Marker Materials
label | 2c9b7967-160f-536e-a28b-4bd1712851fa |  | note | Test frequency - After Delivery and acceptance of Settlement Marker Materials; Prior to Installation.
label | abeb4c4b-eee1-5237-9714-a27ffa8bd5b5 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.10 - Surface monitoring marker material
label | c4008508-cc50-5c19-be8f-4018488f2557 |  | note | Method/Description - Inspection of Surface Monitoring Marker Materials
label | d86f0420-126e-5a8d-88ff-7c3066693792 |  | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | 13ad65bb-3c90-5749-ade3-e6a0e787ead1 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.11 - Lateral deformation marker material
label | a7981613-659f-5d55-981d-5d3e613e1e42 |  | note | Method/Description - Inspection of Lateral Deformation Marker Materials
label | 657d885f-23ab-5574-b5d9-a08ea4deb6ad |  | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | 2a2be6e3-afff-5414-b3ad-fa7767e0a6f8 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 2.12 - Profilometer material
label | 70f4ec1f-91f0-564f-81eb-d3a72d163771 |  | note | Method/Description - Inspection of Profilometer Tubing & Backfill Materials
label | ec702f18-1775-5b9c-b45f-6b30324f79c6 |  | note | Test frequency - After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation.
label | 3d08e78a-3bd5-5c7d-b526-4aae589252f8 |  | note | Installer - I
label | a3b00f9c-02d3-5924-b8b9-bb65e7b7e852 |  | note | Contractor - W
label | 81283718-b5f4-5ae1-bf42-f99eb026a96c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
checkpoint-group |  |  | section | 3.1.0 Vibrating Wire Piezometer Installation
checkpoint-status |  |  | checkpoint | 3.1.1 - Piezometer location per construction drawings
label | 97f06828-2caf-5cd7-a4a3-409b96e73e83 |  | note | Method/Description - Inspection of borehole location
label | 08542b2f-5be8-5165-a9f4-80124dd5228e |  | note | Test frequency - Before borehole drilling
label | e01a595e-dee2-5b3e-bdfb-c83057676e35 |  | note | Installer - I
label | d52632ce-52de-55ab-b1d1-eb9d0b6463fc |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.1.2 - Borehole Drilling
label | 997af7b4-aab4-5825-8684-2a5aaf387751 |  | note | Method/Description - Inspection of borehole
label | ab4b7269-2c4e-58b5-982e-0a1a4ee68169 |  | note | Test frequency - After borehole drilling
label | 0b79cad7-6874-5b1c-8c45-1a37607add57 |  | note | Installer - I
label | fcfd834b-52e9-5fad-abc1-0c9deb9f9a2d |  | note | Contractor - W
label | 234d71aa-d17a-5f15-a34b-1776293e0e26 |  | note | Designer - W
label | 8be6940c-1648-52ae-9a58-c5101015ec9a |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint-status |  |  | checkpoint | 3.1.3 - Depth of piezometers
label | 19339646-ac6e-5c9f-af2f-bbf5f09561d2 |  | note | Method/Description - Review & approval of depths of piezometer based on the results of the core logging
label | 91b842e6-26dd-5935-824a-00c2399679f5 |  | note | Test frequency - After borehole drilling
label | 5297a916-5715-5bd6-907b-5319098e1934 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.4 - Core materials
label | 9554b4d3-c4ea-5dea-9d2c-0cd07e9bc21b |  | note | Method/Description - Inspection of all retaining cores
label | d3f129c9-1e47-59bc-83dd-9a69cd3fa3e9 |  | note | Test frequency - After borehole installation
label | bcfba8db-e93c-527c-bdfc-62d56597a233 |  | note | Installer - I
checkpoint-status |  |  | checkpoint | 3.1.5 - Heavy duty connecting cable placement
label | ee72f1d2-f712-5ae6-8c68-294c2596e4a2 |  | note | Method/Description - Inspection of completed heavy duty connecting cable placement
label | bc9713f9-36ab-56f9-be37-524735907d41 |  | note | Test frequency - After placement of heavy duty connecting cable
label | 2729dba7-b3fd-5cbd-af0e-2f6e4c777e68 |  | note | Installer - I
label | e54b085e-8565-5831-9956-3e783fbaff05 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.1.6 - Splicing of heavy duty connecting cable
label | 0ee7fefa-c864-5e69-9cd5-30013489f77d |  | note | Method/Description - Review & approval regarding acceptance of cable splicing
label | e919a43b-93c1-52ae-9cff-a7a28a9573e4 |  | note | Test frequency - Prior to splicing of heavy duty connecting cable
label | edd93939-dc7a-56eb-86d7-51940cf19269 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.7 - Readout unit/data logger placement
label | 1b610c73-588c-5083-bec8-876c667ca86f |  | note | Method/Description - Inspection of completed readout unit/data logger placement
label | 6fefb079-9f32-574c-8ef1-8943af052b27 |  | note | Test frequency - After placement of readout unit/data logger
label | 2db1dc4a-eea4-51fe-a4d3-f66abcd9afd6 |  | note | Installer - I
label | e31763d6-db63-58a6-be45-ea0b50234ba0 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.1.8 - Ground surface finish of installed piezometer
label | 6cbe5381-8918-5cd6-b52e-6485a9b4c197 |  | note | Method/Description - Inspection After completion of the installation process of Piezometer
label | 5f058a59-0929-5775-a961-872daac29d9e |  | note | Test frequency - After completion of the installation process of Piezometer
label | 27761d93-7b50-52d9-a0b2-3bc85df1f09c |  | note | Installer - I
label | 79bf7090-19a2-5072-a267-555b01d9e09a |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.1.9 - Ground surface finish of installed connecting cables
label | 4a8e6ed2-a4ed-55bf-9b16-50d3b59d7487 |  | note | Method/Description - Inspection After completion of the installation process of Piezometer
label | dcb90d5c-7062-5b1d-a38c-53435a0c5e18 |  | note | Test frequency - After completion of the installation process of Piezometer
label | b7afbdc8-5937-55d5-a73c-b756f25bfcdf |  | note | Installer - I
label | 317758d8-ba30-5957-9ef7-e14079ebd6d5 |  | note | Contractor - W
label | bb1293a6-aac6-55e9-9921-f9dc6a422b23 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint-group |  |  | section | 3.2.0 Inclinometer Installation
checkpoint-status |  |  | checkpoint | 3.2.1 - Inclinometer location per construction drawings
label | 266d8360-3ba0-58e9-b0a7-a8db93ae308e |  | note | Method/Description - Inspection of Inclinometer Placement
label | ad89ab14-1762-543c-a9b7-a9706711ee0e |  | note | Test frequency - After Placement of Inclinometer
label | a68a3803-ebe6-5f40-aac2-735cdeb2d727 |  | note | Installer - I
label | 8cd09675-fef7-51a4-8847-2123720ee558 |  | note | Contractor - W
label | b97b2a5e-d4e0-599d-a9fb-ea374b7f9702 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.2 - Borehole drilling
label | ef57b910-6bac-547d-99bb-3d8ac65bb105 |  | note | Method/Description - Inspection of Borehole Installation
label | 678a720e-e033-5fcb-a395-32f93a26ff9a |  | note | Test frequency - After Borehole drilling
label | 94641131-d845-599b-9f75-11074bbc3bc0 |  | note | Installer - I
label | 770c3480-2a1f-5472-997f-2d8de63c579c |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.2.3 - Depth of inclinometer
label | ea8324a4-cc97-5fcc-a8c6-96470d2fd7c6 |  | note | Method/Description - Review & Approval regarding depth of Inclinometer based on the results of the core logging
label | 8aa05df7-b4b3-5cbf-b59b-4a670c41f60f |  | note | Test frequency - During Borehole drilling
label | ee8f1b46-f208-5c94-930f-9ff75aec8109 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.4 - Core materials
label | 6f6c3361-01a9-5af3-b8c5-1f77923dba36 |  | note | Method/Description - Inspection of all retained cores
label | 0d720a3c-ce38-5bcd-b087-ce24a5292585 |  | note | Test frequency - After Borehole drilling
label | ee833ebd-1609-5ba5-bcca-8fdb572fa472 |  | note | Installer - I
label | ca8a0db4-d3cc-5ca2-897b-adb297c7e6e6 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.2.5 - Grouting installation
label | c0addd41-8376-5dd4-8ed4-305fb1b1402d |  | note | Method/Description - Inspection of Grouting Installation
label | e5fd02fa-8c25-5462-ba69-1e7931a3b790 |  | note | Test frequency - After Grouting Installation
label | 33a90bd8-e353-5005-946a-51d06a4ddc15 |  | note | Installer - I
label | 56544afb-bc15-58cb-a996-18b3092a94b9 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.2.6 - Ground surface finish of installed inclinometer
label | 98208c70-480a-5133-be0f-a1a21a5ffefa |  | note | Method/Description - Inspection After completion of the installation process of Inclinometer
label | 8f5b2dff-6126-5aed-b9d7-b97245f67267 |  | note | Test frequency - After completion of the installation process of Inclinometer
label | e46e9ffe-71a6-5e3d-9764-848f1e8e4ab5 |  | note | Installer - I
label | 8ccbe5f1-3cf5-59b7-9647-963661ba9fd5 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.3.0 Profilometer Installation
checkpoint-status |  |  | checkpoint | 3.3.1 - Profilometer tubing levels and location per construction drawings
label | 9e0f73d3-b9d3-5e14-82c0-eed9dfc2b27a |  | note | Method/Description - Inspection of profilometer tubing Placement
label | 9e1c7723-acb4-5fca-9191-35f7196ecf53 |  | note | Test frequency - After placement of the profilometer tubing
label | 7f3be2e5-d344-5eca-b438-40b7d865db39 |  | note | Installer - I
label | 5a388a25-82a3-5b60-9b4c-ddfea206fa35 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.3.2 - Profilometer installation
label | fef720e7-04ca-50fd-9d16-b8c1a341e50f |  | note | Method/Description - Inspection of profilometer tubing Placement
label | c6419f97-c873-565c-8a1b-7dc6efa71f46 |  | note | Test frequency - After placement of the profilometer tubing
label | 6b2766be-0847-58cb-9cd6-95df8f7d30bf |  | note | Installer - I
label | 5c9b39d5-3606-5511-ac86-fe246754d9e1 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.3.3 - Ground surface finish of installed profilometer
label | 727a19eb-7b56-597b-bb6f-a7ed93a2f355 |  | note | Method/Description - Inspection after completion of the installation process of profilometer
label | 594d1ea3-ddb0-515c-b99d-e41c2aea2530 |  | note | Test frequency - After completion of the installation process of profilometer
label | f8dfe5e3-e0e9-5bfc-ac43-ed37c8b588e7 |  | note | Installer - I
label | 37ffdf9e-e743-57ee-a470-334dbdd69142 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.4.0 Rod and Plate Settlement Plate Installation
checkpoint-status |  |  | checkpoint | 3.4.1 - Settlement plate installation
label | 8f2adc4a-81f7-5727-aa98-8adcd2b9541e |  | note | Method/Description - Inspection of Settlement Plate Placement
label | ced4007a-bb2a-5128-b5a9-450451a53d9a |  | note | Test frequency - Before placement of the Settlement Plate
label | 178b4a6e-95c0-5bc1-81e9-47fb89dfe5bd |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.4.2 - Ground surface finish of installed settlement plate
label | b0d87ca3-c6d6-56d1-b1d2-5c7d154e48e9 |  | note | Method/Description - Inspection After completion of the installation process of Settlement Plate
label | dff90545-1264-54d1-a485-97a9f651e52c |  | note | Test frequency - After completion of the installation process of Settlement Plate
label | 01feb329-aa58-576d-895f-6fbb32cf4390 |  | note | Contractor - W
label | fa8f12dc-b4e2-5d9e-a40c-4bb87668536c |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.5.0 Surface Settlement Marker Installation
checkpoint-status |  |  | checkpoint | 3.5.1 - Ground surface finish of installed surface settlement marker
label | 12c28ec4-7509-5eea-866f-55a4eb60490b |  | note | Method/Description - Inspection After completion of the installation process of Surface Settlement Marker
label | 8e782d1b-2327-5607-91e6-ba940ddaefb2 |  | note | Test frequency - After completion of the installation process of Settlement Marker
label | 19b40d84-cffa-5151-a230-a3b87eb72286 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.6.0 Surface Monitoring Marker Installation
checkpoint-status |  |  | checkpoint | 3.6.1 - Ground surface finish of installed surface monitoring marker
label | 8a0d960c-a395-504f-aa6e-cfc85c03df45 |  | note | Method/Description - Inspection After completion of the installation process of Surface Monitoring Marker
label | f41722d4-3d83-5ab8-974c-c1198d6042a9 |  | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | 5d6ccca7-17d1-51ba-8cfa-2a511b156897 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.7.0 Lateral Deformation Marker Installation
checkpoint-status |  |  | checkpoint | 3.7.1 - Ground surface finish of installed lateral deformation marker
label | 5f4684ae-85e6-5f75-b3f4-a64a75da9f3b |  | note | Method/Description - Inspection After completion of the installation process of Lateral Deformation Marker
label | 8d7bc81c-b034-5de6-ab15-5913d1bd0520 |  | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | c5184587-7eaf-5514-9aee-a96b95b725a4 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.8.0 UAV Survey/Face Scan
checkpoint-status |  |  | checkpoint | 3.8.1 - Ground surveys using unmanned aerial vehicles (UAVs)
label | ff397604-66ba-5727-82c1-e50612b044cf |  | note | Method/Description - Survey
label | 16c126cf-4cf4-5f99-92d3-2d754dba672c |  | note | Test frequency - 1. Prior to any ground disturbance;
label | fa761dd1-6a0a-5f2d-a356-7c89bbe5d2a5 |  | note | 2. Upon completion of vegetation and topsoil strip;
label | fe26bbcc-8f75-5746-86b0-8d78b232c25c |  | note | 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys);
label | 47523000-bb8a-5cd6-bc86-329d428d6862 |  | note | 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths;
label | c408f7c8-88d9-5581-98df-2c4f1abb8d27 |  | note | 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season;
label | 970944db-e1b8-5ff4-9efb-b53d40e2ac9a |  | note | 6. Following removal of surcharge and final embankment profiles have been formed;
label | cfe094c5-f654-503a-97bf-2f7a0a5c714a |  | note | 7. Immediately prior to pavement construction;
label | bd0c50c0-63a4-5997-a98b-239aec0cc083 |  | note | 8. At completion of pavement construction;
label | 3c070420-743b-52ba-b14d-cbcebdcd7782 |  | note | 9. Practical Completion;
label | 6a9fc6f2-38e4-561b-82a7-ba8ead8b497a |  | note | 10. Every 3 months during Defects Liability Period;
label | 7fbbd909-0a83-527d-937a-81320481ebe6 |  | note | 11. End of Defects Liability Period.
label | 9291600c-56f5-5442-9762-9598619a6b38 |  | note | ○ Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar.
label | 449c42a6-1111-5837-a418-2724896acca6 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.9.0 Extensometer Installation
checkpoint-status |  |  | checkpoint | 3.9.1 - Extensometer location per construction drawings
label | 72b433e7-4cbe-5e1b-89de-0c7eeadc0f3a |  | note | Method/Description - Inspection of extensometer Placement
label | 4c53ae68-18d2-5be5-8527-5805a39dc404 |  | note | Test frequency - After Placement of extensometer
label | 6c0a9d21-4865-552d-96f1-1577037db03b |  | note | Installer - I
label | e210a09b-d647-511f-b5d3-6e454a621574 |  | note | Contractor - W
label | 247066ec-c6aa-5131-94ea-cb154365f94b |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9.2 - Borehole Drilling
label | e73b1582-6f35-5058-bdfd-72b66ef4d71c |  | note | Method/Description - Inspection of Borehole Installation
label | 8a028854-8e69-5f3d-8b50-04970fdf686b |  | note | Test frequency - After Borehole drilling
label | d45c498c-9a80-5018-898d-55c6b2f860ed |  | note | Installer - I
label | 559b6cf4-7830-50d5-8486-ad5ec590d965 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.9.3 - Extensometer tubes
label | e1114823-735b-5dc5-89e5-b59d438ce1f8 |  | note | Method/Description - Inspection of Grouting Installation
label | 0dc02987-80e2-585a-9e9f-c3585fba33e8 |  | note | Test frequency - After Grouting Installation
label | 9884911d-7e85-5ec3-9242-12a86d880434 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.9.4 - Spider magnets
label | 5197d379-87f2-5d41-a9ea-1ddd38391deb |  | note | Method/Description - Review & Approval regarding depth of based on the results of the core logging
label | 6e17de07-c027-5506-ad0c-fc19c838fa42 |  | note | Test frequency - During Borehole drilling
label | 85763d7a-c607-5ede-8e4e-3d7866579910 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9.5 - Reading and recording settlement
label | 21def668-4d44-52bb-b14e-d0331b2b4ed4 |  | note | Method/Description - Inspection after completion of the installation process
label | ce9f5d49-1213-550a-8a67-c970b89cbcbb |  | note | Test frequency - After completion of the installation process
label | 72379078-f1bb-548b-b1ac-710d3c8335e1 |  | note | Contractor - W
checkpoint-group |  |  | section | 3.10.0 Reflected Survey Marker Installation
checkpoint-status |  |  | checkpoint | 3.10.1 - Reflective survey target marker installation
label | b97cdc96-bec8-5919-bc35-ff5dc190fb81 |  | note | Method/Description - Inspection of Reflective Survey Target Marker Placement
label | 3688127d-ee25-582f-8596-32c2ab883506 |  | note | Test frequency - Before placement of the Reflective Survey Target Marker
label | c5fb0be3-84e7-5e2b-8adc-dabccb5da398 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.10.2 - Reflective survey target marker installation completion
label | 97500cb2-4b45-5c75-bef2-05c3273cf05e |  | note | Method/Description - Inspection After completion of the installation of Reflective Survey Target Marker
label | 8205f658-8159-548b-9e09-c28f697db238 |  | note | Test frequency - After completion of the installation process of Reflective Survey Target Market
label | c95eb16f-4a6d-57cf-ad36-9f798b2c3d2a |  | note | Contractor - W
checkpoint-group |  |  | section | 4.0 Completion of Instrumentation Installation
checkpoint-status |  |  | checkpoint | 4.01 - Vibrating Wire Piezometer completion of placement
label | 91bae5e2-adff-5e01-8a18-a08ff63dba4f |  | note | Method/Description - Document Review submitted through Hold Point
label | d8f0ae87-7708-52c4-b3d5-e28da38ed040 |  | note | Test frequency - After Piezometer Completion of Placement
label | 1f1925bb-697a-56c6-8f98-70f0e557ebcd |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 - Inclinometer Completion of Placement
label | c1e1cef4-b791-555c-8e55-9b79edace93a |  | note | Method/Description - Document Review submitted through Hold Point
label | b367d381-b385-5da6-8bb4-16537299825c |  | note | Test frequency - After Inclinometer Completion of Placement
label | 1b373216-a562-5ee8-b9ca-231fe044321c |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.03 - Profilometer Completion of Placement
label | 722dc441-c4a1-52bf-8443-a52ad721351a |  | note | Method/Description - Document Review submitted through Hold Point in Aconex
label | de53ffa8-244d-5d30-9b11-3dda284f00dc |  | note | Test frequency - After Profilometer Completion of Placement
label | 2c6dc184-f948-507a-abf6-b47dccf41918 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.04 - Instrument has been received and approved by the Designer
label | d3be3eb0-81e3-5b87-b470-fe7b9c733dce |  | note | Method/Description - Document Review submitted through Hold Point in Aconex
label | 5b9b3803-1b96-51b6-9c19-33c8507be1f9 |  | note | Test frequency - After Completion of Instrumentation Installation
label | 19e1a056-7e2b-5508-81e5-dc5bddf34a3c |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.05 - If an instrument is blocked, obstructed or damaged
label | bfcf9f5d-f544-5fea-a5e5-cd73fc10727d |  | note | Method/Description - Inspection and Document Review
label | d6dff28b-fac1-5fb7-aa97-c12a8371292a |  | note | Test frequency - After completion of the remedials work on the instrument
label | 963535b4-5bef-5647-8f94-50fb96e14367 |  | note | Designer - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Monitoring
checkpoint-status |  |  | checkpoint | 5.01 - Base Line Readings
label | b6f75633-e64a-5c5a-9077-e265a91b7a3d |  | note | Method/Description - Survey
label | edd211c2-4364-55e4-a3b5-e7bfe7eca4d2 |  | note | Test frequency - Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes
label | 799e7cca-1c0c-5637-8749-228bd57ec4b1 |  | note | Contractor - H
label | a136935f-33f9-59fd-b609-06e9bc6056b4 |  | note | Designer - H
label | d21a9e11-563f-5033-b18c-8431495d4449 |  | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.0 Verification Testing
checkpoint-status |  |  | checkpoint | 6.01 - Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground.
label | 25b83bab-2e63-58d2-8161-f74d2f3fad0b |  | note | Method/Description - Document Review
label | a526018d-a623-57d9-916c-77b4e4e84e3a |  | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | aed0e893-ae5a-5015-be33-fb306be96076 |  | note | Designer - H
label | f7cedd37-a9cb-5174-b18a-f0e0cb7926ad |  | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02 - Geonor Shear Vane Test in Borehole
label | b5ba8aac-43bd-5d42-932b-787b8bca6b46 |  | note | Method/Description - Document Review
label | 983d5752-c4d4-5df5-aae7-2aceeb77145c |  | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | cbf20790-1bc4-5707-a234-67dfa0e10846 |  | note | Designer - H
label | 3edad595-afdc-5c62-aeac-a93461fb4435 |  | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP-013 - Fill 13 Rev 2 | itp |  |  |  | Yes | ITP-013 - Fill 13 Rev 2 | df1538e2-6c7e-41a9-a4d1-dfde850c4234
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - CWP
label | 1fd7bc15-7b75-56ee-90ea-64d2ed7cd0fa |  | note | Method/Description - Document Review
label | 2d6fe952-cf71-5bfc-9670-82288734cf09 |  | note | Test frequency - Prior to personal starting
label | edeb92b5-8427-55c7-a8c3-c6d9907e3017 |  | note | Contractor - H
label | 3d72a513-8b7c-5811-9207-becb8381f6b0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - Design
label | 8c4b0047-156c-586f-8f33-0259491ef1fb |  | note | Method/Description - Document Review
label | 5d603b27-a348-586b-9d5d-4a9e16c405df |  | note | Test frequency - Prior to starting
label | 58328657-106f-576e-bef9-66260f63f3bb |  | note | Contractor - H
label | 94770155-8c54-523d-86d3-f5001fe94dac |  | note | Designer - H
label | 230170c5-4b0d-5a1c-831d-aee8dcc0214b |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material
label | 843a877e-afab-5723-b797-d1e3e4a6d016 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 1ef9ada4-cbd5-5c9f-8615-b75fcad5a5a7 |  | note | Contractor - H
label | 5e07418b-5d1e-525a-a70f-5f83018efce4 |  | note | Designer - R
label | 15750547-c9ba-5ba1-9d88-1a2406902a8e |  | note | Lab - I
label | 79172de2-0ca6-53ba-a825-f50e292e216d |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.02 - Atterberg limits test for Structural fill Material
label | 72f577ab-2a72-5a15-ad9a-e191a2caf005 |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | de4a0cb6-c889-55ba-8927-2ac74ed52b77 |  | note | Test frequency - 1 test per 20,000m3
label | 68c11a0c-177b-5be6-93bf-517e2dfc875e |  | note | Contractor - H
label | 961cda57-bca9-5b4a-955e-9a7dbb6bed30 |  | note | Designer - H
label | 7a1bc3f8-bd1e-5d53-9c31-69881a980b0e |  | note | Lab - I
label | 4bc29786-16d7-58af-bf4a-a7ad9a0c980c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
label | 77274685-363e-5166-8b0d-d0c591def09e |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 7752ce6a-848f-5a2b-a67a-7bafbb4ea3cc |  | note | Test frequency - 1 test per 20,000m3
label | 6528791e-e046-5199-961c-637065c8e122 |  | note | Contractor - H
label | ba85572a-b910-5b85-a31c-3d45d151896b |  | note | Designer - R
label | fd085827-22c6-5c13-8b09-7169179cdc50 |  | note | Lab - I
label | c04d6f18-c424-5035-b42f-9e3927ce7a25 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
label | 8a95d50b-0ed7-5eb7-ac6b-cb116f08a00c |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | d40d8914-fc9f-5087-b619-570794d09068 |  | note | Test frequency - 1 test per 20,000m3
label | d0e7a1bf-18ae-5d3c-9ddc-11a18a26a493 |  | note | Contractor - H
label | 86321d19-6dbb-5254-a501-5d77605be0e4 |  | note | Designer - H
label | e465448c-730b-51f5-ae47-fb85cf4cf9c3 |  | note | Lab - I
label | d2039d21-6adb-51fe-b0b6-42b6ffe81ea3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | 59c8614f-2e45-5e4f-9743-8a85113f31d2 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 4c5d01f7-83ce-5d1e-a077-be848a7a3331 |  | note | Test frequency - Source approval 3 no. tests
label | 89b60b08-8f3e-54ca-9ef8-dfb5b94e8796 |  | note | Contractor - H
label | e9e855b8-09c3-54ef-a955-eaf22a116a54 |  | note | Designer - R
label | fd0f7e41-5f28-5608-ab38-013121f9a32c |  | note | Lab - I
label | 5680fc2a-f6a3-5777-ab0d-2e4c09368ab6 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.06 - Particle size distribution (PSD) Test for GAP 65 material
label | c58ec3c9-7664-5157-bca8-635f273b82ed |  | note | Method/Description - NZS 4402:1986, Test 2.8
label | cf0895ad-19e5-5b0e-b9d8-091871b6f1b5 |  | note | Test frequency - Source approval 3 no. tests then every 2000m3.
label | 1abed39a-ae15-58af-970a-6dbfe703977a |  | note | Contractor - H
label | 269fd288-f6d2-57f6-82de-75a839740e51 |  | note | Designer - H
label | de9dfa1a-7598-5996-a7af-4af5f530f547 |  | note | Lab - I
label | 002b2aff-3acf-56b7-a722-7313097c1c9c |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Permeability test for GAP 65 material
label | 7dc369cc-95bb-57ae-916d-21dc44695ba0 |  | note | Method/Description - ASTM D5084 - 16a
label | d1a1acf0-6d24-5080-bea1-1c701a025846 |  | note | Test frequency - Source approval 3 no. tests
label | 94a91b89-d0a8-5a67-a9f3-b94e543b9ed3 |  | note | Contractor - H
label | b903f8b7-4152-5c05-a0a5-a4d33407e4a2 |  | note | Designer - H
label | 7ab9cec1-9ef3-5aa9-b1c6-78aec72effc7 |  | note | Lab - I
label | b81b7762-fb5d-52d7-9768-8556a5d26523 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.08 - Large Shear Box test for GAP 65 material (Minimum 3 normal stresses)
label | c7dd4807-fd23-5a31-8f65-bf05b38287ff |  | note | Method/Description - BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear
label | 64d05026-d66a-5dab-a65c-e3d8a405ddfb |  | note | Test frequency - Source approval 3 no. tests
label | dd13388b-8d66-5cc1-9dfa-f06963b57cc2 |  | note | Contractor - H
label | 4337f88f-dca1-5467-bd54-55c5b1554046 |  | note | Designer - H
label | 788774d5-ab12-5488-b468-77e7e0765170 |  | note | Lab - I
label | 1e1555b5-06a7-5c07-b84b-a6f929879d60 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Direct Shear Strength Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents of fill and check against design
label | 54470988-20a7-588b-9eaa-7de92c883ade |  | note | Method/Description - Survey/visual
label | dbbcf320-807a-50e3-a052-c5f4f8daaca6 |  | note | Test frequency - Prior to Commencement
label | a3ca4369-038a-5267-ae01-95a64d991327 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | 4689b6f4-b066-5f1b-8240-8fcc4de99da1 |  | note | Method/Description - Survey/visual
label | 997ac537-43b3-5192-9017-0bf3e3dcb597 |  | note | Test frequency - Prior to Commencement
label | d9ac4fbc-7600-56df-85a5-8ea200705489 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.03 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. Except for Fill 12 and 13 where the fill height is >=5m.
label | b4fb3a68-71ef-58da-8097-40b7a89c112a |  | note | Method/Description - Survey/visual
label | 8970b38d-8b8a-5e49-9c38-d63fc8472797 |  | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13
label | f6a103a5-5e83-54ad-a66a-0eff52520bbf |  | note | Contractor - H
label | b87f98d4-d11c-551d-81c7-8f4f29f9fedf |  | note | Designer - H
label | 21e996d7-b1c6-5e55-bfcc-f4f44de77c3c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
label | ba2f9358-a9a9-5881-bc01-18f984aee4f3 |  | note | Method/Description - Inspection
label | 11f42312-c5e8-5541-9374-4f1594c9a91e |  | note | Test frequency - Prior to Filling
label | 8a0edce7-145a-5525-b5b4-f396d248a2e9 |  | note | Contractor - H
label | 36da4f01-26aa-5525-99f1-2d9554b96007 |  | note | Designer - H
label | 62478400-b8e3-59d6-a6a1-8dcf7c77e368 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Undercuts
label | 69ecde8d-3869-5cf5-ae08-76c8bd5d180a |  | note | Method/Description - Visual inspection
label | 438a220f-e72c-56fb-9404-7451932cbae9 |  | note | Test frequency - 100% of works area
label | bc6f60ed-4f21-5290-8116-2a8222b4d19d |  | note | Contractor - H
label | 8d209e60-b20b-5233-9b84-a05bf17c9165 |  | note | Designer - H
label | 34a39f77-c01f-567f-94a3-2f5cb3545c04 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.06 - When required Undercuts (cut-to-fill operations)
label | 1a089570-6390-58b5-8b70-7e61af11ec2d |  | note | Method/Description - Visual inspection
label | 1b9050a5-547b-527d-9c0b-c94f51eff89c |  | note | Test frequency - Prior to Filling
label | 9e02960e-ab55-55c1-9b30-b7fca11a2b74 |  | note | Contractor - H
label | eb43c112-b2d0-56f7-882d-36705c85ffc3 |  | note | Designer - H
label | dbc35f7b-b8a8-52b7-a189-44533021e349 |  | note | Lab - I
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Sub soil Drainage
label | 1ef14143-ffb9-517a-8f56-4a92d767339c |  | note | Method/Description - Inspection
label | de174a21-52f0-5099-bc2a-2fce93f54897 |  | note | Test frequency - During subsoil construction
label | 988e2157-806d-5f8a-b89e-c6251768791b |  | note | Contractor - I
label | 9a75421e-9f90-5e9f-93ee-665134a87991 |  | note | Designer - I
label | 5e4495f7-1404-5969-92b4-0f14e57f6446 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint-status |  |  | checkpoint | 3.08 - Monitoring Equipment
label | adbb1f75-98dc-556c-a631-3bc5b41ba1e0 |  | note | Method/Description - Survey/ data logging
label | 66e1ae20-c616-5dc4-9692-bfd386ade1d1 |  | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | 17d7b1e3-8e17-59c3-b4c2-f7bfadb16577 |  | note | Contractor - W
label | 57217e4a-375b-5ffc-9541-bfc283c15f5a |  | note | Designer - R
label | 6e784698-1cef-5ede-821d-0ea3d92bd445 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs, borehole logs and monitoring instrumentation asbuilts.
checkpoint-status |  |  | checkpoint | 3.09 - Filling operations
label | ee8cacb4-bc0a-5ead-b3e9-8dd2e866d9f6 |  | note | Method/Description - Visual inspection
label | 310c020a-61b0-587d-a195-8b4d2bc41a10 |  | note | Test frequency - Daily
label | 10983cb4-a0f8-543a-84d5-dfe3867faf88 |  | note | Contractor - H
label | a587fd4b-1255-5608-80ce-994f8219d2a4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet
checkpoint-status |  |  | checkpoint | 3.10 - Filling operations
label | 69a46851-b372-5748-8d21-a101d637e99b |  | note | Method/Description - Survey/visual
label | 8d5d5d55-7dbc-5e0a-b42b-4505a96aae12 |  | note | Test frequency - Daily
label | c350c99f-eccb-585b-82ac-03e070b715f7 |  | note | Contractor - H
label | 7364e9ca-6681-5b8c-be6d-f877ddd2313d |  | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet/ Survey Report
checkpoint-status |  |  | checkpoint | 3.11 - insitu fill testing-Plateau Test
label | 600dd621-0d81-50d0-80c4-9dc0f518b981 |  | note | Method/Description - Plateau Test
label | 0c1794d4-660b-55ea-acae-9466ec554854 |  | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
label | 09464a21-4611-56a8-a5fe-3e0edf4ffdaa |  | note | ○ Buttress Fill - 1 test per material type per earthworks zone
label | 6a52ccdc-6010-5574-b132-a0d049b97e2d |  | note | ○ GAP65 - 1 test per material type per structure / location
label | bf649d32-6efc-510e-a4e4-7ac5a51a475c |  | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | ab9c7014-a1ba-5128-ac98-b04a6a10e016 |  | note | Contractor - W
label | 9845a94d-a7ac-57ea-b6ec-a955ba36eed0 |  | note | Designer - R
label | dd83c3d4-fd48-537b-b1fa-abfd1bf94a9c |  | note | Lab - I
label | b7a0974c-d85d-5dbc-be75-46e04d7fa2f4 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.12 - insitu fill testing-In situ moisture content and density
label | a0afe7b1-fee4-5fa3-9c71-8fbf8f5a5acf |  | note | Method/Description - In situ moisture content and density
label | af0fabf9-9e6b-5b60-adc5-e80a21430127 |  | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
label | 6c4d0280-0c7d-5097-98a7-f68560fc8028 |  | note | ○ Buttress fill - 1 test per 200m length Average
label | fbe8a438-4bda-5e3c-9d73-322b30940467 |  | note | ○ GAP65 - 4 tests per lift per structure
label | f28bd76e-62a3-5f63-9305-592f4b3f88d1 |  | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
label | 9dba6b2e-7d63-58a8-ac07-edade3b7c580 |  | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label | c225eafe-d341-5a94-9124-1ca33e130548 |  | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | 0ceafaf5-dffb-5f33-ae88-522e879fb571 |  | note | Contractor - W
label | a403cb72-3a42-5cf3-ad38-936d5a074e5c |  | note | Designer - R
label | 843c14af-e1da-5815-ab95-509aeb970ca2 |  | note | Lab - I
label | 786578df-e825-5f5a-9a37-4f5fbd88e254 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.13 - insitu fill testing- Undrained shear Strength
label | 5c909215-a304-562f-ba2e-1b17343aed8e |  | note | Method/Description - Undrained shear Strength
label | 02bc81e6-ca2b-5dc5-a474-4c20bd89a2c7 |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2
label | c69f231d-1c8d-5151-846b-45fe51c69acf |  | note | ○ Buttress Fill - 1 Test per layer per 2000m2
label | 49638fac-20ae-5cd6-a1f4-ceed719c72c3 |  | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | 75a7bf48-2394-5764-bda7-b7e8a5b794e6 |  | note | Contractor - W
label | c81227cd-0bca-59ab-aa02-b5a01e9f1978 |  | note | Designer - R
label | bc66198b-6847-5e0f-9023-3cafec664952 |  | note | Lab - I
label | bfbd1086-6106-58ae-a278-b5dce3a27894 |  | note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint-status |  |  | checkpoint | 3.14 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
label | f555f46b-d1e3-5003-8844-e622c6d88ac5 |  | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | b9934e02-df02-58e0-87fd-ee458ddd54ac |  | note | Test frequency - Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
label | fd34ab6a-c392-52d6-9c5c-0fed575b1764 |  | note | Contractor - W
label | d86a7167-2b5a-5754-bb5f-f0e4f1a196b9 |  | note | Designer - R
label | f70c4512-c156-5f81-8234-2b77eed4595c |  | note | Lab - I
label | 11325940-a36c-5b2e-b0af-8a8f27652ba0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.15 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
label | c9fb14e6-4cd2-5dc0-af5c-95b191f08475 |  | note | Method/Description - Benkelman beam or FWD Testing
label | c428f2d7-9aa5-5956-98a3-072d60654b87 |  | note | Test frequency - 10m interval in each wheel path at the following levels: 1) 1.0m below Subgrade Formation Level 2) 0.5m below Subgrade Formation Level 3) At Subgrade Formation Level
label | ec4011ac-576e-544f-b4aa-606496abe07b |  | note | Contractor - W
label | d2973614-4cc8-59bc-8d68-4022b26ad1d4 |  | note | Designer - R
label | 8799388d-3b99-53dd-9b44-0bc3daefce40 |  | note | Lab - I
label | d2f8f714-14cc-55e1-ae0b-bee7ddb3740c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.16 - Laboratory Soaked CBR testing for Subgrade Fill
label | 3e147788-ed35-54be-8ec5-a539d24bf29e |  | note | Method/Description - Laboratory Soaked CBR
label | 0fc8e469-f22c-5704-89f9-d7fe018fb000 |  | note | Test frequency - Test per 5000m2 at subgrade formation level
label | 8931dde4-2398-509e-9f8e-52ed93d5f832 |  | note | Contractor - W
label | 0fb58b69-8f60-5619-bacf-d43c590a3e70 |  | note | Designer - R
label | 6edd5fe1-939d-536b-bc73-212a41358941 |  | note | Lab - I
label | 37689b01-0ff3-596d-a36a-925c3feb4deb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Monitoring Data
label | a7db3a4b-38db-57a6-b6e3-59634dff1edc |  | note | Method/Description - Data Recordings
label | 2a085e1a-02b9-5208-940b-25fa6a85b2e1 |  | note | Test frequency - During construction and at end
label | 3167efb4-0f87-5712-9e42-e14a688fc186 |  | note | Contractor - H
label | c842e8aa-996e-5622-a3a8-8af7e1d2ec92 |  | note | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
checkpoint-status |  |  | checkpoint | 4.02 - Survey As-builts
label | 36fe3d22-feb1-5dc2-9164-8b5f09094e1d |  | note | Method/Description - Survey As-built
label | 52dd3e4e-8331-5648-bad5-815d78477912 |  | note | Test frequency - During construction and at end
label | 5193b0a9-ec26-5a50-b6c1-11b49445bce8 |  | note | Contractor - H
label | 1674725e-8610-5f4e-9cb6-85c094bf0c22 |  | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint-status |  |  | checkpoint | 4.03 - As-builts
label | 2454005a-a3a1-5a1e-8746-49dd0e0d6520 |  | note | Method/Description - Red Pen Mark up
label | 96a442d1-51b2-58fb-8c6a-9faa90e5fc92 |  | note | Test frequency - End of Construction
label | 464ca93d-6b25-544b-a8d5-12229c34574b |  | note | Contractor - H
label | e733f8c7-53c6-5be1-a3de-610e2867dd0c |  | note | Designer - H
label | c8c4f16c-a75c-5270-82f0-708815469c7c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP-001 - Cableway Works | itp |  |  |  | Yes | ITP-001 - Cableway Works | e9c79f31-8943-4eb9-b1e2-74bcc4a27366
checkpoint-group |  |  | section | Construction - Earthworks
checkpoint-status |  |  | checkpoint | 3.1. Removal of Topsoil and Vegetation
label | f446cf7b-05ab-5495-b466-d0e3f249c2b2 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | ec3ddf8c-a3c9-52f8-8775-6d2cca7e1bfa |  | note | • Drawings
label | cac61a98-1105-52b7-8330-64b1c149b435 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | be59532d-0bce-5d68-a579-86de718394d0 |  | note | • Confirm when topsoil and vegetation stop
label | fd443fef-f2fa-5125-a828-8a3f9f1f1c29 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ca7b77a7-17eb-5284-9e68-c6070efbe9aa |  | note | • Visual Checks
label | c6cb625f-26e7-5493-9885-07b84061c5f5 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 28d53178-2f58-5162-b80d-5635e3d0af6f |  | note | • Ongoing
label | 7164c0f2-90aa-505e-aa41-e419fcf72d86 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | ede6a507-f4b6-5208-97b5-5af4aeac3162 |  | note | • I
label | 2ec9688f-0f10-5bbb-89cc-2c906031f137 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 3d5d285e-29dc-5daa-a838-a987095bfe17 |  | note | • PE
label | a2f07ebc-f767-5e05-8044-56b1eff727d1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 776b06e8-64a2-5150-9dc5-cd04b81dd42f |  | note | • N/A
checkpoint-status |  |  | checkpoint | 3.2. ESC Measures
label | 4d4ffe01-b599-5b6b-82b6-824b347e03a7 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 82292996-b39c-5ed4-a138-b810503877a0 |  | note | • ESCP
label | 8bad29e3-4d28-5493-bc0a-8b544875b442 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | a30b8b7b-d84a-5844-a587-ed0c3ffa6d47 |  | note | • Environmental controls to be installed as per ESCP prior to removal of topsoil
label | 93f53a88-385a-54cb-9546-4521a3c6e60b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | baa5ed11-4caa-55bc-8af3-5bd3a312b479 |  | note | • Visual Checks
label | 9dc30442-9ae1-5f90-9128-052248c5b8b1 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bfa81637-972e-51ea-b882-71d5ec2e5d09 |  | note | • Ongoing
label | 4cde16de-d88d-5bfd-b964-527759515c17 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 2b931c43-0234-57fc-af3d-50e0cc58101a |  | note | • I
label | 4bbebaee-9383-5324-81ae-ed66caee389f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 21f20ff1-be2f-5168-a121-46e8abd20700 |  | note | • PE
label | 327ea502-e626-5cd3-a9a0-34daa5fab716 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 152632e1-ec83-5423-9f93-15f4c4abd00b |  | note | • N/A
checkpoint-status |  |  | checkpoint | 3.3. Cut to Waste – Bulk earthworks removal
label | 0510bb34-6df4-5870-abc2-89ccc0403d62 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 9c193eba-96de-54d4-9cfd-ed4fa5e1e486 |  | note | • Drawing
label | 4419470d-b4f2-5f20-b5d5-1a66505409c5 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 27f704c8-9c2f-569d-ad98-860f1bc6dd5a |  | note | • Level of cut matches drawings
label | 4286bfef-2f98-5c8d-90e9-c0151e943636 |  | note | • Global Position of cuts
label | 2fab4e7a-a63a-59c0-81c7-cd2d0decab8a |  | note | • Inspection by MSQA
label | a101317d-a0f7-542d-a4c3-edd010a4e5b0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c49f0e1c-f813-5234-9b6f-6e0739b07e5f |  | note | • Survey Checks
label | 5e0d5509-497e-5e6d-94d6-319756479af2 |  | note | • Survey Checks
label | 8c09e4f8-fbcf-503c-b199-d7c00108b718 |  | note | • Visual Inspection
label | 1d66461a-ac73-5e07-bf97-0e5dbf767e3d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 72f9bf49-645c-5327-9ac2-1732b2da362a |  | note | • Daily
label | 5262752c-8f0c-5cc8-bbb4-beb1f3735c5a |  | note | • Daily
label | 75520e72-e460-5cfb-8583-dc2516cbbf52 |  | note | • 3 x visit per location
label | a05d2171-63cf-589a-8700-718a8cded3b8 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | eb19f1cc-37ea-5378-b2ec-0593f107c724 |  | note | • I
label | 45572226-71db-5e36-9629-5b05bce0eced |  | note | • I
label | b940d53d-0a6f-5ef4-9bcc-99d8b8e8c167 |  | note | • H
label | 2460b0db-4b5e-530e-9a99-fb65d15b0c6e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 9d6c1ef6-d405-5b4b-8a40-889aae36dfcd |  | note | • PE
label | 3f88913a-2237-5d6f-a898-90c98f633c5a |  | note | • PE
label | e460ac10-0540-5e72-8032-8f75dc3f0660 |  | note | • MSQA/DSR
label | 45d7d401-1fa1-5a4c-9d94-910ad6b6e783 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7c1e5d85-5363-5c79-88b1-8d58082e778c |  | note | • Survey Records, As Built (3a)
label | 52f748fe-7bd2-5df8-9ad9-48659fefbc66 |  | note | • Survey Records, As Built, 3D mapping to be provided (3b)
label | b6dfe628-0696-5d97-a540-c23c13ff339c |  | note | • Site Report (3c)
label | a1c53a01-c8d3-5e0f-a010-ae4aedde5508 |  | note | CERTIFIED COMPLETE (DATE, RELEVANT CHECKLIST TITLE/LAB REPORT NUMBER ETC):
label | 82369f8f-e107-54a5-b4a9-72301c63afa5 |  | note | • 3a No details received
label | bd803e80-891b-538b-83d9-8cdb241614e0 |  | note | • 3b No details received
label | d078bc43-14b4-5371-8d99-6d40d8c17934 |  | note | • 3c Tower Site – 13/10/22 Three site reports uploaded for Tower Site. NAB – 1 site report unloaded – missing two reports. SAB – missing 3 reports
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 3.4. Install Fill Retaining Area (North Anchor Block only)
label | 840a6f4e-0865-5376-9ed4-d869c2acda83 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a37abe55-c354-5eae-8953-bdd1442b7205 |  | note | • Temp works design
label | f7ff324d-6507-5178-83fa-3bf2bd551a42 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 90e3fe80-68e6-5ab9-b243-dec4d653ca1d |  | note | • Level and Position
label | 043a4502-27b6-5a30-9ac4-f2db912fb991 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 5e7daf55-28a1-5d7c-8fe4-d5dbcebc706f |  | note | • Survey Checks
label | 4abcb998-7f41-56e1-a4a4-363a101e8366 |  | note | • Visual Checks
label | 1740af0e-2138-569b-9cf9-080baf8ba77b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 61454d78-ea80-5e74-846b-15bdd8c4b7be |  | note | • Each Temp works
label | a73b3217-fa40-5fcc-b8d9-20054ba77a6a |  | note | • Daily
label | 00e50aa8-482b-5895-a0cc-205550e5eb9a |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 088757b5-4143-5eb5-8a05-524e45d4d9e1 |  | note | • W
label | fb2ef8bb-a07a-5f36-b6d6-62eba00575f8 |  | note | • H
label | ba5a3fdd-2817-53c4-8335-a93692b4d48c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b9ef9355-211f-53cf-a356-223417b31981 |  | note | • PE
label | 5c162536-dca0-59b9-901e-831b66d85f98 |  | note | • PE
label | 6d575111-72a8-586f-933c-36605f13e4cd |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 6d45613a-bb68-5f34-b156-58bdc7b2d1c1 |  | note | • N/A
label | acbf9c61-30e4-5fdf-92b8-5270aebc6b65 |  | note | • Temp works sign off
checkpoint-status |  |  | checkpoint | 3.5. Cut Access Track (South Anchor Block)
label | 0296bd65-109e-5d79-b43e-b4009a94f08c |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a12a652b-0f65-5cb0-8fa9-9f57231899b3 |  | note | • Temp works design
label | aab5b90c-c035-5999-92eb-d1b5213888bc |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | d9742b39-3681-5a5b-8d54-bfdf52b656b1 |  | note | • Level and Position
label | d69fab44-7e58-5638-bd1f-ebffa08a1c12 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 020df4c0-11a8-51d2-a117-53a4a05b47f0 |  | note | • Survey Checks
label | e7ecf537-f50f-5644-bc27-70d23628939d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 21e30579-e39a-527c-a516-1e0da9178352 |  | note | • Each Temp works
label | f1a916d3-4afa-5783-b1b9-3db7e7e5fe8f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8985f5ca-a61b-5372-ad05-c61547e5bdde |  | note | • W
label | d4326e56-ca63-5431-b4c2-6936bc93cc82 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 481b3d24-3215-5ccf-aae1-67394e8c29eb |  | note | • PE
label | 14678cf9-b4a9-5e8b-9c08-6c45f8e29346 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | a6cd570a-5685-55f3-b313-c872e93774d1 |  | note | • Survey Record
checkpoint-status |  |  | checkpoint | 3.6. Trim to Grade (Compound Only)
label | 3ee56e6b-42c2-5339-8748-879019ed37b0 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | f501d13f-57af-52f6-b501-c5860e0719b0 |  | note | • As required
label | e590f687-6a3c-58ec-83fd-9d7e7c2d4495 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2058ee40-5d46-5f4e-940c-223f46af7195 |  | note | • Grade to control water
label | e5025be0-b307-5e95-99e8-6c22f692732b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c1d4efff-4179-5e33-8780-97d947731499 |  | note | • Survey Checks
label | 7b973601-3e06-52eb-b452-6624a3d50ff7 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 9702a9bc-2888-5a6b-9092-dac49f0e4e16 |  | note | • Daily
label | f6951156-71aa-5b0e-b76c-dfccfcf34119 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 376a2884-bd16-59b6-9979-9238d964fce8 |  | note | • W
label | e05ef43e-4a01-5008-b875-d5ea0bc83558 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 04535899-7df2-56bf-af7d-db315fe74ae5 |  | note | • PE
label | 9d28e230-8b83-53f2-8f3a-cc6c155ac7dc |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 94a96841-0e6a-5b30-8ef0-5f93887a3fc8 |  | note | • Survey Record
checkpoint-group |  |  | section | Structures - Piling Works incl Micro Piles (Central Tower Only)
checkpoint-status |  |  | checkpoint | 4.1. Set Out Piles
label | afbd161d-f768-56a1-a6f4-8a258594fab8 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 8fe47ac2-b682-5cd1-87eb-b0e34e56cd9d |  | note | • Drawings and Survey Model
label | 97026ff4-3e7a-5d16-b8f9-237a5c6679fa |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 194ac4fd-8e04-5d74-b6e6-be0e13778478 |  | note | • Position and Depth
label | eeccdd2c-6a6c-520c-9057-2d3d5087f2f1 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 3dc1eb25-1611-543a-8e4e-50cd5dcc0b9f |  | note | • Survey
label | 0eae9148-16b2-56d2-904a-f1649d4c9a9b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 24664740-5fc9-5a15-bf27-68086cf75d01 |  | note | • All Piles
label | e6fbd6e6-0e6a-57ad-b708-82ca60820dd3 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 69b9c6b2-90bb-53e5-87ac-9fd51ff7ebe4 |  | note | • I
label | a7f71cae-cad6-5195-8a30-3f1565a36c29 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 10de8b3f-31a9-5787-b03e-55bd6891d1a3 |  | note | • PE
label | 1fe6e74d-0dba-5d6d-9735-dec1fef67ae1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9291c85b-437a-5819-96fa-c513e9eff3a3 |  | note | • Pile Record Sheet
checkpoint-status |  |  | checkpoint | 4.2. Drill Piles
label | 23798a48-4725-5c1f-bab3-6deebb12d0f9 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 4d4abece-2e3c-5c6f-b4c0-049b4ee53daa |  | note | • Drawings & Spec (TBI)
label | 8aefd90a-16e1-5fab-a300-b52b85776714 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 627500fa-3900-55b6-adf8-cdf8b5384bfa |  | note | • Piles drilled to set and/or required depth as per design drawings. Location within +/-75mm. Verticality of 1 in 75
label | 67baab02-bfe7-5953-b897-fd184199ccd2 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | d20076ca-01cf-5084-8d3a-ca7cb10e6f88 |  | note | • Visual Inspection
label | 939c8ee2-4718-5f89-9c24-b8d1c08d5f7d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 4660e484-2661-5bac-ae09-95d6611551d8 |  | note | • All Piles
label | 91a4fa9e-0f18-5e78-a76f-fa80826199ad |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 3dd45958-dbaf-59f2-b481-833edab21acb |  | note | • H
label | 8f6e01f8-f9f6-5903-95d0-3e11d0c09ac8 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 371dea6e-2f33-5dbd-9e39-597b19897d06 |  | note | • PE, MSQA/DSR
label | a4f06133-2cee-5617-875e-a350359f65b1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | b4f136b3-bb67-5879-9b2e-3e4f9e038ec7 |  | note | • Pile Record Sheet, Site Report
checkpoint-status |  |  | checkpoint | 4.3. Inspection of ground conditions
label | 9fd8ea15-13d6-5181-be4d-9267f218548a |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 363d7832-a943-553f-b6dd-5526bcaa32dd |  | note | • Drawings
label | cdd3dd28-50c4-5826-91f9-b3934e53104b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 8caf943f-be91-5ad0-8825-b2ef5bad38a4 |  | note | • Confirm as expected
label | e20e554f-2918-5536-a85d-7800fc2d0a67 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 066469dc-3222-55b1-a97f-79b11c01962f |  | note | • Visual Inspection
label | 098c7633-e6e8-5391-84cb-b8adedf5f6c3 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 3c202d14-908f-56c1-8da8-0880ef639ec5 |  | note | • 1st Pile
label | 7b92fd7f-a11f-5acd-a930-5020f9a73b14 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | bc11ca72-c34e-5270-bd06-3105af2dc58e |  | note | • H
label | 3151e508-6076-5614-9787-8c1a844506ce |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b5c0489e-7a77-5f88-8951-875812f435fe |  | note | • MSQA/DSR
label | 0caf3356-58e2-57d0-bb0b-58fb6abb2564 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 80a34909-005c-564a-8953-9dde1fa82232 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 4.4. As-built
label | e9a13268-54f3-5368-8269-b9c81f1062b3 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | c78357ca-bad1-5361-a2b4-d12da5e22572 |  | note | • Drawings & Spec (To be issued)
label | b3bb51d0-1c9d-5f2c-b8ce-be8c99631899 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | f50155e3-b1a9-5b0c-b4ea-a55a2e572385 |  | note | • Cut off level correct for follow on connections.
label | d2cc34b6-1aef-5321-b06f-481df0fe3702 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | be933e2c-b74f-546b-b3ef-5a01e0dffd8b |  | note | • Survey
label | 09da8206-34ad-50db-b635-72b5f604388b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | a0a5becf-062a-5308-8f16-dfd366665215 |  | note | • Once per pile
label | fd7c7df7-1b93-5615-84a7-617e11edd34b |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 9cdc8855-81a3-59a9-b90e-90dde8f01b6d |  | note | • I
label | cd2cd197-569d-5db0-a18d-e3cc9a4e3d65 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 965fad1b-6a56-5389-81b0-41c5df8986e2 |  | note | • PE
label | de74877c-cc93-544c-bfb9-e9692d42a6c0 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 513e6ee2-5918-5ef7-b24c-3afd002a43d2 |  | note | • As built, Pile Record
checkpoint-status |  |  | checkpoint | 4.5. Install Reinforcement
label | 736e31ac-9d22-5666-ace3-d1caa58396ed |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d5995795-2ee3-5220-8459-28ee4dccd01e |  | note | • Drawings & Spec (To be issued)
label | 9f622647-52eb-5ecf-abca-e258e6ba3b95 |  | note | • NZS3101 & NZS3109
label | b10b0c7b-72cd-5c6a-8f2b-f8524e272045 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 78caa8ef-cb4f-5e9f-b176-9858e56dde53 |  | note | • Reinforcement is fixed to design of IFC Drawing. Correct reinforcement used that is not damaged.
label | 15d2ebbf-6a27-5a9c-b745-23f136700ffb |  | note | • All cover block/wheels installed to achieve minimum 50mm cover.
label | 8fd03d2c-0c7a-52ca-8931-52c4a5c48049 |  | note | • Confirm all reinforcement matches drawings
label | 18a79500-5aac-51bf-bf99-be7507a4f890 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | f8bc78cc-04f0-51f4-9842-1469aa65f0f2 |  | note | • Visual inspections
label | 5593e5d4-47bb-55ec-aca3-8cb4bfc8fbd9 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 23a931eb-b7b3-5378-8151-25be5c2ddb47 |  | note | • Each reinforced cage
label | f255343c-5431-5746-95f5-bc5b16c0a62f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 84dc1d8d-3110-5fc5-9e0b-3707717dc738 |  | note | • I
label | 4d93497c-e78a-541b-ac0c-d278298f99b9 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 6c6afb15-71a1-5151-93db-3aabe0895b8c |  | note | • PE
label | 5634a5b8-6036-5e74-b48c-b9512eb7e4fa |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | a0b0b318-81ec-5b54-aa86-0e4d5af72341 |  | note | • Concrete Pour Inspection Check sheet, As built
checkpoint-status |  |  | checkpoint | 4.6. Pre-Pour MSQA Inspection
label | 991448a5-f7c4-518b-a6c9-fda7e9c71929 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 7ee8aa61-5039-55a9-ba07-9d63d8da4b85 |  | note | • Drawings
label | d7a9aaeb-772f-587d-9341-abf3f525ad06 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3578c6a9-aba9-5255-9012-73b304e4e96b |  | note | • All above is as drawings
label | c2dd6fe0-b977-5bb1-8f64-98c46fdfa496 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 30a37170-aa7e-58e5-b22b-0d13e716705c |  | note | • Visual
label | b9b43c83-0fa1-5d58-88af-a21cc4c3f0fc |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 69b1aaad-2261-5799-9fb1-77993cb15767 |  | note | • All Piles
label | b04585fc-de7c-529e-82ad-1a1c4c657330 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 20c19885-3067-54d5-9155-b15cffa3bfb1 |  | note | • H
label | b18626a4-fc1f-5d66-97a1-772c797800a1 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fe8bfa77-f048-5b10-9005-8caba3e4b7ec |  | note | • PE, MSQA/DSR
label | 8cfb0014-4d79-50c6-8cc0-221b19e0512e |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 743327f1-b7f1-5649-9030-6312cc88b551 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 4.7. Concrete supply
label | 032d7ce1-446c-5bcd-9bdb-73aea61448dc |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 198c326d-a8df-55cd-b082-80cc54a1765e |  | note | • Drawings & Project Spec
label | a3a3a402-9b0a-576d-a8d1-e6f233ecdec2 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3a3d029f-44e3-5c15-bdc9-dd3f1df2dbb4 |  | note | • Request a minimum of 3no cylinder test on all structural items, 7 day, 28day.
label | 9df9431d-e8f7-518f-abf7-f371eadf0235 |  | note | • Concrete cures to strength (40MPa).
label | b177ec3d-f8b7-5e16-aa9c-d5297962f6ee |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | dd300bb5-a65f-56a5-8af9-1d02cf1f9d8b |  | note | • Concrete sampling and cylinder crushing
label | 20e582b9-3497-5c0b-afd2-ed5639635744 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | df076d07-f9be-5c33-9f53-fa9cb5b69cb7 |  | note | • Each Pour (or 1no set every 75m3)
label | 39a3ae16-6e8d-5027-834a-210c838d75e6 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 6bb38144-a861-547e-b547-a088a83527b7 |  | note | • R
label | bbaf2431-6888-5d4b-b583-a54c097ce530 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 8b1d2888-4a38-5c93-b83a-297e33f88380 |  | note | • PE, MSQA/DSR, Lab
label | d974aa5a-dce8-56f0-b26e-6dad36f11747 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 3aac9b27-c56a-54ea-af54-d89c1dcbefe1 |  | note | • Concrete Test Result Register, Compressive crush lab test results
checkpoint-status |  |  | checkpoint | 4.8. Concrete Finish
label | 47ccefd2-e8da-5149-b0d7-8f25ba2bbc82 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b6b84316-eb9b-57cf-80b3-f457094a344f |  | note | • Drawings & Project Spec
label | a80583c2-b41a-52b7-8ae4-fbe4521fcda6 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 05e35909-663a-536d-a71e-b6a5c66f70a6 |  | note | • As per drawing request, type B joint on top
label | f9296017-8b0e-5aa0-8c3e-4f0344ec24fd |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | d30945b0-ae45-5f1c-89c5-32998430dabb |  | note | • Visual
label | 026b379a-9404-5aec-b923-f44daa7732b5 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 0a758f03-9a78-5023-9fad-2b528e3e777f |  | note | • Each joint
label | cf8ac7ec-7d07-5b45-a3da-0676f517c3b9 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 86775a06-2d8f-5601-b1b0-74897bf471c8 |  | note | • I
label | 1706c6fe-4e77-5b21-befc-532b4e15e919 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 50a6ab0d-b797-5b6d-82bb-b570d7b224b9 |  | note | • PE
label | ec2ac623-2268-5e7a-a985-d935bafb15ea |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9b187eee-9f51-5a22-a3c3-9ffecd673250 |  | note | • Post-pour inspection record.
checkpoint-group |  |  | section | Structures - Formwork and Steel Fixing (NAB, SAB, Central Tower Footings, misc)
checkpoint-status |  |  | checkpoint | 5.1. Install Footings for Temp Works
label | e268598c-e2c3-5ceb-aae7-1c74d25d0420 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | bb25648b-a534-5151-8012-d635744a7d70 |  | note | • As per Drawings
label | 82ae4e69-304f-5a15-aeea-a204ee1b2eaa |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 071d7c61-b8ba-5c0f-aac8-0fb82a5d0255 |  | note | • As per the formwork design
label | 835099f4-04a2-5773-a60b-d9c2e5b90c8c |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 5aadcd3e-6c6c-547c-b039-ae591594d07f |  | note | • Level Check by Engineer
label | a37b9509-747d-55ce-bd6e-9624718682ea |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 85be25e4-2789-5a6b-b76a-3e10c7723d90 |  | note | • Per Element
label | aef767e7-d43a-56ac-adf3-c8cb984f9bea |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | f9d38607-21fd-5b5d-a7b0-4a98281f9216 |  | note | • W
label | 29378c0f-47a1-5d40-bdb4-1ad2c64be667 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | d28460d2-f230-50f7-b78c-5116c0ecd58c |  | note | • PE
label | bc3c2cf0-9a96-5533-a86b-4cf3b4686d56 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 43302cf0-dc16-5977-9414-dd20f968c0d1 |  | note | • Concrete Pour Inspection Check sheet
checkpoint-status |  |  | checkpoint | 5.2. Install Blinding
label | c72f13d6-eb54-58fe-a99f-48afe95305b4 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 68be54f4-b071-58d1-bf7d-f7d5ba7cdad4 |  | note | • As per Drawings
label | c8e891e7-8b36-5e2a-9bfd-0da017c7bcf3 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 87490d91-9d31-5c52-a23f-8ace31786cce |  | note | • Blinding thickness and level to be as per drawings/required
label | 158fe809-1428-595a-9786-bb86b16a3443 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 983e1c19-1c1c-5015-8276-c5b04bb49f2d |  | note | • Level Check by Engineer
label | cd9ee49f-7b64-554e-bad3-28a6474caa41 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | c5d2add7-5a41-52e2-84cf-cceb93925b56 |  | note | • Per Element
label | f8a92c6b-1453-59b9-bdcd-fc702dcccdad |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 1277f853-ad06-5633-ae23-888008f6c7bf |  | note | • W
label | 9e30256f-7c23-59d6-ac83-9cdbf1b1d30c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 1acdf262-91dc-5312-9337-0c0105214596 |  | note | • PE
label | cc287c50-55b6-5772-bbc6-0e3d91dc7547 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 33413fbc-0a66-57fa-b08a-6fcf28067d7b |  | note | • Concrete Pour Inspection Check sheet
checkpoint-status |  |  | checkpoint | 5.3. Formwork Placement
label | 437ac288-5afc-50e0-b536-17e189957f66 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 99c7903d-4f94-52e4-b0bb-0f4097005717 |  | note | • Drawings & Spec (To be issued)
label | b17009a4-2672-5b40-bfb3-8cebee5a6517 |  | note | • Formshore Temp Works
label | 7c24b5ee-aa45-5c1f-b32e-2e98994409c5 |  | note | • Doppelmayr Drawings
label | d55a4a42-32d2-58ac-92f1-2f524bef6a65 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | c8c24328-58a1-54fc-b6b8-e0484ecdb83f |  | note | • Formwork as per temporary works drawing if relevant.
label | 5cb74200-be5f-5997-a786-25fa0a162793 |  | note | • Position, orientation, dimensions checked.
label | 9eb9126b-690a-5345-9613-c6adb9a32e14 |  | note | • Oiled, Area cleaned of all debris, Cover correct as per spec and drawing requirements.
label | 01f1f0de-5894-5181-a35f-03ab37d6cefc |  | note | • All inserts inserted, block outs, dross backs, bolt clusters etc See temporary works design.
label | 87193310-b343-5bf7-a740-3a7dc30a38de |  | note | • Confirm any inserts are included as per drawings.
label | 08bd278d-4ff4-59e8-bd57-858c914160f6 |  | note | • Ground anchor drossbachs critical – placement takes precedent over all over items.
label | a0254689-ac92-5c2a-96e3-b961893d7fce |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c38c96e1-577c-56eb-8ed8-b672a6e0a46e |  | note | • Onsite Visual Inspection
label | f5b60228-a58f-5ff8-9ac8-cf88ac9a9f27 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | f4779be4-9e3e-516e-a49c-6c1a3d28ab38 |  | note | • Per Element
label | 6f3df709-1078-59a2-9843-d3a50b60f224 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8bf2f972-9d4d-50af-8faf-b21a1b6eb074 |  | note | • I, R, H
label | 706351bd-ad7e-5519-a309-823eaac3bd86 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 89bea273-9eb6-5926-b1de-3a07caaa3dc0 |  | note | • PE
label | 1ff3a2cd-bd8f-577e-b76c-c5ff172cce42 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 872e5186-1874-57c2-b18e-31e7f214d8ae |  | note | • Concrete Pour Inspection Check sheet Photographic evidence, Survey Checks pre pour
checkpoint-status |  |  | checkpoint | 5.4. Earthing
label | 179068e3-2a4c-5050-ad92-ec72211b74d2 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 13ac616b-7696-5169-8129-1e49a73a9baf |  | note | • As per requirements
label | 85882a9c-8e2a-50e1-b886-37a4d15a627b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | cd199acf-4057-5037-a5ef-8681a188eee1 |  | note | • Each concrete element TO BE ELECTRICALLY GROUNDED BY AN APPROPRIATELY QUALIFIED CONTRACTOR.
label | acda63c9-56d5-5be3-8d16-7565bb53496b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 08cb715d-9cd4-509c-b48d-2a0d46bcef54 |  | note | • Visual Inspection
label | b073c7e5-2c9b-53ca-a309-f878fbac87c2 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | a82b1937-9954-53c7-9d88-932ce82ccd9c |  | note | • Per element
label | 18275b99-0739-5687-9ab8-9eb8932ac79e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 34a046d1-a132-521f-bdbc-592560056b69 |  | note | • H
label | 9c407851-ae51-5cfc-b76b-3dd07870deee |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fdb4f05b-c02f-5ecd-bd26-e39d88ddcc97 |  | note | • PE
label | ddda06e8-5cb8-5cfe-a748-5e7c766e3f8d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 05f189fe-7ab9-53d0-a43d-3490a4320d9b |  | note | • Report, Photo
checkpoint-status |  |  | checkpoint | 5.5. Reinforcement Placement
label | 1f93b989-a739-528d-8023-8891866d3b48 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 80c1e902-229c-525c-b0a2-8e419db5ab09 |  | note | • Drawings & Spec (To be issued)
label | 692a076a-a433-556c-9562-e4df13363127 |  | note | • NZS3101 & NZS3109
label | 287cba95-828d-5278-ac58-e7bf89bb2130 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 72145de4-044e-5cfe-885d-540a4693bf9d |  | note | • Reinforcement as per relevant design IFC and standards NZS3101 & NZS3109
label | abb37c2a-9c09-5a4b-bcf4-f4f74ae8ce97 |  | note | • Grade, number, diameter, spacing, starters, cover, welds, lap length and position all checked.
label | 25452442-36f6-57cb-9122-c39da4f29266 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ec69c584-4d8f-5989-bc6f-dc8946ccda1a |  | note | • Visual Inspection
label | ad63d122-cc30-5ff5-a30e-5f8ad3829f4e |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b91d0cd9-51be-58a5-83a6-44d90f0518e6 |  | note | • Per Element
label | eb3461ef-4443-5a38-bcdb-df653a36a894 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 2d4a55ad-5626-538c-acac-c33926da3252 |  | note | • I, W
label | dfde7c5e-ba22-503e-8a3b-643a9d99db44 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 1925c479-78a4-5962-9205-9085d2d4db75 |  | note | • PE
label | 7e1660f8-6df3-5f43-96a2-b5286df89802 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 60c4c56e-2ebd-59e9-9b10-2621c4f4f2fd |  | note | • Concrete Pour Inspection Check sheet, Photos taken and stored in QA File
checkpoint-status |  |  | checkpoint | 5.6. Cableway SAB/NAB Williams bolts
label | ff63ea0e-7e74-5f2c-a77c-43f6a0f24795 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 962de1da-1433-5d3d-a61f-cd6041eb3ece |  | note | • IFC Drawings
label | 57f40c0d-70fe-5905-ac38-e555e703df6a |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | dc5ef26c-ed66-5a76-8288-e1c95df3a4f9 |  | note | • Size, length and position of the bolts to be as per the design
label | cc07cdc5-1168-58d7-942e-3d44a7d83eae |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 4c890d17-0612-54d3-828e-728f104c6f91 |  | note | • Visual Inspection
label | 4a060cbc-fbc2-52b4-9781-427a7115ceb9 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 58e64bad-afdc-5b60-9c53-067af7178010 |  | note | • Per bolt
label | fdcbbf4c-45da-5e28-ab77-50f9436daeec |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 3285f756-ade8-510a-8336-231ddbf8178c |  | note | • H
label | 1688a166-2562-5e6b-b431-3f1b2881e9f3 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | d2fd7f3e-b593-54a9-bddf-93cc5f3bc1b8 |  | note | • PE, MSQA/DSR
label | 06da6a19-9a5d-5ca1-b329-6267a070662d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7c609c0a-d5d6-5b01-9849-d723f3d59bf7 |  | note | • As-built
checkpoint-status |  |  | checkpoint | 5.7. MSQA Pre Pour Inspection
label | f0fd00fb-f614-5bbb-b393-5b5b8768392e |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a83e7a70-62e2-5295-8ce9-9da4aa279e1d |  | note | • Drawings
label | efad27e3-2ea5-50f4-a82a-058d8b48909e |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 947a35c4-de07-5f19-b012-130c823a44a2 |  | note | • Confirmation of all above, reinforcement, dimensions, inserts, finish
label | 10fa8e6b-d2bb-5993-8a1c-4daa73cff85b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 78173002-645c-536b-8426-a8122f654340 |  | note | • Visual Inspection
label | ba33cce6-9010-5b7b-ba1f-97e9287fab3a |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 784da88f-3073-5688-9a83-756703e08c69 |  | note | • Per Element, Holmes provided 48hour notice to inspect.
label | b5f0f3a2-00f0-5d66-9cb0-7c8ef865f1e2 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | ebab0b2e-59c5-549c-90f8-cdc2e10a46a2 |  | note | • H
label | 26a37a1e-52d5-520d-aec8-b51f5472d824 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f231e42e-ffbd-59aa-a6e5-a4da3ca8a72b |  | note | • PE, MSQA/DSR
label | 2f5e6ec7-a01f-5927-9409-922dd3abce84 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 970e3e1b-8f11-5d65-bcd0-a61cf8fc12fb |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-group |  |  | section | Structures - Concreting
checkpoint-status |  |  | checkpoint | 6.1. Concrete Delivery
label | c1789aed-752d-5bd2-9fa8-7f6e26d8479f |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 8cff6ca9-ffdd-5437-b8b5-2a4359cf00c2 |  | note | • Drawings & Project Spec
label | d962de97-cf50-5705-a665-8e17438dfcff |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 62afc40b-0f17-5ff5-bb22-7999bc82e126 |  | note | • Supply to match design drawings and specification.
label | e0aa8a2a-87df-59e2-8ff9-ea57e8e474a7 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 6a69ce40-44bc-53f1-84ea-afd0ec0dc72f |  | note | • Docket Checked on site for correct Concrete type.
label | b53c6379-44c6-5099-8dbf-41193b98a1a8 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | f65ab9f7-5d30-5c47-8b31-968d1642a461 |  | note | • Per Element / Per Pour (minimum)
label | 13efd765-8cb9-531c-8620-601999e3dc04 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | df44e847-1b76-597c-bc87-656e923b49c0 |  | note | • W
label | 730b32f6-7cff-505d-80e2-6714b3809052 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b104134c-07a2-5880-808a-52b36bbbc7bf |  | note | • PE, Lab
label | cd96dd29-ebb3-5952-8104-2132e6d3e597 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | dab9479b-0ce8-524b-b236-d6bccd38b201 |  | note | • Concrete Pour Inspection Check sheet
label | 9229eca3-4676-51db-88bd-2336528a83db |  | note | • Concrete Test Result Register
label | 165fd99d-4e22-5d87-a174-3a99b38aecdf |  | note | • Docket checked onsite/Filed
checkpoint-status |  |  | checkpoint | 6.2. Concrete Finish
label | 7a43dcd1-75b4-58d0-a1c8-31083ef43fdf |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | c1b9ac54-cfa1-5a7e-8eba-39300a951b7c |  | note | • Drawings & Project Spec
label | e513370a-78e7-5dff-b612-c8af62b68437 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 800cd600-a0f6-5089-88f9-d5b618bbfb18 |  | note | • Concrete finish to be as per on drawing, U1-5 or F1-5 (inline with relevant NZS standard 3109 and NZS3101)
label | eba79f05-f6ff-5c2b-9281-c9c2fdfa9520 |  | note | • Concrete checked for any cracks and other irregularities.
label | 79d65d07-b94c-5148-bf68-cac3093a321a |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 10986c05-633c-5bf6-8b4a-698ed892af64 |  | note | • Visual
label | 4fc0f5a8-612b-5ae8-a2b4-bdf32fadaa41 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 84d13530-4021-596b-98f4-d027207f78f5 |  | note | • Per Element
label | 01768efc-f44b-5d12-9e99-961b35ab1c09 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | dac6bf88-0de5-5b72-aaff-97e40cea1409 |  | note | • W
label | 8b2daeee-6ec1-59a7-ba98-3379c9a69a32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 83c92c0b-9e13-50ec-8712-9941cc778619 |  | note | • PE
label | b3482b89-e1f9-5e36-b7f5-ad24cba35ff3 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | dc5a2134-8e17-5e5a-bf5c-f2f79bfe507e |  | note | • Concrete Pour Inspection Check sheet
label | 68e6f27d-a7a8-524c-80fa-5988171d0177 |  | note | • Photographic evidence
checkpoint-status |  |  | checkpoint | 6.3. Concrete Strength
label | b59f4473-1956-55cd-ac57-24b6f3691f8a |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | dc6b6518-9f1a-5aa9-8839-2b15f5a56822 |  | note | • Drawings & Project Spec
label | 92dafc3b-8539-5339-be15-199674041e7d |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ef077e8a-cf7d-5140-94ee-665f8390ecd6 |  | note | • Compressive strength results to match design drawings and specification.
label | b2f17c9b-9fa9-50f1-ae14-d8b764a37cd0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c3bee8e5-931b-5614-a3f7-e78fdc3a6344 |  | note | • Review of 7day and 28day strength results.
label | 7664085e-0ad9-5afe-a6fa-1fdaba8509c1 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 0b714584-2c8f-5d11-b77e-403ce9fc0157 |  | note | • Per Pour (minimum) or 1no set of 7day, 2no 28days taken for every 50m3 +
label | c5f245c8-9d07-5904-bd60-784439c78566 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | c1bcadb9-0fd0-54d5-8331-0a9e949952cf |  | note | • R
label | 307741a8-14fa-5925-89d9-63ff64446687 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b27a237e-75af-5171-9f91-296b4ba3dbb5 |  | note | • PE, Lab
label | 4b931d97-7f7b-5ea7-8599-ce3a17ef1bcb |  | note | • (MSQA/DSR)
label | d086303c-227c-5c34-bbfd-905145ed4553 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | ababe297-35e5-5845-b376-00c7e0d6daf8 |  | note | • Concrete Test Result Register
label | a2af986b-60a0-528b-8d8e-91a8d95d47f5 |  | note | • Compressive Strength Results.
checkpoint-status |  |  | checkpoint | 6.4. Construction Joint Creation – Type B
label | 66fa461a-3d7e-56b8-995f-b8b2d3185212 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 446dd4fc-c6e1-5c73-a3d4-0ee194655a1a |  | note | • Drawings & Project Spec
label | 3ae21d96-bfbe-508d-aafc-f9dc50922111 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 46b15712-0fe5-59a6-a7e1-2a8c3cd88c0d |  | note | • Construction Joint type B
label | 18993b11-2616-5315-b18c-9df955876458 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 0b49efa0-006f-529b-bdd5-933bd8b8d5f9 |  | note | • Visual
label | d53ea45a-2cf9-5bc3-9019-358c9f0ab8ba |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 6ee674f2-54c6-56cf-8499-4fcfcbeae9c2 |  | note | • Per joint
label | 35d68d67-fed2-5471-856e-111861476888 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 46d89852-b12c-5cd8-b425-96072bb58693 |  | note | • H
label | 70be5109-b57d-5b10-b483-479a8c628905 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f7e42152-a1ac-516e-bddc-e4c434018461 |  | note | • PE, MSQA/DSR
label | d836dfec-aae4-52b3-bc7e-042c200a6571 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 2bdeed45-c32f-50f0-b4de-9a2bd7f66bf5 |  | note | • Prepour inspection
checkpoint-status |  |  | checkpoint | 6.5. Curing
label | b517d131-5c90-5b25-a0af-b3bd124b86f8 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 329c82e7-812c-53ea-a1f4-52017db87883 |  | note | • Drawings & Project Spec
label | 3f42da58-24ba-5053-b817-0cd15d173600 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 53ab0f8c-55e8-5770-a9bb-3227b010a6b0 |  | note | • Wet curing method or As per approved alternative curing method
label | d9d062a7-326b-5d2c-87fe-7cee618ea746 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 13ca13bf-6159-50eb-9bf6-48ee31032e40 |  | note | • Approved curing method
label | 4d6cee37-7ac7-53e5-a701-9a4f16e1dc8c |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b113d2a5-5382-5092-9574-cee6cf655f15 |  | note | • Per Element
label | 0246f6ef-db3d-5ef1-b95d-1fc109622a54 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 4ddb561c-8deb-58a6-bd7f-23b17f7a7aaf |  | note | • W
label | 60082181-85ea-5b99-a2df-be1336333d5f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 136683cc-bc55-5fad-bff9-a67cebfd377b |  | note | • PE
label | fd3d84a4-e80c-5a67-a689-90c5ccc3d029 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | c624afa2-78cb-5343-b8a3-f018d67c10f6 |  | note | • Concrete Pour Inspection Check sheet
checkpoint-group |  |  | section | Structures - Anchor Install (NAB & SAB)
checkpoint-status |  |  | checkpoint | 7.1. Drill Anchor Hole
label | 2aef55d4-79c5-5e33-ad1a-fe0d8053e229 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b8a43414-7851-5480-9cfd-59d504cba5d5 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 08cc91ff-fb7f-5e83-9ebb-e191a750e09b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 78ef6b86-200b-5f0e-acbe-0ce2797c349b |  | note | • Inclination angle of anchor 13deg North & South
label | 5bd92697-5430-521f-bacc-0172863d0fcb |  | note | • 4no Anchors at each anchor block – 2 contingences if required
label | d69ac742-df60-5202-896e-92d53d4d00a4 |  | note | • Length – 18m North (TBC), 15m South
label | 5452b269-354a-515d-bd76-272f78102aa6 |  | note | • Tolerance on drilling angle is ±2° both horizontal and vertical.
label | 247f4b9d-45f7-535c-b2da-f703f4aec4d2 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c2e39778-54fd-5b6f-a57c-66104d497e46 |  | note | • Onsite Checks by Engineer
label | d3e17edf-011c-5b8c-9127-6405ef350076 |  | note | • Inspection by MSQA Checker
label | b9af2402-6f96-534c-8898-3dbe54e66d4e |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 30ae3177-9f5e-5af8-8aa7-db1fae16a78b |  | note | • All Anchors
label | d24ad75d-751a-530c-ade6-f493333b6800 |  | note | • One Anchor per anchor block
label | f0dc9fc8-b844-58e3-b1b3-20ded3a2e637 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 866c0e5f-b2b6-528e-8580-fdedf2dcc53e |  | note | • W
label | e4163eb5-36d9-5da5-9e01-e4c34d10516b |  | note | • H
label | eedc747f-62d5-5dfa-a31c-224f8ae10da1 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 817e8c47-282b-5b7c-bfbe-42fd7f566035 |  | note | • PE
label | c9cff728-416c-56c7-8160-ee88358f808c |  | note | • MSQA/DSR
label | d260c863-57d8-5c03-a5bb-2f0c1340670a |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 6d75ec59-5e93-5bf5-b96e-e8ac193c89f2 |  | note | • Drill Log/Anchor Install Check sheet
label | 78314b2c-ceb5-56ad-ad34-a4384f9863b5 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.2. Camera/Inspection of Drill Hole
label | f0380a49-1226-5222-99a3-c055a8755c42 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 84fafd66-469b-5dcc-9c39-d154c183da93 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | a5e8c377-2b55-5522-b1c7-79630308f069 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7378136a-227e-5ca5-b3ea-973d539f7c3e |  | note | • Anchor to be open and clean of debris.
label | 2cce5180-9e36-5fa6-ad3a-12960324cff0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 218f6e8f-6464-53fb-8ff2-c993bce8a696 |  | note | • Visual Inspection
label | fe7635e7-12a5-58fe-88f0-169f397358cc |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 89855936-c104-52d3-9ae7-f406c11233fe |  | note | • All Anchors
label | ac7c0fbb-16de-52fa-8d0c-225b8d13e5bc |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | d7478e24-e08b-580f-99e4-85a340a75dd8 |  | note | • W, R
label | 40031843-f9fe-56e0-b760-221ff7373e9c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f8974acd-57c7-5c82-8f16-2fadfc9e97dd |  | note | • PE
label | f0718beb-3c24-5daf-ab2b-37e5ed7f9e5b |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9cb75679-9c45-582f-9a30-535b4ee877fc |  | note | • Drill log/Anchor Install Check sheet, Video footage
checkpoint-status |  |  | checkpoint | 7.3. Install Anchor Tendon
label | d030f946-cd46-53bb-845c-e572b102ae58 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | dc02220b-5b59-5e4e-b3e2-5299a3909efd |  | note | • MMA-DES-GEO-E1-DRG-4081
label | adeff8fa-6893-5717-9a4b-c732627587cc |  | note | • BS 8081:2015+A2:2018
label | 0496b8c7-0cc8-5606-a86a-3d33295f49d3 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ad16959f-a0ea-5183-872c-9c986a07e77d |  | note | • 11strand Anchor for North Anchor Block
label | f91b5c88-616a-5d69-9e10-241e65b21f6c |  | note | • 10strand anchor for South Anchor Block
label | 3354f77f-ac93-5936-9b8c-07bef61836bf |  | note | • Anchors to be installed with fixed length and free length indicated on drawings. Centralisers (internal and external) should be in accordance with manufacturer’s instructions.
label | c1bf3969-bcf4-5c2c-83c4-42895f691e26 |  | note | • Anchors to be kept clean and free of any detritus materials. Anchor strand stick-out to be sufficient for wedge removal during future maintenance/re-stressing.
label | 15697f23-09b7-5b97-b5af-e60c286b9737 |  | note | • Anchor corrosion protection in accordance with design drawings.
label | 43666071-6870-51f0-a598-44a44cf60cb4 |  | note | • The anchor head shall be protected with a galvanised end cap, fixed to the bearing plate and filled with grease.
label | 0de21082-e86f-5c15-b742-7905b82b8731 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | a3b7a33a-fb02-5c9b-964c-6b987b5aee92 |  | note | • Visual inspection
label | 37f022bd-7611-5747-a1f7-5901868de2c1 |  | note | • MSQA Inspection
label | d59f08ba-f147-57b5-8a2e-4656f125c264 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | c0266762-d75d-5094-9c37-67b4faf9e786 |  | note | • All Anchors
label | 15b87e7c-6eb2-5052-961c-1dd32b985056 |  | note | • One Anchor Per Block
label | 5b04035b-0b7c-59b5-907a-a411975d254e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 969bdf10-fe67-5d94-8218-6f61bc975539 |  | note | • W
label | b185fe54-749b-56cf-8f75-ea616383fc65 |  | note | • H
label | aa37b538-6bae-5aee-bf46-29c8ebbefded |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 28559f47-7550-5e89-8b8b-9ae9b64b15e7 |  | note | • PE
label | 94fd321d-8f1a-5015-b7f7-70002eeb3804 |  | note | • MSQA/DSR
label | 87af0cda-1e9f-5166-b764-6560d5ab172d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 2e6bab53-3a6f-5f48-a363-f592a99bf104 |  | note | • Drilling log and Anchor install check sheet
label | 2e5218f9-fef7-5ca7-88f3-124fda7b23c4 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.4. Place Stage 1 Grout
label | cfd5d6b2-5d25-559d-b101-b02cc8d7c4e5 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d9ccfc7a-850e-543d-aff7-1b32eb6cf5d9 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 8a5b982a-205d-531a-a395-3fc2e970ee95 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2daba3c6-44b2-5589-bc26-1ccb58744d54 |  | note | • Holes to be grouted within 3 hours of flushing hole/completion of drilling.
label | 631221a1-0709-5345-8604-42291bef2d51 |  | note | • Confirm 10m Bond Length grouted and top of grout is behind anchor block.
label | 51cc2083-34a1-5a0a-835e-f74d818ea09d |  | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
label | f6e35a24-3666-5f8e-b2aa-505427efd4e1 |  | note | • Grout shall not be used more than one hour after mixing.
label | c3968f41-c160-5fa3-89a2-cd4fcc482b09 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 9c2626c3-e7bc-54fa-94ab-f54120183447 |  | note | • MSQA Check
label | 7d9245bc-bfed-5ad2-9b8f-39a0a4cc049d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b4ff0389-6088-5d6f-8df3-6c9c1da9e829 |  | note | • One Anchor per anchor block
label | 8d935654-67dc-5a3b-8a81-54c64aa0f6c8 |  | note | • Take grout samples for each grout batch. Review laboratory documentation for all anchors
label | 0bc609bb-0fdd-5971-ac72-f620f519d508 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 9b989be8-9847-5f57-964f-6e21d638d0e4 |  | note | • W
label | 378cef99-2b3a-540f-9e63-6d7dba3faaa0 |  | note | • H
label | 0e7f7dbe-bf07-5ffa-a16d-b08aa41477aa |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | bdd32e71-7359-547b-9b48-06f2ddf7b7dd |  | note | • MSQA/DSR
label | eb4d06fa-1ee2-51b9-8ea0-2759d456319f |  | note | • MSQA/DSR, Lab
label | ff5a0662-7e06-5a77-8522-cac2e7e8462c |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 378a9a58-2148-5ef1-981c-4d0a848712dd |  | note | • Anchor install check sheet
label | d9eb75a2-855a-5c0e-b379-37badb8142d8 |  | note | • Photographic evidence of grout pouring
label | ccc2c777-e386-51ee-8025-12031ec33797 |  | note | • Grout strength results
label | fa6057fe-f5c5-54ec-963e-38a1923cddef |  | note | • Site Report
checkpoint-status |  |  | checkpoint | 7.5. Stressing Jack Calibration
label | b13cc457-6418-5af4-899c-9e2f3eb2c6bb |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d7cad1fb-9139-5a2f-ad0c-68f01dc3d6ea |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 67df6b19-334e-56a4-a1bb-d0e4ce5a4081 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2c4ce277-193e-5c97-b7d8-9781c873255d |  | note | • All jacks and Pressure gauges used need to have current (within 12 months) calibration sheets.
label | 89a5906e-f6fa-5418-ab9a-2629bc18bbaf |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 707340ff-c3f4-5d50-9091-a97d618d3a79 |  | note | • Contractor to get calibration sheets from sub-contractor
label | 606df6f0-1adc-5958-a770-298fc210c086 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 686ce674-4c85-5423-aca4-0bb435c7a775 |  | note | • Once – prior to work starting
label | e0589f1d-d2f5-56d7-85af-6bc004a560cd |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 52e52f40-f0a7-5bc9-ad20-3d03cc6fe0a5 |  | note | • W
label | e9c22565-204a-5938-8a44-a10df4aea376 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b0bce8de-00d0-56ca-bdd5-c8b9df61265d |  | note | • PE, Lab
label | b37f39bc-eba1-5d6d-bb33-5ba24c0fbc97 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | acabf496-9621-5f6f-b91a-c0e50a0d5952 |  | note | • Photo graphic evidence, Anchor install check sheet
checkpoint-status |  |  | checkpoint | 7.6. Smart Cell installation
label | c587e0f0-0df7-56b3-aeab-9de7e33ce9ea |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 41636209-9b21-5c37-8ceb-f80ae6797563 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | b51ecf03-7be1-5f2e-b76d-fc9b194f4ac3 |  | note | • Manufacturer Instructions
label | 7528b220-0abb-5b3a-8a8f-b2f537f87dea |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ff75d6e3-dad9-57a7-b98d-001dd04be76b |  | note | • Need to be appropriately installed and calibrated.
label | 77a646b8-defe-5d07-a66c-b1fed107335a |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 135bc391-c851-5155-84e3-6f6ab5dda88a |  | note | • Physical testing
label | 5b6dbd0e-92f7-599d-9330-39f608d9ee08 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 72472d8d-6bd1-56f8-bd83-b65226d19a63 |  | note | • Prior to working and after pre-load
label | 8bda275e-e5fb-57fa-b0b6-69ee10f9233e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 309aa66c-d656-5f38-a49b-109ca669d2bc |  | note | • W
label | 08928ec8-d72c-5c4a-ab29-5338cfffe03e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 5c91c43a-150c-53ff-b021-62cfb705cfa6 |  | note | • PE, MSQA/DSR
label | 6f3d67c5-be0e-51f2-9cfa-47086a0a11c0 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | f3d9636b-9d9b-566d-926e-e722ef9e9d61 |  | note | • Contractor records.
label | d172d617-0c02-5d9f-9d80-d6cb6496668a |  | note | • Site diary.
checkpoint-status |  |  | checkpoint | 7.7. Stress and Lock off Anchor
label | 5906d67b-db74-5030-924b-e7785fc513a7 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 20b167d7-56e6-5821-8a52-98a5562f9f54 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 7dee3307-8a96-5919-9af9-f296449ad657 |  | note | • ISO 22477-5:2018
label | b97ceb95-a716-5404-9026-e0a98a2fd661 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3de7c8a3-aaf6-504a-bce1-e717932444e0 |  | note | • Confirm RC block concrete and anchor grout have achieved a strength of minimum 30 Mpa.
label | 1c854980-d747-5deb-a7e4-9dff7408b35b |  | note | • All anchors shall be stressed and locked off at the lock off load shown on design drawing.
label | d1859baf-e3ef-5fe8-81b8-4ba521943633 |  | note | ○ Acceptance test Proof Loads:
label | e3105079-fea2-5529-baa8-a7eefb36d6e3 |  | note | – NAB -1500kN,
label | ff3528ad-3adf-51b8-aa57-3ed8ee14453b |  | note | – SAB – 1350kN
label | 87171c6b-ffc8-572c-8b89-ddab3970c13d |  | note | ○ Anchor Lock off loads:
label | 695e6527-c729-5eab-916c-2c1ce9cd095a |  | note | – NAB – 1350kN
label | 95d00891-4484-5565-8f25-79b96b11ee5a |  | note | – SAB – 1230kN
label | 3ed04603-4e2a-56ac-bf1f-0476a7112b61 |  | note | • All anchors to be acceptance tested in accordance with ISO 22477-5 and Table 2 of design drawing.
label | 63b0dac1-6b15-55ab-890a-ccb1c6d82315 |  | note | • If anchors pass acceptance criteria on design drawing (displacement, creep, and apparent tendon free length) they can be locked off. If fail these criteria must inform Engineer immediately for instruction on how to proceed.
label | ad9051dd-ca79-526d-81fd-e5e65955a520 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 62b49a4b-5287-5cd0-9841-9559795f590e |  | note | • Visual Inspection, grout tests, stressing records.
label | 4780e038-cdac-5fa1-b67b-eaec727e301c |  | note | • Acceptance test reports prepared in accordance with ISO 22477-5:2018 are to be provided to the designer's representative within 48 hours of completing each test. Results to be provided in electronic format, including raw data in .xls or similar format for ease of interrogation.
label | 78d2b485-be50-5778-a8a3-7e11f2c83345 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bc4eaa11-c6d6-56ed-a043-f74676da41a1 |  | note | • Each Pour by PE & One Acceptance Anchor per anchor block by MSQA
label | bcc9299f-82b3-543a-941a-8db0eb03759c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 37593edc-5979-5039-b56f-35342c4d7d83 |  | note | • I, H
label | 967783e4-b249-51a1-aa1d-34236ad160ff |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b672ea79-c6a9-516e-89c0-a561b9f9dd4f |  | note | • PE, MSQA/DSR, Lab
label | b8311861-dba8-5897-8ff9-931068ee95d7 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 0eb6f617-0b62-5979-a99b-4742f4a887e0 |  | note | • Grout test Results
label | 79cf509f-1ab9-56dc-98e3-7f9872d23e1a |  | note | • Stressing Acceptance Test
label | 4f3b0a46-f968-50cb-82dc-231f6280c889 |  | note | • Stressing Record
label | 643ead2d-aed9-5edb-a013-40314f3afd9d |  | note | • Anchor install check sheet
label | a8bf8ad9-7ecc-53fb-8e1e-a1d5ed2d48db |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.8. Place Stage two grout
label | bbf7c506-da8a-5c80-abb6-3e42c4925cf1 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b8518063-fac5-5ec9-86ce-bea9a7653470 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 6623cc7a-d7d7-519a-9b67-558b684b927a |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 62a79a77-60f5-5690-b865-223524faefe3 |  | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
label | ec11d289-5378-51d0-bb73-df2e47abab90 |  | note | • Grout shall not be used more than one hour after mixing.
label | 51bdd483-e2f1-508c-a617-d24dce6cefa4 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 1d02b962-d66a-58dc-85b5-aa9c6cad3992 |  | note | • Visual Inspection - MSQA
label | a005cae9-5cc8-5b6f-9f30-af1744fdbb89 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | eed4cb44-e4be-5772-810d-623cbef249af |  | note | • One Anchor per anchor block
label | c381de70-8574-56ba-b087-3ac4f23d0813 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 25186918-2fa8-52bd-bd42-d6b82933f39c |  | note | • W, H
label | d64287c0-fa1a-5f25-9f01-d3e8298e775d |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | bf22cd46-6f72-52ce-a7c0-e809e516e914 |  | note | • MSQA/DSR, Lab
label | 18c789c9-0215-5ccf-9840-f5cf2c2333f6 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | b3ea81cb-2545-553c-ad06-75bf4468dd2c |  | note | • Anchor install check sheet
label | 3769a5e4-d7f9-55d9-bd53-06a66a210dfd |  | note | • Photographic Evidence of grout pouring
label | 95f52c8c-6348-52c7-8e72-cf8f436eef3f |  | note | • Grout test results
label | eab18c75-2cc8-5315-9d6f-a9363ec71237 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.9. Finishing Works
label | 21c60541-38e0-5569-823a-ba2f2d87a121 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 26ba656c-5977-5a71-817d-f12ec653efb7 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | a4d50a92-e93e-5bf2-b415-abc4ae5a3f2e |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 27bfc3da-c26d-5acd-aded-7dcdce3226b5 |  | note | • Install Rubber Gasket
label | 1d432c2c-016e-58e2-94de-75e4d09fdb46 |  | note | • Strand to be left (100mm or more) as advised by contractor beyond anchor head to allow for wedge withdrawal and future re-stressing.
label | c3be627f-70b3-571c-8ddf-f29d6e0a12d8 |  | note | • Top Cap (HDG) Installed and Packed with Grease
label | 484a31fb-3960-5f27-abc7-8993a7df516a |  | note | • Bearing Plate and anchor head detail to be in accordance with drawings.
label | e04409eb-4522-5a96-82dc-776499944d34 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | f34872d6-2b77-5f5d-b885-108dcc56c8c5 |  | note | • Visual Inspection
label | 6d5a3526-3317-5c56-bb03-fac39f291c37 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 8a2711a4-024b-57fd-ac09-29cf6ad9f6fb |  | note | • All Anchors
label | 08890ef9-298d-57d9-881a-d59de240404a |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 6a48b1e0-9780-5d01-b8b5-0688efa6154c |  | note | • W
label | 89d411c8-30d3-59c9-9d43-5a6ab372a798 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fe128b84-d8da-5f70-9c1e-1cdc23f0216e |  | note | • PE
label | ad2a9973-0231-55f0-97a3-d45531c1d6a5 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | fbfa9864-a7c2-5e8a-9c54-b8a8bb5486f1 |  | note | • Mill Certs for Plate
label | ae743f65-9b88-5edf-b4fa-cee3304b7b6e |  | note | • Anchor install check sheet
checkpoint-group |  |  | section | Structures - Structural Steelwork Fabrication and Erection (Drive Station Shelter Building and Tower Footings)
checkpoint-status |  |  | checkpoint | 8.1. Weld Inspections
label | ba33134b-b330-5492-8650-4e42ead6ce9f |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 29616399-4a00-5a73-8581-9bbdf440b7c6 |  | note | • Structural Steel Work Specification, AS/NZS 1554.1
label | 03643554-676c-5ac7-87f8-748ff4d630e2 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | cfe2939b-2a3d-5a28-8d28-095353e8f7c1 |  | note | • 100% Visual Inspection
label | 9d941a0f-4d8d-519c-bfd2-3479cecf7c0c |  | note | • 100% Visual Examination
label | ef012016-c7f9-5899-b8b6-791affe790df |  | note | • 100% NDT (Ultrasonic or Radiographic Inspection) for butt welds
label | fa07419d-91e2-5a7b-b551-dc7d95ed8911 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 1dad4487-b85e-5885-be19-770297a4d7b0 |  | note | • Visual Inspection/NDT
label | 78ed558d-02b9-5cc7-9227-e62fdcdf1532 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 1d1b87d0-0ff9-50e1-8df1-d61f4dae2581 |  | note | • All welds
label | 07c44b9c-3c41-550a-8131-44171d43db32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 18e89607-1e21-5715-8620-65f18b8be1ef |  | note | • I
label | 919f1b09-4615-5d3b-bb0f-74fc7ea020a7 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 7bb37fc5-ba5f-5e5d-b53f-9ea9cfd3ba23 |  | note | • PE
label | f90eb9f2-4cfb-546c-b44e-7a1aaaff8e75 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 42873eef-4ffb-5c35-9a10-50a4f5263668 |  | note | • Weld Inspection Report
checkpoint-status |  |  | checkpoint | 8.2. Weld Inspector
label | 51362cac-edcc-5f3c-a9ac-f7f7e1232613 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | f098dd26-72ca-51a0-9c27-29b3aeb6f1a3 |  | note | • Structural Steel Work Specification, AS/NZS 1554.1
label | 0d7abdd0-1ce1-569b-9bde-708db5726aad |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 536bc3d0-5f13-57a1-a2ea-e135124e584d |  | note | • Weld Inspector to be independent of Fabricator
label | ff5cec3e-1f84-5e68-8011-8a0b0a8341fa |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | aaed8b71-a89c-56a4-82a0-4bf9b381431e |  | note | • Review of Qualifications
label | 0b609d6a-dba1-5ca6-bc60-303f8f159705 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | ed036ab5-e9b3-5e59-8345-3089bc3802f5 |  | note | • Once
label | 3d7104cd-9c89-5f98-a48e-bf3a34f6b04f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | fe75674c-c24e-59bb-a9ad-6fc722a3c261 |  | note | • R
label | 8b5b11be-d0a0-558e-b4dc-67540044f5a4 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 2d7065e5-d908-5878-92a1-2690af579243 |  | note | • PE, MSQA/DSR
label | 2bf45c07-34cf-5a15-a8d5-c5b842afb4f5 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7e31d082-d1ab-5ca9-b8fd-174e49b78e47 |  | note | • Inspectors qualifications/Certification
checkpoint-status |  |  | checkpoint | 8.3. Shear Studs
label | af7e38e8-35e4-5e4c-9167-0e82438fe4b3 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 880f7036-4f2e-528b-8585-4a9494c6052b |  | note | • Structural Steel Work Specification, AS/NZS 1554.2
label | 0e16f785-688a-5979-844c-037c8e075dff |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | d6b639ca-af94-5e71-b696-0198c4fc4572 |  | note | • All studs to be ring tested in accordance with AS/NZS 1554.2
label | a49baf49-ec5b-5658-a536-7b98311d3224 |  | note | • Any studs that fail the ring test to be bend tested in accordance with AS/NZS 1554.2
label | d3fb0851-fb1e-5953-8ecf-472c9545f175 |  | note | • Bend tests to be performed on 1st and 2nd Stud from production run followed by 1 in 50 there after
label | 45fb79ba-79a6-5406-a6c0-3e9b7bb290ac |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ecfaaf52-669b-5d58-826a-cdf597b570b7 |  | note | • Bend/Ring Test
label | 3f3260dc-d5d1-5bea-bf8b-5b1fa8fb6828 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bc875b9c-30a7-5d0d-a538-d40fee723d73 |  | note | • Ring Test all
label | 87833d64-7573-59ab-ac24-f4bca4faee54 |  | note | • Bend test 1st and 2nd, 1/50 and then as required
label | 989c6a7e-0d4f-5bd0-ab35-e9ae8184230b |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8614e4ea-4fab-5657-88c0-0d6bbfc900a9 |  | note | • I
label | 2001407d-e59e-5cef-8d54-a30f0918cf72 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 66c01beb-7341-51be-9e50-810186ffe5ec |  | note | • PE
label | c27ae4aa-7ace-5ebc-b38d-bdb728bb0289 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | c9ec53a3-c707-5a36-89fb-9f4ec07ebd69 |  | note | • Test Report
checkpoint-status |  |  | checkpoint | 8.4. Inspection of Bolted Connections
label | ec93ce4a-1885-5af1-b394-c52cfafccbcd |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d766a913-1736-5401-9d10-a683da132b0d |  | note | • Structural Steelwork Specification, AS/NZS 5131
label | f365f078-5c85-51fd-9047-d6391f374cee |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7c8b58f4-06a0-5b5c-a7f5-994cc72d02b3 |  | note | • Designer/DSR to inspect min 10% of bolted connections
label | 862c36a4-7f93-5c7c-a296-915bd8c49faa |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 15f6b036-abba-5f4d-bbce-272cd8225a50 |  | note | • Visual Inspection
label | a5930786-1323-5d61-908f-fb749c542cfd |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 504e92a3-bf88-531c-aeaa-faa2afa95e5d |  | note | • Minimum 10% but no fewer than 2 per connection
label | 84c8e556-898b-5a5b-97d9-6f5c247ac4be |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 29dcb543-c5d0-5768-80af-a09f85e2b932 |  | note | • I, H
label | c5fdbd7e-a1ff-5143-b1a3-8037fbcb2a75 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 8b62a166-4173-5f0e-9723-9acf1a6a3773 |  | note | • PE, MSQA/DSR
label | 4b3b6245-e8da-5404-89cd-2df87434c6d9 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | d65f5e5e-af22-5226-858b-e027a3ed6bc2 |  | note | • DSR Inspection
checkpoint-status |  |  | checkpoint | 8.5. Inspection of Fabricated/Erected Steel Work
label | 6cf27208-0f22-5b3b-bd83-b73e37abd4cb |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 5badd6b2-357b-5424-be4e-26c3089384a3 |  | note | • Structural Steel Work Specification, AS/NZS 5131
label | 27764164-59ba-527b-9e4a-9e0c3f38a776 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7fada03c-f191-5c9d-9fd3-d5b5ffd07c13 |  | note | • Designer/DSR to inspect fabricated steel work
label | 7bd67302-88c9-57c6-93b4-8c9a07f1ea9d |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 9bc0dfb8-3a79-5905-8937-073462e4629e |  | note | • Visual Inspection
label | 2862460f-6615-584b-a674-3c471fec9d9c |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 120503d1-8084-5e0c-9e83-3f0b0cfef51b |  | note | • Per Element
label | b0de2df8-7e01-58ac-a71d-2ba4e0f2811f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 57c3d65b-10cd-5ace-9b1c-a296d02e3a33 |  | note | • I, H
label | 50c8b810-b818-5258-9e36-41eee8503b32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b3c714eb-4657-51f4-92ee-d67da24e249c |  | note | • PE, MSQA/DSR
label | f89b1150-13e4-5c8d-910d-af87707f4baa |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 1dbc3972-f751-56af-a505-1609c9a82e42 |  | note | • DSR Inspection
checkpoint-status |  |  | checkpoint | Completion Verification
label | c7a84e57-84b4-5814-be7b-1eb68a616f55 |  | note | Work under this ITP has been Certified complete by:
text | e6f51531-700f-5aad-8a9b-7d0b7a0ed105 |  | textbox | Name:
text | 9515b7c7-2d95-57bb-837a-4ab02bcb92f0 |  | textbox | Date:
label | 55ad0b7c-ea15-57be-8f79-cfbb9b951cff |  | note | Reviewed by [as applicable]
text | 264c0f64-8419-5254-bd37-d741f5f21c4c |  | textbox | Name:
text | a6ace094-bbec-5f6c-96f6-55b441411afa |  | textbox | Date:
label | d0d2fe25-b83d-5222-9413-d7d0836ea8fd |  | note | Reviewed by [as applicable]
text | c368c579-e632-5c5c-803b-ca915f223ff1 |  | textbox | Name:
text | b654b67e-a819-5afd-b5fa-cdef1b467410 |  | textbox | Date:
label | d7341bb1-1a59-5932-9451-25105159d29c |  | note | Approved by [as applicable]
text | 33c84292-cfca-57e0-97dd-f5807986ed1f |  | textbox | Name:
text | dd952e5b-5f8e-541a-9e18-33c62baada87 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-002 - Earthworks Fill | itp |  |  |  | Yes | ITP-002 - Earthworks Fill | f4c3e066-0932-40ed-82e1-a83142e282ca
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - CWP
label | 5fd9bb88-3b79-53e3-9151-353f080bd54b |  | note | Method/Description - Document Review
label | 47382efa-a9d9-5d1e-83aa-6a05fa97ace4 |  | note | Test frequency - Prior to personal starting
label | b77c7875-b811-5025-bafc-27f6d37f572b |  | note | Contractor - H
label | 7299414b-6f95-5680-a6ef-ae4c2fa1b1c8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - Design
label | f44f467c-9408-5bcf-9fd6-d46310dfd28b |  | note | Method/Description - Document Review
label | 4ca92241-da4c-58c7-95ad-cf800a026dd0 |  | note | Test frequency - Prior to starting
label | 7989a9a4-1cbb-5e51-ad22-e8c44fc8778c |  | note | Contractor - H
label | e6be7e3c-b931-5500-85a9-5972ab61d3ad |  | note | Designer - H
label | 6be46ad8-eea7-594c-a498-66c2e59c9454 |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Structural fill
label | 9e5b08e8-2b69-5acb-89e2-a25aebaf0795 |  | note | Method/Description - Determination of the dry density/water content, Atterberg limits, Triaxial (Single stage min. 3 samples)
label | 31206767-71f5-5027-997e-b86de2cf2de8 |  | note | Test frequency - 1 test per 20,000m3
label | 8d183d8c-ad83-531a-874d-7aa219e3fcc6 |  | note | Contractor - H
label | 1932695e-7547-5119-a74f-77096e2f8881 |  | note | Designer - H
label | 1db0813b-af1b-5381-9717-85b6487f9286 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 - Buttress Fill
label | 2e6de0d0-a355-5e5f-ad34-2b0e001809e0 |  | note | Method/Description - Determination of the dry density/water content, Atterberg limits,
label | 5a0e8040-a39c-5d31-af50-cf0df8f5bbe0 |  | note | Test frequency - 1 test per 20,000m3
label | ce2ef2fa-b52a-53e4-81a9-c33565e4ff09 |  | note | Contractor - H
label | d73ede5e-dbbd-5377-80c8-721f81795d1b |  | note | Designer - H
label | cf86c65f-3429-5715-99c8-e6c9982af3ac |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - GAP 65
label | 15e9a983-1bfd-57d8-ba74-b0add443f371 |  | note | Method/Description - Determination of the dry density/water content, Particle size distribution, Permeability, Large shear box (min 3 normal stresses)
label | 3f5d0a04-08ce-51c8-8f92-8d1f8ab9ae99 |  | note | Test frequency - PSD - Source approval 3 no. tests then every 2000m3. Determination of the dry density/water content, Permeability, Large shear box (min 3 normal stresses) - Source approval 3 no. tests
label | a9db67e3-ac43-5f96-82f2-7d89636a0d27 |  | note | Contractor - H
label | 70365c2e-051b-511c-9cd8-41b081169eac |  | note | Designer - H
label | 290defed-37ae-55af-93aa-bf0d5fd6591f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04 - GAP 65
label | 350edae1-1e81-5717-8bb8-c6a5578c23b0 |  | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content
label | def10a62-885b-5f00-8d45-28de02bb0347 |  | note | Test frequency - Source approval 3 no. tests + 1 test per 2000m3
label | fbdcec5c-a1df-5eee-b172-5627805f8d24 |  | note | Contractor - H
label | 7785a918-9c8d-5df8-b230-8a162534488e |  | note | Designer - H
label | 79ce4812-3fe6-5ef5-82ec-8f1037134094 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents of fill and check against design
label | 75c7cef1-8867-5d0f-9578-0069837d3003 |  | note | Method/Description - Survey/visual
label | 0c5e6299-0c2e-5e21-a165-61b06b76c802 |  | note | Test frequency - Prior to Commencement
label | c2d0117a-88cf-5d4e-acbc-d64c8a496997 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | d924b07f-21aa-52d9-8112-81d344a40670 |  | note | Method/Description - Survey/visual
label | dfbe2773-e6be-5a1b-aa5b-fba78835d452 |  | note | Test frequency - Prior to Commencement
label | 9fd05145-a528-5dce-a4d2-e62de04af0d1 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.03 - Vegetation Clearance
label | 0f0af823-8fe8-5d5e-a03c-3f58f8a11194 |  | note | Method/Description - Survey/visual
label | 6f93a3a8-5d3a-5131-8e28-8588e892910a |  | note | Test frequency - Fill area foot print
label | 05abdca3-8277-5941-bd25-fc1cf843867c |  | note | Contractor - H
label | 39f4019b-3fec-5f61-9b5d-118e76c2e571 |  | note | Designer - W
label | 34916c14-082e-519b-af61-d838d9caa4ec |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint-group |  |  | section | 3. Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.04 - any area that requires ground improvements must be completed as per Ground improvements ITP prior to fill operations
label | d70a76c0-0199-54db-b00b-ee6bd229d93a |  | note | Method/Description - Document Review
label | ec292842-fb72-570d-a29d-d022223adeb6 |  | note | Contractor - H
checkpoint-status |  |  | checkpoint | 3.05 - Designer witness of in-situ subgrade prior to filling
label | f67d3db3-591b-5401-9754-20110fa6358e |  | note | Method/Description - Inspection
label | 9f6309ec-3e45-52fa-9979-2f1af5262228 |  | note | Test frequency - Prior to Filling
label | ad6e5240-145a-50fb-bb4b-f8e9ae734ed8 |  | note | Contractor - H
label | 1b7fac84-ccf7-5400-bc09-91ed1ad49256 |  | note | Designer - W
label | 6fbb749c-448b-5dd1-8c91-1898ceafae10 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 3.06 - Undercuts
label | 2d0af70b-c794-5503-9033-ba43c835b09d |  | note | Method/Description - Visual inspection
label | cfcd7212-f0eb-5704-a4be-63ad21cc7f70 |  | note | Test frequency - Prior to Filling
label | c5ed561f-0178-51c6-802a-46c360af8a75 |  | note | Contractor - I
label | 9be81781-869e-54a7-882d-fbf18c635cc8 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint-status |  |  | checkpoint | 3.07 - Sub soil Drainage
label | 71d845ea-235c-5376-9722-6da2b01fd1a0 |  | note | Method/Description - Inspection
label | 9bcd2c4b-c539-5a75-bad8-878cfc2c10d7 |  | note | Test frequency - During subsoil construction
label | ab77947f-a695-5209-b06f-9a22a36c7fd5 |  | note | Contractor - I
label | 028657ff-6a46-5346-8610-d4f36c3429e3 |  | note | Designer - W
label | 3f0b1e1f-9079-59a0-bbb1-6cd3ef45c480 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 3.08 - Monitoring Equipment
label | 65cee39e-b457-51a2-8526-3bea5889f27e |  | note | Method/Description - Survey/ data logging
label | 3769ba62-ba63-5a7e-a4f1-4daf0165a6e8 |  | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | 535a97fa-0c43-5828-b38e-4e5a33e1b156 |  | note | Contractor - W
label | 28ea856a-3d5c-5954-bd60-a241c0d523e9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
checkpoint-status |  |  | checkpoint | 3.09 - Filling operations
label | 0627c5e2-57e4-5e30-b660-397c88a31749 |  | note | Method/Description - Visual inspection
label | bf085430-a72a-54ba-8faf-7282ab15435d |  | note | Test frequency - Daily
label | ae1ede3c-774b-56b1-ba3c-119224f765bb |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.1 - Filling operations
label | 5c74cef0-80d7-5309-90f4-b0d6e75bfa35 |  | note | Method/Description - Survey/visual
label | 71bc3c38-6785-50ba-baf6-b9c94573a5cf |  | note | Test frequency - Daily
label | d624b885-1e9a-5d49-808a-a71b4928a022 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.11 - insitu fill testing
label | 19f81deb-7bdf-5c7d-8561-e178d987aa30 |  | note | Method/Description - Plateau Test
label | 8ac635ae-286d-53c4-ae6e-29080fa08a5d |  | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, Buttress Fill - 1 test per material type per earthworks zone GAP65 - 1 test per material type per structure / location Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | cb903f11-6058-5f65-bdfe-47e6130f6b2b |  | note | Contractor - W
label | e1f1e7e3-5dff-57e8-b890-5b4256dd10fb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.12 - insitu fill testing
label | 08545eff-8973-5173-86fb-8a6078fb113d |  | note | Method/Description - In situ moisture content and density
label | a5a83701-0ca5-50a1-8e22-46a6f123ac33 |  | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length Buttress fill - 1 test per 200m length Average GAP65 - 4 tests per lift per structure Subsoil Drainage Back fill - 1 test per 500m3 , Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | 85d60d18-49b0-5977-9e0d-0d9d1e6e5767 |  | note | Contractor - W
label | 509c23d1-ac26-5227-a4cb-24e7a0822757 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.13 - insitu fill testing
label | 7078c771-36c0-5386-b279-b02ab335ad7e |  | note | Method/Description - Undrained shear Strength
label | 4e6ae58b-a527-5452-ac15-c340b85ceb35 |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | 12b58351-ea85-5116-9d51-40acb2f1dec2 |  | note | Contractor - W
label | 62f427bb-df52-5f0c-9b50-324d9eb5fa07 |  | note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint-status |  |  | checkpoint | 3.14 - Confirm testing requirements are meet for insitu fill
label | 2841e285-4b18-5444-bed5-ac39119ab227 |  | note | Method/Description - Document Review
label | f297e722-dd38-5da1-b526-9444aad1be21 |  | note | Contractor - H
label | bf4cac24-d27a-5609-9a2a-e2dd9b509b73 |  | note | Designer - H
label | 719617e2-d0d8-5d0c-b308-b0ad1a08124c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.15 - Subgrade Fill Testing
label | 786ca940-d793-573a-930f-0ab5e8889f93 |  | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | a683be9f-c197-5116-8148-5e3770fbc00b |  | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
label | 77049b5f-4c04-5fb9-bb0e-09579b9b6992 |  | note | Contractor - W
label | 2791387a-c94f-5c2b-9bcb-e458a2cf35d0 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.16 - Subgrade Fill Testing
label | 8b97f0d9-081d-5467-a11c-eb9dae7282f9 |  | note | Method/Description - Scalar Penetrometer Surcharged Fills
label | 80732b32-aeef-55be-ab37-cf296e39db06 |  | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
label | 464900f3-9006-50eb-98dc-a0a902b6ff48 |  | note | Contractor - W
label | f13a78fd-fb7e-5276-8768-eb78a8d1d1c3 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.17 - Subgrade Fill Testing
label | 071d5b19-4862-5e55-83df-d99905d86057 |  | note | Method/Description - Benkelman beam or FWD Testing
label | 30e11867-faf6-50a4-9319-2207e9f3ad36 |  | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path Fill 12 & 13 - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
label | 50264382-bc18-538b-a9da-fde8558dbde0 |  | note | Contractor - W
label | 1808f137-bb07-51bf-8ce1-ba320fd935b7 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.18 - Subgrade Fill Testing
label | a3d075a4-83d8-5b21-bf47-46648fb6daad |  | note | Method/Description - Laboratory Soaked CBR
label | 87af8b37-2e2f-5718-a4ec-c2a643dd82c9 |  | note | Test frequency - Surcharged Fills, Fill 12 & 13, Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
label | 588fe656-4375-586c-91d9-0cafb5d8fb59 |  | note | Contractor - W
label | 208c8c2c-76ed-5e74-b473-49e35b46d929 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.19 - Confirm testing requirements are meet for subgrade fill
label | 294fe096-51ba-5674-a5dc-ae231c84fc42 |  | note | Method/Description - Document Review
label | 54967401-c342-5c0d-8346-7b86d98efb0a |  | note | Test frequency - Completion of Filling
label | 88bf2fe5-c3bd-5556-973c-488b9b2d8fd1 |  | note | Contractor - H
label | 48251e97-84dd-5077-b9e2-0abf5f2d930e |  | note | Designer - H
label | 60acab08-90fc-5bee-983c-34f0da0fb92c |  | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - where Required, place additional fill for surcharge
label | 4033421d-2de2-5294-81a6-a47746d94b7b |  | note | Method/Description - Surcharge ITP
label | 48f6a582-ee92-5872-af6a-b13048e0b0f3 |  | note | Test frequency - Completion of Filling
label | a21d2d4a-050f-566f-9e08-15e9ec7022d8 |  | note | Contractor - H
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Monitoring Data
label | 9f5b84e1-8bba-5383-b955-454655df0f03 |  | note | Method/Description - Data Recordings
label | 45f9d7f4-60d0-5040-ad84-1f01f42d8f0a |  | note | Test frequency - During construction and at end
label | 5e8abda4-8aca-5cfc-955f-fce75564f273 |  | note | Contractor - H
label | 0cdb52a6-6504-5493-9c64-7a667c62d9f1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
checkpoint-status |  |  | checkpoint | 4.02 - Survey As-builts
label | 0d5cb304-2b6f-570d-8a11-e6cd8b83792d |  | note | Method/Description - Survey As-built
label | ea788fcc-f973-52b5-b43b-2439e69c3520 |  | note | Test frequency - During construction and at end
label | 084b954b-8259-586b-9f7e-f703c0adc6b5 |  | note | Contractor - H
label | e735e578-12a8-59e9-8a80-f7540ed6ed2e |  | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint-status |  |  | checkpoint | 4.03 - As-builts
label | 39a17fd4-38db-5dca-a420-2fd7b5c0a1d8 |  | note | Method/Description - Red Pen Mark up
label | e51510ac-c87b-59f1-a2ad-f514855f53e8 |  | note | Test frequency - End of Construction
label | 2846e468-d9dd-5115-8bc8-88f816f39110 |  | note | Contractor - H
label | ee3c1540-fe9f-5b40-acee-7ffbf4858627 |  | note | Designer - H
label | 47755efe-e59c-51a7-a679-c219d7e6f957 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Fill 12 Rev 2 | itp |  |  |  | Yes | ITP - Fill 12 Rev 2 | fa231c55-fca2-4b05-a1d6-913ca1bfeca1
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - CWP
label | fb664a72-e171-5e36-ab8f-f6dd3f949cc1 |  | note | Method/Description - Document Review
label | 70a83330-58e8-552d-9db8-6e56a9f87f94 |  | note | Test frequency - Prior to personal starting
label | b2748313-849f-5c1d-a688-1bd896297d75 |  | note | Contractor - H
label | d60c4887-6495-512a-afd2-3c4705407f86 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - Design
label | 7cdccebb-a505-5b78-8c70-2d5f8e33a186 |  | note | Method/Description - Document Review
label | f88efe67-5095-54d0-9559-e85400613b4c |  | note | Test frequency - Prior to starting
label | 032f22ea-2f61-5b1a-a7b8-de57a55a0cb8 |  | note | Contractor - H
label | 37114cda-cee2-52db-9234-258f921175c6 |  | note | Designer - H
label | 84355d15-0176-5fba-ad0a-13a6efb89feb |  | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material
label | 4e14b593-e8c5-5f41-b65e-9c1a1b8b0100 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 918ef461-7d0b-5f06-a12e-7fc437daad2d |  | note | Test frequency - 1 test per 20,000m3
label | fe4c6413-b11f-5e42-992d-c6b4016deb38 |  | note | Contractor - H
label | 3afd822d-a24e-52e3-b04d-661e9e006270 |  | note | Designer - R
label | 019bcf3b-5907-5727-b8ca-876deaacd2eb |  | note | Lab - I
label | ceca5d14-9f6f-5202-87a6-8613faa41e7c |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.02 - Atterberg limits test for Structural fill Material
label | 58bc7ded-605f-5ae4-8e79-ac3e1568cd4c |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 34f7af07-687b-5d9d-81f0-e4aa6911831f |  | note | Test frequency - 1 test per 20,000m3
label | b53ce078-1a14-5c00-bd74-3087694449d7 |  | note | Contractor - H
label | 3b2bf412-28d5-5583-b405-ca86a6ac91f1 |  | note | Designer - H
label | 476cf28c-b97f-5e4e-bf91-e3841eba7299 |  | note | Lab - I
label | 5f39c429-9592-5afc-bed4-a1a09ca98814 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
label | 8229c3c3-194f-5458-8656-69e0deca6813 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | d1c50a0e-d542-5d29-92df-fb27fa05e7d2 |  | note | Test frequency - 1 test per 20,000m3
label | 6cdee1e6-6ba4-502e-b0db-152707a2a453 |  | note | Contractor - H
label | fb48c7b3-3a05-5343-ab12-1d03b9ce7a39 |  | note | Designer - R
label | cde610eb-b31c-5424-9437-354c64efa368 |  | note | Lab - I
label | 788032a3-8edf-5798-894c-acf2894dd69c |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
label | ecede97a-bb51-5139-90b7-4aec966801ed |  | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | 83ea8ac5-cbd4-5551-85a2-ef5bc097eaa5 |  | note | Test frequency - 1 test per 20,000m3
label | 3bb2114a-3298-5538-b54e-a5a7dbc717b7 |  | note | Contractor - H
label | 959d599b-6d0b-5bb4-8d5e-bc81be994f6e |  | note | Designer - H
label | 23584793-154a-5099-bc08-bf32dd8a9c3e |  | note | Lab - I
label | 06b25e96-b8c4-519c-be9a-281fea0b69a1 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.05 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | 5c67c79c-eda3-5a80-af91-266a53016298 |  | note | Method/Description - NZS 4402:1986, Test 4.1.2
label | 3d6c8533-a8c9-59b0-8065-ed6c30448435 |  | note | Test frequency - Source approval 3 no. tests
label | 4d0b44ac-5f02-5a7b-8ec4-38f0438c1bcd |  | note | Contractor - H
label | 9f8b930e-e131-58d9-8296-278ed51836d9 |  | note | Designer - R
label | 394945aa-6a62-5263-b960-3c85ec182505 |  | note | Lab - I
label | 63cf6667-fdb1-5df9-aa09-64c03b058d22 |  | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint-status |  |  | checkpoint | 2.06 - Particle size distribution (PSD) Test for GAP 65 material
label | 289936c9-0928-53a9-8157-8a6a6d5be5fc |  | note | Method/Description - NZS 4402:1986, Test 2.8
label | 1b90de68-5d3e-51d7-9e82-96a6afe82106 |  | note | Test frequency - Source approval 3 no. tests then every 2000m3.
label | 32401c7b-2015-5381-b8ad-9c4a78018e8a |  | note | Contractor - H
label | eba1b39a-a2da-58cd-a305-8ac1bdbaa710 |  | note | Designer - H
label | f9f8baf0-13dd-5d7c-8735-6a1ef668bc16 |  | note | Lab - I
label | 3266ecdf-daa0-57ee-bb87-a1062f4eacae |  | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Permeability test for GAP 65 material
label | b47bf4cb-a33e-5f42-8ef9-f866aa45b068 |  | note | Method/Description - ASTM D5084 - 16a
label | 57a8715e-b4f2-56cc-9ee6-337041097a14 |  | note | Test frequency - Source approval 3 no. tests
label | 096f8fc5-5724-5c2a-a820-075005b5e38b |  | note | Contractor - H
label | de432b98-93d3-5771-9f55-4df77b372aa8 |  | note | Designer - H
label | e427fa78-6276-512e-9a42-c2a4e186e3e3 |  | note | Lab - I
label | 48318e62-673f-5308-a0f2-7db6ebc91ceb |  | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.08 - Large Shear Box test for GAP 65 material (Minimum 3 normal stresses)
label | 456169af-8390-51c1-9c4d-fb72b54001b7 |  | note | Method/Description - BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear
label | 2866340d-6b9d-5813-b5c3-9c6c91bc7d78 |  | note | Test frequency - Source approval 3 no. tests
label | 33b93899-828a-5ea3-891e-de9c2bab628d |  | note | Contractor - H
label | 8307e1e3-531c-5d41-bfa9-bddd24713831 |  | note | Designer - H
label | 8d1fd2f3-763f-54f1-9384-932dbe97ca5b |  | note | Lab - I
label | d0b928ce-801d-55f2-a5be-39fd2537bd34 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Direct Shear Strength Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 During Construction
checkpoint-status |  |  | checkpoint | 3.01 - Set out extents of fill and check against design
label | c52def2f-2109-5b5c-ad95-4ea04e9cd97b |  | note | Method/Description - Survey/visual
label | ac031b91-f2a4-5881-b693-4c63e95ab9b6 |  | note | Test frequency - Prior to Commencement
label | 4d47c5f7-a2f8-508e-abf7-93a59ae0c335 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | de7d798d-cb48-5672-a148-0d3cb7eb1e29 |  | note | Method/Description - Survey/visual
label | 6a08abb5-2286-5fa3-a65b-566f57916f22 |  | note | Test frequency - Prior to Commencement
label | 18576264-457f-5a5f-97ef-4fcc327ce8b8 |  | note | Contractor - W
checkpoint-status |  |  | checkpoint | 3.03 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. Except for Fill 12 and 13 where the fill height is >=5m.
label | 9c885834-2a05-552c-ad4a-10775f4aa66f |  | note | Method/Description - Survey/visual
label | 1ceb6a75-efde-52cb-aab8-ec863ba203b1 |  | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13
label | 4dd8fc92-344e-5f72-92a1-ea2932f02d9e |  | note | Contractor - H
label | 79d08386-5ae6-5d2a-87a1-43a4158e7c94 |  | note | Designer - H
label | 17d1c2e6-e9c3-5e33-a7f6-8f49d770a6ac |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
label | ab7f8317-43eb-555d-9d3d-183b9214d086 |  | note | Method/Description - Inspection
label | 3f7d1430-d594-504c-aac6-943df5437658 |  | note | Test frequency - Prior to Filling
label | 51613f83-605d-528e-9a08-5935151d273c |  | note | Contractor - H
label | 065766cc-d893-5902-ae2a-664ea598f82a |  | note | Designer - H
label | d0438fd8-b2a6-5373-83e4-a55ab09c708f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Undercuts
label | 6a247c14-a5c4-5160-a781-6ddbb0a7f70f |  | note | Method/Description - Visual inspection
label | 4265eefb-8165-5c9f-9e1a-9c717668d00f |  | note | Test frequency - 100% of works area
label | 2797ee5c-bba2-5334-9268-d825f5e4da7b |  | note | Contractor - H
label | cf71ba8b-b7c3-514a-99fd-c213c2509fc5 |  | note | Designer - H
label | 9745ef4d-ec00-5cb2-a244-7f1f1ef8f98e |  | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.06 - When required Undercuts (cut-to-fill operations)
label | debe45a7-584d-5ce1-bdb4-557f0c8e813f |  | note | Method/Description - Visual inspection
label | 7f2fcffa-1eb3-5998-8842-b8555461cc30 |  | note | Test frequency - Prior to Filling
label | 1e376a62-1752-5cf0-ad5b-f226ae1548cb |  | note | Contractor - H
label | 75528299-e470-532b-bc26-4b56da0a037c |  | note | Designer - H
label | 6c6ea7d9-c62a-5c00-8c93-8166ab29cfd9 |  | note | Lab - I
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 - Sub soil Drainage
label | 9163e960-06f7-557b-ade5-7365b9f79677 |  | note | Method/Description - Inspection
label | 4069e98c-35fd-55bf-a8dc-cf3314e4c29a |  | note | Test frequency - During subsoil construction
label | 4dde36bf-f539-506a-94a6-f6e2dcbde0bc |  | note | Contractor - I
label | e0263c49-b0ae-55a4-bf49-42c986dbf85f |  | note | Designer - I
label | f625f46b-68d8-5844-ba1a-6dce0b346fc2 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint-status |  |  | checkpoint | 3.08 - Monitoring Equipment
label | f4f5f137-94c9-5c26-89a6-d1bf1ee418ab |  | note | Method/Description - Survey/ data logging
label | 62f2a2ca-798d-5954-bcba-857dc1448c1d |  | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | 0e5bcbc9-f14c-5bec-b825-5cc6b24e042e |  | note | Contractor - W
label | ba8609b5-b6f3-52fb-bc2b-7ca53f0cc70a |  | note | Designer - R
label | bfc9acba-a2ce-588d-a11d-32c1a4a10b6f |  | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
checkpoint-status |  |  | checkpoint | 3.09 - Filling operations
label | ad955907-2159-56a7-8ffd-e5fc9b963359 |  | note | Method/Description - Visual inspection
label | 3063d0e1-0dad-5ccc-9e61-40b4b412bae1 |  | note | Test frequency - Daily
label | 815ba075-215a-55b7-a1ee-12e673279413 |  | note | Contractor - H
label | 06bc61c0-efb8-5497-a238-d391f2538cd9 |  | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet
checkpoint-status |  |  | checkpoint | 3.10 - Filling operations
label | ccb4e9e9-985f-5567-8cf0-7417da9199d0 |  | note | Method/Description - Survey/visual
label | f58a6b83-69c5-5f2e-af40-913f6472c40f |  | note | Test frequency - Daily
label | 98674dd3-9591-57cd-8f92-407b743cb7b0 |  | note | Contractor - H
label | cf0e763c-bc9c-532f-a6fd-bf9bdfa25665 |  | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet/ Survey Report
checkpoint-status |  |  | checkpoint | 3.11 - insitu fill testing-Plateau Test
label | c8325e1d-71f0-54c7-9b55-da598b924065 |  | note | Method/Description - Plateau Test
label | 44ca0705-bfc3-5ce7-8998-9d50c1df2bd8 |  | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
label | 96d040cf-8859-5075-8f0e-01bf68b5104b |  | note | ○ Buttress Fill - 1 test per material type per earthworks zone
label | 91e3c67d-0b5f-5115-82ed-3836ffe881a5 |  | note | ○ GAP65 - 1 test per material type per structure / location
label | 1f0198bd-718f-5132-8231-ec9730b5cab0 |  | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | 756ffbfb-684f-5370-9056-ec58078d83b2 |  | note | Contractor - W
label | 0b2c8187-1723-5aaa-87e5-7cc1338ca595 |  | note | Designer - I
label | 580cdb20-596d-5c03-a60d-786bf6b109c3 |  | note | Lab - I
label | bef97d2e-e20c-566e-a03d-b4ff4d647f52 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.12 - insitu fill testing-In situ moisture content and density
label | 13c0b8c3-eb11-5e71-b617-e58d0c38662c |  | note | Method/Description - In situ moisture content and density
label | d87458c3-88c7-5964-8504-18840501bee4 |  | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
label | 3c8ed8fe-1536-5781-a749-b19c2caa3f85 |  | note | ○ Buttress fill - 1 test per 200m length Average
label | 87b6b8d5-400e-5379-8453-1da5111e6bbf |  | note | ○ GAP65 - 4 tests per lift per structure○
label | bd7b717a-be9b-54b2-b65c-c33acc8e1815 |  | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
label | feaaef30-3805-5931-b1be-8418dd08f651 |  | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label | 271a6dcc-edf0-519f-b566-d119ec88da08 |  | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | 0c1c9d43-6351-5e28-b282-d337e1cf7cd9 |  | note | Contractor - W
label | 5781d64a-7557-50bd-a333-23ad16e2c5c6 |  | note | Designer - R
label | 73ecea43-0c6a-54f4-9c71-3a9ef68da5a2 |  | note | Lab - I
label | cfea635d-453e-5f1b-8948-d0c9b0642071 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.13 - insitu fill testing- Undrained shear Strength
label | c67d69b2-0d36-59d1-a44f-2965981ca06a |  | note | Method/Description - Undrained shear Strength
label | 35e33ec8-b0d4-502b-9b3c-5f693e9d0d0c |  | note | Test frequency - Structural fill - 1 test per layer per 1000m2
label | 8605b40b-f9a5-5de7-9d8a-787e59bbfc77 |  | note | ○ Buttress Fill - 1 Test per layer per 2000m2
label | 142930a3-34b1-5e8b-a82d-2c05debb1a78 |  | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | 204714da-422a-5f73-b5e1-ab5eb713eb52 |  | note | Contractor - W
label | 8c058d99-dbee-56a5-bcdf-33376a9f1d94 |  | note | Designer - R
label | e2c32b3d-c756-5aac-8e96-77eb10bc9e74 |  | note | Lab - I
label | 7c4d522e-83e7-5da0-a0e7-5bafbe3b47bb |  | note | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint-status |  |  | checkpoint | 3.14 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
label | ef3a1542-01ba-574c-bc5d-6fe2da870f41 |  | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | f194cada-3f64-5c37-923f-9ffdfc6d0121 |  | note | Test frequency - Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
label | ce865698-0f30-5f20-acb7-16b2237e1698 |  | note | Contractor - W
label | 44e69cbf-2958-5994-93c8-9daba860050e |  | note | Designer - R
label | 88e54547-4107-57ba-85b7-460d6e8d29ff |  | note | Lab - I
label | 0ba11cab-23e5-5f19-af10-01da722e5a80 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.15 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
label | 9963858c-e44c-541d-845f-e7fe7d723ba4 |  | note | Method/Description - Benkelman beam or FWD Testing
label | df745ad1-d40a-5377-93b6-a56c6ee3617e |  | note | Test frequency - 10m interval in each wheel path at the following levels:
label | 3cc424d3-bc2b-5f6d-8472-76874d61d352 |  | note | 1) 1.0m below Subgrade Formation Level
label | f1691c7a-289b-5d8a-8427-59487e1e72fb |  | note | 2) 0.5m below Subgrade Formation Level
label | 751460d3-f6e5-5fb6-b5ed-d2ab65971b2c |  | note | 3) At Subgrade Formation Level
label | aea5ee05-c9e1-5db9-ae96-2435e30c7d53 |  | note | Contractor - W
label | 23a271da-052f-5930-ae65-ae4819fc7f03 |  | note | Designer - R
label | a4c69df8-622d-5f26-bf5e-f508e6b73255 |  | note | Lab - I
label | c09331bc-9246-505b-8909-d0307c4bf60b |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-status |  |  | checkpoint | 3.16 - Laboratory Soaked CBR testing for Subgrade Fill
label | 308ea3c8-956c-5a07-8845-28536f3c7ff1 |  | note | Method/Description - Laboratory Soaked CBR
label | d1a1d32d-7efa-5432-a906-6b92e6f40d65 |  | note | Test frequency - Test per 5000m2 at subgrade formation level
label | bc63d8ee-326f-55d3-8c6e-182f7a4d288b |  | note | Contractor - W
label | 4f4c3482-f302-5c56-b3bf-4f7eb416a27b |  | note | Designer - R
label | 2a2d4a16-7759-54ab-8439-88ee29bdbc09 |  | note | Lab - I
label | c79ffa2d-f9fe-5179-9408-72979631322d |  | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint-group |  |  | section | 4.0 Post Construction
checkpoint-status |  |  | checkpoint | 4.01 - Monitoring Data
label | 1e78f3e9-37d6-51df-8954-24ef9578207c |  | note | Method/Description - Data Recordings
label | 9b23dc58-c1d3-5020-9f1d-4c0885a3b15c |  | note | Test frequency - During construction and at end
label | 89d77eed-cc7f-5f86-bfba-8c92a63eba04 |  | note | Contractor - H
label | 47f11da2-c16a-5301-a57d-48f62e4d2853 |  | note | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
checkpoint-status |  |  | checkpoint | 4.02 - Survey As-builts
label | cffa44b3-1ced-5a9d-b1b2-02a09d533f3e |  | note | Method/Description - Survey As-built
label | 58eb9d98-438e-5754-8a7b-6da27f2ea094 |  | note | Test frequency - During construction and at end
label | 0e92b21d-6520-585e-a748-0b15cea0394c |  | note | Contractor - H
label | 9eb2cdf3-6e3e-5573-8c9d-aec197727b05 |  | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint-status |  |  | checkpoint | 4.03 - As-builts
label | 700f7a4f-3aea-5967-82cd-4b4d18452424 |  | note | Method/Description - Red Pen Mark up
label | 4b3d0966-9800-58be-9613-1a8ad7a7bbe6 |  | note | Test frequency - End of Construction
label | 1190487e-55ab-5617-b4e2-deccdecdf745 |  | note | Contractor - H
label | 7d929f3e-2cfc-56fd-b23f-966a85871ec2 |  | note | Designer - H
label | acde1e63-8cb9-592d-9aea-47c02d5b8758 |  | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT