## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Cable Support System |  |  |  |  | Yes | Cable Support System | 10af0ecc-c489-430d-bbf4-b6f0c70dbbb6
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
checkpoint-status |  |  | checkpoint | Cable support system has been selected to correctly hold the required weight
checkpoint-status |  |  | checkpoint | Each cable support has sufficient room for future expansion
checkpoint-status |  |  | checkpoint | Cable support system has been correctly installed and is secure in place
checkpoint-status |  |  | checkpoint | Height of cable support system has been confirmed and installed to that height in all areas
checkpoint-status |  |  | checkpoint | Cable support system is as per shop drawings and not impacting any other services
checkpoint-status |  |  | checkpoint | All threaded rods have been cut off to correct size
checkpoint-status |  |  | checkpoint | All nuts/bolts/channel nuts have been tightened
checkpoint-status |  |  | checkpoint | Any changes to drawings have been noted on the site as built drawings
checklist-flat |  |  | checklist | Temp Board Install Checklist |  |  |  |  | Yes | Temp Board Install Checklist | 13dec25a-773d-4c5a-948c-f1115169cae1
checkpoint-status |  |  | checkpoint | Are all final circuits protected by an RCD
checkpoint-status |  |  | checkpoint | Are all DB doors lockable
checkpoint-status |  |  | checkpoint | Are all DB’s securely fixed in position
checkpoint-status |  |  | checkpoint | Are all switchboards labelled correctly
checkpoint-status |  |  | checkpoint | Are all final circuits labelled at board
checkpoint-status |  |  | checkpoint | Are all live parts at DB inaccessible
checkpoint-status |  |  | checkpoint | Are socket outlets in DB in good working order
checkpoint-status |  |  | checkpoint | Are empty glands and holes covered over
checkpoint-status |  |  | checkpoint | Is switchboard door lockable, fitted with a retaining bar, and unable to be removed without the use of a tool
checkpoint-status |  |  | checkpoint | Is emergency lighting provided adjacent to switchboard
checkpoint-status |  |  | checkpoint | CCEW form been completed? (Take photo of each page)
checklist-flat |  |  | checklist | Installation of in-deck/slab conduits |  |  |  |  | Yes | Installation of in-deck/slab conduits | 17014ead-3c6a-4555-bdcf-99edacd9d804
checkpoint-status |  |  | checkpoint | Confirm that the selected conduit is of adequate size for purpose
button | d3124e1f-2b3d-5d9e-877c-9b1ed429842c |  | button | It has been confirmed that all outlets/fittings in slab have been captured | Yes, No, N/A
button | ec86dc7c-cf03-5b85-8175-601e7c57bba1 |  | button | Conduit has been securely fixed | Yes, No, N/A
button | 603b25e1-860a-5df4-b849-8a089fdbfda1 |  | button | Conduit has been securely fixed to the box or volcano | Yes, No, N/A
button | d7bab7e0-f734-59c2-8478-017d0d5815ce |  | button | Conduit box has temporarily been secured and tied down in place for pour | Yes, No, N/A
button | c521875b-fd67-5735-885f-133da36408ce |  | button | Alternative route has been supplied in case main route is damaged | Yes, No, N/A
button | 87fd1751-07a3-5483-9fda-c5a302dff7ab |  | button | Conduit runs have all been marked on as builts | Yes, No, N/A
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Main Switchboard & Termination of Cables ITP002 |  |  |  |  | Yes | Main Switchboard & Termination of Cables ITP002 | 17c0418a-c912-4ec5-8a9c-b447fd5887bc
checkpoint-group |  |  | section | Preparation
checkpoint-status |  |  | checkpoint | Locate & fix switchboard into position - check for clearances fix correctly
checkpoint-status |  |  | checkpoint | Determine cable sizes for cable glands & mark out gland plate (check cable O.D's for cable size glands)
button | 96f51ae8-7474-5341-852a-c8a80c4cf602 |  | button | Install cable glands & cables | Yes, No, N/A
button | 8a5d7cd1-30af-51eb-ba12-2a54a52e9de6 |  | button | Install lugs & terminate | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Clean & vacuum out board - please take a photo
checkpoint-status |  |  | checkpoint | Check all circuits are terminated & safe at the other end or disconnect
checkpoint-status |  |  | checkpoint | Final visual inspection of board - please take a photo
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Test earth continuity & resistance
button | a0f757ee-f49a-56be-88dd-cc6f30d94e9c |  | button | Test insulation resistance | Yes, No, N/A
button | ba171f2b-954b-5982-80b8-7684cdbb3adf |  | button | Test polarity | Yes, No, N/A
button | 31f20699-26b8-545c-9d7d-904988d3e4d5 |  | button | Test phase rotation | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Attach prescribed certificate of electrical safety. Organise inspection by inspector (Add photo or attached certification
checkpoint-status |  |  | checkpoint | Isolate / lock off/ dange tag all outgoing circuits - please take a photo
button | 02434c22-4718-5061-a35d-54c2fa884d7b |  | button | Ensure labelling is complete & accurate | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Energise system
button | 0c3c997a-ed91-5865-a58c-9c27edb51cd9 |  | button | Check phase rotation | Yes, No, N/A
button | c8a9f477-c7ee-5f00-80a4-496d00a79760 |  | button | Check switchboard as installed as per drawings | Yes, No, N/A
text | 946e935f-2c5d-5530-8a03-cdc810cc2e75 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Ensure any modifications to shop drawings are matched to existing & returned to office / attach drawings
checkpoint-status |  |  | checkpoint | Ensure switch room is left clean - please take a photo
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Switchboard Delivery ITP013 |  |  |  |  | Yes | Switchboard Delivery ITP013 | 3145bc00-d8ac-4097-8516-688b4feefc49
checkpoint-status |  |  | checkpoint | Prior to delivery, visual inspection to coordinate delivery on site - please take a photo if delivery is unable to be completed
checkpoint-status |  |  | checkpoint | Review & determine method of unloading (eg. Crane, forklift, man power, specialist subcontractor. Arrange & upload all necessary documentation
checkpoint-status |  |  | checkpoint | Coordinate time of delivery - take photo of delivery docket
checkpoint-status |  |  | checkpoint | Check delivery for damage & correct quantity
checkpoint-status |  |  | checkpoint | Safely position delivery into place (eg. crane, forklift, rollers, manual, specialist subcontractor
label | d7fd7b80-04e6-5e68-a406-4104e7d0d864 |  | note | If Ergo Group are positioning main switchboard maneuvering kit is to be delivered with main switchboard.
label | 37668fa8-cf71-530a-847d-4dc1d377fb48 |  | note | Distributions boards require a lifting trolley
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Mains, Sub Mains Cable in Conduits or on Trays ITP004 |  |  |  |  | Yes | Mains, Sub Mains Cable in Conduits or on Trays ITP004 | 3287c7be-6d85-46f4-b523-07c323e1bf9c
checkpoint-status |  |  | checkpoint | Measure cable runs with appropriate accurate measuring instrument (eg tape measure, wheel)
checkpoint-status |  |  | checkpoint | Check cable sizes resistance of protective earth conductor - shall be low enough to permit passage of current necessary to operate protective device
checkpoint-status |  |  | checkpoint | Confirm length of cable if sub contract item & order
text | 9c04ca77-34ec-5b5f-88cd-caa4e5e73ba9 |  | textbox | Record length of cable
checkpoint-status |  |  | checkpoint | Install cable in appliance method (EG. Cable stands, electric winch, pulleys etc.) - ANY CABLE NOT TERMINATED IMMEDIATELY MUST HAVE THE ENDS TAPED COVERING THE BARE COPPER - please take a photo
checkpoint-status |  |  | checkpoint | Trefoil cables & tie cables to support system (ensure spacing)
button | df51ff38-800d-5fe9-b8fe-b1516336b0d9 |  | button | Check requirements for cable identification & install | Yes, No, N/A
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Test and Tag Register |  |  |  |  | Yes | Test and Tag Register | 3907c67d-7b53-421d-bf0a-a4efaa38670d
checkpoint-status |  |  | checkpoint | Test and Tag register completed (upload picture of each page)
checklist-flat |  |  | checklist | Pre-start Toolbox Talks |  |  |  |  | Yes | Pre-start Toolbox Talks | 4635958f-cefe-484e-bae8-3a7e1b398b0f
checkpoint-status |  |  | checkpoint | Pre-start Toolbox Safety meeting completed
text | ff49b524-6995-5b8d-bfa4-8e5f02aa2646 |  | textbox | Location:
text | ef24ace5-415d-558a-85d0-ddf1c4c9d2df |  | textbox | Date:
text | 160e78cc-a807-5252-8a72-e25ffbf9a962 |  | textbox | Client:
text | cf597fa1-960f-5766-9ff1-45eeca8793d5 |  | textbox | Supervisor:
text | c52ce046-cc8b-59e0-8a3f-a683cb7938c8 |  | textbox | Subject:
text | d76890e5-9d6d-5eb0-a7f4-49319f793054 |  | textbox | Duration:
text | a367da39-7292-5d1f-8b52-573854767608 |  | textbox | Persons present
text | fb30855c-70b9-5f8b-b1dd-26e88c4f0b8c |  | textbox | Comments & points raised
checkpoint-status |  |  | checkpoint | Signed off by Ergo Group Supervisor
checklist-sectioned |  |  | checklist | Electrical Installation Testing |  |  |  |  | Yes | Electrical Installation Testing | 52939610-50f1-4c05-bd52-e244bb367d79
checkpoint-group |  |  | section | Test Point/ Circuit Number
checkpoint-status |  |  | checkpoint | Main earth tested
text | 9d6c9fee-7fa3-5a60-b4ee-7a147a672a1e |  | textbox | Conductor Sizes (mm²) Actives/Earths
text | b2104591-3d44-534b-a811-a8bf4e85fbb8 |  | textbox | MCB (Rating & Type)
checkpoint-group |  |  | section | Continuity
checkpoint-status |  |  | checkpoint | Continuity tested
text | 52257cca-a18d-5dc8-b27d-df487aaa126b |  | textbox | Active Conductor (Rph)
text | dc41095d-088a-5c2b-80fb-bef183acef45 |  | textbox | Earth Conductor (Re)
checkpoint-group |  |  | section | IR
checkpoint-status |  |  | checkpoint | IR tested
text | ad330d9a-c85e-5de2-88c0-af879dfc4a8c |  | textbox | Insulation Resistance (MΩ)
checkpoint-group |  |  | section | CCC
checkpoint-status |  |  | checkpoint | Correct Circuit Connections
checkpoint-group |  |  | section | Polarity
checkpoint-status |  |  | checkpoint | Polarity tested
checkpoint-group |  |  | section | Fault Loop Impedance
checkpoint-status |  |  | checkpoint | Measured Loop Value R
checkpoint-status |  |  | checkpoint | Maximum Permitted Loop Value
checkpoint-group |  |  | section | RCD
checkpoint-status |  |  | checkpoint | RCD tested
checklist-flat |  |  | checklist | Installation of steel tray/basket |  |  |  |  | Yes | Installation of steel tray/basket | 56d02774-ac3c-4fe6-9ce9-9be5a71c85fc
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been selected as per drawings and specifications
button | 21596123-18f9-5483-873b-79276c3efec5 |  | button | Cable support system has been selected to correctly hold the required weight | Yes, No, N/A
button | bc19b897-025d-5141-bb2e-d235a1e494bc |  | button | Each cable support has sufficient room for future expansion | Yes, No, N/A
button | cd0078fe-510e-523f-b719-ffbcc655462e |  | button | Cable support system has been correctly installed and is secure in place | Yes, No, N/A
button | 3b60378d-7236-5204-aee5-ea17f62bba32 |  | button | Height of cable support system has been confirmed and installed to that height in all areas | Yes, No, N/A
button | cc665325-8043-585c-877f-72ca7963d8d4 |  | button | Cable support system is as per shop drawings and not impacting any other services | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All threaded rods have been cut off to correct size
checkpoint-status |  |  | checkpoint | All nuts/bolts/channel nuts have been tightened
checkpoint-status |  |  | checkpoint | Any changes to drawings have been noted on the site as built drawings
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Lighting cabling and outlets |  |  |  |  | Yes | Lighting cabling and outlets | 5f2d3d1f-a671-4887-b8fa-f057bcbf77d2
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All lights have been wired as per drawings
checkpoint-status |  |  | checkpoint | All lights and switches have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each switch
checkpoint-status |  |  | checkpoint | Lighting control system has been confirmed (DALI/240v)
checkpoint-status |  |  | checkpoint | Ceiling supports have been installed where required (ceiling fans/pendants)
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Switches have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All lights are sitting flush and/or been levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each switch has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each switch and light
checkpoint-status |  |  | checkpoint | Each circuit has been marked on the site as built
checklist-flat |  |  | checklist | Install Distribution Boards -Terminate Cables ITP006 |  |  |  |  | Yes | Install Distribution Boards -Terminate Cables ITP006 | 62c2403d-0c97-4d10-9e30-a887b784b5e4
checkpoint-status |  |  | checkpoint | Check delivery of distribution board - Check for damage (paint finish, dimensions & door against drawing) - Please take a photo
checkpoint-status |  |  | checkpoint | Locate & fix into position
checkpoint-status |  |  | checkpoint | Install sub mains cabling as appropriate (glands, tray & duct)
checkpoint-status |  |  | checkpoint | Install lugs & terminate
checkpoint-status |  |  | checkpoint | Install sub circuit & terminate (if circuit not complete at the other end, it must not be terminated)
checkpoint-status |  |  | checkpoint | Clean & vacuum area - please take a photo
text | e8315d51-889c-58b1-930b-f8175df29b78 |  | textbox | Record results
checkpoint-status |  |  | checkpoint | Clearly identify services
checkpoint-status |  |  | checkpoint | Energise system
button | ef96d1e0-d6ca-514f-a052-7e884dd10f35 |  | button | Check phase rotation | Yes, No, N/A
button | c3a0d74c-50d4-51f8-a88c-2e1e01d138e6 |  | button | Check switchboard as installed as per drawings | Yes, No, N/A
text | 454c9f2f-959a-565e-bb1c-8288fe9c0d2e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Check typed schedule for accuracy & install
checkpoint-status |  |  | checkpoint | Ensure switchboard cupboard & area is left clean - Please take a photo
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Installation of lighting cabling and fit off |  |  |  |  | Yes | Installation of lighting cabling and fit off | 6c13ef15-6aae-4622-adad-6b099d6abf10
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized & selected to ensure that they will support currently installed & future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All lights have been wired as per drawings
button | 19a008a9-a479-567e-878e-05c08e440d87 |  | button | All lights & switches have been marked on the site as built drawings | Yes, No, N/A
button | 10fa333d-45cd-5903-a887-b3ecc2c3aca5 |  | button | Height & location have been confirmed for each switch | Yes, No, N/A
button | 663c63fd-210d-58a2-88ce-719eb9d32dd2 |  | button | Lighting control system has been confirmed (DALI /2 40v) | Yes, No, N/A
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Ceiling supports have been installed where required (ceiling fans / pendants
checkpoint-status |  |  | checkpoint | Terminations have been checked & all terminations are correct & secure in all outlets
checkpoint-status |  |  | checkpoint | Switches have all been secured in place & levelled
checkpoint-status |  |  | checkpoint | All lights are sitting flush & / or been levelled
checkpoint-status |  |  | checkpoint | All cablings has been tested for insulations resistance & continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB & protected by the correct protection device
checkpoint-status |  |  | checkpoint | Each switch has been labelled
button | 483d899d-4a60-5690-8706-e44bf0e29903 |  | button | Functional test carried out on each switch & light | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Each circuit has been marked on the site as build's
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Site Variations |  |  |  |  | Yes | Site Variations | 79439ae1-7925-45ac-a800-2363d405908a
checkpoint-group |  |  | section | Contract Variation/Site Instruction Request
checkpoint-status |  |  | checkpoint | Contract Variation/SI Request
text | ecf8f05e-c5b5-5af4-9ecb-d8f1d49cb3bd |  | textbox | Company:
text | b2b1de8c-d9e2-5e02-b680-f0077a2354c1 |  | textbox | Address:
text | c9492efc-22c2-5f8b-85ac-1ab2ffb25916 |  | textbox | Project Name:
text | eb41256b-3ed9-59c3-ac76-02eb5f00d905 |  | textbox | Representative:
text | 95ca27fc-d07a-5656-ae0a-b76d2527a0c1 |  | textbox | Variation date:
checkpoint-group |  |  | section | Scope of Works
checkpoint-no-status |  |  | checkpoint | Scope of Works:
text | a75068a4-feb5-52b9-a08b-c74c89b5b670 |  | textbox
checkpoint-no-status |  |  | checkpoint | DATE (1)
text | 49333b66-ab7d-51d2-b37a-6125b9bb03a6 |  | textbox
text | 7a167e21-2eca-5154-9577-dbf9378b9732 |  | textbox | LABOUR
text | 9126fb06-56eb-5310-b5b2-f99426037ea8 |  | textbox | HRS
text | 546b3d24-e7ae-5f76-8489-dfd33dcf9362 |  | textbox | MATERIALS
text | f4bf1c68-8a26-567b-964b-f5738092bd3b |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (2)
text | da00de81-b275-5622-aa32-94dbfc5c5947 |  | textbox
text | 08de56e6-7c91-5d8a-af05-36a6bc8d8bf3 |  | textbox | LABOUR
text | 6a5d302b-6328-595d-a2ce-17fb77b339fa |  | textbox | HRS
text | 24e779c1-a155-53fd-b34a-1746a9d590b7 |  | textbox | MATERIALS
text | f151df19-364c-5b01-b152-9032adc10980 |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (3)
text | f8521350-3f48-54d2-9449-03c93755bfa9 |  | textbox
text | f53ebcb0-0bed-53ee-a66a-67bc0d27042a |  | textbox | LABOUR
text | b9fa1578-b6e4-5f57-af73-c3278e1663c5 |  | textbox | HRS
text | d95787fa-d8e8-5a86-bffb-841091e72621 |  | textbox | MATERIALS
text | 9b6d8df1-717c-54d2-92ea-0f803fe126f7 |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (4)
text | 0db5a785-d34c-572f-a190-5671f1f735c3 |  | textbox
text | ecc5b394-3a91-5c28-93cb-44c5972f5ac2 |  | textbox | LABOUR
text | 947f1e8b-4b81-5a6c-81d2-ad7cc0d31975 |  | textbox | HRS
text | b94d599b-e580-57f7-8d81-f3b03565075b |  | textbox | MATERIALS
text | 645b19f2-da0d-55dc-8982-789eed24a7ee |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (5)
text | 816181e8-b5eb-532f-9dce-63adb6d96e85 |  | textbox
text | f9bbd5ec-413c-5752-9f4f-8913ec93b66b |  | textbox | LABOUR
text | 104c05bb-3252-5c01-a483-71b3e929a57f |  | textbox | HRS
text | c19269fc-ffc4-5704-bf25-597dd93c77e3 |  | textbox | MATERIALS
text | 717d66db-7736-5905-ade9-d0cb47bb2198 |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (6)
text | 2a964e1b-574b-5e21-ab7d-442bb2366d32 |  | textbox
text | dd6f33cd-d599-583c-8c94-90acb6d1b7b5 |  | textbox | LABOUR
text | 294ab235-963c-5244-9d95-1a8ecb8f4912 |  | textbox | HRS
text | 0692d18d-9154-5917-9375-4f90230a23d8 |  | textbox | MATERIALS
text | 55b0882f-82bf-53ad-bec1-59d46766397a |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (7)
text | 9d43961a-204f-5d4e-8981-469705956567 |  | textbox
text | 8dd24b1f-d741-56f6-8c7b-80f73d618181 |  | textbox | LABOUR
text | 43e34995-8e5e-5122-a567-ba5d075f3e2e |  | textbox | HRS
text | 4e5c4516-c107-50ce-88c1-abcb6ade2a46 |  | textbox | MATERIALS
text | 92f6a681-06c2-55ed-b27d-e5ce31b7ad2d |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (8)
text | b9d00bae-685e-5092-98a7-b134a8229c8e |  | textbox
text | 30b594e8-b495-5fea-90c7-98cc0c96ddee |  | textbox | LABOUR
text | 211a6e97-3816-5a43-973d-f8d3030e02f1 |  | textbox | HRS
text | ac9d7b59-d371-51b9-beb2-f529688d0006 |  | textbox | MATERIALS
text | 3b6236d6-e303-5838-b72c-6c4d1f6b6f9c |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (9)
text | 4677e410-6ed2-5d91-8811-06c598b5e1a0 |  | textbox
text | c0ccf001-aed9-50a2-96ba-abe1e848908d |  | textbox | LABOUR
text | e8660633-5619-59d7-9898-c3cce51987ee |  | textbox | HRS
text | c4cdde0a-e0fe-5ff4-bdc6-3c085ec448dc |  | textbox | MATERIALS
text | aa00fc54-558a-568b-988e-a599707b8461 |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (10)
text | 9eca556c-db25-55b2-9139-accaaf45de26 |  | textbox
text | bcb5c246-bc33-584b-8265-8bc35ef541e9 |  | textbox | LABOUR
text | 13310c12-65ed-5c10-b6b8-6b88acc2cfc7 |  | textbox | HRS
text | 34a6f7dc-d662-564f-83f2-4f288384a031 |  | textbox | MATERIALS
text | 5e75926a-09d6-5a9a-99a9-ac2b4a1eae76 |  | textbox | QTY
checkpoint-no-status |  |  | checkpoint | DATE (11)
text | 42c6f1e3-5667-5571-accc-101e0aed3ec5 |  | textbox
text | 7df04fa9-1506-5cb7-9d66-ac3d4161fe96 |  | textbox | LABOUR
text | 01234db3-3a80-5ecb-81d9-a0ca3052641f |  | textbox | HRS
text | dfb121cb-a87f-5541-967d-a1d5e6f377de |  | textbox | MATERIALS
text | ffb08200-77ce-5f8a-a60e-f3c332be919d |  | textbox | QTY
checkpoint-group |  |  | section | The above Variation is accepted by:
checkpoint-status |  |  | checkpoint | Client Representative
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Ergo Representative
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Emergency Lighting Testing Evidence |  |  |  |  | Yes | Emergency Lighting Testing Evidence Checklist | 7cd6303c-1e54-4c87-83dd-30b8c65f60a3
checkpoint-status |  |  | checkpoint | Pass once image is uploaded
checklist-sectioned |  |  | checklist | Underground Conduits ITP001 |  |  |  |  | Yes | Underground Conduits ITP001 | 7fbd65ce-0f78-4611-bb98-101fd1973854
checkpoint-group |  |  | section | Preparation
checkpoint-status |  |  | checkpoint | Check clear of other services (The Clearance for gas pipes is 300mm & other services 100mm)
checkpoint-status |  |  | checkpoint | Check cable size to verify conduit size & determine size of trench
checkpoint-status |  |  | checkpoint | Organise barricades, webbing, plates, warning lights (if applicable prior to excavation) - please take a photo
checkpoint-status |  |  | checkpoint | Determine spoil removal, backfill material, compaction, cable marking protection & installment requirements
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 35ece88e-c9a2-53c7-b09f-cbb5d4adcda6 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Mark out trench route - Arrange saw cutting if required
checkpoint-status |  |  | checkpoint | Excavate trench & install barricades as required - please take a photo
checkpoint-status |  |  | checkpoint | Determine which way cable will be installed & lay coupling in no friction direction, install conduit glue.
button | 03eca2fc-4555-59c3-b4c9-18dafdbd770f |  | button | Install draw wire if required | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Inspect trench by supply authority if applicable
button | 6b355d99-5b9e-56c5-88aa-1c597a16e2cf |  | button | Inspect & backfill trench | Yes, No, N/A
button | 48d97f2f-c301-56de-92a9-edea097e55ab |  | button | Reinstate & clean area | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Install direction marker if applicable
checkpoint-status |  |  | checkpoint | Mark up DGR for future as builts
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Contractor |  |  |  |  | Yes | Contractor | 861913ac-5c50-42ad-b027-14d0dea847b7
checkpoint-status |  |  | checkpoint | Has contractors ITP been received - Please take a photo / up load checklist
checklist-flat |  |  | checklist | ITP019 Communications Cabinet |  |  |  |  | Yes | ITP019 Communications Cabinet | 9423baba-b12c-4b83-b7a7-729312a33052
checkpoint-status |  |  | checkpoint | 1 - Ensure room layout, cabinets and equipment have been approved
checkpoint-status |  |  | checkpoint | 2 - Confirm that cable support system has been completed as documented
checkpoint-status |  |  | checkpoint | 3 - Adhere to a single certified system throughout a new building installation
checkpoint-status |  |  | checkpoint | 4 - Comply with the detailed installation specifications
checkpoint-status |  |  | checkpoint | 5 - Network cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | 6 - Connections have been correctly terminated and insulated to ensure perfect connectivity and protect against faults and interference
checkpoint-status |  |  | checkpoint | 7 - Sufficient spare cable has been left coiled up outside of the cabinet
checkpoint-status |  |  | checkpoint | 8 - Check all internal wiring as per panel wiring diagram. Has all equipment including cable managers been installed as per rack layout
checkpoint-status |  |  | checkpoint | 9 - Has a dedicated power circuit been supplied for the cabinet
checkpoint-status |  |  | checkpoint | 10 - Is there a steel tray/raceway installed between each cabinet to accommodate linking patch leads
checkpoint-status |  |  | checkpoint | 11 - All cabling has been tested using the Fluke data tester
checkpoint-status |  |  | checkpoint | 12 - Undergo certification tests prior to acceptance of work completed
checkpoint-status |  |  | checkpoint | 13 - Provide copies of certification tests to the Office of IT Services
checklist-sectioned |  |  | checklist | Power cabling and outlets |  |  |  |  | Yes | Power cabling and outlets | a7eaebea-17df-43df-9f94-ef515f9b4af6
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All outlets have been marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each outlet
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-flat |  |  | checklist | Toolbox Safety Talks Meeting Minutes |  |  |  |  | Yes | Toolbox Safety Talks Meeting Minutes | b26edbe3-b953-476f-bd63-ac14fd528651
checkpoint-status |  |  | checkpoint | Toolbox Safety meeting completed
text | 2a89c104-f7e9-5149-b1b3-f0b716afab44 |  | textbox | Location:
text | 418dc8ac-d145-5638-871a-fc7587bb5e0e |  | textbox | Date:
text | 358f1937-df0b-587e-8f48-8070e79972a9 |  | textbox | Client:
text | 8b0f244c-659e-5be6-8e40-18518758e711 |  | textbox | Supervisor:
text | 9c7f2b34-9642-5c10-86f0-fc6cc8aa28cc |  | textbox | Subject:
text | 9fae3c6d-f41a-57a3-bc49-cd8c33425315 |  | textbox | Duration:
text | d87e0f1f-3abf-5db1-ab36-aaab268d4663 |  | textbox | Persons present
text | 22d0c969-9512-5e57-8214-1e6d63a88dd7 |  | textbox | Comments & points raised
checkpoint-status |  |  | checkpoint | Signed off by Ergo Group Supervisor
checklist-sectioned |  |  | checklist | 8B. Investigation - Witness Statement |  |  |  |  | Yes | 8B. Investigation - Witness Statement | ba0e9554-7cc7-411b-ba46-e9b758feb57c
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | b179979e-03cf-56b3-b1d6-157050c55629 |  | textbox | Name:
text | cdea9793-5375-5858-be38-a5d21871681e |  | textbox | Job Title:
text | 0294e5d8-7edb-593c-8393-a700b1f4a426 |  | textbox | Employer:
text | 67244d15-6ac4-5d08-8032-f171b1762067 |  | textbox | Supervisor:
text | 22e98108-8cce-5a59-bac1-96f566658412 |  | textbox | Work Location:
text | bfa31aa4-32cf-5043-bc02-7f75711f54a2 |  | textbox | Contact Details:
text | 38e35423-420f-54ad-87de-0ea32686a366 |  | textbox | Location of Incident:
text | b22d23e5-25cc-5e91-9309-f9262ebc43d4 |  | textbox | Date/Time of Incident:
text | 843992a7-c7b5-5aab-b846-8e07b50acc1c |  | textbox | Interview Time/Date:
text | bdda74e5-0284-5dff-b54c-15ea008cb967 |  | textbox | Interview Number:
text | 755084f1-a159-5714-a855-5eb11bd2f7dd |  | textbox | Please fully describe the work and conditions in progress leading up to the incident.
text | 10983555-6c03-5ed4-acbb-c1dc8d2d831a |  | textbox | Please fully describe the incident sequence from start to finish.
text | 56c8f2f9-79dc-54d9-88ad-8e02ea3604e7 |  | textbox | Note anything unusual observed prior to, or during the incident (sights, sounds, smells etc.)
text | d6211f41-3bac-5d0b-ba61-f8fae4ff6c55 |  | textbox | What was your role in the incident sequence?
text | 733f4a8a-29e6-5c06-95a2-dba212421c04 |  | textbox | What conditions influenced the incident (weather, time of day, equipment malfunctions etc.)?
text | 85afce3e-d1df-5f4f-912a-8086cb738bf5 |  | textbox | How did people influence the incident (actions, emergency response etc.)?
text | 88a3b9a9-1795-5ef0-b2f0-51c97c5dc32f |  | textbox | What do you think caused the incident?
text | 1c4286a6-74af-5cd5-86c3-eb389f7d47b6 |  | textbox | How do you think the incident could have been prevented?
text | 592f86ac-1281-5e8c-ae07-10f9db6bacac |  | textbox | Please list other possible witnesses.
text | 0e8f9f3e-48a9-5c08-aeaa-3b28aaf83786 |  | textbox | Additional comments/observations.
checkpoint-status |  |  | checkpoint | Interviewee Details:
text | 1467ccf4-fb4c-5248-b708-7acc2bd6add9 |  | textbox | Interviewee:
holdpoint |  |  | signoff | Signature:
checkpoint-status |  |  | checkpoint | Interviewer Details:
text | 40527e59-00c3-583d-ac95-4e16305c2e05 |  | textbox | Interviewer:
holdpoint |  |  | signoff | Signature:
checklist-sectioned |  |  | checklist | Installation of power cabling |  |  |  |  | Yes | Installation of power cabling | be3e8e13-41f5-42e9-b389-df4957c55df2
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Electrical cables have been appropriately sized and selected to ensure that they will support currently installed and future equipment
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
button | 862c62d5-b7fa-56c8-92c5-acfe4340b244 |  | button | All outlets have been marked on the site as built drawing | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
button | f3e592df-ad58-594e-ae60-31728f70e5f5 |  | button | Outlets have all been secured in place and levelled | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All cabling has been tested for insulations resistance and continuity
checkpoint-status |  |  | checkpoint | Each circuit is terminated at the DB and protected by the correct protective device
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Functional test carried out on each outlet
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as build’s
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Temporary DB Monthly Testing |  |  |  |  | Yes | Temporary DB Monthly Testing | cee8fb5a-fdd0-4a1b-8c1f-e8b50284ec89
checkpoint-status |  |  | checkpoint | Operating time of RCD’s (note trip times in comments)
checkpoint-status |  |  | checkpoint | RCD Push button Operation
checkpoint-status |  |  | checkpoint | General condition of DB (must include a photo)
checkpoint-status |  |  | checkpoint | Photo of completed tag on DB
checklist-sectioned |  |  | checklist | 8A. Incident / Accident Register |  |  |  |  | Yes | 8A. Incident / Accident Register | cf848d84-9d89-450f-840e-70671d387b58
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | dabf244f-1b28-5a2d-9e4b-399d5d2be427 |  | textbox | Client:
text | 1ddc5457-b7ca-590e-acf4-a97e2848b2d1 |  | textbox | Project:
date | 4c6f1340-071a-5054-9031-8405b4214487 |  | date | Date:
text | 6024c298-9583-51e0-b241-48a05f20e444 |  | textbox | Site Address:
date | 9577b72f-9e63-51f7-86e8-e185dad9cd50 |  | date | Date of Incident:
text | e563789f-e4ad-5dd5-ad9f-36aed14bf047 |  | textbox | Time of Incident:
text | 7212644a-7f39-56db-92b1-4606cd5b4632 |  | textbox | Incident Report No:
text | ba226d84-938b-5a11-8f77-ae1322015003 |  | textbox | Workers Name:
text | 3662b5d0-4767-5fb7-a6dc-c90517e1311f |  | textbox | Supervisor Name:
text | ce54a187-8610-5b5a-8904-5d96ff50cefc |  | textbox | Location:
select | caf4c90c-8909-5b5e-a0d6-12c89c137e06 |  | dropdown | Outcome - 1st Aid: (FAT), Medical: (MTI), Lost Time: (LTI), Near Miss: (NM), Report Only: (REP) | 1st Aid: (FAT), Medical: (MTI), Lost Time: (LTI), Near Miss: (NM), Report Only: (REP)
select | cc33c01d-0cb5-5792-82f2-53a2e61a7d06 |  | dropdown | Outcome - Return to Work: (RTW), Doctor: (Doc), Hospital: (Hosp), Snt Home: (SH), Report Only: (Rep) | Return to Work: (RTW), Doctor: (Doc), Hospital: (Hosp), Snt Home: (SH), Report Only: (Rep)
text | 0f64f120-9dbb-5faa-85ad-2aabd4d88c4d |  | textbox | Days Lost (If LTI):
checklist-sectioned |  |  | checklist | Data cabling and outlets |  |  |  |  | Yes | Data cabling and outlets | dff3f9a3-b25d-4faf-ab69-f0711ce10c5c
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Data cabling has been selected as per drawings and specifications (Cat6/CatA & brand)
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
checkpoint-status |  |  | checkpoint | All data outlets have been numbered and marked on the site as built drawing
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested using the Fluke data tester
checkpoint-status |  |  | checkpoint | Each cable has been correctly installed and terminated in the patch panel
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as built
checklist-flat |  |  | checklist | ITP003 Conduit & Cable Tray form |  |  |  |  | Yes | ITP003 Conduit & Cable Tray form | e43e5b4f-8852-4020-bc6e-a9715f0dde9e
checkpoint-status |  |  | checkpoint | Check delivery for damage & correct quantity
checkpoint-status |  |  | checkpoint | Ensure locations of lights is coordinated with other trades
checkpoint-status |  |  | checkpoint | Refer to reflected ceiling plan for set out
checkpoint-status |  |  | checkpoint | Plug in or fit off light
checkpoint-status |  |  | checkpoint | Fit off data capable (if applicable)
checkpoint-status |  |  | checkpoint | Install light fighting
button | e30298a8-47ec-5c38-a046-53033a9aeadc |  | button | Install lamp & diffuser & clean fitting | Yes, No, N/A
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Temporary DB checklist |  |  |  |  | Yes | Temporary DB checklist | e5d123c7-217f-4eb0-aa94-d57834f123d5
checkpoint-status |  |  | checkpoint | RCD
text | ad973e0c-c9f1-54d1-9eb9-d7b3aa882f00 |  | textbox | Date of testing
text | c226dc07-fdb2-590a-a47f-316f6c698dc1 |  | textbox | Next test due
checkpoint-status |  |  | checkpoint | Results and/or trip current (less 30mA) for Earth Leakage Device
checkpoint-status |  |  | checkpoint | Has a new tag been installed on the DB - please take a photo
checkpoint-status |  |  | checkpoint | Has the front cover been updated
label | 3cc688c7-5890-5708-834a-bafe06239fd8 |  | note | Please take a photo of DB
text | f8a1c469-5baf-51a7-97b3-7b7a45df6376 |  | textbox | License No.
checklist-sectioned |  |  | checklist | Installation of data cabling and outlets |  |  |  |  | Yes | Installation of data cabling and outlets | fb29fb49-7223-4495-8f22-f76887b5b6c3
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Confirm that the cable support system has been completed as per documentation
checkpoint-status |  |  | checkpoint | Data cabling has been selected as per drawings and specifications (Cat6/CatA & brand)
checkpoint-status |  |  | checkpoint | Mechanical protection has been provided to minimise the likelihood of physical damage to cabling
checkpoint-status |  |  | checkpoint | Cabling has been concealed where possible in ceiling spaces, wall cavities or risers
checkpoint-status |  |  | checkpoint | All outlets have been wired as per drawings
button | 71eebfb2-f11e-588c-b9a8-8312d881ad2c |  | button | All data outlets have been numbered and marked on the site as built drawing | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Height and location have been confirmed for each outlet
checkpoint-group |  |  | section | Fit Off & Commission
checkpoint-status |  |  | checkpoint | Equipment/materials have been selected and installed as per drawings/specifications
checkpoint-status |  |  | checkpoint | Terminations have been checked and all terminations are correct and secure in all outlets
checkpoint-status |  |  | checkpoint | Outlets have all been secured in place and levelled
checkpoint-status |  |  | checkpoint | All cabling has been tested using the Fluke data tester
checkpoint-status |  |  | checkpoint | Each cable has been correctly installed and terminated in the patch panel
checkpoint-status |  |  | checkpoint | Each outlet has been labelled
checkpoint-status |  |  | checkpoint | Each outlet marked on the site as build’s
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)