## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-154-STR-SSB-Precast Super T Installaton
ITP Description: |  | SSB-Precast Super T Installaton
Discipline (e.g. CIV/STR/RAIL: |  | 154-STR
Revision Number: |  | 0
Revision Date: |  | 2024-05-01
ITP created by: |  | Dan O'Brien
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Station St Beaconsfield
Inspection & Test Plan - Precast Bridge Beams (Supply & Installation)
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-05-01
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR 652 June 2010 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR 656 June 2010 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VR 610 February 2020 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VR 620 May 2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Epoxy bedding | IFC Drawings | Product to be selected based on the following criteria: i. Have a minimum compressive strength equal to or greater than substrate Ii. Can be applied in IFC specified nominal thickness (1mm) Enter: Teambinder Material Approval number [free text box] | Document Review | When applicable | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Bolts | IFC Drawings | M16 grade 4.6/S countersunk socket cap screw Enter: Teambinder Material Approval number [free text box] | Document Review | When applicable | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Precast Elements | IFC Drawings 610.47 (a) Table 610.473 (March/June 2019) 620.03 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Pre-stressing check sheet / ITP vi. Post-pour check sheet / ITP vii. Covermeter check record viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder Enter: Teambinder MDR Lot number [free text box] | Document Review | Each element | HP* | PE/SE/SPE | This ITP
3.2 | Elastomeric Bearings-crosshead and restraining blocks | IFC Drawings 652.02 652.03 652.04 AS5100.4 | Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4. Tolerances: Dimensions in plan = +4mm, -2mm Thickness = ≤100mm = ±2mm >100mm ≤ 150mm = ±3mm > 150mm = ±4mm Testing: Each bearing tested under compression Batch tested for shear stiffness Attach: Elastomeric Bearing Test Reports Attach: Elastomeric Dimensional Records | Document Review | Each element | HP | PE/SE/SPE | This ITP
3.3 | Tapper plates / Keeper Plates | VR 620.05 | Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm. Enter: Teambinder MDR Lot number [free text box] | Document Review | Each Plate | IP | SE/PE | This ITP
4 | Pre-construction Activities
4.1 | Bearing Plates-Check | IFC Drawing | Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and bearing orientation are correct | Visual | Each Tapper plate | IP | SE/PE | This ITP
4.2 | Crosshead / Pedestal Tolerances | Survey As-builts / Survey Report | Re-check that the As-built dimensional tolerances comply with the requirements below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm | Document Review | Each element | IP | PE/SE/SPE | This ITP
4.3 | Precast Beam Inspection | IFC Shop Drawings IFC Drawings | Check that material inspection checklist has been completed for each beam. Engineer to check that each beam has been loaded with each end at the specified position (truck or jinker end) | Document Review | Each element | IP | SE/PE | This ITP
5 | Construction Activities
5.1 | Elastomeric Bearing Placement | IFC Drawings VR 656.05 | Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances. Tolerances: Plan position: ±2mm in any direction Level: ±2mm Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report | Measure Visual | Where applicable, each bearing location | IP | Surveyor SE/PE/SPE | This ITP
5.2 | Restraining Blocks-Bearings | IFC Drawing | 230x150x35mm elastomeric bearings are to be installed in designated recesses on restraining blocks. Base plate 260x170x10mm cast flush into lateral restraint block with 2 x 10mm diameter, 75mm long dowels (grade 250R) cast into restraint block (4mm CFW all around to base plate) | Visual | Each restraining block | IP | SE/PE | This ITP
5.3 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | SE/PE/SPE | This ITP
5.4 | Precast Placement | IFC Drawings 610.27 Temporary Works Design Drawings (IFC) | Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The nominal gap between elements is as per the IFC Drawings. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.5 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | Visual | Each element | IP | SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | As-built Survey | IFC Drawings 610.47 (a) Table 610.472 (March/June 2019) | Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /