## Export
Lot Number | Lot | Status | Opened date | Area | Activity type | Inspection Test Plan | Responsible Engineer | Work commenced date | WBS Code | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
CC0375-BOP-FRP-005 | Fuel Diesel Tank (South) | Submitted To Client | 2023-02-13 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-02-13 | 03-02-01 | 2023-05-30 | Yes | Yes | Not Required | [5 empty] | 2023-08-25 |  | 87 | Overdue | 341 | Overdue | No | No | No
CC0375-BOP-FRP-006 | Fuel Diesel Tank (North) | Submitted To Client | 2023-02-13 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-02-13 | 03-02-01 | 2023-05-30 | Yes | Yes | Not Required | [5 empty] | 2023-08-25 |  | 87 | Overdue | 341 | Overdue | No | No | No
CC0375-BOP-FRP-007 | Demin Tank | Submitted To Client | 2023-05-05 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-05-05 | 03-03-01 | 2023-05-29 | Yes | Yes | Not Required | [5 empty] | 2023-08-29 |  | 92 | Overdue | 342 | Overdue | No | No | No
CC0375-BOP-FRP-008 | Potable Water Tank | Submitted To Client | 2023-03-23 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-03-23 | 03-04-01 | 2023-05-17 | Yes | Yes | Yes | NCR-007 |  | Yes | 2023-10-11 |  | 2023-06-06 |  | 20 | Early | 354 | Overdue | No | No | No
CC0375-BOP-FRP-012 | HV Transmission Pole | Submitted To Client | 2023-04-04 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-04-04 | 05-01-02 | 2023-07-13 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 |  | 203 | Overdue | 297 | Overdue | No | No | No
CC0375-BOP-FRP-036 | Emergency Diesel Generator | Submitted To Client | 2023-11-17 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-18 | 03-08-01 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-03-19 |  | 116 | Overdue | 163 | Overdue | No | No | No
CC0375-BOP-FRP-037 | LV Switch Room | Submitted To Client | 2023-10-10 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-10-10 | 03-06-02 | 2023-11-13 | Yes | Yes | Not Required |  | 2024-02-01 | No |  |  | 2024-02-14 |  | 93 | Overdue | 174 | Overdue | No | No | No
CC0375-BOP-FRP-038 | BOP - Unit Transformer | Physical Works Complete | 2023-11-17 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-21 | 03-06-04 | 2024-01-12 | Yes | Yes | Not Required | [7 empty] | 114 | Overdue | 114 | Overdue | No | No | No
CC0375-BOP-FRP-039 | BOP - Oily Water Pit / Interceptor Pit | Submitted To Client | 2023-06-02 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-06-02 | 04-08-02 | 2023-11-01 | No | No | Not Required | [5 empty] | 2024-04-29 |  | 180 | Overdue | 186 | Overdue | Yes | Yes | No
CC0375-BOP-FRP-039-04 | Interceptor Pit-Base (Wingslab) | Physical Works Complete | 2024-01-23 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-23 | 04-08-02 | 2024-02-08 | [10 empty] | 87 | Overdue | 87 | Overdue | No | No | No
CC0375-BOP-FRP-039-05 | Interceptor Pit-Wingslab-Foundation | Work In Progress | 2024-01-23 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-25 | 04-08-02 | [15 empty] | No | No | No
CC0375-BOP-FRP-039-06 | Interceptor Pit-Wingslab-HOB Walls and Pedestals | Work In Progress | 2024-02-03 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-05 | 04-08-02 | [15 empty] | No | No | No
CC0375-BOP-FRP-040 | BOP - Plant and Instrument Air Container | Physical Works Complete | 2024-02-13 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-17 | 03-05-01 | 2024-03-08 | [10 empty] | 58 | Nearly Overdue | 58 | Nearly Overdue | No | No | No
CC0375-BOP-FRP-041 | BOP - Air Receiver Vert Tank | Physical Works Complete | 2024-03-15 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-19 | 03-05-01 | 2024-03-28 | [10 empty] | 38 | Due | 38 | Due | No | No | No
CC0375-BOP-FRP-042 | BOP - Neutralisation Pit | Submitted To Client | 2023-08-04 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-08-07 | 04-07-02 | 2023-11-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-29 |  | 180 | Overdue | 186 | Overdue | No | No | No
CC0375-BOP-FRP-043 | BOP - Demineralised Water Shelter | Work In Progress | 2023-10-26 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-19 | 03-03-02 | [15 empty] | No | No | No
CC0375-BOP-FRP-044 | BOP - Demin equipment container | Submitted To Client | 2024-02-10 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-15 | 03-03-03 | 2024-03-14 |  |  | Yes | NCR -055 |  |  |  |  | 2024-03-14 |  | 0 | Early | 52 | Nearly Overdue | No | No | Yes
CC0375-BOP-FRP-045 | BOP - Fuel Forwarding Pump | Submitted To Client | 2024-01-08 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-08 | 03-02-03 | 2024-01-25 | Yes | Yes | Yes | NCR -056 & 062 |  | No | 2024-03-14 |  | 2024-04-29 |  | 95 | Overdue | 101 | Overdue | No | No | Yes
CC0375-BOP-FRP-046 | BOP - Fuel Oil/Diesel Fuel Unloading Shelter | Submitted To Client | 2024-01-15 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-15 | 03-02-02 | 2024-01-31 | Yes | Yes | Yes | NCR -065 |  | No | 2024-03-14 |  | 2024-04-29 |  | 89 | Overdue | 95 | Overdue | No | No | Yes
CC0375-BOP-FRP-047 | BOP - Fuel Unloading | Submitted To Client | 2024-02-10 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-10 | 03-02-02 | 2024-02-09 | Yes | Yes | Yes | NCR-065 |  | No | 2024-03-14 |  | 2024-03-14 |  | 34 | Due | 86 | Overdue | No | No | Yes
CC0375-BOP-FRP-048 | BOP - Fire Water | Closed | 2023-05-08 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-05-08 | 03-01-01 | 2023-08-16 | Yes | Yes | Not Required |  |  | Yes |  |  | 2023-10-14 | 2024-11-20 | 59 | Nearly Overdue | 462 | Overdue | No | No | No
CC0375-BOP-FRP-053 | HV Gantry & Switchyard Equipment | Submitted To Client | 2022-03-31 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2022-03-31 | 05-01-03 | 2023-11-01 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 105 | Overdue | 186 | Overdue | No | No | No
CC0375-BOP-FRP-054 | Protection Switch Yard Room | Submitted To Client | 2023-11-14 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-14 | 05-02-01 | 2023-11-22 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 84 | Overdue | 165 | Overdue | No | No | No
CC0375-BOP-FRP-055 | BOP-Diesel Tank Bund Area/Slab | Submitted To Client | 2023-04-27 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-04-27 | 03-02-01 | 2023-08-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-29 |  | 271 | Overdue | 277 | Overdue | No | No | No
CC0375-BOP-FRP-058 | Temp - Ringer crane Foundation | Closed | 2023-06-07 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-06-07 |  | 2023-06-07 | Yes | Yes | Not Required | [5 empty] | 2023-09-07 | 2023-09-13 | 92 | Overdue | 98 | Overdue | No | No | No
CC0375-BOP-FRP-059 | Temp - Admin Building Pad-Backfilling and Compaction | Closed | 2023-05-16 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-05-16 |  | 2023-05-25 | Yes | Yes | Not Required | [5 empty] | 2023-09-13 | 2023-10-09 | 111 | Overdue | 137 | Overdue | No | No | No
CC0375-BOP-FRP-060 | Temp - Workshop Building Pad-Backfilling and Compaction | Closed | 2023-05-16 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-05-16 |  | 2023-05-25 | Yes | Yes | Not Required | [5 empty] | 2023-09-13 | 2023-10-09 | 111 | Overdue | 137 | Overdue | No | No | No
CC0375-BOP-FRP-061 | Temp - 3B Laydown Area | Cancelled | 2023-06-05 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-06-05 |  | 2023-11-17 | Yes | Yes | Not Required | [7 empty] | 170 | Overdue | 170 | Overdue | No | No | No
CC0375-BOP-FRP-065 | Fire water pump house | Submitted To Client | 2024-02-02 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-02 | 03-01-02 | 2024-02-07 | Yes | Yes | Not Required | [5 empty] | 2024-03-07 |  | 29 | Early | 88 | Overdue | No | No | No
CC0375-BOP-FRP-075 | CC0375-BOP-FRP-XXX-01 - BOP PIPE TRENCH PT1 #X | Work In Progress | 2024-02-18 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-17 | [16 empty] | No | No | No
CC0375-BOP-FRP-076 | CC0375-BOP-FRP-XXX-01 - BOP PIPE TRENCH PT1 #X | Open | 2024-02-18 | Balance of Plant | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | [17 empty] | No | No | No
CC0375-BOP-PIL-001 | Fuel Diesel Tank (South)-Pile 05-09 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-19 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-002 | Fuel Diesel Tank (South)-Pile 05-10 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-19 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-003 | Fuel Diesel Tank (South)-Pile 05-11 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-19 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-004 | Fuel Diesel Tank (South)-Pile 05-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-19 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-005 | Fuel Diesel Tank (South)-Pile 05-06 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-19 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-006 | Fuel Diesel Tank (South)-Pile 05-19 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-007 | Fuel Diesel Tank (South)-Pile 05-07 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-008 | Fuel Diesel Tank (South)-Pile 05-05 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-009 | Fuel Diesel Tank (South)-Pile 05-04 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-13 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-010 | Fuel Diesel Tank (South)-Pile 05-18 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-13 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-0100 | HV Transmission Pole Foundation-Pile 12-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-03 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0101 | HV Transmission Pole Foundation-Pile 12-06 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-03 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0102 | HV Transmission Pole Foundation-Pile 12-11 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-03 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0103 | HV Transmission Pole Foundation-Pile 12-07 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-04 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0104 | HV Transmission Pole Foundation-Pile 12-03 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-04 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0105 | HV Transmission Pole Foundation-Pile 12-12 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-04 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0106 | HV Transmission Pole Foundation-Pile 12-10 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-06 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0107 | HV Transmission Pole Foundation-Pile 12-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-06 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0108 | HV Transmission Pole Foundation-Pile 12-04 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-06 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-0109 | HV Gantry Pole Foundation BOP-Pile 16-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-08 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-011 | Fuel Diesel Tank (South)-Pile 05-16 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-13 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-0110 | HV Gantry Pole Foundation-Pile 16-03 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-08 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0111 | HV Gantry Pole Foundation-Pile 16-05 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-08 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0112 | HV Gantry Pole Foundation-Pile 16-07 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-08 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0113 | HV Gantry Pole Foundation-Pile 16-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-09 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0114 | HV Gantry Pole Foundation-Pile 16-04 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-09 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0115 | HV Gantry Pole Foundation-Pile 16-06 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-09 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0116 | HV Gantry Pole Foundation-Pile 16-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-09 | 05-01-01 | 2023-05-09 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-BOP-PIL-0117 | Fire Water Tank BOP-Pile 17-20 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 03-01-01 | 2023-04-04 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 91 | Overdue | 189 | Overdue | No | No | No
CC0375-BOP-PIL-0118 | Fire Water Tank-Pile 17-26 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 03-01-01 | 2023-04-04 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 91 | Overdue | 189 | Overdue | No | No | No
CC0375-BOP-PIL-0119 | Fire Water Tank-Pile 17-18 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 03-01-01 | 2023-04-04 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 91 | Overdue | 189 | Overdue | No | No | No
CC0375-BOP-PIL-012 | Fuel Diesel Tank (South)-Pile 05-20 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-13 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-0120 | Fire Water Tank-Pile 17-24 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-01-01 | 2023-04-05 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 90 | Overdue | 188 | Overdue | No | No | No
CC0375-BOP-PIL-0121 | Fire Water Tank-Pile 17-22 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-01-01 | 2023-04-05 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 90 | Overdue | 188 | Overdue | No | No | No
CC0375-BOP-PIL-0122 | Fire Water Tank-Pile 17-28 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-01-01 | 2023-04-05 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 90 | Overdue | 188 | Overdue | No | No | No
CC0375-BOP-PIL-0123 | Fire Water Tank-Pile 17-04 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-01-01 | 2023-04-05 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 90 | Overdue | 188 | Overdue | No | No | No
CC0375-BOP-PIL-0124 | Fire Water Tank-Pile 17-12 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-01-01 | 2023-04-05 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 90 | Overdue | 188 | Overdue | No | No | No
CC0375-BOP-PIL-0125 | Fire Water Tank-Pile 17-19 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-12 | 03-01-01 | 2023-04-12 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 83 | Overdue | 181 | Overdue | No | No | No
CC0375-BOP-PIL-0126 | Fire Water Tank-Pile 17-17 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-12 | 03-01-01 | 2023-04-12 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 83 | Overdue | 181 | Overdue | No | No | No
CC0375-BOP-PIL-0127 | Fire Water Tank-Pile 17-02 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-12 | 03-01-01 | 2023-04-12 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 83 | Overdue | 181 | Overdue | No | No | No
CC0375-BOP-PIL-0128 | Fire Water Tank-Pile 17-21 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-12 | 03-01-01 | 2023-04-12 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 83 | Overdue | 181 | Overdue | No | No | No
CC0375-BOP-PIL-0129 | Fire Water Tank-Pile 17-07 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-013 | Fuel Diesel Tank (South)-Pile 05-12 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-13 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-0130 | Fire Water Tank-Pile 17-05 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0131 | Fire Water Tank-Pile 17-25 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0132 | Fire Water Tank-Pile 17-23 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0133 | Fire Water Tank-Pile 17-10 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0134 | Fire Water Tank-Pile 17-27 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0135 | Fire Water Tank-Pile 17-15 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0136 | Fire Water Tank-Pile 17-13 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-13 | 03-01-01 | 2023-04-13 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 82 | Overdue | 180 | Overdue | No | No | No
CC0375-BOP-PIL-0137 | Fire Water Tank-Pile 17-03 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-0138 | Fire Water Tank-Pile 17-01 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-0139 | Fire Water Tank-Pile 17-08 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-014 | Fuel Diesel Tank (South)-Pile 05-17 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-17 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-0140 | Fire Water Tank-Pile 17-06 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-0141 | Fire Water Tank-Pile 17-11 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-0142 | Fire Water Tank-Pile 17-09 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-14 | 03-01-01 | 2023-04-14 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 81 | Overdue | 179 | Overdue | No | No | No
CC0375-BOP-PIL-0143 | Fire Water Tank-Pile 17-16 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-10 | 03-01-01 | 2023-05-10 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 55 | Nearly Overdue | 153 | Overdue | No | No | No
CC0375-BOP-PIL-0144 | Fire Water Tank-Pile 17-14 | Closed | 2023-04-01 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-11 | 03-01-01 | 2023-05-11 | Yes | Yes | Yes | NCR-013 |  | Yes |  |  | 2023-07-04 | 2023-10-10 | 54 | Nearly Overdue | 152 | Overdue | No | No | No
CC0375-BOP-PIL-015 | Fuel Diesel Tank (South)-Pile 05-24 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-17 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-016 | Fuel Diesel Tank (South)-Pile 05-15 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-17 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-017 | Fuel Diesel Tank (South)-Pile 05-23 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-018 | Fuel Diesel Tank (South)-Pile 05-13 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-019 | Fuel Diesel Tank (South)-Pile 05-03 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-020 | Fuel Diesel Tank (South)-Pile 05-22 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-24 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-021 | Fuel Diesel Tank (South)-Pile 05-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-24 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-022 | Fuel Diesel Tank (South)-Pile 05-21 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-25 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-023 | Fuel Diesel Tank (South)-Pile 05-14 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-01 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-024 | Fuel Diesel Tank (South)-Pile 05-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-02 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-025 | Fuel Diesel Tank (North)-Pile 06-07 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-026 | Fuel Diesel Tank (North)-Pile 06-06 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-027 | Fuel Diesel Tank (North)-Pile 06-05 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-20 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-028 | Fuel Diesel Tank (North)-Pile 06-17 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-24 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-029 | Fuel Diesel Tank (North)-Pile 06-04 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-24 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-030 | Fuel Diesel Tank (North)-Pile 06-03 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-24 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-031 | Fuel Diesel Tank (North)-Pile 06-23 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-25 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-032 | Fuel Diesel Tank (North)-Pile 06-16 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-01-25 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-033 | Fuel Diesel Tank (North)-Pile 06-18 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-01 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-034 | Fuel Diesel Tank (North)-Pile 06-15 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-01 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-035 | Fuel Diesel Tank (North)-Pile 06-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-02 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-036 | Fuel Diesel Tank (North)-Pile 06-19 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-02 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-037 | Fuel Diesel Tank (North)-Pile 06-09 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-03 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-038 | Fuel Diesel Tank (North)-Pile 06-10 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-03 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-039 | Fuel Diesel Tank (North)-Pile 06-22 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-03 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-040 | Fuel Diesel Tank (North)-Pile 06-24 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-03 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-041 | Fuel Diesel Tank (North)-Pile 06-14 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-03 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-042 | Fuel Diesel Tank (North)-Pile 06-21 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-04 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-043 | Fuel Diesel Tank (North)-Pile 06-20 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-04 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-044 | Fuel Diesel Tank (North)-Pile 06-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-04 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-045 | Fuel Diesel Tank (North)-Pile 06-11 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-07 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-046 | Fuel Diesel Tank (North)-Pile 06-13 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-07 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-047 | Fuel Diesel Tank (North)-Pile 06-12 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-08 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-048 | Fuel Diesel Tank (North)-Pile 06-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-08 | 03-02-01 | 2023-03-15 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-03-22 | 2023-03-22 | 7 | Early | 7 | Early | No | No | No
CC0375-BOP-PIL-049 | Demin Tank-Pile 07-7 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-03-01 | 2023-02-09 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 194 | Overdue | 222 | Overdue | No | No | No
CC0375-BOP-PIL-050 | Demin Tank-Pile 07-3 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-03-01 | 2023-02-09 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 194 | Overdue | 222 | Overdue | No | No | No
CC0375-BOP-PIL-051 | Demin Tank-Pile 07-5 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-03-01 | 2023-02-09 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 194 | Overdue | 222 | Overdue | No | No | No
CC0375-BOP-PIL-052 | Demin Tank-Pile 07-6 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-14 | 03-03-01 | 2023-02-14 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 189 | Overdue | 217 | Overdue | No | No | No
CC0375-BOP-PIL-053 | Demin Tank-Pile 07-4 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-14 | 03-03-01 | 2023-02-14 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 189 | Overdue | 217 | Overdue | No | No | No
CC0375-BOP-PIL-054 | Demin Tank-Pile 07-15 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-16 | 03-03-01 | 2023-02-16 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 187 | Overdue | 215 | Overdue | No | No | No
CC0375-BOP-PIL-055 | Demin Tank-Pile 07-17 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-16 | 03-03-01 | 2023-02-16 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 187 | Overdue | 215 | Overdue | No | No | No
CC0375-BOP-PIL-056 | Demin Tank-Pile 07-16 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-24 | 03-03-01 | 2023-02-24 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 179 | Overdue | 207 | Overdue | No | No | No
CC0375-BOP-PIL-057 | Demin Tank-Pile 07-14 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-25 | 03-03-01 | 2023-02-25 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 178 | Overdue | 206 | Overdue | No | No | No
CC0375-BOP-PIL-058 | Demin Tank-Pile 07-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-27 | 03-03-01 | 2023-02-27 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 176 | Overdue | 204 | Overdue | No | No | No
CC0375-BOP-PIL-059 | Demin Tank-Pile 07-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-28 | 03-03-01 | 2023-02-28 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 175 | Overdue | 203 | Overdue | No | No | No
CC0375-BOP-PIL-060 | Demin Tank-Pile 07-21 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-28 | 03-03-01 | 2023-02-28 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 175 | Overdue | 203 | Overdue | No | No | No
CC0375-BOP-PIL-061 | Demin Tank-Pile 07-10 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-28 | 03-03-01 | 2023-02-28 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 175 | Overdue | 203 | Overdue | No | No | No
CC0375-BOP-PIL-062 | Demin Tank-Pile 07-22 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-01 | 03-03-01 | 2023-03-01 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 174 | Overdue | 202 | Overdue | No | No | No
CC0375-BOP-PIL-063 | Demin Tank-Pile 07-13 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-01 | 03-03-01 | 2023-03-01 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 174 | Overdue | 202 | Overdue | No | No | No
CC0375-BOP-PIL-064 | Demin Tank-Pile 07-11 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-01 | 03-03-01 | 2023-03-01 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 174 | Overdue | 202 | Overdue | No | No | No
CC0375-BOP-PIL-065 | Demin Tank-Pile 07-12 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-02 | 03-03-01 | 2023-03-02 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 173 | Overdue | 201 | Overdue | No | No | No
CC0375-BOP-PIL-066 | Demin Tank-Pile 07-24 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-02 | 03-03-01 | 2023-03-02 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 173 | Overdue | 201 | Overdue | No | No | No
CC0375-BOP-PIL-067 | Demin Tank-Pile 07-20 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 03-03-01 | 2023-04-04 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 140 | Overdue | 168 | Overdue | No | No | No
CC0375-BOP-PIL-068 | Demin Tank-Pile 07-23 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-05 | 03-03-01 | 2023-04-05 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 139 | Overdue | 167 | Overdue | No | No | No
CC0375-BOP-PIL-069 | Demin Tank-Pile 07-19 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-12 | 03-03-01 | 2023-04-12 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 132 | Overdue | 160 | Overdue | No | No | No
CC0375-BOP-PIL-070 | Demin Tank-Pile 07-18 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-11 | 03-03-01 | 2023-05-11 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 103 | Overdue | 131 | Overdue | No | No | No
CC0375-BOP-PIL-071 | Demin Tank-Pile 07-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-12 | 03-03-01 | 2023-05-12 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 102 | Overdue | 130 | Overdue | No | No | No
CC0375-BOP-PIL-072 | Demin Tank-Pile 07-09 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-13 | 03-03-01 | 2023-05-13 | Yes | Yes | Not Required | N/A |  |  |  |  | 2023-08-22 | 2023-09-19 | 101 | Overdue | 129 | Overdue | No | No | No
CC0375-BOP-PIL-073 | Potable Water Tank-Pile 08-12 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-08 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-074 | Potable Water Tank-Pile 08-02 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-08 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-075 | Potable Water Tank-Pile 08-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-076 | Potable Water Tank-Pile 08-03 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-077 | Potable Water Tank-Pile 08-05 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-09 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-078 | Potable Water Tank-Pile 08-20 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-10 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-079 | Potable Water Tank-Pile 08-14 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-10 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-080 | Potable Water Tank-Pile 08-04 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-10 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-081 | Potable Water Tank-Pile 08-06 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-10 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-082 | Potable Water Tank-Pile 08-11 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-11 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-083 | Potable Water Tank-Pile 08-15 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-14 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-084 | Potable Water Tank-Pile 08-13 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-15 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-085 | Potable Water Tank-Pile 08-16 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-15 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-086 | Potable Water Tank-Pile 08-10 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-15 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-087 | Potable Water Tank-Pile 08-07 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-15 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-088 | Potable Water Tank-Pile 08-21 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-16 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-089 | Potable Water Tank-Pile 08-19 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-16 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-090 | Potable Water Tank-Pile 08-17 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-16 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-091 | Potable Water Tank-Pile 08-22 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-21 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-092 | Potable Water Tank-Pile 08-24 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-21 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-093 | Potable Water Tank-Pile 08-23 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-24 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-094 | Potable Water Tank-Pile 08-09 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-24 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-095 | Potable Water Tank-Pile 08-18 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-25 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-096 | Potable Water Tank-Pile 08-08 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-02-27 | 03-04-01 | 2023-04-04 | Yes | Yes | Yes | NCR-005 |  | Yes |  |  | 2023-04-14 | 2023-04-14 | 10 | Early | 10 | Early | No | No | No
CC0375-BOP-PIL-097 | HV Transmission Pole Foundation-Pile 12-09 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-02 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-098 | HV Transmission Pole Foundation-Pile 12-05 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-02 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-PIL-099 | HV Transmission Pole Foundation-Pile 12-01 | Closed | 2022-10-10 | Balance of Plant | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-02 | 05-01-02 | 2023-05-10 | Yes | Yes | Yes | NCR-006 |  | Yes |  |  | 2023-08-02 | 2023-08-02 | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-BOP-SPL-001 | BOP - Screw Piling OW 30nos & TW 5nos | Closed | 2023-08-06 | Balance of Plant | Screw Piles | INF-HSEQ CC0375-ITP-021 Screw Piling | Jackson Smith | 2023-08-06 |  | 2023-09-15 | Yes | Yes | Not Required | [5 empty] | 2023-11-06 | 2023-11-06 | 52 | Nearly Overdue | 52 | Nearly Overdue | No | No | No
CC0375-COM-COND-001 | Comms Conduits-01UCZ01 GZ250 to GZ280 | Physical Works Complete | 2023-05-08 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-13 | 03-07-02 | 2023-07-14 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 189 | Overdue | 296 | Overdue | No | No | No
CC0375-COM-COND-002 | Comms Conduits-01UCZ01 GZ240 to GZ250 | Physical Works Complete | 2023-05-08 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-14 | 03-07-02 | 2023-07-14 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 189 | Overdue | 296 | Overdue | No | No | No
CC0375-COM-COND-003 | Comms Conduits-01UCZ01 GZ280 Eastern Turnups | Physical Works Complete | 2023-05-22 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-03 | 03-07-02 | 2023-07-27 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 176 | Overdue | 283 | Overdue | No | No | No
CC0375-COM-COND-004 | Comms Conduits-01UCZ01 GZ280 to GZ320 | Physical Works Complete | 2023-05-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-13 | 03-07-02 | 2023-09-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 122 | Overdue | 229 | Overdue | No | No | No
CC0375-COM-COND-005 | Comms Conduits-01UCZ01 GZ320 Eastern Turnups | Physical Works Complete | 2023-05-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-19 | 03-07-02 | 2023-09-22 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 119 | Overdue | 226 | Overdue | No | No | No
CC0375-COM-COND-006 | Comms Conduits-01UCZ01 GZ230 to GZ240 | Physical Works Complete | 2023-05-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-10 | 03-07-02 | 2023-07-11 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 192 | Overdue | 299 | Overdue | No | No | No
CC0375-COM-COND-007 | Comms Conduits-01UCZ01 GZ220 to GZ230 | Physical Works Complete | 2023-06-21 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-08 | 03-07-02 | 2023-08-09 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 163 | Overdue | 270 | Overdue | No | No | No
CC0375-COM-COND-008 | Comms Conduits-01UCZ01 GZ420 Turnups | Physical Works Complete | 2023-06-23 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-03 | 03-07-02 | 2023-08-08 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 164 | Overdue | 271 | Overdue | No | No | No
CC0375-COM-COND-009 | Comms Conduits-01UCZ01 GZ240 Southbound | Physical Works Complete | 2023-07-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-11 | 03-07-02 | 2023-07-14 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 189 | Overdue | 296 | Overdue | No | No | No
CC0375-COM-COND-010 | Comms Conduits-Fire Tank East Comms Turnups | Physical Works Complete | 2023-07-14 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-15 | 03-07-02 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 184 | Overdue | 291 | Overdue | No | No | No
CC0375-COM-COND-011 | Comms Conduits-Fire Tank West Comms Turnups | Physical Works Complete | 2023-07-17 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-17 | 03-07-02 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 184 | Overdue | 291 | Overdue | No | No | No
CC0375-COM-COND-012 | Comms Conduits-Fire Tank North Comms Turnups | Physical Works Complete | 2023-07-18 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-18 | 03-07-02 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 184 | Overdue | 291 | Overdue | No | No | No
CC0375-COM-COND-013 | Comms Conduits-01CO GCB to EXC | Physical Works Complete | 2023-07-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-31 | 03-07-02 | 2023-08-03 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 169 | Overdue | 276 | Overdue | No | No | No
CC0375-COM-COND-014 | Comms Conduits-01UCZ01 GZ410 to GZ420 including Turnups | Physical Works Complete | 2023-07-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-12 | 03-07-02 | 2023-09-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 122 | Overdue | 229 | Overdue | No | No | No
CC0375-COM-COND-015 | Comms Conduits-02CO GCB to EXC | Physical Works Complete | 2023-08-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-25 | 03-07-02 | 2023-08-28 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 144 | Overdue | 251 | Overdue | No | No | No
CC0375-COM-COND-016 | Comms Conduits-02UCZ01 GZ420 Turnups | Physical Works Complete | 2023-08-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-31 | 03-07-02 | 2023-09-01 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 140 | Overdue | 247 | Overdue | No | No | No
CC0375-COM-COND-017 | Comms Conduits-02UCZ01 GZ250 to GZ280 | Physical Works Complete | 2023-08-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-18 | 03-07-02 | 2023-08-21 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 151 | Overdue | 258 | Overdue | No | No | No
CC0375-COM-COND-018 | Comms Conduits-02UCZ01 GZ240 Southbound | Physical Works Complete | 2023-08-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-31 | 03-07-02 | 2023-09-05 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 136 | Overdue | 243 | Overdue | No | No | No
CC0375-COM-COND-019 | Comms Conduits-02 CO 02UCZ10 GZ280 Turnups | Physical Works Complete | 2023-08-18 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-22 | 03-07-02 | 2023-08-24 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 148 | Overdue | 255 | Overdue | No | No | No
CC0375-COM-COND-020 | Comms Conduits-02 CO 02UCZ01 GZ230 to 02UCZ01 GZ240 | Physical Works Complete | 2023-08-18 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-04 | 03-07-02 | 2023-09-05 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 136 | Overdue | 243 | Overdue | No | No | No
CC0375-COM-COND-021 | Comms Conduits-02 CO 02UCZ01 GZ240 to UCZ01 GZ250 | Physical Works Complete | 2023-08-18 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-01 | 03-07-02 | 2023-09-05 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 136 | Overdue | 243 | Overdue | No | No | No
CC0375-COM-COND-022 | Comms Conduits-02UCZ01 GZ220 to 02UCZ01 GZ230 | Physical Works Complete | 2023-08-24 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-24 | 03-07-02 | 2023-09-18 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 123 | Overdue | 230 | Overdue | No | No | No
CC0375-COM-COND-023 | Comms Conduits-90UCZ01 GZ030 to 90UCZ01 GZ040 | Submitted To Client | 2023-08-31 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-18 | 03-07-02 | 2023-09-18 | Yes | Yes | Yes | NCR-022 | 2023-10-23 | Yes | 2024-03-08 |  | 2024-04-22 |  | 217 | Overdue | 230 | Overdue | No | No | No
CC0375-COM-COND-024 | Comms Conduits-90UCZ01 GZ030 Turnups | Submitted To Client | 2023-08-31 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-19 | 03-07-02 | 2023-09-19 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE Model is attached as "Asbuilt" | 2024-04-22 |  | 216 | Overdue | 229 | Overdue | No | No | No
CC0375-COM-COND-025 | Comms Conduits-90UCZ01 GZ040 Turnups | Submitted To Client | 2023-08-31 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-18 | 03-07-02 | 2023-09-18 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE Model is attached as "Asbuilt" | 2024-04-22 |  | 217 | Overdue | 230 | Overdue | No | No | No
CC0375-COM-COND-026 | Comms Conduits-01UCZ01 GZ410 Eastern Turnups | Physical Works Complete | 2023-09-12 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-18 | 03-07-02 | 2023-12-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 31 | Due | 138 | Overdue | No | No | No
CC0375-COM-COND-027 | Comms Conduits-02UCZ01 GZ220 to GZ010 | Submitted To Client | 2023-09-12 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-18 | 03-07-02 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 80 | Overdue | 93 | Overdue | No | No | No
CC0375-COM-COND-028 | Comms Conduits-nm | Cancelled | 2024-02-05 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-02 |  | No | No | Not Required | [11 empty] | Yes | Yes | No
CC0375-COM-COND-029 | Comms Conduits-01UCZ01 GZ420 Eastern Turnups | Physical Works Complete | 2023-09-19 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-22 | 03-07-02 | 2023-09-23 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 118 | Overdue | 225 | Overdue | No | No | No
CC0375-COM-COND-030 | Comms Conduits-02UCZ01 GZ420 Eastern Turnups | Physical Works Complete | 2023-09-19 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-24 | 03-07-02 | 2023-10-25 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 86 | Overdue | 193 | Overdue | No | No | No
CC0375-COM-COND-031 | Comms Conduits-01 CO Prefab Substation to Step Up Transformer | Physical Works Complete | 2023-09-21 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-21 | 03-07-02 | 2023-09-21 | No | No | Not Required | [7 empty] | 227 | Overdue | 227 | Overdue | Yes | Yes | No
CC0375-COM-COND-032 | Comms Conduits-01UCZ01 GZ510 West turnups | Physical Works Complete | 2023-09-22 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-27 | 03-07-02 | 2023-09-27 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 114 | Overdue | 221 | Overdue | No | No | No
CC0375-COM-COND-033 | Comms Conduits-02UCZ02 GZ220 to 410 | Submitted To Client | 2024-02-05 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-04-08 | 03-07-02 | 2024-04-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 21 | Early | 26 | Early | No | No | No
CC0375-COM-COND-034 | Comms Conduits-02UCZ02 GZ220 South Turnups | Submitted To Client | 2023-09-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-04-09 | 03-07-02 | 2024-04-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 20 | Early | 25 | Early | No | No | No
CC0375-COM-COND-035 | Comms Conduits-02 CO Lube Oil to Mitsubishi Sub | Submitted To Client | 2023-09-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-29 | 03-07-02 | 2024-01-31 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 82 | Overdue | 95 | Overdue | No | No | No
CC0375-COM-COND-036 | Comms Conduits-02 CO Air Intake to Aux Transformer | Submitted To Client | 2024-02-01 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-01 | 03-07-02 | 2024-03-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 54 | Nearly Overdue | 59 | Nearly Overdue | No | No | No
CC0375-COM-COND-037 | Comms Conduits-01 CO 6.6kV Substation to SFC Transformer | Physical Works Complete | 2023-10-03 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-02 | 2023-10-04 | No | No | Not Required | [7 empty] | 214 | Overdue | 214 | Overdue | Yes | Yes | No
CC0375-COM-COND-038 | Comms Conduits-01 CO SFC Transformer Connections | Physical Works Complete | 2023-10-03 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-02 | 2023-10-04 | No | No | Not Required | [7 empty] | 214 | Overdue | 214 | Overdue | Yes | Yes | No
CC0375-COM-COND-039 | Comms Conduits-90UBZ01 GZ262 (Mega Pit) to 90UCZ01 GZ0270 | Submitted To Client | 2023-10-03 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-05 | 03-07-02 | 2023-10-05 | Yes | Yes | Not Required | NCR-029 | 2023-11-10 | No |  |  | 2024-04-22 |  | 200 | Overdue | 213 | Overdue | No | No | No
CC0375-COM-COND-040 | Comms Conduits-02UCZ01 GZ410 to GZ420 including Turnups | Physical Works Complete | 2023-10-09 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-09 | 03-07-02 | 2023-10-19 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 92 | Overdue | 199 | Overdue | No | No | No
CC0375-COM-COND-041 | Comms Conduits-02 CO Prefab Substation to Step Up Transformer | Submitted To Client | 2023-10-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-17 | 03-07-02 | 2023-11-18 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 156 | Overdue | 169 | Overdue | No | No | No
CC0375-COM-COND-042 | Comms Conduits-02UCZ01 GZ510 West turnups | Physical Works Complete | 2023-10-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-23 | 03-07-02 | 2023-10-24 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 87 | Overdue | 194 | Overdue | No | No | No
CC0375-COM-COND-043 | Comms Conduits-02UCZ01 GZ410 Eastern Turnups | Physical Works Complete | 2023-10-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-11 | 03-07-02 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 38 | Due | 145 | Overdue | No | No | No
CC0375-COM-COND-044 | Comms Conduits-02 CO Prefab Substation to SFC Transformer | Physical Works Complete | 2023-10-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-25 | 03-07-02 | 2023-10-25 | No | No | Not Required | [7 empty] | 193 | Overdue | 193 | Overdue | Yes | Yes | No
CC0375-COM-COND-045 | Comms Conduits-02 CO SFC Transformer Connections | Physical Works Complete | 2023-12-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-10 | 03-07-02 | 2024-01-10 | No | No | Not Required | [7 empty] | 116 | Overdue | 116 | Overdue | Yes | Yes | No
CC0375-COM-COND-046 | Comms Conduits-90UCZ01 GZ270 to 90UCZ01 GZ340 | Submitted To Client | 2023-10-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-10 | 03-07-02 | 2023-10-10 | Yes | Yes | Not Required | NCR-042 | 2023-11-24 | No |  |  | 2024-04-22 |  | 195 | Overdue | 208 | Overdue | No | No | No
CC0375-COM-COND-047 | Comms Conduits-90UCZ10 GZ020 West Turnups | Submitted To Client | 2023-10-24 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-01 | 03-07-02 | 2023-11-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 173 | Overdue | 186 | Overdue | No | No | No
CC0375-COM-COND-048 | Comms Conduits-90UCZ01 GZ020 to KNSS Existing Conduits | Submitted To Client | 2023-10-24 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-02 | 2023-11-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 160 | Overdue | 173 | Overdue | No | No | No
CC0375-COM-COND-049 | Comms Conduits-90UCZ01 GZ030 East Turnups | Submitted To Client | 2023-10-24 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-06 | 03-07-02 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 167 | Overdue | 180 | Overdue | No | No | No
CC0375-COM-COND-050 | Comms Conduits-90UCZ01 GZ340 to 90UCZ01 GZ330 | Submitted To Client | 2023-10-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-30 | 03-07-02 | 2023-11-17 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 157 | Overdue | 170 | Overdue | No | No | No
CC0375-COM-COND-051 | Comms Conduits-90UCZ01 GZ330 to 90UCZ01 GZ320 | Submitted To Client | 2023-10-25 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-08 | 03-07-02 | 2023-11-17 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 157 | Overdue | 170 | Overdue | No | No | No
CC0375-COM-COND-052 | Comms Conduits - 02UCZ01 GZ320 East | Submitted To Client | 2023-11-01 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-31 | 03-07-02 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 174 | Overdue | 185 | Overdue | No | No | No
CC0375-COM-COND-053 | Comms Conduits - 02UCZ01 GZ320 - 02UCZ01 GZ280 | Submitted To Client | 2023-11-06 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-06 | 03-07-02 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 169 | Overdue | 180 | Overdue | No | No | No
CC0375-COM-COND-054 | Comms Conduits - 02UCZ01 GZ280 West Turnups | Physical Works Complete | 2023-11-01 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-02 | 03-07-02 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-02-17 |  | 102 | Overdue | 180 | Overdue | No | No | No
CC0375-COM-COND-055 | 02UCZ01 GZ320 West Turnups | Submitted To Client | 2023-11-06 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-02 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 168 | Overdue | 179 | Overdue | No | No | No
CC0375-COM-COND-056 | Comms Conduits 02UCZ01 GZ320 South Turnup | Physical Works Complete | 2023-11-14 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-06 | 03-07-02 | 2023-12-08 | No | No | Not Required | [7 empty] | 149 | Overdue | 149 | Overdue | Yes | Yes | No
CC0375-COM-COND-057 | CO Conduits - 90UCZ01 GZ320 to 90UCZ01 GZ310 | Submitted To Client | 2023-11-14 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-14 | 03-07-02 | 2023-11-18 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 158 | Overdue | 169 | Overdue | No | No | No
CC0375-COM-COND-058 | Comms Conduits - 90UCZ01 GZ320 to 90UCZ01 GZ300 | Submitted To Client | 2023-11-14 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-14 | 03-07-02 | 2023-11-18 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 158 | Overdue | 169 | Overdue | No | No | No
CC0375-COM-COND-059 | Comms Conduits - 90UBZ01 GZ310 South Conduits and Turnups | Submitted To Client | 2023-11-16 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-16 | 03-07-02 | 2024-04-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 8 | Early | 13 | Early | No | No | No
CC0375-COM-COND-060 | Comms Conduits - 90UBZ01 GZ262 (mega pit) to 90UCZ01 GZ110 | Submitted To Client | 2023-11-20 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-20 | 03-07-02 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 152 | Overdue | 163 | Overdue | No | No | No
CC0375-COM-COND-061 | Comms Conduits - 90UCZ01 GZ110 to 90UCZ01 GZ020 | Submitted To Client | 2023-11-20 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-04 | 03-07-02 | 2024-01-11 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 112 | Overdue | 115 | Overdue | No | No | No
CC0375-COM-COND-062 | Comms Conduits 01UCZ01 GZ510 to GZ010 | Submitted To Client | 2023-11-23 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-30 | 03-07-02 | 2023-11-23 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 153 | Overdue | 164 | Overdue | No | No | No
CC0375-COM-COND-063 | CO Conduits - CO LV 90-241(mega pit) to 90UCZ01 GZ230 | Submitted To Client | 2023-11-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-29 | 03-07-02 | 2023-12-06 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 140 | Overdue | 151 | Overdue | No | No | No
CC0375-COM-COND-064 | CO Conduits - 02UCZ01 GZ010 to 90UBC01 GZ270 | Submitted To Client | 2023-11-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-06 | 03-07-02 | 2023-12-15 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 131 | Overdue | 142 | Overdue | No | No | No
CC0375-COM-COND-065 | Comms Conduits - 01UCZ01 GZ220 North | Submitted To Client | 2023-11-30 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-28 | 03-07-02 | 2023-11-30 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 146 | Overdue | 157 | Overdue | No | No | No
CC0375-COM-COND-066 | 90UCZ01 GZ210 to GZ220 | Submitted To Client | 2023-12-20 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-19 | 03-07-02 | 2023-12-20 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 126 | Overdue | 137 | Overdue | No | No | No
CC0375-COM-COND-067 | 02UCZ01 GZ010 to 02UCZ01 GZ510 | Submitted To Client | 2024-01-10 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-02 | 03-07-02 | 2024-01-05 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 118 | Overdue | 121 | Overdue | No | No | No
CC0375-COM-COND-068 | Comms Conduits 01UCZ01 GZ320 West Turnups | Submitted To Client | 2024-01-08 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-08 | 03-07-02 | 2024-01-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 104 | Overdue | 107 | Overdue | No | No | No
CC0375-COM-COND-069 | Comms Conduits 01UCZ01 GZ280 West Turnups | Submitted To Client | 2024-01-08 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-08 | 03-07-02 | 2024-01-13 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 110 | Overdue | 113 | Overdue | No | No | No
CC0375-COM-COND-070 | Comms Conduits 01UCZ01 GZ220 to GZ010 | Submitted To Client | 2024-01-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-02 | 2024-01-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 104 | Overdue | 107 | Overdue | No | No | No
CC0375-COM-COND-071 | 01 CO Lube Oil to Mitsubishi Sub | Submitted To Client | 2024-01-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-02 | 2024-01-19 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 84 | Overdue | 107 | Overdue | No | No | No
CC0375-COM-COND-072 | CO 90UCZ01 GZ350 TO 90UCZ01 GZ910 | Submitted To Client | 2024-01-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-15 | 03-07-02 | 2024-02-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 71 | Overdue | 94 | Overdue | No | No | No
CC0375-COM-COND-073 | CO 90UCZ01 GZ910 West Turnups | Open | 2024-01-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-02 | [15 empty] | No | No | No
CC0375-COM-COND-074 | CO 90UCZ01 GZ910 East Turnups | Submitted To Client | 2024-01-29 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-23 | 03-07-02 | 2024-01-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 74 | Overdue | 97 | Overdue | No | No | No
CC0375-COM-COND-075 | 90UCZ01 GZ300 to Kiosk | Physical Works Complete | 2024-01-11 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-02 | 2024-01-16 | No | No | Not Required | [7 empty] | 110 | Overdue | 110 | Overdue | Yes | Yes | No
CC0375-COM-COND-076 | 90UCZ01 GZ220 to GZ230 | Physical Works Complete | 2024-01-30 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-30 | 03-07-02 | 2024-01-31 | No | No | Not Required | [7 empty] | 95 | Overdue | 95 | Overdue | Yes | Yes | No
CC0375-COM-COND-077 | 01UCZ01 GZ220 to GZ410 | Submitted To Client | 2024-03-18 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-19 | 03-07-02 | 2024-03-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 39 | Due | 44 | Due | No | No | No
CC0375-COM-COND-078 | 01UCZ01 GZ220 South Turnups | Work In Progress | 2024-01-01 | Communications | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-19 | 03-07-02 | [15 empty] | No | No | No
CC0375-COM-IPIT-001 | GT01 Comms Pit-01UCZ01 GZ420 | Submitted To Client | 2023-05-25 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-25 | 03-07-02 | 2024-04-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 0 | Early | 11 | Early | No | No | No
CC0375-COM-IPIT-002 | GT01 Comms Pit-01UCZ01 GZ230 | Physical Works Complete | 2023-06-16 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-16 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-003 | GT01 Comms Pit-01UCZ01 GZ240 | Physical Works Complete | 2023-06-16 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-16 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-004 | GT01 Comms Pit-01UCZ01 GZ250 | Physical Works Complete | 2023-06-24 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-26 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-005 | GT01 Comms Pit-01UCZ01 GZ280 | Physical Works Complete | 2023-06-29 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-30 | 03-07-02 | 2024-02-25 | Yes | Yes | Not Required | [7 empty] | 70 | Overdue | 70 | Overdue | No | No | No
CC0375-COM-IPIT-006 | GT01 Comms Pit-01UCZ01 GZ010 | Physical Works Complete | 2023-07-10 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-10 | 03-07-02 | 2024-01-29 | Yes | Yes | Not Required | [7 empty] | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-COM-IPIT-007 | GT01 Comms Pit-01UCZ01 GZ220 | Physical Works Complete | 2023-07-14 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-15 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-008 | GT01 Comms Pit-01UCZ01 GZ510 | Submitted To Client | 2023-07-18 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-20 | 03-07-02 | 2024-01-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 70 | Overdue | 97 | Overdue | No | No | No
CC0375-COM-IPIT-009 | GT01 Comms Pit-01UCZ01 GZ320 | Physical Works Complete | 2023-07-28 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-31 | 03-07-02 | 2024-02-28 | Yes | Yes | Not Required | [7 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-COM-IPIT-010 | GT01 Comms Pit-01UCZ01 GZ410 | Physical Works Complete | 2023-08-01 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-01 | 03-07-02 | 2024-02-18 | Yes | Yes | Not Required | [7 empty] | 77 | Overdue | 77 | Overdue | No | No | No
CC0375-COM-IPIT-011 | GT02 Comms Pit-02UCZ01 GZ420 | Physical Works Complete | 2023-05-30 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-30 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-012 | GT02 Comms Pit-02UCZ01 GZ510 | Physical Works Complete | 2023-07-07 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-02 | 2024-02-08 | Yes | Yes | Not Required | [7 empty] | 87 | Overdue | 87 | Overdue | No | No | No
CC0375-COM-IPIT-013 | GT02 Comms Pit-02UCZ01 GZ010 | Physical Works Complete | 2023-07-07 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-02 | 2024-02-12 | Yes | Yes | Not Required | [7 empty] | 83 | Overdue | 83 | Overdue | No | No | No
CC0375-COM-IPIT-014 | GT02 Comms Pit-02UCZ01 GZ250 | Physical Works Complete | 2023-07-17 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-18 | 03-07-02 | 2024-02-28 | Yes | Yes | Not Required | [7 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-COM-IPIT-015 | GT02 Comms Pit-02UCZ01 GZ280 | Submitted To Client | 2023-08-01 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-01 | 03-07-02 | 2024-02-26 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 42 | Due | 69 | Overdue | No | No | No
CC0375-COM-IPIT-016 | GT02 Comms Pit-02UCZ01 GZ320 | Submitted To Client | 2023-08-03 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-04 | 03-07-02 | 2024-02-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 46 | Due | 73 | Overdue | No | No | No
CC0375-COM-IPIT-017 | GT02 Comms Pit-02UCZ01 GZ220 | Physical Works Complete | 2023-08-08 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-08 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [5 empty] | 2024-02-20 |  | -69 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-018 | GT02 Comms Pit-02UCZ01 GZ230 | Physical Works Complete | 2023-08-05 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-05 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-019 | GT02 Comms Pit-02UCZ01 GZ240 | Physical Works Complete | 2023-08-08 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-08 | 03-07-02 | 2024-04-29 | Yes | Yes | Not Required | [5 empty] | 2024-02-20 |  | -69 | Early | 6 | Early | No | No | No
CC0375-COM-IPIT-020 | GT02 Comms Pit-02UCZ01 GZ410 | Submitted To Client | 2023-09-16 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-18 | 03-07-02 | 2024-02-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 46 | Due | 73 | Overdue | No | No | No
CC0375-COM-IPIT-021 | BOP Comms Pit-90UCZ01 GZ330 | Submitted To Client | 2023-06-28 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-29 | 03-07-02 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-COM-IPIT-022 | BOP Comms Pit-90UCZ01 GZ320 | Submitted To Client | 2023-06-29 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-30 | 03-07-02 | 2023-12-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 117 | Overdue | 144 | Overdue | No | No | No
CC0375-COM-IPIT-023 | BOP Comms Pit-90UCZ01 GZ110 | Submitted To Client | 2023-07-04 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-10 | 03-07-02 | 2023-11-28 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 132 | Overdue | 159 | Overdue | No | No | No
CC0375-COM-IPIT-024 | BOP Comms Pit-90UCZ01 GZ340 | Submitted To Client | 2023-07-06 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-02 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 129 | Overdue | 156 | Overdue | No | No | No
CC0375-COM-IPIT-025 | BOP Comms Pit-90UCZ01 GZ040 | Submitted To Client | 2023-07-08 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-08 | 03-07-02 | 2023-11-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 138 | Overdue | 165 | Overdue | No | No | No
CC0375-COM-IPIT-026 | BOP Comms Pit-90UCZ01 GZ020 | Submitted To Client | 2023-08-08 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-09 | 03-07-02 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 136 | Overdue | 163 | Overdue | No | No | No
CC0375-COM-IPIT-027 | BOP Comms Pit-90UCZ01 GZ030 | Submitted To Client | 2023-07-13 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-13 | 03-07-02 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 133 | Overdue | 160 | Overdue | No | No | No
CC0375-COM-IPIT-028 | BOP Comms Pit-90UCZ01 GZ210 | Submitted To Client | 2023-10-02 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-10-03 | 03-07-02 | 2023-12-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 132 | Overdue | 143 | Overdue | No | No | No
CC0375-COM-IPIT-029 | BOP Comms Pit-90UCZ01 GZ220 | Submitted To Client | 2023-10-03 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-10-03 | 03-07-02 | 2023-12-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 132 | Overdue | 143 | Overdue | No | No | No
CC0375-COM-IPIT-030 | BOP Comms Pit-90UCZ01 GZ230 | Submitted To Client | 2023-08-26 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-05 | 03-07-02 | 2023-12-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 116 | Overdue | 143 | Overdue | No | No | No
CC0375-COM-IPIT-031 | BOP Comms Pit-90UCZ01 GZ270 | Physical Works Complete | 2023-08-11 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-11 | 03-07-02 | 2023-11-30 | Yes | Yes | Not Required | [5 empty] | 2024-03-15 |  | 106 | Overdue | 157 | Overdue | No | No | No
CC0375-COM-IPIT-032 | BOP Comms Pit-90UCZ01 GZ300 | Submitted To Client | 2023-08-17 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-18 | 03-07-02 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-COM-IPIT-033 | BOP Comms Pit-90UCZ01 GZ310 | Submitted To Client | 2023-09-18 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-12-19 | 03-07-02 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 134 | Overdue | 145 | Overdue | No | No | No
CC0375-COM-IPIT-034 | BOP Comms Pit-90UCZ01 GZ350 | Submitted To Client | 2023-08-28 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-05 | 03-07-02 | 2024-01-15 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 100 | Overdue | 111 | Overdue | No | No | No
CC0375-COM-IPIT-035 | BOP Comms Pit-90UCZ01 GZ910 | Submitted To Client | 2023-09-15 | Communications | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-16 | 03-07-02 | 2024-01-15 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 100 | Overdue | 111 | Overdue | No | No | No
CC0375-ELE-COND-001 | LV Conduits-01UBZ01 GZ250 to GZ280 | Submitted To Client | 2023-05-08 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-05-08 | 03-07-01 | 2023-05-12 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 357 | Overdue | 359 | Overdue | No | No | No
CC0375-ELE-COND-002 | MV Conduits-01UBY01 GZ270 to GZ420 | Physical Works Complete | 2023-05-08 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-20 | 03-07-01 | 2023-06-21 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 212 | Overdue | 319 | Overdue | No | No | No
CC0375-ELE-COND-003 | LV Conduits-01UBZ01 GZ240 to GZ250 | Submitted To Client | 2023-05-08 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-01 | 03-07-01 | 2023-06-14 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 324 | Overdue | 326 | Overdue | No | No | No
CC0375-ELE-COND-004 | LV Conduits-01UBZ01 GZ280 Turnups | Submitted To Client | 2023-05-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-27 | 03-07-01 | 2023-06-30 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 308 | Overdue | 310 | Overdue | No | No | No
CC0375-ELE-COND-005 | LV Conduits-01UBZ01 GZ280 to GZ320 | Submitted To Client | 2023-05-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-16 | 03-07-01 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 288 | Overdue | 291 | Overdue | No | No | No
CC0375-ELE-COND-006 | LV Conduits-01UBZ01 GZ320 Eastern Turnups | Submitted To Client | 2023-05-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-19 | 03-07-01 | 2023-09-22 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 224 | Overdue | 226 | Overdue | No | No | No
CC0375-ELE-COND-007 | LV Conduits-01UBZ01 GZ230 to GZ240 | Submitted To Client | 2023-05-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-18 | 03-07-01 | 2023-07-21 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 287 | Overdue | 289 | Overdue | No | No | No
CC0375-ELE-COND-008 | MV Conduits-02UBY01 GZ270 to GZ420 | Physical Works Complete | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-21 | 03-07-01 | 2023-08-23 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 149 | Overdue | 256 | Overdue | No | No | No
CC0375-ELE-COND-009 | LV Conduits-02UBZ01 GZ250 to GZ280 | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-26 | 03-07-01 | 2023-06-30 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 307 | Overdue | 310 | Overdue | No | No | No
CC0375-ELE-COND-010 | LV Conduits-02UBZ01 GZ240 to GZ250 | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-05 | 03-07-01 | 2023-07-07 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 300 | Overdue | 303 | Overdue | No | No | No
CC0375-ELE-COND-011 | LV Conduits-02UBZ01 GZ280 Turnups | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-15 | 03-07-01 | 2023-08-18 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 258 | Overdue | 261 | Overdue | No | No | No
CC0375-ELE-COND-012 | LV Conduits-02UBZ01 GZ280 to GZ320 | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-30 | 03-07-01 | 2023-10-30 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 185 | Overdue | 188 | Overdue | No | No | No
CC0375-ELE-COND-013 | LV Conduits-02UBZ01 GZ320 Western Turnups | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-01 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 167 | Overdue | 180 | Overdue | No | No | No
CC0375-ELE-COND-014 | LV Conduits-02UBZ01 GZ230 to GZ240 | Submitted To Client | 2023-06-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-05 | 03-07-01 | 2023-09-06 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 239 | Overdue | 242 | Overdue | No | No | No
CC0375-ELE-COND-015 | MV Conduits-01UBY01 GZ420 to GZ450 & GZ421 Northbound | Physical Works Complete | 2023-06-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-28 | 03-07-01 | 2023-07-04 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 199 | Overdue | 306 | Overdue | No | No | No
CC0375-ELE-COND-016 | MV Conduits-01UBY01 GZ422 Southbound | Physical Works Complete | 2023-06-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-08 | 03-07-01 | 2023-08-31 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 141 | Overdue | 248 | Overdue | No | No | No
CC0375-ELE-COND-017 | MV Conduits-01 SFC Transformer Connections | Physical Works Complete | 2023-06-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-03 | 03-07-01 | 2023-08-07 | No | No | Not Required | [7 empty] | 272 | Overdue | 272 | Overdue | Yes | Yes | No
CC0375-ELE-COND-018 | MV Conduits-01UBY01 GZ440 to GZ450 & Prefab Sub | Physical Works Complete | 2023-06-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-25 | 03-07-01 | 2023-10-06 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 105 | Overdue | 212 | Overdue | No | No | No
CC0375-ELE-COND-019 | LV Conduits-01UBZ01 GZ420 Turnups | Submitted To Client | 2023-06-23 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-05 | 03-07-01 | 2023-08-07 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 269 | Overdue | 272 | Overdue | No | No | No
CC0375-ELE-COND-020 | LV Conduits-01UBZ01 GZ230 Southbound | Submitted To Client | 2023-07-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-10 | 03-07-01 | 2023-07-12 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 295 | Overdue | 298 | Overdue | No | No | No
CC0375-ELE-COND-021 | LV Conduits-Fire Tank East LV Turnups | Submitted To Client | 2023-07-14 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-15 | 03-07-01 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 288 | Overdue | 291 | Overdue | No | No | No
CC0375-ELE-COND-022 | LV Conduits-Fire Tank West LV Turnups | Submitted To Client | 2023-07-17 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-17 | 03-07-01 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 288 | Overdue | 291 | Overdue | No | No | No
CC0375-ELE-COND-023 | LV Conduits-Fire Tank North LV Turnups | Submitted To Client | 2023-07-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-18 | 03-07-01 | 2023-07-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 289 | Overdue | 291 | Overdue | No | No | No
CC0375-ELE-COND-024 | MV Conduits-01 MV Prefab Substation to Step Up Transformer | Physical Works Complete | 2023-07-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-25 | 03-07-01 | 2023-08-03 | No | No | Not Required | [7 empty] | 276 | Overdue | 276 | Overdue | Yes | Yes | No
CC0375-ELE-COND-025 | MV Conduits-01UBY01 GZ210 to GZ420 | Physical Works Complete | 2023-07-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-17 | 03-07-01 | 2023-08-22 | No | No | Not Required | [7 empty] | 257 | Overdue | 257 | Overdue | Yes | Yes | No
CC0375-ELE-COND-026 | LV Conduits-01LV GCB to EXC | Submitted To Client | 2023-07-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-07-31 | 03-07-01 | 2023-08-03 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 274 | Overdue | 276 | Overdue | No | No | No
CC0375-ELE-COND-027 | LV Conduits-01UBZ01 GZ410 to GZ420 including Turnups | Submitted To Client | 2023-07-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-05 | 03-07-01 | 2023-09-22 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 224 | Overdue | 226 | Overdue | No | No | No
CC0375-ELE-COND-028 | LV Conduits-01UBZ01 GZ210 to GZ230 | Submitted To Client | 2023-08-08 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-27 | 03-07-01 | 2023-11-28 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 157 | Overdue | 159 | Overdue | No | No | No
CC0375-ELE-COND-029 | LV Conduits-01UBZ01 GZ210 to GZ410 | Submitted To Client | 2023-08-08 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-09 | 03-07-01 | 2023-08-11 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 266 | Overdue | 268 | Overdue | No | No | No
CC0375-ELE-COND-030 | LV Conduits-02LV GCB to EXC | Submitted To Client | 2023-08-11 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-25 | 03-07-01 | 2023-08-28 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 248 | Overdue | 251 | Overdue | No | No | No
CC0375-ELE-COND-031 | LV Conduits-02UBZ01 GZ230 Southbound | Submitted To Client | 2023-08-11 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-28 | 03-07-01 | 2023-09-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 245 | Overdue | 247 | Overdue | No | No | No
CC0375-ELE-COND-032 | MV Conduits-01UBY01 GZ270 West | Physical Works Complete | 2023-08-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-15 | 03-07-01 | 2023-09-18 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 123 | Overdue | 230 | Overdue | No | No | No
CC0375-ELE-COND-033 | MV Conduits-02UBY10 GZ411 to 02UBY10 GZ412 SFC transformer | Submitted To Client | 2023-08-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-25 | 03-07-01 | 2023-11-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 154 | Overdue | 165 | Overdue | No | No | No
CC0375-ELE-COND-034 | MV Conduits-01UBY01 GZ421 North Turnups - (Redundant w/ ELE-COND-015) | Cancelled | 2023-08-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-06-28 | 03-07-01 | 2023-09-18 | No | No | Not Required | [7 empty] | 230 | Overdue | 230 | Overdue | Yes | Yes | No
CC0375-ELE-COND-035 | MV Conduits-02UBY01 GZ210 to 02UBY01 GZ420 | Physical Works Complete | 2023-08-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-03 | 03-07-01 | 2023-09-18 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 206 | Overdue | 230 | Overdue | No | No | No
CC0375-ELE-COND-036 | LV Conduits-02UBZ01 GZ420 Turnups | Submitted To Client | 2023-08-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-08-30 | 03-07-01 | 2023-09-05 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 230 | Overdue | 243 | Overdue | No | No | No
CC0375-ELE-COND-037 | LV Conduits-90UBZ01 GZ030 to 90UBZ01 GZ040 | Submitted To Client | 2023-08-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-01 | 03-07-01 | 2023-09-05 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE model is attached as "asbuilt" | 2024-04-22 |  | 230 | Overdue | 243 | Overdue | No | No | No
CC0375-ELE-COND-038 | LV Conduits-90UBZ01 GZ030 North Turnups | Submitted To Client | 2023-08-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-11 | 03-07-01 | 2023-09-15 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE Model is attached as "Asbuilt" | 2024-04-22 |  | 220 | Overdue | 233 | Overdue | No | No | No
CC0375-ELE-COND-039 | LV Conduits-90UBZ01 GZ030 South Turnups | Submitted To Client | 2023-08-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-05 | 03-07-01 | 2023-09-07 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE Model is attached as "Asbuilt" | 2024-04-22 |  | 228 | Overdue | 241 | Overdue | No | No | No
CC0375-ELE-COND-040 | LV Conduits-90UBZ01 GZ040 North Turnups | Submitted To Client | 2023-08-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-07 | 03-07-01 | 2023-09-15 | Yes | Yes | Not Required | NCR-022 | 2023-10-23 | No |  | WAE Model is attached as "Asbuilt" | 2024-04-22 |  | 220 | Overdue | 233 | Overdue | No | No | No
CC0375-ELE-COND-041 | LV Conduits-90UBZ01 GZ040 South Turnups | Submitted To Client | 2023-08-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-04 | 03-07-01 | 2023-09-05 | Yes | Yes | Yes | NCR-022 |  | Yes | 2024-03-08 |  | 2024-04-22 |  | 230 | Overdue | 243 | Overdue | No | No | No
CC0375-ELE-COND-042 | MV Conduits-02UBY01 GZ270 West | Physical Works Complete | 2023-10-28 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-28 | 03-07-01 | 2023-10-28 | Yes | Yes | Not Required | [5 empty] | 2024-01-19 |  | 83 | Overdue | 190 | Overdue | No | No | No
CC0375-ELE-COND-043 | LV Conduits-02UBZ01 GZ210 to GZ230 | Submitted To Client | 2023-11-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-24 | 03-07-01 | 2023-12-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 131 | Overdue | 144 | Overdue | No | No | No
CC0375-ELE-COND-044 | LV Conduits-01UBZ01 GZ410 Eastern Turnups | Submitted To Client | 2023-09-12 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-18 | 03-07-01 | 2023-09-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 227 | Overdue | 229 | Overdue | No | No | No
CC0375-ELE-COND-045 | LV Conduits-02UBZ01 GZ210 to GZ010 (including North and East Turnups) | Submitted To Client | 2023-09-12 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-29 | 03-07-01 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 80 | Overdue | 93 | Overdue | No | No | No
CC0375-ELE-COND-046 | LV Conduits-90UBZ01 GZ020 to KNSS Existing Conduits | Cancelled | 2023-09-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-01 |  | No | No | Not Required | [11 empty] | Yes | Yes | No
CC0375-ELE-COND-047 | LV Conduits-90UBZ10 GZ033 (BOP TU1) to 90UBZ10 GZ034 (BOP LVSR) Turnups [LV+CO] | Submitted To Client | 2023-09-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-09 | 03-07-01 | 2023-10-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 195 | Overdue | 208 | Overdue | No | No | No
CC0375-ELE-COND-048 | LV Conduits-90UBZ10 GZ035 (BOP TU2) to 90UBZ10 GZ036 (BOP LVSR) Turnups [LV+CO] | Submitted To Client | 2023-09-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-10 | 03-07-01 | 2023-10-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 193 | Overdue | 206 | Overdue | No | No | No
CC0375-ELE-COND-049 | LV Conduits-90UBZ10 GZ037 (BOP TU3) to 90UBZ10 GZ038 (BOP LVSR) Turnups [LV+CO] | Submitted To Client | 2023-09-18 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-10 | 03-07-01 | 2023-10-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 193 | Overdue | 206 | Overdue | No | No | No
CC0375-ELE-COND-050 | MV Conduits-01UBY01 GZ440 to 90UBY01 GZ260 | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-01 | 2023-11-20 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 154 | Overdue | 167 | Overdue | No | No | No
CC0375-ELE-COND-051 | MV Conduits-02 MV Prefab Substation to Step Up Transformer | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-06 | 03-07-01 | 2023-10-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 196 | Overdue | 209 | Overdue | No | No | No
CC0375-ELE-COND-052 | MV Conduits-90UBY01 GZ040 to 90UBY01 GZ260 | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-25 | 03-07-01 | 2023-09-27 | Yes | Yes | Not Required | NCR-029 | 2023-11-10 | No |  |  | 2024-04-22 |  | 208 | Overdue | 221 | Overdue | No | No | No
CC0375-ELE-COND-053 | LV Conduits-01UBZ01 GZ320 Western Turnups | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-08 | 03-07-01 | 2024-01-19 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 94 | Overdue | 107 | Overdue | No | No | No
CC0375-ELE-COND-054 | LV Conduits-01 LV Prefab Substation to Step Up Transformer | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-22 | 03-07-01 | 2023-09-23 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 223 | Overdue | 225 | Overdue | No | No | No
CC0375-ELE-COND-055 | LV Conduits-02UBZ01 GZ410 to GZ420 including Turnups | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-09 | 03-07-01 | 2023-10-12 | No | No | Not Required | [5 empty] | 2024-04-22 |  | 193 | Overdue | 206 | Overdue | Yes | Yes | No
CC0375-ELE-COND-056 | LV Conduits-02UBZ01 GZ410 Eastern Turnups | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-13 | 03-07-01 | 2023-10-17 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 199 | Overdue | 201 | Overdue | No | No | No
CC0375-ELE-COND-057 | LV Conduits-90UBZ10 GZ039 South Turnups | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-05 | 03-07-01 | 2023-10-09 | Yes | Yes | Not Required | NCR-029 | 2023-11-10 | No |  |  | 2024-04-22 |  | 196 | Overdue | 209 | Overdue | No | No | No
CC0375-ELE-COND-058 | LV Conduits-90UBZ10 GZ093 to 90UBZ10 GZ092 Turnups [LV+CO] | Submitted To Client | 2023-09-21 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-12 | 03-07-01 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 167 | Overdue | 180 | Overdue | No | No | No
CC0375-ELE-COND-059 | LV Conduits-01UBZ01 GZ510 West turnups | Submitted To Client | 2023-09-22 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-09-27 | 03-07-01 | 2023-09-27 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 219 | Overdue | 221 | Overdue | No | No | No
CC0375-ELE-COND-060 | MV Conduits-02UBY01 GZ210 East to Aux Transformer | Submitted To Client | 2023-09-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-01 | 03-07-01 | 2024-03-07 | No | No | Not Required | [5 empty] | 2024-04-30 |  | 54 | Nearly Overdue | 59 | Nearly Overdue | Yes | Yes | No
CC0375-ELE-COND-061 | LV Conduits-02 LV Lube Oil to Mitsubishi Sub | Submitted To Client | 2023-09-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-29 | 03-07-01 | 2024-04-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 20 | Early | 25 | Early | No | No | No
CC0375-ELE-COND-062 | LV Conduits-02 LV Air Intake to Aux Transformer | Submitted To Client | 2023-09-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-01 | 03-07-01 | 2024-03-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 54 | Nearly Overdue | 59 | Nearly Overdue | No | No | No
CC0375-ELE-COND-063 | LV Conduits-02 LV Air Intake to Mitsubishi Sub | Submitted To Client | 2023-09-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-01 | 03-07-01 | 2024-03-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 54 | Nearly Overdue | 59 | Nearly Overdue | No | No | No
CC0375-ELE-COND-064 | LV Conduits-02UBZ01 GZ210 to GZ410 | Submitted To Client | 2023-09-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-06 | 03-07-01 | 2023-12-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 137 | Overdue | 150 | Overdue | No | No | No
CC0375-ELE-COND-065 | MV Conduits-01 MV 6.6kV Substation to SFC Transformer | Physical Works Complete | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-01 | 2023-10-03 | No | No | Not Required | [7 empty] | 215 | Overdue | 215 | Overdue | Yes | Yes | No
CC0375-ELE-COND-066 | MV Conduits-01UBY01 GZ450 to 02UBY01 GZ210 | Submitted To Client | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-29 | 03-07-01 | 2023-11-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 160 | Overdue | 173 | Overdue | No | No | No
CC0375-ELE-COND-067 | MV Conduits-90UBY01 GZ260 to 01UBY01 GZ340 | Submitted To Client | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-09 | 03-07-01 | 2023-10-24 | Yes | Yes | Not Required | NCR-042 | 2023-11-24 | No |  |  | 2024-04-22 |  | 181 | Overdue | 194 | Overdue | No | No | No
CC0375-ELE-COND-068 | MV Conduits-01UBY01 GZ421 to GZ422 | Submitted To Client | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-29 | 03-07-01 | 2023-11-03 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 171 | Overdue | 184 | Overdue | No | No | No
CC0375-ELE-COND-069 | LV Conduits-01 LV Prefab Substation to SFC Transformer | Physical Works Complete | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-01 | 2023-10-03 | No | No | Not Required | [7 empty] | 215 | Overdue | 215 | Overdue | Yes | Yes | No
CC0375-ELE-COND-070 | LV Conduits-01 LV SFC Transformer Connections | Physical Works Complete | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-03 | 03-07-01 | 2023-10-03 | No | No | Not Required | [7 empty] | 215 | Overdue | 215 | Overdue | Yes | Yes | No
CC0375-ELE-COND-071 | LV Conduits-90UBZ01 GZ262 (Mega Pit) to 90UBZ01GZ270 | Submitted To Client | 2023-10-03 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-04 | 03-07-01 | 2023-10-17 | Yes | Yes | Not Required | NCR-029 | 2023-11-10 | No |  |  | 2024-04-22 |  | 188 | Overdue | 201 | Overdue | No | No | No
CC0375-ELE-COND-072 | MV Conduits-02UBY01 GZ420 to 450 | Physical Works Complete | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-20 | 03-07-01 | 2023-10-23 | Yes | Yes | Not Required | [5 empty] | 2024-02-29 |  | 129 | Overdue | 195 | Overdue | No | No | No
CC0375-ELE-COND-073 | MV Conduits-02UBY01 450 East Turnups | Submitted To Client | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-23 | 03-07-01 | 2023-10-23 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 182 | Overdue | 195 | Overdue | No | No | No
CC0375-ELE-COND-074 | MV Conduits-02 MV Prefab Substation to SFC Transformer | Physical Works Complete | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-25 | 03-07-01 | 2023-10-25 | No | No | Not Required | [7 empty] | 193 | Overdue | 193 | Overdue | Yes | Yes | No
CC0375-ELE-COND-075 | LV Conduits-02UBZ01 GZ510 West turnups | Submitted To Client | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-23 | 03-07-01 | 2023-10-24 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 192 | Overdue | 194 | Overdue | No | No | No
CC0375-ELE-COND-076 | LV Conduits-02UBZ01 GZ410 Eastern Turnups (Duplicate with 056) | Cancelled | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-01 |  | No | No | Not Required | [11 empty] | Yes | Yes | No
CC0375-ELE-COND-077 | LV Conduits-02 LV Prefab Substation to Step Up Transformer | Submitted To Client | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-31 | 03-07-01 | 2023-10-31 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 185 | Overdue | 187 | Overdue | No | No | No
CC0375-ELE-COND-078 | LV Conduits-02 LV Prefab Substation to SFC Transformer | Physical Works Complete | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-25 | 03-07-01 | 2023-10-25 | No | No | Not Required | [7 empty] | 193 | Overdue | 193 | Overdue | Yes | Yes | No
CC0375-ELE-COND-079 | LV Conduits-02 LV SFC Transformer Connections | Physical Works Complete | 2023-10-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-10 | 03-07-01 | 2023-10-10 | No | No | Not Required | [7 empty] | 208 | Overdue | 208 | Overdue | Yes | Yes | No
CC0375-ELE-COND-080 | LV Conduits-90UBZ01 GZ270 to 90UBZ01 GZ340 | Physical Works Complete | 2023-10-17 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-17 | 03-07-01 | 2023-10-24 | Yes | Yes | Yes | NCR-042 | 2023-11-24 | Yes | 2024-03-08 |  | 2024-03-08 |  | 136 | Overdue | 194 | Overdue | No | No | No
CC0375-ELE-COND-081 | LV Conduits-90UBZ01 GZ020 to KNSS Existing Conduits | Submitted To Client | 2023-10-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-01 | 2023-11-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 160 | Overdue | 173 | Overdue | No | No | No
CC0375-ELE-COND-082 | LV Conduits-90UBZ01 GZ030 to 90UBZ01 GZ020 & Turnups | Submitted To Client | 2023-10-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-31 | 03-07-01 | 2023-11-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 173 | Overdue | 186 | Overdue | No | No | No
CC0375-ELE-COND-083 | Lighting & GP Conduits-LS90-020 to LS90-010 & LS90-010 East Turnups | Physical Works Complete | 2023-10-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-10 | 03-07-01 | 2023-11-14 | No | No | Not Required |  |  |  |  | WAE Model is pending to receive from GREG. 1 Overlay testing report is pending. |  |  | 173 | Overdue | 173 | Overdue | Yes | Yes | No
CC0375-ELE-COND-084 | Lighting & GP Conduits-LS90-050 to LS90-040 to LS90-030 & LS90-030 East Turnups | Physical Works Complete | 2023-10-24 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-14 | 03-07-01 | 2024-03-26 | No | No | Not Required | [7 empty] | 40 | Due | 40 | Due | Yes | Yes | No
CC0375-ELE-COND-085 | MV Conduits-90UBY01 GZ340 to 90UBZ01 GZ300 | Physical Works Complete | 2023-10-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-25 | 03-07-01 | 2023-11-20 | No | No | Not Required | [7 empty] | 167 | Overdue | 167 | Overdue | Yes | Yes | No
CC0375-ELE-COND-086 | LV Conduits-90UBZ01 GZ340 to 90UBZ01 GZ330 | Physical Works Complete | 2023-10-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-25 | 03-07-01 | 2023-10-31 | No | No | Not Required | [7 empty] | 187 | Overdue | 187 | Overdue | Yes | Yes | No
CC0375-ELE-COND-087 | LV Conduits-90UBZ01 GZ330 to 90UBZ01 GZ320 | Submitted To Client | 2023-10-25 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-07 | 03-07-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 143 | Overdue | 156 | Overdue | No | No | No
CC0375-ELE-COND-088 | MV Conduits - 90UBY01 GZ010 to 90UBY01 GZ020 to 90UBY01 GZ030 and South Turnups | Submitted To Client | 2023-10-31 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-02 | 03-07-01 | 2023-11-03 | Yes | Yes | Yes | NCR-042 | 2023-11-24 | Yes | 2024-03-08 |  | 2024-04-22 |  | 171 | Overdue | 184 | Overdue | No | No | No
CC0375-ELE-COND-089 | MV Conduits - 90UBY01 GZ030 to 90UBY01 GZ040 | Submitted To Client | 2023-11-02 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-02 | 03-07-01 | 2023-11-02 | Yes | Yes | Yes | NCR-042 | 2023-11-24 | Yes | 2024-03-08 |  | 2024-04-22 |  | 172 | Overdue | 185 | Overdue | No | No | No
CC0375-ELE-COND-090 | LV Conduits - 02UBZ01 GZ320 East Turnups | Submitted To Client | 2023-11-06 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-31 | 03-07-01 | 2023-11-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 173 | Overdue | 186 | Overdue | No | No | No
CC0375-ELE-COND-091 | LV Conduits - 02UBZ01 GZ280 West Turnups | Physical Works Complete | 2023-11-06 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-02 | 03-07-01 | 2023-11-06 | No | No | Not Required | [7 empty] | 181 | Overdue | 181 | Overdue | Yes | Yes | No
CC0375-ELE-COND-092 | LV Conduits - 90UBZ01 GZ320 to 90UBZ01 GZ310 | Submitted To Client | 2023-11-14 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-14 | 03-07-01 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 149 | Overdue | 160 | Overdue | No | No | No
CC0375-ELE-COND-093 | LV Conduits - 90UBZ01 GZ310 to 90UBZ01 GZ300 | Submitted To Client | 2023-11-15 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-15 | 03-07-01 | 2023-11-20 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 164 | Overdue | 167 | Overdue | No | No | No
CC0375-ELE-COND-094 | LV Conduits - 90UBZ01 GZ310 South Conduits and Turnups | Submitted To Client | 2023-11-16 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-16 | 03-07-01 | 2024-04-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 8 | Early | 13 | Early | No | No | No
CC0375-ELE-COND-095 | LV Conduits - 90UBZ01 GZ262 (mega pit) to 90UBZ01 GZ110 | Submitted To Client | 2023-11-20 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-24 | 03-07-01 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 160 | Overdue | 163 | Overdue | No | No | No
CC0375-ELE-COND-096 | LV Conduits - 90UBZ01 GZ110 to 90UBZ01 GZ020 | Submitted To Client | 2023-11-20 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-04 | 03-07-01 | 2024-01-23 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 100 | Overdue | 103 | Overdue | No | No | No
CC0375-ELE-COND-097 | LV Conduits 01UBZ01 GZ510 to 01UBZ01 GZ010 | Submitted To Client | 2023-11-22 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-22 | 03-07-01 | 2023-12-19 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 135 | Overdue | 138 | Overdue | No | No | No
CC0375-ELE-COND-098 | LV Conduits - 90UBZ10 GZ074 to 90UBZ01 GZ350 [LV] & 90UCZ055 to 90UCZ01 GZ350 [CO] | Physical Works Complete | 2023-11-27 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-27 | 03-07-01 | 2024-02-01 | No | No | Not Required | [7 empty] | 94 | Overdue | 94 | Overdue | Yes | Yes | No
CC0375-ELE-COND-099 | LV&CO Conduits - 90UBZ01 GZ220 to 90UBZ10 GZ070 (LV) & 90UCZ01 GZ220 to 90UCZ10 GZ010 (CO) | Submitted To Client | 2023-11-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-30 | 03-07-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 153 | Overdue | 156 | Overdue | No | No | No
CC0375-ELE-COND-100 | LV&CO Conduits - 90UBZ10 GZ076 to 90UBZ10 GZ077 (LV) & 90UCZ10 GZ059 to 90UCZ10 GZ060 (CO) | Submitted To Client | 2023-11-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-11-29 | 03-07-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 153 | Overdue | 156 | Overdue | No | No | No
CC0375-ELE-COND-101 | LV Conduits - CO LV 90-241(mega pit) to 90UBZ01 GZ230 | Submitted To Client | 2023-11-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-06 | 03-07-01 | 2023-12-07 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 147 | Overdue | 150 | Overdue | No | No | No
CC0375-ELE-COND-102 | LV Conduits - 02UBZ01 GZ010 to 90UBZ01 GZ270 | Submitted To Client | 2023-11-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-06 | 03-07-01 | 2023-12-15 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 139 | Overdue | 142 | Overdue | No | No | No
CC0375-ELE-COND-103 | LV Conduits 01UBZ01 GZ210 to GZ010 | Submitted To Client | 2023-12-01 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-01 | 03-07-01 | 2023-12-04 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 150 | Overdue | 153 | Overdue | No | No | No
CC0375-ELE-COND-104 | LV Conduits 90UBZ01 GZ210 to GZ220 | Submitted To Client | 2023-12-19 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-12-19 | 03-07-01 | 2023-12-20 | Yes | Yes | Not Required | [5 empty] | 2024-05-02 |  | 134 | Overdue | 137 | Overdue | No | No | No
CC0375-ELE-COND-105 | 02UCZ01 GZ010 to 02UCZ01 GZ510 | Physical Works Complete | 2024-01-10 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-02 | 03-07-01 | 2024-01-05 | No | No | Not Required | [7 empty] | 121 | Overdue | 121 | Overdue | Yes | Yes | No
CC0375-ELE-COND-106 | 01 LV Lube Oil to Mitsubishi Sub | Submitted To Client | 2024-01-11 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-01 | 2024-03-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 39 | Due | 44 | Due | No | No | No
CC0375-ELE-COND-107 | LV 01UBZ01 GZ280 West Turnups | Physical Works Complete | 2024-01-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-08 | 03-07-01 | 2024-01-19 | No | No | Not Required | [7 empty] | 107 | Overdue | 107 | Overdue | Yes | Yes | No
CC0375-ELE-COND-108 | LV 90UBZ01 GZ350 TO 90UBZ01 GZ910 | Submitted To Client | 2024-01-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-15 | 03-07-01 | 2024-02-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 71 | Overdue | 94 | Overdue | No | No | No
CC0375-ELE-COND-109 | LV 90UBZ01 GZ910 East Turnups | Submitted To Client | 2024-01-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-29 | 03-07-01 | 2024-01-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 74 | Overdue | 97 | Overdue | No | No | No
CC0375-ELE-COND-110 | MV 02UBY01 GZ450 TO 90UBY01 GZ910 | Submitted To Client | 2024-01-15 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-15 | 03-07-01 | 2024-02-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 71 | Overdue | 94 | Overdue | No | No | No
CC0375-ELE-COND-111 | MV 90UBZ01 GZ300 to Kiosk | Physical Works Complete | 2024-01-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-01 | 2024-01-16 | No | No | Not Required | [7 empty] | 110 | Overdue | 110 | Overdue | Yes | Yes | No
CC0375-ELE-COND-112 | LV 90UBZ01 GZ300 to Kiosk | Physical Works Complete | 2024-01-29 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-11 | 03-07-01 | 2024-01-16 | No | No | Not Required | [7 empty] | 110 | Overdue | 110 | Overdue | Yes | Yes | No
CC0375-ELE-COND-113 | 90UBZ01 GZ220 to GZ230 | Physical Works Complete | 2024-01-30 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-01-30 | 03-07-01 | 2024-01-31 | No | No | Not Required | [7 empty] | 95 | Overdue | 95 | Overdue | Yes | Yes | No
CC0375-ELE-COND-114 | LV/CO 90-210 North Turnups | Physical Works Complete | 2024-03-04 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-02-05 | 03-07-01 | 2024-02-09 | No | No | Not Required | [7 empty] | 86 | Overdue | 86 | Overdue | Yes | Yes | No
CC0375-ELE-COND-115 | LV/CO 90-210 East Turnups | Submitted To Client | 2024-03-04 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-08 | 03-07-01 | 2024-03-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 30 | Due | 53 | Nearly Overdue | No | No | No
CC0375-ELE-COND-116 | LV/CO 90-220 East Turnups | Physical Works Complete | 2024-03-04 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-11 | 03-07-01 | 2024-03-12 | No | No | Not Required | [7 empty] | 54 | Nearly Overdue | 54 | Nearly Overdue | Yes | Yes | No
CC0375-ELE-COND-117 | LV/CO 90-230 East Turnups | Submitted To Client | 2024-03-04 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-09 | 03-07-01 | 2024-03-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 49 | Due | 54 | Nearly Overdue | No | No | No
CC0375-ELE-COND-118 | LV/CO 01-010 to 90-110 | Submitted To Client | 2024-02-19 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-02-20 | 03-07-01 | 2024-03-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 41 | Due | 64 | Overdue | No | No | No
CC0375-ELE-COND-119 | LV/CO 90-110 to Light Pit 90-120 | Physical Works Complete | 2024-03-12 | Electrical Services | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-03-13 | 03-07-01 | 2024-03-13 | No | No | Not Required | [7 empty] | 53 | Nearly Overdue | 53 | Nearly Overdue | Yes | Yes | No
CC0375-ELE-IPIT-001 | GT01 MV Pit-01UBY01 GZ 270 | Submitted To Client | 2023-05-22 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-22 | 03-07-01 | 2024-02-25 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 59 | Nearly Overdue | 70 | Overdue | No | No | No
CC0375-ELE-IPIT-002 | GT01 MV Pit-01UBY01 GZ 421 | Physical Works Complete | 2023-05-23 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-23 | 03-07-01 | 2024-05-02 | Yes | Yes | Not Required | [7 empty] | 3 | Early | 3 | Early | No | No | No
CC0375-ELE-IPIT-003 | GT01 MV Pit-01UBY01 GZ 420 | Submitted To Client | 2023-05-30 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-30 | 03-07-01 | 2024-02-17 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 67 | Overdue | 78 | Overdue | No | No | No
CC0375-ELE-IPIT-004 | GT01 LV Pit-01UBZ01 GZ420 | Physical Works Complete | 2023-05-30 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-05 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-005 | GT01 MV Pit-01UBY01 GZ 450 | Submitted To Client | 2023-06-06 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-06 | 03-07-01 | 2024-02-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 62 | Overdue | 73 | Overdue | No | No | No
CC0375-ELE-IPIT-006 | GT01 LV Pit-01UBZ01 GZ230 | Physical Works Complete | 2023-06-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-13 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-007 | GT01 LV Pit-01UBZ01 GZ240 | Physical Works Complete | 2023-06-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-13 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-008 | GT01 LV Pit-01UBZ01 GZ250 | Physical Works Complete | 2023-06-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-13 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-009 | GT01 LV Pit-01UBZ01 GZ280 | Physical Works Complete | 2023-06-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-13 | 03-07-01 | 2024-02-25 | Yes | Yes | Not Required | [7 empty] | 70 | Overdue | 70 | Overdue | No | No | No
CC0375-ELE-IPIT-010 | GT01 LV Pit-01UBZ01 GZ320 | Physical Works Complete | 2023-06-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-13 | 03-07-01 | 2024-02-28 | Yes | Yes | Not Required | [7 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-ELE-IPIT-011 | GT01 LV Pit-01UBZ01 GZ210 | Submitted To Client | 2023-07-06 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-01 | 2024-03-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 31 | Due | 42 | Due | No | No | No
CC0375-ELE-IPIT-012 | GT01 LV Pit-01UBZ01 GZ410 | Physical Works Complete | 2023-07-07 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-10 | 03-07-01 | 2024-02-20 | Yes | Yes | Not Required | [7 empty] | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-ELE-IPIT-013 | GT01 LV Pit-01UBZ01 GZ010 | Physical Works Complete | 2023-07-10 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-13 | 03-07-01 | 2024-01-28 | Yes | Yes | Not Required | [7 empty] | 98 | Overdue | 98 | Overdue | No | No | No
CC0375-ELE-IPIT-014 | GT01 MV Pit-01UBY01 G Z210 | Physical Works Complete | 2023-07-13 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-14 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-015 | GT01 MV Pit-01UBY01 GZ 440 | Physical Works Complete | 2023-07-18 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-20 | 03-07-01 | 2024-02-22 | Yes | Yes | Not Required | [7 empty] | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-ELE-IPIT-016 | GT01 LV Pit-01UBZ01 GZ510 | Submitted To Client | 2023-07-18 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-20 | 03-07-01 | 2024-01-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 74 | Overdue | 97 | Overdue | No | No | No
CC0375-ELE-IPIT-017 | GT02 MV Pit-02UBY01 GZ 420 | Physical Works Complete | 2023-05-30 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-30 | 03-07-01 | 2024-02-29 | Yes | Yes | Not Required | [7 empty] | 66 | Overdue | 66 | Overdue | No | No | No
CC0375-ELE-IPIT-018 | GT02 MV Pit-02UBY01 GZ 450 | Physical Works Complete | 2023-05-30 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-05-30 | 03-07-01 | 2024-02-29 | Yes | Yes | Not Required | [7 empty] | 66 | Overdue | 66 | Overdue | No | No | No
CC0375-ELE-IPIT-019 | GT02 LV Pit-02UBZ01 GZ250 | Physical Works Complete | 2023-06-08 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-09 | 03-07-01 | 2024-03-06 | Yes | Yes | Not Required | [7 empty] | 60 | Overdue | 60 | Overdue | No | No | No
CC0375-ELE-IPIT-020 | GT02 LV Pit-02UBZ01 GZ280 | Physical Works Complete | 2023-06-08 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-09 | 03-07-01 | 2024-02-28 | Yes | Yes | Not Required | [7 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-ELE-IPIT-021 | GT02 LV Pit-02UBZ01 GZ240 | Physical Works Complete | 2023-06-09 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-10 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-022 | GT02 LV Pit-02UBZ01 GZ420 | Physical Works Complete | 2023-06-22 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-23 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-023 | GT02 LV Pit-02UBZ01 GZ320 | Physical Works Complete | 2023-06-26 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-27 | 03-07-01 | 2024-02-22 | Yes | Yes | Not Required | [7 empty] | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-ELE-IPIT-024 | GT02 LV Pit-02UBZ01 GZ010 | Physical Works Complete | 2023-07-07 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-01 | 2024-02-11 | Yes | Yes | Not Required | [7 empty] | 84 | Overdue | 84 | Overdue | No | No | No
CC0375-ELE-IPIT-025 | GT02 LV Pit-02UBZ01 GZ510 | Submitted To Client | 2023-07-07 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-10 | 03-07-01 | 2024-02-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-12 |  | 63 | Overdue | 86 | Overdue | No | No | No
CC0375-ELE-IPIT-026 | GT02 MV Pit-02UBY01 GZ 270 | Physical Works Complete | 2023-07-21 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-21 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-027 | GT02 MV Pit-02UBY01 GZ 210 | Physical Works Complete | 2023-07-01 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-02 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-028 | GT02 MV Pit-02UBY01 GZ 422 | Physical Works Complete | 2023-07-01 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-02 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-029 | GT02 LV Pit-02UBZ01 GZ210 | Physical Works Complete | 2023-07-01 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-02 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-030 | GT02 LV Pit-02UBZ01 GZ230 | Physical Works Complete | 2023-07-01 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-02 | 03-07-01 | 2024-04-29 | Yes | Yes | Not Required | [7 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-ELE-IPIT-031 | GT02 LV Pit-02UBZ01 GZ410 | Physical Works Complete | 2023-07-01 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-02 | 03-07-01 | 2024-02-26 | Yes | Yes | Not Required | [7 empty] | 69 | Overdue | 69 | Overdue | No | No | No
CC0375-ELE-IPIT-032 | BOP LV Pit-90UBZ01 GZ330 | Submitted To Client | 2023-06-26 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-28 | 03-07-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 129 | Overdue | 156 | Overdue | No | No | No
CC0375-ELE-IPIT-033 | BOP LV Pit-90UBZ01 GZ340 | Submitted To Client | 2023-06-26 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-28 | 03-07-01 | 2023-11-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 154 | Overdue | 165 | Overdue | No | No | No
CC0375-ELE-IPIT-034 | BOP LV Pit-90UBZ01 GZ320 | Submitted To Client | 2023-06-27 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-28 | 03-07-01 | 2023-12-11 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 119 | Overdue | 146 | Overdue | No | No | No
CC0375-ELE-IPIT-035 | BOP MV Pit-90UBY01 GZ 340 | Submitted To Client | 2023-06-28 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-06-29 | 03-07-01 | 2023-11-30 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 130 | Overdue | 157 | Overdue | No | No | No
CC0375-ELE-IPIT-036 | BOP LV Pit-90UBZ01 GZ040 | Submitted To Client | 2023-07-06 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-07 | 03-07-01 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 133 | Overdue | 160 | Overdue | No | No | No
CC0375-ELE-IPIT-037 | BOP LV Pit-90UBZ01 GZ110 | Submitted To Client | 2023-07-11 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-07-12 | 03-07-01 | 2023-11-28 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 132 | Overdue | 159 | Overdue | No | No | No
CC0375-ELE-IPIT-038 | BOP MV Pit-90UBY01 GZ 010 | Submitted To Client | 2023-09-15 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-29 | 03-07-01 | 2023-12-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 114 | Overdue | 141 | Overdue | No | No | No
CC0375-ELE-IPIT-039 | BOP MV Pit-90UBY01 GZ 020 | Submitted To Client | 2023-09-15 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-29 | 03-07-01 | 2023-12-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 114 | Overdue | 141 | Overdue | No | No | No
CC0375-ELE-IPIT-040 | BOP MV Pit-90UBY01 GZ 030 | Submitted To Client | 2023-09-15 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-29 | 03-07-01 | 2023-12-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 114 | Overdue | 141 | Overdue | No | No | No
CC0375-ELE-IPIT-041 | BOP MV Pit-90UBY01 GZ 040 | Submitted To Client | 2023-08-28 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-29 | 03-07-01 | 2023-11-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 147 | Overdue | 158 | Overdue | No | No | No
CC0375-ELE-IPIT-042 | BOP MV Pit-90UBY01 GZ 260 | Submitted To Client | 2023-08-28 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-16 | 03-07-01 | 2023-12-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 114 | Overdue | 141 | Overdue | No | No | No
CC0375-ELE-IPIT-043 | BOP MV Pit-90UBY01 GZ 300 | Submitted To Client | 2023-08-07 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-07 | 03-07-01 | 2023-12-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 133 | Overdue | 144 | Overdue | No | No | No
CC0375-ELE-IPIT-044 | BOP MV Pit-90UBY01 GZ 910 | Submitted To Client | 2023-09-15 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-16 | 03-07-01 | 2024-02-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 75 | Overdue | 86 | Overdue | No | No | No
CC0375-ELE-IPIT-045 | BOP LV Pit-90UBZ01 GZ020 | Submitted To Client | 2023-07-31 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-01 | 03-07-01 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 133 | Overdue | 160 | Overdue | No | No | No
CC0375-ELE-IPIT-046 | BOP LV Pit-90UBZ01 GZ030 | Submitted To Client | 2023-07-31 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-01 | 03-07-01 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 133 | Overdue | 160 | Overdue | No | No | No
CC0375-ELE-IPIT-047 | BOP LV Pit-90UBZ01 GZ039 | Physical Works Complete | 2023-07-31 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-01 | 03-07-01 | 2023-11-29 | Yes | Yes | Not Required | [7 empty] | 158 | Overdue | 158 | Overdue | No | No | No
CC0375-ELE-IPIT-048 | BOP LV Pit-90UBZ01 GZ210 | Physical Works Complete | 2023-10-02 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-10-03 | 03-07-01 | 2023-12-16 | Yes | Yes | Not Required | [5 empty] | 2024-03-01 |  | 76 | Overdue | 141 | Overdue | No | No | No
CC0375-ELE-IPIT-049 | BOP LV Pit-90UBZ01 GZ220 | Physical Works Complete | 2023-10-03 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-10-03 | 03-07-01 | 2023-12-14 | Yes | Yes | Not Required | [5 empty] | 2024-03-01 |  | 78 | Overdue | 143 | Overdue | No | No | No
CC0375-ELE-IPIT-050 | BOP LV Pit-90UBZ01 GZ230 | Submitted To Client | 2023-10-03 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-10-03 | 03-07-01 | 2023-12-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 116 | Overdue | 143 | Overdue | No | No | No
CC0375-ELE-IPIT-051 | BOP LV Pit-90UBZ01 GZ242 | Submitted To Client | 2023-10-02 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Jackson Smith | 2023-10-04 | 03-07-01 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 136 | Overdue | 163 | Overdue | No | No | No
CC0375-ELE-IPIT-052 | BOP LV Pit-90UBZ01 GZ262 | Submitted To Client | 2023-10-02 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Jackson Smith | 2023-10-04 | 03-07-01 | 2023-11-23 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 137 | Overdue | 164 | Overdue | No | No | No
CC0375-ELE-IPIT-053 | BOP LV Pit-90UBZ01 GZ270 | Submitted To Client | 2023-09-19 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-19 | 03-07-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 129 | Overdue | 156 | Overdue | No | No | No
CC0375-ELE-IPIT-054 | BOP LV Pit-90UBZ01 GZ300 | Physical Works Complete | 2023-09-19 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-19 | 03-07-01 | 2023-12-11 | Yes | Yes | Not Required | [7 empty] | 146 | Overdue | 146 | Overdue | No | No | No
CC0375-ELE-IPIT-055 | BOP LV Pit-90UBZ01 GZ310 | Submitted To Client | 2023-09-19 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-19 | 03-07-01 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 134 | Overdue | 145 | Overdue | No | No | No
CC0375-ELE-IPIT-056 | BOP LV Pit-90UBZ01 GZ350 | Submitted To Client | 2023-08-28 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-08-28 | 03-07-01 | 2024-01-15 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 100 | Overdue | 111 | Overdue | No | No | No
CC0375-ELE-IPIT-057 | BOP LV Pit-90UBZ01 GZ910 | Submitted To Client | 2023-09-15 | Electrical Services | Insitu Pits | INF-HSEQ CC0375-ITP-018 Conduit Pits (In-situ) | Jackson Smith | 2023-09-16 | 03-07-01 | 2024-02-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-24 |  | 70 | Overdue | 81 | Overdue | No | No | No
CC0375-FM-PIP-001 | Fire Ring Main-01SGA04AA008 - GT1 Excitation | Closed | 2023-07-18 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-07-20 | 03-01-03 | 2023-08-02 | Yes | Yes | Yes | NCR-026 | 2023-10-27 | Yes | 2023-11-07 |  | 2023-12-05 | 2023-12-18 | 125 | Overdue | 138 | Overdue | No | No | No
CC0375-FM-PIP-002 | Fire Ring Main-01SGA01BR006 - GT1 Fuel Oil | Closed | 2023-07-18 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-07-31 | 03-01-03 | 2023-08-03 | Yes | Yes | Yes | NCR-026 | 2023-10-27 | Yes | 2023-11-07 |  | 2023-12-05 | 2023-12-18 | 124 | Overdue | 137 | Overdue | No | No | No
CC0375-FM-PIP-003 | Fire Ring Main-02SGA04AA008 - GT2 Excitation | Closed | 2023-07-18 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-08-16 | 03-01-03 | 2023-08-23 | Yes | Yes | Yes | NCR-026 | 2023-10-27 | Yes | 2023-11-07 |  | 2023-12-05 | 2023-12-18 | 104 | Overdue | 117 | Overdue | No | No | No
CC0375-FM-PIP-004 | Fire Ring Main-02SGA04AA005 - GT2 Fuel Oil | Closed | 2023-07-18 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-08-25 | 03-01-03 | 2023-08-29 | Yes | Yes | Yes | NCR-026 | 2023-10-27 | Yes | 2023-11-07 |  | 2023-12-05 | 2023-12-18 | 98 | Overdue | 111 | Overdue | No | No | No
CC0375-FM-PIP-005 | Fire Ring Main-90SGA04AA003 - LV Switch Room | Physical Works Complete | 2023-09-19 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-09-25 | 03-01-03 | 2023-09-27 | No | No | Yes | NCR-026 |  | No |  |  |  |  | 221 | Overdue | 221 | Overdue | Yes | Yes | Yes
CC0375-FM-PIP-006 | Fire Ring Main-90SGA01AA002 - Switchyard | Physical Works Complete | 2023-09-27 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-09-27 | 03-01-03 | 2023-09-03 | No | No | Yes | NCR-026 |  | No |  |  |  |  | 245 | Overdue | 245 | Overdue | Yes | Yes | Yes
CC0375-FM-PIP-007 | Fire Ring Main-90SGA04AA001 - Control Room | Physical Works Complete | 2023-09-29 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-09-29 | 03-01-03 | 2023-09-03 | No | No | Yes | NCR-026 |  | No |  |  |  |  | 245 | Overdue | 245 | Overdue | Yes | Yes | Yes
CC0375-FM-PIP-008 | Fire Ring Main-01SGA01BR004 - GT1 Switchroom Sprinkler | Physical Works Complete | 2023-10-04 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-09-27 | 03-01-03 | 2023-10-03 | No | No | Yes | NCR-026 |  | No |  |  |  |  | 215 | Overdue | 215 | Overdue | Yes | Yes | Yes
CC0375-FM-PIP-009 | CC0375-FM-PIP-009 - 01SGA01BR003 - GT1 GSUT | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-11-01 | 03-01-03 | 2023-11-04 | No | No | Not Required | [7 empty] | 183 | Overdue | 183 | Overdue | Yes | Yes | No
CC0375-FM-PIP-010 | GT1 Auxiliary Plant Enclosure | Physical Works Complete | 2023-12-04 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-12-04 | 03-01-03 | 2024-02-13 | No | No | Not Required | [7 empty] | 82 | Overdue | 82 | Overdue | Yes | Yes | No
CC0375-FM-PIP-011 | CC0375-FM-PIP-011 - 02SGA01BR004 - GT2 Switchroom Sprinkler | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-10-22 | 03-01-03 | 2023-10-25 | No | No | Not Required | [7 empty] | 193 | Overdue | 193 | Overdue | Yes | Yes | No
CC0375-FM-PIP-012 | CC0375-FM-PIP-012 - 02SGA01BR009 - GT2 GSUT | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-10-21 | 03-01-03 | 2023-12-10 | No | No | Not Required | [7 empty] | 147 | Overdue | 147 | Overdue | Yes | Yes | No
CC0375-FM-PIP-013 | GT2 Auxiliary Plant Enclosure | Physical Works Complete | 2023-12-06 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-12-06 | 03-01-03 | 2024-04-06 | No | No | [8 empty] | 29 | Early | 29 | Early | Yes | Yes | No
CC0375-FM-PIP-014 | CC0375-FM-PIP-014 - East Main to Hydrant 90SGA03AA005 | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-20 | 03-01-03 | 2024-03-25 | No | No | [8 empty] | 41 | Due | 41 | Due | Yes | Yes | No
CC0375-FM-PIP-015 | East Main to Hydrant 90SGA03AA007 | Work In Progress | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-25 | 03-01-03 | [15 empty] | No | No | No
CC0375-FM-PIP-016 | CC0375-FM-PIP-016 - 90SGA01AA027 - Booster Inlet | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-02-14 | No | No | Not Required | [7 empty] | 81 | Overdue | 81 | Overdue | Yes | Yes | No
CC0375-FM-PIP-017 | CC0375-FM-PIP-017 - 90SGA01BR011 - Control and Admin Building Riser | Physical Works Complete | 2023-11-08 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-11-10 | 03-01-03 | 2024-03-26 |  |  | Yes | OMC-CIVILEX-NCRRS-000011 | 2024-02-29 | No |  | AS-BUILT-Civilex-RFID-000040 PENDING RESPONSE |  |  | 40 | Due | 40 | Due | No | No | Yes
CC0375-FM-PIP-018 | 90SGA01BR006 - Workshop Sprinkler | Physical Works Complete | 2023-11-27 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2023-11-27 | 03-01-03 | 2024-03-23 | No | No | [8 empty] | 43 | Due | 43 | Due | Yes | Yes | No
CC0375-FM-PIP-019 | GT2 SOUTH 90SGA01BR012-H1-160 | Physical Works Complete | 2024-03-01 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-02 | 03-01-03 | 2024-03-22 | [10 empty] | 44 | Due | 44 | Due | No | No | No
CC0375-FM-PIP-021 | Fire Main - GT1 South | Physical Works Complete | 2023-11-15 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers |  | 03-01-03 | 2024-04-19 | No | No | [8 empty] | 16 | Early | 16 | Early | Yes | Yes | No
CC0375-FM-PIP-022 | 01SGA01BR006 - West Central | Work In Progress | 2024-04-16 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-04-18 | 03-01-03 | [15 empty] | No | No | No
CC0375-FM-PIP-024 | CC0375-FM-PIP-024 - 90SGA01BR011 - North West Main | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-13 | 03-01-03 | 2024-02-05 | No | No | [8 empty] | 90 | Overdue | 90 | Overdue | Yes | Yes | No
CC0375-FM-PIP-025 | CC0375-FM-PIP-025 - 90SGA01BR011 - North West | Physical Works Complete | 2024-02-13 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-13 | 03-01-03 | 2024-02-09 | Yes | Yes | Not Required | [7 empty] | 86 | Overdue | 86 | Overdue | No | No | No
CC0375-FM-PIP-026 | CC0375-FM-PIP-026 - 90SGA01BR011 - South West | Physical Works Complete | 2024-02-01 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-02 | 03-01-03 | 2024-02-14 | Yes | Yes | Not Required | [7 empty] | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-FM-PIP-027 | 90SGA01BR011 - South West Corner | Physical Works Complete | 2024-04-08 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-12 | 03-01-03 | 2024-02-19 | [10 empty] | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-FM-PIP-029 | 90SGA01BR011 - South | Physical Works Complete | 2024-02-21 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-02 | 03-01-03 | 2024-03-10 | [10 empty] | 56 | Nearly Overdue | 56 | Nearly Overdue | No | No | No
CC0375-FM-PIP-033 | CC0375-FM-PIP-033 - 90SGA01BR011 - North East | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-02-14 | No | No | Yes | NCR -058 | 2024-02-29 | No |  |  |  |  | 81 | Overdue | 81 | Overdue | Yes | Yes | Yes
CC0375-FM-PIP-034 | CC0375-FM-PIP-034 - 90SGA03AA011 - North East Main | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-03-26 | No | No | Yes | Civilex-NCRRS-000011 | 2024-02-26 | No |  |  |  |  | 40 | Due | 40 | Due | Yes | Yes | Yes
CC0375-FM-PIP-035 | CC0375-FM-PIP-035 - 90SGA01BR011 - North East Main | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-03-26 | No | No | [8 empty] | 40 | Due | 40 | Due | Yes | Yes | No
CC0375-FM-PIP-036 | North South Road | Physical Works Complete | 2024-01-05 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-10 | 03-01-03 | 2024-02-15 | No | No | [8 empty] | 80 | Overdue | 80 | Overdue | Yes | Yes | No
CC0375-FM-PIP-037 | 90SGA01BR011 - South West | Physical Works Complete | 2024-02-08 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-24 | 03-01-03 | 2024-04-09 | No | No | [8 empty] | 26 | Early | 26 | Early | Yes | Yes | No
CC0375-FM-PIP-039 | CC0375-FM-PIP-023 - 90SGA01BR011 - North West Main | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-13 | 03-01-03 | 2024-02-09 | Yes | Yes | Not Required | [7 empty] | 86 | Overdue | 86 | Overdue | No | No | No
CC0375-FM-PIP-040 | CC0375-FM-PIP-038 - 90SGA01BR011 - North South Road | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-02-15 | No | No | Not Required | [7 empty] | 80 | Overdue | 80 | Overdue | Yes | Yes | No
CC0375-FM-PIP-041 | CC0375-FM-PIP-037 - North South Road | Work In Progress | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-14 | 03-01-03 |  | No | No | [12 empty] | Yes | Yes | No
CC0375-FM-PIP-104 | CC0375-PW-PIP-104 - Potable Water 1-04 | Physical Works Complete | 2024-02-14 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 03-01-03 | 2024-02-14 | No | No | Not Required | [7 empty] | 81 | Overdue | 81 | Overdue | Yes | Yes | No
CC0375-FM-PIP-118 | CC0375-PW-PIP-118 - Potable Water 1-18 | Physical Works Complete | 2024-02-01 | Fire Main | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-02 | 03-01-03 | 2024-02-14 | No | No | Not Required | [7 empty] | 81 | Overdue | 81 | Overdue | Yes | Yes | No
CC0375-GT01-FRP-001 | PI North - GT1 | Submitted To Client | 2022-11-10 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2022-11-10 | 01-01-01 | 2024-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | -226 | Early | -221 | Early | No | No | No
CC0375-GT01-FRP-002 | PI North - Transformer GT1 | Physical Works Complete | 2023-09-28 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-08 | 01-06-02 | 2023-11-18 |  |  | Not Required | [7 empty] | 169 | Overdue | 169 | Overdue | No | No | No
CC0375-GT01-FRP-009 | PI North - Circuit Breaker & EXC GT-1 | Submitted To Client | 2023-04-19 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-04-19 | 01-07-01 | 2023-11-20 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 80 | Overdue | 167 | Overdue | No | No | No
CC0375-GT01-FRP-010 | PI North - Exhaust Stack & Duct | Submitted To Client | 2023-04-14 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-04-14 | 01-03-02 | 2023-08-09 | Yes | Yes | Yes | NCR-00041 and 00044 |  | Yes | 2024-03-08 |  | 2023-11-29 |  | 112 | Overdue | 270 | Overdue | No | No | No
CC0375-GT01-FRP-011 | PI North - Fuel Gas Heater | Submitted To Client | 2023-04-18 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-04-18 | 01-04-04 | 2023-09-23 | Yes | Yes | Yes | NCR-00040 |  | Yes | 2024-03-08 |  | 2023-11-24 |  | 62 | Overdue | 225 | Overdue | No | No | No
CC0375-GT01-FRP-016 | PI North - Air Intake/Air Duct | Submitted To Client | 2023-07-08 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-07-08 | 01-07-05 | 2024-04-29 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 1 | Early | 6 | Early | No | No | No
CC0375-GT01-FRP-018-01 & 02 | Auxiliary Switchroom Foundation | Physical Works Complete | 2024-02-14 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-14 | 01-07-05 | 2024-02-28 | [10 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-GT01-FRP-018-03 | Western slab-Pedestals | Physical Works Complete | 2024-02-28 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-28 | 01-07-05 | 2024-03-09 | [10 empty] | 57 | Nearly Overdue | 57 | Nearly Overdue | No | No | No
CC0375-GT01-FRP-018-04 | Auxiliary Switchroom-GT-1-Eastern Slab-Foundation | Physical Works Complete | 2024-02-28 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-01 | 01-07-05 | 2024-03-09 | [10 empty] | 57 | Nearly Overdue | 57 | Nearly Overdue | No | No | No
CC0375-GT01-FRP-018-05 | Eastern Slab-Pedestals | Physical Works Complete | 2024-03-07 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-07 | 01-07-05 | 2024-03-10 | [10 empty] | 56 | Nearly Overdue | 56 | Nearly Overdue | No | No | No
CC0375-GT01-FRP-018-06 | Auxiliary Switchroom-GT-1-North/East Plinth | Physical Works Complete | 2024-04-04 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-04 | 01-07-05 | 2024-04-06 | [10 empty] | 29 | Early | 29 | Early | No | No | No
CC0375-GT01-FRP-020 | PI North - Lube Oil Building & Lube Oil Unit | Open | 2024-04-08 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 01-01-10 | [15 empty] | No | No | No
CC0375-GT01-FRP-022 | PI North - Aux Transformer | Submitted To Client | 2024-02-12 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-13 | 01-06-07 | 2024-03-16 | [8 empty] | 2024-04-26 |  | 41 | Due | 50 | Nearly Overdue | No | No | No
CC0375-GT01-FRP-024 | PI North - Mitsubishi Substation | Open | 2024-04-08 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 01-01-16 | [15 empty] | No | No | No
CC0375-GT01-FRP-026 | PI North - Rotor Removal | Submitted To Client | 2023-09-25 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-09-25 | 01-02-07 | 2023-10-18 | Yes | Yes | Yes | NCR-00025 |  | Yes | 2024-03-08 |  | 2023-11-27 |  | 40 | Due | 200 | Overdue | No | No | No
CC0375-GT01-FRP-028 | PI North - SFC Building | Submitted To Client | 2023-11-26 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-12-04 | 01-02-05 | 2024-02-03 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 74 | Overdue | 92 | Overdue | No | No | No
CC0375-GT01-FRP-030 | PI North - GT Fuel Oil Drain Pump and Tank | Physical Works Complete | 2023-08-07 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-08-07 | 01-01-02 | 2024-01-25 | No | No | Not Required | [7 empty] | 101 | Overdue | 101 | Overdue | Yes | Yes | No
CC0375-GT01-FRP-032 | PI North - SFC Transformer | Submitted To Client | 2023-11-23 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-25 | 01-06-06 | 2024-03-10 | No | No | Yes | NCR -060 |  | No | 2024-04-22 |  | 2024-04-22 |  | 43 | Due | 56 | Nearly Overdue | Yes | Yes | Yes
CC0375-GT01-FRP-034 | PI North - Prefab Substation | Submitted To Client | 2023-11-28 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-28 | 01-07-04 | 2023-12-18 | No | No | Not Required | [5 empty] | 2024-04-08 |  | 112 | Overdue | 139 | Overdue | Yes | Yes | No
CC0375-GT01-FRP-049- | Fin-Fan-GT-1-Staircases | Physical Works Complete | 2024-04-20 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-20 | 01-05-01 | 2024-02-16 | [10 empty] | 79 | Overdue | 79 | Overdue | No | No | No
CC0375-GT01-FRP-049-01 & 02 | PI North - Fin-Fan GT-1-Eastern Slab | Physical Works Complete | 2024-02-06 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-06 | 01-05-01 | 2024-02-23 | [10 empty] | 72 | Overdue | 72 | Overdue | No | No | No
CC0375-GT01-FRP-049-03 | PI North - Fin-Fan Eastern slab-Plinths | Physical Works Complete | 2024-02-17 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-17 | 01-05-01 | 2024-04-13 | [10 empty] | 22 | Early | 22 | Early | No | No | No
CC0375-GT01-FRP-049-04 | Fin-Fan-GT-1-Western Slab | Physical Works Complete | 2024-03-25 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-25 | 01-05-01 | 2024-04-20 | [10 empty] | 15 | Early | 15 | Early | No | No | No
CC0375-GT01-FRP-049-05 | Fon-Fan Western slab-Pedestals | Physical Works Complete | 2024-04-14 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-14 | 01-05-01 | 2024-04-20 | [10 empty] | 15 | Early | 15 | Early | No | No | No
CC0375-GT01-FRP-051 | PI North - Lube Oil Unit | Physical Works Complete | 2023-10-26 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-03-20 | 01-01-10 | 2024-04-17 | [10 empty] | 18 | Early | 18 | Early | No | No | No
CC0375-GT01-FRP-057 | PI North - C02 FF | Open | 2023-10-26 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 01-01-12 | [15 empty] | No | No | No
CC0375-GT01-FRP-062 | Gas System-Fuel Gas Filter & 17m Vent Stack-North | Work In Progress | 2023-10-26 | Gas Turbine 1 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-08 | 01-01-03 | [15 empty] | No | No | No
CC0375-GT01-FRP-063 | Gas System-Fuel Gas Filters & 17m Vent Stack-South | Work In Progress | 2024-04-24 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-20 | 02-01-03 | [15 empty] | No | No | No
CC0375-GT01-PIL-001 | PI North - GT1-Pile 01-14 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-13 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-002 | PI North - GT1-Pile 01-12 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-13 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-003 | PI North - GT1-Pile 01-10 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-13 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-004 | PI North - GT1-Pile 01-08 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-13 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-005 | PI North - GT1-Pile 01-06 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-13 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-006 | PI North - GT1-Pile 01-05 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-14 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-007 | PI North - GT1-Pile 01-03 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-14 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-008 | PI North - GT1-Pile 01-01 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-14 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-009 | PI North - GT1-Pile 01-13 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-14 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-010 | PI North - GT1-Pile 01-11 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-14 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-0100 | PI North - Exhaust Stack-Pile 10-10 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0101 | PI North - Exhaust Stack-Pile 10-08 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0102 | PI North - Exhaust Stack-Pile 10-06 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0103 | PI North - Exhaust Stack-Pile 10-20 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0104 | PI North - Exhaust Stack-Pile 10-18 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0105 | PI North - Exhaust Stack-Pile 10-16 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0106 | PI North - Exhaust Stack-Pile 10-24 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-23 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0107 | PI North - Exhaust Stack-Pile 10-09 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0108 | PI North - Exhaust Stack-Pile 10-07 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0109 | PI North - Exhaust Stack-Pile 10-19 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-011 | PI North - GT1-Pile 01-09 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-0110 | PI North - Exhaust Stack-Pile 10-17 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0111 | PI North - Exhaust Stack-Pile 10-30 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0112 | PI North - Exhaust Stack-Pile 10-27 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-24 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0113 | PI North - Exhaust Stack-Pile 10-22 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0114 | PI North - Exhaust Stack-Pile 10-29 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0115 | PI North - Exhaust Stack-Pile 10-11 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0116 | PI North - Exhaust Stack-Pile 10-28 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0117 | PI North - Exhaust Stack-Pile 10-26 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-0118 | PI North - Fin Fan Cooler/Heater GT01-Pile 11-04 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0119 | PI North - Fin Fan Cooler/Heater-Pile 11-03 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-012 | PI North - GT1-Pile 01-07 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-0120 | PI North - Fin Fan Cooler/Heater-Pile 11-02 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0121 | PI North - Fin Fan Cooler/Heater-Pile 11-01 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-30 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0122 | PI North - Fin Fan Cooler/Heater-Pile 11-08 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0123 | PI North - Fin Fan Cooler/Heater-Pile 11-07 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0124 | PI North - Fin Fan Cooler/Heater-Pile 11-06 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-0125 | PI North - Fin Fan Cooler/Heater-Pile 11-05 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-01-03 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-07-17 | 2023-07-17 | 19 | Early | 19 | Early | No | No | No
CC0375-GT01-PIL-013 | PI North - GT1-Pile 01-04 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-014 | PI North - GT1-Pile 01-02 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-015 | PI North - GT1-Pile 01-28 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-016 | PI North - GT1-Pile 01-26 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-17 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-017 | PI North - GT1-Pile 01-24 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-18 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-018 | PI North - GT1-Pile 01-22 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-18 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-019 | PI North - GT1-Pile 01-20 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-18 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-020 | PI North - GT1-Pile 01-18 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-18 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-021 | PI North - GT1-Pile 01-16 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-18 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-022 | PI North - GT1-Pile 01-27 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-19 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-023 | PI North - GT1-Pile 01-25 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-19 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-024 | PI North - GT1-Pile 01-23 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-19 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-025 | PI North - GT1-Pile 01-21 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-19 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-026 | PI North - GT1-Pile 01-19 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-19 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-027 | PI North - GT1-Pile 01-17 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-21 | 01-01-01 | 2022-12-07 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 36 | Due | 36 | Due | No | No | No
CC0375-GT01-PIL-028 | PI North - GT1-Pile 01-15 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-21 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-029 | PI North - GT1-Pile 01-42 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-25 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-030 | PI North - GT1-Pile 01-40 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-25 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-031 | PI North - GT1-Pile 01-38 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-032 | PI North - GT1-Pile 01-36 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-033 | PI North - GT1-Pile 01-34 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-034 | PI North - GT1-Pile 01-32 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-035 | PI North - GT1-Pile 01-30 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-036 | PI North - GT1-Pile 01-41 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-27 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-037 | PI North - GT1-Pile 01-56 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-28 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-038 | PI North - GT1-Pile 01-39 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-28 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-039 | PI North - GT1-Pile 01-37 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-28 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-040 | PI North - GT1-Pile 01-35 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-28 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-041 | PI North - GT1-Pile 01-33 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-28 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-042 | PI North - GT1-Pile 01-31 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-29 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-043 | PI North - GT1-Pile 01-29 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-29 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-044 | PI North - GT1-Pile 01-55 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-29 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-045 | PI North - GT1-Pile 01-54 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-31 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-046 | PI North - GT1-Pile 01-52 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-31 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-047 | PI North - GT1-Pile 01-50 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-10-31 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-048 | PI North - GT1-Pile 01-48 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-03 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-049 | PI North - GT1-Pile 01-46 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-03 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-050 | PI North - GT1-Pile 01-44 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-03 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-051 | PI North - GT1-Pile 01-53 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-03 | 01-01-01 | 2022-12-07 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 36 | Due | 36 | Due | No | No | No
CC0375-GT01-PIL-052 | PI North - GT1-Pile 01-51 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-03 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-053 | PI North - GT1-Pile 01-43 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-04 | 01-01-01 | 2022-12-07 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 36 | Due | 36 | Due | No | No | No
CC0375-GT01-PIL-054 | PI North - GT1-Pile 01-45 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-04 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-055 | PI North - GT1-Pile 01-47 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-04 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-056 | PI North - GT1-Pile 01-49 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-04 | 01-01-01 | 2022-12-06 | Yes | Yes | Yes | NCR-001 |  | Yes |  |  | 2023-01-12 | 2023-01-12 | 37 | Due | 37 | Due | No | No | No
CC0375-GT01-PIL-057 | PI North - Transformer-Pile 02-19 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-058 | PI North - Transformer-Pile 02-20 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-059 | PI North - Transformer-Pile 02-21 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-060 | PI North - Transformer-Pile 02-13 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-061 | PI North - Transformer-Pile 02-14 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-062 | PI North - Transformer-Pile 02-15 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Not Required |  |  |  |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-063 | PI North - Transformer-Pile 02-7 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-064 | PI North - Transformer-Pile 02-8 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-08 | 01-06-02 | 2022-12-08 | Yes | Yes | Not Required |  |  |  |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 329 | Overdue | 331 | Overdue | No | No | No
CC0375-GT01-PIL-065 | PI North - Transformer-Pile 02-22 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-066 | PI North - Transformer-Pile 02-23 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-067 | PI North - Transformer-Pile 02-24 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-068 | PI North - Transformer-Pile 02-16 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-069 | PI North - Transformer-Pile 02-17 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-070 | PI North - Transformer-Pile 02-18 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-071 | PI North - Transformer-Pile 02-10 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-072 | PI North - Transformer-Pile 02-11 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-073 | PI North - Transformer-Pile 02-12 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-09 | 01-06-02 | 2022-12-09 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 328 | Overdue | 330 | Overdue | No | No | No
CC0375-GT01-PIL-074 | PI North - Transformer-Pile 02-09 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-10 | 01-06-02 | 2022-12-10 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 327 | Overdue | 329 | Overdue | No | No | No
CC0375-GT01-PIL-075 | PI North - Transformer-Pile 02-06 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-16 | 01-06-02 | 2022-12-16 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 321 | Overdue | 323 | Overdue | No | No | No
CC0375-GT01-PIL-076 | PI North - Transformer-Pile 02-04 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-16 | 01-06-02 | 2022-12-16 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 321 | Overdue | 323 | Overdue | No | No | No
CC0375-GT01-PIL-077 | PI North - Transformer-Pile 02-02 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-16 | 01-06-02 | 2022-12-16 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 321 | Overdue | 323 | Overdue | No | No | No
CC0375-GT01-PIL-078 | PI North - Transformer-Pile 02-05 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-10 | 01-06-02 | 2023-03-10 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 237 | Overdue | 239 | Overdue | No | No | No
CC0375-GT01-PIL-079 | PI North - Transformer-Pile 02-03 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-10 | 01-06-02 | 2023-03-10 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 237 | Overdue | 239 | Overdue | No | No | No
CC0375-GT01-PIL-080 | PI North - Transformer-Pile 02-01 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-10 | 01-06-02 | 2023-03-10 | Yes | Yes | Yes | NCR-019 |  | Yes |  | Pending PIT test | 2023-11-02 | 2023-11-04 | 237 | Overdue | 239 | Overdue | No | No | No
CC0375-GT01-PIL-081 | PI North - GCB & EXC-GT-1-Pile 09-03 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-07-01 | 2023-03-31 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 138 | Overdue | 217 | Overdue | No | No | No
CC0375-GT01-PIL-082 | PI North - GCB & EXC-GT-1-Pile 09-07 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-31 | 01-07-01 | 2023-03-31 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 138 | Overdue | 217 | Overdue | No | No | No
CC0375-GT01-PIL-083 | PI North - GCB & EXC-GT-1-Pile 09-02 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-01 | 01-07-01 | 2023-04-01 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 137 | Overdue | 216 | Overdue | No | No | No
CC0375-GT01-PIL-084 | PI North - GCB & EXC-GT-1-Pile 09-04 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-01 | 01-07-01 | 2023-04-01 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 137 | Overdue | 216 | Overdue | No | No | No
CC0375-GT01-PIL-085 | PI North - GCB & EXC-GT-1-Pile 09-06 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-01 | 01-07-01 | 2023-04-01 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 137 | Overdue | 216 | Overdue | No | No | No
CC0375-GT01-PIL-086 | PI North - GCB & EXC-GT-1-Pile 09-01 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-01 | 01-07-01 | 2023-04-01 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 137 | Overdue | 216 | Overdue | No | No | No
CC0375-GT01-PIL-087 | PI North - GCB & EXC-GT-1-Pile 09-05 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-04-04 | 01-07-01 | 2023-04-04 | Yes | Yes | Yes | NCR-015 |  | Yes |  |  | 2023-08-16 | 2023-11-03 | 134 | Overdue | 213 | Overdue | No | No | No
CC0375-GT01-PIL-088 | PI North - Exhaust Stack GT1-Pile 10-05 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-16 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-089 | PI North - Exhaust Stack-Pile 10-03 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-16 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-090 | PI North - Exhaust Stack-Pile 10-01 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-16 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-091 | PI North - Exhaust Stack-Pile 10-15 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-16 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-092 | PI North - Exhaust Stack-Pile 10-13 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-16 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-093 | PI North - Exhaust Stack-Pile 10-14 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-094 | PI North - Exhaust Stack-Pile 10-12 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-095 | PI North - Exhaust Stack-Pile 10-25 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-096 | PI North - Exhaust Stack-Pile 10-23 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-097 | PI North - Exhaust Stack-Pile 10-21 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-098 | PI North - Exhaust Stack-Pile 10-02 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT01-PIL-099 | PI North - Exhaust Stack-Pile 10-04 | Closed | 2022-10-10 | Gas Turbine 1 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-03-22 | 01-03-02 | 2023-06-28 | Yes | Yes | Yes | NCR-008 |  | Yes |  |  | 2023-08-01 | 2023-08-01 | 34 | Due | 34 | Due | No | No | No
CC0375-GT02-FRP-003 | PI South - GT2 | Physical Works Complete | 2022-12-12 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2022-12-12 | 02-01-01 | 2023-09-11 | Yes | No | Not Required | [7 empty] | 237 | Overdue | 237 | Overdue | No | Yes | No
CC0375-GT02-FRP-004 | PI South - Transformer GT2 | Work In Progress | 2023-10-28 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-10-28 | 02-06-02 | 2023-10-31 | Yes | No | Not Required | [7 empty] | 187 | Overdue | 187 | Overdue | No | Yes | No
CC0375-GT02-FRP-013 | PI South - Circuit Breaker & EXC GT-2 | Submitted To Client | 2023-09-08 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-09-08 | 02-07-01 | 2024-01-17 | Yes | Yes | Not Required | [5 empty] | 2024-02-19 |  | 33 | Due | 109 | Overdue | No | No | No
CC0375-GT02-FRP-014 | PI South - Exhaust Stack & Duct | Submitted To Client | 2023-06-20 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-06-21 | 02-03-02 | 2023-09-13 | Yes | Yes | Yes | NCR-00031 & 00037 |  | Yes | 2024-03-08 |  | 2023-11-23 |  | 71 | Overdue | 235 | Overdue | No | No | No
CC0375-GT02-FRP-015 | PI South - Fuel Gas Heater | Submitted To Client | 2023-09-08 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-09-08 | 02-01-03 | 2023-11-02 | Yes | No | Yes | NCR-00032 |  | Yes | 2024-03-08 |  | 2024-02-19 |  | 109 | Overdue | 185 | Overdue | No | Yes | No
CC0375-GT02-FRP-017 | PI South - Air Intake/Air Duct-Blinding | Submitted To Client | 2023-08-21 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-08-21 | 02-04-04 | 2023-08-23 | Yes | No | Not Required | [5 empty] | 2024-05-01 |  | 252 | Overdue | 256 | Overdue | No | Yes | No
CC0375-GT02-FRP-019 | PI South - Aux Switchroom | Open | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 02-07-05 | [15 empty] | No | No | No
CC0375-GT02-FRP-021 | PI South - Lube Oil Building & Lube Oil Unit | Open | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 02-01-10 | [15 empty] | No | No | No
CC0375-GT02-FRP-023 | PI South - Aux Transformer | Submitted To Client | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-02-13 | 02-06-07 | 2024-03-16 | [8 empty] | 2024-04-26 |  | 41 | Due | 50 | Nearly Overdue | No | No | No
CC0375-GT02-FRP-025 | PI South - Mitsubishi Substation | Open | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 02-01-16 | [15 empty] | No | No | No
CC0375-GT02-FRP-027 | PI South - Rotor Removal | Submitted To Client | 2023-10-18 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-10-18 | 02-02-07 | 2023-11-13 | Yes | No | Not Required | [5 empty] | 2024-04-05 |  | 144 | Overdue | 174 | Overdue | No | Yes | No
CC0375-GT02-FRP-029 | PI South - SFC Building | Submitted To Client | 2023-12-09 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-12-09 | 02-02-05 | 2024-01-20 | Yes | Yes | Not Required | NCR-075 |  |  |  |  | 2024-04-09 |  | 80 | Overdue | 106 | Overdue | No | No | No
CC0375-GT02-FRP-031 | PI South - GT Fuel Oil Drain Pump and Tank | Submitted To Client | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-08 | 02-01-02 | 2024-03-22 | [8 empty] | 2024-04-29 |  | 38 | Due | 44 | Due | No | No | No
CC0375-GT02-FRP-033 | PI South - SFC Transformer | Submitted To Client | 2024-01-08 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-01-08 | 02-06-06 | 2024-01-24 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 89 | Overdue | 102 | Overdue | No | No | No
CC0375-GT02-FRP-035 | PI South - Prefab Substation | Closed | 2023-11-18 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-18 | 02-07-04 | 2023-11-22 | No | No | Not Required | [5 empty] | 2024-02-27 | 2024-04-05 | 97 | Overdue | 135 | Overdue | Yes | Yes | No
CC0375-GT02-FRP-050 | PI South - Cooling System | Physical Works Complete | 2023-10-26 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-30 | 02-05-01 | 2023-12-05 | [10 empty] | 152 | Overdue | 152 | Overdue | No | No | No
CC0375-GT02-FRP-052 | PI South - Lube Oil Unit | Open | 2024-04-08 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar |  | 02-01-10 | [15 empty] | No | No | No
CC0375-GT02-FRP-056 | PI South - C02 FF | Closed | 2023-11-19 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-11-19 | 02-01-12 | 2023-11-24 | Yes | Yes | Not Required | [5 empty] | 2024-03-12 | 2024-04-05 | 109 | Overdue | 133 | Overdue | No | No | No
CC0375-GT02-FRP-063 | Gas System-Fuel Gas Filters & 17m Vent Stack-South | Work In Progress | 2024-04-24 | Gas Turbine 2 | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2024-04-20 | 02-01-03 | [15 empty] | No | No | No
CC0375-GT02-PIL-001 | PI South - GT2-Pile 03-14 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-07 | 02-01-01 | 2022-11-07 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 98 | Overdue | 98 | Overdue | No | No | No
CC0375-GT02-PIL-002 | PI South - GT2-Pile 03-12 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-003 | PI South - GT2-Pile 03-10 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-004 | PI South - GT2-Pile 03-08 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-005 | PI South - GT2-Pile 03-06 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-006 | PI South - GT2-Pile 03-04 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-007 | PI South - GT2-Pile 03-02 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-008 | PI South - GT2-Pile 03-28 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-08 | 02-01-01 | 2022-11-08 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 97 | Overdue | 97 | Overdue | No | No | No
CC0375-GT02-PIL-009 | PI South - GT2-Pile 03-13 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-010 | PI South - GT2-Pile 03-11 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-0100 | PI South - Exhaust Stack-GT-2-Pile 14-09 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-0101 | PI South - Exhaust Stack-GT-2-Pile 14-07 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-0102 | PI South - Exhaust Stack-GT-2-Pile 14-27 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-0103 | PI South - Exhaust Stack-GT-2-Pile 14-26 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-19 | 02-03-02 | 2023-05-19 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 70 | Overdue | 171 | Overdue | No | No | No
CC0375-GT02-PIL-0104 | PI South - Exhaust Stack-GT-2-Pile 14-24 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-19 | 02-03-02 | 2023-05-19 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 70 | Overdue | 171 | Overdue | No | No | No
CC0375-GT02-PIL-0105 | PI South - Exhaust Stack-GT-2-Pile 14-22 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-19 | 02-03-02 | 2023-05-19 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 70 | Overdue | 171 | Overdue | No | No | No
CC0375-GT02-PIL-0106 | PI South - Exhaust Stack-GT-2-Pile 14-30 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-0107 | PI South - Exhaust Stack-GT-2-Pile 14-28 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-0108 | PI South - Exhaust Stack-GT-2-Pile 14-20 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-0109 | PI South - Exhaust Stack-GT-2-Pile 14-18 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-011 | PI South - GT2-Pile 03-09 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-0110 | PI South - Exhaust Stack-GT-2-Pile 14-16 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-0111 | PI South - Exhaust Stack-GT-2-Pile 14-14 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-23 | 02-03-02 | 2023-05-23 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 66 | Overdue | 167 | Overdue | No | No | No
CC0375-GT02-PIL-0112 | PI South - Exhaust Stack-GT-2-Pile 14-12 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0113 | PI South - Exhaust Stack-GT-2-Pile 14-10 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0114 | PI South - Exhaust Stack-GT-2-Pile 14-08 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0115 | PI South - Exhaust Stack-GT-2-Pile 14-06 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0116 | PI South - Exhaust Stack-GT-2-Pile 14-04 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0117 | PI South - Exhaust Stack-GT-2-Pile 14-02 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-24 | 02-03-02 | 2023-05-24 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 65 | Overdue | 166 | Overdue | No | No | No
CC0375-GT02-PIL-0118 | PI South - Fin Fan Cooler/Heater GT2-Pile 15-08 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-12 | 02-01-03 | 2023-05-12 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 132 | Overdue | 200 | Overdue | No | No | No
CC0375-GT02-PIL-0119 | PI South - Fin Fan Cooler/Heater-Pile 15-07 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-12 | 02-01-03 | 2023-05-12 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 132 | Overdue | 200 | Overdue | No | No | No
CC0375-GT02-PIL-012 | PI South - GT2-Pile 03-07 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-0120 | PI South - Fin Fan Cooler/Heater-Pile 15-06 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-12 | 02-01-03 | 2023-05-12 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 132 | Overdue | 200 | Overdue | No | No | No
CC0375-GT02-PIL-0121 | PI South - Fin Fan Cooler/Heater-Pile 15-05 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-12 | 02-01-03 | 2023-05-12 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 132 | Overdue | 200 | Overdue | No | No | No
CC0375-GT02-PIL-0122 | PI South - Fin Fan Cooler/Heater-Pile 15-04 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-13 | 02-01-03 | 2023-05-13 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 131 | Overdue | 199 | Overdue | No | No | No
CC0375-GT02-PIL-0123 | PI South - Fin Fan Cooler/Heater-Pile 15-03 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-13 | 02-01-03 | 2023-05-13 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 131 | Overdue | 199 | Overdue | No | No | No
CC0375-GT02-PIL-0124 | PI South - Fin Fan Cooler/Heater-Pile 15-02 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-13 | 02-01-03 | 2023-05-13 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 131 | Overdue | 199 | Overdue | No | No | No
CC0375-GT02-PIL-0125 | PI South - Fin Fan Cooler/Heater-Pile 15-01 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-15 | 02-01-03 | 2023-05-15 | Yes | Yes | Yes | NCR-020 |  | Yes |  |  | 2023-09-21 | 2023-11-28 | 129 | Overdue | 197 | Overdue | No | No | No
CC0375-GT02-PIL-013 | PI South - GT2-Pile 03-05 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-014 | PI South - GT2-Pile 03-03 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-015 | PI South - GT2-Pile 03-01 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-09 | 02-01-01 | 2022-11-09 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 96 | Overdue | 96 | Overdue | No | No | No
CC0375-GT02-PIL-016 | PI South - GT2-Pile 03-26 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-017 | PI South - GT2-Pile 03-24 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-018 | PI South - GT2-Pile 03-22 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-019 | PI South - GT2-Pile 03-20 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-020 | PI South - GT2-Pile 03-18 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-021 | PI South - GT2-Pile 03-16 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-10 | 02-01-01 | 2022-11-10 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 95 | Overdue | 95 | Overdue | No | No | No
CC0375-GT02-PIL-022 | PI South - GT2-Pile 03-42 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-023 | PI South - GT2-Pile 03-27 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-024 | PI South - GT2-Pile 03-25 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-025 | PI South - GT2-Pile 03-23 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-026 | PI South - GT2-Pile 03-21 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-027 | PI South - GT2-Pile 03-19 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-028 | PI South - GT2-Pile 03-17 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-24 | 02-01-01 | 2022-11-24 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 81 | Overdue | 81 | Overdue | No | No | No
CC0375-GT02-PIL-029 | PI South - GT2-Pile 03-15 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-25 | 02-01-01 | 2022-11-25 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 80 | Overdue | 80 | Overdue | No | No | No
CC0375-GT02-PIL-030 | PI South - GT2-Pile 03-41 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-25 | 02-01-01 | 2022-11-25 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 80 | Overdue | 80 | Overdue | No | No | No
CC0375-GT02-PIL-031 | PI South - GT2-Pile 03-39 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-25 | 02-01-01 | 2022-11-25 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 80 | Overdue | 80 | Overdue | No | No | No
CC0375-GT02-PIL-032 | PI South - GT2-Pile 03-37 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-033 | PI South - GT2-Pile 03-56 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-034 | PI South - GT2-Pile 03-40 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-035 | PI South - GT2-Pile 03-35 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-036 | PI South - GT2-Pile 03-33 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-037 | PI South - GT2-Pile 03-31 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-038 | PI South - GT2-Pile 03-29 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-039 | PI South - GT2-Pile 03-55 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-29 | 02-01-01 | 2022-11-29 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 76 | Overdue | 76 | Overdue | No | No | No
CC0375-GT02-PIL-040 | PI South - GT2-Pile 03-54 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-041 | PI South - GT2-Pile 03-38 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-042 | PI South - GT2-Pile 03-36 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-043 | PI South - GT2-Pile 03-34 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-044 | PI South - GT2-Pile 03-32 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-045 | PI South - GT2-Pile 03-30 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-046 | PI South - GT2-Pile 03-53 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-11-30 | 02-01-01 | 2022-11-30 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 75 | Overdue | 75 | Overdue | No | No | No
CC0375-GT02-PIL-047 | PI South - GT2-Pile 03-52 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-01 | 02-01-01 | 2022-12-01 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 74 | Overdue | 74 | Overdue | No | No | No
CC0375-GT02-PIL-048 | PI South - GT2-Pile 03-50 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-01 | 02-01-01 | 2022-12-01 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 74 | Overdue | 74 | Overdue | No | No | No
CC0375-GT02-PIL-049 | PI South - GT2-Pile 03-48 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-01 | 02-01-01 | 2022-12-01 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 74 | Overdue | 74 | Overdue | No | No | No
CC0375-GT02-PIL-050 | PI South - GT2-Pile 03-46 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-01 | 02-01-01 | 2022-12-01 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 74 | Overdue | 74 | Overdue | No | No | No
CC0375-GT02-PIL-051 | PI South - GT2-Pile 03-44 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-01 | 02-01-01 | 2022-12-01 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 74 | Overdue | 74 | Overdue | No | No | No
CC0375-GT02-PIL-052 | PI South - GT2-Pile 03-51 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-02 | 02-01-01 | 2022-12-02 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-GT02-PIL-053 | PI South - GT2-Pile 03-49 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-02 | 02-01-01 | 2022-12-02 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-GT02-PIL-054 | PI South - GT2-Pile 03-47 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-02 | 02-01-01 | 2022-12-02 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-GT02-PIL-055 | PI South - GT2-Pile 03-45 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-02 | 02-01-01 | 2022-12-02 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-GT02-PIL-056 | PI South - GT2-Pile 03-43 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-02 | 02-01-01 | 2022-12-02 | Yes | Yes | Yes | NCR-002 |  | Yes |  |  | 2023-02-13 | 2023-02-13 | 73 | Overdue | 73 | Overdue | No | No | No
CC0375-GT02-PIL-057 | PI South - Transformer-Pile 04-22 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-10 | 02-06-02 | 2022-12-10 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 342 | Overdue | 353 | Overdue | No | No | No
CC0375-GT02-PIL-058 | PI South - Transformer-Pile 04-23 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-10 | 02-06-02 | 2022-12-10 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 342 | Overdue | 353 | Overdue | No | No | No
CC0375-GT02-PIL-059 | PI South - Transformer-Pile 04-24 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-10 | 02-06-02 | 2022-12-10 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 342 | Overdue | 353 | Overdue | No | No | No
CC0375-GT02-PIL-060 | PI South - Transformer-Pile 04-19 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-12 | 02-06-02 | 2022-12-12 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 340 | Overdue | 351 | Overdue | No | No | No
CC0375-GT02-PIL-061 | PI South - Transformer-Pile 04-20 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-12 | 02-06-02 | 2022-12-12 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 340 | Overdue | 351 | Overdue | No | No | No
CC0375-GT02-PIL-062 | PI South - Transformer-Pile 04-21 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-12 | 02-06-02 | 2022-12-12 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 340 | Overdue | 351 | Overdue | No | No | No
CC0375-GT02-PIL-063 | PI South - Transformer-Pile 04-13 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-12 | 02-06-02 | 2022-12-12 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 340 | Overdue | 351 | Overdue | No | No | No
CC0375-GT02-PIL-064 | PI South - Transformer-Pile 04-14 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-12 | 02-06-02 | 2022-12-12 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 340 | Overdue | 351 | Overdue | No | No | No
CC0375-GT02-PIL-065 | PI South - Transformer-Pile 04-15 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-066 | PI South - Transformer-Pile 04-07 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-067 | PI South - Transformer-Pile 04-08 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-068 | PI South - Transformer-Pile 04-09 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-069 | PI South - Transformer-Pile 04-16 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-070 | PI South - Transformer-Pile 04-17 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-13 | 02-06-02 | 2022-12-13 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 339 | Overdue | 350 | Overdue | No | No | No
CC0375-GT02-PIL-071 | PI South - Transformer-Pile 04-18 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-072 | PI South - Transformer-Pile 04-10 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-073 | PI South - Transformer-Pile 04-11 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-074 | PI South - Transformer-Pile 04-12 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-075 | PI South - Transformer-Pile 04-05 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-076 | PI South - Transformer-Pile 04-06 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-077 | PI South - Transformer-Pile 04-04 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-078 | PI South - Transformer-Pile 04-02 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2022-12-14 | 02-06-02 | 2022-12-14 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 338 | Overdue | 349 | Overdue | No | No | No
CC0375-GT02-PIL-079 | PI South - Transformer-Pile 04-01 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-06-02 | 2023-05-16 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 185 | Overdue | 196 | Overdue | No | No | No
CC0375-GT02-PIL-080 | PI South - Transformer-Pile 04-03 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-06-02 | 2023-05-16 | Yes | Yes | Yes | NCR-033 |  | Yes |  |  | 2023-11-17 | 2023-11-28 | 185 | Overdue | 196 | Overdue | No | No | No
CC0375-GT02-PIL-081 | PI South - GCB & EXC-GT-2-Pile 13-03 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-07-01 | 2023-05-16 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 121 | Overdue | 146 | Overdue | No | No | No
CC0375-GT02-PIL-082 | PI South - GCB & EXC-GT-2-Pile 13-07 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-07-01 | 2023-05-16 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 121 | Overdue | 146 | Overdue | No | No | No
CC0375-GT02-PIL-083 | PI South - GCB & EXC-GT-2-Pile 13-02 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-07-01 | 2023-05-16 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 121 | Overdue | 146 | Overdue | No | No | No
CC0375-GT02-PIL-084 | PI South - GCB & EXC-GT-2-Pile 13-04 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-07-01 | 2023-05-16 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 121 | Overdue | 146 | Overdue | No | No | No
CC0375-GT02-PIL-085 | PI South - GCB & EXC-GT-2-Pile 13-06 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-16 | 02-07-01 | 2023-05-16 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 121 | Overdue | 146 | Overdue | No | No | No
CC0375-GT02-PIL-086 | PI South - GCB & EXC-GT-2-Pile 13-01 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-07-01 | 2023-05-17 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 120 | Overdue | 145 | Overdue | No | No | No
CC0375-GT02-PIL-087 | PI South - GCB & EXC-GT-2-Pile 13-05 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-07-01 | 2023-05-17 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-10-09 | 120 | Overdue | 145 | Overdue | No | No | No
CC0375-GT02-PIL-088 | PI South - Exhaust Stack-GT-2-Pile 14-05 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-15 | 02-03-02 | 2023-05-15 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 74 | Overdue | 175 | Overdue | No | No | No
CC0375-GT02-PIL-089 | PI South - Exhaust Stack-GT-2-Pile 14-03 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-15 | 02-03-02 | 2023-05-15 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 74 | Overdue | 175 | Overdue | No | No | No
CC0375-GT02-PIL-090 | PI South - Exhaust Stack-GT-2-Pile 14-01 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-15 | 02-03-02 | 2023-05-15 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 74 | Overdue | 175 | Overdue | No | No | No
CC0375-GT02-PIL-091 | PI South - Exhaust Stack-GT-2-Pile 14-29 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-03-02 | 2023-05-17 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 72 | Overdue | 173 | Overdue | No | No | No
CC0375-GT02-PIL-092 | PI South - Exhaust Stack-GT-2-Pile 14-25 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-03-02 | 2023-05-17 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 72 | Overdue | 173 | Overdue | No | No | No
CC0375-GT02-PIL-093 | PI South - Exhaust Stack-GT-2-Pile 14-23 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-03-02 | 2023-05-17 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 72 | Overdue | 173 | Overdue | No | No | No
CC0375-GT02-PIL-094 | PI South - Exhaust Stack-GT-2-Pile 14-21 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-03-02 | 2023-05-17 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 72 | Overdue | 173 | Overdue | No | No | No
CC0375-GT02-PIL-095 | PI South - Exhaust Stack-GT-2-Pile 14-19 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-17 | 02-03-02 | 2023-05-17 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 72 | Overdue | 173 | Overdue | No | No | No
CC0375-GT02-PIL-096 | PI South - Exhaust Stack-GT-2-Pile 14-17 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-097 | PI South - Exhaust Stack-GT-2-Pile 14-15 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 | 2023-11-06 | Yes |  |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-098 | PI South - Exhaust Stack-GT-2-Pile 14-13 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-GT02-PIL-099 | PI South - Exhaust Stack-GT-2-Pile 14-11 | Closed | 2022-10-10 | Gas Turbine 2 | CFA Piling | INF-HSEQ CC0375-ITP-014 Piles with Checklist | Yash Bhavsar | 2023-05-18 | 02-03-02 | 2023-05-18 | Yes | Yes | Yes | NCR-014 |  | Yes | 2023-11-06 |  | 2023-07-28 | 2023-11-06 | 71 | Overdue | 172 | Overdue | No | No | No
CC0375-KNSS-EWK-001 |  | Work In Progress | 2024-01-16 | Kurri North Substation | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor | 2024-01-30 | [16 empty] | No | No | No
CC0375-KNSS-FRP-001 | KNSS South Yard and West walkway AC plinths | Physical Works Complete | 2023-12-07 | Kurri North Substation | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Oliver Pryor | 2023-12-07 |  | 2023-12-11 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 59 | Nearly Overdue | 146 | Overdue | No | No | No
CC0375-KNSS-FRP-002 | KNSS Kerb and Driveway Layback | Physical Works Complete | 2024-01-18 | Kurri North Substation | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Oliver Pryor | 2024-01-18 |  | 2024-01-22 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 17 | Early | 104 | Overdue | No | No | No
CC0375-KNSS-PAV-0001 | KNSS Carpark Pavement | Physical Works Complete | 2024-02-05 | Kurri North Substation | Earthworks | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-01-09 |  | 2024-01-29 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 10 | Early | 97 | Overdue | No | No | No
CC0375-LS-COND-001 | KNSS | Work In Progress | 2024-02-21 | Light and Security | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2023-10-01 | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-COND-002 | BOP North | Work In Progress | 2024-02-21 | Light and Security | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo | 2024-02-15 | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-COND-003 | BOP South | Open | 2024-02-21 | Light and Security | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-COND-004 | GT1 | Open | 2024-02-21 | Light and Security | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-COND-005 | GT2 | Open | 2024-02-21 | Light and Security | Conduits | INF-HSEQ CC0375-ITP-008 Conduit and Pit Installation & Checklist | Vincent Foo |  | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-FT-001 | Light Pole 90-190 & 90-200 Footings | Work In Progress | 2024-02-21 | Light and Security | Footings | INF-HSEQ CC0375-ITP-023 Light & Security Pole Foundations | Vincent Foo | 2024-02-21 | 03-07-01 | [15 empty] | No | No | No
CC0375-LS-FT-002 | LP 90-010 & 90-020 Footi ngs | Work In Progress | 2024-03-14 | Light and Security | Footings | INF-HSEQ CC0375-ITP-023 Light & Security Pole Foundations | Vincent Foo | 2024-03-14 | 03-07-01 | [15 empty] | No | No | No
CC0375-OW-IPIT-001 | Insitu Pit-OW025-1 | Closed | 2023-06-13 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-06-14 | 04-08-01 | 2023-06-22 | Yes | Yes | Not Required | [5 empty] | 2024-02-20 | 2024-03-01 | 243 | Overdue | 253 | Overdue | No | No | No
CC0375-OW-IPIT-002 | Insitu Pit-OW25-02 | Physical Works Complete | 2023-06-30 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-07-01 | 04-08-01 | 2024-02-25 | No | No | Not Required | [7 empty] | 70 | Overdue | 70 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-003 | Insitu Pit-OW01-11 | Work In Progress | 2023-06-14 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-06-15 | 04-08-01 | 2023-06-30 | No | No | Not Required | [7 empty] | 310 | Overdue | 310 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-004 | Insitu Pit-OW07-02 | Physical Works Complete | 2023-07-07 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-07-07 | 04-08-01 | 2024-02-18 | No | No | Not Required | [7 empty] | 77 | Overdue | 77 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-005 | Insitu Pit-OW12-01 | Closed | 2023-07-23 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-07-23 | 04-08-01 | 2023-08-07 | Yes | Yes | Not Required | [5 empty] | 2024-02-20 | 2024-03-01 | 197 | Overdue | 207 | Overdue | No | No | No
CC0375-OW-IPIT-006 | Insitu Pit-OW24-01 | Work In Progress | 2023-07-14 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-07-15 | 04-08-01 | 2023-08-10 | No | No | Not Required | [7 empty] | 269 | Overdue | 269 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-007 | Insitu Pit-OW03-01 | Work In Progress | 2023-09-07 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-09-08 | 04-08-01 | 2023-09-21 | No | No | Not Required | [7 empty] | 227 | Overdue | 227 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-008 | Insitu Pit-OW04-02 | Work In Progress | 2023-12-13 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-12-13 | 04-08-01 | 2023-11-08 | [10 empty] | 179 | Overdue | 179 | Overdue | No | No | No
CC0375-OW-IPIT-009 | Insitu Pit-OW04-03 | Work In Progress | 2023-12-13 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-12-13 | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-IPIT-010 | Insitu Pit-OW04-04 | Work In Progress | 2023-12-13 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-12-13 | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-IPIT-011 | Insitu Pit-OW11-01 | Work In Progress | 2023-09-05 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-09-05 | 04-08-01 | 2023-09-16 | No | No | Not Required | [7 empty] | 232 | Overdue | 232 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-012 | Insitu Pit-OW30-03 | Work In Progress | 2023-08-22 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-08-23 | 04-08-01 | 2023-09-01 | No | No | Not Required | [7 empty] | 247 | Overdue | 247 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-013 | Insitu Pit-OW30-02 | Work In Progress | 2023-08-21 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-08-22 | 04-08-01 | 2023-08-30 | No | No | Not Required | [7 empty] | 249 | Overdue | 249 | Overdue | Yes | Yes | No
CC0375-OW-IPIT-014 | Insitu Pit OW42-01 | Work In Progress | 2023-11-01 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-11-01 | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-IPIT-015 | Insitu Pit-OW19-02 | Work In Progress | 2023-10-02 | Oily Water Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-10-04 | 04-08-01 | 2023-11-10 | No | No | Not Required | [7 empty] | 177 | Overdue | 177 | Overdue | Yes | Yes | No
CC0375-OW-PIP-001 | O20-03 to O20-05 | Physical Works Complete | 2023-06-08 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-13 | 04-08-01 | 2023-06-14 | No | No | Not Required | [7 empty] | 326 | Overdue | 326 | Overdue | Yes | Yes | No
CC0375-OW-PIP-002 | O20-02 to O20-03 | Physical Works Complete | 2023-06-08 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-13 | 04-08-01 | 2023-06-14 | No | No | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  |  |  | 326 | Overdue | 326 | Overdue | Yes | Yes | No
CC0375-OW-PIP-003 | O01-11 to O25-01 | Closed | 2023-06-08 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-13 | 04-08-01 | 2023-06-20 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 212 | Overdue | 224 | Overdue | No | No | No
CC0375-OW-PIP-004 | O25-01 to O02-01, O25-02, O26-01 & O40-01 | Physical Works Complete | 2023-10-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-15 | 04-08-01 | 2023-11-10 | No | No | Not Required | [7 empty] | 177 | Overdue | 177 | Overdue | Yes | Yes | No
CC0375-OW-PIP-005 | O08-02 to O14-01 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-09 | 04-08-01 | 2023-10-13 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 178 | Overdue | 192 | Overdue | No | No | No
CC0375-OW-PIP-006 | O14-01 to O15-01 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-13 | 04-08-01 | 2023-10-17 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 174 | Overdue | 188 | Overdue | No | No | No
CC0375-OW-PIP-007 | O01-03 to O04-01 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-18 | 04-08-01 | 2023-09-29 | Yes | Yes | Not Required | [5 empty] | 2024-02-22 | 2024-02-27 | 146 | Overdue | 151 | Overdue | No | No | No
CC0375-OW-PIP-008 | O04-01 to O30-01 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-29 | 04-08-01 | 2023-10-03 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 188 | Overdue | 202 | Overdue | No | No | No
CC0375-OW-PIP-009 | O08-05 to O08-06 | Submitted To Client | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-23 | 04-08-01 | 2023-06-28 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 310 | Overdue | 312 | Overdue | No | No | No
CC0375-OW-PIP-010 | O08-06 to O08-07 | Closed | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-28 | 04-08-01 | 2023-07-03 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-11-08 | 2023-12-19 | 128 | Overdue | 169 | Overdue | No | No | No
CC0375-OW-PIP-011 | O08-07 to O08-08 | Closed | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-03 | 04-08-01 | 2023-07-06 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-12-20 | 2024-01-16 | 167 | Overdue | 194 | Overdue | No | No | No
CC0375-OW-PIP-012 | O08-08 to O06-01 | Physical Works Complete | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-06 | 04-08-01 | 2023-07-08 | No | No | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  |  |  | 302 | Overdue | 302 | Overdue | Yes | Yes | No
CC0375-OW-PIP-013 | O06-01 to O06-02, O09-01, O33-01, O41-01 | Physical Works Complete | 2023-10-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-24 | 04-08-01 | 2023-11-20 | No | No | Not Required | [7 empty] | 167 | Overdue | 167 | Overdue | Yes | Yes | No
CC0375-OW-PIP-014 | O08-06 to O16-02 | Closed | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-09 | 04-08-01 | 2023-07-12 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 190 | Overdue | 202 | Overdue | No | No | No
CC0375-OW-PIP-015 | O08-07 to O31-02 | Physical Works Complete | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-08 | 04-08-01 | 2023-07-08 | No | No | Not Required | [7 empty] | 302 | Overdue | 302 | Overdue | Yes | Yes | No
CC0375-OW-PIP-016 | O08-02 to O08-03 | Physical Works Complete | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-02 | 04-08-01 | 2023-08-08 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 271 | Overdue | 271 | Overdue | Yes | Yes | No
CC0375-OW-PIP-017 | O08-03 to O08-04 | Submitted To Client | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-08 | 04-08-01 | 2023-08-20 | Yes | Yes | Yes | NCR-034 |  | Yes | 2024-03-08 |  | 2024-05-03 |  | 257 | Overdue | 259 | Overdue | No | No | No
CC0375-OW-PIP-018 | O08-04 to O08-05 | Submitted To Client | 2023-10-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-14 | 04-08-01 | 2023-11-20 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 165 | Overdue | 167 | Overdue | No | No | No
CC0375-OW-PIP-019 | O08-04 to O23-01 | Closed | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-22 | 04-08-01 | 2023-08-27 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 225 | Overdue | 239 | Overdue | No | No | No
CC0375-OW-PIP-020 | O24-03 to O24-01 | Physical Works Complete | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2024-02-20 | 04-08-01 | 2024-02-25 | No | No | Not Required | [7 empty] | 70 | Overdue | 70 | Overdue | Yes | Yes | No
CC0375-OW-PIP-021 | O17-01 to O20-02 | Closed | 2023-06-23 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-27 | 04-08-01 | 2023-11-29 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 71 | Overdue | 84 | Overdue | No | No | No
CC0375-OW-PIP-022 | O01-03 to O01-04 | Physical Works Complete | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-13 | 04-08-01 | 2023-07-20 | No | No | Not Required | [7 empty] | 290 | Overdue | 290 | Overdue | Yes | Yes | No
CC0375-OW-PIP-023 | O01-04 to O08-01 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-20 | 04-08-01 | 2023-07-25 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-16 | 149 | Overdue | 175 | Overdue | No | No | No
CC0375-OW-PIP-024 | O08-01 to O08-02 | Closed | 2023-06-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-25 | 04-08-01 | 2023-08-01 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-16 | 142 | Overdue | 168 | Overdue | No | No | No
CC0375-OW-PIP-025 | O01-04 to O01-05 | Physical Works Complete | 2023-08-15 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-18 | 04-08-01 | 2023-08-22 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 257 | Overdue | 257 | Overdue | Yes | Yes | No
CC0375-OW-PIP-026 | O01-05 to O01-06 | Closed | 2023-08-15 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-25 | 04-08-01 | 2023-08-29 | Yes | Yes | Not Required |  |  | No |  |  | 2024-02-01 | 2024-02-21 | 156 | Overdue | 176 | Overdue | No | No | No
CC0375-OW-PIP-027 | O01-06 to O01-07 | Closed | 2023-08-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-29 | 04-08-01 | 2023-09-12 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 209 | Overdue | 223 | Overdue | No | No | No
CC0375-OW-PIP-028 | O01-07 to O07-02 | Submitted To Client | 2023-09-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-12 | 04-08-01 | 2023-09-18 | Yes | Yes | Yes | NCR-034 |  | Yes | 2024-03-08 |  | 2024-05-03 |  | 228 | Overdue | 230 | Overdue | No | No | No
CC0375-OW-PIP-029 | O01-07 to O01-08 | Closed | 2023-09-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-24 | 04-08-01 | 2023-10-25 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 85 | Overdue | 97 | Overdue | No | No | No
CC0375-OW-PIP-030 | O01-01 to O01-02 | Submitted To Client | 2023-09-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-06 | 04-08-01 | 2023-10-22 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 194 | Overdue | 196 | Overdue | No | No | No
CC0375-OW-PIP-031 | O01-02 to O01-03 | Closed | 2023-09-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-06 | 04-08-01 | 2023-10-08 | Yes | Yes | Not Required | [5 empty] | 2024-02-22 | 2024-02-27 | 137 | Overdue | 142 | Overdue | No | No | No
CC0375-OW-PIP-032 | O30-01 to O12-01 | Physical Works Complete | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-28 | 04-08-01 | 2023-09-30 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 218 | Overdue | 218 | Overdue | Yes | Yes | No
CC0375-OW-PIP-033 | O01-02 to O29-01 | Closed | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | [5 empty] | 2024-02-22 | 2024-02-27 | 122 | Overdue | 127 | Overdue | No | No | No
CC0375-OW-PIP-034 | O14-01 to O14-02 | Physical Works Complete | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-03 | 04-08-01 | 2023-11-06 | No | No | Not Required | [7 empty] | 181 | Overdue | 181 | Overdue | Yes | Yes | No
CC0375-OW-PIP-035 | O14-02 to O14-03 | Closed | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-06 | 04-08-01 | 2023-11-07 | Yes | Yes | Not Required | NCR-046 | 2024-01-12 | No |  |  | 2024-04-08 | 2024-04-22 | 153 | Overdue | 167 | Overdue | No | No | No
CC0375-OW-PIP-036 | O01-08 to O01-09 | Physical Works Complete | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-30 | 04-08-01 | 2023-10-31 | No | No | Not Required | [7 empty] | 187 | Overdue | 187 | Overdue | Yes | Yes | No
CC0375-OW-PIP-037 | O01-09 to O01-10 | Physical Works Complete | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-31 | 04-08-01 | 2023-11-01 | No | No | Not Required | [7 empty] | 186 | Overdue | 186 | Overdue | Yes | Yes | No
CC0375-OW-PIP-038 | O01-10 to O01-11 | Physical Works Complete | 2023-09-18 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-01 | 04-08-01 | 2023-11-03 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 184 | Overdue | 184 | Overdue | Yes | Yes | No
CC0375-OW-PIP-039 | O30-01 to O30-02 | Closed | 2023-10-03 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-29 | 04-08-01 | 2023-10-03 | Yes | Yes | Not Required | NCR-00034 |  | No |  |  | 2024-01-18 | 2024-01-30 | 107 | Overdue | 119 | Overdue | No | No | No
CC0375-OW-PIP-040 | O30-02 to O30-03 | Closed | 2023-10-03 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-29 | 04-08-01 | 2023-10-03 | Yes | Yes | Not Required | NCR-000034 |  | No |  |  | 2024-02-08 | 2024-02-21 | 128 | Overdue | 141 | Overdue | No | No | No
CC0375-OW-PIP-041 | O08-03 to O34-01 | Physical Works Complete | 2023-10-03 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-10 | 04-08-01 | 2023-10-12 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 206 | Overdue | 206 | Overdue | Yes | Yes | No
CC0375-OW-PIP-042 | O19-02 to O19-03 | Closed | 2023-10-13 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-13 | 04-08-01 | 2023-10-16 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 | 2024-02-21 | 108 | Overdue | 128 | Overdue | No | No | No
CC0375-OW-PIP-043 | O19-01 to O19-02 | Submitted To Client | 2023-10-13 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-23 | 04-08-01 | 2023-10-26 | Yes | No | Yes | NCR-046 |  | Yes | 2024-03-08 |  | 2024-05-03 |  | 190 | Overdue | 192 | Overdue | No | Yes | No
CC0375-OW-PIP-044 | O08-03 to O19-01 | Closed | 2023-10-13 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-20 | 04-08-01 | 2023-11-25 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 54 | Nearly Overdue | 66 | Overdue | No | No | No
CC0375-OW-PIP-045 | O15-01 to O13-01 | Physical Works Complete | 2023-10-17 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-17 | 04-08-01 | 2023-10-19 | No | No | Yes | NCR-046 |  | Yes |  |  |  |  | 199 | Overdue | 199 | Overdue | Yes | Yes | No
CC0375-OW-PIP-046 | O15-01 to O15-02 | Physical Works Complete | 2023-10-19 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | No | No | Not Required | [7 empty] | 195 | Overdue | 195 | Overdue | Yes | Yes | No
CC0375-OW-PIP-047 | O15-02 to O15-03 | Submitted To Client | 2023-10-19 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Yes | NCR-034 |  | Yes | 2024-03-08 |  | 2024-04-08 |  | 168 | Overdue | 195 | Overdue | No | No | No
CC0375-OW-PIP-048 | O29-01 to O05-03 | Physical Works Complete | 2023-10-19 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-20 | 04-08-01 | 2023-10-24 | No | No | Not Required | [7 empty] | 194 | Overdue | 194 | Overdue | Yes | Yes | No
CC0375-OW-PIP-049 | O05-03 to O05-05 | Closed | 2023-10-24 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-06 | 04-08-01 | 2024-02-01 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 | 2024-02-21 | 0 | Early | 20 | Early | No | No | No
CC0375-OW-PIP-050 | O14-01 to O39-01 | Submitted To Client | 2023-10-24 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-31 | 04-08-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 183 | Overdue | 185 | Overdue | No | No | No
CC0375-OW-PIP-051 | O14-03 to O14-05 | Physical Works Complete | 2023-11-01 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-07 | 04-08-01 | 2023-11-15 | No | No | Not Required | [7 empty] | 172 | Overdue | 172 | Overdue | Yes | Yes | No
CC0375-OW-PIP-052 | O29-01 to O10-01, O05-01 to O28-01, O05-02 to O27-01 | Submitted To Client | 2023-11-07 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-06 | 04-08-01 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 153 | Overdue | 180 | Overdue | No | No | No
CC0375-OW-PIP-053 | O01-11 to O38-01 | Submitted To Client | 2023-11-13 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-10-10 | 04-08-01 | 2023-10-12 | Yes | Yes | Yes | NCR-034 |  | Yes | 2024-03-08 |  | 2024-05-03 |  | 204 | Overdue | 206 | Overdue | No | No | No
CC0375-OW-PIP-054 | O01-10 to O03-01 | Physical Works Complete | 2023-11-10 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-10 | 04-08-01 | 2023-11-12 | No | No | Not Required | [7 empty] | 175 | Overdue | 175 | Overdue | Yes | Yes | No
CC0375-OW-PIP-055 | O29-01 to O42-01 | Physical Works Complete | 2023-11-21 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-21 | 04-08-01 | 2023-11-23 | No | No | Not Required | [7 empty] | 164 | Overdue | 164 | Overdue | Yes | Yes | No
CC0375-OW-PIP-056 | O08-08 to O35-01 | Submitted To Client | 2023-11-21 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-22 | 04-08-01 | 2023-11-24 | Yes | Yes | Yes | NCR-046 |  | Yes | 2024-03-08 |  | 2024-04-08 |  | 136 | Overdue | 163 | Overdue | No | No | No
CC0375-OW-PIP-057 | O08-01 to O17-01 | Physical Works Complete | 2023-11-29 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-11-29 | 04-08-01 | 2023-12-04 | No | No | Not Required | [7 empty] | 153 | Overdue | 153 | Overdue | Yes | Yes | No
CC0375-OW-PIP-058 | O17-01 to O17-02 | Physical Works Complete | 2023-11-29 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-01 | 04-08-01 | 2023-12-05 | No | No | Yes | NCR-046 |  | Yes |  |  |  |  | 152 | Overdue | 152 | Overdue | Yes | Yes | No
CC0375-OW-PIP-059 | O17-02 to O17-03 | Submitted To Client | 2023-11-29 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-01 | 04-08-01 | 2023-12-05 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 125 | Overdue | 152 | Overdue | No | No | No
CC0375-OW-PIP-060 | O17-03 to O17-08 | Submitted To Client | 2023-11-29 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-05 | 04-08-01 | 2023-12-20 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 110 | Overdue | 137 | Overdue | No | No | No
CC0375-OW-PIP-061 | O04-01 to O04-02 | Submitted To Client | 2023-12-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-12 | 04-08-01 | 2023-12-20 | Yes | Yes | Yes | NCR-046 |  | Yes | 2024-03-08 |  | 2024-04-08 |  | 110 | Overdue | 137 | Overdue | No | No | No
CC0375-OW-PIP-062 | O04-02 to O04-04 | Work In Progress | 2023-12-12 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-12 | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-063 | O11-01 to O11-03 | Open | 2023-12-15 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-064 | O11-01 to O32-02 | Open | 2024-02-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-065 | O15-03 to O15-05 | Open | 2024-02-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-066 | O30-03 to O30-05 | Open | 2024-02-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-067 | O24-01 to O22-02 | Open | 2024-02-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PIP-068 | O01-06 to O36-01, O01-07 to O37-01 | Open | 2024-02-25 | Oily Water Network | Pipe Installation | INF-HSEQ CC0375-ITP-004 Oily Water (Pipe Laying) & Checklist | Mahmoud Medoukh |  | 04-08-01 | [15 empty] | No | No | No
CC0375-OW-PPIT-001 | Precast Pit-008-02 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-25 | 04-08-01 | 2023-08-10 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-11-09 | 2023-12-19 | 91 | Overdue | 131 | Overdue | No | No | No
CC0375-OW-PPIT-002 | Precast Pit-014-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 168 | Overdue | 182 | Overdue | No | No | No
CC0375-OW-PPIT-003 | Precast Pit-015-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 168 | Overdue | 182 | Overdue | No | No | No
CC0375-OW-PPIT-004 | Precast Pit-001-03 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-13 | 04-08-01 | 2023-07-20 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 | 2024-04-22 | 263 | Overdue | 277 | Overdue | No | No | No
CC0375-OW-PPIT-005 | Precast Pit-004-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-09-18 | 04-08-01 | 2023-09-28 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 105 | Overdue | 110 | Overdue | No | No | No
CC0375-OW-PPIT-006 | Precast Pit-030-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-09-28 | 04-08-01 | 2023-09-29 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 111 | Overdue | 123 | Overdue | No | No | No
CC0375-OW-PPIT-007 | Precast Pit-008-05 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-06-23 | 04-08-01 | 2023-06-28 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-19 | 169 | Overdue | 174 | Overdue | No | No | No
CC0375-OW-PPIT-008 | Precast Pit-008-06 | Physical Works Complete | 2023-06-22 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-06-22 | 04-08-01 | 2023-07-03 | No | No | Not Required | [7 empty] | 307 | Overdue | 307 | Overdue | Yes | Yes | No
CC0375-OW-PPIT-009 | Precast Pit-008-07 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-06-29 | 04-08-01 | 2023-07-06 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-12-14 | 2023-12-19 | 161 | Overdue | 166 | Overdue | No | No | No
CC0375-OW-PPIT-010 | Precast Pit-008-08 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-03 | 04-08-01 | 2023-07-06 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-12-14 | 2023-12-19 | 161 | Overdue | 166 | Overdue | No | No | No
CC0375-OW-PPIT-011 | Precast Pit-006-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-09 | 04-08-01 | 2023-08-21 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-19 | 115 | Overdue | 120 | Overdue | No | No | No
CC0375-OW-PPIT-012 | Precast Pit-006-02 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-26 | 04-08-01 | 2023-08-21 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-19 | 115 | Overdue | 120 | Overdue | No | No | No
CC0375-OW-PPIT-013 | Precast Pit-016-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-08 | 04-08-01 | 2023-07-12 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 183 | Overdue | 188 | Overdue | No | No | No
CC0375-OW-PPIT-014 | Precast Pit-031-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-08 | 04-08-01 | 2023-07-08 | Yes | Yes | Not Required | [5 empty] | 2024-01-18 | 2024-01-30 | 194 | Overdue | 206 | Overdue | No | No | No
CC0375-OW-PPIT-015 | Precast Pit-008-03 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-06 | 04-08-01 | 2023-08-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 | 2024-04-22 | 230 | Overdue | 244 | Overdue | No | No | No
CC0375-OW-PPIT-016 | Precast Pit-008-04 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-16 | 04-08-01 | 2023-11-16 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 84 | Overdue | 97 | Overdue | No | No | No
CC0375-OW-PPIT-017 | Precast Pit-023-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-22 | 04-08-01 | 2023-08-24 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 228 | Overdue | 242 | Overdue | No | No | No
CC0375-OW-PPIT-018 | Precast Pit-001-04 | Physical Works Complete | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-13 | 04-08-01 | 2023-08-24 | No | No | Not Required | [7 empty] | 255 | Overdue | 255 | Overdue | Yes | Yes | No
CC0375-OW-PPIT-019 | Precast Pit-008-01 | Closed | 2023-06-23 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-22 | 04-08-01 | 2023-07-24 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 171 | Overdue | 176 | Overdue | No | No | No
CC0375-OW-PPIT-020 | Precast Pit-001-05 | Closed | 2023-08-15 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-18 | 04-08-01 | 2023-08-22 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 230 | Overdue | 244 | Overdue | No | No | No
CC0375-OW-PPIT-021 | Precast Pit-001-06 | Closed | 2023-08-15 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-25 | 04-08-01 | 2023-08-29 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 135 | Overdue | 140 | Overdue | No | No | No
CC0375-OW-PPIT-022 | Precast Pit-001-07 | Closed | 2023-08-25 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-29 | 04-08-01 | 2023-09-18 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 115 | Overdue | 120 | Overdue | No | No | No
CC0375-OW-PPIT-023 | Precast Pit-001-08 | Closed | 2023-09-12 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-24 | 04-08-01 | 2023-10-25 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 78 | Overdue | 83 | Overdue | No | No | No
CC0375-OW-PPIT-024 | Precast Pit-005-01 | Physical Works Complete | 2023-10-19 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | No | No | Yes | NCR-034 | 2023-11-11 | Yes |  |  |  |  | 195 | Overdue | 195 | Overdue | Yes | Yes | No
CC0375-OW-PPIT-025 | Precast Pit-001-02 | Closed | 2023-09-12 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-06 | 04-08-01 | 2023-10-09 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 94 | Overdue | 99 | Overdue | No | No | No
CC0375-OW-PPIT-026 | Precast Pit-029-01 | Closed | 2023-09-18 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 80 | Overdue | 85 | Overdue | No | No | No
CC0375-OW-PPIT-027 | Precast Pit-014-02 | Closed | 2023-09-18 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-03 | 04-08-01 | 2023-10-06 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 97 | Overdue | 102 | Overdue | No | No | No
CC0375-OW-PPIT-028 | Precast Pit-014-03 | Closed | 2023-09-18 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-06 | 04-08-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 64 | Overdue | 69 | Overdue | No | No | No
CC0375-OW-PPIT-029 | Precast Pit-001-09 | Physical Works Complete | 2023-09-18 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-30 | 04-08-01 | 2023-11-02 | No | No | Not Required | [7 empty] | 185 | Overdue | 185 | Overdue | Yes | Yes | No
CC0375-OW-PPIT-030 | Precast Pit-001-10 | Closed | 2023-09-18 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-30 | 04-08-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 70 | Overdue | 75 | Overdue | No | No | No
CC0375-OW-PPIT-031 | Precast Pit-019-01 | Closed | 2023-10-13 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-23 | 04-08-01 | 2023-10-26 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 77 | Overdue | 82 | Overdue | No | No | No
CC0375-OW-PPIT-032 | Precast Pit O13-01 | Physical Works Complete | 2023-10-17 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-17 | 04-08-01 | 2023-10-19 | No | No | Not Required | [7 empty] | 199 | Overdue | 199 | Overdue | Yes | Yes | No
CC0375-OW-PPIT-033 | Precast Pit 015-02 | Closed | 2023-10-19 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 80 | Overdue | 85 | Overdue | No | No | No
CC0375-OW-PPIT-034 | Precast Pit O15-03 | Closed | 2023-10-19 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 168 | Overdue | 182 | Overdue | No | No | No
CC0375-OW-PPIT-035 | Precast Pit 005-02 | Closed | 2023-10-19 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | NCR-034 | 2023-11-11 | No |  |  | 2024-04-08 | 2024-04-22 | 168 | Overdue | 182 | Overdue | No | No | No
CC0375-OW-PPIT-036 | Precast Pit 005-03 | Closed | 2023-10-19 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-10-19 | 04-08-01 | 2023-10-23 | Yes | Yes | Not Required | NCR-034 |  | Yes |  |  | 2024-04-08 | 2024-04-22 | 168 | Overdue | 182 | Overdue | No | No | No
CC0375-OW-PPIT-037 | Precast Pit 005-5 | Closed | 2023-11-07 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-08 | 04-08-01 | 2023-11-15 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 | 2024-02-21 | 78 | Overdue | 98 | Overdue | No | No | No
CC0375-OW-PPIT-038 | Precast Pit O14-05 | Closed | 2023-11-07 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-07 | 04-08-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2024-01-11 | 2024-01-16 | 64 | Overdue | 69 | Overdue | No | No | No
CC0375-OW-PPIT-039 | Precast Pit O17-01 | Submitted To Client | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Yes | NCR-034 | 2023-11-11 | Yes | 2024-03-08 |  | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-OW-PPIT-040 | Precast Pit O17-02 | Submitted To Client | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Yes | NCR-034 | 2023-11-11 | Yes | 2024-03-08 |  | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-OW-PPIT-041 | Precast Pit O17-03 | Submitted To Client | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-OW-PPIT-042 | Precast Pit O17-04 | Physical Works Complete | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-01-31 |  | 50 | Nearly Overdue | 145 | Overdue | No | No | No
CC0375-OW-PPIT-043 | Precast Pit O17-06 | Submitted To Client | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 118 | Overdue | 145 | Overdue | No | No | No
CC0375-OW-PPIT-044 | Precast Pit O20-01 | Physical Works Complete | 2023-11-29 | Oily Water Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-11-30 | 04-08-01 | 2023-12-12 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 58 | Nearly Overdue | 145 | Overdue | No | No | No
CC0375-PW-PIP-100 | CC0375-PW-PIP-100 - Potable Water 1-00 | Physical Works Complete | 2024-02-14 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-24 | 04-06-02 | 2024-03-07 | No | No | [8 empty] | 59 | Nearly Overdue | 59 | Nearly Overdue | Yes | Yes | No
CC0375-PW-PIP-101 | CC0375-PW-PIP-101 - Potable Water 1-01 | Physical Works Complete | 2024-02-14 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 04-06-02 | 2024-02-14 | No | No | Yes | NCR -058 | 2024-02-29 | No |  |  |  |  | 81 | Overdue | 81 | Overdue | Yes | Yes | Yes
CC0375-PW-PIP-102 | BOP East Perimeter - North Section | Physical Works Complete | 2024-03-30 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-31 | 04-06-02 | 2024-04-04 | [10 empty] | 31 | Due | 31 | Due | No | No | No
CC0375-PW-PIP-103 | CC0375-PW-PIP-103 - Potable Water 1-03 | Physical Works Complete | 2024-02-14 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 04-06-02 | 2024-02-14 | No | No | Not Required | [7 empty] | 81 | Overdue | 81 | Overdue | Yes | Yes | No
CC0375-PW-PIP-105 | BOP East Perimeter - North Section | Physical Works Complete | 2024-03-30 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-31 | 04-06-02 | 2024-04-04 | [10 empty] | 31 | Due | 31 | Due | No | No | No
CC0375-PW-PIP-106 | BOP EAST PERIMETER | Physical Works Complete | 2024-03-18 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-20 | 04-06-02 | 2024-04-08 | [10 empty] | 27 | Early | 27 | Early | No | No | No
CC0375-PW-PIP-107 | CC0375-PW-PIP-107 - Potable Water | Physical Works Complete | 2024-03-01 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-05 | 04-06-02 | 2024-04-10 | [10 empty] | 25 | Early | 25 | Early | No | No | No
CC0375-PW-PIP-108 | Fire Tanks South | Physical Works Complete | 2024-04-12 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-04-13 | 04-06-02 | 2024-04-30 | [10 empty] | 5 | Early | 5 | Early | No | No | No
CC0375-PW-PIP-109 | Admin South | Physical Works Complete | 2024-01-23 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-03-25 | 04-06-02 | 2024-03-31 | [10 empty] | 35 | Due | 35 | Due | No | No | No
CC0375-PW-PIP-111 | Chemical Storage Area | Open | 2024-04-18 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers |  | 04-06-02 | [15 empty] | No | No | No
CC0375-PW-PIP-112 | Chemical Storage Area | Open | 2024-02-20 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-20 | 04-06-02 | [15 empty] | No | No | No
CC0375-PW-PIP-113 | Chemical Storage Area | Open | 2024-04-18 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers |  | 04-06-02 | [15 empty] | No | No | No
CC0375-PW-PIP-115 | GT2 West | Work In Progress | 2024-02-12 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-15 | 04-06-02 | [15 empty] | No | No | No
CC0375-PW-PIP-116 | GT2 North | Physical Works Complete | 2024-04-01 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-04-12 | 04-06-02 | 2024-04-18 | [10 empty] | 17 | Early | 17 | Early | No | No | No
CC0375-PW-PIP-117 | CC0375-PW-PIP-117 - Potable Water 1-17 | Physical Works Complete | 2024-02-14 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 04-06-02 | 2024-02-09 | No | No | [8 empty] | 86 | Overdue | 86 | Overdue | Yes | Yes | No
CC0375-PW-PIP-119 | CC0375-PW-PIP-119 - Potable Water 1-19 | Physical Works Complete | 2024-01-30 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 04-06-02 | 2024-04-17 | No | No | [8 empty] | 18 | Early | 18 | Early | Yes | Yes | No
CC0375-PW-PIP-120 | GT2 SOUTH | Physical Works Complete | 2024-02-18 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-19 | 04-06-02 | 2024-04-18 | No | No | Yes | NCR -058 | 2024-02-29 | No |  |  |  |  | 17 | Early | 17 | Early | Yes | Yes | Yes
CC0375-PW-PIP-121 | Workshop Building West | Work In Progress | 2024-04-17 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-04-18 | 04-06-02 | [15 empty] | No | No | No
CC0375-PW-PIP-122 | BOP AIR RECIEVER | Physical Works Complete | 2024-01-29 | Potable Water | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-01-31 | 04-06-02 | 2024-04-18 | [10 empty] | 17 | Early | 17 | Early | No | No | No
CC0375-RW-EWK-002 | CH 27.515 - 111.222 layer 2 | Work In Progress | 2023-11-06 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor | 2023-11-15 | 04-02-01 | [15 empty] | No | No | No
CC0375-RW-EWK-003 | Roadway CH111.222 - CH 175 layer 2 | Work In Progress | 2023-11-13 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor | 2023-11-17 | 04-02-01 | 2024-01-25 |  | Yes | [8 empty] | 101 | Overdue | 101 | Overdue | No | No | No
CC0375-RW-EWK-004 | BOP 3 Lot 3 Fill to Subgrade | Submitted To Client | 2024-02-19 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor | 2024-02-19 | 04-02-01 | 2024-02-26 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 67 | Overdue | 69 | Overdue | No | No | No
CC0375-RW-EWK-005 | BOP LOT 005 | Submitted To Client | 2024-02-28 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-02-28 | 04-02-01 | 2024-04-14 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 17 | Early | 21 | Early | No | No | No
CC0375-RW-EWK-006 | Admin 1 Lot 006 - Found to Subgrade | Submitted To Client | 2024-02-29 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-02-29 | 04-02-01 | 2024-03-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 61 | Overdue | 65 | Overdue | No | No | No
CC0375-RW-EWK-007 | BOP 5 - Lot 007 - Found to Subgrade | Submitted To Client | 2024-03-06 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-03-29 | 04-02-01 | 2024-03-06 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 56 | Nearly Overdue | 60 | Overdue | No | No | No
CC0375-RW-EWK-008 | BOP 2 Lot 2 | Submitted To Client | 2024-03-11 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-03-11 | 04-02-01 | 2024-03-11 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 53 | Nearly Overdue | 55 | Nearly Overdue | No | No | No
CC0375-RW-EWK-009 | CC0375-RW-EWK-BOP 1 Lot 001 | Physical Works Complete | 2024-03-11 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor | -685160 | 04-02-01 | 2024-03-11 | No | Yes | Not Required | [7 empty] | 55 | Nearly Overdue | 55 | Nearly Overdue | Yes | No | No
CC0375-RW-EWK-010 | CC0375-RW-EWK- BOP 4 Lot 004 | Physical Works Complete | 2024-03-11 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor |  | 04-02-01 | 2024-03-11 | [10 empty] | 55 | Nearly Overdue | 55 | Nearly Overdue | No | No | No
CC0375-RW-EWK-011 - Roadway CH6.000 - CH70.000 | Roadway CH - CH | Submitted To Client | 2024-03-20 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-03-20 | 04-02-01 | 2024-03-22 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 42 | Due | 44 | Due | No | No | No
CC0375-RW-EWK-012 | Carpark (ROAD) | Submitted To Client | 2024-04-11 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-04-04 | 04-02-01 | 2024-04-12 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 21 | Early | 23 | Early | No | No | No
CC0375-RW-EWK-013 | Admin 2 (HARDSTAND) | Submitted To Client | 2024-04-12 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-04-01 | 04-02-01 | 2024-04-12 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 21 | Early | 23 | Early | No | No | No
CC0375-RW-EWK-014 | BOP 6.1 (HARDSTAND) - Lot 011 | Submitted To Client | 2024-04-08 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-04-08 | 04-02-01 | 2024-04-14 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 17 | Early | 21 | Early | No | No | No
CC0375-RW-EWK-015 | BOP 7 North interceptor | Submitted To Client | 2024-04-22 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Oliver Pryor |  | 04-02-01 | 2024-05-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 0 | Early | 4 | Early | No | No | No
CC0375-RW-EWK-016 | Carpark 2 (ROAD) - Lot 013 | Physical Works Complete | 2024-04-17 | Roadworks | Earthworks | INF-HSEQ CC0375-ITP-001 Bulk Earthworks & Checklist | Darren Fernandes | 2024-04-16 |  | 2024-04-20 | Yes | Yes | Not Required | [7 empty] | 15 | Early | 15 | Early | No | No | No
CC0375-RW-PAV-001 | BOP - Lot 01 Subbase | Submitted To Client | 2024-02-12 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-02-14 | 04-03-02 | 2024-04-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 0 | Early | 13 | Early | No | No | No
CC0375-RW-PAV-002 | BOP - Lot 01 Base | Submitted To Client | 2024-02-21 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-02-19 | 04-03-02 | 2024-03-04 | No | Yes | Not Required | [5 empty] | 2024-04-24 |  | 51 | Nearly Overdue | 62 | Overdue | Yes | No | No
CC0375-RW-PAV-003 | BOP 2 Lot 2 - Subbase | Open | 2024-03-13 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor |  | 04-03-02 | [15 empty] | No | No | No
CC0375-RW-PAV-004 | BOP 2 Lot 2 - Base | Work In Progress | 2024-03-15 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | 2024-03-14 | 04-03-02 | [15 empty] | No | No | No
CC0375-RW-PAV-005 | BOP - Lot 3 Subbase | Submitted To Client | 2024-02-20 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-02-26 | 04-03-02 | 2024-02-26 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 56 | Nearly Overdue | 69 | Overdue | No | No | No
CC0375-RW-PAV-006 | Lot 3 Base | Submitted To Client | 2024-02-26 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-02-27 | 04-03-02 | 2024-03-04 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 49 | Due | 62 | Overdue | No | No | No
CC0375-RW-PAV-007 | BOP - Lot 4 Subbase | Submitted To Client | 2024-02-26 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-02-24 | 04-03-02 | 2024-03-04 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 49 | Due | 62 | Overdue | No | No | No
CC0375-RW-PAV-008 | BOP lot 4 Base | Submitted To Client | 2024-02-26 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-03-04 | 04-03-02 | 2024-04-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 0 | Early | 13 | Early | No | No | No
CC0375-RW-PAV-009 | BOP South Rd - Lot 05 Subbase (ROAD) | Submitted To Client | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-03-20 | 04-03-01 | 2024-03-28 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 34 | Due | 38 | Due | No | No | No
CC0375-RW-PAV-010 | BOP South Rd - Lot 05 Base (ROAD) | Submitted To Client | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-05-01 | 04-03-01 | 2024-05-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 0 | Early | 4 | Early | No | No | No
CC0375-RW-PAV-012 | Admin 1 - Lot 07 Base (HARDSTAND) | Cancelled | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes |  | 04-03-02 | [15 empty] | No | No | No
CC0375-RW-PAV-013 | BOP 5 - Lot 07 Subbase (HARDSTAND) | Physical Works Complete | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | 2024-02-24 | 04-03-02 | 2024-03-02 | Yes | Yes | Not Required | [7 empty] | 64 | Overdue | 64 | Overdue | No | No | No
CC0375-RW-PAV-014 | BOP 5 - Lot 07 Base (HARDSTAND) | Open | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes |  | 04-03-02 | [15 empty] | No | No | No
CC0375-RW-PAV-015 | BOP North East Rd - Lot 08 Subbase (ROAD) | Physical Works Complete | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | 2024-04-03 | 04-03-02 | 2024-04-02 | [10 empty] | 33 | Due | 33 | Due | No | No | No
CC0375-RW-PAV-016 | BOP North East Rd - Lot 08 Base (ROAD) | Physical Works Complete | 2024-03-28 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes |  | 04-03-01 | 2024-03-29 | Yes | Yes | Not Required | [7 empty] | 37 | Due | 37 | Due | No | No | No
CC0375-RW-PAV-017 | Carpark 1 - Lot 09 Subbase (ROAD) | Open | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-018 | Carpark 1 - Lot 09 Base (ROAD) | Open | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-019 | Admin 2 Lot 10 Subbase (HARDSTAND) | Open | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-020 | Admin 2 - Lot 10 Base (HARDSTAND) | Open | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-021 | BOP - 6 Interceptor Surround - Subbase (HARDSTAND) | Physical Works Complete | 2024-04-15 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-04-17 | 04-03-01 | 2024-04-18 | Yes | Yes | Not Required | [7 empty] | 17 | Early | 17 | Early | No | No | No
CC0375-RW-PAV-022 | Lot 6 Interceptor Surround - base | Work In Progress | 2024-04-27 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-04-24 | 04-03-02 | [15 empty] | No | No | No
CC0375-RW-PAV-023 | North Interceptor Pit - Lot 12 Subbase (HARDSTAND) | Open | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-024 | North Interceptor Pit - Lot 12 Base (HARDSTAND) | Cancelled | 2024-05-02 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-RW-PAV-025 | Carpark 2 - Lot 13 Subbase (ROAD) | Work In Progress | 2024-05-06 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Oliver Pryor | 2024-04-06 | [16 empty] | No | No | No
CC0375-RW-PAV-026 | Carpark 2 - Lot 13 Base (ROAD) | Cancelled | 2024-05-06 | Roadworks | Flexible Pavement | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist | Darren Fernandes | [17 empty] | No | No | No
CC0375-SEW-PIP-001 | PVC SEWER ADMIN AREA | Physical Works Complete | 2024-03-12 | Sewerage System | Pipe Installation | INF-HSEQ CC0375-ITP-026 Sewerage System | Mathew Chambers | 2024-03-12 | 04-06-01 | 2024-04-16 | [10 empty] | 19 | Early | 19 | Early | No | No | No
CC0375-SEW-PIP-002 | HDPE Sewer Admin Area | Physical Works Complete | 2024-04-06 | Sewerage System | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-04-08 | 04-06-01 | 2024-04-16 | [10 empty] | 19 | Early | 19 | Early | No | No | No
CC0375-SW-FRP-001 | Stormwater Head wall-Outlet Key | Submitted To Client | 2023-07-18 | Stormwater Network | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-10-18 | 04-05-02 | 2023-11-06 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 100 | Overdue | 181 | Overdue | No | No | No
CC0375-SW-FRP-002 | Stormwater Head wall-Outlet Base | Submitted To Client | 2023-07-18 | Stormwater Network | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-07-18 | 04-05-02 | 2023-08-12 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 186 | Overdue | 267 | Overdue | No | No | No
CC0375-SW-FRP-003 | Stormwater Head wall-Outlet Walls | Submitted To Client | 2023-07-18 | Stormwater Network | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-08-12 | 04-05-02 | 2023-08-28 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 170 | Overdue | 251 | Overdue | No | No | No
CC0375-SW-FRP-004 | Stormwater Head wall-Outlet Stairs | Submitted To Client | 2023-10-24 | Stormwater Network | Concrete | INF-HSEQ CC0375-ITP-015 FRP Works (Structures) & Checklist | Yash Bhavsar | 2023-10-24 | 04-05-02 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2024-02-14 |  | 99 | Overdue | 180 | Overdue | No | No | No
CC0375-SW-GAB-001 | Rock Beaching and Gabions Stormwater Headwall | Physical Works Complete | 2023-11-13 | Stormwater Network | Open Drain & Gabions | INF-HSEQ CC0375-ITP-007 Open Drains & Checklist | Oliver Pryor | 2023-11-10 | 04-05-02 | 2023-11-13 | Yes | Yes | Not Required | [7 empty] | 174 | Overdue | 174 | Overdue | No | No | No
CC0375-SW-PIP-001 | A02-06 to A04-01 | Submitted To Client | 2023-02-16 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-02-17 | 04-05-01 | 2023-02-18 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 403 | Overdue | 442 | Overdue | No | No | No
CC0375-SW-PIP-002 | A01-01 to A01-02 | Closed | 2023-08-28 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-08-30 | 04-05-01 | 2023-08-31 | Yes | Yes | Yes | NCR-021 | 2023-10-19 | Yes | 2023-11-07 |  | 2023-11-29 | 2023-12-19 | 90 | Overdue | 110 | Overdue | No | No | No
CC0375-SW-PIP-003 | A01-02 to A01-03 | Closed | 2023-08-28 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-09-05 | 04-05-01 | 2023-09-06 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-19 | 99 | Overdue | 104 | Overdue | No | No | No
CC0375-SW-PIP-004 | A10-02 to A10-03 | Closed | 2023-09-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-09-18 | 04-05-01 | 2023-09-21 | Yes | Yes | Not Required | [5 empty] | 2023-11-22 | 2023-12-20 | 62 | Overdue | 90 | Overdue | No | No | No
CC0375-SW-PIP-005 | A03-01 to A03-02 | Closed | 2023-09-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-09-21 | 04-05-01 | 2023-09-25 | Yes | Yes | Not Required | [5 empty] | 2023-11-08 | 2023-12-20 | 44 | Due | 86 | Overdue | No | No | No
CC0375-SW-PIP-006 | A03-02 to A03-03 | Closed | 2023-09-22 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-09-29 | 04-05-01 | 2023-09-29 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 76 | Overdue | 80 | Overdue | No | No | No
CC0375-SW-PIP-007 | A03-03 to A03-04 | Closed | 2023-09-25 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-03 | 04-05-01 | 2023-10-05 | Yes | Yes | Not Required | [5 empty] | 2023-11-08 | 2023-12-20 | 34 | Due | 76 | Overdue | No | No | No
CC0375-SW-PIP-008 | A03-05 to A03-06 | Closed | 2023-10-03 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-05 | 04-05-01 | 2023-10-06 | Yes | Yes | [6 empty] | 2023-12-14 | 2023-12-19 | 69 | Overdue | 74 | Overdue | No | No | No
CC0375-SW-PIP-009 | A03-06 to A03-07 | Closed | 2023-10-03 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-05 | 04-05-01 | 2023-10-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-19 | 67 | Overdue | 72 | Overdue | No | No | No
CC0375-SW-PIP-010 | A02-05 to A07-01 | Submitted To Client | 2023-10-03 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-09 | 04-05-01 | 2023-10-09 | No | No | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 170 | Overdue | 209 | Overdue | Yes | Yes | No
CC0375-SW-PIP-011 | A03-01 to A10-04 | Closed | 2023-10-09 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-11 | 04-05-01 | 2023-10-12 | Yes | Yes | Not Required | [5 empty] | 2023-11-15 | 2023-12-20 | 34 | Due | 69 | Overdue | No | No | No
CC0375-SW-PIP-012 | A25-05 to A25-04 | Closed | 2023-10-12 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-13 | 04-05-01 | 2023-10-15 | Yes | Yes | Not Required | [5 empty] | 2023-11-29 | 2023-12-19 | 45 | Due | 65 | Overdue | No | No | No
CC0375-SW-PIP-013 | A25-04 to A25-03 | Closed | 2023-10-12 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-14 | 04-05-01 | 2023-10-17 | Yes | Yes | Not Required | [5 empty] | 2023-11-29 | 2023-12-19 | 43 | Due | 63 | Overdue | No | No | No
CC0375-SW-PIP-014 | A25-03 to A25-02 | Submitted To Client | 2023-10-12 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-11 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-04-08 |  | 149 | Overdue | 176 | Overdue | No | No | No
CC0375-SW-PIP-015 | A25-02 to A25-01 | Submitted To Client | 2023-10-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-13 | Yes | Yes | Yes | NCR-035 |  | Yes | 2024-03-08 |  | 2024-04-02 |  | 141 | Overdue | 174 | Overdue | No | No | No
CC0375-SW-PIP-016 | A25-01 to A28-01 | Submitted To Client | 2023-10-12 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-15 | Yes | Yes | Yes | NCR-035 |  | Yes | 2024-03-08 |  | 2024-04-02 |  | 139 | Overdue | 172 | Overdue | No | No | No
CC0375-SW-PIP-017 | A01-09 to A01-10 | Submitted To Client | 2023-10-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-15 | 04-05-01 | 2023-10-22 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 157 | Overdue | 196 | Overdue | No | No | No
CC0375-SW-PIP-018 | A01-10 to A01-11 | Submitted To Client | 2023-10-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-20 | 04-05-01 | 2023-10-27 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 152 | Overdue | 191 | Overdue | No | No | No
CC0375-SW-PIP-019 | A02-03 to A02-04 | Closed | 2023-10-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-10-31 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR -058 |  | No |  |  | 2023-12-21 | 2024-01-18 | 43 | Due | 71 | Overdue | No | No | Yes
CC0375-SW-PIP-020 | A01-11 to A20-01 | Submitted To Client | 2023-10-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-01 | 04-05-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 146 | Overdue | 185 | Overdue | No | No | No
CC0375-SW-PIP-021 | A20-01 to A20-02 | Submitted To Client | 2023-11-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-02 | 04-05-01 | 2023-11-02 | Yes | Yes | Yes | NCR-045 & NCR -058 |  | Yes | 2024-03-08 |  | 2024-04-02 |  | 152 | Overdue | 185 | Overdue | No | No | No
CC0375-SW-PIP-022 | A20-02 to A20-03 | Submitted To Client | 2023-11-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-02 | 04-05-01 | 2023-11-03 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 145 | Overdue | 184 | Overdue | No | No | No
CC0375-SW-PIP-023 | A20-03 to A20-04 | Submitted To Client | 2023-11-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-02 | 04-05-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 146 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PIP-024 | A20-04 to A20-05 | Submitted To Client | 2023-11-11 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 141 | Overdue | 174 | Overdue | No | No | No
CC0375-SW-PIP-025 | A16-01 to A16-02 | Submitted To Client | 2023-11-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-07 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 140 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PIP-026 | A15-01 to A16-01 | Physical Works Complete | 2023-11-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-07 | 04-05-01 | 2024-03-15 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-13 |  | -2 | Early | 51 | Nearly Overdue | No | No | No
CC0375-SW-PIP-027 | A27-01 to A16-01 | Submitted To Client | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-09 | 04-05-01 | 2024-02-15 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 63 | Overdue | 80 | Overdue | No | No | No
CC0375-SW-PIP-028 | A01-10 to A15-01 | Submitted To Client | 2023-11-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-07 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 140 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PIP-029 | A01-11 to A01-12 | Submitted To Client | 2024-01-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-12 | No | No | Yes | NCR -058 |  | No |  |  | 2024-05-01 |  | 110 | Overdue | 114 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-030 | A01-12 to A01-13 | Submitted To Client | 2024-01-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-16 | Yes | Yes | Not Required |  |  | No |  |  | 2024-04-17 |  | 92 | Overdue | 110 | Overdue | No | No | No
CC0375-SW-PIP-031 | A01-13 to A01-14 | Physical Works Complete | 2024-01-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-16 | No | No | Not Required | [7 empty] | 110 | Overdue | 110 | Overdue | Yes | Yes | No
CC0375-SW-PIP-032 | A01-13 to A05-01 | Submitted To Client | 2024-01-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-21 | 04-05-01 | 2024-03-26 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 22 | Early | 40 | Due | No | No | No
CC0375-SW-PIP-033 | A1-14 to A1-15 | Physical Works Complete | 2024-03-04 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-27 | 04-05-01 | 2024-03-01 | [10 empty] | 65 | Overdue | 65 | Overdue | No | No | No
CC0375-SW-PIP-034 | A01-15 to A01-16 | Physical Works Complete | 2024-03-04 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-03-04 | 04-05-01 | 2024-03-15 | [10 empty] | 51 | Nearly Overdue | 51 | Nearly Overdue | No | No | No
CC0375-SW-PIP-035 | A01-16 to A01-17 | Submitted To Client | 2024-03-05 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-28 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 36 | Due | 38 | Due | No | No | No
CC0375-SW-PIP-036 | A11-01 to A11-02 | Physical Works Complete | 2024-01-05 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-08 | 04-05-01 | 2024-01-10 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 116 | Overdue | 116 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-037 | A11-02 to A11-03 | Submitted To Client | 2024-01-05 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-08 | 04-05-01 | 2024-01-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 99 | Overdue | 116 | Overdue | No | No | No
CC0375-SW-PIP-038 | A07-01 to A08-01 | Physical Works Complete | 2024-03-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-07 | [10 empty] | 59 | Nearly Overdue | 59 | Nearly Overdue | No | No | No
CC0375-SW-PIP-039 | A07-02 to A11-01 | Submitted To Client | 2024-03-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-07 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 57 | Nearly Overdue | 59 | Nearly Overdue | No | No | No
CC0375-SW-PIP-040 | A07-01 to A07-02 | Physical Works Complete | 2023-12-04 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-05 | 04-05-01 | 2023-12-13 | Yes | Yes | Not Required | [5 empty] | 2024-03-18 |  | 96 | Overdue | 144 | Overdue | No | No | No
CC0375-SW-PIP-041 | A07-02 to A07-02 | Submitted To Client | 2023-12-04 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-12 | 04-05-01 | 2023-12-18 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 106 | Overdue | 139 | Overdue | No | No | No
CC0375-SW-PIP-042 | A07-03 to A07-04 | Closed | 2023-11-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-08 | 04-05-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 36 | Due | 40 | Due | No | No | No
CC0375-SW-PIP-043 | A07-04 to A07-05 | Submitted To Client | 2024-02-02 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-03 | 04-05-01 | 2024-02-10 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 83 | Overdue | 85 | Overdue | No | No | No
CC0375-SW-PIP-044 | A25-01 to A07-02 | Submitted To Client | 2023-11-10 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 141 | Overdue | 174 | Overdue | No | No | No
CC0375-SW-PIP-045 | A28-01 to A28-02​​​​​​​ | Closed | 2023-11-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-15 |  |  | Not Required | [5 empty] | 2024-03-25 | 2024-03-25 | 131 | Overdue | 131 | Overdue | No | No | No
CC0375-SW-PIP-046 | A02-11 to A02-12 | Physical Works Complete | 2023-11-24 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-25 | 04-05-01 | 2023-11-27 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 160 | Overdue | 160 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-047 | A02-10 to A02-11 | Physical Works Complete | 2023-11-24 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-25 | 04-05-01 | 2023-11-27 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 160 | Overdue | 160 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-048 | A02-10 to A02-09 | Submitted To Client | 2023-11-17 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-17 | 04-05-01 | 2023-11-23 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 131 | Overdue | 164 | Overdue | No | No | No
CC0375-SW-PIP-049 | A02-09 to A22-01 | Physical Works Complete | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-22 | 04-05-01 | 2024-01-25 | No | No | Not Required | [7 empty] | 101 | Overdue | 101 | Overdue | Yes | Yes | No
CC0375-SW-PIP-050 | A22-01 to A22-02 | Physical Works Complete | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-26 | No | No | Not Required | [7 empty] | 100 | Overdue | 100 | Overdue | Yes | Yes | No
CC0375-SW-PIP-051 | A22-02 to A22-03 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 75 | Overdue | 99 | Overdue | No | No | No
CC0375-SW-PIP-052 | A22-03 to A22-04 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-23 | 04-05-01 | 2024-01-30 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 72 | Overdue | 96 | Overdue | No | No | No
CC0375-SW-PIP-053 | A23-04 to A23-05 | Physical Works Complete | 2023-11-29 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-28 | 04-05-01 | 2023-12-01 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 156 | Overdue | 156 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-054 | A23-03 to A23-04 | Physical Works Complete | 2023-11-28 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-28 | 04-05-01 | 2023-11-29 | No | No | Not Required | [7 empty] | 158 | Overdue | 158 | Overdue | Yes | Yes | No
CC0375-SW-PIP-055 | A23-02 to A23-03 | Physical Works Complete | 2023-11-24 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-28 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 159 | Overdue | 159 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-056 | A23-01 to A23-02 | Physical Works Complete | 2023-11-24 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-27 | No | No | Not Required | [7 empty] | 160 | Overdue | 160 | Overdue | Yes | Yes | No
CC0375-SW-PIP-057 | A02-08 to A23-01 | Physical Works Complete | 2023-11-24 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-28 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 159 | Overdue | 159 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-058 | A02-08 to A02-09 | Physical Works Complete | 2023-11-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-22 | 04-05-01 | 2023-11-22 | Yes | Yes | Yes | NCR -058 |  | No |  |  | 2024-02-08 |  | 78 | Overdue | 165 | Overdue | No | No | Yes
CC0375-SW-PIP-059 | A02-07 to A02-08 | Submitted To Client | 2023-12-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-06 | 04-05-01 | 2023-12-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 117 | Overdue | 150 | Overdue | No | No | No
CC0375-SW-PIP-060 | A04-02 to A04-04 | Physical Works Complete | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-14 | 04-05-01 | 2024-02-16 | No | No | Not Required | [7 empty] | 79 | Overdue | 79 | Overdue | Yes | Yes | No
CC0375-SW-PIP-061 | A04-04 to A04-05 | Submitted To Client | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-17 | 04-05-01 | 2024-03-07 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 42 | Due | 59 | Nearly Overdue | No | No | No
CC0375-SW-PIP-062 | A02-07 to A02-06 | Submitted To Client | 2023-12-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-08 | 04-05-01 | 2023-12-18 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 100 | Overdue | 139 | Overdue | No | No | No
CC0375-SW-PIP-063 | A04-01 to A04-02 | Submitted To Client | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-06 | 04-05-01 | 2024-02-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 59 | Nearly Overdue | 83 | Overdue | No | No | No
CC0375-SW-PIP-065 | A02-06 to A02-05 | Physical Works Complete | 2023-12-11 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-18 | 04-05-01 | 2024-01-12 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 114 | Overdue | 114 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-066 | A02-04 to A02-05 | Physical Works Complete | 2023-11-20 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-20 | 04-05-01 | 2024-01-08 | No | No | Not Required | [7 empty] | 118 | Overdue | 118 | Overdue | Yes | Yes | No
CC0375-SW-PIP-067 | A02-04 to A09-01 | Physical Works Complete | 2024-01-17 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-17 | 04-05-01 | 2024-01-22 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 104 | Overdue | 104 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-068 | A13-01 to A13-02 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-01 | 04-05-01 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 75 | Overdue | 93 | Overdue | No | No | No
CC0375-SW-PIP-069 | A13-02 to A13-03 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-01 | 04-05-01 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 75 | Overdue | 93 | Overdue | No | No | No
CC0375-SW-PIP-070 | A09-01 to A13-01 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-29 | 04-05-01 | 2024-01-31 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 78 | Overdue | 95 | Overdue | No | No | No
CC0375-SW-PIP-071 | A09-01 to A09-02 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-22 | 04-05-01 | 2024-01-25 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 88 | Overdue | 101 | Overdue | No | No | No
CC0375-SW-PIP-072 | A09-02 to A09-03 | Submitted To Client | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-05-01 | 04-05-01 | 2024-03-11 | Yes | Yes | Not Required | [5 empty] | 2024-05-01 |  | 51 | Nearly Overdue | 55 | Nearly Overdue | No | No | No
CC0375-SW-PIP-073 | A09-03 to A09-04 | Physical Works Complete | 2024-03-07 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-16 | [10 empty] | 50 | Nearly Overdue | 50 | Nearly Overdue | No | No | No
CC0375-SW-PIP-075 | A03-08 to A03-09 | Cancelled | 2024-03-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-076 | A03-07 to A03-08 | Submitted To Client | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-14 | 04-05-01 | 2024-02-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 66 | Overdue | 79 | Overdue | No | No | No
CC0375-SW-PIP-077 | A03-07 to A31-01 | Physical Works Complete | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-09 | 04-05-01 | 2024-02-12 | No | No | Not Required | [7 empty] | 83 | Overdue | 83 | Overdue | Yes | Yes | No
CC0375-SW-PIP-078 | A03-04 to A03-05 | Cancelled | 2024-03-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-079 | A10-01 to A10-02​​​​​​​ | Physical Works Complete | 2023-11-15 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-16 | 04-05-01 | 2023-11-17 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 170 | Overdue | 170 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-080 | A29-01 to A29-03 | Physical Works Complete | 2024-01-19 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-19 | 04-05-01 | 2024-01-19 | No | No | Not Required | [7 empty] | 107 | Overdue | 107 | Overdue | Yes | Yes | No
CC0375-SW-PIP-081 | A10-03 to A10-04 | Submitted To Client | 2024-01-23 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-23 | 04-05-01 | 2024-02-01 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 92 | Overdue | 94 | Overdue | No | No | No
CC0375-SW-PIP-082 | A10-05 to A10-04 | Submitted To Client | 2024-02-02 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-03 | 04-05-01 | 2024-02-05 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 88 | Overdue | 90 | Overdue | No | No | No
CC0375-SW-PIP-083 | A10-05 to A10-06 | Physical Works Complete | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-05 | 04-05-01 | 2024-02-07 | No | No | Not Required | [7 empty] | 88 | Overdue | 88 | Overdue | Yes | Yes | No
CC0375-SW-PIP-084 | A10-06 to A10-07 | Work In Progress | 2024-04-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-05-01 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-085 | A10-08 to A10-07 | Work In Progress | 2024-04-29 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-04-29 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-086 | A10-09 to A10-08 | Physical Works Complete | 2024-04-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-04-22 | 04-05-01 | 2024-04-29 | [10 empty] | 6 | Early | 6 | Early | No | No | No
CC0375-SW-PIP-087 | A10-10 to A10-09 | Physical Works Complete | 2024-04-22 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-04-22 | 04-05-01 | 2024-04-25 | [10 empty] | 10 | Early | 10 | Early | No | No | No
CC0375-SW-PIP-088 | A06-05 to A06-04​​​​​​​ | Submitted To Client | 2023-11-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-08 | 04-05-01 | 2023-11-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 145 | Overdue | 178 | Overdue | No | No | No
CC0375-SW-PIP-089 | A06-04 to A06-03 | Physical Works Complete | 2024-01-03 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-03 | 04-05-01 | 2024-01-05 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 121 | Overdue | 121 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-090 | A06-03 to A06-02​​​​​​​ | Submitted To Client | 2023-11-11 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-15 | 04-05-01 | 2023-11-15 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-04-02 |  | 139 | Overdue | 172 | Overdue | No | No | No
CC0375-SW-PIP-091 | A06-01 to A06-02 | Work In Progress | 2024-02-28 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-03-19 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-092 | A02-03 to A06-01 | Work In Progress | 2024-02-06 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-04-20 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-093 | A14-01 to A06-01 | Physical Works Complete | 2024-02-16 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-17 | 04-05-01 | 2024-02-21 | No | No | Not Required | [7 empty] | 74 | Overdue | 74 | Overdue | Yes | Yes | No
CC0375-SW-PIP-094 | A14-01 to A14-02 | Submitted To Client | 2024-02-16 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-17 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 56 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PIP-095 | A02-02 to A02-03 | Physical Works Complete | 2024-01-02 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-14 | 04-05-01 | 2023-12-15 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 142 | Overdue | 142 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-096 | A02-01 to A02-02 | Physical Works Complete | 2023-11-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-01 | 04-05-01 | 2023-12-12 | No | No | Not Required | [7 empty] | 145 | Overdue | 145 | Overdue | Yes | Yes | No
CC0375-SW-PIP-097 | A17-03 to A17-04 | Physical Works Complete | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-01 | [10 empty] | 65 | Overdue | 65 | Overdue | No | No | No
CC0375-SW-PIP-098 | A17-02 to A17-03 | Submitted To Client | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-02-26 | Yes | Yes | Not Required | [5 empty] | 2024-05-03 |  | 67 | Overdue | 69 | Overdue | No | No | No
CC0375-SW-PIP-099 | A01-08 to A02-01 | Physical Works Complete | 2023-12-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-01 | 04-05-01 | 2023-12-06 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 151 | Overdue | 151 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-100 | A01-08 to A01-09​​​​​​​ | Physical Works Complete | 2023-11-13 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-24 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 163 | Overdue | 163 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-101 | A17-01 to A17-02 | Physical Works Complete | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-21 | 04-05-01 | 2024-02-28 | [10 empty] | 67 | Overdue | 67 | Overdue | No | No | No
CC0375-SW-PIP-102 | A10-01 to A17-01 | Physical Works Complete | 2024-01-17 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-17 | 04-05-01 | 2024-01-22 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 104 | Overdue | 104 | Overdue | Yes | Yes | Yes
CC0375-SW-PIP-103 | A17-01 to A01-08 | Physical Works Complete | 2024-01-17 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-01-17 | 04-05-01 | 2024-01-24 | No | No | Not Required | [7 empty] | 102 | Overdue | 102 | Overdue | Yes | Yes | No
CC0375-SW-PIP-104 | A01-06 to A01-07 | Closed | 2023-12-01 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-01 | 04-05-01 | 2023-12-11 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 10 | Early | 38 | Due | No | No | No
CC0375-SW-PIP-105 | A01-07 to A01-08 | Closed | 2023-11-30 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-01 | 04-05-01 | 2023-12-11 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 10 | Early | 38 | Due | No | No | No
CC0375-SW-PIP-106 | A12-01 to A01-07 | Physical Works Complete | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-15 | 04-05-01 | 2024-02-17 | No | No | Not Required | [7 empty] | 78 | Overdue | 78 | Overdue | Yes | Yes | No
CC0375-SW-PIP-107 | A12-01 to A12-02 | Submitted To Client | 2024-02-14 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-19 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 57 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PIP-108 | A01-05 to A01-06 | Closed | 2023-11-20 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-21 | 04-05-01 | 2023-11-29 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 22 | Early | 50 | Nearly Overdue | No | No | No
CC0375-SW-PIP-109 | A01-04 to A01-05 | Closed | 2023-11-10 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-10 | 04-05-01 | 2023-11-21 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 30 | Due | 58 | Nearly Overdue | No | No | No
CC0375-SW-PIP-110 | A01-03 to A01-04 | Physical Works Complete | 2023-11-03 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-11-03 | 04-05-01 | 2023-11-14 | Yes | Yes | Yes | NCR-045 & NCR -058 |  | No | 2024-03-08 |  | 2024-03-13 |  | 120 | Overdue | 173 | Overdue | No | No | Yes
CC0375-SW-PIP-112 | A01-03 to A19-03 | Physical Works Complete | 2023-11-17 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2023-12-04 | 04-05-01 | 2024-03-29 | Yes | Yes | Yes | NCR -058 |  | No |  |  |  |  | 37 | Due | 37 | Due | No | No | Yes
CC0375-SW-PIP-113 | A03-03 to A30-02 with bends | Physical Works Complete | 2024-02-08 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-08 | 04-05-01 | 2024-02-08 | No | No | Not Required | [7 empty] | 87 | Overdue | 87 | Overdue | Yes | Yes | No
CC0375-SW-PIP-114 | A03-06 to A18-01 | Cancelled | 2024-03-11 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali |  | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-115 | A06-01 to A14-01 | Work In Progress | 2024-02-16 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-02-18 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PIP-116 | A01-03 to A19-03 | Work In Progress | 2024-03-22 | Stormwater Network | Pipe Installation | INF-HSEQ CC0375-ITP-002 Drainage (Pipe Laying) & Checklist | Sajjad Ali | 2024-03-22 | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PPIT-001 | Precast Pit-A10-02 | Closed | 2023-09-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-09-18 | 04-05-01 | 2023-09-22 | Yes | Yes | Not Required | [5 empty] | 2023-10-23 | 2023-10-24 | 31 | Due | 32 | Due | No | No | No
CC0375-SW-PPIT-002 | Precast Pit-A10-03 | Closed | 2023-09-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-09-19 | 04-05-01 | 2023-09-22 | Yes | Yes | Not Required | [5 empty] | 2023-10-24 | 2023-10-25 | 32 | Due | 33 | Due | No | No | No
CC0375-SW-PPIT-003 | Precast Pit-A03-01 | Closed | 2023-09-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-09-21 | 04-05-01 | 2023-09-25 | Yes | Yes | Not Required | [5 empty] | 2023-10-30 | 2023-11-03 | 35 | Due | 39 | Due | No | No | No
CC0375-SW-PPIT-004 | Precast Pit-A03-02 | Closed | 2023-09-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-09-22 | 04-05-01 | 2023-09-29 | Yes | Yes | Not Required | [5 empty] | 2023-10-30 | 2023-11-03 | 31 | Due | 35 | Due | No | No | No
CC0375-SW-PPIT-005 | Precast Pit-A03-03 | Closed | 2023-09-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-09-28 | 04-05-01 | 2023-09-29 | Yes | Yes | Not Required | [5 empty] | 2023-10-30 | 2023-12-18 | 31 | Due | 80 | Overdue | No | No | No
CC0375-SW-PPIT-006 | Precast Pit-A03-04 | Closed | 2023-09-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-03 | 04-05-01 | 2023-10-05 | Yes | Yes | Not Required | [5 empty] | 2023-10-30 | 2023-12-18 | 25 | Early | 74 | Overdue | No | No | No
CC0375-SW-PPIT-007 | Precast Pit-A03-05 | Closed | 2023-10-03 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-06 | 04-05-01 | 2023-10-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 67 | Overdue | 71 | Overdue | No | No | No
CC0375-SW-PPIT-008 | Precast Pit-A03-06 | Closed | 2023-10-03 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-07 | 04-05-01 | 2023-10-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 67 | Overdue | 71 | Overdue | No | No | No
CC0375-SW-PPIT-009 | Precast Pit-A03-07 | Closed | 2023-10-03 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-05 | 04-05-01 | 2023-10-10 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 65 | Overdue | 69 | Overdue | No | No | No
CC0375-SW-PPIT-010 | Precast Pit-A02-05 | Closed | 2023-10-03 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-06 | 04-05-01 | 2023-10-11 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 71 | Overdue | 99 | Overdue | No | No | No
CC0375-SW-PPIT-011 | Precast Pit-A07-01 | Closed | 2023-10-03 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-06 | 04-05-01 | 2023-10-11 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 71 | Overdue | 99 | Overdue | No | No | No
CC0375-SW-PPIT-012 | Precast Pit-A10-04 | Closed | 2023-10-09 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-10 | 04-05-01 | 2023-10-12 | Yes | Yes | Not Required | [5 empty] | 2024-02-07 | 2024-02-21 | 118 | Overdue | 132 | Overdue | No | No | No
CC0375-SW-PPIT-013 | Precast Pit-A25-05 | Closed | 2023-10-12 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-13 | 04-05-01 | 2023-10-19 | Yes | Yes | Not Required | [5 empty] | 2023-11-29 | 2023-12-19 | 41 | Due | 61 | Overdue | No | No | No
CC0375-SW-PPIT-014 | Precast Pit-A25-04 | Closed | 2023-10-12 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-14 | 04-05-01 | 2023-10-18 | Yes | Yes | Not Required | [5 empty] | 2023-11-29 | 2023-12-19 | 42 | Due | 62 | Overdue | No | No | No
CC0375-SW-PPIT-015 | Precast Pit-A25-03 | Closed | 2023-10-12 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-15 | 04-05-01 | 2023-10-18 | Yes | Yes | Not Required | [5 empty] | 2023-11-29 | 2023-12-19 | 42 | Due | 62 | Overdue | No | No | No
CC0375-SW-PPIT-016 | Precast Pit-A25-02 | Submitted To Client | 2023-10-12 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-15 | Yes | Yes | Yes | NCR-035 |  | Yes | 2024-03-08 |  | 2024-04-08 |  | 145 | Overdue | 172 | Overdue | No | No | No
CC0375-SW-PPIT-017 | Precast Pit-A28-01 | Closed | 2023-10-12 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-15 | Yes | Yes | Not Required |  |  | No |  |  | 2024-03-27 | 2024-03-27 | 133 | Overdue | 133 | Overdue | No | No | No
CC0375-SW-PPIT-018 | Precast Pit-A01-09 | Submitted To Client | 2023-10-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-14 | 04-05-01 | 2023-10-20 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 159 | Overdue | 198 | Overdue | No | No | No
CC0375-SW-PPIT-019 | Precast Pit-A01-10 | Submitted To Client | 2023-10-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-15 | 04-05-01 | 2023-10-20 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 159 | Overdue | 198 | Overdue | No | No | No
CC0375-SW-PPIT-020 | Precast Pit-A01-11 | Submitted To Client | 2023-10-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-10-17 | 04-05-01 | 2023-10-31 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 148 | Overdue | 187 | Overdue | No | No | No
CC0375-SW-PPIT-021 | Precast Pit A12-01 | Submitted To Client | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-15 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 57 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PPIT-022 | Precast Pit-A01-08 | Physical Works Complete | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-25 | No | No | Not Required | [7 empty] | 162 | Overdue | 162 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-023 | Precast Pit-A02-01 | Physical Works Complete | 2023-12-11 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-12-01 | 04-05-01 | 2023-12-01 | No | No | Not Required | [7 empty] | 156 | Overdue | 156 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-024 | Precast Pit A02-02 | Physical Works Complete | 2023-12-11 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-12-11 | 04-05-01 | 2023-12-07 | No | No | Not Required | [7 empty] | 150 | Overdue | 150 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-025 | Precast Pit A02-03 | Closed | 2023-10-30 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-01 | 04-05-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 42 | Due | 46 | Due | No | No | No
CC0375-SW-PPIT-026 | Precast Pit A16-02 | Submitted To Client | 2023-11-02 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-07 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 140 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PPIT-027 | Precast Pit A16-01 | Submitted To Client | 2023-11-02 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-06 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 140 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PPIT-028 | Precast Pit A15-01 | Submitted To Client | 2023-11-02 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-06 | 04-05-01 | 2023-11-08 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-03-27 |  | 140 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PPIT-030 | Precast Pit A20-04 | Submitted To Client | 2023-11-10 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-13 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 141 | Overdue | 174 | Overdue | No | No | No
CC0375-SW-PPIT-031 | Precast Pit A20-05 | Submitted To Client | 2023-11-10 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-02 | 04-05-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 146 | Overdue | 179 | Overdue | No | No | No
CC0375-SW-PPIT-032 | Precast Pit A20-03 | Closed | 2023-10-31 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-01 | 04-05-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 49 | Due | 77 | Overdue | No | No | No
CC0375-SW-PPIT-033 | Precast Pit A20-02 | Submitted To Client | 2023-10-30 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-01 | 04-05-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 146 | Overdue | 185 | Overdue | No | No | No
CC0375-SW-PPIT-034 | Precast Pit A20-01 | Submitted To Client | 2023-10-30 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-01 | 04-05-01 | 2023-11-02 | Yes | Yes | Not Required | [5 empty] | 2024-03-27 |  | 146 | Overdue | 185 | Overdue | No | No | No
CC0375-SW-PPIT-035 | Precast Pit A01-12 | Submitted To Client | 2024-01-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 96 | Overdue | 114 | Overdue | No | No | No
CC0375-SW-PPIT-036 | Precast Pit A01-13 | Submitted To Client | 2024-01-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 94 | Overdue | 112 | Overdue | No | No | No
CC0375-SW-PPIT-037 | Precast Pit A05-01 | Submitted To Client | 2024-01-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-20 | 04-05-01 | 2024-02-22 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 55 | Nearly Overdue | 73 | Overdue | No | No | No
CC0375-SW-PPIT-038 | Precast Pit A01-14 | Physical Works Complete | 2024-01-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-14 | No | No | Not Required | [7 empty] | 112 | Overdue | 112 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-039 | Precast Pit A1-15 | Physical Works Complete | 2024-03-04 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-03-04 | 04-05-01 | 2024-03-16 | [10 empty] | 50 | Nearly Overdue | 50 | Nearly Overdue | No | No | No
CC0375-SW-PPIT-040 | Precast Pit A01-16 | Physical Works Complete | 2024-03-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-03-07 | 04-05-01 | 2024-03-16 | [10 empty] | 50 | Nearly Overdue | 50 | Nearly Overdue | No | No | No
CC0375-SW-PPIT-041 | Precast Pit A02-04 | Closed | 2023-11-01 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-06 | 04-05-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 36 | Due | 40 | Due | No | No | No
CC0375-SW-PPIT-042 | Precast Pit A11-03 | Submitted To Client | 2024-01-05 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-08 | 04-05-01 | 2024-01-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 99 | Overdue | 116 | Overdue | No | No | No
CC0375-SW-PPIT-043 | Precast Pit A11-02 | Submitted To Client | 2024-01-05 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-08 | 04-05-01 | 2024-01-10 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 99 | Overdue | 116 | Overdue | No | No | No
CC0375-SW-PPIT-044 | Precast Pit A11-01 | Physical Works Complete | 2024-01-05 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-09 | 04-05-01 | 2024-01-10 | No | No | Not Required | [7 empty] | 116 | Overdue | 116 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-045 | Precast Pit A01-17 | Physical Works Complete | 2024-03-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-03-07 | 04-05-01 | 2024-03-19 | [10 empty] | 47 | Due | 47 | Due | No | No | No
CC0375-SW-PPIT-047 | Precast Pit A07-03 | Closed | 2023-11-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-06 | 04-05-01 | 2023-11-07 | Yes | Yes | Not Required | [5 empty] | 2023-12-14 | 2023-12-18 | 37 | Due | 41 | Due | No | No | No
CC0375-SW-PPIT-048 | Precast Pit A07-04 | Closed | 2023-11-02 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-07 | 04-05-01 | 2023-11-08 | Yes | Yes | Not Required | [5 empty] | 2023-12-21 | 2024-01-18 | 43 | Due | 71 | Overdue | No | No | No
CC0375-SW-PPIT-049 | Precast Pit A07-05 | Physical Works Complete | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-05 | 04-05-01 | 2024-02-09 | No | No | Not Required | [7 empty] | 86 | Overdue | 86 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-050 | Precast Pit-A28-02 | Closed | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-12-15 | 04-05-01 | 2023-11-16 | Yes | Yes | Not Required | NCR-035 |  | No |  |  | 2024-03-27 | 2024-03-27 | 132 | Overdue | 132 | Overdue | No | No | No
CC0375-SW-PPIT-051 | Precast Pit A02-12 | Physical Works Complete | 2023-11-24 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-24 | 04-05-01 | 2023-11-27 | No | No | Not Required | [7 empty] | 160 | Overdue | 160 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-052 | Precast Pit A02-11 | Physical Works Complete | 2023-11-24 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-24 | 04-05-01 | 2023-11-27 | No | No | Not Required | [7 empty] | 160 | Overdue | 160 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-053 | Precast Pit A02-10 | Physical Works Complete | 2023-11-11 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-11 | 04-05-01 | 2023-11-27 | No | No | Not Required | [7 empty] | 160 | Overdue | 160 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-054 | Precast Pit A22-04 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-31 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 71 | Overdue | 95 | Overdue | No | No | No
CC0375-SW-PPIT-055 | Precast Pit A22-03 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 75 | Overdue | 99 | Overdue | No | No | No
CC0375-SW-PPIT-056 | Precast Pit A22-02 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-26 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 76 | Overdue | 100 | Overdue | No | No | No
CC0375-SW-PPIT-057 | Precast Pit A22-01 | Physical Works Complete | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-23 | 04-05-01 | 2024-01-25 | No | No | Not Required | [7 empty] | 101 | Overdue | 101 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-058 | Precast Pit A02-09 | Submitted To Client | 2023-11-17 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-18 | 04-05-01 | 2023-11-21 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 79 | Overdue | 166 | Overdue | No | No | No
CC0375-SW-PPIT-059 | Precast Pit A23-05 | Physical Works Complete | 2023-11-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-30 | 04-05-01 | 2023-11-30 | No | No | Not Required | [7 empty] | 157 | Overdue | 157 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-060 | Precast Pit A23-04 | Physical Works Complete | 2023-11-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-28 | No | No | Not Required | [7 empty] | 159 | Overdue | 159 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-061 | Precast Pit A23-03 | Physical Works Complete | 2023-11-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-28 | No | No | Not Required | [7 empty] | 159 | Overdue | 159 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-062 | Precast Pit A23-02 | Physical Works Complete | 2023-11-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-27 | No | No | Not Required | [7 empty] | 160 | Overdue | 160 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-063 | Precast Pit A23-01 | Closed | 2023-11-28 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-28 | 04-05-01 | 2023-12-01 | Yes | Yes | Not Required | [5 empty] | 2024-02-07 | 2024-02-21 | 68 | Overdue | 82 | Overdue | No | No | No
CC0375-SW-PPIT-064 | Precast Pit A02-08 | Submitted To Client | 2023-11-11 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-17 | 04-05-01 | 2023-11-18 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 |  | 82 | Overdue | 169 | Overdue | No | No | No
CC0375-SW-PPIT-065 | Precast Pit-A02-07 | Submitted To Client | 2023-11-25 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-27 | 04-05-01 | 2023-11-27 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 133 | Overdue | 160 | Overdue | No | No | No
CC0375-SW-PPIT-066 | Precast A02-06 | Physical Works Complete | 2023-12-08 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-12-10 | 04-05-01 | 2024-01-02 | Yes | Yes | Not Required | [7 empty] | 124 | Overdue | 124 | Overdue | No | No | No
CC0375-SW-PPIT-067 | Precast Pit A04-01 | Submitted To Client | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-23 | 04-05-01 | 2024-02-09 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 62 | Overdue | 86 | Overdue | No | No | No
CC0375-SW-PPIT-068 | Precast Pit A04-02 | Submitted To Client | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-09 | 04-05-01 | 2024-02-12 | Yes | Yes | Not Required | [5 empty] | 2024-04-11 |  | 59 | Nearly Overdue | 83 | Overdue | No | No | No
CC0375-SW-PPIT-069 | Precast Pit A04-04 | Submitted To Client | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-14 | 04-05-01 | 2024-02-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 64 | Overdue | 81 | Overdue | No | No | No
CC0375-SW-PPIT-070 | Precast Pit A04-05 | Submitted To Client | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-15 | 04-05-01 | 2024-02-16 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 62 | Overdue | 79 | Overdue | No | No | No
CC0375-SW-PPIT-071 | Precast Pit A09-02 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-24 | 04-05-01 | 2024-01-25 | Yes | Yes | Not Required | [5 empty] | 2024-04-22 |  | 88 | Overdue | 101 | Overdue | No | No | No
CC0375-SW-PPIT-072 | Precast Pit A09-04 | Physical Works Complete | 2024-03-07 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-08 | 04-05-01 | 2024-02-12 | [10 empty] | 83 | Overdue | 83 | Overdue | No | No | No
CC0375-SW-PPIT-073 | A03-09 | Open | 2024-03-21 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | [15 empty] | No | No | No
CC0375-SW-PPIT-074 | Precast Pit A03-08 | Submitted To Client | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-14 | 04-05-01 | 2024-02-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-30 |  | 76 | Overdue | 81 | Overdue | No | No | No
CC0375-SW-PPIT-075 | Precast Pit A09-03 | Physical Works Complete | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-02-12 | [10 empty] | 83 | Overdue | 83 | Overdue | No | No | No
CC0375-SW-PPIT-076 | Precast A09-01 | Submitted To Client | 2024-01-17 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-17 | 04-05-01 | 2024-01-31 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 78 | Overdue | 95 | Overdue | No | No | No
CC0375-SW-PPIT-077 | Precast Pit A13-02 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-01 | 04-05-01 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 75 | Overdue | 93 | Overdue | No | No | No
CC0375-SW-PPIT-078 | Precast Pit A13-01 | Submitted To Client | 2024-01-17 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-01-31 | 04-05-01 | 2024-01-31 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 77 | Overdue | 95 | Overdue | No | No | No
CC0375-SW-PPIT-079 | Precast Pit-A06-03 | Physical Works Complete | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-12-15 | 04-05-01 | 2023-11-16 | No | No | Not Required | [7 empty] | 171 | Overdue | 171 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-080 | Precast Pit A13-03 | Submitted To Client | 2024-01-23 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-01 | 04-05-01 | 2024-02-02 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 75 | Overdue | 93 | Overdue | No | No | No
CC0375-SW-PPIT-083 | Precast Pit A10-06 | Physical Works Complete | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-01-27 | [10 empty] | 99 | Overdue | 99 | Overdue | No | No | No
CC0375-SW-PPIT-084 | Precast Pit A12-02 | Physical Works Complete | 2024-02-20 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-21 | 04-05-01 | 2024-02-05 | No | No | Not Required | [7 empty] | 90 | Overdue | 90 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-085 | Precast Pit A10-07 | Physical Works Complete | 2024-04-29 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-04-29 | 04-05-01 | 2024-04-30 | [10 empty] | 5 | Early | 5 | Early | No | No | No
CC0375-SW-PPIT-086 | Precast Pit A10-09 | Physical Works Complete | 2024-04-22 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-04-22 | 04-05-01 | 2024-04-24 | [10 empty] | 11 | Early | 11 | Early | No | No | No
CC0375-SW-PPIT-087 | A10-10 | Physical Works Complete | 2024-04-22 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-04-21 | 04-05-01 | 2024-04-24 | [10 empty] | 11 | Early | 11 | Early | No | No | No
CC0375-SW-PPIT-088 | Precast Pit A06-05 | Submitted To Client | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 140 | Overdue | 173 | Overdue | No | No | No
CC0375-SW-PPIT-089 | Precast Pit-A06-04 | Submitted To Client | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-14 | 04-05-01 | 2023-11-14 | Yes | Yes | Not Required | [5 empty] | 2024-04-02 |  | 140 | Overdue | 173 | Overdue | No | No | No
CC0375-SW-PPIT-090 | Precast Pit- A06-02 | Submitted To Client | 2023-11-13 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-15 | 04-05-01 | 2023-11-15 | Yes | Yes | Yes | NCR-045 |  | Yes | 2024-03-08 |  | 2024-04-02 |  | 139 | Overdue | 172 | Overdue | No | No | No
CC0375-SW-PPIT-091 | Precast Pit A06-01 | Physical Works Complete | 2024-02-06 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-19 | 04-05-01 | 2024-02-21 | No | No | Not Required | [7 empty] | 74 | Overdue | 74 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-092 | Precast Pit A14-02 | Submitted To Client | 2024-02-16 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-15 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 56 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PPIT-093 | Precast Pit A14-02 | Submitted To Client | 2024-02-16 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-16 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-17 |  | 56 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PPIT-094 | Precast Pit A17-04 | Physical Works Complete | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-06 | [10 empty] | 60 | Overdue | 60 | Overdue | No | No | No
CC0375-SW-PPIT-096 | Precast Pit A17-03 | Physical Works Complete | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-03-06 | [10 empty] | 60 | Overdue | 60 | Overdue | No | No | No
CC0375-SW-PPIT-097 | Precast Pit A17-02 | Physical Works Complete | 2024-02-14 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | 2024-02-25 | [10 empty] | 70 | Overdue | 70 | Overdue | No | No | No
CC0375-SW-PPIT-098 | Precast Pit A10-01 | Physical Works Complete | 2023-11-15 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2023-11-16 | 04-05-01 | 2023-11-21 | No | No | Yes | NCR-045 |  | Yes |  | NCR-045 |  |  | 166 | Overdue | 166 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-099 | Precast Pit A12-02 | Submitted To Client | 2024-02-20 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-02-21 | 04-05-01 | 2024-02-21 | Yes | Yes | Not Required | [5 empty] | 2024-04-18 |  | 57 | Nearly Overdue | 74 | Overdue | No | No | No
CC0375-SW-PPIT-100 | Precast Pit A08-01 | Physical Works Complete | 2024-02-29 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali | 2024-03-01 | 04-05-01 | 2024-03-01 | No | No | Not Required | [7 empty] | 65 | Overdue | 65 | Overdue | Yes | Yes | No
CC0375-SW-PPIT-101 | A18-01 | Open | 2024-03-21 | Stormwater Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Sajjad Ali |  | 04-05-01 | [15 empty] | No | No | No
CC0375-TW-IPPIT-001 | Insitu Pit-W02-10 | Work In Progress | 2023-05-16 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-16 | 04-07-01 | 2023-05-19 | No | No | Not Required | [7 empty] | 352 | Overdue | 352 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-002 | Insitu Pit-W02-11 | Work In Progress | 2023-04-26 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-04-26 | 04-07-01 | 2023-05-16 | No | No | Not Required | [7 empty] | 355 | Overdue | 355 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-003 | Insitu Pit-W02-13 | Work In Progress | 2023-04-26 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-04-26 | 04-07-01 | 2023-05-14 | No | No | Not Required | [7 empty] | 357 | Overdue | 357 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-004 | Insitu Pit-W02-15 | Work In Progress | 2023-04-26 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-04-26 | 04-07-01 | 2023-05-12 | No | No | Not Required | [7 empty] | 359 | Overdue | 359 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-005 | Insitu Pit-W02-17 | Open | 2023-10-26 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith |  | 04-07-01 | [15 empty] | No | No | No
CC0375-TW-IPPIT-006 | Insitu Pit-W02-08 | Work In Progress | 2023-05-16 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-16 | 04-07-01 | 2023-06-20 | No | No | Not Required | [7 empty] | 320 | Overdue | 320 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-007 | Insitu Pit-W02-09 | Work In Progress | 2023-05-16 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-16 | 04-07-01 | 2023-06-07 | No | No | Not Required | [7 empty] | 333 | Overdue | 333 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-008 | Insitu Pit-W01-01 | Work In Progress | 2023-06-14 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-06-15 | 04-07-01 | 2023-06-23 | No | No | Not Required | [7 empty] | 317 | Overdue | 317 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-009 | Insitu Pit-W03-01 | Work In Progress | 2023-05-22 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-22 | 04-07-01 | 2023-05-22 | No | No | Not Required | [7 empty] | 349 | Overdue | 349 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-010 | Insitu Pit-W02-18 | Work In Progress | 2023-06-29 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-06-29 | 04-07-01 | 2023-07-11 | No | No | Not Required | [7 empty] | 299 | Overdue | 299 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-011 | Insitu Pit-W04-3 | Work In Progress | 2023-05-19 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-20 | 04-07-01 | 2023-05-21 | No | No | Not Required | [7 empty] | 350 | Overdue | 350 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-012 | Insitu Pit-W04-4 | Work In Progress | 2023-05-19 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-19 | 04-07-01 | 2023-06-01 | No | No | Not Required | [7 empty] | 339 | Overdue | 339 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-013 | Insitu Pit-W04-5 | Open | 2024-02-05 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith |  | 04-07-01 | 2023-10-26 | No | No | Not Required | [7 empty] | 192 | Overdue | 192 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-014 | Insitu Pit-W04-6 | Work In Progress | 2023-05-30 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-30 | 04-07-01 | 2023-06-09 | No | No | Not Required | [7 empty] | 331 | Overdue | 331 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-015 | Insitu Pit-W04-8 | Work In Progress | 2023-05-31 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-31 | 04-07-01 | 2023-06-09 | No | No | Not Required | [7 empty] | 331 | Overdue | 331 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-016 | Insitu Pit-W04-10 | Work In Progress | 2023-05-31 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-05-31 | 04-07-01 | 2023-06-13 | No | No | Not Required | [7 empty] | 327 | Overdue | 327 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-017 | Insitu Pit-W04-12 | Work In Progress | 2023-06-06 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-06-06 | 04-07-01 | 2023-06-20 | No | No | Not Required | [7 empty] | 320 | Overdue | 320 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-018 | Insitu Pit-W04-13 | Work In Progress | 2023-08-07 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-08-08 | 04-07-01 | 2023-08-11 | No | No | Not Required | [7 empty] | 268 | Overdue | 268 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-019 | Insitu Pit-W05-1 | Work In Progress | 2023-08-07 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-08-10 | 04-07-01 | 2023-08-16 | No | No | Not Required | [7 empty] | 263 | Overdue | 263 | Overdue | Yes | Yes | No
CC0375-TW-IPPIT-020 | Insitu Pit-W06-1 | Work In Progress | 2023-08-19 | Trade Waste Network | Insitu Pits | INF-HSEQ CC0375-ITP-011 Drainage (Cast In-situ Structures) Checklist | Jackson Smith | 2023-08-21 | 04-07-01 | 2023-08-30 | No | No | Not Required | [7 empty] | 249 | Overdue | 249 | Overdue | Yes | Yes | No
CC0375-TW-PIP-001 | W04-02 to W04-01 | Closed | 2023-04-03 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-03 | 04-07-01 | 2023-04-06 | Yes | Yes | Not Required | [5 empty] | 2023-08-30 | 2023-12-20 | 146 | Overdue | 258 | Overdue | No | No | No
CC0375-TW-PIP-002 | W04-01 to W02-05 | Closed | 2023-04-03 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-18 | 04-07-01 | 2023-04-21 | Yes | Yes | Not Required | [5 empty] | 2023-12-19 | 2023-12-20 | 242 | Overdue | 243 | Overdue | No | No | No
CC0375-TW-PIP-003 | W02-05 to W02-06 | Closed | 2023-04-18 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-01 | 04-07-01 | 2023-05-02 | Yes | Yes | Not Required | [5 empty] | 2023-08-30 | 2023-12-20 | 120 | Overdue | 232 | Overdue | No | No | No
CC0375-TW-PIP-004 | W02-06 to W02-07 | Closed | 2023-05-02 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-04 | 04-07-01 | 2023-05-06 | Yes | Yes | Yes | NCR-016 |  | Yes | 2023-11-01 |  | 2023-11-01 | 2023-12-20 | 179 | Overdue | 228 | Overdue | No | No | No
CC0375-TW-PIP-005 | W02-10 to W02-11 | Closed | 2023-04-26 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-26 | 04-07-01 | 2023-04-28 | Yes | Yes | Not Required | [5 empty] | 2023-12-19 | 2023-12-20 | 235 | Overdue | 236 | Overdue | No | No | No
CC0375-TW-PIP-006 | W02-11 to W02-13 | Closed | 2023-04-26 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-27 | 04-07-01 | 2023-04-28 | Yes | Yes | Yes | NCR-016 |  | Yes | 2023-11-01 |  | 2024-02-08 | 2024-02-21 | 286 | Overdue | 299 | Overdue | No | No | No
CC0375-TW-PIP-007 | W02-13 to W02-15 | Closed | 2023-04-26 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-27 | 04-07-01 | 2023-04-28 | Yes | Yes | Yes | NCR-016 |  | Yes | 2023-11-01 |  | 2024-02-08 | 2024-02-21 | 286 | Overdue | 299 | Overdue | No | No | No
CC0375-TW-PIP-008 | W02-15 to W02-17 | Physical Works Complete | 2023-04-26 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-04-26 | 04-07-01 | 2024-01-08 | No | No | Not Required | [7 empty] | 118 | Overdue | 118 | Overdue | Yes | Yes | No
CC0375-TW-PIP-009 | W02-07 to W02-08 | Closed | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-08 | 04-07-01 | 2023-05-09 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 275 | Overdue | 288 | Overdue | No | No | No
CC0375-TW-PIP-010 | W02-08 to W02-09 | Closed | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-10 | 04-07-01 | 2023-05-11 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 273 | Overdue | 286 | Overdue | No | No | No
CC0375-TW-PIP-011 | W02-09 to W02-10 | Physical Works Complete | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-12 | 04-07-01 | 2023-05-12 | No | No | Not Required | [7 empty] | 359 | Overdue | 359 | Overdue | Yes | Yes | No
CC0375-TW-PIP-012 | W02-08 to W01-01 | Physical Works Complete | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-12 | 04-07-01 | 2023-05-12 | No | No | Not Required | [7 empty] | 359 | Overdue | 359 | Overdue | Yes | Yes | No
CC0375-TW-PIP-013 | W02-09 to W03-01 | Closed | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-12 | 04-07-01 | 2023-05-12 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 | 2024-02-21 | 265 | Overdue | 285 | Overdue | No | No | No
CC0375-TW-PIP-014 | W04-02 to W04-03 | Closed | 2023-05-16 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-16 | 04-07-01 | 2023-05-17 | Yes | Yes | Yes | NCR-016 |  | Yes | 2023-11-01 |  | 2023-11-01 | 2023-12-20 | 168 | Overdue | 217 | Overdue | No | No | No
CC0375-TW-PIP-015 | W04-03 to W04-04 | Closed | 2023-05-16 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-17 | 04-07-01 | 2023-05-18 | Yes | Yes | Yes | NCR-016 |  | Yes | 2023-11-01 |  | 2024-02-08 | 2024-02-21 | 266 | Overdue | 279 | Overdue | No | No | No
CC0375-TW-PIP-016 | W04-03 to W05-01 | Closed | 2023-07-12 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-23 | 04-07-01 | 2023-08-23 | Yes | Yes | Not Required | [5 empty] | 2023-12-19 | 2023-12-20 | 118 | Overdue | 119 | Overdue | No | No | No
CC0375-TW-PIP-017 | W04-04 to W06-01 | Closed | 2023-07-12 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-09-14 | 04-07-01 | 2023-09-15 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 206 | Overdue | 220 | Overdue | No | No | No
CC0375-TW-PIP-018 | W04-06 to W04-08 | Closed | 2023-05-05 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-30 | 04-07-01 | 2023-05-30 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 254 | Overdue | 267 | Overdue | No | No | No
CC0375-TW-PIP-019 | W04-08 to W04-10 | Closed | 2023-05-30 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-05-31 | 04-07-01 | 2023-06-01 | Yes | Yes | Not Required | [5 empty] | 2024-02-08 | 2024-02-21 | 252 | Overdue | 265 | Overdue | No | No | No
CC0375-TW-PIP-020 | W04-10 to W04-12 | Closed | 2023-06-06 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-06-07 | 04-07-01 | 2023-06-07 | Yes | Yes | Not Required | NCR-034 |  | No |  |  | 2024-04-08 | 2024-04-22 | 306 | Overdue | 320 | Overdue | No | No | No
CC0375-TW-PIP-021 | W02-01 to W02-02 | Physical Works Complete | 2023-07-18 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-25 | 04-07-01 | 2023-07-26 | No | No | Not Required | [7 empty] | 284 | Overdue | 284 | Overdue | Yes | Yes | No
CC0375-TW-PIP-022 | W02-02 to W02-03 | Closed | 2023-07-18 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-26 | 04-07-01 | 2023-08-01 | Yes | Yes | Not Required | NCR-00034 |  | No |  |  | 2023-12-19 | 2023-12-20 | 140 | Overdue | 141 | Overdue | No | No | No
CC0375-TW-PIP-023 | W02-03 to W02-04 | Closed | 2023-07-18 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-01 | 04-07-01 | 2023-08-04 | Yes | Yes | Not Required | NCR-00034 |  | No |  |  | 2023-12-19 | 2023-12-20 | 137 | Overdue | 138 | Overdue | No | No | No
CC0375-TW-PIP-024 | W02-04 to W02-05 | Closed | 2023-07-18 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-04 | 04-07-01 | 2023-08-12 | Yes | Yes | Not Required | [5 empty] | 2024-02-22 | 2024-02-27 | 194 | Overdue | 199 | Overdue | No | No | No
CC0375-TW-PIP-025 | W02-17 to W02-18 | Closed | 2023-07-19 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-07-20 | 04-07-01 | 2024-01-08 | Yes | Yes | Not Required | [5 empty] | 2024-02-01 | 2024-02-21 | 24 | Early | 44 | Due | No | No | No
CC0375-TW-PIP-026 | W04-12 to W04-13 | Physical Works Complete | 2023-08-22 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-08-24 | 04-07-01 | 2023-08-24 | No | No | Yes | NCR-034 |  | Yes |  |  |  |  | 255 | Overdue | 255 | Overdue | Yes | Yes | No
CC0375-TW-PIP-028 | W02-18 to W02-19 | Work In Progress | 2023-12-16 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-18 | 04-07-01 | [15 empty] | No | No | No
CC0375-TW-PIP-031 | W02-02 to W07-01 | Physical Works Complete | 2024-01-09 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2024-02-08 | 04-07-01 | 2024-02-08 | No | No | Not Required | [7 empty] | 87 | Overdue | 87 | Overdue | Yes | Yes | No
CC0375-TW-PIP-032 | W08-01 to W09-01 | Physical Works Complete | 2024-01-08 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2024-01-10 | 04-07-01 | 2024-01-09 | No | No | Not Required | [7 empty] | 117 | Overdue | 117 | Overdue | Yes | Yes | No
CC0375-TW-PIP-033 | W08-02 to W11-02 | Physical Works Complete | 2024-01-08 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2024-01-10 | 04-07-01 | 2024-01-11 | No | No | Not Required | [7 empty] | 115 | Overdue | 115 | Overdue | Yes | Yes | No
CC0375-TW-PIP-034 | W10-01 to W10-06 | Physical Works Complete | 2023-12-01 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-005 Trade Waste (Pipe Laying) & Checklist | Mahmoud Medoukh | 2023-12-01 | 04-07-01 | 2024-01-11 | No | No | Not Required | [7 empty] | 115 | Overdue | 115 | Overdue | Yes | Yes | No
CC0375-TW-PIP-035 | North-East HDPE Line | Physical Works Complete | 2024-02-01 | Trade Waste Network | Pipe Installation | INF-HSEQ CC0375-ITP-019 HDPE Pipe Installation | Mathew Chambers | 2024-02-04 | 04-07-01 | 2024-04-24 | No | No | Yes | NCR -058 |  | No |  |  |  |  | 11 | Early | 11 | Early | Yes | Yes | Yes
CC0375-TW-PPIT-001 | Precast Pit-W04-02 | Closed | 2023-04-03 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-04-15 | 04-07-01 | 2023-04-20 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-12-19 | 147 | Overdue | 243 | Overdue | No | No | No
CC0375-TW-PPIT-002 | Precast Pit-W04-01 | Closed | 2023-04-03 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-04-15 | 04-07-01 | 2023-04-20 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-12-19 | 147 | Overdue | 243 | Overdue | No | No | No
CC0375-TW-PPIT-003 | Precast Pit-W02-05 | Physical Works Complete | 2023-04-03 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-04-14 | 04-07-01 | 2023-04-21 | No | No | Not Required | TBA |  | No |  | To be raised |  |  | 380 | Overdue | 380 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-004 | Precast Pit-W02-06 | Closed | 2023-04-18 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-04-25 | 04-07-01 | 2023-05-10 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-09-14 | 2023-12-19 | 127 | Overdue | 223 | Overdue | No | No | No
CC0375-TW-PPIT-005 | Precast Pit-W02-07 | Closed | 2023-05-02 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-05-05 | 04-07-01 | 2023-05-10 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-12-19 | 127 | Overdue | 223 | Overdue | No | No | No
CC0375-TW-PPIT-006 | Precast Pit-W02-02 | Closed | 2023-07-18 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-25 | 04-07-01 | 2023-08-01 | Yes | Yes | Not Required | [5 empty] | 2023-09-14 | 2023-12-19 | 44 | Due | 140 | Overdue | No | No | No
CC0375-TW-PPIT-007 | Precast Pit-W02-03 | Closed | 2023-07-18 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-07-28 | 04-07-01 | 2023-08-07 | Yes | Yes | Not Required | NCR-034 | 2023-08-22 | No | 2023-09-27 |  | 2024-04-08 | 2024-04-22 | 245 | Overdue | 259 | Overdue | No | No | No
CC0375-TW-PPIT-008 | Precast Pit-W02-04 | Closed | 2023-07-18 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-08-02 | 04-07-01 | 2023-08-17 | Yes | Yes | Yes | NCR-016 | 2023-08-22 | Yes | 2023-09-27 |  | 2023-12-13 | 2023-12-19 | 118 | Overdue | 124 | Overdue | No | No | No
CC0375-TW-PPIT-009 | Precast Pit W02-17 | Submitted To Client | 2023-12-22 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2024-01-02 | 04-07-01 | 2024-01-15 | Yes | Yes | Yes | NCR-016 | 2022-08-22 | Yes | 2023-09-27 |  | 2024-04-08 |  | 84 | Overdue | 111 | Overdue | No | No | No
CC0375-TW-PPIT-010 | Precast Pit W10-02 | Physical Works Complete | 2023-12-08 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2024-01-10 | 04-07-01 | 2023-12-17 | No | No | Not Required | [7 empty] | 140 | Overdue | 140 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-011 | Precast Pit W10-03 | Physical Works Complete | 2023-12-08 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-12-10 | 04-07-01 | 2023-12-17 | No | No | Not Required | [7 empty] | 140 | Overdue | 140 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-012 | Precast Pit W10-04 | Physical Works Complete | 2023-12-08 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-12-10 | 04-07-01 | 2023-12-17 | No | No | Not Required | [7 empty] | 140 | Overdue | 140 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-013 | Precast Pit W11-01 | Physical Works Complete | 2023-12-15 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-12-16 | 04-07-01 | 2023-12-20 | No | No | Not Required | [7 empty] | 137 | Overdue | 137 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-014 | Precast Pit W11-02 | Physical Works Complete | 2023-12-15 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-12-16 | 04-07-01 | 2023-12-20 | No | No | Not Required | [7 empty] | 137 | Overdue | 137 | Overdue | Yes | Yes | No
CC0375-TW-PPIT-015 | Precast Pit W09-01 | Submitted To Client | 2023-12-15 | Trade Waste Network | Precast Pits | INF-HSEQ CC0375-ITP-003 Drainage (Pre-cast Structures) & Checklist | Mahmoud Medoukh | 2023-12-16 | 04-07-01 | 2023-12-20 | Yes | Yes | Not Required | [5 empty] | 2024-04-08 |  | 110 | Overdue | 137 | Overdue | No | No | No