## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Tiling ITP |  |  |  |  | Yes | Tiling ITP | 7291579c-a02b-4384-9614-e2f46b21106b
checkpoint-group |  |  | section | 1. Check Drawing
checkpoint-status |  |  | checkpoint | Confirm Drawing, specification and revision #
label | 771fc7c6-0533-5961-8aab-5f30ea7af078 |  | note | Inspection: admin
select | 708d54f9-7e7d-58dc-a948-ba39b5b8959d |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 2. Substrate Prep - Wall
checkpoint-status |  |  | checkpoint | Inspect for wall quality to accept tiles and ensure that substrate free from debris
label | 3e04e220-7381-59db-a8bb-ee315341237b |  | note | Inspection: visual
select | 28163313-12a9-53f7-bb7f-5a9e21d6f356 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Clean and dry
label | 867a744f-89fb-5344-b051-a7b624bf8ce6 |  | note | Inspection: visual
select | 651bb41a-dfa2-5a77-9d57-38046c98385c |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Joints Sealed
label | 28ecc26a-42ec-5f85-8dd5-c6d52a2928bb |  | note | Inspection: visual
select | 8418f01f-3d4a-59cd-9629-e291963f6fa6 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 3. Substrate Prep - Floor
checkpoint-status |  |  | checkpoint | Inspect concrete substrate free from debris Cracks >0.2mm to be filled with Polyurethane
label | 2a192dec-27eb-5c8c-9132-c8fe70a34be3 |  | note | Inspection: visual
select | 71fe2ba5-0f3c-589a-8141-06b03b1ee4c3 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Clean and dry
label | 45867f06-16cf-5329-aab2-9b013c5ab1dd |  | note | Inspection: visual
select | de2f9c30-c4d1-59e3-a6f1-a58b93f94590 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 4. Tile Termination Points
checkpoint-status |  |  | checkpoint | Locate termination points and set for Angle location at door entry.
label | 20536554-c674-5bae-a156-b4e1b154b6a2 |  | note | Inspection: visual / setout / laser
select | f974d1e8-b072-50cc-93e5-9a42650fe874 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Set angle / termination points under door leaf
label | ec4b83c5-8f47-509b-a4a3-f9b472a26e50 |  | note | Inspection: visual / setout / laser
select | a15327ea-fd7b-50ba-a8cb-4e82393cbf3e |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Correct RL as per architectural drawings
label | a580c396-3e80-56ee-80a7-23385c33e00f |  | note | Inspection: visual / setout / laser
select | 4e351354-120f-54ec-9813-ddcfe1d015fe |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 5. HOLD POINT
checkpoint-status |  |  | checkpoint | Waterproofing membrane inspected by Toga and approved to receive screed beds. Check with waterproofer for go ahead
label | 7062d763-f98c-51be-9c74-31523b6bdd84 |  | note | Inspection: site foreman / waterproofing contractor
select | 7136c814-ede8-51cc-9963-b5a3dceddc61 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 6. Sand and Cement Bedding
checkpoint-status |  |  | checkpoint | Screed mixed by machine ratio1:4
label | 880e11fd-36f7-5cff-b8d0-48cb8582989a |  | note | Inspection: 100L stand mixer
select | 493dce4b-a74d-54fe-a77e-c028e64aa2e8 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Floorwastes protected to prevent debris entering into drains with compressible sponges
label | 7b54c8f2-3fde-53b0-88e3-47bc73e98dbd |  | note | Inspection: visual
select | e2c5c680-10e3-58fd-a833-6a96e6bca1ba |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Clearout pipework to finish at screed bed level
select | 25b49733-df46-56fc-86e0-5f0542a6332d |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 7. HOLD POINT
checkpoint-status |  |  | checkpoint | Setout and starting point verified with Builder and Drawings
label | d1f74977-6ba4-558c-8bad-7ab77b71bafd |  | note | Inspection: laser / visual / chalk line
select | 9bce1a4d-21a7-5140-b053-62560e3c52a3 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Ensure standard sceed thickness minimum of 15mm.
label | 5c58317b-b512-5050-8a7b-7ecda328a464 |  | note | Inspection: visual / guage
select | ffcb9118-1610-5811-bce5-634bf7ee8c42 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Screed areas lower than 15mm to minimum 10mm to recieve engineered binder (Keracem ECO in replacement of Grey cement)
label | 25998d9e-a45f-5a3b-8d5d-d8c4489d64a8 |  | note | Inspection: visual / guage / markup
select | c7d0c411-bb4e-5d53-89d0-f4eeec5d41a0 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Where screed beds lower than 10mm use Keralevel LR with Universal Primer
label | fb53584d-7dad-595d-964a-b5f03be72d0f |  | note | Inspection: visual / guage / markup
select | 9cf2a9d9-0b39-52fc-9e65-45335eece19b |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 24hrs curing minimum
label | 1a780cfe-8dae-5e23-97a3-1cd7af689403 |  | note | Inspection: visual / guage / markup
select | 1f3d6f04-b78e-52b1-b0fc-e7a3c2a05695 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 8. Acoustic
checkpoint-status |  |  | checkpoint | Ensure substrate free from loose material to maximise bond to acoustic mat / screed bed
label | 4177a373-8c45-51c6-9e01-601cc1e50b67 |  | note | Inspection: visual
select | aa6ee990-dcf1-5380-b0b8-a072a912bf49 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 4mm notch trowel / bioflex grey adhesive
label | bff15328-3de2-599f-ac14-052d98ee91fa |  | note | Inspection: visual
select | 5423eea7-ad2c-5dc6-8a8d-a6f56fe828c4 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Ensure acoustic matting has no gaps / weighted roller
label | d66784d8-dd94-535e-81f4-92c66d63b119 |  | note | Inspection: visual
select | f9be7214-07c5-58ee-9541-67e5a0fe4b3f |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Any gaps to be filled with Polyurethane and finished flush
label | 9dadb359-edc0-5474-97fe-61be2095b9d7 |  | note | Inspection: visual
select | 9467e419-69e4-5a9a-b368-1a01e7aadeeb |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 9. Inspect Tile Laying
checkpoint-status |  |  | checkpoint | Quality (Set-out, tile cuts, even joints & flatness)
label | aab8532d-4b2a-56ea-b3a0-6538aca4cad8 |  | note | Inspection: visual / straightedge
select | 2483f1a3-d336-53cf-bcf7-61daff02d6f6 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Set-out as per drawing
label | 8fd77c76-0e82-5597-9513-a6f9eb4ef778 |  | note | Inspection: visual
select | 402c4119-d2d4-5846-832a-f9be58aca75d |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Verify strip drain size and position of waste outlet
label | 87723885-705b-5fa9-9dff-5de99ff57bf6 |  | note | Inspection: visual
select | 1e96b90d-34b7-5c2e-84f6-f579cf6feac9 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Falls to waste as per drawing / isolate falls to waste
label | 62545cfc-8d7c-5e10-9662-1902ce4de10b |  | note | Inspection: visual
select | 6c47179d-8f8c-551d-8b4a-0d290a2a7843 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | No lipping tiles exceeding A.S tolerances 1.5mm
label | 3afad3cf-4548-58ac-b2d9-b61c27b5c57b |  | note | Inspection: visual
select | d3545ece-eab1-50a5-ab8d-0410816415b9 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 10. Preseal
checkpoint-status |  |  | checkpoint | General sweep clean of terrazzo floors
label | 3309f117-4908-55c6-b1f5-449ee8936d60 |  | note | Inspection: visual
select | fee66047-5b0b-5682-8132-ed1a3a0721dd |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Wet wipe excess dust off tile surface
label | 7b49d7dc-f0e4-5300-aac3-17c42796f99c |  | note | Inspection: visual
select | b6fd3da3-d95a-5297-8c7b-11fc157c9dd3 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Lambs wool application of presealer to terrazzo floor surface prior to grouting - 1 coat
label | b5d94f0c-98e0-5457-824a-a79254c644db |  | note | Inspection: visual
select | f5bc534c-e9ff-5e60-9891-f1e6cf141324 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Allow preseal to cure minimum 8 hours before grouting. Area to be baricaded off from entering.
label | ec84285b-c4d7-5010-9c8c-f2787dc98261 |  | note | Inspection: visual
select | 42fc9028-5a85-582b-b7c7-ba8ad10744db |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 11. Grouting
checkpoint-status |  |  | checkpoint | Grout mixed by machine
label | 8eefe2f8-c703-5593-ae0f-b69a0652244a |  | note | Inspection: visual
select | f332ff09-da0a-5988-a38c-49a95df250e1 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Joints free from debris / spacers
label | 5ac36d27-72b5-5445-9605-08d90f9bbcf5 |  | note | Inspection: visual
select | 7cbe8798-b0f0-5baf-9575-26245048d01a |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Surface is uniform and clean / no grout build up / internal corners free of grout
label | df5bb407-c65e-50d0-83c6-d6c1404d00e8 |  | note | Inspection: visual
select | 3d146264-f327-5567-a8ec-0c5fcd28717b |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 12. Protection
checkpoint-status |  |  | checkpoint | Corflute taped down (no black corflute) cover entire tiled surface
label | e1dbcf2b-b24b-5c80-ac59-1b913dc204ed |  | note | Inspection: visual
select | f4d2d48f-9795-5beb-889e-c02b8619f35d |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | Make allowance for toilet pans, partitions / glass installation
label | 45f82cfb-38e8-54a2-a0c6-1077f57a2782 |  | note | Inspection: visual
select | 9d0f249d-d8ef-520e-a9da-497007ed4fbd |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-group |  |  | section | 13. Repair Any
checkpoint-no-status |  |  | checkpoint | Repair Any
checkpoint-group |  |  | section | 14. Final Inspection
checkpoint-no-status |  |  | checkpoint | Final Inspection
text | 7b0fb972-c0f9-5334-b9bd-01bbd0ec6ac5 |  | textbox | Position:
date | 27888008-0d64-57a9-9d5c-18387395c5ab |  | date | Date:
holdpoint |  |  | signoff | Prepared By:
checklist-sectioned |  |  | checklist | Waterproofing ITP |  |  |  |  | Yes | Waterproofing ITP | 7e2f745e-19a2-4457-a483-48d4ada29313
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | 1. Waterproofer to inspect substrate to confirm acceptability. Ensure clean, dry, devoid of contamination and excess dust removed and vacuumed.
label | 9bdf6290-8d7b-5159-abea-7411c74c4d02 |  | note | Inspection: visual
select | 0e8ea806-4589-58a5-b398-69fcb61fdc65 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 2. Fillet bond breaker using Aquastop 70 tape and Nanosil to improve adhesion. Ensure all tape is bonded to the substrate.
label | e0da82ac-5aa3-55ac-b18d-30ee6c8c9965 |  | note | Inspection: visual
select | c370b75e-14fb-5e5c-87f1-3808071a089a |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 3. Polyurethane fillet to internal vertical corners in shower, at junction of concrete with puddleflange, clearout, pipework
label | e44b8ba1-950a-585c-bf7c-298671727745 |  | note | Inspection: visual
select | 2c7e41f2-01e2-5172-a71c-4f2919cdeb50 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 4. Primer A Eco to be applied to porous substrate (Data Sheet attached) All concrete and wall linings
label | 566d87d0-f07e-532f-96a5-dd178e9baaf1 |  | note | Inspection: visual
select | 840dd0d9-5330-5fb0-9547-16891ff84732 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 5. Prime Keragrip Eco for non porous primer (Data sheet attached) Angles, puddlefalnges, threaded pipework
label | 765f12c5-f1a0-5c0e-ac57-f252e7ea980d |  | note | Inspection: visual
select | b1ddf47f-fb74-5f7e-a85c-c034faa3c637 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 6. 1st Coat Kera Trade WPM (Data Sheet attached) Applied to floor, 150mm high including perimeter banding and 200mm above shower rose and extending 200mm past shower screen location. Extend to vanity 150mm min. surround to side and above vanity shelf. Extend 150mm below level of vanity.
label | ced7c6d1-587e-5b12-8f25-5130c34e6425 |  | note | Inspection: visual
select | 0c64e9be-81a5-5655-8e38-5d6e3c3ab940 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 7. 24hr Curing (Typical*) *curing time are typical, refer to manufacturer spec for product curing times
label | b3f85187-ab13-57e3-a814-5b2926d560a5 |  | note | *curing time are typical, refer to manufacturer spec for product curing times
label | f39fdbb5-c41a-5480-a5b1-cb985bbe6082 |  | note | Inspection: visual and touch
select | 457cebc4-3a7a-5c39-822b-a8e74c6a6a46 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 8. 2nd Coat Keratrade WPM applied
label | ccd984b9-4190-5aee-88b9-fca4cb71bffa |  | note | Inspection: visual and touch
select | 7b160cd5-bf99-50e9-b393-82b2ff31e49b |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 9. 48hr Curing (Typical*)
label | 2ad89966-0978-508b-9791-6beb167e2f5c |  | note | *curing time are typical, refer to manufacturer spec for product curing times
label | f45d3cd0-7369-50d1-861c-fbda48b52a88 |  | note | Inspection: visual and touch
select | 25b9702b-8839-5f52-be19-dff94964069b |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 10. Dry Film Thickness (DFT) Test completed min 1.13mm
label | 9a94ca08-23d1-5b99-9238-e748891ca09a |  | note | Inspection: electronic testing
select | c732c0c5-4d4d-5901-81e4-615931c5deaa |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 11. 24hr Water Test
label | 365778d1-ae72-5890-83eb-5703e1a4bb30 |  | note | Inspection: visual and marker
select | 69aace4b-9ea0-52ec-8775-9fdcf9e10838 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 12. Final Water Test Measure Completed - AS3740-2010
label | 1cffe44d-85e4-5b37-aa30-299f2f2cddf7 |  | note | Inspection: visual
select | dbd87837-0d66-5053-bb8d-2bbb7c13bcee |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint-status |  |  | checkpoint | 13. Drain Down by waterproof installer
label | 762a48d1-3237-51d6-bd3d-f12d8c4d9d1b |  | note | Inspection: visual
select | 6cd87419-ae69-5f81-8562-86e1274f5c70 |  | dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint |  |  | signoff | 14. Waterproof installer to check / provide go ahead
checkpoint-group |  |  | section | 15. RECTIFICATION ITEMS
checkpoint-status |  |  | checkpoint | RECTIFICATION ITEMS
checkpoint-status |  |  | checkpoint | 16. Area Handover to Tiler
holdpoint |  |  | signoff | Verify with Tiler
checkpoint-group |  |  | section | 18. Quality Assurance from Builder
checkpoint-status |  |  | checkpoint | Quality Assurance from Builder
checkpoint-group |  |  | section | 19. Final Inspection
checkpoint-status |  |  | checkpoint | Final Inspection (1)
text | 1edad775-33be-5322-90aa-69d710a4ba23 |  | textbox | Position:
date | 2a740eae-0a90-5bea-aafd-a08705a22266 |  | date | Date:
holdpoint |  |  | signoff | Prepared By:
checkpoint-status |  |  | checkpoint | Final Inspection (2)
text | c4f50682-cbed-5c75-9f72-b1e48a745922 |  | textbox | Position:
holdpoint |  |  | signoff | Approved By:
checklist-sectioned |  |  | checklist | Time Sheet |  |  |  |  | Yes | Add Time Sheet | 99f2569f-42bf-4ae8-a149-7abdba16a78d
checkpoint-group |  |  | section | Time Sheet
checkpoint-no-status |  |  | checkpoint | Details
date | 94e47690-8b1c-58ca-b139-ef69a8b4a3d3 |  | date | DATE:
text | dcf6be24-6f16-5941-923a-f0f8f6fab18e |  | textbox | CLIENT:
text | 3dc1a08d-45b6-50ce-a2be-18e20db89e7a |  | textbox | SITE:
text | ec67f581-1cb5-5c42-a028-ffa5f227853c |  | textbox | SITE INST. NO:
checkpoint-no-status |  |  | checkpoint | DETAILS OF WORKS
text | f2b4650e-05ce-54c3-82b8-3c7870b3440f |  | textbox | Description of works carried out:
text | 27c1fb72-ea0e-5239-a7ac-49212cd89858 |  | textbox | Reasons for works that have been carried out:
text | 009ade48-ec88-5b35-a525-349460bdb6b0 |  | textbox | Areas where works have been carried out:
checkpoint-no-status |  |  | checkpoint | Photo of area before works carried out
checkpoint-no-status |  |  | checkpoint | Photo of area after works carried out
checkpoint-no-status |  |  | checkpoint | LABOUR
text | 998972e4-ec92-57e6-aa81-0555f8d8f885 |  | textbox | (1) Dates:
number | a14a2e6b-5963-5b97-91e8-9aaf09ff60a2 |  | number | (1) HOURS
text | 5e7415de-0232-5378-93f2-3ceab4720597 |  | textbox | (2) Dates:
number | abe30f6b-0724-5df1-a964-42648b81a75a |  | number | (2) HOURS
text | 56b6b6c2-7a8a-50ce-a2cd-2eb710568d51 |  | textbox | (3) Dates:
number | 88cf6357-edc1-5527-9013-b3c92fa2257f |  | number | (3) HOURS
text | e6cc7f55-5577-57b6-a15c-f2bb29166a93 |  | textbox | (4) Dates:
number | a5d206d8-585a-55fe-9ad2-721ae11a88e3 |  | number | (4) HOURS
text | 5b1c5cde-f0e7-5db8-8208-a9965d469406 |  | textbox | (5) Dates:
number | 9b650f26-7b97-5c98-a833-86fde6db2ba9 |  | number | (5) HOURS
text | 6408649b-32b3-5236-a8bc-b992c0c4028c |  | textbox | (6) Dates:
number | 40c17368-75f0-5cc5-b06b-27a3db6a7c6d |  | number | (6) HOURS
checkpoint-no-status |  |  | checkpoint | MATERIALS
text | 1803dece-bf56-5d6f-9ab3-a26dadc35f73 |  | textbox | (1) MATERIAL USED
number | d91b9c8f-aa1f-5650-bf43-7586a661fe3c |  | number | (1) QTY
text | 07476e4f-45c0-53c2-9d39-9b38edcd3331 |  | textbox | (2) MATERIAL USED
number | 46042b3d-4435-5c9d-9a4f-981b8056ea35 |  | number | (2) QTY
text | 7e21d221-fc8c-579f-aad9-6cc858430f15 |  | textbox | (3) MATERIAL USED
number | 72e215e9-094a-54a9-bbe5-c490b4bd27e3 |  | number | (3) QTY
text | 17ecff9d-2859-5ec5-8184-0e6cec315bc1 |  | textbox | (4) MATERIAL USED
number | 6171903d-cef5-51f2-9a8b-d65cc957e4a5 |  | number | (4) QTY
text | 700534f8-9ca2-57b5-986f-786d7b8d9e12 |  | textbox | (5) MATERIAL USED
number | 3e6c1b0e-f99b-5888-862c-7131238903f4 |  | number | (5) QTY
text | 870e9171-5d72-5c78-bd73-f12b9fa3e54b |  | textbox | (6) MATERIAL USED
number | 603010f2-5545-557e-8432-525ca243d2f7 |  | number | (6) QTY
checkpoint-no-status |  |  | checkpoint | ACCEPTANCE
label | 998972e4-ec92-57e6-aa81-0555f8d8f885 |  | note | Teammembers Project P/L
text | a14a2e6b-5963-5b97-91e8-9aaf09ff60a2 |  | textbox | NAME
holdpoint |  |  | signoff | SIGNATURE