## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Tiling ITP | [5 empty] | Tiling ITP
section | 1. CHECK DRAWING
checkpoint | Confirm current drawing, specification and revision #
label | Inspection: admin
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 2. SUBSTRATE PREP - WALL
checkpoint | Inspect for wall quality to accept tiles and ensure that substrate free from debris
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Clean and dry
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Joints set and sealed
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 3. SUBSTRATE PREP - FLOOR
checkpoint | Check FFL from substrate
label | Inspection: laser / visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Check angle termination position
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 4. SAND & CEMENT BEDDING
checkpoint | Floorwastes protected to prevent debris entering into drains with compressible sponges
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Falls to waste as per drawing / isolate falls to waste
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Ensure slurry material is correct and is not dry prior to screeding
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Screed mixed by machine ratio1:4
label | Inspection: 100L stand mixer
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Ensure minimum screed is 15mm.
label | Inspection: visual / gauge
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 24hrs curing minimum
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | For large areas - check concrete porosity and de-dust
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 5. HOLD POINT
checkpoint | Setout and starting point verified with Builder and Drawings
label | Inspection: laser / visual / chalk line
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint | HOLD POINT
section | 6. INSPECT TILE LAYING
checkpoint | Penetrations checked prior to cuts
label | Inspection: admin / visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Installation of waste covers
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | General lipping wall/floor
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Confirmation of removal of floorwaste sponge
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 7. PRESEAL
checkpoint | Any material to be sealed to be cleaned free of dust
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Allow preseal to cure minimum 8 hours before grouting. Area to be baricaded off from entering.
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 8. GROUTING
checkpoint | Ensure approved grout colour is used
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Secure watersource and discharge location
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Grout mixed without lumpiness
label | Inspection: Visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Joints free from debris / spacers
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Surface is uniform and clean / no grout build up / internal corners free of grout
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 9. PROTECTION
checkpoint | Corflute taped down (no black corflute) cover entire tiled Surface
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Photo record of protection
label | Inspection: admin
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | Builders acceptance
label | Inspection: photo / signature
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
section | 10. Notes
checkpoint-no-status | Notes
textbox | Position:
date | Date:
signoff | Prepared By:
checklist | Waterproofing ITP | [5 empty] | Waterproofing ITP
section | Details
checkpoint | 1. Waterproofer to inspect substrate to confirm acceptability. Ensure clean, dry, devoid of contamination and excess dust removed and vacuumed.
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 2. Polyurethane fillet to internal vertical corners in shower, at junction of concrete with puddleflange, clearout, pipework
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 3. Primer A Eco to be applied to porous substrate (Data Sheet attached) All concrete and wall linings
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 4. Prime Keragrip Eco for non porous primer (Data sheet attached) Angles, puddlefalnges, threaded pipework
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 5. 1st Coat Kera Trade WPM (Data Sheet attached) Applied to floor 150mm high and 200mm above shower rose and extending 200mm past shower screen location. Extend to vanity 150mm min. surround to side and above vanity shelf. Extend 150mm below level of vanity.
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 6. 24hr Curing (Typical*)
label | Inspection: visual and touch
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 7. 2nd Coat Keratrade WPM applied
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 8. 48hr Curing (Typical*)
label | Inspection: visual and touch
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 9. Dry Film Thickness (DFT) Test completed min 1.13mm
label | Inspection: electronic testing
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 10. 24hr Water Test
label | Inspection: visual and marker
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 11. Final Water Test Measure Completed - AS3740-2010
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
checkpoint | 12. Drain Down by waterproof installer
label | Inspection: visual
dropdown | Inspected By: | Minjeong Hong,Hwanho Chung,Caspar Chong,Philip Chong,Mario Denaro,Bol Ajak,Ji Kang
holdpoint | 13. Waterproof installer to check / provide go ahead
section | 14. RECTIFICATION ITEMS
checkpoint | RECTIFICATION ITEMS
checkpoint | 15. Area Handover to Tiler
holdpoint | Verify with Tiler
section | 17. QUALITY ASSURANCE FROM BUILDER
checkpoint | Quality Assurance from Builder
section | 18. FINAL INSPECTION
checkpoint | Final Inspection (1)
textbox | Position:
date | Date:
signoff | Prepared By:
checkpoint | Final Inspection (2)
textbox | Position:
signoff | Approved By: