## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 1 - Roadway Pavements Rev 3 | itp |  |  |  | Yes | ITP 1 - Roadway Pavements Rev 3 | 05d5f44e-1861-4244-9061-cfaeca88b357
section | 1 - Initial subgrade assessment
checkpoint | 1.1 - Strength
label | ACCEPTANCE CRITERIA: Subgrade will be proof rolled to so that the resultant impression in the surface under a smooth wheel roller or other approved plant having a minimum loading of 6259 kg per metre width of fill, shall not be greater than 7 mm for bulk fill or 5 mm for subgrade fill.
label | ○ Scala penetrometer - Scala penetrometer tests shall be undertaken to check the subgrade strength of a CBR greater than 7%.
label | FREQUENCY: 20m intervals
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection, Scala Check Sheet QF021A
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H
holdpoint | HOLD POINT
section | 2 - Undercut treatment
checkpoint | 2.1 - Strength
label | ACCEPTANCE CRITERIA: Where the CBR is less than 5%, subgrade shall be uncut as follows:
label | ○ CBR between 4% and 5% - undercut 100mm and backfill with GAP65.
label | ○ CBR between 3% and 4% - undercut 150mm and backfill with GAP65.
label | ○ CBR between 2% and 3% - undercut 200mm, place Geo-textile to TNF F/7 Class C and backfill with GAP65
label | ○ CBR <2% - Notify the engineer within 1 working day of the result in writing. The engineer will advise what to do within 5 working days.
label | FREQUENCY: 20m intervals
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Undercut Quantities Check Sheet QF003
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H
holdpoint | HOLD POINT
section | 3 - GAP 65
checkpoint | 3.1 - Material Supplied
label | ACCEPTANCE CRITERIA: Meets Specification
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 3.2 - Crushing Resistance
label | ACCEPTANCE CRITERIA: 110 kN As per NZS 4407: 1991, test 3.10
label | FREQUENCY: Prior to commencement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: IANZ Report
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 3.3 - Weathering Quality Index
label | ACCEPTANCE CRITERIA: AA,AB,AC,BA,BB,CA,CB As per NZS4407 1991, test 3.11
label | FREQUENCY: Prior to commencement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: IANZ Report
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 3.4 - Sand Equivalent
label | ACCEPTANCE CRITERIA: 28 As per NZS4407 1991, test 3.6
label | FREQUENCY: Prior to commencement
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: IANZ Report
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 3.5 - Grading Envelope
label | ACCEPTANCE CRITERIA/FREQUENCY: As per NZS 4407 Test 3.8.1
label | – – – – – – – – – – –
label | Test Sieve Aperture ¦¦ Percentage passing for GAP 65
label | – – – – – – – – – – –
label | 63.0 mm ¦¦ 100
label | 37.5 mm ¦¦ 70-85
label | 19.0 mm ¦¦ 46-68
label | 9.5 mm ¦¦ 31-54
label | 4.75 mm ¦¦ 20-41
label | 2.36 mm ¦¦ 13-32
label | 1.18 mm ¦¦ 9-23
label | 600 micron ¦¦ 6-16
label | 300 micron ¦¦ 3-12
label | 150 micron ¦¦ 10 max
label | 75 micron ¦¦ 6 max
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As per Supplier Documentation
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 3.6 - Aggregate Grading Shape Control
label | ACCEPTANCE CRITERIA/FREQUENCY:
label | – – – – – – – – – – –
label | Fractions ¦¦ Percentage of Material in Fraction GAP 65
label | – – – – – – – – – – –
label | 37.5 - 9.5 mm ¦¦ 24-46
label | 19.0 - 4.75 mm ¦¦ 15-37
label | 9.5 - 2.36 mm ¦¦ 10-31
label | 4.75 - 1.18 mm ¦¦ 7-25
label | 2.36 mm - 600 micron ¦¦ 6-19
label | 1.18 mm - 300 micron ¦¦ 5-16
label | 600 - 150 micron ¦¦ 2-12
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As per Supplier Documentation
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 4 - TNZ M/4/GAP40/GAP65
checkpoint | 4.1 - Material Supplied
label | ACCEPTANCE CRITERIA: As specified by the Engineer
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 4.2 - Crushing Resistance/ Weathering Resistance/ Sand Equivalent
label | ACCEPTANCE CRITERIA/FREQUENCY:
label | – – – – – – – – – – –
label | Material Description ¦¦ Crushing Resistance ¦¦ Weathering Quality index ¦¦ Sand Equivalent
label | – – – – – – – – – – –
label | TNZ M/4 1995 (AP40) ¦¦ 130 kN ¦¦ AA,AB,AC,BA,BB,CA ¦¦ 40
label | GAP 65 ¦¦ 110 kN ¦¦ AA,AB,AC,BA,BB,CA,CB ¦¦ 28
label | GAP 40 ¦¦ 110 kN ¦¦ AA,AB,AC,BA,BB,CA,CB ¦¦ 25
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: IANZ Report
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 4.3 - Grading Envelope
label | ACCEPTANCE CRITERIA/FREQUENCY: As per NZS4407 Test 3.8.1
label | – – – – – – – – – – –
label | Test Sieve Aperture :: TNZ M/4 (AP 40) ¦¦ GAP 65 ¦¦ PAP 40 GAP 40 ¦¦ PAP 20
label | – – – – – – – – – – –
label | 63.00 mm :: - ¦¦ 100 ¦¦ - ¦¦ -
label | 37.5 mm :: 100 ¦¦ 70-85 ¦¦ 100 ¦¦ -
label | 19.0 mm :: 66-81 ¦¦ 46-68 ¦¦ 63-81 ¦¦ 100
label | 9.5 mm :: 43-57 ¦¦ 31-54 ¦¦ 41-57 ¦¦ 52-75
label | 4.75 mm :: 28-43 ¦¦ 20-41 ¦¦ 26-43 ¦¦ 31-55
label | 2.36 mm :: 19-33 ¦¦ 13-32 ¦¦ 18-33 ¦¦ 21-42
label | 1.18 mm :: 12-25 ¦¦ 9-23 ¦¦ 11-25 ¦¦ 13-31
label | 600 micron :: 7-19 ¦¦ 6-16 ¦¦ 6-19 ¦¦ 7-23
label | 300 micron :: 3-14 ¦¦ 3-12 ¦¦ 3-14 ¦¦ 5-16
label | 150 micron :: 10 max ¦¦ 10 max ¦¦ 10 max ¦¦ 12 max
label | 75 micron :: 7 max ¦¦ 6 max ¦¦ 7 max ¦¦ 8 max
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As per Supplier Documentation
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 4.4 - Grading Shape control
label | ACCEPTANCE CRITERIA/FREQUENCY:
label | – – – – – – – – – – –
label | Fractions :: TNZ M/4 (AP 40) ¦¦ GAP 65 ¦¦ PAP 40 GAP 40 ¦¦ PAP 20
label | – – – – – – – – – – –
label | 37.5 - 9.5 mm :: - ¦¦ 24-46 ¦¦ - ¦¦ -
label | 19.0 - 4.75 mm :: 28-48 ¦¦ 15-37 ¦¦ 27-49 ¦¦ -
label | 9.5 - 2.36 mm :: 14-34 ¦¦ 10-31 ¦¦ 13-34 ¦¦ 19-47
label | 4.75 - 1.18 mm :: 7-27 ¦¦ 7-25 ¦¦ 7-28 ¦¦ 8-35
label | 2.36 mm - 600 micron :: 6-22 ¦¦ 6-19 ¦¦ 6-22 ¦¦ 6-27
label | 1.18 mm - 300 micron :: 5-19 ¦¦ 5-16 ¦¦ 5-19 ¦¦ 3-21
label | 600 - 150 micron :: 2-14 ¦¦ 2-12 ¦¦ 2-14 ¦¦ 2-17
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: As per Supplier Documentation
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 5 - Sub-basecourse
checkpoint | 5.1 - Spreading of Aggregate
label | ACCEPTANCE CRITERIA: To be 200mm thick and constructed of GAP 65
label | ○ Placed in uniform layers with the average un-compacted thickness of each layer not less than 100mm or greater than 200mm.
label | FREQUENCY: Per layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection/QF023
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 6 - Basecourse
checkpoint | 6.1 - Spreading of Aggregate
label | ACCEPTANCE CRITERIA: To be 100mm thick and constructed of TNZ M/4.
label | FREQUENCY: Per layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey as-built
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 7 - Geotextile
checkpoint | 7.1 - Supply
label | ACCEPTANCE CRITERIA: Geotextile to be BIDIM A19 geotextile or equivalent
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 7.2 - Installation
label | ACCEPTANCE CRITERIA: To be installed in between the sub-basecourse and basecourse layers
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection/Photos
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H
holdpoint | HOLD POINT
section | 8 - Sub-basecourse
checkpoint | 8.1 - In-situ Density
label | ACCEPTANCE CRITERIA: As per NZS4407 Test 4.2.2 “Nuclear Surface Moisture Density Gauge - Backscatter Mode with correlation test every 100 NDM tests”
label | FREQUENCY: Alternating between right and left lane at 20m intervals
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
checkpoint | 8.2 - Dry Density
label | ACCEPTANCE CRITERIA/FREQUENCY:
label | – – – – – – – – – – –
label | Values ¦¦ Sub-basecourse Pavement Layer
label | – – – – – – – – – – –
label | Mean Value ¦¦ ≥95
label | Minimum Value ¦¦ ≥92
label | – – – – – – – – – – –
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: IANZ Report
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 9 - Subgrade Surface
checkpoint | 9.1 - Surface Level
label | ACCEPTANCE CRITERIA: Vertical -25mm +5mm
label | FREQUENCY: 20m intervals, 5 points per cross section
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Stringline Check Sheet QF023/Survey GPS as-built
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 10 - Sub-basecourse Surface
checkpoint | 10.1 - Surface Level
label | ACCEPTANCE CRITERIA: Vertical -25mm +5mm
label | FREQUENCY: 20m intervals, 5 points per cross section
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey GPS as-built
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 11 - Basecourse Surface
checkpoint | 11.1 - Surface Level
label | ACCEPTANCE CRITERIA: Vertical
label | ○ -5mm +15mm
label | ○ -5mm +5mm at or close to lip of channel
label | FREQUENCY: 20m intervals, 5 points per cross section
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Survey as-built
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT