## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Metal Windows & Doors Checklist |  |  |  |  | Yes | Metal Windows & Doors Checklist | 06c607f9-0221-4f9d-b62c-69dcaf718b1b
checkpoint-group |  |  | section | Pre Check
checkpoint-status |  |  | checkpoint | Working area is clean and ready for work to commence
checkpoint-status |  |  | checkpoint | Latest revision working documents provided
checkpoint-status |  |  | checkpoint | Storage area agreed
checkpoint-status |  |  | checkpoint | Datum & gridlines provided
checkpoint-status |  |  | checkpoint | Correct opening sizes confirmed
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Windows/Doors in correct location
checkpoint-status |  |  | checkpoint | Frames fixed level & secure
checkpoint-status |  |  | checkpoint | Flashings weathertight
checkpoint-status |  |  | checkpoint | Sealants correctly applied & weathertight
checkpoint-status |  |  | checkpoint | Glass & frames cleaned & protected
checkpoint-group |  |  | section | Glazing
checkpoint-status |  |  | checkpoint | Glass as per approved shop drawing/s.
checkpoint-status |  |  | checkpoint | Glass is defect free (scratches, shells, excessive roller wave, internal sucker marks of DGU).
checkpoint-status |  |  | checkpoint | Depth of cover is correct.
checkpoint-status |  |  | checkpoint | Bite and aesthetic of silicone seal is acceptable.
checkpoint-status |  |  | checkpoint | Decals are installed if required.
checkpoint-status |  |  | checkpoint | Hardware (Locks & handles) fitted & operation tested
checkpoint-group |  |  | section | Final Checks
checkpoint-status |  |  | checkpoint | Glass Installed correctly
checkpoint-status |  |  | checkpoint | Gasket Wedge applied
checkpoint-status |  |  | checkpoint | All Stickers & Dots removed
checkpoint-status |  |  | checkpoint | Glass cleaned to trade standard
checkpoint-status |  |  | checkpoint | Window Completed - New Era Glazing signoff (attach signature)
checklist-flat |  |  | checklist | Document Upload |  |  |  |  | Yes | Document Upload | 9e224654-6dd9-412b-89f0-b3913618424b
checkpoint-status |  |  | checkpoint | Upload relevant documents & drawings