## ITP-031_Item2.2_Status
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
work-in-progress | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-applicable | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
pass | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
not-started | checkpoint | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection