## Symal Infrastructure__CC0398 VI
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
16a2782d-ee4f-4d33-b468-deb50ecda756 |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks
94e29ae8-970c-4b00-aaa7-f6fecb3de456 |  | work-in-progress | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade
b94c7e93-5326-53d7-a7b8-0b28240293b4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries
277c1085-815c-5263-a9f7-5b1601936071 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries | 1.1 - Determine lot size
8c9efade-ee5a-53c3-b50e-09ebe9e77876 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries | 1.2 - Survey set-out
af29ff22-6018-5fe2-8d4b-aecefceb8218 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries | 1.3 - Excavation material classification
0bee8dc8-8c3a-5f97-8f80-5ba2cdf332b0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries | 1.4 - Material Submission / Approval
4cf85975-b588-5d49-a3a3-e5a672a26f06 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 1.0 Preliminaries | AUTHORITY HOLDPOINT
f6725d53-f209-59b9-ba05-ec86cf074f2c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 2.0 Bulk earthworks – cut
823595e9-7377-5489-9d68-a1e86ad6498f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
c6459125-449c-5547-b73c-8d9c8bc68f91 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
843e1f85-dba7-5db1-995d-226acc69e906 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill
56b05c9c-226e-5d70-9e96-ace80f1764da |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
bebacaa1-2e86-5693-8e4e-f6f03d5765ac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
91ab137b-e63f-5528-8e9d-0c0ce857c604 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
aed7e42b-185b-5875-a184-d8f1d2010357 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.4 - Moisture
6e39e62b-5c48-5e40-9085-bd276177a61d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.5 - Compaction
b1c8ef90-3aed-5391-b1fa-868b3c939947 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
e1a21525-aec1-5764-96fe-8239b8e862ee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
069f7932-ac09-5133-8432-27372a962c94 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
ceb261cb-9d9e-58c3-893c-213f89f42da2 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 4.0 Conformance check
b8501368-fa91-5775-b370-436a5c3eb0d2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-025 - East GRE Subgrade | 4.0 Conformance check | 4.1 - Subgrade level and shape
1277a7e0-5e8d-4a94-8524-0ce3151c531e |  | work-in-progress | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade
1a005ff4-2252-557f-bad5-e558d007e8d2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries
2157bf9e-0bd4-5d59-a321-655d6cacc50b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries | 1.1 - Determine lot size
0386abdc-5083-5c50-a1cb-4fba79b0fee0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries | 1.2 - Survey set-out
847fdb8f-95ce-5bbf-8e6d-88652739b0a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries | 1.3 - Excavation material classification
9caad8a8-3fba-5271-8ac8-2b720d017ddb |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries | 1.4 - Material Submission / Approval
45dbaf6f-ca55-52df-bf6b-9b3c2afb015f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 1.0 Preliminaries | AUTHORITY HOLDPOINT
e6dd7fe2-5710-5e7e-ac36-ba6ca50f5052 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 2.0 Bulk earthworks – cut
1ca82d1b-3b2d-5ed9-86d1-97287fa24964 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
ac5e7c7c-ec74-5ac4-8667-da08976b4d1d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
0960153c-2063-52ec-898a-72b9790b0186 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill
db40e71a-9402-514a-b2cb-ba6c2e84de9b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
56e4278d-a6d5-58e9-9f65-7ead8b417214 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
6db73f2f-f578-5115-9d7c-738209cd88c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
bb27152b-8eda-5e5e-bf3a-5a9538c2c62c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.4 - Moisture
c190f8f9-2025-5ce8-8708-02a32dc2bc8f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.5 - Compaction
30a6818d-3f22-5703-9fe1-59f8c0d80de0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
340253e2-2d7a-52bb-aade-89f3231cdb5d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
99a66aa9-7f32-5765-8491-bf366e76dbd5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
89163902-1a31-59b1-be85-c5b1cb0b3e9d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 4.0 Conformance check
db893f98-fcf1-58c0-beb5-5e32a7ba9ea5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-026 - CWT Pavements Subgrade | 4.0 Conformance check | 4.1 - Subgrade level and shape
0f2fae5e-4874-4a07-86e3-6cf4e6163050 |  | not-started | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA
04b0541d-339c-5dd8-8336-0cb490c0b75a |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries
d099d1c7-11cc-5578-a12c-3216004ca75f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.1 - Determine lot size
6400d0e5-5a55-5a67-89c6-ea5f4f594223 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.2 - Survey set-out
dedc0916-6944-56e8-acd4-171509026b8c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.3 - Excavation material classification
f1fa7b85-31d0-5a58-af6c-35eb0ae77928 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.4 - Material Submission / Approval
fc48db16-51fb-5493-adcd-c220b32fb7ba |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | AUTHORITY HOLDPOINT
24052bfa-f756-5d2d-8dba-eddb6321e779 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut
ff171631-0b17-5c69-bd03-db2605f583de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
2fd40e3d-306d-55da-a958-7014e6638047 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
5a03c817-d738-5789-9fb2-a4ac3ef52885 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill
8713dfe1-9bc9-5ad8-baf7-02ef85848f4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
f4db41c6-c365-528f-b4c9-e693f716c137 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
3505e074-3f28-54e4-88ac-97a5880a5ff5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
4317c248-071e-55aa-a711-66f54d559b30 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.4 - Moisture
37e6291c-9480-5bcc-9cab-ee23b18287ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.5 - Compaction
80f6b14c-3580-51c4-9ec6-a1c33b52a781 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
3387cc8b-071f-5087-b904-31ac61e1807a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
ae9f2e0a-aaf3-5592-8152-26863d779f74 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
3f9a252e-1bdb-554b-aade-cf283c1219e5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 4.0 Conformance check
4e303123-925f-5878-ab77-ce3396685d22 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-027 - CWA111 - CONCRETE PAVEMENT AREA | 4.0 Conformance check | 4.1 - Subgrade level and shape
e151c8b8-83a8-42e1-b8c5-5dd216673caa |  | not-started | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA
b2b0db34-d86f-54b9-ad53-938a39ae6aba |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries
933f2c07-a231-587e-8bb3-5831aeb5032c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.1 - Determine lot size
a45193ad-f2b3-58f0-974c-7fabc32de301 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.2 - Survey set-out
ae6131af-c71a-5cd1-abd8-75a8cdbf3a4c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.3 - Excavation material classification
c0eaea03-f7cf-5333-a974-2e2e06a15c00 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.4 - Material Submission / Approval
1f32c6e9-41fc-569c-a2bd-3bb075868840 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | AUTHORITY HOLDPOINT
cec5eb09-4a68-56cc-be40-02367b2102d0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut
cfa98636-bb08-5dfa-bde3-aa2064c0f7fb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
ea7012a3-e41f-57f2-a29e-6ec12af5b693 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
22ec026c-561f-58cf-9f6b-1a51b43de607 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill
ab631be8-be4a-5326-9636-186601a9e1e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
19ee11cc-2f00-5e7d-9264-8efbbac4502e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
d82f9e32-8b30-5229-a4c5-e162b63209b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
62323ad9-7e0b-5777-89bb-10389edcca66 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.4 - Moisture
ba41224e-c644-5886-b967-508d4504d331 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.5 - Compaction
10e2dcb2-e3b3-58d4-a92b-17c1352bc6fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
0f4d60e5-274d-5698-b535-aaaa126fe5ca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
0af536ba-54ea-5954-ab4c-970e7b403536 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
e88df57b-942f-5125-a353-7365d57548ad |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 4.0 Conformance check
15358287-0e80-56ae-87b7-35993ec1a5eb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-028 - CWA-114 - CONCRETE PAVEMENT AREA | 4.0 Conformance check | 4.1 - Subgrade level and shape
101b7979-ed14-4b71-a25d-2265b8435fed |  | not-started | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA
69c80f98-cba9-53af-a2af-2a5ffd34ff87 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries
ce4eede4-d477-5e5b-9c3a-6603b3f0d4d8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.1 - Determine lot size
005d15ba-37da-5e61-a80d-bde0a42d30a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.2 - Survey set-out
767bf9b9-3b47-52ac-bbca-bea753456bca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.3 - Excavation material classification
437f3e61-abe9-5223-bd4c-82723e0e248f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.4 - Material Submission / Approval
4a0ab0ca-014b-5f66-8056-4614f63e450d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | AUTHORITY HOLDPOINT
24ab27ec-64fa-5e15-beec-59e8f0e75b44 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut
f52219ae-8666-5e28-a0b3-b12799f5cede |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
9cab6209-b198-5c0d-a172-a5ac81ae2d3c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
d8b69e3d-6ff3-5ad9-b0d5-8f9a9b21b93f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill
112e3b3b-e49a-5651-a5a4-fb27d25d6e22 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
38b568a5-5c74-5fb9-9b16-47732ce07545 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
332db0c4-2663-5702-9279-5a00506fc0a5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
dbc4ddbb-f66d-5469-8471-3d40ee930f0a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.4 - Moisture
beaf4f63-0162-5fb8-bd95-8091d04a2289 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.5 - Compaction
deba1b27-2305-58a9-8b0d-4779ec7ad6bf |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
ddbe5e28-a873-5bd7-9589-25fa05b63787 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
7a81e7b2-a963-5ae6-8ff4-15800734ef9f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
cbb29a92-d382-5732-b5ee-44388c17ff51 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 4.0 Conformance check
28fd45ab-7c1a-5f67-ae67-d96ffee171bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-029 - CWA113 - CONCRETE PAVEMENT AREA | 4.0 Conformance check | 4.1 - Subgrade level and shape
544a0d04-b9c6-43d2-a17d-026fb015a145 |  | not-started | INF-HSEQ CC0398-ITP-002 Bulk Earthworks REV D | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA
d9465fc0-11a3-5a0b-bc3e-24e044039596 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries
2ea5ee16-8f40-5fca-a20d-245bc9c7b4a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.1 - Determine lot size
f5c7dae5-d238-576e-94c8-177c7c2c44c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.2 - Survey set-out
4ce37cbe-91f8-5f1f-9f4f-bc54aed1a53e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.3 - Excavation material classification
a213e279-f976-5fdd-87c3-dd3e6d8e1dc4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | 1.4 - Material Submission / Approval
43921c61-6543-5831-b29c-e56134be9cde |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 1.0 Preliminaries | AUTHORITY HOLDPOINT
46af81c6-156b-588f-b986-21d2987edaa2 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut
a27274fa-9d3c-5617-891f-ca42f75831f6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.1 - Subgrade preparation
5cd0910b-1618-5190-8171-85e0f4854b6a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 2.0 Bulk earthworks – cut | 2.2 - Material Export / Stockpiling
74c87371-b0f2-5565-8b75-19f5374a6e6b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill
6744d3c3-3f63-56dd-835f-23b7ba8e4335 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.1 - Preparation of surface
6427c26a-439a-5bc9-8b96-00865693d228 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.2 - Compaction Trial for Blended Material
637c926c-4829-504c-8173-e4e82e723f68 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.3 - Fill Placement
dfa53f61-f3bd-5ae3-893d-18631bac38c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.4 - Moisture
b0093e53-0737-5563-b0c9-36e452f822ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.5 - Compaction
8c23ec1e-3bf6-5496-866b-1e3f1a4ae37f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.6 - Fill layer – test rolling
aab00b08-8e06-5f6c-b6ad-19454ee249b5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.7 - Identification of soft wet or unstable material
5064f9e9-66e4-57d8-a589-d8d6d4062af7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 3.0 Bulk earthworks - fill | 3.8 - Treatment of unsuitable material
bfaa260f-7ab8-50a1-8f6d-e4901532190e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 4.0 Conformance check
fecd9195-670d-5c56-94ac-99ed20ce8281 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-002 Bulk Earthworks | VIVA-BEW-002-030 - CWA112 - CONCRETE PAVEMENT AREA | 4.0 Conformance check | 4.1 - Subgrade level and shape
fc651388-351c-4a91-a2d3-a9d2bb1c206d |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction
e932dd82-f0a5-49ea-ac00-085a9ecbdbbd |  | work-in-progress | 2b601689dd20acc00fdf54a7bd896d3573e061690635d038b11c372942196739 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE
b28c1827-e5a9-576e-9338-d4e7e5cbd622 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 1.0 Preliminaries
0828c656-98d1-58b8-8353-38ed0e16e5bc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 1.0 Preliminaries | 1.1 - Determine lot size
ecc71845-e22f-5f69-868a-e2232acbfeec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 1.0 Preliminaries | 1.2 - Survey set-out
9df9d8e3-4d15-5c69-b54f-298c46d8a508 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 1.0 Preliminaries | 1.3 - Material classification and source
60624091-f642-5108-8b67-d7ff3865df2d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 1.0 Preliminaries | AUTHORITY HOLDPOINT
38fc88ad-6c4f-5dea-8cdb-4de3adf2ce37 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 2.0 Conformance of previous layer
92ac2f59-41ae-5ff7-b4d4-faad44dc8f79 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
d8712ec1-d2c1-51cf-9b64-3b42a0ad0f1c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
57e268b5-94bf-5dcc-86d2-a321c0221b40 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 2.0 Conformance of previous layer | Type of Pavement:
728789c5-d8e5-55dc-ba74-427c03863889 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving
b6c73872-a920-5e1c-8da9-7db6221f49cd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
5bee1b31-b845-5aca-9f12-525b529e1dfd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
b1e9f25f-bdaa-4d0e-970b-b10afd577fa8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
b8acd22e-8d65-5f3a-928e-a0736781ab1e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
5e418057-94db-5f6b-9d99-19629bd99c42 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
197e9081-d8ea-58d4-8be1-20b4cc91f47e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
a0fb1df0-fe48-5bfd-b31a-19d791f2e0a4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
cbac294b-f1f0-549e-8f97-0fd687b32049 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving
cff21f62-882e-564e-a272-60ba8c91b545 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
e87a71ae-bc07-5c79-9ff9-099cb8fa38e4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
b35081b0-a6cd-5f08-9489-08b145aed03c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.3 - Moisture
84c10952-3b00-4766-8463-5a186139fee5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.4 - Compaction
2c49242e-0bae-59b9-8d20-77b76407fbd9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.5 - Test rolling
4b5f5e56-3f77-59d9-a2fc-bb4c310684e8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
b4bbec83-0fd5-5a30-bb31-7db942b9609b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
4811019a-6a29-50e1-ab6e-b1af456950e0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 5.0 Conformance check
98ff9bcb-b4a5-58b1-af86-3dbb663bd4f8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 5.0 Conformance check | 5.1 - Pavement finish
d01c2897-0e6e-5697-b94d-4c4aae831e5a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 5.0 Conformance check | 5.2 - Surface level of pavement courses
e7cd3d93-63d3-5e67-9c27-8f28e4fe4e40 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-001 - East GRE | 5.0 Conformance check | AUTHORITY HOLDPOINT
f6bc5ff4-b71e-46aa-a16c-090274169fe7 |  | work-in-progress | 2b601689dd20acc00fdf54a7bd896d3573e061690635d038b11c372942196739 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower
4428ffc2-27b9-502d-ac46-d8b75ce27669 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 1.0 Preliminaries
96c81d8c-957a-51c8-bd2b-94a2e12459a3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 1.0 Preliminaries | 1.1 - Determine lot size
3160838c-d585-598e-9a39-7cf0ff381f21 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 1.0 Preliminaries | 1.2 - Survey set-out
3142da9a-7ed9-5e2b-a02d-47152d0484c6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 1.0 Preliminaries | 1.3 - Material classification and source
96449466-dcf9-507a-8a69-417aa7c7a970 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 1.0 Preliminaries | AUTHORITY HOLDPOINT
aa4840ca-89d0-53fb-9f32-452ff6a46475 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 2.0 Conformance of previous layer
aebbdfc5-5120-593b-ac2e-ec4b63c7ff29 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
97735745-52fe-5505-aef3-192e5c176e0a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
dc0ad0ca-6138-5892-b6bb-4e9ce56118b8 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 2.0 Conformance of previous layer | Type of Pavement:
65bbaf7e-052b-593c-91c9-600fd39cb632 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving
ca465e5f-ff59-532d-947e-914e9e0f00b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
bd296fc3-484c-50e0-83e2-3a85e52e1193 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
b5945292-fb38-4d01-aaac-5a73235681a9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
0a116431-e767-5416-9a0b-56c04ca9218d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
edda922b-cd66-509c-89eb-bf356142dd92 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
6247f52e-95fe-55e2-b899-134fbe8da606 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
b6950409-5dcb-58d0-9ac0-ebb5931a253c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
2c629406-d56b-5e62-a8bd-cc307310e6de |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving
2aed7238-80a4-5eab-ab50-50cb27e9a168 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
f4b15a68-f489-5ea4-b546-1c79e6a63f41 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
7ef097f6-51b4-5a7f-adb9-3bf490e863ff |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.3 - Moisture
52b66da8-8661-439b-8620-bafa1e6d66f2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.4 - Compaction
6f3081af-49ad-5a7e-ae91-22eeeca6e668 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.5 - Test rolling
3aaf46a1-10b2-5672-8c4a-3e45c44f1653 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
db13dffa-6f36-50d4-b328-6e5d13d7cbfb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
36d3967e-8e0d-543c-9e84-60baa60e3890 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 5.0 Conformance check
e3c90e5c-f4cb-5070-89fb-bfd9990f9cb8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 5.0 Conformance check | 5.1 - Pavement finish
19d856f5-5fa8-5529-b9b8-848552fd35c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 5.0 Conformance check | 5.2 - Surface level of pavement courses
bb7c83f1-a682-5395-9191-437f95d8eafe |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-002 - Cooling Water Tower | 5.0 Conformance check | AUTHORITY HOLDPOINT
42e5e5e2-f2fb-4446-b5ec-27ada90db423 |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1
d0d9a789-91b8-5cb2-b10b-66d56676d8cc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 1.0 Preliminaries
18e39d7a-8153-42b6-b47c-ac8c8ce7ba54 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 1.0 Preliminaries | 1.1 - Determine lot size
480f3082-1fa2-52df-a5ce-ecb1058d651b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 1.0 Preliminaries | 1.2 - Survey set-out
b244e74a-b27f-511a-b798-cdc1becce5d7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 1.0 Preliminaries | 1.3 - Material classification and source
75182a71-3c6f-5dcb-88a6-7e3342ff47b9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
42d94c6f-4fdc-5ebb-bcb3-2374c7cb666f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 2.0 Conformance of previous layer
71f0e390-dfe1-5182-a0bd-9ad7c746ecec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
79f00ee4-6073-5062-993c-86abf498f029 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
24c494ce-da95-5572-b466-c0299108d876 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 2.0 Conformance of previous layer | Type of Pavement:
282799ae-14e8-5ac7-875a-5ef28eec81ae |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving
fff854e0-d064-5684-bd68-149d7431291b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
62c69f44-0a5f-555c-8104-9af0a2c1ba4e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
b37def55-3312-4708-93e7-b2df44bdad8d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
dda9a430-ffeb-5d3f-a4c5-c55cfb3ae433 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
6fbc99e9-61c4-5cff-95d3-b01dcc861b3b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
50cc54a7-f5f1-5d4b-ae2e-221a2df643f7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
ead70dd1-4b6f-5273-bcdb-ab0dbe72b999 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
7bb9c018-2c76-51f1-b350-166b5dab0f07 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving
d56b642b-2601-5c7c-bf5d-2111d4eb0550 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
ec245153-ca61-5839-a7a5-5d72f2fd21a5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
314dade6-86e8-543e-b7cb-f19ebaad21cd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.3 - Moisture
897b2fc1-364d-4a1c-bd94-095342eb231c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.4 - Compaction
e2e78552-918b-585d-b0e8-b759ca792599 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
0eec1d72-49f3-5013-a08f-41be610e10c3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
0dd9e975-93a8-5168-bf5a-6ccd1c2af2fa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
16fa59dd-9fe2-5cff-bae8-888e6e775e6e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 5.0 Conformance check
0a1a89dc-0351-5604-8a33-f52786cb0e5b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 5.0 Conformance check | 5.1 - Pavement finish
cb4b50c7-8b49-5ae1-8f27-8460f4b88330 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
69833702-d686-560b-990b-c31cb856e50b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-003 - 175mm Pavement - Pour 1 | 5.0 Conformance check | AUTHORITY HOLDPOINT
61134578-d6b8-4276-b7a7-a40c988b626c |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2
79dd65d5-4683-568a-94db-85d5e9e06eea |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 1.0 Preliminaries
be225ccf-7249-422f-af5c-0a52fe763fea |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 1.0 Preliminaries | 1.1 - Determine lot size
eacaa148-e674-59b2-be6b-7ca0a3645dce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 1.0 Preliminaries | 1.2 - Survey set-out
3452e92f-3223-5c38-bc70-1523948985fb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 1.0 Preliminaries | 1.3 - Material classification and source
144b512e-d1da-5e38-9279-5db94101f5f7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
ab967bad-906e-50f9-906e-acbdafde79cf |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 2.0 Conformance of previous layer
2ec23f2d-238f-5fb2-9bf1-1c8915e65d05 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
a0d126f1-88da-5831-9b8f-eb81e4b98d8c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
4dba4975-0905-5124-85b1-47d9fb89d908 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 2.0 Conformance of previous layer | Type of Pavement:
fabe6461-73e1-5585-99f6-296741ff68b8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving
3e062bac-0422-5510-8e5d-603aa5da7c2f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
3d7109ea-4ba1-56e0-9965-50809d8bf886 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
3bf3aaf2-89a3-45e9-9f37-257301ff580b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
a9a47dcf-075d-587a-9c22-9f4ff28b95af |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
f70a11e2-21b9-53c4-b760-bad879ba8023 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
93a7c874-aa12-5f67-871c-3a897b18a611 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
533fa8e1-3a87-5c53-8b8f-0b398b75aeb6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
a784ec1b-575e-5f36-9685-2f3910dabfed |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving
394db49b-a6f2-5113-82a2-fbb5db8dd00b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
bbbed625-47d7-548f-909f-801af16f878e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
0e821abc-00b4-55a9-8e7e-7194a54facde |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.3 - Moisture
95ef49b6-4f37-49f0-8ac5-5f16391f1fd6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.4 - Compaction
655aee3e-6089-5f24-931f-8dd7d4145561 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
7164e353-5c28-5868-a1cf-704b8cb42dbb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
a4697350-720d-5ffb-b2ce-1f2289857be0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
b41f338f-b6c5-5b16-af35-bd0e7b18060a |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 5.0 Conformance check
58f33cb7-df76-5c41-a690-9cf88d5c84d6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 5.0 Conformance check | 5.1 - Pavement finish
6c239bc9-7bfa-5228-96ef-93c01017e69e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
179d95b7-20bc-5d9f-acb5-162d7d71dc87 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-004 - 175mm Pavement - Pour 2 | 5.0 Conformance check | AUTHORITY HOLDPOINT
d7c7a609-0a59-4563-be8e-25006ee6306e |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3
2bc1dea0-10d9-50ea-b207-900be6eaa498 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 1.0 Preliminaries
203037c2-6ad7-4cfc-98ec-3699b6bdfa06 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 1.0 Preliminaries | 1.1 - Determine lot size
3e4194b3-21dd-5353-bb28-50e9a893abe8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 1.0 Preliminaries | 1.2 - Survey set-out
95244618-1732-5611-8a54-7003a115259d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 1.0 Preliminaries | 1.3 - Material classification and source
424ad585-2d9c-5839-91e2-2a444102e8ea |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
13166340-7cda-5988-b7c4-6f278a16279e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 2.0 Conformance of previous layer
79734852-8671-5175-bca0-245a5c0ad3d6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
f87b2342-3137-5a78-9d97-c13f6d5b3c26 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
7885af08-696e-55f3-a581-a551601204af |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 2.0 Conformance of previous layer | Type of Pavement:
43484518-56ca-5752-b4c0-66ef8a5115b1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving
f6508df5-3c91-5fe8-860b-77f49e8a79ca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
c859a751-13ed-5a7b-85cc-bf115a693584 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
c9006a49-6515-4c71-b9e7-524050ffc1a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
2a83cc46-d7e1-55c1-80cf-586a36dcc264 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
775b061c-98be-5d06-af87-160993da099d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
268a2b8b-e781-529d-9bfa-1494697fd414 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
4bbe1588-eb0d-597b-a82d-08d528dd06cb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
58443ef6-84e9-542b-a52b-cc28db4379a8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving
a9a05023-c82a-584d-956e-d619f1799eb1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
adb0dac1-e63e-5f67-a96f-8bb5db41d539 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
38b0de4e-b163-5bee-9296-b3fb14976e2c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.3 - Moisture
2b242331-6102-4aea-bdda-c89382c42f28 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.4 - Compaction
9162ce4f-45fb-57f6-b208-c61a72ff96a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
ac190c5e-3168-5038-ab05-225d2fdbec01 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
74f83a47-1434-542d-8b87-033e25f59b11 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
cd99354b-f585-5292-b3f9-1fd3f9b4957e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 5.0 Conformance check
bd22a5a4-5cad-5676-8406-2aaa9c93fef6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 5.0 Conformance check | 5.1 - Pavement finish
63cf6cf2-e02f-5edc-adc1-b50eacad81b8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
45c89768-7aaa-57a1-9f74-75c9d8cebc4d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-005 - 175mm Pavement - Pour 3 | 5.0 Conformance check | AUTHORITY HOLDPOINT
3560e90f-6c7b-4a3d-85c7-23e2e26bf135 |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4
20b425c7-a31c-5386-bc0d-42c42ba62b35 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 1.0 Preliminaries
e8e38837-e801-4021-b2bc-03f5b32f9315 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 1.0 Preliminaries | 1.1 - Determine lot size
a88fb3de-693f-5fca-8bb0-6eced07dab91 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 1.0 Preliminaries | 1.2 - Survey set-out
2518c4a9-7b1d-5ad1-ac09-3a970c0a1071 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 1.0 Preliminaries | 1.3 - Material classification and source
2abe1bd9-cc04-516b-8645-19d503f68683 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
f2ee58ea-e028-5ff4-847c-da68c8e1a5b1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 2.0 Conformance of previous layer
a93f9c2a-9558-5f02-a9e1-9d5d8e759fb3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
35979b5d-bacc-52b3-ad8f-ccda057cb1c3 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
00b75321-aaa3-5464-bda6-01e05a744bc1 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 2.0 Conformance of previous layer | Type of Pavement:
ccf58953-90ea-54e1-991f-59a2b295aa48 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving
401c0a59-c12c-5bbd-a668-7d3c5c3ed6ce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
a5c52df5-9200-5bfc-9e9e-3e907224a7c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
cd510ddc-8063-4e62-a802-79821c2b192c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
591534cf-27f3-5f18-b7d6-dd4531368a46 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
2d7a08d6-fa2d-5daf-be5f-dacbee206bdd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
ae0d8ed6-1823-5c8e-8764-fd15d8b66ef3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
61c9f677-7006-55e7-a352-58a6b04148f0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
ef65e916-99be-5640-aede-0d96bb60fd71 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving
da733789-47fa-5165-ba93-5459729df54f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
eab5efb4-bf82-5df6-951c-9865c3b316c7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
082f1f81-123b-5e36-be5d-c79ead2e3b5d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.3 - Moisture
f946eded-2c98-4dde-8802-a1bd3be5dabf |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.4 - Compaction
8bf1f3a8-77a8-532f-ba84-4fa73077e6c9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
ef1314ae-689e-5a32-94d1-16352b7f4099 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
923707bb-99d8-5d1c-bc0f-5a64a8196dd9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
07bfbc9f-8e3a-529a-92d7-4b5e57e4ea7e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 5.0 Conformance check
d7e6b702-a99d-51f9-ab98-24540b0cab32 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 5.0 Conformance check | 5.1 - Pavement finish
cea76304-bb6d-5b34-839e-2dd6ac4b36b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
7cdcf184-35d9-5f79-a71d-abe4fbc83f57 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-006 - 175mm Pavement - Pour 4 | 5.0 Conformance check | AUTHORITY HOLDPOINT
339fb4be-b3c8-4e51-80fb-0daf14ebeb5e |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5
225c02aa-b9e7-58e4-a4b4-7773c2cb3d79 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 1.0 Preliminaries
6cf2b9a6-7f95-442b-a664-7cdb69a65226 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 1.0 Preliminaries | 1.1 - Determine lot size
6517936d-9d13-5f86-be5d-81a34e7fb818 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 1.0 Preliminaries | 1.2 - Survey set-out
4dc9d921-9f72-584a-970c-422229360e09 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 1.0 Preliminaries | 1.3 - Material classification and source
37a0f1b3-610b-5409-8734-45efa7f99d58 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
82c2112f-f6d5-5265-8512-69e065a00239 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 2.0 Conformance of previous layer
025910ba-eff4-5c67-9982-06fd3f81d0f0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
b34e5c21-f56d-5a58-9ba8-5486d2671c21 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
e97d3534-7d09-5244-9da3-4abcf7666ac3 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 2.0 Conformance of previous layer | Type of Pavement:
70e8e5e3-d56b-5bf2-90a3-770e19a4c30f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving
1d8a5952-10ab-5527-8fd6-1f9b309b0c26 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
92e65d99-ac0f-5c5e-b711-860079babd13 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
24482670-2499-487a-9972-95f74d871e0d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
b6a06431-c114-5656-bab4-3c7b0a3697c9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
7a6c1a90-e9f5-5d77-b722-db044be527ad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
edbf91dc-b8ac-54f6-ba63-08eeba82ff06 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
59d51181-4467-5fd0-ac75-fefe0bcc2b39 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
7df71b4a-ceb8-5061-94ec-3a6384daa3fc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving
3f4e4d9f-d0b1-56e5-a234-0113201b885c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
8a03bf15-66bd-5371-b25d-8a02eb4e548d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
3acedc83-a02f-5abc-b929-6906034c517e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.3 - Moisture
b1e69fba-73c4-45ba-9047-d956132735c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.4 - Compaction
db008e07-625c-51ea-8b5a-1368abb023b4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
7e527bed-ee33-50d8-9823-de1e560269c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
f5acab66-52ee-5550-bbde-07c8eb8d173a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
3d852520-efdb-5898-804b-9d2f349b15ba |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 5.0 Conformance check
7e79868b-bed8-5bef-956a-645c8d7fcc9c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 5.0 Conformance check | 5.1 - Pavement finish
9ebf72eb-a5b9-52ac-be2c-0e33da1803e6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
a2ccd631-58f4-59c9-bb8d-9b5cb1d16e1a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-007 - 175mm Pavement - Pour 5 | 5.0 Conformance check | AUTHORITY HOLDPOINT
de5dd0fc-e5e7-4d07-b632-148032bf2127 |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6
c9c2023b-fb4f-59ab-97a4-261ac729a2a5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 1.0 Preliminaries
f24fb34a-9293-40a7-bf1f-f18957533972 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 1.0 Preliminaries | 1.1 - Determine lot size
67a6572d-e82b-5db2-818e-e0f8403b460a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 1.0 Preliminaries | 1.2 - Survey set-out
d2c3d381-1e90-5a22-ada3-3b3d6beb44b1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 1.0 Preliminaries | 1.3 - Material classification and source
f7c8cec1-08d2-521e-af19-248ba164e8ed |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
14dcc87b-b07a-5b47-87bd-8af9c15ade6b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 2.0 Conformance of previous layer
f6a1746e-a2b9-5a4a-a684-58aaa275833a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
8c7e3cb2-9d12-52af-97f6-3078082dfebb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
a1fa3b84-0bc9-5576-b768-550e684bc148 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 2.0 Conformance of previous layer | Type of Pavement:
c1298dd3-9237-5136-b494-cc59c7db92b4 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving
ea380600-8ea3-59a4-9442-7ec6856d43e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
87229e97-b4b6-5b49-85e3-098e74c94989 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
d0545b17-26d7-4a26-a5af-d0ea46a6ff1b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
e7062401-9900-5355-951d-f70f05c0673a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
52c2f2c5-12fb-5964-9012-05449b40069a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
6b2e2b37-a314-587f-86f2-62e26a34b23e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
b6a03712-7eb9-5a63-b651-41c70f4a7c2b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
23dc27bc-db30-58dd-8ca2-fb7e13c50ba4 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving
9953db9a-a730-5c4c-af6d-bdd7d989cae1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
38d26b23-7e58-54ed-acf6-dfbccdfcb516 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
2c864526-5269-593a-89f8-831d22c1b011 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.3 - Moisture
3a7e19b3-6e1b-4409-8e62-6469df66ef55 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.4 - Compaction
1597983f-a46a-5721-b1f6-2fbc581e9821 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
d575232f-8847-59bc-97f9-38cc164cb99f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
5b060c46-8b0d-59c9-8339-d9172e0e8d1d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
7ef9bf88-320a-5177-9b14-4a541d86d947 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 5.0 Conformance check
f4bfdb5e-ccc8-5000-a7a0-e82a228f5edd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 5.0 Conformance check | 5.1 - Pavement finish
dcea5964-db4f-5aac-8bdb-c72715c3a7b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
4d338756-5cd2-58fb-8883-7e6e9f2016c8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-008 - 175mm Pavement - Pour 6 | 5.0 Conformance check | AUTHORITY HOLDPOINT
710c076c-602f-4b61-854e-48f1839910b6 |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7
e6ec90ba-260c-5fa8-bbcd-e6a4e62fc9f6 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 1.0 Preliminaries
e309d801-272d-417a-af2d-0da11d03646a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 1.0 Preliminaries | 1.1 - Determine lot size
5a8fa409-ce50-5d6e-aadd-c170d3afb01b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 1.0 Preliminaries | 1.2 - Survey set-out
2cef8a4f-74c2-5145-af84-da5266d344bd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 1.0 Preliminaries | 1.3 - Material classification and source
7ce737ee-17a1-53ff-806b-51154a9c77cf |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
602c5b36-627f-5a9b-ab9f-cbb3ca99e4f0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 2.0 Conformance of previous layer
60828c15-3317-56e2-b16f-ab573a1d5aa1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
b8cf23f4-0e67-5e86-b1f7-e7ab3ef6e669 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
769f71f4-e282-5897-b32d-96441e9f8000 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 2.0 Conformance of previous layer | Type of Pavement:
46d83419-9c8b-5aa4-b2f4-d4db799fd0e9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving
f61be7f9-f1bf-562f-aace-e2b82f284e24 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
945391e3-1b60-5da4-819e-4731f5441b0f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
c66c52d3-02fb-4ae5-b811-bb63a96f3e4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
36fccf96-7062-5e92-bc2a-e7fbc9a62351 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
c74e9c6d-b8c4-5eba-a045-10a3422b3544 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
fef0bfbe-254a-5d1f-865c-2c6e011a4889 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
236c5f6f-b559-5f47-b859-11c6533f3b06 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
fded976c-d48a-5f32-8670-bebbc8323f4c |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving
ceab797c-0e97-5e6a-a169-41dc41f4bc5d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
f849f195-b950-5c74-b3b9-be81ec7478bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
8a6b4dad-fb67-5ebd-b04e-a94509b3c329 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.3 - Moisture
df6cc9d9-c416-4e0a-87f9-5769926a1c95 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.4 - Compaction
32dddd16-fcf4-54f9-9f03-146a49952082 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
81f17db6-0822-5fc4-b995-503a3ff32ab1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
d29fa486-5638-57d6-80c2-5896e12a4839 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
4513379a-abef-5928-9d7b-a4a23d97fe39 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 5.0 Conformance check
4c4cc188-b0ce-55b0-a401-2e45e09bce89 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 5.0 Conformance check | 5.1 - Pavement finish
73f2b7ea-19cf-59af-af7e-e7d4411f1d6e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
07cdbd29-7dd1-51e9-9973-7e7cea8a04a7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-009 - 175mm Pavement - Pour 7 | 5.0 Conformance check | AUTHORITY HOLDPOINT
67d2476d-1b60-4ecc-a5f6-959e30e05515 |  | not-started | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8
7d62f57e-58ad-5d6b-8ba3-003d89c4e2bf |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 1.0 Preliminaries
af9713ca-04a8-45db-b938-0936e116a3d9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 1.0 Preliminaries | 1.1 - Determine lot size
97249309-b235-5b00-a912-9b5b025b894b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 1.0 Preliminaries | 1.2 - Survey set-out
6d0a70bb-da80-5ed4-9921-b776e4844d51 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 1.0 Preliminaries | 1.3 - Material classification and source
9e65ba61-1662-56af-9276-57691f223a1f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
10fc404e-1758-5096-b86d-77eeba288982 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 2.0 Conformance of previous layer
4f5c7e60-0c1d-56a1-a243-77c858102bd6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 2.0 Conformance of previous layer | 2.1 - Conformance of previous layer
32e3d62a-639a-5ff1-a19a-1ed52e01aa90 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 2.0 Conformance of previous layer | AUTHORITY HOLDPOINT
40f7bdb0-c3e1-59eb-8a83-dcdab5562886 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 2.0 Conformance of previous layer | Type of Pavement:
b91c71bb-a568-587d-ba5c-4614b4baa31d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving
c1a7f1b2-7459-5bf0-a105-059479125f16 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.1 - Placement
8ae82f2c-f44e-5731-895a-c864ed0b8d15 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.2 - Moisture
7c102c58-0571-4cad-9b14-a3e1628cb36c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.3 - Compaction
5ea57ec3-3baf-59a6-92a9-1e1df63a9cf3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.5 - Test rolling
85e77129-63d4-5ec8-806e-77bb770ce19b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.6 - Identification of soft wet or unstable material
ba9f1116-5d46-50a7-aad2-ca6cd73c4ffa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.7 - Treatment of unsuitable material
f5a0f7d4-01bd-56b3-bd2e-6e669772bab8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 3.0 Crushed Rock Placement Below Concrete Paving | 3.8 - Placement of Polythene Membrane
d0a394ff-293c-512c-89e0-3eeee3835ab0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving
931220f7-d62c-5ff8-84bd-3c2c7729d233 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.1 - Placement of Geogrid
58bcc4b7-0880-5949-9911-ef2cabb8ede1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.2 - Placement of Crushed Rock
e1497317-8945-574e-8fa0-72a1c38a42fd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.3 - Moisture
e389a440-d8c6-4222-9d58-c87df6dfd7ff |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.4 - Compaction
49a7d84a-f044-55c7-9a2e-b392767eab61 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.5 - Test rolling
969b9590-8ffe-53d1-98c7-971caab719c1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.6 - Identification of soft wet or unstable material
3d75ed09-80a7-54e9-b0b7-30af4014c027 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 4.0 Crushed Rock Paving | 4.7 - Treatment of unsuitable material
8d5ddf71-ac49-55c8-943c-25e439642fa8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 5.0 Conformance check
6dccf38e-396c-5172-b67e-a40a648a6339 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 5.0 Conformance check | 5.1 - Pavement finish
a7a510e6-3305-5ff3-92e8-be484b26a7e7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 5.0 Conformance check | 5.2 - Surface level of pavement courses
4d2c39bf-b5c5-5a8c-aff3-1d22571424ef |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-003 Base Pavement Construction | VIVA-BPV-003-010 - 175mm Pavement - Pour 8 | 5.0 Conformance check | AUTHORITY HOLDPOINT
deda5346-3509-4829-ae32-f7c8573e4797 |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation
b5039268-42e5-4fea-a74b-92cfd1e316eb |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation
31245968-4ac0-598a-9696-0a5b181fab6c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities
0a52f046-8093-5610-894f-3cc094b7fada |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.1 - Set out
25a4da3b-769f-56da-99a6-29ba482fdbf4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
2ee86cf2-8f52-550f-bf30-b3a204a807e4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
879e2de5-0cb1-591c-835f-bfbd4fc4552e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.3 - Permits
7b27ab67-e7e4-5726-865a-b0604f0bfdd3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.4 - Determine Lot Size
8c954e21-d86b-576d-8b24-72d7b7f2bc5c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.5 - Delivered materials
05b84326-b8ae-5c74-a2f7-47f3ade435c7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
fd1df68a-5e08-5f97-a2ed-429ae9626000 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
5e8b96e9-bff7-5b98-9ec0-1ef2d2e56979 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
ae342001-6cd5-56bc-b68e-99a509226b03 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
89709706-ec05-53da-8ce3-48edc3013783 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement
a8a91aa7-7d38-5441-8210-d6236db7f660 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | 2.1 - Service Location
0dcb348f-be50-52ba-b9a1-7e91ec32159b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | 2.2 - Excavation
7ba12fa5-6337-5c80-b8ff-99bd77f32eee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
ea6c4921-42ac-58d2-94f7-7e04eac5e5d7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
bc2c3a41-06f4-5378-bb87-f93b3126f840 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | 2.4 - Conduit placement
bb3a0c97-72ad-553a-af06-7908b4ef8961 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
a0428ba4-66c9-5e96-a89f-9eee4dc00bca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
04433fd8-189b-5008-988d-9aa26ef0da15 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing
290bb86f-f3df-579d-ae99-ae2402cab1c1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | 3.1 - Clean-up of site
ad926900-9236-59bd-a9ce-5da3f6e01959 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | 3.2 - Identification and recording
cde20dab-11ef-5e11-872f-7da18312b129 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | AUTHORITY HOLDPOINT
65e98b76-15bf-5f03-b327-7024ea0ef763 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
b7e36043-a493-54bf-8e0d-e5c0b453dc70 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | AUTHORITY HOLDPOINT
0c5504c6-1a82-5844-aa42-7a89f9dce14f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | 3.4 - Certificate of electrical safety
6e0dadd3-5946-5f50-ab7d-32d309a09b76 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-001 - Substation | 3.0 Finishing | AUTHORITY HOLDPOINT
e77cbb46-1b34-42c1-916c-20c9c5bcaa2e |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I
aca57aaa-6714-57a7-8125-ae63277414b7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities
f9501b7d-6c58-5217-8338-0cf3d855eefb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.1 - Set out
fbc5d093-de6c-5339-b235-9d77ead934de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
1d68b3df-ea07-5260-acbf-2376b4013908 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
97174cba-421d-587a-9f1f-153c12808ef1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.3 - Permits
96b0e7a9-5b16-57f0-a785-f66b4596fbce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.4 - Determine Lot Size
a9cd331f-a729-5b80-94c4-d908a27aa380 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.5 - Delivered materials
ba7abe77-c58d-51b7-a968-328d6da65360 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
45a217b1-3e20-5e05-81f2-0e69d487d8fb |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
ccc011a2-9e8b-5dc2-8f57-6b557657f34c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
ce03b185-ab11-5f61-9f78-b77adf08566f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
967d9c8d-6850-589f-997f-fdde0a2589c4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement
0da5bec4-1d74-5980-af72-6b3de2e16151 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | 2.1 - Service Location
f9c1071b-e57f-537d-a2a5-18bc789d32c2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | 2.2 - Excavation
8759f460-6701-5467-8d32-833012bb85af |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
10aeaa5f-8466-5257-9f86-d97847756cfd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
3dd05866-b2b8-5355-a5b6-275f83e0471d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | 2.4 - Conduit placement
bfedf8fd-09ed-51e1-8f5c-2150225c0c72 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
6d353a06-f529-5904-a3ee-b6f67d502c20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
3dcb6bbe-7e6d-59c7-b978-48c420f2d77c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing
345ffbdc-87ef-5713-bf53-5054cbb18ed0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | 3.1 - Clean-up of site
b59bbe17-7fda-5d27-9461-2092f872668c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | 3.2 - Identification and recording
5c6c34bf-b8b9-54ad-983e-f5a659b41abd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | AUTHORITY HOLDPOINT
918dbf33-84c7-5593-a8f6-d7d45f10e611 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
fd7c0f9a-8759-5236-925e-1f58b726b549 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | AUTHORITY HOLDPOINT
c195a5ba-4998-5a29-9b02-8bc74a92246a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | 3.4 - Certificate of electrical safety
f04c24fe-f837-50c1-b552-66e7ad217114 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-002 - CWT E&I | 3.0 Finishing | AUTHORITY HOLDPOINT
3b65b96d-6168-484a-a1f1-973a99ca324c |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench
2cad1566-3f64-5384-9f8f-6df27d9af48c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities
98d7917d-8ad2-51e2-8bbe-0a490cfb259e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.1 - Set out
72618547-3a3f-5be8-a657-3355d9fef8d5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
e627cbd3-e15e-5c78-ad0a-ff05d34390d0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
b45d4feb-6c80-5c0f-a83d-2c11e9e15de4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.3 - Permits
2501f1fb-d544-59a3-9a0e-d2185db6a06c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.4 - Determine Lot Size
da026252-700d-5c96-8789-c323086ab296 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.5 - Delivered materials
cd5796bd-37cb-5762-8257-5cce3b2b9eea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
a7d54595-4dcf-5509-9e61-b5f0197dac9c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
62150339-38e0-5087-8b9a-1c6809b7bd38 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
b04c89f9-bbca-5717-a679-96c968cb551a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
33e8426d-7c70-551f-bb38-dd2aca11d6eb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement
b02f982f-2b33-5a2e-b0f4-bcb2b9171aa2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | 2.1 - Service Location
aa5de481-9d25-55c2-9842-41f379579c20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | 2.2 - Excavation
dbb5fded-9d69-53ca-a033-d1cfb73bf1ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
ff3e336e-9518-5f42-bec4-6a9747767790 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
a0194944-7e61-540e-9b5a-885065215706 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | 2.4 - Conduit placement
512cb769-b381-50db-be85-a8a0b7582d45 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
fe8aa069-3537-528e-b9da-18e1578499c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
ff6b05f2-6760-53bb-9329-2d37b4e27d21 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing
71d858e8-6ec9-5102-9baf-fdfc889e744a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | 3.1 - Clean-up of site
52eb0bcc-9e98-56eb-9e21-1e50a1935d43 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | 3.2 - Identification and recording
1528085f-f4f0-594b-8393-c9c647332286 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | AUTHORITY HOLDPOINT
3ddf7aed-dde9-586b-8270-4a9ad5035962 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
456c16f0-3d3f-5e47-ba03-0e0669136427 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | AUTHORITY HOLDPOINT
e9a3cb22-0b87-5864-8013-87914567500c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | 3.4 - Certificate of electrical safety
d9642ec9-ffb7-57a4-8625-d28188fd3c3c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-003 - Eastern Combined Trench | 3.0 Finishing | AUTHORITY HOLDPOINT
1a3f018a-37f8-423a-a1ef-511c2be6fee0 |  | pass | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank
ec9bbe01-04ba-5c6b-b7cd-bbe540320911 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities
57bbe607-b540-5134-be46-0f9050f16d91 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.1 - Set out
0974e121-ce67-5a4a-aae0-a562c29f40ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
71c6e6d2-9287-59e0-b0a6-3104b16e8968 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
044922d7-c511-53b0-91b2-94723c016fc1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.3 - Permits
93fcd8cd-3e2f-5141-9664-4073f0c079dc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.4 - Determine Lot Size
d5a50173-b30c-5186-9791-f525235db272 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.5 - Delivered materials
ad321a30-5498-5630-8646-ca8081011a23 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
1febc95e-110e-555c-ab78-be9860eb9a34 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
5421ba3c-6435-523f-bb1e-029f5d0c56f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
e35dc2e4-68bc-503f-a4d1-1d778a7469e4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
c8a10000-66a4-5d77-aead-6479c10f5640 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement
c402c1a5-77ee-552e-9c4a-dd50f2609df0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | 2.1 - Service Location
725e7f6d-f252-582f-8661-a4176c323612 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | 2.2 - Excavation
462cbd51-ce55-5bff-a882-a0fef27ae458 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
f574a91f-059b-5854-a1e5-7d74e10e3c5d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
e37646cf-922d-5ce2-98b3-65e78324cfd9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | 2.4 - Conduit placement
f5a3a269-29c8-5277-89d5-4519e913b5d6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
8188fd37-14c5-538c-a458-e9ee379ac9a9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
a1a5c6f1-2320-58e6-b681-ac1f1be687e5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing
3da9d37b-aba8-54ec-9c83-dcbc34930504 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | 3.1 - Clean-up of site
d8455e32-c56d-5fe3-bcca-54b85fbcdb95 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | 3.2 - Identification and recording
1f0b32c6-64b5-59da-b1fc-763ac719a6c3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | AUTHORITY HOLDPOINT
ee3824d3-cc6d-5cbe-aa34-b95637181ef4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
16961b86-398c-5df2-bcdb-df696629a283 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | AUTHORITY HOLDPOINT
2764c331-5fd2-5955-b10f-4e0660119d34 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | 3.4 - Certificate of electrical safety
f8c30018-b941-58b4-917e-158483be6eb6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-004 - Duct Bank | 3.0 Finishing | AUTHORITY HOLDPOINT
b3917faa-6bd0-4e8e-8db0-17b9de878109 |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111
b7671f52-1496-5ca8-ade7-5978143dc0f8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities
0fa96b71-f0e3-523a-b7eb-3804a8f67ff5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.1 - Set out
4c466999-4355-58cc-8ea0-cb3516b40192 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
9708c8d8-133b-5d98-a8d0-d52c85637eee |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
3f9b00a3-068b-5c6b-a2eb-0c23dc3644ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.3 - Permits
86e9248b-4da8-571d-90e3-7f419d0d2c77 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.4 - Determine Lot Size
5b413ad2-79d4-5da7-aec6-0a34b76cf396 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.5 - Delivered materials
e4a57b6d-79e7-5548-957a-88d89a058793 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
50099892-9815-533f-bc83-1242f3335f4c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
4ccc86fe-1b69-5d5d-b422-1c78f551dd91 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
71a46a5b-afcb-5e81-a63f-af296a9bca54 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
d4678e7b-6162-579b-8a3f-742536dd0cfb |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement
fdaff9f9-7c3a-5ba0-945c-6cc15d994322 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | 2.1 - Service Location
b6aa7252-a733-546f-a73b-aad4e795cfd3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | 2.2 - Excavation
1c7117cf-022c-53df-b71e-291760290582 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
d5ee74f4-4429-51ed-b410-22d97eb51d15 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
0de90478-55ad-5aa3-a4c1-5cf4496093cd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | 2.4 - Conduit placement
7344bb75-b2d5-5042-a142-81caede26a0a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
77407cba-49dc-5a55-aa51-a76c620cda48 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
f15bad3f-91ef-5144-82cd-62b2e5f74ca9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing
6ac2e5af-b3a3-555c-b826-b0c2f2df08b5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | 3.1 - Clean-up of site
6ad04693-9907-53aa-bb45-aac98d77daf5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | 3.2 - Identification and recording
f82a7d62-b742-54f7-b23f-33f52c4f94f1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | AUTHORITY HOLDPOINT
d94e3b69-bc21-5bbb-87f4-8a266423c55a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
c88aa30b-9b38-5565-8c4a-c495c9f0e935 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | AUTHORITY HOLDPOINT
bf6aface-e252-5de0-a7db-5b7492a2caf5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | 3.4 - Certificate of electrical safety
3e8830d5-5955-557a-8992-a5ab214aec8b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-005 - North - CWA111 | 3.0 Finishing | AUTHORITY HOLDPOINT
4addc7e2-4207-4746-aff4-44db45cb4f4a |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS
c20aa34a-5956-50b8-96d2-45ede2673ecd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities
2e517e60-8d07-57c2-ab5d-e71a634956a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.1 - Set out
7e96879d-8e2f-56d4-b7f6-2a70414b6aa6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
948166b3-1273-57a5-92c9-a2a09feb4402 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
cbf6339c-6e8c-5cb4-aefd-f18c685de9fc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.3 - Permits
024dd13c-6fc5-5b1d-956c-04dd943fb4e5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.4 - Determine Lot Size
18618dc6-195a-5cf0-9a6f-b8dce828ce9e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.5 - Delivered materials
d25daf6b-03c3-53d0-a90e-0475d892a3f3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
66fe1dc1-3929-53c2-8a8b-35307f686516 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
2ecaaec3-ba1d-5fa5-8359-bbedddeddefb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
27174ff3-1b10-545c-a5fa-976dc1915459 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
39c410af-5345-5c3c-a5e1-d0952a824250 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement
c4e9f1ee-f6e9-59dd-ad80-009477d85e1d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | 2.1 - Service Location
5a5728da-ab31-54bf-8fa2-fab8636405e8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | 2.2 - Excavation
0992f3b6-03d1-50af-9c70-988c2d8424b6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
f5356a8e-a029-5ba8-9b10-c22332cde020 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
cfec6e9d-200d-5f1f-924f-68f2c586806d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | 2.4 - Conduit placement
63a25dca-1037-509c-b051-59b185ee2315 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
01ea36b4-d91a-58d3-9a2f-922835e11209 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
ec947b77-f7de-5cfd-8715-15496fd42d21 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing
a5599067-f29c-5c87-a97e-ac6802cf7e31 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | 3.1 - Clean-up of site
51d2ea1d-8309-5c38-b25b-4a61f1414ce0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | 3.2 - Identification and recording
e52adb1b-5df1-5316-8e49-d7601f30cac1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | AUTHORITY HOLDPOINT
d06bfad8-551f-54a6-8cd2-67973a2a2327 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
7126474f-4beb-51fe-afea-397f5f077dfc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | AUTHORITY HOLDPOINT
8ee4059f-b20b-5f76-9bee-00e56c179684 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | 3.4 - Certificate of electrical safety
5c6d38c3-cce4-5f2e-af1d-74685f95c625 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-006 - F5401/5402 to Fan Stack/PPS | 3.0 Finishing | AUTHORITY HOLDPOINT
e7189221-5cd5-4f9d-864d-278201bd1096 |  | work-in-progress | INF-HSEQ CC0398-ITP-014 Electrical Conduit Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits
732e9f8f-989a-54f2-a7fe-2872034266ec |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities
00f8e8cb-6edd-5a73-b78c-c510e95100cd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.1 - Set out
61f36836-a53d-5237-b00a-17689637f5d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
d5f77629-ce65-5607-b65c-b134a7ba9676 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
769c3e3d-2a06-5c3e-9f7d-ee4e9d4c7f62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.3 - Permits
4b681721-d14e-5808-8667-23c4a2e7f551 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.4 - Determine Lot Size
130b60d2-920c-591e-93d0-12fbbdd42024 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.5 - Delivered materials
b50983a5-0bb7-5b6e-b137-ce4f089c56f8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
c67f90af-7231-5d78-87e2-69e22c6a78e9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
5052c0cb-d42e-5be6-9f45-0f74e0cfb7e7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | 1.7 - Backfill Materials Approval
93edff0d-5904-5697-b06d-20ef72781c87 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
1b60cbb4-99d0-5818-a097-0b83a7404bbb |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement
92af0a62-69ce-5698-acb0-0d1caadc4472 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | 2.1 - Service Location
2f5fc802-6810-5f64-8fa6-0a3e97f60a84 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | 2.2 - Excavation
c025de00-526a-569a-b096-8ddd44ec8b89 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | 2.3 - Conduit materials and size
f8128c89-7cf3-53c7-aca2-95dd92abe094 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
3e23e65f-435a-571b-81f0-d3a2f656965c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | 2.4 - Conduit placement
cac9bc40-82c0-5698-a91f-bb54d09b2f85 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | AUTHORITY HOLDPOINT
e2ba72e2-6848-52d8-9917-f6bb08eff691 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 2.0 Excavation and Placement | 2.5 - Backfill placement & Marker Tape & Rope
cb6e04a4-7860-5dd5-bb9f-eee4f2572353 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing
610b3c09-5d92-5669-a6df-89d9f739c4f9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | 3.1 - Clean-up of site
c6fdac38-e60c-5c00-b29b-5a2b2600373e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | 3.2 - Identification and recording
c9dcf4d8-9912-5d77-8894-b4214e18ee56 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | AUTHORITY HOLDPOINT
664bc10a-688d-53d1-9d74-4e716b5d26cc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | 3.3 - Work is complete and complies with design plans / drawings / specs
6f4774e4-8f5a-5853-ab12-0700579bce88 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | AUTHORITY HOLDPOINT
9f2f809b-65c7-5e06-8e5a-eba954a6114c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | 3.4 - Certificate of electrical safety
c021c082-49aa-5da4-9f23-b6122c41ee55 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-011 Electrical Pit and Conduit Installation | VIVA-E&I-011-007 - K5401 E&I Conduits | 3.0 Finishing | AUTHORITY HOLDPOINT
87f617ab-4cd0-4c47-abbb-b145a22ace1e |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions
03a7ff01-2ecd-459e-a7cb-8810afdf6781 |  | work-in-progress | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement
137acda9-4c46-5b1d-a24a-1d398783e41e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 1.0 Preliminaries
6c35fdb0-268c-56b6-9243-10da11c5d943 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 1.0 Preliminaries | 1.1 - Determine Lot Size
a490bbe6-b926-5005-b469-813921af04fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 1.0 Preliminaries | 1.2 - Survey set-out
cbdcd581-0e7a-5cf6-8c8d-317f48d58fa4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 1.0 Preliminaries | 1.3 - Material Submission / Approval
88f6d882-475d-51a1-91ec-e8a29472e64c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 1.0 Preliminaries | AUTHORITY HOLDPOINT
dcfc5bb9-4aa3-521b-b282-731f72799772 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 2.0 Form Work
59dab6f9-261e-58bb-b627-8edf59abb514 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 2.0 Form Work | 2.1 - Vapour Barrier Installed
c1560f66-a9a7-5478-a535-6d435357a446 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
2d01bdf1-35a4-5ee6-a556-52b94f92ac2a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 2.0 Form Work | 2.3 - Concrete jointing
70d251bd-8d26-5361-8061-7f78aefbb2ec |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 3.0 Reinforcement
9b0528ae-7203-50bb-8d81-b123714621bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
cefa1189-8d3a-571f-9a6e-f8a7f11c2f8d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
e40887d5-8e19-5b3d-a1d9-37a21386739a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement
bf28170b-d21a-5684-a5a2-cf593931db1d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
0c69e973-413d-50fd-8e32-653112a21a56 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
089c58dd-a14b-572e-a342-93ce3137926e |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.2 - Placement
e3e669e4-f912-59bc-bef3-8a1cc63668f8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
35a99b17-19e5-5b7a-9547-c62dbe4dc54f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
00d8b732-6934-5118-b18f-47988a6c9c2b |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
df8aa241-0ac1-51ad-bb15-7442c6b21a73 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
4c56a0e2-15b5-51d4-bda1-508ea1997744 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
74113f65-0f61-5129-b44f-c5a0fa8e9523 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
62833738-19af-5052-b7b8-524b3c921847 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
7d7f602b-a6be-5df3-bb5a-598fbea7a6ba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
531f01ef-e4ca-5e34-9e6e-c03a05d46046 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
814dae22-7372-5f92-ae42-3a4778c0d097 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 5.0 Completion
6d1200d6-bfb0-5655-9b23-a9c0ba9f6dc3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 5.0 Completion | 5.1 - As Built
298f2c6c-11cd-5524-999a-7fec4bd87d8c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 5.0 Completion | AUTHORITY HOLDPOINT
9be18538-140d-57f7-afa8-a1bde7821044 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 5.0 Completion | 5.2 - Concrete Test Results
d80e78a1-3be6-5390-a576-ee0a559148ee |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 6.0 Crack Repairs (if applicable)
e2cc63d6-5ecb-5732-af46-13ba39c7ad9e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
5e7b84c0-4812-5eb4-b08a-b78e0e0e6827 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
f7c88b48-7eec-5ae5-b142-5117ce069c7b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
93f1af7f-cc55-5a12-b9db-e661916ba78c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-001 - CWT 150mm Pavement | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
d0dfe737-9ea1-4798-9217-8dd2e56e8620 |  | work-in-progress | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1
d39739f3-4b3c-538f-9321-7189cdaeec7f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 1.0 Preliminaries
a3e7a961-55d8-52f0-886c-cc2fface1dac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 1.0 Preliminaries | 1.1 - Determine Lot Size
d5276281-4e47-5f11-94a3-d00355ff4063 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 1.0 Preliminaries | 1.2 - Survey set-out
f3c6f998-d4b7-50e0-8151-9f2e932a5e5d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
ad4ff52b-a7cd-54a1-94d4-fff9aedcc3b4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
eb64ebed-dd55-5b3b-8d60-0aead3ac3bd5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 2.0 Form Work
dea0a70a-c350-52a5-8fa6-5bc7755d0b84 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
ff466812-d6c3-5975-b26a-41d8c2d7703c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
3ceb724b-72bf-52f0-91af-3a2b10a0ebe3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 2.0 Form Work | 2.3 - Concrete jointing
ffb10c73-f79f-564a-9100-662f8892961a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 3.0 Reinforcement
8226ffcd-535c-5847-bb8b-23b9cb9294b2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
3bb18874-1bea-5c47-a177-8b731dfcf360 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
c9f24c43-3bde-5482-addf-d3ec5c828ec7 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement
ac0505f3-4fe5-5cff-b658-7e3cb43dccf8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
d7120b30-938e-5a1d-b488-0bc90d2d92dd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
8b3e7450-e602-572c-8426-6e40bc5aa5e6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.2 - Placement
31f931d5-4654-57f9-a734-9bdfd2966523 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
1cb82bb1-afeb-511d-a16b-d3afd235c344 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
05bb2241-4b0e-5620-a2a9-129fe181d953 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
b28ba47a-a245-50fa-aee5-bcdb94f4d8a2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
5ed5c56e-8e98-5998-a230-228bb693b624 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
93a2bf2e-74d7-5a0e-b002-f6cf2731521c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
6dc833f3-6d34-55f2-9830-1a6e444fda4e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
35b04392-8a81-5767-ad45-4b4a3716a3c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
662b2cac-b366-5458-a85d-3439aec57311 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
f8fd384a-b9ae-58ef-9412-74209e42ec07 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 5.0 Completion
df6ccd9e-f990-5bd9-984b-3da45fcc1981 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 5.0 Completion | 5.1 - As Built
5be5d59e-b572-5546-8f80-c8de3dec986e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 5.0 Completion | AUTHORITY HOLDPOINT
846f7424-613a-5b3d-b980-759170f55022 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 5.0 Completion | 5.2 - Concrete Test Results
883e3007-3b3b-50af-80e7-c8a617c4ab9e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 6.0 Crack Repairs (if applicable)
213e58ba-1671-510a-b786-874108ff77f1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
4c9c91a3-45df-56a1-a794-1ac7961625ac |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
c32ff4f3-f693-5c0c-8b8f-53a40f5f27ba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
8f3a5d01-4902-51bd-bfee-459fecd4a3d5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-002 - 175mm Pavement Pour 1 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
d7e2dce5-095b-4d8e-a8f3-b08fa13e540f |  | work-in-progress | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2
fadd7cf8-fd7b-573b-9c99-ba466ff40028 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 1.0 Preliminaries
380d7bfd-b8b0-5623-9bb8-7ecd0e23aa8f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 1.0 Preliminaries | 1.1 - Determine Lot Size
edcb0c8a-9097-54f9-9ada-c918a4e86eb6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 1.0 Preliminaries | 1.2 - Survey set-out
e0baf721-555c-5b7d-9a3a-bc54c102245e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
527ffb8e-2404-5f25-9afd-7c0791a73f79 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
f749ca68-4565-5167-bc80-a92b8a5b8051 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 2.0 Form Work
ceab6bfb-9a40-5cb9-a327-1b4ea5fbd232 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
6f2f1d76-52c1-5506-afb5-1bdff364bfc1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
c7efe804-6be4-5f6b-a644-25b1a1d7256c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 2.0 Form Work | 2.3 - Concrete jointing
4e346b82-5f74-5e20-8113-0a36740aa674 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 3.0 Reinforcement
32d12d98-08e6-56c6-9d98-7c69ee37f005 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
bec7389b-0ba5-5996-abae-1cb5f4c0cdf2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
0d9a909b-2b99-5165-999c-2eb532b4dd09 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement
addf0a64-7476-5975-81f4-a71bd0a598f0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
32ed0587-66cd-5364-93db-a952c1892608 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
896c1a6b-2456-5c64-8a61-4ccd104356a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.2 - Placement
e50f1d33-883a-5760-bb7c-a5e44e3bf3a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
0cd5bc06-b58b-5201-a309-cc716028b9a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
223b05bb-bfa5-5aa1-8222-9dc22ac74419 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
a3e9d1fd-ca7f-5863-be44-02586dfaa2a2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
5e6c4d63-e100-5a51-90b9-3088135844a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
0fdc0773-9865-53cc-b297-23bb7fd42f9d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
523d5168-46d1-5bf8-a55f-a2cbc81c73cc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
8b3cbf13-d2b5-55a1-8537-aa6414ad4b94 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
e645f94a-258f-5411-a00a-75cb67fcbdd8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
cefbfa31-09de-56c1-813e-f5a45619232a |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 5.0 Completion
63a1b935-2e64-5fd8-b013-fa63c53739bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 5.0 Completion | 5.1 - As Built
f1f5017d-7f41-5c54-8dc4-84c8fbd34e65 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 5.0 Completion | AUTHORITY HOLDPOINT
86007a17-5101-5c65-980b-ceed53e1edc3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 5.0 Completion | 5.2 - Concrete Test Results
dd16e965-2d15-5ec3-bf14-871ad881e8ec |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 6.0 Crack Repairs (if applicable)
5d2cc8e1-29e1-56f6-8c2e-c3e475917acc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
994941f8-c624-5b04-b448-6b2c0883b432 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
9e400c9a-7578-56e5-b6ae-265b612cc74b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
b79e2532-60fa-56d6-89d6-fccea165c84a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-003 - 175mm Pavement Pour 2 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
efec2ca9-fb03-4a8b-8bb7-12e03d2a3edf |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3
f3aa9c2e-686c-5a63-9d4a-e99a4a4e4cd6 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 1.0 Preliminaries
6ab75014-f554-57bd-97ba-42385b704a29 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 1.0 Preliminaries | 1.1 - Determine Lot Size
d6b51cab-4e53-5357-ae1e-b84d8bad7c1b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 1.0 Preliminaries | 1.2 - Survey set-out
60376846-d6a7-5308-80cd-d1bda7531585 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
2f11a745-1880-5eae-b249-1cf2320dba56 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
d3fd6409-714d-59f9-b11c-16bd5e70fe68 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 2.0 Form Work
05b29550-9de7-57a5-97d7-b40b29bc501d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
157e9c1d-3cd1-5903-9488-8d97b6decf29 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
db316f78-7277-55e3-9534-eb25ba6100a2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 2.0 Form Work | 2.3 - Concrete jointing
3101a628-9996-5399-9fe5-5742e6166fa5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 3.0 Reinforcement
2131511c-87f0-575f-b117-94e83ebc3e02 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
050c8b84-d00b-5da3-8063-e1f6801c9f53 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
ca47a4e5-5d3b-5e88-b688-27916ed71ff1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement
8c72f761-3007-56ce-beca-01a7248eab21 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
02657dda-60ab-5368-b874-65fa0be419e4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
08925989-b060-55e4-9fa8-e04fdaef9b15 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.2 - Placement
5ba41dfc-7ce5-51fe-b5c9-2fe1a8321813 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
d92d1992-03fa-54b4-9d51-6b2ddf8603e2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
ab15ff59-296a-50f7-9097-457fb361d6d2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
84e5b767-45b9-524e-bcdb-18c69bfefea7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
fba2e7b3-fe60-5049-b4cb-819a5542e88b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
c01c3c6f-aeac-58f6-b246-7e98a826e1a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
cbbc48e2-839e-58ef-ab79-d631d14da4bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
f2fff654-1ff2-553f-b18c-3c22f1b4eebd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
a82d0e81-ab19-5c99-8e81-c9596790b1bc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
e9d8c11c-bc5e-5c99-9c2f-fe7248d1db5e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 5.0 Completion
f0afd294-f92f-54c8-80ed-08bf2e18251d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 5.0 Completion | 5.1 - As Built
f79a5eaf-6ef2-5a85-92be-2ecabb984d72 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 5.0 Completion | AUTHORITY HOLDPOINT
8b55f6c7-850b-5a7b-ba4c-3f8f2fd3521a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 5.0 Completion | 5.2 - Concrete Test Results
2617fab5-501b-5263-8ecc-802f510d4f28 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 6.0 Crack Repairs (if applicable)
27bc7068-7cb1-57e4-b04e-65a1fba47b4e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
410934d5-6673-5737-ac9b-6f7c156d9371 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
b51e9bfd-fd59-5e91-bc37-695bfa8f835f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
1ca455e6-17ad-56c2-a3b3-b49fd15e5d46 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-004 - 175mm Pavement Pour 3 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
d8406b74-2f01-48b6-b227-80ef2ad1a013 |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4
76ef2cdd-e584-5cf7-b5a9-408796a9d569 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 1.0 Preliminaries
76370c13-8f8c-50e2-b695-02680812cf4a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 1.0 Preliminaries | 1.1 - Determine Lot Size
e62e76a1-88b7-5c39-ba8a-5c1ed4b2f533 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 1.0 Preliminaries | 1.2 - Survey set-out
a02eed7c-eacf-504a-8b99-dbc94ad15b1e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
bce1c752-5191-5ec7-b1b3-4d2e36186561 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
e642b523-a10a-5ade-ac11-84b7a76cfd83 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 2.0 Form Work
23803101-258c-5829-9b33-79f35a88e309 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
1f2256db-918b-5fd3-a61d-a37bd9d1f624 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
f0b96259-e63d-5d21-8592-f9952c406ea5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 2.0 Form Work | 2.3 - Concrete jointing
9c5f274c-4266-5998-86ef-4fe966c3e683 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 3.0 Reinforcement
7f0fe92c-f723-5e35-a85c-90ce36e9a621 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
ef6d7454-5505-54da-9245-f3d83bee36ef |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
b0582337-efd5-55b4-b96b-8f2cf815d52d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement
6e290fce-dbac-50e7-86e2-ae1a5394ecb3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
ddd98e48-c2f5-5e51-bb7b-f048141c001a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
0fdfac0e-0e44-5e5a-8a57-27c0a80bd54e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.2 - Placement
0965990b-6651-5064-bac2-67ccffc71801 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
277712af-8b99-548b-9b53-cbe45de83da3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
dcead567-e08d-5f0e-9ce1-cdbac2c8fb67 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
56a1ef4a-b67c-5190-b0d9-eee0bd957784 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
be6fafe7-1d50-5220-971c-9b0995548c47 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
7075cb63-83e2-58c8-a0a5-79ea861c07d7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
5b5098bc-aa0d-56c6-a608-9ff0142ad278 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
24e6799c-154e-5bb5-89a7-5cdc372fba77 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
ad040ffa-a27e-5c90-86fb-bb90e4c7096d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
d0af561c-d63f-5e42-8528-65dfad8c6835 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 5.0 Completion
6ee6c0c3-cf67-5fbc-af30-0f6e27f9235d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 5.0 Completion | 5.1 - As Built
cf50e19c-1930-56f6-ae13-162fefcc5a67 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 5.0 Completion | AUTHORITY HOLDPOINT
70331194-6d2e-5165-b7e2-9ddfd10b3306 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 5.0 Completion | 5.2 - Concrete Test Results
9c811719-98d5-5b75-8b55-180ac437ed38 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 6.0 Crack Repairs (if applicable)
220ede38-bf73-51a3-9859-93b8b2881db1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
1ae9bd58-0755-5216-b8db-eb2266647529 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
614cd617-9345-57a3-8f1a-847ce4f9edd9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
a19f52dd-3a20-5a1e-b951-f3051f0b5963 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-005 - 175mm Pavement Pour 4 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
42dc59ee-33e5-4117-9304-15b6fc467e08 |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5
c7b25bae-20d2-5139-8ab6-a634f78aeb9f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 1.0 Preliminaries
05d33fd5-190f-5146-94f2-3f77a2c893ae |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 1.0 Preliminaries | 1.1 - Determine Lot Size
66c5d9c6-fa82-5cbd-a507-83382ad7ef97 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 1.0 Preliminaries | 1.2 - Survey set-out
89e5c9eb-5ef0-5410-a86d-3151708f26f5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
4a3fea42-affd-5271-a7e5-d56ed5864bba |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
2de1badb-fb99-5b63-9473-e58ea5217d99 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 2.0 Form Work
f9795d15-3545-5612-8097-58145d18a978 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
0e88034f-800b-5a8e-83b8-756100018f80 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
c6b30271-2f61-5b97-a5ca-5500247d8727 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 2.0 Form Work | 2.3 - Concrete jointing
726be99b-eb03-576e-84e5-ef4e100919e2 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 3.0 Reinforcement
304d959e-7c27-5956-8537-c8c960bed1b7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
56ef78a3-8bed-50b3-875c-b1be36074f26 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
493803b6-a60d-584f-8115-fb0048a73231 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement
3740e658-97bd-59b4-a71d-15733187a362 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
142ca347-3f8b-5a9d-81c6-4022baee152c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
f0c5d11a-9e5a-542b-a7a0-d9112a32d8d9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.2 - Placement
ca4e516b-3e07-5b35-9226-6ccb0aa73270 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
92dc4c77-85ca-510a-9cce-01747290b731 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
57e53e70-688e-5555-95da-0f371a5a3b96 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
90547983-7353-5c00-80f2-c533624c299f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
737cdd32-3b90-5194-ae5a-e4024f3343be |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
de888426-baae-5861-a6b4-d1548e63481e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
5bac8d69-9230-5c73-8d61-4de0e022e044 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
74ab820e-0720-5b5e-b405-123c3bddf86f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
04622472-8cb5-5588-ae18-011d888fd4f2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
f4a4af57-d7c1-53ef-9ae1-e14a154c92ea |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 5.0 Completion
dd0cdb6c-2efd-522e-8b86-2e42f2943c51 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 5.0 Completion | 5.1 - As Built
f33fdd59-9324-5866-b628-0842ebd87a08 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 5.0 Completion | AUTHORITY HOLDPOINT
87d13594-a5ec-54bb-b669-51821de9a2a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 5.0 Completion | 5.2 - Concrete Test Results
d0078744-266e-51b3-9ad2-5f053adf66b8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 6.0 Crack Repairs (if applicable)
4c47e80a-c8be-5b61-ad24-9b8220daf052 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
6299e258-3387-58be-bd2a-01af2d3def72 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
8d5862eb-1d62-5fb4-8e37-63b5d46671df |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
e0050105-fed5-57ee-b772-a597ed8d3cc2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-006 - 175mm Pavement Pour 5 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
1e7d63f5-ea43-4cf6-9522-e96ee92ce730 |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6
f8154fd9-1358-593f-897f-d6bfbb0a13bb |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 1.0 Preliminaries
a285a07d-7c47-553e-86f5-9e4982ec8b75 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 1.0 Preliminaries | 1.1 - Determine Lot Size
2862688c-5bd4-5404-a4c3-f3a8b91fa52e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 1.0 Preliminaries | 1.2 - Survey set-out
168af24d-6551-5e83-a474-45a59e886914 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
dd6b8e2b-e160-58e8-8e66-3ed08625f3e5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
f0c4bfbf-2b9e-50c7-aabd-c4805761e73f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 2.0 Form Work
1bfda372-873a-5be9-9d7d-5e1e38eb02ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
602d64bf-ca56-5069-91f2-4741f17840bd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
278e9a27-474e-5d45-815f-981c9cbb7dd1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 2.0 Form Work | 2.3 - Concrete jointing
f415006c-680a-56e7-a88a-40971d993493 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 3.0 Reinforcement
c58f22b6-0360-5a22-8baf-88bff910c826 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
8112d49c-8794-5ea1-8cfd-f6178358d7e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
0878c517-fa56-5d71-b290-72b6e3dbbea5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement
1ceaf28c-978a-509c-85f1-cc53b9142e79 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
3e6ef34c-20a2-56eb-a5eb-eb613956e362 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
3c93c243-2707-5d79-a696-a2f804ce9b5f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.2 - Placement
8fa1836a-99d4-5b67-9b4b-86fe3d15c005 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
e5f41f06-e10e-5c7c-8125-2eb75f40dd44 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
0207fc56-5505-57ef-b322-99a118c793e0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
da6db727-ecc8-5de3-ac9a-5ba924a78a46 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
215ed66b-895a-59fd-8368-eb0dd45b1de5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
80572b86-e5c9-52a8-bf45-1dd8b4fdeccc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
ef910b64-54af-5bde-8b7c-18b6af403684 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
555f0da8-c476-59c0-8852-0ac1ea7f3d84 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
b436b0b4-7025-557a-9957-e4b699e0a486 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
73d86652-08c1-5cbc-abb1-5b681d309443 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 5.0 Completion
58fbde48-7db0-5704-ad86-39468e1faca7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 5.0 Completion | 5.1 - As Built
a4d78a96-16f0-5362-b94a-b29d3c36e893 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 5.0 Completion | AUTHORITY HOLDPOINT
c16a0430-c44d-50e2-a366-c34b1e4ed8ca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 5.0 Completion | 5.2 - Concrete Test Results
e10f430b-dcdb-5fab-923a-6c241819768f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 6.0 Crack Repairs (if applicable)
7f3e7888-3812-5c4f-a5c6-77613af25cba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
793d5703-976b-51b2-806c-23785c70db76 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
591cd2c4-24b3-5881-b530-c489fcb46232 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
e6e1227c-07f8-54c8-80df-974672914f30 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-007 - 175mm Pavement Pour 6 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
b270e0de-d571-4735-9f7f-73c083aacbe6 |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7
65e55e55-4bcb-549d-98f3-d08e1ae2bc3d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 1.0 Preliminaries
3b8f3e63-b673-5ede-a59e-ecd5a1d26426 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 1.0 Preliminaries | 1.1 - Determine Lot Size
8d4ce04a-5c56-5aa5-9eff-e57172041852 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 1.0 Preliminaries | 1.2 - Survey set-out
25ee2e76-3730-5655-9dfa-8bf974f27710 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
1e8d95d0-b1f6-58f6-abb7-1bf65efb400a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
b80dc874-40a8-50e8-87ef-b5edc04f9d74 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 2.0 Form Work
0156ce57-f69c-5d00-b2fc-1c5ed01fd6d5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
9575988c-b091-5bf0-a53b-77e399a17593 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
8b4051bd-abeb-51a3-bf12-0a7824bdc533 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 2.0 Form Work | 2.3 - Concrete jointing
a08975b5-a522-5a74-a84c-dc245e3aa3e0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 3.0 Reinforcement
02e9f821-22c1-5ae6-b393-f4fff4aa7925 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
cb6bc8fd-e570-59bd-a54f-2f11d78b09b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
ea31b537-967a-50a4-bad5-ef793e3c53c4 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement
7c7b3b3c-6fa9-5c15-a420-3d54bcfe88b7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
ea28834d-0bb7-5570-9c05-ad7f9907d80b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
6c066a4e-15a3-5095-87e5-895a06adb7f7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.2 - Placement
41ee6b41-1c2c-5c4c-a2a6-6abcda7f7848 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
1e05510f-4709-599c-aae8-7e5be4555d84 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
d23872b7-0420-5f8e-afab-7631692573e2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
25c3be9f-94ce-5e35-ae20-ded6962235c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
33850104-4134-57f4-ae69-e0b2ea8d3fbe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
44f31ee2-a089-525f-abf8-eab5804c3b68 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
b3e75b62-d35d-5d39-b821-58fbb75ca105 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
44e8c764-285b-511a-8a36-3d3008c3ae8c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
865d3433-0d7e-510f-828d-bfb9df347cb1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
8f30109a-3aa0-5911-9fff-123452814d9d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 5.0 Completion
c1e24767-aec9-5b62-9911-645debbb6fb9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 5.0 Completion | 5.1 - As Built
597d39a9-2fd3-51d6-8fa0-6e977064d656 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 5.0 Completion | AUTHORITY HOLDPOINT
cc1c2561-b518-5e81-9130-e5f49dea0f24 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 5.0 Completion | 5.2 - Concrete Test Results
e0ad4a8f-e04b-50eb-8f90-9466c709efa9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 6.0 Crack Repairs (if applicable)
2d2c6f10-39c4-5a9c-ab01-618188b6b01c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
a30b0f06-90bf-5386-80cc-bd69ca8dfc0e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
a7fd95e6-26c0-58d7-b372-06aaecc87e73 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
492d19e6-5a2a-513d-92eb-94ff401223ed |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-008 - 175mm Pavement Pour 7 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
e90b32c7-1086-4f63-868e-b4d98ea7ee13 |  | not-started | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions Rev 0 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8
e283d2a3-4b3d-5e6d-a4b4-f4380ff52dac |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 1.0 Preliminaries
3cc77ca0-d4b3-5fa0-bdc6-dfc2d73b49f9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 1.0 Preliminaries | 1.1 - Determine Lot Size
5ff179dc-1768-5232-a13b-98b26ef9ea10 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 1.0 Preliminaries | 1.2 - Survey set-out
2a3655b0-dcce-5e6a-8324-9cc755fcde17 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 1.0 Preliminaries | 1.3 - Material Submission / Approval
d995136b-d573-5c59-810a-bbd8568d706a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 1.0 Preliminaries | AUTHORITY HOLDPOINT
5b52565a-901b-523b-ac56-0b57381f104b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 2.0 Form Work
066f388a-29c3-538b-94e0-adbce41ea20d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 2.0 Form Work | 2.1 - Vapour Barrier Installed
00bcf023-fb6b-5d01-840a-f002e7074957 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 2.0 Form Work | 2.2 - Formwork Setout and positioning correct
f8a77445-935e-5bdd-9c69-8a19332299ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 2.0 Form Work | 2.3 - Concrete jointing
bbbed0b4-684b-5c4a-ba41-036905753dee |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 3.0 Reinforcement
1b5b6f23-f576-5c9b-9b00-6e216bed4a7c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 3.0 Reinforcement | 3.1 - Steel reinforcement Supply
8e572b91-4dc2-5b37-9018-39b145606a68 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 3.0 Reinforcement | 3.2 - Steel reinforcement installation
c31d0d1a-91c3-5bb4-b111-d23dee726f30 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement
1b6b5d4e-ebd5-5c10-86d2-16b5015b478f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.1 - Pre-pour Inspection
595c007f-cdce-5972-8dbf-22fd0427dd8a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
592de6bd-e2c5-5ad8-9dac-8a8d841822b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.2 - Placement
db24c779-7248-54bb-a370-4b3c69349bf9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.3 - Slump Test
85d3f75b-a08e-5e3d-bcde-285c9e008fe7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.4 - Strength Testing
90656804-04fd-5eb8-93e0-74b2ae0fce08 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.5 - Curing of Concrete
cefecca8-6089-56b3-b93c-f9a6e606e590 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.6 - Colouring of Concrete
e3729390-6904-5eee-9bc8-8eb5660d5cf7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.7 - Concrete Finishing
2a2fb906-e093-5e3a-bd45-ffad53cbd85d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.8 - Formwork Stripping
195c79f0-cc90-5df5-9b64-dddf37737dc6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.9 - Saw Cutting of contraction joints
a9f9944b-2237-5cf5-9ba5-1cbe3ea92d45 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | 4.10 - Post Pour inspection
25e89849-2e3d-5c3e-82ab-75ca330e7a66 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 4.0 Concrete Pavement Placement | AUTHORITY HOLDPOINT
930c5bb1-a7e6-57ee-be21-100adbfcd9a5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 5.0 Completion
d1b27539-5b2a-5031-a626-9a009c35d4a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 5.0 Completion | 5.1 - As Built
635e4188-255b-5604-9286-102a440002f7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 5.0 Completion | AUTHORITY HOLDPOINT
0879bbdc-22cc-5879-9cfd-24ab344abdc6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 5.0 Completion | 5.2 - Concrete Test Results
16e1af4b-95b8-5cc9-89a3-e39d4fffd305 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 6.0 Crack Repairs (if applicable)
1875a398-8526-5651-b5ed-b8470f10307d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 6.0 Crack Repairs (if applicable) | 6.1 - Cracking repair methodology approval
63b60c7b-1818-583a-a2bf-9a4d258719e9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
d187d944-8e1d-5f00-9cfe-ee0947fdbf69 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 6.0 Crack Repairs (if applicable) | 6.2 - Crack Repair
a4d5816b-3fad-5410-99bb-f9b94b60ae5f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-021 Concrete Pavement Constructions | VIVA-FRP-021-009 - 175mm Pavement Pour 8 | 6.0 Crack Repairs (if applicable) | AUTHORITY HOLDPOINT
0833bec1-8f30-4e95-af1c-b828633f9280 |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings
ea377b33-ada0-4658-8a22-68c0e2494feb |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap
3e5ad364-0e82-5fb0-90e0-b47044e960e3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 1.0 General
4c7fe0bc-baf7-5c5d-87da-6259a12b23d2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
673a4de3-8554-5ba3-8dfc-0497456f11de |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
86d9682d-3694-5788-b7e7-560392b55bdf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 1.0 General | 1.2 - Determine lot size
86db62c7-e0ee-56ad-ac70-948099926d57 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 1.0 General | 1.3 - Permits
8eb48ec0-14a2-534b-8197-68d6c93a2e74 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete
e2ae321a-58a9-5554-906c-f4638084c2fa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
d556a33d-f7aa-53b5-a014-6fe166e4ea6c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
e49f61cd-c714-54e5-bcf7-45a2e841ea38 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
f177704a-59b1-5525-9e82-62e0813e21df |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
3e65047e-e856-5488-b7d5-4800ec63290d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f1a2b46e-1c93-5ab7-94f1-21ea9991de92 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork
d3bbc717-e6a9-52ee-a696-2b1bebffa3e1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
2126786f-a7db-5161-98ae-29cbcf923344 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
c8d16e38-645d-5dbe-b713-161e2139d0c6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
29ec2cfe-6aad-5587-b549-e13639abfef8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
1f12e141-e8cf-5be6-b36d-c601b45eb0bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
0d7cdf67-0603-5082-bd1d-02d988990032 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 4.0 Reinforcement
83724216-b652-5c81-bd6c-bc345cad8475 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
41f7bce3-e9b6-5bbe-89f2-f8a26501d626 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
42c37260-342a-5aa3-ae15-3a591a9e6af8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour
5e96022e-387e-54c4-8bcd-c816e3a92f22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
cde30143-c592-5474-a5f7-302bdf78ca1d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e95a037b-2e19-568a-89e5-bc693ada8acb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
7d0f31cb-7223-5fce-a5ce-2b59895d2ae4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
687eefab-329e-5ef5-8e97-0f9edad1d35c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
6db932a0-212e-5345-9c78-86b7abd9b87c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ccfb6a82-f779-5ace-aa98-6bda656090b9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
89c3aece-a279-5c42-a07a-2c964f2174a1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
2e932722-7b8d-58a0-a04c-bcfc80b17014 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
f202516e-c96a-5237-9f41-e7bfbdc25415 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b025a877-99dd-5d7e-b4f8-0627fa939fb4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion
ea13c725-b112-5d4f-b43f-3491bc97b58b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | 6.1 - As Built
c598f4e7-081f-546d-ac30-2729e1f9f892 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
5f4678d5-6265-5368-b9df-594cc17f07f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
b8441b2a-ca72-5c56-a3ea-7785a60164a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
9b3b329d-e684-5a58-8688-03c99bbb7fd2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
2c91050a-6c2c-5bc7-bf0d-02e86c0a82c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
cf49efa9-e847-5e45-be24-82233782347b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-004 - Cooling Water Tower Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
5e07385d-6bbd-48dd-96e7-ae1a45a3e1f6 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap
c35fa808-2672-564e-b778-f7eb2d4a03a6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 1.0 General
3469887f-c73f-5152-b29e-ca60af555dd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
60a6a6dc-0768-51e7-9135-e7dc09e6301b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
91f397d3-b24b-5942-bb2b-34659322601e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 1.0 General | 1.2 - Determine lot size
1ef728a0-9d9b-5b83-8904-e84874f54911 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 1.0 General | 1.3 - Permits
c0999bf7-28b8-5770-a2c2-43fbdbf0bde2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete
d01250db-e8ab-5644-bc6e-2c4069fd4bf3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
7c5518fe-b4ca-51d4-8b95-fb89ec298c5d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
676b68e5-0cc1-5a3b-ad03-5f9710b01057 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
f0098588-4d37-510f-9928-26cd28fb30e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
629de374-ee6a-5d38-87cf-2cf6a0678e2b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
8a74e828-67d6-53a4-a91e-cecc5c1e1445 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork
6072974a-1bdb-5e39-8d63-53aa039f4ea8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
7cc2c1ab-397d-552b-9581-a438d9d6ae07 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
cfeea4dc-3726-5f22-969a-12ea7561430d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
3c8e8cda-8470-5f51-a9c4-53537386b048 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
f773bc57-3fa3-55a1-a799-c128fe8eb161 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
f9ff6e40-57ab-594e-b957-c2e51d0de6c1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 4.0 Reinforcement
b410410f-aa18-55a7-9481-b8325f0ec4fb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
1348826d-1518-5ac1-8d8f-56df41c82c94 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
5453ea34-e806-54c7-ad44-fa5d40e3e980 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour
72ecad70-9042-598e-93ef-cbd6f423d412 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
5fe5167f-0b70-50d2-a0f2-5464f647f04b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0bdc725a-a0d6-5dce-bec1-77152aa06035 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
f58e1500-3e35-5f2c-8e75-1614adfe7c51 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
c86c3464-1720-5033-9094-eec79378160f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
e8d733c4-6dc4-596d-9d92-155956d518e3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
a1971e93-7ca7-59bd-ba36-ffc0facb46fa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
267aed8a-140e-5cc9-94bf-f7549d544d45 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
cf68710d-5901-5ff7-85e6-8a1dc42be58a |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d59f0c0e-f993-5ffd-8621-9f29a89990bb |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
07e6b88f-1776-5837-8b1a-e67a548afd8d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion
92625b36-4b3a-5846-82e3-22daa3a5a6f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | 6.1 - As Built
81fd969a-93e8-5def-b114-d1b3cb02972d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
03f87624-e2b3-5062-ba41-73782105c91f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
4dc5c2f2-bc62-55eb-bad3-2c325b2e16da |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
b19691d7-85e2-508e-b036-5ec31f581f62 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
8b5422ea-69f2-58e4-aeda-3035e610221f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
b57d4f60-66b7-54ea-b1e8-5aa5ffea71f7 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-005 - R5401/C5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
64148f6c-4363-4c28-aaf0-c45ecfd58045 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps
e6d5a6ca-8db1-551c-9a25-036303435588 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 1.0 General
b2d58bb8-f097-5af9-8e99-81afc6c2cec3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 1.0 General | 1.1 - Material Submission / Approval
7f5c34fd-877b-5b58-b900-e7de3af43201 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 1.0 General | AUTHORITY HOLDPOINT
1c85606c-953c-51d2-9df5-33e83e4106a1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 1.0 General | 1.2 - Determine lot size
c5f61186-bc21-5c71-9dc6-b87d659f4ed4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 1.0 General | 1.3 - Permits
ebd2a920-938b-56ca-85eb-a2ce57b7fe97 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete
cde44fc6-d989-5071-bb96-e2ddc970a478 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | 2.1 - Set out
d757d1a9-4b76-57f2-99f7-0e85ca49b403 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
7623cf09-e483-5922-92b0-e60d5d7eabe1 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
562b5f8f-3565-572c-9bec-e912d75d5449 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
78fad6b0-6b68-5d92-9666-fe219aacf176 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
50eb1169-c118-5308-aa4d-fabe2d0a4184 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork
7cdf1302-8ab2-58e3-96c9-22e50773f4e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork | 3.1 - Temporary works requirements
274707e0-00cb-5d06-bbdc-bd02b3729da1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork | 3.2 - Pile Penetration
680342f9-d8c8-5e34-ad73-d5353e0fae98 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork | AUTHORITY HOLDPOINT
3252f08b-c451-5cd0-8771-4914e77d8297 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
390862f9-7038-5a0a-aa1c-c0352392b339 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 3.0 Formwork | 3.4 - Concrete jointing
268be9a1-ee7f-5e2f-9110-21b9dfcee455 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 4.0 Reinforcement
cf0b2f36-7fd0-5a57-a867-5405d84b98d5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
aafb041b-bf44-545c-b56f-983a61b87102 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
9ec7c48c-caf4-5eab-b24b-9112e03232d7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour
03e9bef6-4653-595a-89e7-7205b837cb69 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
7ec12508-7b82-5c66-a7a3-cba66952c757 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e90725ae-a0ea-5383-a427-fb54cbfd73ac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.2 - Placement
8cb644a8-1f08-5606-94a0-14e49dafccf7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.3 - Slump Test
524f55ea-1c03-5c89-9060-1032dca0333e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
0ea1ce02-8b64-50f5-a9ab-44d32688c994 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
aa5ee04b-c9dc-5c39-8fc7-dbaccd41919a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
c423cd07-686e-5d02-8d0c-2a95424b68fd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
d9a4d5ca-70bb-5bab-a7ef-d11892090332 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
5d80343e-7083-58bb-bd33-4f57359f9d36 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
87ddc6c9-b456-5ee6-8d59-b1c5d6ff774a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion
078a53ac-212d-5f4c-a72f-c1dbd59d179a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | 6.1 - As Built
5ffb940e-38cf-513a-a3a2-497f651813ba |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
ab75ab64-87f3-512b-b28f-466f044f9a3b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | 6.2 - Concrete Test Results
4a14dd1d-a4c4-5489-8737-33dd7370db72 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | 6.3 - Concrete cracking approval
a3f5b30d-7da7-539e-8916-b7fa5403a69a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
f6a3b243-fd3e-5966-b5ab-22d2b3dc5980 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | 6.4 - Concrete cracking repair
7dece02a-9fbe-517b-b7df-43ad064076f4 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-006 - C5402/C5404 Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
aa5cdc4a-7c1c-4385-9e0e-8c2a00ba56c4 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1)
4da36fbd-4092-5149-8e8d-4b00cd22da13 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 1.0 General
f05f8700-d40c-5476-8385-e55678595081 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 1.0 General | 1.1 - Material Submission / Approval
1332f304-b724-5e60-9035-db1ec8999b76 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 1.0 General | AUTHORITY HOLDPOINT
426ef995-e887-5137-b314-f47fb5f4e854 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 1.0 General | 1.2 - Determine lot size
3a3b2c14-12aa-59b6-b416-5d0bdcd57d5e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 1.0 General | 1.3 - Permits
91760737-972c-5445-b8f7-2619bd6f2519 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete
cb80ad09-992e-553d-93e2-610ae159b853 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.1 - Set out
5ce84039-af51-5e4c-9ca4-372ce1b7fc23 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
91fe5e23-088b-5bcb-93ae-7bf0e39e8e57 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
2fbfa896-b046-59ef-8920-daa3f3218e4e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
fd521ded-3fc7-5756-9945-3de77d1be055 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
5980e210-5dbc-5440-b8aa-40158e9ece46 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork
ac495f42-a040-5725-aaae-246aeca1e3c2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork | 3.1 - Temporary works requirements
686e57ef-476e-536b-9947-e07b417ba1dc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork | 3.2 - Pile Penetration
3464f0b8-02e7-52ee-b327-bd8dfa7fba0d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork | AUTHORITY HOLDPOINT
23fe2e99-7ad8-5b7b-ada9-62f80be916e1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
de1c08e5-73a3-590a-b0c2-a85c517f2f8d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 3.0 Formwork | 3.4 - Concrete jointing
db4eb472-4cb7-569f-ba61-eb5b4fd630f0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 4.0 Reinforcement
5bd36392-c0ae-5485-aed6-7aad360d7f65 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
409b5f77-50e8-5f6d-9c5c-a37cbdd0e795 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ebd14fb5-6673-5152-9a9a-a59083ca156b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour
0d30f073-4bde-552b-a3a1-cdfac04a7c9b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
6781dc2a-4db9-5798-a9b4-8287ec9f48c3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
02197f40-6a94-5e99-af41-ac80a4a934e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.2 - Placement
3788d0e3-1e4d-54eb-9212-21e585376318 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.3 - Slump Test
741bf15f-5ee9-5e53-915c-47e4f3cc876b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
111b93c6-b2b0-5f5e-a8e8-e6a6a6ad8fb4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
6af2d5e9-61b1-54dc-94bf-6177a56c572d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
beb5065c-115e-5c31-9183-c546684ec897 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
6f30196a-0ccb-5fcb-b234-6e86809a33b1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d6943e20-ae7e-576c-8a86-9613ef15e0c8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d138c602-44ae-52d0-b69d-9b2153993dc6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion
0bc595f0-73c0-58e6-adae-33037e71b62b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | 6.1 - As Built
db4ff0df-5084-55b0-9810-eb27705868cd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
fdb504e1-c1c1-5ea0-82e6-3d2201b33237 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | 6.2 - Concrete Test Results
00a6d458-b09b-5e21-afd5-c004f8ec9a4e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | 6.3 - Concrete cracking approval
4bd193aa-eb48-5945-979d-2045a3bd8fc7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
97084846-5395-58db-ae00-af69d0f6c58b |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | 6.4 - Concrete cracking repair
a4945833-7aa6-5ce0-b81a-64de72d9c4c7 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-007 - PAU01 Pile Cap - Excluding F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
8f698c71-6a22-48c8-b70b-028a54a8e8df |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1)
c7054fd6-5360-53dc-bc4d-6125c06cbb52 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 1.0 General
ff880e4b-2183-57c5-b07d-42fd95e9884b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 1.0 General | 1.1 - Material Submission / Approval
313fa988-d8d5-5f58-b3bb-ef40ddbcdad2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 1.0 General | AUTHORITY HOLDPOINT
2f37f891-6e6d-5932-8bd9-d0442e98d037 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 1.0 General | 1.2 - Determine lot size
1c8785e0-5cb4-580b-8956-62d04d8d81af |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 1.0 General | 1.3 - Permits
3e64a03c-0505-5a2e-b43c-d483ca4f2a5c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete
d0304ca4-a0ed-5993-800f-83531db891ab |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | 2.1 - Set out
1e66e38d-315e-5721-a647-8c081f871077 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
73c6b89e-821a-536a-9a7e-dcb8c258e15c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
db350648-109f-507b-a627-477dc37d7c29 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
96efdc1c-f701-5e9a-9810-2796138a3e71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
de8e5ef1-789b-560a-b61f-cbf83f638e00 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork
66599148-9e6c-5fff-b31f-734eb87dfbd3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork | 3.1 - Temporary works requirements
db92e141-b045-5ffa-ba05-a79b18c6731c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork | 3.2 - Pile Penetration
e30360ff-da18-560e-8493-048a41514231 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork | AUTHORITY HOLDPOINT
bcc1507a-3206-51b4-93b2-45e163c94b02 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
12178113-71fb-5fc6-a0c4-9653561d38f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 3.0 Formwork | 3.4 - Concrete jointing
eace65ae-1258-566c-b727-e73c6139c952 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 4.0 Reinforcement
e2916727-8a85-5f1f-8a9e-082393b22b11 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
97da623c-8e51-5076-a0f1-4d56f6d2efd6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
26e340f7-30ca-5e05-afab-3840431ff226 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour
fc06f4e6-6b39-569d-8d35-901c261d14c7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
1ada16ce-fb35-58c7-a150-332bb9bdb76f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
736832e7-dec8-5d29-9372-5482fd572f60 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.2 - Placement
8d46ed52-eaf6-54c6-8850-f6a55e1df296 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.3 - Slump Test
f0f7731d-88e8-53f4-841b-6e35d484ba78 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
e769bb60-f73d-567d-83d4-a3900c3fe0bb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
e2b82b9a-22c5-5cfc-98d4-a0e6f8652416 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
3ceff44d-adca-5384-938c-cebfb0a4e8ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
e1ce2143-c499-53cf-8641-8c1683b0fac1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d2408d46-5867-5114-9a56-9ba51ea02be8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
33df8d45-793b-5c2f-a257-206db05fd56d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion
f2d45d25-d5fc-559a-889b-ee7678e671b2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | 6.1 - As Built
ed6e9c22-f5f8-5867-8973-b97ef8cb9da2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | AUTHORITY HOLDPOINT
d41a0513-3bbc-5465-926f-f76d2dcf484a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | 6.2 - Concrete Test Results
01ac3e2c-cb0f-5037-9352-7c45241aea17 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | 6.3 - Concrete cracking approval
95014f43-0fac-5aec-954e-0d8534c1790b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | AUTHORITY HOLDPOINT
8637b325-aff0-522c-b318-fbc9c980ffa1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | 6.4 - Concrete cracking repair
35296423-1d09-5c8e-902b-3740e3544e15 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-008 - PAU02 Grid line B Pile Cap - Excluding F1(B1) | 6.0 Completion | AUTHORITY HOLDPOINT
3aa557e9-474f-4117-addb-6b8657449d92 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap
859c087b-034b-5f91-bd8b-6539e754f798 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 1.0 General
6d4e84d6-3a5f-5567-b939-ae4bccb56b01 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
94a63b36-506f-5aba-b140-77ab9f319391 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
b4783fdf-c067-55dc-9230-b20e4b872596 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 1.0 General | 1.2 - Determine lot size
e04e690c-6e24-5fa9-98a4-4fd99d24a6bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 1.0 General | 1.3 - Permits
f9216251-93fc-522b-a126-636a15985b12 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete
26c2ce77-d019-5b38-89fe-0ebc5fdba7f5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
0d2db4e5-7aed-5751-97be-1534b6f48a90 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
6a3f716e-9e7c-5fda-ae8a-8f273ef1c7f2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
a405bc00-3b5d-5234-bab7-06b2150b5525 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
21c65e76-b135-5aa7-8320-26075f9ef827 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
03a56f2b-6d59-524e-ab9d-00ef7fdb5efe |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork
3a913398-86be-5231-9bdd-5dded9e9cf4c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
a3320253-fdb8-57fc-85a7-fb7ac2aa52f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
68f0550a-96f5-5d89-b42c-6b0d7c0eb90f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
1a1c3948-4b8d-55ea-b4e0-8f492dda5cf7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
7d16528e-5875-598c-ae7b-8e5303d730e7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
f61923e4-8389-5de0-977f-72b67e0f3221 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 4.0 Reinforcement
2c6c4931-f2fa-5cda-a63f-78fa2f5c883f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
4d11dd94-131f-584a-8ebc-6376511eedd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
6beaa1a1-5bf6-5e42-8e52-40ce2ab96e94 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour
475ed137-42d5-5136-a8c5-ff3025f642f6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
b84fc9bd-eefb-5d7a-b050-b1d5bfbd1c93 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
7df8d0bc-19b0-543f-a13d-750a183f24cb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
117a047c-e106-5910-9f73-6a8bbcce7b5c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
b6648202-7fd6-5705-b9a9-7de6d6cf0850 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
660a5d34-ddc6-5a80-b82c-35b0dc632dbf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
0f4ec5e1-e720-5e67-9f16-3e055192537a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
4ecf762a-dfc1-548a-908b-9aefc05838ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
db519914-46cc-5828-be75-253f25b0c57f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
c619aeca-89f9-5996-84d4-4bb542e393f3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e40090cf-03ad-5133-9de9-032a4a968f30 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion
fd6bdb74-90a7-53ad-8b8d-cf3ca1093b3e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | 6.1 - As Built
76a6c349-820e-508e-bc36-2732c5719a18 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
4777c7b2-b000-544a-a895-8bea1e52e550 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
0b2dc4f7-7560-5cbf-808c-77ed89801172 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
c0e0e49d-c90b-5e73-9a95-ea60f9e9d892 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
3e5ff4f9-942a-55d7-acd1-8b66eb0950ef |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
299ee484-f06b-5b31-aa0e-71d2c401594e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-009 - PAR01 2A & 2B Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
1310c043-f846-4304-b0b6-5d67318b6f83 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap
a6de315f-e205-5832-b298-84fbac7d959c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 1.0 General
8e65fd82-aa33-5ce6-b9d4-e006c57c71e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
e3011dc3-bfe5-5a8d-881a-deb14fdf7656 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
47989feb-a723-5c54-9a42-bbeabb937ef3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 1.0 General | 1.2 - Determine lot size
19b5a943-4ede-5e90-ab11-93f16dbb759c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 1.0 General | 1.3 - Permits
170aa1e2-95f0-5848-92cc-c302040b4201 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete
817d0fe6-9ccb-53e1-ac6b-d3270692c9aa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
a4b6f9cb-0a20-58c5-afbe-93cc42a02890 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
468bdcc0-1a62-5784-a27b-4e7845c5e337 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
e1f1483d-bb6e-5e26-a0b2-d32ca679c9c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
07fafe1e-2378-5b4e-8635-6b968ffefed3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
421472ef-420f-589c-8e84-e3feb4c3f19f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork
a13415d3-0fc0-5b36-8d82-cf16bbf2e267 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
02548d17-4de9-5892-ae31-dba1e79b12a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
df984c53-b873-5680-9cac-d5213b442bed |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
a56479b4-a830-5b1d-a184-93765f1a7194 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
82e463c1-c8bd-587f-8cd5-aabf9b8779f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
3bc53c30-f80e-5182-bff2-a6766f5a1e82 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 4.0 Reinforcement
a4f70a0c-9864-5a27-b658-8aaac4a98b3f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
b9a7c4ea-b0fa-5382-8723-8bc58e0f63b3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
3ac60703-81e0-50cf-bb05-b0f270bb60e3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour
1f7abc07-c705-508d-bfaa-a408e96f5812 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
021ea47e-b54f-5f66-acc9-b12a127e1657 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
566a904f-071d-5dd2-bd2f-414bc7a84722 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
63fda753-0d74-5846-8298-55829efd692e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
f69a6c21-3d14-56e0-bf27-1bbd254f5c94 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
ad6d35f2-14be-52fe-9300-787fb7f874be |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
556d84e2-2173-5b3f-b05c-dd02fa7dab22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d3ba4dd6-4242-5e06-bf26-a0f79feefc35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
d412dcf9-9be3-524c-8845-4fe550c9ead5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9ffbb94e-4552-5444-9fe2-74e6220d1d5b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b899944c-aed1-5ba9-b192-d9960fc787c7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion
980e39b8-ef7f-521d-8b45-753824a19e2c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | 6.1 - As Built
feb22966-4fb1-5719-ba02-9430daaa9914 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
83dacedd-ee41-594c-ae51-76417a88c1f3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
883d5c20-d513-5b75-ac31-2f28ce6aa22d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
dca61cbc-5b69-5568-80fe-5d166a0a480b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
fc4de22e-4db8-56c5-b0a3-a2ede9345205 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
2a8bdf24-aa03-5504-b09c-3b552cc0d2a1 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-010 - PAR02 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
ab729075-081d-4c48-b555-024ca0e58232 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02
99b1764e-9138-5095-8ee0-5be4c4feb65a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 1.0 General
130e8f96-1ffc-5e6a-b6f2-ee35e426fafd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 1.0 General | 1.1 - Material Submission / Approval
0c22971e-77fb-591e-99b5-198304d73754 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 1.0 General | AUTHORITY HOLDPOINT
0b7abbd6-445b-5c2f-a56e-ba3f6c24af57 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 1.0 General | 1.2 - Determine lot size
ba3a71ba-1051-5a7b-a020-be6ab2505f62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 1.0 General | 1.3 - Permits
66026754-16d1-5522-b62b-b3423cdbd183 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete
f64fb19a-203f-5208-ba43-6ed4137f61ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
0f03b060-c8a0-5d1a-8629-8f8eca2fb198 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
8f8fb0cf-9593-5882-b0bf-ae10423076eb |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
71ef0d17-6e11-5869-9c8e-ca477b7e82c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
a5a326a5-f141-5f0a-9c64-a8eb9a2d53d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
b1e3f85e-8e8c-5a1f-8bf0-cd2a13b5610b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork
16c560c5-f81b-552a-882b-ae861a251683 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork | 3.1 - Temporary works requirements
629adaf5-5bc9-53c7-b31f-49f8242f4a8c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork | 3.2 - Pile Penetration
ccdc02f5-380b-53bb-9312-65f98fae920d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork | AUTHORITY HOLDPOINT
3452a41d-5c70-5450-a3c7-c7c97f87d9ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
a5858be2-0579-5a3f-b969-3486651ded4f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 3.0 Formwork | 3.4 - Concrete jointing
b7b00412-ddb9-5aeb-928d-ef353c9d3f4a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 4.0 Reinforcement
4e625510-0f28-5b0a-a16d-9e311a4d3f33 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ca3aa224-45e6-582d-aed6-346bee67bb08 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
3c489fb8-9cd2-5aaf-a703-86eb6b5d941c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour
5ba823b1-2669-51de-ad38-8b1a59f8824a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
bd73974f-764c-52a5-8742-9555d0d5307b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f5455ee8-dd5b-5369-afc9-388c95bff5b0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.2 - Placement
22166be8-2c14-5924-bedc-badbe41417c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
0cf5fceb-8eb2-5fe8-8270-7404e4149364 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
cddbaf54-b0ff-5943-95e8-a25dd221927f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
c8b6da38-571e-569c-b8d7-bf2c71cfdfa9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
492049eb-12cf-5e75-a15f-e12fac193b7e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
1a925670-fd87-5cad-b341-4887234cd814 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
ee96bc3c-5f5e-51e3-a4e0-847b192d9c18 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
11daa66e-3ec3-5511-af5f-c8372353ebb2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion
50a3eac8-53f9-5a50-ad93-5ca92ed61d50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | 6.1 - As Built
ffd12ab3-0a64-5a80-93fb-f01dcccb6c5b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | AUTHORITY HOLDPOINT
dd0b1fab-d70c-54d4-945a-a24a45cd3505 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | 6.2 - Concrete Test Results
872b5da9-4b8a-5fe5-806d-73c7d8086d81 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | 6.3 - Concrete cracking approval
8e2befe6-b9b2-52fb-a049-6d934f96fa3e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | AUTHORITY HOLDPOINT
902ea72e-3db5-5415-a112-e5cf77428508 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | 6.4 - Concrete cracking repair
cb238f8a-fbfa-5480-a416-35c24da961e2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-011 - BP01/02 | 6.0 Completion | AUTHORITY HOLDPOINT
e02fb7da-1ee3-48ed-9d29-73b46a4a5c3f |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002
59dc073d-62c5-5cc6-bdcc-4530778920c3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 1.0 General
cf61ece3-f2b2-50ed-aba8-cb69fa46c6c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 1.0 General | 1.1 - Material Submission / Approval
a4c7b213-7005-505c-9f9b-f0328dda1d60 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 1.0 General | AUTHORITY HOLDPOINT
effec4f9-db36-59ff-bbcc-088d0eb19211 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 1.0 General | 1.2 - Determine lot size
2100d96d-a09d-59cd-85f6-4ff534517d9b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 1.0 General | 1.3 - Permits
da7cf783-6450-513a-8e00-8c3cd2e6b33c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete
df45503a-a756-5cec-834e-8984de8f00a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
65e7a711-c6aa-5992-88a5-9b49ffd9b332 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
adf00220-504c-5d2c-b907-ec0d78ea3f28 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
dbb937ae-19e2-574d-90fb-ea36c099801a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
df1ed3af-451d-52c9-b129-8acfc63e8399 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
e07eddc0-d484-53c7-8207-f378bb14dbd7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork
969adbff-c6cb-5af0-a7d0-793d6ce92066 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork | 3.1 - Temporary works requirements
a1296e9e-456b-5b12-82bb-b5b58828db25 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork | 3.2 - Pile Penetration
072165ec-3006-5fb8-97c7-a70885b76a04 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork | AUTHORITY HOLDPOINT
801b1f81-4a0b-59d2-bc32-3de8d84859d9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
98eb3f0d-28ac-5919-aa3f-d737591ef153 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 3.0 Formwork | 3.4 - Concrete jointing
d6848e77-35f7-5c5e-b7c0-af77729b7c38 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 4.0 Reinforcement
e44876e0-c4aa-5aa9-9386-316511d501dd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7d4ff39d-ad41-51d1-ab95-a852a2c47c18 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
887a1d69-cd1b-552a-ad2a-c3df13f3e7f0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour
b07af15b-32a9-57dd-a5c0-4ab637baf6bf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
f489f0ab-7350-5e7c-a724-7064c9a422ad |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5468f9cc-3341-527e-bb20-ae781eadf4ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.2 - Placement
23be350b-5ff0-5d0c-8139-541b76035725 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
93178b34-d6c7-5d5a-ab72-7e5e623c7f61 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
d99cd297-b132-54f7-9dc0-9eeeea6cab79 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
cc920b70-8ded-5261-b1f6-184f2c5fcca3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
1da19bb4-97bd-5fa2-87b8-23bcb5e96e3c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
915be9d9-67f6-52cf-9b72-6a7906b51ad6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
abe8ba8b-e4da-5083-8b50-972d12ddde03 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
80e1f301-16fa-5a40-bbf4-8fcb1bd02224 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion
3796c618-b4d5-5435-982e-02c27aad1a7c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | 6.1 - As Built
8b758bc5-022a-5d59-be1f-80b55b72fd28 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | AUTHORITY HOLDPOINT
267e557d-e4b0-5368-b680-3b1a46520edb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | 6.2 - Concrete Test Results
7e0738c7-11ba-5c8a-80af-0b033195d910 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | 6.3 - Concrete cracking approval
95ac4008-f3e4-5f03-83b1-c09f7f9ca32f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | AUTHORITY HOLDPOINT
c0bddf76-036b-5c9d-92a5-62299a8309c1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | 6.4 - Concrete cracking repair
dc1cf1de-0a0b-5134-a2f9-59444dd1d981 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | AUTHORITY HOLDPOINT
2ed2cc29-52bf-4b67-a2e6-f7291879fb9e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | 6.5 - Leak Testing
e2f1ad63-3aa8-5a90-b070-ab012ecc164c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-012 - 101-MH-001, 101-MH-002 | 6.0 Completion | AUTHORITY HOLDPOINT
9e6e8724-b8dc-45c0-860a-af066613e858 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006
356adb32-6ceb-5166-970d-af67b8eb0aa1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 1.0 General
5c91f8e3-c32e-53d1-a34b-1239cf958f51 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 1.0 General | 1.1 - Material Submission / Approval
ee837263-9566-5320-a27a-c9aa693842c5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 1.0 General | AUTHORITY HOLDPOINT
fe808c86-6b36-5262-8ecf-d0dcc28e40a3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 1.0 General | 1.2 - Determine lot size
e8c57af7-a37f-5178-aa79-de76b40f0509 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 1.0 General | 1.3 - Permits
ff62ea63-ec0b-517b-b1d8-3dbc0e4849b1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete
44d1fc9b-aea7-5cb5-b26e-5af7a16f45c7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
3a4ac67d-eca0-55a3-995e-e41f234bdd26 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
34be0a6a-fb7b-5ec9-89c9-3b93e98643d4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
6c0583f5-99a5-524d-86e6-03b16f8b6e53 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
64e0bf03-108f-597b-934c-b996513c165e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
bfe4ad66-fa5a-5a34-9a50-06c93e95ebab |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork
1912b986-d690-5554-afb9-85826a91ca4a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork | 3.1 - Temporary works requirements
de8984cb-9d41-5cf0-9f9b-ab0ed45e4271 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork | 3.2 - Pile Penetration
7b72f6bf-3a12-5110-bb9a-9746e1457efd |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork | AUTHORITY HOLDPOINT
75321fb6-537e-5ff9-9c89-d681d681431b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
cbcd29a9-e644-5427-a5c8-a3c5dd16b18f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 3.0 Formwork | 3.4 - Concrete jointing
cef06d50-7045-523a-88d0-c991fca3f692 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 4.0 Reinforcement
abcc3063-111b-5515-b9c9-387aca31eb4a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
31bbe9f8-0e6d-54b8-8aa4-a7294aa56eca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ed556ab0-cf8c-5a5c-bd1b-a01207bc62ae |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour
2ff55be1-5900-59d3-83b2-5d220fddb6d4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
c7a27218-725a-5e08-be44-e0119eedaea0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f987643a-f40d-526f-a1d3-fdc3ad08698a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.2 - Placement
e5e1748a-0ee2-505b-b707-de1837de65a1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
c642ca0f-0a55-5b13-8ea8-86ff7a445ca7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b4fc1cee-5f9f-525d-8620-7d9db6fbe018 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
f5d8a1d5-b4ab-5caf-beda-ea9e0b0ea6f6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
b17da6d6-6ec3-596f-961c-a42788131441 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
22badd8e-1ad2-587a-9293-5e5ad4eae6a8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
49ae374f-30da-56d0-a162-842fbb71d6db |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b088a43b-3582-54f7-8d93-2e36e262450e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion
49933350-49ae-52b3-9d20-d10fc7bdcb8e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | 6.1 - As Built
fdc171fe-7031-50d8-9e23-cc32641aab7c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | AUTHORITY HOLDPOINT
0d9d5d9d-887a-5b98-b9af-467c3de6a07e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | 6.2 - Concrete Test Results
24bf3c9d-3fc6-523a-bbca-9194a3cb7de0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | 6.3 - Concrete cracking approval
b76f6af0-62e6-54f9-8c45-f7d518dc1cde |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | AUTHORITY HOLDPOINT
4976478d-42d8-5848-a0d1-8f635463fa50 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | 6.4 - Concrete cracking repair
cb2feeb0-849b-56aa-a79d-daf83ad86a6c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | AUTHORITY HOLDPOINT
9d5402e0-0818-4abd-88ec-1da46e058b9b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | 6.5 - Leak Testing
e16931cc-069e-59bf-85de-f709a9b053ed |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-013 - 101-CB-005, 101-CB-006 | 6.0 Completion | AUTHORITY HOLDPOINT
19ee5a98-30cc-4297-829e-44c799b382f7 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps
f72fa3f2-f2ca-5aa7-8d6e-36658b6ff9a1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 1.0 General
a344af77-821c-5b50-a415-2597be010ead |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 1.0 General | 1.1 - Material Submission / Approval
4a8f9cc4-06f1-5362-9d39-c577415225b5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 1.0 General | AUTHORITY HOLDPOINT
6ccee2d8-e8f3-5141-89a0-44660081a6f7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 1.0 General | 1.2 - Determine lot size
34bac1c7-23f0-5da5-82fc-4bdcf5ce9325 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 1.0 General | 1.3 - Permits
e1e0a37c-8add-5f30-8a17-4915afd28028 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete
f5e0d733-fa6e-5d88-9481-7042166d0a0a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | 2.1 - Set out
66561d12-9d4e-5a4e-8e5c-0cf055ce2cac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
8ae6ef02-f4dd-5133-a81e-74cf9a8eb823 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
39638834-1508-50c5-a8c9-540b015b7a22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
670f5d2a-8484-56d8-9e03-5f514610084c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
2ae2acc4-dc3f-5868-9818-3fe9cabbf6d9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork
9d1f87ac-80aa-5ff5-84e6-bd4dc45e1be6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork | 3.1 - Temporary works requirements
7185f7ee-57d9-5739-a324-b22185c35241 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork | 3.2 - Pile Penetration
481be7cb-1615-564f-8ea9-952400ac779c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork | AUTHORITY HOLDPOINT
6390963c-aa98-5ee3-8ae8-907795faabd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
3b40c1e2-cba6-51da-acaa-f5d581bab622 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 3.0 Formwork | 3.4 - Concrete jointing
d9914677-4015-5d9d-abe0-9d2b151a61f5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 4.0 Reinforcement
943b980d-b78e-576e-ae6d-f32ea83cc66e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a2b4c34e-afe4-5db6-a10e-9c857f2c45d4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
cb839e81-150a-5415-bd88-9fa8a43ad4fd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour
d8766ee4-9d68-5661-8b40-d71701a2f929 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
cbc2c3f5-6890-56fb-8f42-e545c19f6b97 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
711021ae-80e7-5152-bb95-ec186eece40f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.2 - Placement
95a9e076-5569-5ce0-810d-c9762d1394a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.3 - Slump Test
db6d8cfd-53d1-596c-aec0-e8dfdab488ef |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
015c55fd-a082-5396-809e-6027fafd44c2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
0a6f4c21-e338-5c83-ad37-db26b7af4ec2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
13917fda-555b-5a73-b85e-70ab0c85cbfb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
ca48574a-c579-5f7b-9045-378311d2dbbf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
1858eea6-97f2-593c-a5b5-4baaae475f91 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
ad87cac4-6ae8-5755-a53a-c939f9abe4c4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion
52aa9b0d-944e-5886-b352-3bf35fdb4f59 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | 6.1 - As Built
b7ae695c-9b31-54fe-84f8-ae042c1736e8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
9064683c-2b0b-5fcf-a71c-eb726cd41003 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | 6.2 - Concrete Test Results
e6ec9a10-c588-5737-a55a-190377b68a2a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | 6.3 - Concrete cracking approval
48a95b22-bf44-5904-88cf-9b86048fdf7c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
020e409e-6a80-5dc2-9f1f-d52d9b506bbd |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | 6.4 - Concrete cracking repair
472da952-074b-5be2-be5b-451000fdd98e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-014 - CWT Stair Case Pile Caps | 6.0 Completion | AUTHORITY HOLDPOINT
d3d86e9b-d274-47a8-b631-fd4a0536c977 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1)
1a5208da-bfb5-527c-9d20-0575364eaf8e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 1.0 General
737cb4e9-89f9-5522-9b2a-dd76061eb023 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 1.0 General | 1.1 - Material Submission / Approval
db05fb7c-fdfe-5398-abb3-104b99eb6f9c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 1.0 General | AUTHORITY HOLDPOINT
3da41f6a-eb8c-581c-abfd-8868bd73d0e4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 1.0 General | 1.2 - Determine lot size
a1d40574-e86c-575e-b0a7-0d4595c9d243 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 1.0 General | 1.3 - Permits
d0190237-de30-55cb-97b4-47688c1a322c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete
f06ea4b8-397b-5035-b5a1-d1c2c06eacc6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | 2.1 - Set out
91fe1b0c-f1ea-53d5-bac9-74d9c25866a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
2b4db672-6ab5-5bd4-9700-258f10c1132b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
3031e558-582d-55e3-a231-00cccef91823 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
be7b4f64-305e-5a68-a01d-c52bc1b3f5ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
13722edf-7581-5c52-b019-eed3c9008592 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork
d7976639-807f-590a-8048-bbd5dc2cb565 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork | 3.1 - Temporary works requirements
aab63162-7579-5fc4-b402-439d5b83cae8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork | 3.2 - Pile Penetration
3a0f3b2a-2029-5f7a-8a03-3d7d7115f20c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork | AUTHORITY HOLDPOINT
aa2a8275-8a79-57e8-b1e7-14320caccf0e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
5a05bf6e-fd3c-53fe-be28-069bea817fb6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 3.0 Formwork | 3.4 - Concrete jointing
07eb15da-94e3-5ba3-9563-ac5ad6d9adae |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 4.0 Reinforcement
d793fe0c-c91f-5158-b0dd-a20230ffedf6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
2c81bf2d-5d2c-5c94-b9ac-785ce4aa9bf2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
bb6234ed-8766-5e49-9c42-cf9625f2aec3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour
a844ca19-2a98-55ea-a59a-53eeedbd7660 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
e3c9b142-e6cb-565d-881b-1c3872685c4b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
1ae6c748-95ac-504a-b67f-b7b0de80f8d1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.2 - Placement
de69d013-2136-587f-b820-92a370f64bf2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.3 - Slump Test
8be83fd7-f5d3-5766-88d0-6fde489328bb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
ead163d4-5792-58de-8e40-ab14dcce3c08 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
3ebc5cd6-7c1e-5ef5-a165-a786e9f87bf1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
fd5a06c4-e5df-5bec-84df-cdcdadc58c2b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
1b64ba78-c495-5fc8-97b4-ca2ecfa7b36c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
36b79b48-e1cc-5dbc-9ba7-1fe2313da6f3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
33b1efdc-a6fc-5725-af27-502545c29f8d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion
a15dd386-6d6b-5c1d-a26b-5af36388bca6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | 6.1 - As Built
aaa20fb2-92c2-58d3-8e7e-cd0a32ea1648 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
d3e920f0-e2ea-5c09-88bc-e7c2e7a70dfc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | 6.2 - Concrete Test Results
1bf22aec-07f1-50b6-9f55-4573865a1d6c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | 6.3 - Concrete cracking approval
5d374199-2d4f-5d49-9e24-fcfe3322fd67 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
bdad7b1d-5000-5def-9fe4-2b1ed2723abe |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | 6.4 - Concrete cracking repair
e6cf8cfb-956d-5fb7-af30-a17a430a1ba2 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-015 - PAU02 Pile Cap GL A - Excluding F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
505fb58a-b5ea-4683-bdec-499e6ad48442 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B
cd5199ec-c459-5334-9fbd-017b47bd3bf1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 1.0 General
374de5aa-1f65-5411-af88-3b13d1f9a681 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 1.0 General | 1.1 - Material Submission / Approval
cb64552d-51fc-5bc2-aec7-774087a58a8e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 1.0 General | AUTHORITY HOLDPOINT
1bb93573-cd43-58de-9024-267f84c19ae6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 1.0 General | 1.2 - Determine lot size
f5bc6312-0ad5-547e-b2f1-c60ce3505810 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 1.0 General | 1.3 - Permits
a3d68053-cb5b-51a6-bd4d-a7dd7fe33618 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete
909142dc-66d3-53bf-afd3-09c4162df431 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | 2.1 - Set out
ca344e6d-83b2-56fd-8921-1ec85b953deb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
44a5749f-4d2c-5103-9968-ea62abc90b21 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
a44dc651-476f-5dfb-800c-31ed24337fb2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
0a514479-5703-531a-b511-42db4cfe2889 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
5a691f39-3fd6-50a2-961b-473dfe60f136 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork
755b72f8-5b91-5d33-a5cb-e4ebfe943fb8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork | 3.1 - Temporary works requirements
88887ab3-b779-5f1b-a9e8-ce3b543d91db |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork | 3.2 - Pile Penetration
73ac3142-7cf4-57f6-8cdf-ce9d99581214 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork | AUTHORITY HOLDPOINT
88a96ba9-c655-5c34-8d03-f48bf10a0277 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
2cb1c01a-dcf6-58f0-b2ed-66d17ce331ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 3.0 Formwork | 3.4 - Concrete jointing
5a573709-02e8-51af-8d86-e068750348b3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 4.0 Reinforcement
77627202-e849-5109-99f7-2a5ad6a36e01 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
eb922541-9e40-5533-9ba3-cf7cc087052f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
762d1a70-26f5-5095-8faf-800446ff3b62 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour
e5c8ff62-a5e4-5dcc-90af-eb5a7d6e2f6c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
a805cd0c-52b6-54d0-b8d4-19a40a4bf52b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
42fb7131-cde9-5fd2-9fc4-f77c83799232 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.2 - Placement
9c983abf-3590-5f31-b4ea-ef5248ac96bf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.3 - Slump Test
cee5ffaa-0247-56fe-b8b5-905d025c9c7c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
9fd4c5d4-169d-59a3-a7a7-2b7534cb1a85 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ec28f41d-4ac7-5c22-8fbd-d2cad0c05be9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d752523a-4259-5fb3-b5bc-708cb2b1fc44 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
26e0e990-fb00-553d-b2d3-0745bf9bab46 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d5a25ecc-bd5c-5f1c-8ac7-65505cf97e48 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0747f282-d667-5445-b3ad-d4650173ea83 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion
66df13e5-eb87-5d3f-b862-01b47c618f17 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | 6.1 - As Built
9a5030cc-29fc-5259-9841-27753bc101e5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | AUTHORITY HOLDPOINT
aff49c5f-f21e-5280-9333-ded6b96afcac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | 6.2 - Concrete Test Results
32b78de6-d90c-5d84-a1a7-889854122f1a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | 6.3 - Concrete cracking approval
d41c1b54-c719-564c-a76b-1c1162f9a6cb |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | AUTHORITY HOLDPOINT
b3869536-6047-59d4-b03a-f9de180c5324 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | 6.4 - Concrete cracking repair
f49763c3-3141-591a-bf15-80d09fb7798a |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | AUTHORITY HOLDPOINT
87bacce0-5f43-4043-9efa-3394915c4e4d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | 6.5 - Leak Testing
1fd0a8dd-9c5e-5a12-b059-6912597581eb |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-016 - PAU03 Pile Cap GL B | 6.0 Completion | AUTHORITY HOLDPOINT
04dc5819-9fdf-42d0-ba2a-5d17bc99d123 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab
9b34d4ff-044e-5131-a62c-7b0ea718c32f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 1.0 General
a5af2b9d-ba23-5a11-a2d9-5033d590443f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 1.0 General | 1.1 - Material Submission / Approval
a61948bf-5098-5e9b-bf3a-ce030680b301 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 1.0 General | AUTHORITY HOLDPOINT
950e255f-c211-5f3d-a4db-3a983adb73e0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 1.0 General | 1.2 - Determine lot size
e76ae068-105f-56bc-a62c-42cfbfe44cd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 1.0 General | 1.3 - Permits
7a97ba0a-5ed8-5d71-8094-57536152dfbc |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete
08646885-7655-57ea-909a-38df7a24cd01 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | 2.1 - Set out
9cdbbeee-16a3-5234-a72c-83578068a2a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
31426549-db49-5c45-b54d-de517f6fa6e4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
aa4873e0-ad95-5257-a251-445aa8afd683 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
8423286b-240a-5f4f-a396-3fe7da7a6910 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
ba9a5db6-e0a2-5ebf-8ac1-bfc9c4ca82ff |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork
666f9582-389d-5bca-9619-c17660d1d0c7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork | 3.1 - Temporary works requirements
cb0c294e-7600-51f9-8532-8c2c6a41b0db |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork | 3.2 - Pile Penetration
2ed929c7-d5c2-5e89-be01-335c04fe6984 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork | AUTHORITY HOLDPOINT
58f0e1cb-75c1-5259-9f80-5bfbbf9eab18 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
28749611-68fb-57b2-ae4b-66d7dbcb4d3f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 3.0 Formwork | 3.4 - Concrete jointing
0d798f87-23d7-5732-8a40-eb897650cfc7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 4.0 Reinforcement
b215e137-6a70-5033-aed9-668c4e28f985 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
5d48fe16-e023-5c4a-a43f-d46e218c0dbd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ce5a729a-7660-514b-8deb-dea12ab77221 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour
591f603d-c661-5ba5-ae69-0353f8c369d0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
8787bfbb-02da-5296-a1c9-d804e57d595e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d04d1016-8289-5167-84ee-e7ccca2a0606 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.2 - Placement
7410c296-a124-5a35-9e60-c9e498f18e3d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.3 - Slump Test
43701b35-6574-5300-8033-58c1fda2a2c8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b3156090-2375-58a5-8566-79643982573c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
97fd2592-9296-54c9-b1ce-f48a9f08ca00 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
00a5171a-ea3b-5397-b04f-cace9477c46b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
277fd2fe-7118-59f5-992d-19b52ce19077 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9fa3dbf3-c638-5f3e-a44a-4ec3b0dc0856 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b649728a-9a37-5e3d-9993-5cd29de5b1bb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion
22983f06-ff88-5dc2-8945-e435b14222d0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | 6.1 - As Built
fd4dc42a-dbef-5d38-9f58-da23adcfadd2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
517a2d4e-b6fe-5dda-a915-535224bd9798 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | 6.2 - Concrete Test Results
66d4f8cf-df90-591d-92ba-2fc9d302bf80 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | 6.3 - Concrete cracking approval
00c52e62-4d14-5bbc-8a63-c21c4b99bdc9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
bf41fc2e-996b-5645-803d-52fb42cc8a8c |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | 6.4 - Concrete cracking repair
ebd1921d-8a6f-596d-8f72-b536fe359ce9 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-017 - K5401A Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
1316b0e2-c479-437a-9323-145f8c29e1ce |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab
a8d269fe-604e-5e39-9b2e-435e649d1578 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 1.0 General
ec586188-3d5c-557a-acc2-4d5a48697be1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 1.0 General | 1.1 - Material Submission / Approval
73896407-eefa-576c-982b-aef26235f4db |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 1.0 General | AUTHORITY HOLDPOINT
e9a095f9-f8f0-5509-873d-e9c264ab4524 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 1.0 General | 1.2 - Determine lot size
4e65d503-1789-572d-877d-0fd771a950c2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 1.0 General | 1.3 - Permits
c380e5ce-f3d0-57b9-86e7-89343b7c0f5a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete
4dcf08b1-28ae-566d-a8eb-65b2015706fa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | 2.1 - Set out
113e6d4f-57b3-571d-b481-95736a6e77de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
651007f1-a5e0-5eff-a46c-3dea9f828dc3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
bbeeee13-04cd-5ea0-91b9-8fdcfbeb024b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
b8d5ddcf-8f6e-534a-8d91-e08843c495e9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
22f14db0-d745-567a-89c3-902df988185d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork
38e3f961-44b5-5b9b-8ffb-472bdff23f7c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork | 3.1 - Temporary works requirements
36aadcfc-8d32-574b-aecb-d88ef1f43655 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork | 3.2 - Pile Penetration
e7fa550a-185b-530f-b6d8-817b5b6fbf8d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork | AUTHORITY HOLDPOINT
09a6fe96-303a-59b1-a624-61e8633e0188 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
68647672-a8a9-59a8-9fd4-4465f3eb6f2b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 3.0 Formwork | 3.4 - Concrete jointing
4d5c6191-d805-5c75-a212-f35c0e213a04 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 4.0 Reinforcement
6828ee30-561f-5005-8a23-a193584589ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
bab42c50-c896-51ef-9ad3-1d74712d3748 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
04dad718-c2ac-5d90-b031-810e67ac2227 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour
1b0902b1-760f-5faf-bda2-0acb566588da |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
9b990d6e-163b-558b-965a-d392d2881e1c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
1552906b-ffca-5dec-872d-c1309985990c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.2 - Placement
d941424c-6291-5af4-be77-28d70a636d66 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.3 - Slump Test
eff7abe3-6e27-568d-9c47-36e3a49bbd62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
0afc50f0-8b8e-582f-8c47-c172a77a4604 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
65750ffb-a0d5-542a-bc85-3f38f5189b4f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
43a3993d-4975-5478-b5a0-94a126ac8ebc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
8392bdc9-e178-5780-b6f7-76fa54988400 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
cbaf5b79-82e0-508a-a533-99b221678d7f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
4ffb8139-d343-5351-9dab-f13c94878107 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion
32b1deee-f00d-5488-a3c7-d12154fea4df |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | 6.1 - As Built
c4f37193-a46c-56f5-83bf-6b9a4169ef9d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
916f4f78-122e-5d7f-be2f-e8bd64e126f9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | 6.2 - Concrete Test Results
458a9106-7647-5f16-81e7-c5e482b61d60 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | 6.3 - Concrete cracking approval
900d0600-eb33-520d-ade6-bdc758b9b55e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
95a653ca-dd6c-5019-845e-8c8e8876ac85 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | 6.4 - Concrete cracking repair
e6b92c76-8518-5a81-abe7-f3ff335b50ca |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-018 - K5401B Base Slab | 6.0 Completion | AUTHORITY HOLDPOINT
e885a3a8-fae5-4857-a3af-bf466ca44bdf |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1)
0ed1d132-aab4-5554-830e-b146241f98c3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General
c04a6b03-19ed-572e-b43f-7ac7b3a9b86c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.1 - Material Submission / Approval
51c571f8-605f-5511-b264-0ddbef38c924 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | AUTHORITY HOLDPOINT
7a988312-1e4a-5378-a161-3359da8f2ebc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.2 - Determine lot size
3d4b58ca-a7ad-5af8-9e52-96535eb2557a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.3 - Permits
2bf36d0c-6821-5a5f-838e-64677795895e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete
c82febb6-ec12-594b-9e64-668f52443df3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.1 - Set out
bd2dd812-4af1-56ac-9b2a-878c2b6d8508 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
ff534474-fedd-5008-a947-55165ea1d2ff |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
e0dc90b2-c2aa-58d2-a78d-7339aa51680c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
785c5e67-ee81-5631-aae1-995aaa441284 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
85af16bc-a14b-5341-9857-76bb66ffeb10 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork
93836ed4-e270-5cd0-b654-750301634174 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.1 - Temporary works requirements
b2973105-5769-59d9-9090-bf5786771aec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.2 - Pile Penetration
7658548d-1330-5c5f-a004-818b77e47a78 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | AUTHORITY HOLDPOINT
d28b0091-a6a9-5565-9e35-1c11d35b02d9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
5b8192e3-288e-5ccd-890b-8ee9518d0e44 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.4 - Concrete jointing
e8d6aabd-a478-58a3-a2f8-056063ffd69f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement
78f013e7-bd04-5b78-82d6-84706da22541 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
87a6efd5-5911-5f71-87db-c17832e1b0e9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
aa071814-c3f6-55c9-8fe2-d9d4ce7d60e5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour
8d28f620-71b0-5ee8-b9fd-3e9600fab783 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
be3e6034-bdce-5c1f-9c00-77f174882abf |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
a482cee0-c145-5fff-ae3d-182693dca159 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.2 - Placement
fd4cd326-ab95-5a03-9406-d83c638db6d1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.3 - Slump Test
0060eb7e-ad1d-5e62-b0c1-68d0667bbc16 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
6373a4a2-2f37-584c-8d9e-2d1c4439f5be |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
868ecd6b-7b14-5fe1-bf4e-e0ab6e545142 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
219a85b1-bd1a-5c81-929e-000d168b91d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
79bec1d0-dd78-5f70-a8e4-8479aded0433 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
987548db-bacc-5ebf-80c4-8736985531f8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d1a37c0c-864a-564c-9a7e-0f6787a8ef2d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion
910f73a0-77fb-5188-b82e-7b65ac54fec7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.1 - As Built
5c3ba373-cea3-5785-8d6e-013e53cb2e4b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
0df6b778-fea1-5a23-b536-fdd6b7814574 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.2 - Concrete Test Results
b857a244-53c4-55c0-b6c8-1b1f0b5d5aad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.3 - Concrete cracking approval
c5656895-4e3e-5f60-a622-888df2a50b5a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
3b6228eb-b8f6-5d15-a1d2-f08be4af0107 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.4 - Concrete cracking repair
38e2531c-1b79-5828-b97d-7efe9d724760 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-019 - PAU01 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
efa225ba-2814-4f75-a705-4ca2732bc522 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1)
43f78aab-2f9e-5c0c-8045-d988a0c57fa6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General
0e3232ba-1b29-5c63-92c6-e93fc990a24b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.1 - Material Submission / Approval
fc8a6fbb-6e4a-5faa-8385-f368156864c3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | AUTHORITY HOLDPOINT
bbfe6753-559e-546a-993e-d92f8a9293b3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.2 - Determine lot size
bf1720b4-84fe-57c4-8fd4-0d6df19a1898 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 1.0 General | 1.3 - Permits
8061e403-7afc-5424-a702-c3e27d354cee |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete
c275472c-0600-5cab-a3f5-136cab4fc650 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.1 - Set out
6f3e5e04-76f3-544d-a6c9-007a388f5b66 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
db7b32c7-88e0-59d7-891c-be047ed1de50 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
acf0bab4-a005-5d5c-8fe2-bd6000230e29 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
87aea83e-0637-560a-8261-226896a9043f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
4e96786e-acdf-5ae2-b60a-54ad93332441 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork
62044546-c9e3-52ce-acd6-3e94152f84fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.1 - Temporary works requirements
134c393b-365c-57bb-ab02-cf2624f1e9f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.2 - Pile Penetration
f69d19e2-9abb-55fb-b36c-760d65e9995b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | AUTHORITY HOLDPOINT
d2618621-59bc-5cc7-a1bc-9326696345ef |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
5d0f4c00-c7a6-5e6e-9240-3d36395b017b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 3.0 Formwork | 3.4 - Concrete jointing
a1eda50d-1d2f-580f-98ab-c7313c592580 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement
a2a73970-e95c-5008-8603-ac45b3b25316 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
927ce8d6-1324-5023-a085-87331d772d80 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
d6d738f2-ad42-59fa-8c0f-50309fd0911e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour
a948aef1-ac6d-5f3e-9281-a0e1af6d65a1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
a83a389c-5f7c-5155-8146-5466e3ca9fa5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
773c8a45-4045-50f0-8c79-29930c237118 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.2 - Placement
f76f7700-5358-524c-bb05-17bf1958458d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.3 - Slump Test
d2fd5d93-d8fd-5cbd-b4b6-a44364220aaa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
7f549543-fcc8-51f1-b611-b7cbd8120549 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
17af20db-8238-5c01-9907-7e4d8f72af80 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
a2436647-addf-590e-9dfb-542234cb4378 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
e3db91b9-0add-5564-b5d5-2b9bee47d8db |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
7ed69f77-bc83-5d16-a0cc-72eb0341b541 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
ea3251cf-c445-54c8-9f02-af33e92dbd28 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion
2f36a0d2-7c7d-50e5-8b69-c60242a986fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.1 - As Built
76900f51-8253-5f79-bfe2-7291fc08e1b3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
e46a9e07-e551-5baa-88d8-fdf0c2f34f5d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.2 - Concrete Test Results
c7c695c4-52bf-513f-a3fd-3b62cef72eda |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.3 - Concrete cracking approval
3a27ca6b-699c-5de3-a1f0-8bd224d4fc3e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
132dd311-7f2e-5632-aaba-051dc904175b |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | 6.4 - Concrete cracking repair
e41c9959-ffda-5b67-8277-e11cb7ab9ecf |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-020 - PAU02 Pile Cap - F1 (B1) & F1A (A1) | 6.0 Completion | AUTHORITY HOLDPOINT
e5bf8e08-9974-41da-8e42-9571e562d81e |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam
e45f36e9-6fb7-5b2a-a982-a06302ce1de7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 1.0 General
3e48ba0d-16f5-5868-8cd4-186346f51a1a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 1.0 General | 1.1 - Material Submission / Approval
8badc095-a077-5b7b-9f07-65a6ae16787e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 1.0 General | AUTHORITY HOLDPOINT
460349ba-9e24-597b-91d3-4c0ef7437ea1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 1.0 General | 1.2 - Determine lot size
2ef14897-8bef-5092-a939-b4602727626b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 1.0 General | 1.3 - Permits
281979ed-3cfd-504e-92ea-d862a8c71710 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete
91cae21b-8314-513f-9ed4-e1a110e5f442 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | 2.1 - Set out
4d45a176-5048-5e79-9060-812f1ef4bae6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
113c6be7-61bf-5650-bf5e-28c3089387ee |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
99e7c21d-4497-5694-9838-b58535b562f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
5e908496-d752-5bd9-8815-eba948d4b5f9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
35531d13-eb4b-56ae-a161-d0fc9dee9b23 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork
d070e2df-b334-5719-9663-34feb6c6516c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork | 3.1 - Temporary works requirements
ee0eb9e5-e566-5cee-95a4-f9048e09d414 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork | 3.2 - Pile Penetration
80a35b2b-e8b2-50bb-a5aa-4221548ced4c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork | AUTHORITY HOLDPOINT
49307dbe-da6a-5f25-a6b2-a08de2603152 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
24bb336a-f858-5c7e-a535-7b11baf00b58 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 3.0 Formwork | 3.4 - Concrete jointing
c487c96e-5a18-5393-b24a-d79dedf7ad05 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 4.0 Reinforcement
998288c5-b337-5ffa-8694-65a33b6704d6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
5a2bbdc0-bcba-5229-8165-ce8f02ea1bf0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
18b0ce99-7693-5b7a-961b-24b793575983 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour
c86fdbb1-78d9-50d9-9c29-7871107c2fc5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
92fcd581-6d15-5dca-a35d-6ab22bd0f004 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
2153b666-1f3c-554f-81ef-3516927a2cd7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.2 - Placement
f4102bda-564b-5f9f-8703-a20d4a4d8344 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.3 - Slump Test
a99ed57a-85a0-570c-8c9b-8a73c190fd45 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
8c5ced20-bec4-556e-8ac0-30238c05cac7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
4c2c6e05-2ae7-582e-85b7-a00eb8479563 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
753a5dd9-22fb-56e2-ab34-0359aee4fb9b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
2c4b7c09-532a-5363-aefd-be78c43216c1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
14859561-c278-5f28-b8fd-c4aca9cbd543 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
83df2176-4fb4-5596-b5b7-143383523f79 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion
28c4cf5b-e1b3-5a25-bd07-9b7d13ae4497 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | 6.1 - As Built
67a73a5c-3249-5f89-b0f4-4520e555b1a4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | AUTHORITY HOLDPOINT
d51168d1-6a57-5269-8ee2-005b1995442e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | 6.2 - Concrete Test Results
2267f201-080e-5863-816e-44f7be981d28 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | 6.3 - Concrete cracking approval
0d1721e1-528f-5efc-a284-ed9d302215e8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | AUTHORITY HOLDPOINT
2dc88c99-8269-5cfd-bd0a-dd76ae6df7db |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | 6.4 - Concrete cracking repair
b051ecd9-ef40-59bd-bb37-5848f2c65e28 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-021 - C5402/C5404 Tie Beam | 6.0 Completion | AUTHORITY HOLDPOINT
774f4138-174a-45c4-b723-ceaf24b87162 |  | work-in-progress | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A
6dfc2e66-e8fb-556e-98c4-10c2b502f6f0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 1.0 General
7520b8d5-e03e-56c9-8e77-0883eb0e4cc6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 1.0 General | 1.1 - Material Submission / Approval
278940e6-e887-58fe-9d24-cd6f855af4d2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 1.0 General | AUTHORITY HOLDPOINT
92ee6e5e-cefc-5847-be77-44fac3210edd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 1.0 General | 1.2 - Determine lot size
9de71455-c63f-5bce-8c22-452441445dd1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 1.0 General | 1.3 - Permits
870733c0-f196-5fc3-a7ac-b97813b91d25 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete
a7ebb5d2-e81e-5ad5-8239-96ff7d353133 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | 2.1 - Set out
591856c2-27f1-5134-96a8-a08c126e11f4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
f08845b2-dc8e-5055-9a0a-07a52ee9a786 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
9afb35cb-e560-577c-939a-c5be9e67f5e0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
b9ab2b34-cdaa-5458-ba0a-c6b32a3318b4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
2442d457-6f3e-5bea-88fc-a0827a81b181 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork
9185e94e-db32-50a5-8972-6ee5f607d009 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork | 3.1 - Temporary works requirements
63c8e345-3199-546b-8627-e0fcdce52b37 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork | 3.2 - Pile Penetration
f64a5152-7cc7-5fc8-b36d-d2d73b9c2cfc |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork | AUTHORITY HOLDPOINT
2744ca2b-6534-5d6b-970c-b8ad5b1f0fa8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
bbef9b3c-5618-5362-ae90-fd5d4139f52e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 3.0 Formwork | 3.4 - Concrete jointing
d82c8fa4-69b9-5178-833f-1f2e73aadbb6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 4.0 Reinforcement
88eebeed-344c-5d68-b83c-89bc4130b270 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
c67497cf-7d8f-5f35-aeac-59677da71793 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
42ab5ed7-9533-5ad8-a484-d808fd1f2c49 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour
05b466ca-282d-5576-94d9-633a8310dbb5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
c45d215e-7186-5975-a5e5-933c16d35c15 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
33f910dd-c975-522b-beb1-8e3f6ca698dc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.2 - Placement
6514ce44-1ce4-5da0-8c26-6794e3c15e9d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.3 - Slump Test
6afa1188-207f-58fd-bed9-8e90869ba37e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
45369bcc-cf4c-5547-9a45-212d230d7444 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
e6070dfd-1103-59aa-a7b9-e851cfe6d6fb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
de5cef36-7965-5264-bd71-23b56d452fa0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
12a55931-17e2-5d40-8bc5-53a24472b765 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
ff231fd1-ca56-55b4-9e72-d1b032abd30b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
4799a51a-9355-5fd9-bb85-3efd1f260121 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion
ef5390d5-a523-585d-b70c-d69961d28e08 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | 6.1 - As Built
52656752-5bc8-58c3-8be4-c3d2dcfe1c58 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
8c9c30fc-7a49-589e-a687-17227815568c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | 6.2 - Concrete Test Results
9dacb7da-42d1-5905-8ad2-b796af4db5bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | 6.3 - Concrete cracking approval
48ab9973-0ace-5df3-ae06-8e436618806b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
73ba9006-4ecb-5e02-a699-2bb77465ca8a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | 6.4 - Concrete cracking repair
c95f65b0-5935-5387-a265-72f19230d2f1 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-022 - PAR01 2A & 2B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
93f38ac8-311e-4319-b91a-919bc227cc7b |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A
19e71fa5-19cd-5d97-8a15-97f935117ed8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 1.0 General
7bfada26-3c58-516d-b2a6-eae05f0f422d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 1.0 General | 1.1 - Material Submission / Approval
4b28e956-515c-5066-8dd4-10b96d6fe76d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 1.0 General | AUTHORITY HOLDPOINT
9cd165ca-88de-51ee-97ff-6b224b6a2036 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 1.0 General | 1.2 - Determine lot size
b513eda2-b2b3-57bc-a640-fedbbde6e96e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 1.0 General | 1.3 - Permits
0e040e34-41d6-58ab-a561-a4a8cca21b18 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete
3fab8a54-8f8d-5f5d-b4ae-9ca151a4a916 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | 2.1 - Set out
6ad6bd45-10a8-5a1f-a1c0-7af915da813e |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
60705d8c-c0de-51a0-8952-96180da6e84d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
57f7f30e-dbcd-5d98-ad36-93327aaef27f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
35893caf-33c5-590c-9527-3717edbe4c76 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
e28b2721-f579-5b82-8cc7-377b2c2ca723 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork
bd01a03d-12d5-56a4-acaa-30136934e2a3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork | 3.1 - Temporary works requirements
6bf9732c-1081-503e-ba0b-603ab62e8bb4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork | 3.2 - Pile Penetration
305acb55-2bcc-5d29-b200-266b22401a52 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork | AUTHORITY HOLDPOINT
3563fcd3-3f46-587c-90f6-96074ba4a850 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
f0cbb3e3-6826-5e8b-9d71-03a9384fe529 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 3.0 Formwork | 3.4 - Concrete jointing
579f832a-a6b0-5d0b-b845-e1465ee006bd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 4.0 Reinforcement
c772b95f-7a4b-534a-9070-45c3d2030fd4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a89d37bf-b620-503b-8349-6afafd4eec13 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
67ba25e8-372a-5e48-8226-a1f702be5e79 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour
43fe231a-08c5-53ce-9292-ced4a2713cc4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
6609286b-9a15-576b-b9f6-f4a7423683c9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
56c22bce-292b-5f42-add9-567c8708b195 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.2 - Placement
18ecb697-a523-50a5-82bd-a359c643cc1d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.3 - Slump Test
9fc7bbf7-2b05-5d16-b7bc-8bab640df688 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
4e5415a3-8db0-58eb-a4f6-db060848fcb9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
23d8ef47-c313-5f34-b3b4-2b2a6baeba17 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
aa21b056-ab0a-59a0-81e4-bddf1edfabbc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
2333364f-5412-5e73-bd6d-3d579795bf4f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
212f9158-aae3-5a42-8da9-ad71e7cba1e6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c988d0b0-2401-5c4a-8a19-d7097b5dc138 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion
b897a190-c97e-5434-aab7-a8bc264921bb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | 6.1 - As Built
0de5ce86-7000-5c5b-b86d-7109047d0671 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
978caef1-7134-5fa8-b353-9a39e6a68627 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | 6.2 - Concrete Test Results
6847a487-04a3-5071-8101-ee0dd7405bd4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | 6.3 - Concrete cracking approval
ad6148fb-f304-516b-b369-cb67a53f85e6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
1aab7ac1-211d-5f13-8b54-6ffa88d66887 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | 6.4 - Concrete cracking repair
f2a59069-46d4-5ad8-985d-aa817e048546 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
9cc96204-86e2-4190-8ea6-f9360df30676 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | 6.5 - Leak Testing
3c61ef7d-ad53-5d7b-adb6-d8700ae828fe |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-023 - PAR02 1A & 1B PED1A | 6.0 Completion | AUTHORITY HOLDPOINT
1c71dd7a-113d-4d3e-b7d5-f364975eb98e |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation
f8f6d0c0-80ad-5b82-9b14-4c8c0fbe87cd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 1.0 General
51e2b98b-4795-5737-98dd-372b32ed754e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 1.0 General | 1.1 - Material Submission / Approval
8479a2e5-9604-5a83-bc39-923064dd8bd7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 1.0 General | AUTHORITY HOLDPOINT
f394eacd-991b-5e2c-8230-7a91ac831a85 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 1.0 General | 1.2 - Determine lot size
b615f59c-b417-57ed-b6f3-4af5e38cf6f8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 1.0 General | 1.3 - Permits
5338e3cc-935b-5111-bc11-b112bbd4d070 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete
0a0dcaa8-8001-5a01-9bde-20984cf21a92 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | 2.1 - Set out
48c041e2-b666-5e77-87ed-d24846facae4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
b194af77-c73c-51ed-82ae-fbad0186c648 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
44385d66-87ab-5d02-abb2-1652a6c4e0c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
6cdb2dd3-0ff3-5a7e-8e9a-0958d05f3b19 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
31c6313d-f129-5c73-b670-c07d26660909 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork
fedfb2cd-6b03-5b68-ab75-68b471ea11b4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork | 3.1 - Temporary works requirements
c5230f6d-b480-5684-9015-2962ddf446ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork | 3.2 - Pile Penetration
602dbab3-0a1b-543b-9ef8-8b13c17844e3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork | AUTHORITY HOLDPOINT
0e95277e-8ae4-53b5-aeba-bed88ddf5492 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
326ff546-0bf1-5353-83cb-30f862bbc294 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 3.0 Formwork | 3.4 - Concrete jointing
d008c042-502d-53ac-a2e7-1f47a02bda61 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 4.0 Reinforcement
95d90b03-c4c7-5257-9860-170545873cd9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a1340184-502e-5c02-95a4-6c996d4add7a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
10d5280b-fbe1-5a13-a039-a193f5c401e2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour
137eabbe-4c78-5956-875e-99575d929c88 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
87d3ab98-0011-5e69-9426-e2aa3ffc6c0f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0a095259-579e-5b6a-b0d7-c804c10bae48 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.2 - Placement
de12a5b3-cab8-5640-89a5-e2f21bd5e5fa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.3 - Slump Test
a27b20e1-1ab0-5c3b-9549-f2286661349c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
e8a7d5a4-6bb4-56c5-a74a-7d19f1b79660 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
aa6cac4e-bb8f-58bf-be8a-40751fa1693f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
c5ee5dc8-e389-505f-9fe4-d5abe814a199 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
99b591c6-2d68-5d2c-b967-589d41a3561b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d4d90bb7-5789-5f1f-94cf-706b874b1416 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0d6cc4fc-a5ed-55b2-93e6-cc60fa992b8a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion
3f7bf911-e226-5d50-8516-a9a05e3d6dda |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | 6.1 - As Built
b13d77ab-ec1c-55e6-b7c9-aead47ca172c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
b93eb66a-c5c0-5e26-bc4c-3b1c0ff415d2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | 6.2 - Concrete Test Results
fcffbbb1-7819-549e-a634-bf878576eadf |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | 6.3 - Concrete cracking approval
de011bbb-d17b-5726-a645-2c16e6dc417e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
223a88ae-a74a-5557-bef9-c385c3ebcf58 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | 6.4 - Concrete cracking repair
90baa830-db8a-54fc-b2b1-150ff515a8f6 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
85884f33-d24f-4232-979a-f766fc98cb67 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | 6.5 - Leak Testing
f8e28b0f-2319-5255-bc2c-81cd3200862a |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-024 - R5402 / R5403 Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
41b9d250-eb67-47a4-bccc-f258c2602dea |  | pass | d0f997f6e23c8ebbc87417e85ddceefa4d66b68c2484a41f0d141665d94e428b | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation
d7446f4a-68e7-54a6-9501-ff61973fd2a2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 1.0 General
90560419-9e73-59a1-9520-e7fb9badbc19 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 1.0 General | 1.1 - Material Submission / Approval
cd0fb34f-3cff-5c20-8493-2c873891c88b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 1.0 General | AUTHORITY HOLDPOINT
1ab3b398-88ba-5abf-905b-2ef236683353 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 1.0 General | 1.2 - Determine lot size
ea1b4fd4-487c-5c1a-86de-72cc5a2e520c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 1.0 General | 1.3 - Permits
b4ac88aa-ebec-5798-bffa-c6f5bebf54c7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete
feb3183b-c5fe-546d-8835-eb09b99c74d6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | 2.1 - Set out
2683e750-6ea5-59b6-86d4-9a0f62d263c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1533eea4-1fa9-53cf-afd2-15d48f161f71 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
19dcf6db-1f2a-504a-a589-7d3253735025 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
84ea3faf-f292-5670-8333-05315af2860f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
7011d5fe-e169-5d8b-97a4-bd2cf658bc8e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork
9bfe7200-7995-5300-841f-f2449e99e5f9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork | 3.1 - Temporary works requirements
7b6496ac-5c34-5cd6-b7bd-c4fa9ee8d6de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork | 3.2 - Pile Penetration
d9827390-d961-59c9-94d3-469db6eabbd3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork | AUTHORITY HOLDPOINT
98047a25-7bb7-5e3b-ba3f-da49db271d40 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
19671d68-bb73-546f-b0c9-f3d48865c070 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 3.0 Formwork | 3.4 - Concrete jointing
708bb4b8-4fa4-5529-9994-d5481228e948 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 4.0 Reinforcement
36dcdd4c-7614-5db6-8185-131b96c5ebb3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
4cb0f257-ed0e-5207-8cfc-9a576b25bb50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
0465ba02-f583-5ca2-8b50-ccd739a86bd3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour
672dccde-e42d-5366-a002-3f15481164e4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
682dcdae-b699-5c96-b7f2-909dcec93a70 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5dea47d4-a7dd-5dab-a484-6d3d71e3ee7a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.2 - Placement
ed8f57c6-ca1d-5d9d-b1c2-b012b35add0e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.3 - Slump Test
b463e91c-6eaa-5972-ba61-4a4b3747d9d7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b3a9dc42-0268-5f03-b2c0-c1b410c916f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
5f2dad2f-fc46-5f31-9a8d-483eb70fc3b7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
64ed7398-8f4e-51fd-9c59-2578196ef389 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
fe199836-896f-585a-be38-7bc7d1e4453f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
fb73ce59-43cc-583e-9970-df65dc97336a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
778f97de-67ce-5bc0-9e30-c1f94687b32e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion
6d54a1c9-6d2f-52bd-8ad1-463e3d160042 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | 6.1 - As Built
4bc35813-3f6f-556a-916e-3551fd96c200 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
c19da8b3-3dc4-543a-a14f-26449eedc5dd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | 6.2 - Concrete Test Results
66cf7f70-53ab-5e3e-957c-3e319cf365f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | 6.3 - Concrete cracking approval
6d6bfa71-10fc-5355-b87a-76841a8d385c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
7466bf45-733d-5e25-aa42-cd8f21eff662 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | 6.4 - Concrete cracking repair
ce5dc7ce-19da-5e6a-96a9-b95f4b705dae |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-025 - PAU-03 F1A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
6c5ddb66-dd67-4581-840d-ac36ec53fdb3 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2
b29deaaa-1f79-569c-ac95-8f9c35875878 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 1.0 General
8d322491-8664-5e07-8a19-48564c973d08 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 1.0 General | 1.1 - Material Submission / Approval
8ed94932-0b08-5439-9bea-0bd66e08bfae |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 1.0 General | AUTHORITY HOLDPOINT
e29254b5-55e1-549a-81ce-a88ca02d9662 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 1.0 General | 1.2 - Determine lot size
b6dcb525-1623-59d9-8da0-38ffc4c6ee93 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 1.0 General | 1.3 - Permits
20b1743c-0170-54da-b90e-43732b6a22dd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete
909c836e-cd46-59c8-a56d-db3c7a249266 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
c476fc63-d0ac-54c4-912b-43b29167d693 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
eac0dbe3-2f40-50e5-ad05-43b67bdb41de |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
4d50ac67-dd2d-5ec7-985c-0bb3368ad43c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f83b840b-a798-556d-8e1b-f6bd538179df |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
cbb5800a-a77f-5b99-9ec2-505e632dde1b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork
25444b89-886b-50d1-88ef-71bf166946f6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork | 3.1 - Temporary works requirements
8e941245-fc82-537c-b612-8cb5b7cea918 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork | 3.2 - Pile Penetration
d950e827-c4b5-54dc-b6bf-7d58c128c3db |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork | AUTHORITY HOLDPOINT
a9a192ab-822a-5b98-8e4e-d8b3f5a987cc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
3ebef35a-3246-5eb4-b41b-a15dbe6328c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 3.0 Formwork | 3.4 - Concrete jointing
a2426349-291d-500a-922a-0a17f999725d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 4.0 Reinforcement
c5b936dd-de19-55f0-a7d9-93a70cfef78c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
e56333f1-7952-5727-b68d-54df360038ef |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
a38fc260-f118-5801-b436-26b35bc22606 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour
e415ee8a-82e6-5a39-96e6-fc0580cff577 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
b74ccdb2-9e7a-532a-b3db-c02ca765cd40 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b27db767-25a0-5572-b6b7-423ce44e8c85 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.2 - Placement
140ab1ce-c4e6-5ce6-8785-6fc9b0f25477 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
ce7d2ef3-74fa-58e3-b7c6-06677ebfe06a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
8a630def-136e-5814-b1c8-a0433b16874e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
df003519-ead6-5d8d-8cc6-02dd4bdb7079 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
e7d753f8-1f49-52bc-84f1-f163b5927a20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
8e917fe3-cc5c-5ebf-b96a-8315f51e81d4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
117267e5-9fa1-5947-a53a-5c6431419a50 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9331283b-3111-50c7-9620-6879c1e32480 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion
91f25fd2-9d75-5b96-806a-2a0de5a1e6ae |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | 6.1 - As Built
04d37090-ab29-5e2a-a554-86af915d2811 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | AUTHORITY HOLDPOINT
9fbc037a-4690-5229-ac9b-93b8269b06b8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | 6.2 - Concrete Test Results
76b13b0e-4a72-5a6f-9680-259720ca9e2a |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | 6.3 - Concrete cracking approval
a846995c-b7c2-5757-88f1-74fee81ccdc2 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | AUTHORITY HOLDPOINT
61ecd17b-c4fc-520a-91dc-6951f4b88164 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | 6.4 - Concrete cracking repair
005c2e8c-1bfc-5a23-9601-03c492e12d75 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | AUTHORITY HOLDPOINT
a341b2d4-994e-407d-ac12-586cb14ac408 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | 6.5 - Leak Testing
262ec7af-8088-5b57-aebf-997bef48ce54 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-026 - PAR-02 PED2 | 6.0 Completion | AUTHORITY HOLDPOINT
adfb2726-9652-4034-bc4d-03f6d7cc5d58 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls
ba9001f1-5bf8-5c0c-aee6-36a0a28595fb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 1.0 General
de38fc2d-fdcf-5d17-a0b0-1e061a904769 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 1.0 General | 1.1 - Material Submission / Approval
d9ea33c7-5553-50f9-a8ca-52d637cdc334 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 1.0 General | AUTHORITY HOLDPOINT
3d992065-9ef4-5653-a541-0b6ca143528a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 1.0 General | 1.2 - Determine lot size
1ae68d2a-7a57-550e-a131-7377b94a92cb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 1.0 General | 1.3 - Permits
4e83d460-27bb-5d3e-b7d5-494bf69259cd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete
9b262977-0096-500a-9c78-9d90946632d6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | 2.1 - Set out
a883df28-9c03-5a63-984a-57c11df36017 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
484f74e7-2aa0-5569-90ce-ec1130b56d07 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
eee64b04-7e01-5181-bf78-27f6278cc3b6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
d9c79037-0885-5f74-96ad-ba3c67e5bb1d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
6861fef0-3379-57f8-8516-00d00599f7f1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork
e5c830e8-5a7e-5421-8396-055f5783fccb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork | 3.1 - Temporary works requirements
d4ba1135-6963-5513-8ae5-68bf092012cb |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork | 3.2 - Pile Penetration
b4baeca3-8ffa-540e-8b23-3220e0a4e5b3 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork | AUTHORITY HOLDPOINT
d5baf0ad-e094-5e25-9d2a-aae8d8191346 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
6f10b728-ec0e-5dc9-9a37-efdaf0147068 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 3.0 Formwork | 3.4 - Concrete jointing
baba64ed-d60a-5c67-b55f-eb483239cfd9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 4.0 Reinforcement
a84b5c60-03bc-5688-9700-8731609c9f2d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
eb45a4b3-d58f-5f1b-a88f-04f459d53ec7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
c35a1aee-06bb-5220-913f-a960d252aa7e |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour
ae8310ba-4716-507e-b8d8-9d7fa2b1f637 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
3afd007a-74cc-5fcf-a2ea-3829aba27c65 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
78a1fe83-6475-5022-8361-7d50a64337c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.2 - Placement
637c174b-2a99-5fd8-8a8d-60f519a71cb1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.3 - Slump Test
6d62cd4e-1623-53e2-b267-bd4ddf30e5ac |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
1d4be02d-26e2-5f37-a7b7-c7ede7fd72bd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
b2c027fb-3412-5c3e-9a06-308f021618f1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
4c170901-d5f4-5816-add1-e9a15225f7b5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
504131c6-ff5e-58f8-9608-018c2213b673 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
47d8a47d-31b4-5867-97e4-2daf248924ca |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
941beb24-5334-5585-8705-e6f05256ba5f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion
8fbc3f1a-e605-5099-a5d6-3e18849107f8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | 6.1 - As Built
fc12aabc-917b-56fb-9473-97363ce7cd5d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | AUTHORITY HOLDPOINT
4aaa20ed-a091-5c5b-a20d-f242f802f5f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | 6.2 - Concrete Test Results
33c4a839-957f-5b40-921e-303c06515e87 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | 6.3 - Concrete cracking approval
9688a6c7-7ca7-5fed-b496-816c4175304c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | AUTHORITY HOLDPOINT
43e2b8c8-6524-5c64-8313-b3d6a011e498 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | 6.4 - Concrete cracking repair
d8f70f41-fea6-5b6f-bf7c-1ded29f9c354 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | AUTHORITY HOLDPOINT
df056442-12a7-4fa8-aa56-8adb428bd34e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | 6.5 - Leak Testing
aa7e6f21-263f-5e2f-bd26-af364e593b96 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-027 - Cooling Tower Basin Walls | 6.0 Completion | AUTHORITY HOLDPOINT
37849772-942d-4d46-b796-15081a484836 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base
6243d97f-c9d9-57fd-800b-2ca1077bcabd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 1.0 General
6c2b073e-d882-5d55-97d5-8629ed3a461f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 1.0 General | 1.1 - Material Submission / Approval
826efc6f-7d55-572f-a764-28f263eb386e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 1.0 General | AUTHORITY HOLDPOINT
fa3abec2-99ed-5ac4-bb92-5eb71639e739 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 1.0 General | 1.2 - Determine lot size
84e57460-f720-535d-ae83-6e6ff6fd95fa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 1.0 General | 1.3 - Permits
6802a08b-ad75-5ad4-b7b9-84de3cf25d35 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete
2ec1297a-d889-5057-8b5e-02d326885f71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | 2.1 - Set out
b759e351-4477-5058-bf39-94df527ce7a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
de0fe5e0-2231-5447-9f67-eeb13504d217 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
034c6983-d8aa-5b5c-92c5-c0a1f035234e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f2a8504f-35b4-5930-8ed1-99e23c7478fb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
6f5c6f90-29c9-5db1-8972-e90fb25521f6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork
c8d1f5b3-c71a-5af3-95d3-4a478eb46bd9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork | 3.1 - Temporary works requirements
9e5682f1-d1be-5a7d-b300-06b0a615d6d9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork | 3.2 - Pile Penetration
0811f7be-5355-5fd0-a640-0f936fd297db |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork | AUTHORITY HOLDPOINT
3d159da1-443e-54a2-b122-cb634ea4d110 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
32d389fd-fd11-54d7-8ccf-fa19ee008916 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 3.0 Formwork | 3.4 - Concrete jointing
29015c20-6f9d-532d-9d35-87eacc86d4e6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 4.0 Reinforcement
de04ad47-704e-597b-82da-787a21d005ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
facb832e-6a42-5603-ad50-fee89c1d4f04 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
d413ff60-5d6b-5348-8d3d-7f006a08d991 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour
ce10a203-bb2f-50a8-b7d7-9466550f9d78 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
1fa32802-529e-5569-867d-4987ec48a516 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b69fa88d-84c2-5199-8825-ca97c04ed948 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.2 - Placement
f0c16e02-2f69-5a44-b624-125ad19fee23 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.3 - Slump Test
77d7a82d-182b-537e-a026-7d7f8fdc7eee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
738b51a7-3f3e-5812-bbb9-9953b673ee1e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
a83519e0-639f-5e52-b932-f241f62f2c63 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d238c1c4-07cf-5770-acaa-c3bf7aacdb47 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
9260cba0-38f5-55a2-b114-269e6e52d176 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
f1f5d162-b366-59d3-a40c-3d9628ca047c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5817da3b-d3bc-5c4d-b2d4-372a5f091f67 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion
9361dba5-5a46-58ac-a207-626777e87eca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | 6.1 - As Built
08508b99-e878-5069-91b6-22579af23ceb |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | AUTHORITY HOLDPOINT
53fb4e0c-b263-55ba-b3f0-a9d42ee6b21b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | 6.2 - Concrete Test Results
4ac71370-1228-55a9-96ce-51f391e86f8a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | 6.3 - Concrete cracking approval
2ca8a3cb-dec3-5040-921d-9e57d8782903 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | AUTHORITY HOLDPOINT
62c3ee64-c13e-5dca-9753-1aab391ca1e9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | 6.4 - Concrete cracking repair
0c18bfe1-cc12-5a8d-b646-efa3dea2d2d4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | AUTHORITY HOLDPOINT
b577d75f-c01e-4d08-8b31-e6bba35da317 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | 6.5 - Leak Testing
fd4cf0bd-6370-5895-8d48-be665dae276f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-028 - POC54 - Base | 6.0 Completion | AUTHORITY HOLDPOINT
1c7d36a2-0664-4731-b7b8-84e86ef408fd |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings
e41147c0-f9ce-58f0-8cc8-d666157f8b92 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 1.0 General
75810041-fe74-5b79-ba23-1d8ed822bf01 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 1.0 General | 1.1 - Material Submission / Approval
131ad50e-e523-5e60-a0ba-bfc6ee522f66 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 1.0 General | AUTHORITY HOLDPOINT
5d44a473-07db-5fa0-8235-151cdcab118e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 1.0 General | 1.2 - Determine lot size
49b89b4c-e357-570c-af3b-782467828022 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 1.0 General | 1.3 - Permits
ffff1dc6-d896-5eb8-81c4-136db6a74215 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete
4c640dad-5f0f-532b-9448-92b62e83687a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | 2.1 - Set out
688cbb2d-7e2a-5575-8f17-849b9bf89c4f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
5116897e-2517-5f9b-bca9-30af30218097 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
b84c524f-061c-5f6b-8925-fb89f2e64c82 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
5b69c6a0-77fe-5364-84ee-e5482e971179 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
368d48b3-6c63-531a-87f2-b00bc2699ebd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork
91170099-5436-5cd9-829b-e20a46480e5c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork | 3.1 - Temporary works requirements
f347f4d6-bbc9-58c1-afe5-f3ccc0039525 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork | 3.2 - Pile Penetration
c809b461-0c32-50bf-a13e-cea30c1cc8ca |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork | AUTHORITY HOLDPOINT
5d84399a-93c4-582b-a771-fba5505a43c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
f4a24e62-34cf-574b-9be4-20b07f147c14 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 3.0 Formwork | 3.4 - Concrete jointing
fd7353f6-606c-50f1-b73c-522713bf58ff |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 4.0 Reinforcement
71c43468-41d0-5dd9-b894-fb59fcaa2193 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7abd9fce-ce15-5a3d-88a3-33b4753e6a0c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
e3c239cb-87d8-539c-844f-83ae2bc72bdb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour
e2cd7758-636d-506d-88c7-d5e260ac744d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
22b56420-da29-57bc-9cb4-4b18fe2d38af |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
2e2344d5-ff3f-5437-8e3b-982e12c22ae2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.2 - Placement
eea8225d-ed5f-5755-a4af-10bf3994f701 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.3 - Slump Test
aed53689-8389-51ec-8869-54a306fa93e4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
bddd966c-de5a-5fde-9c9d-58524d4f2a98 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ab34de13-dae5-5083-9add-350a79e6d780 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d533597d-837c-5f4d-841d-a83f0537a58f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
0f095dc4-c266-5ae9-bd2f-834e115bd2c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
13f6cc1c-c7d1-5419-a1ae-5109dcebb499 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
3d1519d2-e265-59e9-9668-d38e30b857de |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion
5314d717-f730-5d52-b614-3abae823d34e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | 6.1 - As Built
e3b20b52-faf6-5eee-8bf1-4c57a905e25b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | AUTHORITY HOLDPOINT
b688e98e-8840-5577-acda-83ebab5f1364 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | 6.2 - Concrete Test Results
a5a6b79e-9fa3-5f49-ab64-b82b11b5e513 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | 6.3 - Concrete cracking approval
326d6aa0-fe4e-5b47-b89d-2d7cbe0405c3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | AUTHORITY HOLDPOINT
f3c0306a-d610-54f2-b370-515791cdd792 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | 6.4 - Concrete cracking repair
bafb9335-cffc-58e0-9e5d-5429a39de163 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | AUTHORITY HOLDPOINT
7f97850e-3d36-4d9b-9c51-04a17b09bae7 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | 6.5 - Leak Testing
9c282efc-b26c-5d2d-86b4-fd0acb1bb61a |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-029 - Substation F1 Footings | 6.0 Completion | AUTHORITY HOLDPOINT
f1fe0e24-fbf3-4b90-a1e7-4c66cbf730d2 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation
12d90c85-d542-5ddd-8c82-ffcf7756ff03 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 1.0 General
47aec081-44c4-5e36-8b71-2cf97470a1cd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 1.0 General | 1.1 - Material Submission / Approval
33b5095b-a414-5b93-ba2f-25ac92df19ec |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 1.0 General | AUTHORITY HOLDPOINT
50cb592d-9674-5d01-9a2b-c91bc7d8c63b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 1.0 General | 1.2 - Determine lot size
34be6a1d-d518-5447-a012-95a448e35702 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 1.0 General | 1.3 - Permits
6cf813ec-3250-599e-933e-815f8ddb53c8 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete
4a8ad90e-e7bc-5b5c-989e-248de43c5840 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | 2.1 - Set out
b63af934-8523-509f-ac4b-15ba8a352b0f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
37595716-96f3-554b-bcd3-7105be65ec2c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
95177027-7511-50ac-9338-7089c44d9ff3 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
039e2bfc-542f-59ae-9086-195b71684704 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
0be80fad-fbb9-5539-9870-ac6e65dc5f38 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork
bf99ae34-7eec-5462-ae40-5b3384fdd254 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork | 3.1 - Temporary works requirements
f652109f-1354-575e-a88a-3a6e01da0e84 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork | 3.2 - Pile Penetration
d7160ddf-36d4-518f-abff-0d3660a482cd |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork | AUTHORITY HOLDPOINT
b1bcd17d-836c-507f-b18c-3eb7618e2119 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
b374ab16-b170-5fe3-9e27-c3b579aa7b6e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 3.0 Formwork | 3.4 - Concrete jointing
94864ec4-ed42-54b6-b5b4-0dbef8a7cbc3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 4.0 Reinforcement
9fa99222-d6db-5a7d-9620-9aac2b3d038e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
afcb3d08-3220-56ae-917c-2bd7ff2b0960 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
977d5ff4-7e73-50a8-baab-6d4a78b9c4fd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour
f832a6df-72ed-5548-a5dc-8dce59d269d0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
43c2e873-1ad0-5320-bbef-0b2379ad7750 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
4e9c4cde-dbb4-57ed-9bf4-2391e3583c8a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.2 - Placement
4389ace1-f55d-576d-9121-c4553552ba5f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.3 - Slump Test
3836ef13-606a-5edd-ba0b-a091d077015c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
1da18cd3-2c16-5e6b-ba3b-0a954f69bfab |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
96867f1d-8dba-5aec-ad5e-449b337596f3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
bffff58d-41a4-5a11-b72e-869fdac987f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
dbb43b54-2e40-5632-b8f3-1e72d923bfd6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
59ebdcb0-d31d-5198-8acc-c0326ec9189a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
55e936f1-13a6-5a36-bf50-a0c2d15cf3f2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion
89cfb6c2-f7a6-5ba4-8493-e35b24234cba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | 6.1 - As Built
da580450-063d-56ba-a025-6ac8261aad67 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
61e7a91c-8e59-5e1d-85ea-d15abba1adaf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | 6.2 - Concrete Test Results
2b94ed10-71da-58eb-bb56-60de24cd512f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | 6.3 - Concrete cracking approval
3855e8d3-d11b-51a7-934c-75ff5375c3a3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
4b75ae43-232b-5da4-8eba-cfbcc35dbb6d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | 6.4 - Concrete cracking repair
f5e2e6eb-28e7-510c-b26f-091c30b95dd2 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
0167e2ce-d14d-491f-afc5-80c52047047a |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | 6.5 - Leak Testing
37a2c40d-f433-545e-8237-c645b89569c7 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-030 - K5401A Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
d02f032d-25a4-49c8-82f2-7c8c108506ac |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation
96664d9f-db35-5b88-ab92-95025bc166e3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 1.0 General
e11394c5-a221-56bb-bb7a-ebccae1029af |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 1.0 General | 1.1 - Material Submission / Approval
a895634f-8e32-5dc4-909a-d81853accdcd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 1.0 General | AUTHORITY HOLDPOINT
936f95ee-493a-58a9-bb4f-301fe7acee96 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 1.0 General | 1.2 - Determine lot size
c71df1ed-3053-5bd6-82f5-81f72e28d203 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 1.0 General | 1.3 - Permits
0644a85d-1153-5f47-a915-17c4559888db |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete
9f536032-52ad-5ee0-aa02-3f0b930a1076 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | 2.1 - Set out
b55a8f8e-33f5-5c81-8778-c3f63986f014 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1f011610-83e7-58e6-9830-af3be40d7fce |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
4516d1a9-31f5-53be-970d-d7464154ac8d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
ae7915ba-df3a-5b36-9a63-9b91d35cee39 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
cbb46b20-3bb8-5fee-b369-5e049acca055 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork
5efbf26e-f28d-5a7c-9510-2b8794b047d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork | 3.1 - Temporary works requirements
c2dd0ba2-23b8-516f-80ac-6ac83acda425 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork | 3.2 - Pile Penetration
f061731b-e119-55c1-a0a5-dd10e5852837 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork | AUTHORITY HOLDPOINT
d034a128-cd73-56d8-8be7-08b4c1c194db |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
5048d584-a7d9-5995-b367-c07d54c334cf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 3.0 Formwork | 3.4 - Concrete jointing
7cfe78b4-f83d-5fd6-b4f1-ce874ec2fd14 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 4.0 Reinforcement
136dcb6d-0f78-571f-a03a-b1ee877b0f71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
92db2799-a613-5824-90fb-6f99b8737087 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
798b8893-d384-5624-96ca-9bd56a517404 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour
d1e10559-a0f6-59af-9efa-6db1d75859ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
8056faf1-8183-5a33-9565-863ed73d48c3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
8d62c435-6468-5043-b219-c764f0ecb0a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.2 - Placement
18c2f008-ef98-5ce8-93f1-642169f70dd4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.3 - Slump Test
d97b22b3-061b-505a-94c2-de11828937f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
483197e1-c582-53ea-8893-dc8863e20a68 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
b236c108-481b-572d-a953-91938b6b720e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
2dc9fab7-cf7d-50b6-a5d8-732fdd2f7822 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
0b8d523e-cb30-5f09-8020-d56205179319 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
a96d42b3-3fb9-54ec-9e59-bd2c87ab1f35 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
3209e36c-5baa-5e39-88e1-c4f4a773d310 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion
e8692f88-fd81-51b3-91d1-6a27ff96485b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | 6.1 - As Built
abb0d0bb-e4e4-5c57-8baf-e8ca870d0b97 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
aea5dc20-27f1-57a0-a8f4-a02ff8160ff9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | 6.2 - Concrete Test Results
9d013629-67df-5b15-bb22-aebb0e29cb29 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | 6.3 - Concrete cracking approval
f1b527a9-3c5e-5ee3-85ae-4488b6547c6c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
e819cfdc-400f-5429-9991-583a0ce30402 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | 6.4 - Concrete cracking repair
ad81a0df-2ae3-5fc2-a679-f6440773dcf8 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
0530d658-2104-4c4e-9e57-82c719559d9d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | 6.5 - Leak Testing
17331bd2-c5fb-5548-8b08-9f619898a66e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-031 - K5401B Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
5f650b86-6e0b-4b91-a470-5614f8fcfb41 |  | pass | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001
ac2f4c58-be9b-51ab-b790-2561c12201ee |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 1.0 General
a77781bb-4371-53a5-9940-6dd2bce3a691 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 1.0 General | 1.1 - Material Submission / Approval
43a491f6-f726-54f9-9f97-168449d3cc50 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 1.0 General | AUTHORITY HOLDPOINT
8b01f661-c5ec-51bb-a9ba-72f3b0b321ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 1.0 General | 1.2 - Determine lot size
d504b5e9-8150-5a62-88e0-c2effa13bc83 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 1.0 General | 1.3 - Permits
f15f1ea1-3835-5ef5-a9b2-3016a2f6fbda |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete
35c67084-e950-5aad-a923-c7ae2f3878f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
6e5ecaa3-2d4b-5290-9656-fbccd84f5323 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
b90c91ec-fe48-5c34-a7d4-ceb37d2c9918 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
75bc903e-bda5-55c9-89b9-7225d4fc25a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
8d7d3b84-e6da-5e7c-a778-a94f273bbe61 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f0f689ff-7568-5f29-9124-79341e3f06ac |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork
1dd20de7-ef37-56fb-9eb8-c8483046821f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork | 3.1 - Temporary works requirements
5397cdee-3145-5e15-8277-6b2f947c34e4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork | 3.2 - Pile Penetration
82df98b2-1128-5d63-9364-6daf82e73340 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork | AUTHORITY HOLDPOINT
3d6c2234-1074-5430-9aca-76b247cf55ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
7070025b-3f60-5d86-8a06-0b827aabe958 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 3.0 Formwork | 3.4 - Concrete jointing
1c88dcf4-c791-54cd-b194-ea4161d0f851 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 4.0 Reinforcement
ff25e8ef-20ae-530b-9400-bacfde618d6c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ac2162d6-65cf-5d33-a49b-0da459025995 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
aa041844-9181-55e8-b6dc-34176e3e8e84 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour
d04bb082-37b6-527d-99e2-863b846460e0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
5e4f8ae0-e365-5c89-9d93-375dd3e11f18 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f437c4d2-6409-5c9c-a0c2-32d5aee45181 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.2 - Placement
2b1a3608-1c98-51e1-8a70-ffb938568ab2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
1df00c0c-fd9b-5427-9e1c-c506751509de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
911ee345-01f2-5d85-9387-048ca943de75 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ce63feee-fb49-547c-9ec6-e6b3d2d0d80e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
783ddbe6-5ce5-5432-a690-0844e5a4dd8f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
a450f947-768b-539f-bfda-d311840ee2f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d8661f46-aa3c-531f-8fa8-78ddff627890 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
cd84f874-b879-545f-b9a6-5dab17d661b5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion
de8e4a43-f2ea-5ef5-b928-63b6c4a2c704 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | 6.1 - As Built
f2365374-f358-5351-b62c-d88924e4b535 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | AUTHORITY HOLDPOINT
41eb05cf-10ac-58ff-859e-1100e572d2de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | 6.2 - Concrete Test Results
a15468de-1344-5837-ba2b-c96b02600655 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | 6.3 - Concrete cracking approval
28c0d6c9-4462-5e33-bf4f-404f54dda82d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | AUTHORITY HOLDPOINT
c357143f-684e-504d-874a-1c28a4c575a7 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | 6.4 - Concrete cracking repair
2328de16-e34e-57b5-8a81-c34d3f8dc0bc |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | AUTHORITY HOLDPOINT
fef5c476-257b-4175-859e-65211310982c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | 6.5 - Leak Testing
09952305-8fb0-55b3-8b77-4ccfa76ddf3a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-032 - Pit 101-CB-001 | 6.0 Completion | AUTHORITY HOLDPOINT
c2716690-69eb-4b0d-b03a-ecfa2b2a715e |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002
b2dd135b-62ff-5f13-98de-36fe470d8585 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 1.0 General
31e6a56e-5015-571c-b0d9-902b63d34aa1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 1.0 General | 1.1 - Material Submission / Approval
a2ce19c5-6685-5d26-b22a-0fc06396a35c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 1.0 General | AUTHORITY HOLDPOINT
730bcec2-0425-5397-8c54-8ca0bcecb3da |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 1.0 General | 1.2 - Determine lot size
d0810bb4-53dd-5250-9708-82742388f0bf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 1.0 General | 1.3 - Permits
01146d24-4dab-5819-8ec1-ce65b1884e1f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete
86ef90a7-e6f4-55d5-ac75-afdbc8bcacec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
61190b95-3338-5259-882b-0ebb4ae6d65d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
59a67bae-2393-5ca3-adc9-927caf36d333 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
300c1e11-dfa1-5b02-bb94-f851379c9367 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
fb27a6e7-dc44-5a2e-ac6d-d5dd0ad5fb21 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
e106d6b8-51ff-5402-897e-5fd8b6d7474f |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork
7074b676-a481-5bee-a75d-5b5ee1f406f5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork | 3.1 - Temporary works requirements
2fa839da-e671-5e52-9b8c-92553e454f6b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork | 3.2 - Pile Penetration
05ab9178-0305-5aca-9a74-5c9a02143a28 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork | AUTHORITY HOLDPOINT
e0eef43a-21c9-519d-9168-86cc691d865f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
0ef3bf1b-f6df-52a7-8679-d39b97f0a09f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 3.0 Formwork | 3.4 - Concrete jointing
c461aa45-bd19-56da-a3b3-db4301a0989a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 4.0 Reinforcement
fd161fc5-beff-5919-affc-22ebea8dea9c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
3eb35274-e984-5724-ac09-8376955148d1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
234824d8-4548-5ee6-8932-44c6b100475f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour
229e6bed-4e87-51c8-a449-f577b6a97d46 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
658659f2-604f-5458-ba29-7de40f368c81 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
8268fde0-a573-5d9a-a784-083a506006da |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.2 - Placement
b08f9a33-8dd3-5e43-aaef-beb0ed4a3f3d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
62241bda-08e7-561f-ad04-56293fcdc98e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b2f174c4-b160-5098-ada1-754ea1cc89a5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ad547f77-c459-54ce-b331-299c2530432c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
e118a554-00fa-57f8-afbc-bc473686650a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
65944c3e-fedd-5838-b4a4-d1fa27a8dda0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
5cccc125-ac9b-5fc2-af2f-46c54ce5c3fb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
77f8f37e-c8c3-5cf6-803a-db92f98c8547 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion
3a316114-6229-516d-9c6b-eabfbd280ae9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | 6.1 - As Built
35ed9079-546b-55c3-80a2-2028a453a5ef |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | AUTHORITY HOLDPOINT
0d5bd837-cf8c-590b-9ca2-c9cdaade1948 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | 6.2 - Concrete Test Results
793320ae-37c0-589b-8b38-d19d7de6c4f0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | 6.3 - Concrete cracking approval
24309fad-d25d-51ce-b501-c5bd2c4eeda2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | AUTHORITY HOLDPOINT
3c241f4d-d37e-5015-967c-b8014d1f8af9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | 6.4 - Concrete cracking repair
f31c9f3d-0ccb-547d-8277-789a1bb9a93c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | AUTHORITY HOLDPOINT
b408428c-d2f1-4e74-ad25-ac07da253495 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | 6.5 - Leak Testing
e9ad5e4a-db3d-5fe8-8a1b-feffe5f3b1bb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-033 - Pit 101-CB-002 | 6.0 Completion | AUTHORITY HOLDPOINT
454a360e-aaf7-470e-b597-cbe7d89f5ec4 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003
2a9f3de2-d3e6-547f-9df9-b71d9a2f5afb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 1.0 General
e8765e2c-26d5-5fe6-9aee-525d71f829cf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 1.0 General | 1.1 - Material Submission / Approval
1e35a6b2-b52a-5616-910e-dd0b63c3fa8b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 1.0 General | AUTHORITY HOLDPOINT
28dee440-b951-529e-b632-e6020ed0e02d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 1.0 General | 1.2 - Determine lot size
3b475683-a733-5392-9547-59164c345012 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 1.0 General | 1.3 - Permits
ab7eec44-2a88-52cb-997e-1d133b66815d |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete
161dd5d0-a6a9-53df-982f-c53ddab9031b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
80c3609c-eff0-5155-b451-cc74699c8e51 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
9d20726d-9e2f-59fd-b59a-d7a57259c6b7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
40bb3557-be86-5d73-afaa-068bbd847fe7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
7592a2df-29f6-57e6-95a6-139df18e7987 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
0146d8ce-f65d-50f1-852f-c8b8c2c9fec2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork
990d6605-a4df-533a-94f7-a0c04ed9cb25 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork | 3.1 - Temporary works requirements
b76f29bd-aa9e-522b-9c8c-c246e674b9de |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork | 3.2 - Pile Penetration
130571e2-6aa0-5edf-8a3a-2618ea55d361 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork | AUTHORITY HOLDPOINT
ecd5ab4e-19b5-5158-8dc5-dfc65310a184 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
113eee9e-841b-5764-ada7-34e7b193e10b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 3.0 Formwork | 3.4 - Concrete jointing
99440dbb-50f9-50b7-9809-8c6d7fa4e90c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 4.0 Reinforcement
87c6cab8-358c-56ba-83bc-5efee1a5c3e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
cf32e48a-4730-5d9d-9921-f2257b01b2d8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
b39f0237-d2ec-5209-a923-49353cde1423 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour
521614b5-430d-53c1-8722-6372f06e88d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
00509298-b156-51e2-bb26-6a5e9b18a816 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
eb78efbe-7769-547d-9077-e95c64557ae3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.2 - Placement
7946ca8e-38e1-5c7a-a540-0e5f25483b45 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
08784565-b091-5ab4-a867-6fb645801ad5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
a9f1bc9c-d2f9-5958-9c26-edfeb2978eeb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
2586c540-ba01-517d-8d0b-d16b8d33320b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
77d4eef0-6086-5bad-b0c2-8d5db1d59c95 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
c0a65c3f-b21f-5b84-8103-1188bd278744 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
4f05d470-e116-5cbd-ab72-64f4f68c74a1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c1981b11-4f11-55b9-98d2-d5604b67b636 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion
370d878a-6bd5-5e0a-b79e-4e14b635f3ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | 6.1 - As Built
e246000c-9c98-5f7b-8e91-71c0e2a0f959 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | AUTHORITY HOLDPOINT
f6b75957-76a0-55b8-b411-8e914e608c54 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | 6.2 - Concrete Test Results
70e56591-0eeb-5f8c-ac5e-94f381e8bec2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | 6.3 - Concrete cracking approval
4859258c-31f0-5eb7-aaba-e87ab9a61f25 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | AUTHORITY HOLDPOINT
d70c066b-e5f2-5770-88f8-0375d7ede71e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | 6.4 - Concrete cracking repair
2a9ee101-05c7-581a-a9f2-510ca96deb0d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | AUTHORITY HOLDPOINT
91e03547-8a84-452c-b595-ed007a8ecae4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | 6.5 - Leak Testing
c5957d63-89dc-5df1-94b3-3e4ec1eea234 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-034 - Pit 101-CB-003 | 6.0 Completion | AUTHORITY HOLDPOINT
80194640-3c24-4f02-9f29-1fb41d98a85e |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004
6fdc6a36-fa05-57ab-a28c-8d961d6c8c4b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 1.0 General
e70e5d4f-0e91-5915-bdb0-1273b1807b2c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 1.0 General | 1.1 - Material Submission / Approval
a96da654-4e38-5ac7-9ccd-140d789f9c5a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 1.0 General | AUTHORITY HOLDPOINT
e7834652-8085-587e-a588-57b32ae1c04c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 1.0 General | 1.2 - Determine lot size
49c6a9c6-bc1c-5fd7-af8d-b04b75a754af |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 1.0 General | 1.3 - Permits
e78bc43d-cd3e-5b9b-ba58-376566639796 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete
db784a8b-dd11-5e9a-a5a1-65abee6643d5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
287893e3-6a5e-5f5d-ac5e-05ba87af37ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
a619643b-1286-539c-80c6-90ceed698de3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
f09965f1-c242-514a-9cd8-852abb8f5044 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
e6ce6e1a-877e-5b44-8c6b-a0a09cb94c2a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
946e0665-0b0f-5195-b6c8-37ce9a7ecc73 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork
203dec4f-13ea-5fd2-9d33-74547b54c732 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork | 3.1 - Temporary works requirements
087c4f47-d3ab-595b-9cfd-6e434fda5965 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork | 3.2 - Pile Penetration
840f16e0-6dba-5a4a-8a29-52f487f4c456 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork | AUTHORITY HOLDPOINT
ada23a56-3c8e-5480-bedb-582525dc2cca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
e3617d55-caf9-53a6-b753-cf6e252862b3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 3.0 Formwork | 3.4 - Concrete jointing
c8551167-e13e-593c-b561-e3975a747e59 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 4.0 Reinforcement
bb86003d-7baa-590a-833f-4d08590f4302 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
3c974b6f-96dd-568b-9297-b2af9d636a37 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
8c0f12db-8d4b-5ea3-a3f0-7a10e5b41b97 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour
8f782445-5185-549b-a6a0-79aff8696b37 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
a6b717c2-df5c-5c24-86a2-80d03e6368be |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
88d33e19-a3de-509e-b820-796e294585f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.2 - Placement
9e5a4509-84f5-59a5-bdc4-f6693bea63cc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
b15cc87c-9f68-5bfa-b1bb-a201875f008d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
e93be9d3-da3b-58fb-a22b-24dceae52f1e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
7f2fae74-0862-521d-a928-d63e58d846cf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
4c1437cf-e775-5acf-b92b-ab188533c1c4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
ec71f448-c4c0-5b01-8c48-8a518583a15d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
e3e54395-214e-569a-b119-978712bc1886 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c5c107ae-f03e-5f1d-b57f-66195d9f56cd |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion
b24fc4ed-0180-582e-b9ec-8a5d35997b90 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | 6.1 - As Built
60753ddd-ef8b-512f-9819-37e85d3bfb83 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | AUTHORITY HOLDPOINT
69e5b3b9-2eb1-52ed-a793-0150f046334f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | 6.2 - Concrete Test Results
8f79034d-47cf-5439-b8af-151c5194777d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | 6.3 - Concrete cracking approval
f8ecf59e-1c3e-504b-a0fb-2f715e7284e1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | AUTHORITY HOLDPOINT
29aba74d-5a71-5278-a5ed-99be894ce256 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | 6.4 - Concrete cracking repair
c472c7e5-87a0-5555-b056-908923a5cc41 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | AUTHORITY HOLDPOINT
a6cf8d9e-c3f8-48fe-b8ff-2f6ae9f26c6b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | 6.5 - Leak Testing
872b59c5-e45c-5cd2-bfe1-dab8945ede86 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-035 - Pit 101-CB-004 | 6.0 Completion | AUTHORITY HOLDPOINT
a6105242-462d-4b61-a915-a801ce4905a8 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007
0f23165b-5ea4-5f8f-88bb-6d20d011f8a4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 1.0 General
8ed8c99a-cedb-58f6-9db6-1d1d7c718bd2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 1.0 General | 1.1 - Material Submission / Approval
a63e5f04-6ce2-59fe-aa05-5fea65fe8188 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 1.0 General | AUTHORITY HOLDPOINT
ca489d25-3993-54cd-945a-795e6186d11d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 1.0 General | 1.2 - Determine lot size
baa6dea2-02ad-551b-a604-bbfb5bd37bf4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 1.0 General | 1.3 - Permits
3b702f39-b213-5bd9-8f48-5e7038a0485b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete
a9d13c94-f4b4-506e-a2d9-4e1776d3c5d1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
e4186251-6f56-57e5-89cb-d12a8dd2ff50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
581516f0-fc29-5b60-bd7a-84383b47108b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
3e10cce0-42cf-5100-a764-20bebe0dd2b8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
858d4706-a61d-5d24-af95-5032e35507a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
de1bd484-d796-591c-96e3-15d80b8e2119 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork
4cb21bec-317b-5eb2-9627-49051851cb59 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork | 3.1 - Temporary works requirements
da49f4c8-b8a5-51fc-a62b-52c63c5f3291 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork | 3.2 - Pile Penetration
e52021ee-bfc0-5ca6-a084-6d4ecb35ee4e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork | AUTHORITY HOLDPOINT
082219a0-c9fa-545d-9203-780a30cfb143 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
bb6bfdbb-b9ae-58ff-b3f5-47bb306b29ff |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 3.0 Formwork | 3.4 - Concrete jointing
50d61978-41cc-5599-8265-62987248bd63 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 4.0 Reinforcement
97f49792-1c3a-5184-a3e2-7868b23d3b8e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
8b04dc90-ba4d-566d-b39c-acdfb82a5562 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
be2bcdae-3914-59d6-9e29-14a35acb3989 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour
7e4d2a9e-e311-560a-875a-a438a9c702ff |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
d9fc12d3-3d00-59df-8616-561175b552f7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
de3a8a42-ae50-59a6-89b6-de471ef8a6d6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.2 - Placement
e4e1512f-e883-5119-b8c3-0a4754f052d0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
dd7bf4cd-8e8c-50af-843a-825c187e26a8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
9024bbbd-b416-57d5-a01b-0b63ba3d38dd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
d2bf2001-09b5-55d7-8c2d-3c7b44b5f395 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
0f21c520-bea9-5d2e-8886-be2e057c3a07 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
71a895ef-d551-5cc4-b56b-f3b4b4a06430 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
830280e8-a910-5eec-89d5-777d90f73e08 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
81169a56-63f1-59bb-83cc-35a0524cf1cd |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion
46655d42-c9f1-5012-9d7c-129b21e0815f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | 6.1 - As Built
5c3581a6-3ac5-5ede-a936-beb0e8dc9042 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | AUTHORITY HOLDPOINT
d8eff106-9d51-5dc4-92f1-bb9b4301e686 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | 6.2 - Concrete Test Results
55381528-5c0e-50af-979f-4ef255841e22 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | 6.3 - Concrete cracking approval
9e4310b1-5c32-5b7c-9dea-b8255e190a45 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | AUTHORITY HOLDPOINT
4bb0c982-7dc4-5c10-b608-13a09eb4d67e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | 6.4 - Concrete cracking repair
c8c1cc6a-e4f9-514e-87fd-61e2e60311c7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | AUTHORITY HOLDPOINT
f7c5b3ac-e5fb-4a36-9140-339ec47ea55a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | 6.5 - Leak Testing
67380087-a549-5797-845e-a5437b856f8e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-036 - Pit 101-CB-007 | 6.0 Completion | AUTHORITY HOLDPOINT
c9817c05-b56c-4a8c-b06d-71b4b1d2b74c |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010
10c3c961-941d-5428-a5f7-8b30a81f3ea0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 1.0 General
47571b85-6de9-5c56-bd0f-5a438bf126ab |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 1.0 General | 1.1 - Material Submission / Approval
5ca9c63b-e5bb-5ed7-998e-75586c13ae0f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 1.0 General | AUTHORITY HOLDPOINT
d188da5b-4836-5160-894c-7d92391f8eeb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 1.0 General | 1.2 - Determine lot size
47e99540-df19-54c3-b1f6-3be0861f49a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 1.0 General | 1.3 - Permits
8991450e-571e-51e7-ba0a-93f05f44c072 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete
bf8e55db-1ee1-5f43-83ef-74a331be8924 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
591cfb9a-f5fa-5b5d-a46d-7d60e944368e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
3c98db57-8591-5fb0-9bc5-0d559911cab3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
fd86cdfd-a037-571e-bf22-24cf1bd790a9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
8381616d-3160-51df-adab-6c0566a19058 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
7b31fde7-e2c1-51ce-a01e-f90887decdb8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork
cbe80979-f52a-5b3e-a0d7-b8fd93e9a672 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork | 3.1 - Temporary works requirements
f9e5d30f-d034-5d1f-95a1-f4bd0152fd93 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork | 3.2 - Pile Penetration
7caca6b8-11dd-5268-b919-a367334c2e8e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork | AUTHORITY HOLDPOINT
d7ac3289-296e-56fe-ba51-cb236889abec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
59ebcf0d-4f9d-5b76-a463-b9550b59df96 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 3.0 Formwork | 3.4 - Concrete jointing
f0959868-a926-5803-8354-f163e2d0c63c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 4.0 Reinforcement
c7bcccfa-1884-5238-8217-9e363e90a667 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
c0fbf380-91d9-573c-b63f-c95115885493 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
87c1069e-03a1-5ae0-9d7b-4340149126c4 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour
59da6b98-9c38-547c-96a7-f1e8c26ff894 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
1b316d52-334d-5b13-9b77-b62eb0e53e48 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
08943f21-d2b3-5408-b2ec-6450a44b1ded |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.2 - Placement
d470b3c6-e9de-52ac-8f44-741f0a2a777e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
ada45db0-8ba9-5d1e-8372-49ee90f6ce7e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
37b2758c-2fec-5849-aab3-856e6a39caad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
88c50d24-15a1-5ad7-8e6b-420a61545bce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
fc62ddb8-1593-5bd7-9116-d3f07bd6fc27 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
fa09469a-33d8-5af8-9270-aad2936b0931 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9075490e-f164-5d3b-9c1b-2f664f80f579 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
16d02aa7-35ec-55d0-8621-5ac8b70208d1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion
0926165c-2bfe-5337-99f9-cb74d7794e8c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | 6.1 - As Built
010236c6-752e-58c0-ba37-68b98fc0b8e1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | AUTHORITY HOLDPOINT
6ada2eb4-463f-52a9-b903-916d41a69625 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | 6.2 - Concrete Test Results
f4fabe07-0022-5c8a-9c41-9176f7fc229c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | 6.3 - Concrete cracking approval
c422a574-3403-58b2-85f3-7e01256754ac |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | AUTHORITY HOLDPOINT
15528e5a-de65-51e7-b1ed-31ff7bcfa6cb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | 6.4 - Concrete cracking repair
8c59b531-18d1-5131-9543-d96affdbc494 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | AUTHORITY HOLDPOINT
072b5c04-e83f-4557-afc5-6971f62cea50 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | 6.5 - Leak Testing
5c010ca3-cd65-5974-bb5d-d399d1acb4ce |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-037 - Pit 101-CB-010 | 6.0 Completion | AUTHORITY HOLDPOINT
cd2c9587-b765-4d77-af3f-a6cae0e050e8 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011
ad8ff90f-6f4d-56bf-a806-6e29a478f699 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 1.0 General
4e1ff183-a59c-5084-853a-76740370c50a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 1.0 General | 1.1 - Material Submission / Approval
d0066af8-46ca-5fe8-bd94-50022ec65214 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 1.0 General | AUTHORITY HOLDPOINT
f13e68c8-7ff5-593e-81b6-32db62af76ef |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 1.0 General | 1.2 - Determine lot size
a70b6b83-75b8-5393-80ef-11288c0b1139 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 1.0 General | 1.3 - Permits
8755d1bf-2eed-5d72-9055-4ef8e50248a3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete
092fd82d-794f-5964-af12-a4cfd5f445ce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
ae24d5fc-36f3-551a-9680-27c81008cfc6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
203ca65d-1c9c-5c67-a0ef-942d35349cc7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
b6f99565-047d-5c9c-a3f0-6fcd345c7c7b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
51667149-c44e-547a-b314-89c8fd221c36 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
05bfaaf0-6f53-5700-bb57-f2971984bd63 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork
9858a6e2-a0da-5095-a9e0-18d3775639fe |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork | 3.1 - Temporary works requirements
9f6cd354-91f0-5d92-b8ff-f3b3e045f781 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork | 3.2 - Pile Penetration
c1c18563-5d8c-5c02-b992-7f990549b0b8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork | AUTHORITY HOLDPOINT
baa311b1-17e2-57b4-bbd8-33dc89cab98a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
e6ee789d-a264-5225-a3b1-a337dd32aa42 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 3.0 Formwork | 3.4 - Concrete jointing
fc76825e-e50d-599a-8c64-a02e421f0b18 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 4.0 Reinforcement
e7b91c04-5d5c-5594-97e9-9df964e513ea |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
10f18188-a4c9-570c-98d4-63044bb1b1cb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
a0c8dbc2-e1b8-5561-85b1-26298de8c6ef |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour
5f0de2a5-0006-5400-bb57-1cce98401b46 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
eae1d41b-31d8-5051-a54a-57e505146fbb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9dd47640-7cb8-59bd-9f5a-cf5ecd71abde |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.2 - Placement
fef67ba8-be5d-5eed-aa93-53c5bdc8582f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
1682d8ff-9925-545c-a728-491ea3842224 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
210c9e2f-a126-5948-80a4-caab3b010b4e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
f25e5d9d-f703-5fa4-8f5d-4d23f278b250 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
da558914-e9cd-5811-87f3-62b26759faae |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
eb4d0014-e543-5a94-a470-52fea3055f8b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d5725724-a202-5b2a-904f-1eafdf562d94 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
ed3ade07-13e4-5aa7-941d-7e0cd94c412e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion
2cd9273f-17bf-5c6a-8893-62ccf699b888 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | 6.1 - As Built
ddafe17d-0214-5fb7-b1ef-63b810f895d8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | AUTHORITY HOLDPOINT
4b3ea77c-3809-5066-8e14-9bebe7745491 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | 6.2 - Concrete Test Results
6a032b49-daec-5250-9e98-e1430723d880 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | 6.3 - Concrete cracking approval
24f09e13-4fc5-504a-bbeb-ff8b11244a5d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | AUTHORITY HOLDPOINT
61110dca-1f2f-5969-a7a9-54bc8059f377 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | 6.4 - Concrete cracking repair
5d7bec8b-047e-533a-bc04-23d0f9870b86 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | AUTHORITY HOLDPOINT
faf1fecb-9728-49e8-9823-e3063aed0481 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | 6.5 - Leak Testing
9afd3a54-b803-5553-b8ba-dec4871797b4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-038 - Pit 101-CB-011 | 6.0 Completion | AUTHORITY HOLDPOINT
d3100f91-fcee-4d14-a1e8-0991ddf37674 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012
06314611-0be5-504a-a12a-1728909dbb98 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 1.0 General
30d4e7f3-8b8c-5d00-8168-a1adc1b8ad26 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 1.0 General | 1.1 - Material Submission / Approval
471187f5-f61e-52a9-b03b-47e65c3e71a4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 1.0 General | AUTHORITY HOLDPOINT
cbc766bc-f8a5-5a7a-9277-a17153993855 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 1.0 General | 1.2 - Determine lot size
afc9451e-96f0-5935-8411-c11621b0a361 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 1.0 General | 1.3 - Permits
b923279b-6299-5bb5-8515-2e146f897b36 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete
c7791e71-87ed-5e02-83d5-8e4681e3bc90 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
98cd944e-b6cf-591d-a8cd-dbd51e18108b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
294ac7f4-b51d-58c5-8768-a41f8651e99c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
e462e7a7-0547-582b-8f1c-12be82eefbfd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
ad294872-f693-593a-9a6e-d0e8d5004cbe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
33aee021-11c9-556b-bab6-d28e60f2da0c |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork
a4f7087c-5b3b-59b0-ad1a-1becb324cb0f |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork | 3.1 - Temporary works requirements
13af3e53-364f-57ba-8ef0-762976c4a1c7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork | 3.2 - Pile Penetration
f2cabc63-255b-5db0-8810-da44c3a17c2a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork | AUTHORITY HOLDPOINT
0160aea8-77b2-5aef-bbf0-6ee500a34ad5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
f925dc44-dd22-5d5b-91ab-3ef0680af291 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 3.0 Formwork | 3.4 - Concrete jointing
88ec2725-ef0d-56ff-ad16-9324da4aa3b3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 4.0 Reinforcement
a1a11007-720a-5854-b2c2-cc2a38fbd06a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
2a1fc5f8-e430-5f5d-9c2e-48138676d0fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
05f05e94-779f-5483-a0f7-9ad983adc0cf |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour
7d09d94c-cdc0-51b2-92af-ad3f3322c53c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
c2e281e1-d0a4-5bb5-8898-a1660ae85ee9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
563dfb12-edea-5178-924d-40299da90fed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.2 - Placement
1ffae1d1-91f1-52df-ad5d-99d84cd7f125 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
0440e961-0b40-5473-9f57-735846639ef0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
05d910a0-370c-5be5-9011-fb61b6e0db01 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
81e85d3a-7add-5ba5-9212-38d9455d2a62 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
106de641-d8f8-5d8c-b1a3-5fe1899b3032 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
857716f1-823b-55f5-ad56-198523d8b8f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
fba72512-dd03-5df0-902f-f68bd05ecdca |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c6faa8da-2128-53be-a337-11a0aa8234ca |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion
17124974-66bc-5f32-8e6b-218e22603b47 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | 6.1 - As Built
8b9cd4b1-7626-5c19-8b6f-5ffd650261a0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | AUTHORITY HOLDPOINT
e031433b-7283-5c5d-aa3d-7370bfdae0fc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | 6.2 - Concrete Test Results
d4af2dc8-dc1d-5544-aba6-d51f1909ee3d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | 6.3 - Concrete cracking approval
fe540934-a10c-5126-9d4d-2c6baa979a66 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | AUTHORITY HOLDPOINT
8124a065-335d-5198-bb84-9fa642c3d743 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | 6.4 - Concrete cracking repair
006432a4-7420-5b8e-9c3b-4ceb8062cb67 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | AUTHORITY HOLDPOINT
f1725eea-2787-438e-9095-e4a82dc2e073 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | 6.5 - Leak Testing
ec6a3309-faf6-5ee4-9bae-e4c92a40c2ef |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-039 - Pit 101-CB-012 | 6.0 Completion | AUTHORITY HOLDPOINT
65269131-2ff4-4c09-aa7c-be270f8b0f91 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A
de739918-74dd-5b5d-92ce-e9a365811ce6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 1.0 General
d2523e6b-2e63-581d-b310-90dcf396ea7a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 1.0 General | 1.1 - Material Submission / Approval
9a568f2f-65cd-542d-be4d-2ce47234a401 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 1.0 General | AUTHORITY HOLDPOINT
a62513f4-0621-5f89-b189-7fd273565d01 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 1.0 General | 1.2 - Determine lot size
d2c85bbe-3b33-5407-97ba-bc2c987c4a4c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 1.0 General | 1.3 - Permits
b16cbee1-25c0-5d9d-9c7a-cd5a7a72c931 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete
e69a17b2-9f56-51f0-90f6-f7e9a14025d9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | 2.1 - Set out
504b7d8d-7b0b-51ba-b794-644a5ee395a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1c13bdf2-bdfa-5e32-9b9e-a3e1cd21a71a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
04c1afc2-78ea-59b8-bd5c-bb8dcaae3a86 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
5a3f64f7-0f0e-5408-b0c1-426f4a09277a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
103c5398-f079-5083-a4cf-9da8ccca7127 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork
7b7a7a2d-d0ce-505b-a373-6080a1d89c96 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork | 3.1 - Temporary works requirements
e8bed635-f837-5a39-8461-c7cf5c435222 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork | 3.2 - Pile Penetration
e146d3e4-1f4b-5885-8881-3c1f43df95a3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork | AUTHORITY HOLDPOINT
83517888-c353-52d0-be7c-82482e860be5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
a3af9975-e3f5-5f37-8788-a390a3b8c5c1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 3.0 Formwork | 3.4 - Concrete jointing
2dafda2e-2d39-59f4-8428-86f19070ad93 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 4.0 Reinforcement
2100dd7f-a99e-537d-9fd4-396feb45e5a9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
19fb9822-78ad-52e5-ac51-557740a7666d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
e7ec87f0-a069-5a55-830b-4de91f0fc6e2 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour
a66f1095-7426-5aa6-b616-d1ef52ea9fde |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
622f6b03-76d1-5650-aae4-237805dad625 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5662a708-1966-5c03-be7c-fbb4e1e70d63 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.2 - Placement
608b30a6-4ea6-5271-a5db-14571c555fc0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.3 - Slump Test
32999c86-dbc3-52ac-a0a6-908fb036102e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
fda3edc7-d1ee-5d29-8ad1-c32a103cec35 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
e5679239-914f-591d-979b-cdba47ec878d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
3a69941b-1ce2-5259-b83b-e9c3d6efe64a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
c357c735-c074-5aa9-9e7d-f940aeada80e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9475ff8c-73b6-5594-bb65-dd6f550ee153 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b556ee3c-5e06-5aab-aece-c46ead79942f |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion
475c8ab2-86b8-5e70-a92d-4a0cb0068d89 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | 6.1 - As Built
a0da6002-9bca-5f3d-8468-2b6b8aa2e676 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | AUTHORITY HOLDPOINT
e2888655-69a5-5af7-829b-a0b3ec41c9f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | 6.2 - Concrete Test Results
9924f926-5f65-5f8a-a7c4-39821a524e38 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | 6.3 - Concrete cracking approval
ae0ff380-2bea-5313-a1a0-58379a1da283 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | AUTHORITY HOLDPOINT
d1f1fb27-e2f9-5b40-9e6d-f27e3f1901db |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | 6.4 - Concrete cracking repair
f65c19b8-1e74-582d-8180-4d5b18bf3d8c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | AUTHORITY HOLDPOINT
3c056c14-91d9-4543-841e-afce2c42e639 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | 6.5 - Leak Testing
5352e3b9-e2f7-5c2a-869b-7d103c301c61 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-040 - PAU-03 F1A, F2A, F3A | 6.0 Completion | AUTHORITY HOLDPOINT
7939c9af-d9f9-42d5-adf9-901cd9c6238e |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams
3c462b92-9fab-5bd3-b75d-2925e8c5ce87 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 1.0 General
1c4f8b43-7659-5f60-9877-d41e679c6070 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 1.0 General | 1.1 - Material Submission / Approval
c028df91-e856-5fbe-aca9-d3151e476a5d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 1.0 General | AUTHORITY HOLDPOINT
8617cedb-718a-573c-a806-ce327cfb9565 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 1.0 General | 1.2 - Determine lot size
a3beb68a-79c3-5674-9dd5-564ed4c9baae |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 1.0 General | 1.3 - Permits
c085b386-21b3-5b6d-bbc6-b40b3e1af75b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete
e32052f2-f1c9-53a7-9da7-daa280de7a98 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | 2.1 - Set out
f20cdaad-d299-5c0d-9569-45003a9e8ce6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1f96bf2e-fd4e-5371-8100-6d5ad9eb64ab |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
9a13804d-b651-5d05-9437-98f08ecd307a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
eabba24e-3b99-5545-9102-6577a87c9bd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
5cc31a15-f146-518c-babc-b3ce82468bdb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork
a465924e-9baa-5211-9c86-64a3a3abad3a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork | 3.1 - Temporary works requirements
c95899a4-99f0-5f8a-9ce1-bee996b309d9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork | 3.2 - Pile Penetration
35e88b23-0356-5e37-86c4-4f7f01495963 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork | AUTHORITY HOLDPOINT
1273b020-6e42-5431-9e5b-4d87498a5888 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
c742577c-c8c6-5ac2-98df-bbd9ac5dd7bf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 3.0 Formwork | 3.4 - Concrete jointing
ad18ec9c-6a1e-5f82-a599-ab9233c34da0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 4.0 Reinforcement
1b5bb539-9fb3-5636-a5b0-b7432062114a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ed9ae8a6-6542-5c38-a865-0ee22b699dcf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
16dd73c5-1859-587f-801c-d9c5a1e47e42 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour
f249b968-fab0-5f18-9ee7-2386d4c0e258 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
f563fcc6-fdf1-5a04-b47b-c96f180be343 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
466eb040-05a1-5970-9a0e-0357accdc103 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.2 - Placement
b27d75a9-69ab-5054-b759-5d3ee1566ce1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.3 - Slump Test
86e69f75-4428-53cd-99fc-e5e4430487cb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
a9a24bc7-b148-5240-a01c-bf091db6649d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
34c56b80-d32f-54bd-bd00-429984120a83 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
ad7ea195-87ca-5ab2-8f1b-410059b9ad09 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
d1db8e0a-3c14-557b-b5fb-f3c159143c22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
f2bab8d7-7f86-5907-9414-cc0c30bb2b12 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
7160175d-c49e-50bc-b732-1b653a331fa4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion
a4161ce3-bcf9-5f52-bf42-9dea4cb40a46 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | 6.1 - As Built
f48d564c-c0f6-5339-88b1-970f1d42e0c0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | AUTHORITY HOLDPOINT
b7f5b2e5-cb75-528b-9df4-e5279f81db37 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | 6.2 - Concrete Test Results
97dec2b3-ce0e-53ca-b1d1-32623bde22a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | 6.3 - Concrete cracking approval
770e0916-e4a4-503a-9295-07ea2e5577b6 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | AUTHORITY HOLDPOINT
c03ebe11-40ff-55cd-81e1-96347d8bbe12 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | 6.4 - Concrete cracking repair
a5adb4bb-1e05-51ff-ab3d-cc548913cd7a |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | AUTHORITY HOLDPOINT
9c5ffd43-300c-4c3d-8278-3d2cf5763e35 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | 6.5 - Leak Testing
1c35231b-b3b8-5802-887a-f3c33e52f9e9 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-041 - P5451 Pile Cap and Tie Beams | 6.0 Completion | AUTHORITY HOLDPOINT
2f8bf449-9934-4934-8427-85282a2e268a |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation
702d03f1-7010-5d31-bf4b-30e5f5014d99 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 1.0 General
fba39b67-fc14-538d-8c29-d153ea1398b7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 1.0 General | 1.1 - Material Submission / Approval
6f5d86ff-9950-5367-853b-14b5ca07459d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 1.0 General | AUTHORITY HOLDPOINT
ef7eed77-d78b-57b4-9f97-ec3ad9dae980 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 1.0 General | 1.2 - Determine lot size
afad470d-8302-5a9e-b7a1-fc660744945d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 1.0 General | 1.3 - Permits
97dd4f2b-919b-58cb-b03a-57bc1080616b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete
93d94552-fdd8-5741-93a2-f76340cd05c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | 2.1 - Set out
4dc4464c-9f9d-58e7-b538-ca8dac18345f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
6f2395f1-7302-5e31-9e1a-4b00166d8682 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
e5b4f1b5-73c7-508a-8c2d-f2960a332d22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
692015f8-e17f-530a-be5a-adc7ecd4ad87 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
9070b1b9-32bf-5824-b3ce-8f6d0c6e7504 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork
1895acec-99c8-5b3d-8bf9-9214c13082da |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork | 3.1 - Temporary works requirements
ee78c0c6-08f3-5979-962a-284eac127bde |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork | 3.2 - Pile Penetration
1f4418fa-9bfc-519a-b1ef-35877f0780a4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork | AUTHORITY HOLDPOINT
fe763f01-20d5-5614-a447-b24ea5a5ceeb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
c1a5335a-aa21-5570-93ce-00a8e6fb3295 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 3.0 Formwork | 3.4 - Concrete jointing
30f0280c-7630-5e20-8cc3-7d1e60b5e405 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 4.0 Reinforcement
2dc4f6ef-4a62-5955-884f-5b11201198b3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
61f2c801-47b5-555a-9c5e-c2c097606ee7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
3daae067-d8af-5b57-86f1-79e334fa288b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour
04330a96-e02b-5d42-b18c-b8d9a1a6a6b2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
3fec6792-1b02-562c-a50f-bb30ee92469b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9364c089-7b08-582c-9066-dfc5df381d16 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.2 - Placement
493a8839-3ccc-5559-81ed-d504c6e13765 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.3 - Slump Test
c5c7126d-7ea5-5bc0-830b-efb808562a0c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
017f9b51-99e4-5d2b-a1a5-51a5eabc4796 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
cbf57f57-203f-516f-968b-22c0bbd74a43 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
7343daac-9e02-56c6-b883-6f7d622a9ba8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
59e47338-3eae-5746-91c6-2652dd8d28ab |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
5e25f246-dc22-56a4-80d2-d1ff1899487e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
1a365106-9605-5ce9-8e55-849a40ff7429 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion
cbe671b1-cc94-57ff-ac15-9d3ca40c68c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | 6.1 - As Built
d443773a-2fba-5cf0-a4b6-fe712b371a29 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
59e13e17-6dd3-5b81-ab46-dfdc29b10d68 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | 6.2 - Concrete Test Results
fda0cb6f-65ad-5ecc-9e8d-61976ba6839e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | 6.3 - Concrete cracking approval
a570543c-1d4e-5cea-897a-9460cf85c6db |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
4713f169-d193-52df-bffd-2508e68fffc0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | 6.4 - Concrete cracking repair
38dd7401-31f2-5f9c-a33d-1923b3b0b427 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
eceefc91-93a0-479a-931c-57133250ed5f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | 6.5 - Leak Testing
7728bfa4-7a1a-5ea1-b492-7a2688b4012c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-042 - Firewall Foundation | 6.0 Completion | AUTHORITY HOLDPOINT
2bef480d-5a6d-4654-bcd5-4a7b57315da0 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1
f07e758b-57cd-5bff-b34f-302a6660a90d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 1.0 General
7598a073-292b-5dfa-aeff-183c3cf3aa62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 1.0 General | 1.1 - Material Submission / Approval
192337f1-d36b-5eca-b2fc-35e5cf0df17e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 1.0 General | AUTHORITY HOLDPOINT
514b34f5-7b24-5f85-a1ca-d23736eede71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 1.0 General | 1.2 - Determine lot size
61b575f0-7dc2-56c2-b574-3412159ce607 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 1.0 General | 1.3 - Permits
48844e73-4e54-5c67-85e9-811e86f50c63 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete
8b4a7090-9ba7-572e-b773-30952d7d2d0b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
6137900f-2989-553e-b2a3-b3b086e630b6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
82b43445-18d6-5e3b-b952-94806d4f7268 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
d104123c-d8d0-5a4c-8b71-fab924754cd7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
5e5dc47a-d2dd-5128-92a9-eb4113401725 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
752ee224-de98-5af2-9f13-590dbcb2846e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork
2aa1ee39-1f9f-551d-8d15-29f7f83cabee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork | 3.1 - Temporary works requirements
0930e2bd-a74f-52d1-932b-8e27e91696af |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork | 3.2 - Pile Penetration
1480676d-a7de-5112-84c1-d2988825e97b |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork | AUTHORITY HOLDPOINT
72cf254a-e60e-5f9c-9b4c-fec2a2e0db26 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
840dd7ed-cea2-52dc-9260-a775b59a356f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 3.0 Formwork | 3.4 - Concrete jointing
8411341f-b51d-534f-92db-1959a69cdccd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 4.0 Reinforcement
20280df1-0cce-5275-8e8c-48cc08d49992 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
92d46fd7-406f-5422-87cb-ddd61ea1c9ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
39597e11-f08c-5919-835a-0d70843159ea |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour
2bda4297-5a37-5c53-8989-fb0db0ac6aa9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
34873cbd-efdb-5950-bd33-8b76bcf0c7a5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
23324597-2bd3-546f-bd68-dfbd529a4e65 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.2 - Placement
15ba2d91-9349-58a7-8143-08026de487d0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
b4dbbbd7-7efd-5649-9398-d3ae0f99f223 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
70bf60cb-2b74-50d0-9cac-9b0079880416 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
7cf09743-5d91-5f5a-8d29-dabd940d6ff7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
a288dbdf-d82b-5eb4-bb8b-d22f064c9a6e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
0a16fe2b-0398-51f3-ab65-1ccf6cac4a6a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
dbeb9584-0de0-52b6-8ddc-08d6e2417240 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
92086b7a-881f-53ef-80bf-b41678b63b90 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion
d3472d06-0b43-503f-af83-8cace37dbc6c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | 6.1 - As Built
61c04e7c-a56c-5145-84b9-dc6eca97e654 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | AUTHORITY HOLDPOINT
b94ce5c7-b871-5a79-8bce-e844b9ef1906 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | 6.2 - Concrete Test Results
34f41a4c-97ce-5f14-8c87-fff7636d6e24 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | 6.3 - Concrete cracking approval
e06f174b-631d-54f2-acbf-deb67e550108 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | AUTHORITY HOLDPOINT
98822229-4ac5-56f7-91b3-341389425a23 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | 6.4 - Concrete cracking repair
02735465-e1ce-5f6a-82b6-7c5c970255ad |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | AUTHORITY HOLDPOINT
fadabbc8-6f34-43d4-b76e-b3fa4cb56816 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | 6.5 - Leak Testing
7c7318ad-d1ff-5bbd-a8ef-a4e22ff30f08 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-043 - PAR-01 Pile Cap F1 | 6.0 Completion | AUTHORITY HOLDPOINT
cf8bc32e-4666-4fe9-8219-6ec4c2a90592 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2
f50bf48b-fd76-5307-b8c7-901d8b55fd28 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 1.0 General
ae9a06f3-2438-5109-b9f8-0b240d0e8815 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 1.0 General | 1.1 - Material Submission / Approval
5facde1e-710b-5315-96cf-50c8a0c8e4f7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 1.0 General | AUTHORITY HOLDPOINT
9cd3e222-bd29-5f83-828f-5865a2dbd8e4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 1.0 General | 1.2 - Determine lot size
649745f4-71b9-5ec3-ae38-6a83c86d9ae7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 1.0 General | 1.3 - Permits
0e85f5e6-e563-5d23-b616-a35bf106ccab |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete
6b78baf8-4641-5462-a70f-290fe68a658f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
831f9a86-3f6c-5c15-913f-35afa26c022d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1a69b89d-5ff6-513e-8c47-f22e532a6f34 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
8ba76ea9-1902-5743-9585-fc3b74f983c2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
462c3f87-ae43-53ec-b754-fef89d550111 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f5da7dcf-eed4-5135-be36-177d5b45493c |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork
e07d7be3-647a-5f70-bc7a-ff78fac1ec94 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork | 3.1 - Temporary works requirements
0e715e86-dc30-5385-915e-681f56864a65 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork | 3.2 - Pile Penetration
5860a2e2-9819-5db6-954a-51592bd0fb7d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork | AUTHORITY HOLDPOINT
513597c7-b4f9-5f02-a476-ef06fe161e90 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
474d044b-f198-5cc2-9f69-5960ca9d4c8b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 3.0 Formwork | 3.4 - Concrete jointing
c81a9ee8-d09e-545e-961b-b65991aa4011 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 4.0 Reinforcement
77a8b09d-81a1-5d45-93fa-eec76b552412 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7867bf3d-47ce-570d-bdd0-0211526bcf32 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
579c96f6-bf2e-5fe8-a9c4-f66584a190f6 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour
fa3fa0a6-06c3-5cb5-9f52-593c1cdee5ae |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
6bb3cda2-6e35-59c3-a9e6-42d7feb55927 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
51157400-2ba0-551d-9ddb-eddda0d0abe7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.2 - Placement
1549387b-1058-5ddc-8e08-8bcf2f3c38ce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
e7ecc442-fd55-5405-a028-4a7bb6b7c754 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
2fa7daa4-a437-54c8-aece-8bbae00e8880 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
362071bd-cbc5-58cb-8f36-56fe8143fd1f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
010594a1-5e75-5b04-9b6a-7c0d781e9ff5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
1765da3e-9982-500b-8740-5907b49d61ba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
168bc332-5afb-5259-8621-ffa320cac94d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f3b3afe8-c3c2-5f47-931a-0bd51bca1cd8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion
32016865-32d9-5604-8501-12d8e4cf37fb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | 6.1 - As Built
16172209-2e5e-5f2b-b099-0c28a994f53c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | AUTHORITY HOLDPOINT
13caf229-0928-5f17-b898-e930c1f800b1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | 6.2 - Concrete Test Results
cc82449f-0857-5131-aa1a-9fdfbb982963 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | 6.3 - Concrete cracking approval
6c8615fc-2990-514e-abdd-78739fd13743 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | AUTHORITY HOLDPOINT
1b340789-4d3a-5a29-92cf-7ba7001d1033 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | 6.4 - Concrete cracking repair
4b1680df-7d6e-58dd-ad06-4a1bc710df37 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | AUTHORITY HOLDPOINT
02d0e7db-3a4b-49c1-972f-7eb17e4608ab |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | 6.5 - Leak Testing
07ae45fb-222f-5521-9bba-34fe859c4bc1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-044 - PAU-04 F4 F2 | 6.0 Completion | AUTHORITY HOLDPOINT
8b0d6477-681c-4927-9c46-dc8b806890a7 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS
e6e88f58-e32b-5ca2-bddb-3af51ab19d6a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 1.0 General
4ef2f711-400c-5fad-9328-abb0472f72e4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 1.0 General | 1.1 - Material Submission / Approval
52d25f60-a737-535f-98ba-1ed0da27f441 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 1.0 General | AUTHORITY HOLDPOINT
0b178af7-c278-53f8-ade8-dc93c89a7a6f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 1.0 General | 1.2 - Determine lot size
baa1bd90-4a8e-5892-a960-cf46fad6c5a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 1.0 General | 1.3 - Permits
9f2c0ea2-fbc8-5c54-ae8a-521a7337457f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete
c742bf97-6946-5ffd-9f1c-716547600623 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.1 - Set out
b864cca6-e555-58a7-b219-7eeddbf40ba7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
f9e4747e-99d9-5cf9-b425-5c4c18a2781c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
80b86d95-9aa9-5f91-a949-e49048e54916 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
e2e37cb0-3176-5b7b-a65c-3fb14fd19356 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
557b9ac6-f6bd-502a-bc33-25c4b4569553 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork
bf757f40-9f89-5bcd-afe6-f7269d2bb5a8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork | 3.1 - Temporary works requirements
ff2708d9-5756-5604-b9a1-15ef23d78ef6 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork | 3.2 - Pile Penetration
2e86214b-56b5-562f-862e-21a16bf28db7 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork | AUTHORITY HOLDPOINT
d1464628-2bbf-57c8-a23f-9ac8b5bb3945 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
007d3a4f-fb2f-533a-a184-eae89d819389 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 3.0 Formwork | 3.4 - Concrete jointing
c402e359-ad84-5b99-8ca8-875c37edb4f0 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 4.0 Reinforcement
349332da-913d-5e79-a4a2-bd93578d0089 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
d6ee9dd0-52bd-5d4b-a87b-60862a7360c5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ca0081a1-c884-552f-b0f8-f880cedd8726 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour
c30ab540-ceac-5ef5-a67e-36306ea0f116 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
accd67ad-d7e1-542a-b8c0-0b7c120cdf81 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
6b034320-8875-58fd-b986-f242d50da074 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.2 - Placement
a4d9483a-353b-5696-bda4-bf6370eab4ba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.3 - Slump Test
ccc1b0c7-1443-5a76-8061-1a11f4d5c00b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
3f31aa63-167d-5d40-b9a3-9be9c196ff1e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
971a01e2-441e-526c-9a94-10a99e3d595b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
ae6c7c8e-b3b8-5670-9756-fc68962491ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
f180e8b6-1843-5c37-a52a-1127d9b263ab |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
b5082a03-29bf-538c-bb97-402d345f805f |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0899d419-a48f-597b-a16c-a701dd21da5b |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion
e2316e08-2f2c-569d-b9b0-004ed29b57ba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | 6.1 - As Built
dd2c6684-cac6-5cda-8da3-bae1d1f4e025 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
10e6cfb2-e1df-5d29-a0db-604b3da9d28f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | 6.2 - Concrete Test Results
c77c9eb4-2617-5c5b-9137-0e607cc71d4b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | 6.3 - Concrete cracking approval
c8e964b2-dd54-57b8-859c-7f848d603438 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
4973c105-8cfe-5140-adac-c94746b7ddaa |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | 6.4 - Concrete cracking repair
56f4100a-fa57-51d5-8669-a23e0c366748 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
46f550a5-5721-4f6a-b468-e39bb80aece0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | 6.5 - Leak Testing
a81ee82b-fafb-5cbc-8922-ca15ede2a42b |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-045 - POC54 - EXTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
06b223a2-294d-4624-9d01-a4185ce353b7 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South
709905a6-b1d4-589d-a4c4-82ef2f782f7e |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 1.0 General
ecc23648-744b-5298-96d8-f83d6adadfc9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 1.0 General | 1.1 - Material Submission / Approval
f34d2ce8-2ea3-5168-9be7-ed76e88666e6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 1.0 General | AUTHORITY HOLDPOINT
a6f47809-e163-528d-9d3a-d33702f4de22 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 1.0 General | 1.2 - Determine lot size
d9500777-7862-5dd9-a5a8-aea15bf850bf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 1.0 General | 1.3 - Permits
3e178ed8-01f9-5b0b-a6fe-73665e6d6468 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete
51869468-226b-5a54-a027-8aa318988c23 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | 2.1 - Set out
0f037e5b-54ec-51eb-9965-e9a42ea4f223 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
b1278676-f3fa-5ef8-9856-b21156cffc4d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
c509a125-118f-5b47-8f08-c74ec5d4b4ba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
24a3c554-11ef-505b-a35b-f9c92edb9270 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
8611aa56-d1b3-5466-bcf5-2dcb84e4c780 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork
fb8b5763-bc20-5a24-8348-47901c9cb551 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork | 3.1 - Temporary works requirements
74a9d83d-c298-5702-a29b-20dda2548b9d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork | 3.2 - Pile Penetration
304c4c58-d75a-5339-a2fe-7be6d2ad77ec |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork | AUTHORITY HOLDPOINT
928ebf55-5c69-53af-b19b-9ef10c4ce45f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
82bd32d2-cb8d-57e7-9abe-611f8f835452 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 3.0 Formwork | 3.4 - Concrete jointing
00982cef-fcd3-56bf-bbcc-c5df0a766891 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 4.0 Reinforcement
b3db30b4-260d-5010-aa51-0eb8727301f7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
990b6a8d-11c7-57f1-8d21-ebc3e29d8112 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
c537fd5e-3c00-5634-b27a-fe92e79ef906 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour
b35e5652-5e28-51b0-984d-61f18b5c0561 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
2260b4bb-bdba-567a-865a-81e31e0b2faa |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d9c3b191-873d-5935-9b7b-59021f483b34 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.2 - Placement
fdfdaeaa-a9d1-5030-97a7-f68c04e0b741 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.3 - Slump Test
ba4d486c-eda1-518b-bbd6-7d2e919c7022 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
05defb40-d048-5814-9c47-ec268b0939ac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
41894b93-9846-5ea4-bd05-b4e2d2007b6a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
f315b4c8-998e-518d-ba29-9a2415a16d8e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
654ac55e-be87-59fd-ba85-d57feaf73a4d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
ddad3a5c-5fd1-5a87-9902-1d0b1bdb53b7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
1d11b575-1321-5ec6-bfb3-4d49a8df2894 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion
fd53d826-c814-55c7-80f5-68f01e27e4f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | 6.1 - As Built
6095f567-fbcc-5c13-a272-b912226a85b0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | AUTHORITY HOLDPOINT
2672ffcb-f733-54c8-bb41-0531c6708a35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | 6.2 - Concrete Test Results
e5086686-7ac4-5a5d-8eae-1b8e4dc22cb1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | 6.3 - Concrete cracking approval
c69009ce-7591-5b9b-93a8-3a3f6d3e6b41 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | AUTHORITY HOLDPOINT
260587c3-3042-59f9-a243-2f0dfe803fed |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | 6.4 - Concrete cracking repair
984cbccf-11e4-5112-b991-b8526192090d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | AUTHORITY HOLDPOINT
9916eb80-4aac-498a-be77-76e469f0bafc |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | 6.5 - Leak Testing
5b23e73e-edb9-5a97-ada7-623a156dfc6f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-046 - Heater Pipe Support South | 6.0 Completion | AUTHORITY HOLDPOINT
1f6228f4-21f4-4509-ad78-14b7ed9a68a3 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B
42dc9bd1-39f1-5788-b901-890463954d4a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 1.0 General
77dd1ddd-acdb-581a-88a4-4df484483ddb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 1.0 General | 1.1 - Material Submission / Approval
a9812440-5a37-5625-996e-ebd5148e66d1 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 1.0 General | AUTHORITY HOLDPOINT
d4e27ac4-70ff-5847-9905-8ccef9a80c96 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 1.0 General | 1.2 - Determine lot size
323f9cf0-cde9-54f6-8961-bf6cea9715b5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 1.0 General | 1.3 - Permits
72fe6677-8fc8-5472-9430-e807b1b1ca09 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete
fc971c64-3270-575a-9060-4fd020ef8974 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | 2.1 - Set out
0e95b5cd-bbdc-5ac5-a224-830734a16645 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
3cefa2d9-a5f5-58e7-9ccc-5004457dd9aa |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
72b39040-98da-5823-a375-cc1e61d3715d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
481f4475-2958-5332-b4c7-201e34be26f2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
755ef3ff-69c7-5779-8167-3eba09921091 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork
335acd70-2dbc-5a16-85cf-29a4a7740d1a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork | 3.1 - Temporary works requirements
a363b22f-8bfe-5f33-ae43-61f994103cb9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork | 3.2 - Pile Penetration
0ac9b93b-9a64-5a72-a7e6-0c75f619988d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork | AUTHORITY HOLDPOINT
09a88bad-c180-594a-b39e-94c0fa95026d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
a04d86d7-215e-5737-8aae-65a73810a724 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 3.0 Formwork | 3.4 - Concrete jointing
fbfcfc77-1f3e-539d-b6b5-358f62377276 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 4.0 Reinforcement
c1d3b81f-5042-574a-9dca-30554a75c5d2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7638f26a-dad8-5e56-bad3-27cb6a643c32 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
fb600006-e479-5189-ac74-606e287add9e |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour
c18831e1-7b54-5316-aba8-97d21191e482 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
b8be10b3-59e0-5532-b075-787cffdfb36f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
34031b18-5025-594a-b130-dbcbc08099ac |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.2 - Placement
c3b19318-4df4-5cce-833b-1f5deb9b1eda |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.3 - Slump Test
2c675255-a09c-5324-95aa-fcff0b481c61 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
23cb31bf-5657-5ef3-9aad-2c0c581f0a36 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
212d49b1-69d3-51aa-9ce9-9d3587c28828 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
ad4685e0-8444-5f4e-99c1-de96e41e4e8a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
cb9a76a3-e68d-5bba-9a29-6dad179c415c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
6f92c74f-f441-51d3-9295-348536374fc9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
52f9d476-1cd7-59a2-820f-20f06d0039c7 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion
d194126a-e022-5280-a24b-3607ab9c2ff5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | 6.1 - As Built
c5e7801f-3c90-5ad0-a6ba-21c4123a1515 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | AUTHORITY HOLDPOINT
cfd84e62-7e32-52b0-b11d-7902435942ed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | 6.2 - Concrete Test Results
a37a1425-648f-54b0-b838-fc05732cfe41 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | 6.3 - Concrete cracking approval
61ad13de-e6a3-58cb-8dd1-db4aab67c8f7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | AUTHORITY HOLDPOINT
cb19ae13-9401-5a33-98cf-dd905928132a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | 6.4 - Concrete cracking repair
ae369463-ed2d-5a2f-8873-11e785a457b9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | AUTHORITY HOLDPOINT
0003d052-6792-4077-8aab-58b6672480d6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | 6.5 - Leak Testing
fbe7ad87-551b-5ce9-a612-a9f279d36cca |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-047 - Pulsating Pipe Support K5401A&B | 6.0 Completion | AUTHORITY HOLDPOINT
3cc6783d-4236-441a-a9ac-633706a50502 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS
5b836fd0-cc27-55af-b0ec-1642679da8bd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 1.0 General
499834b5-74f3-5407-95c4-f2c9d7693aa9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 1.0 General | 1.1 - Material Submission / Approval
ac5ce6ad-67fa-5731-9b53-4e2ea3ea344b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 1.0 General | AUTHORITY HOLDPOINT
dc431edf-505f-58d7-bdd7-afcb48d72923 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 1.0 General | 1.2 - Determine lot size
2908bf60-2b24-5124-b60d-c7aecc37ccae |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 1.0 General | 1.3 - Permits
0481f54e-8114-5afb-92d7-3b71cff8bb7e |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete
1819e437-3fa0-5638-9312-f12c6adb7b53 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.1 - Set out
8eb4cb93-0db1-5eac-9853-fb5d0b25a38f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
b4c7faa3-81fd-5b34-9ae8-7ecf37dc1c13 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
b00521e7-6932-5628-a971-1634f9a2ac37 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
26038c38-226b-5300-a2d9-dd26c302acfc |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
d49965ca-7332-58e1-bc46-0eeca1d7dc39 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork
62de19d7-a9f2-51f4-a1d2-de3a727e2b3c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork | 3.1 - Temporary works requirements
435c63dc-45e5-5d0d-9e4d-ed4453797ce1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork | 3.2 - Pile Penetration
9d2cf615-1db4-5894-91eb-94c83d259a4e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork | AUTHORITY HOLDPOINT
d99aa0c8-e0ce-57fc-99de-95ffed4aa12b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
7ef5c9a0-5e51-50f5-be62-2d3a35c04ea4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 3.0 Formwork | 3.4 - Concrete jointing
80c2f79f-525d-5bf4-9f9c-e7655ac50e07 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 4.0 Reinforcement
9083d4b3-324b-5a8a-b160-76f9b21c2f1f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
667e0780-4dd8-57e7-a17f-fb43b026ada1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
773abad0-6d3e-5ede-bfe7-c284fabc74f7 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour
e458f4dd-9e16-5659-a506-08047c1291f1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
2d4dc53b-0bb3-58bf-819a-f8a539f9155e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
1d29916a-b9d1-59b9-bba6-306f7f54dfa4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.2 - Placement
89c1eb70-e16d-5a44-b189-28b641a996ad |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.3 - Slump Test
7f9a239d-bf4d-5f2c-96af-a77a5392427d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
7c231a30-094d-5654-aaa4-b90d239ced00 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
0e5c0ba8-b07c-5f56-b8f0-3960d7f2816f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
e017556d-49e5-50e4-abfa-9c6a0be98f92 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
af2ed3f4-bd4f-5134-a041-d370304a10f4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
797f4ab0-47dd-51a2-8014-da6e590a5898 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b68dd2c0-eb73-57ce-b7f9-a5f1cf639764 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion
a48deb04-3f55-5525-8044-111f6f3f83b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | 6.1 - As Built
5476a632-bf32-5577-9025-b10b66dccbfe |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
187f723e-6633-51de-8c4c-f2b914b44b81 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | 6.2 - Concrete Test Results
a3036957-a286-5674-ae94-c5a513279969 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | 6.3 - Concrete cracking approval
c509d3d5-0f2f-51ce-adbc-e044036a0a6c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
f5490afe-d2bf-5557-a21c-3fa281aaa434 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | 6.4 - Concrete cracking repair
e81576b9-b3ce-537e-9ea3-9a3886f6cb50 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
f4742585-8a57-42e0-b5dc-4727b00de106 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | 6.5 - Leak Testing
135ef30c-af42-5e15-80fb-72d38a9b4d81 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-048 - POC54 INTERNAL WALLS | 6.0 Completion | AUTHORITY HOLDPOINT
c961b373-d4aa-475e-9153-4f880d403bca |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1
dfa1dc8f-1d8d-527e-a786-7a339a2e9a32 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 1.0 General
d8c5d577-e87d-589b-b361-cd6ca933389a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 1.0 General | 1.1 - Material Submission / Approval
cdb1eb71-27e6-56df-92e5-d844ded62033 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 1.0 General | AUTHORITY HOLDPOINT
b24ca5c2-da02-568c-83ca-33bb1309cd90 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 1.0 General | 1.2 - Determine lot size
e9aeda85-2917-5ebc-aa04-fc105b212893 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 1.0 General | 1.3 - Permits
11947667-f70b-5d66-9d1a-a15719238b27 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete
522d8642-7900-507a-88d7-d08cd1054d8a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
171d54a0-2c70-5e7a-b5de-c4ff53efe858 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
463dda19-eb27-5327-a43a-3bc46263fe6a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
53c378e6-2ed3-5224-aa29-af39b10d5137 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
dd9b1ad4-a17b-5302-b6e6-ef3571c4d993 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
85610738-1a68-5822-a33c-5c9782d2b394 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork
8f40a770-7200-58ba-a2bb-3b4e6bab4961 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork | 3.1 - Temporary works requirements
0adb4a58-e2b8-5f11-abf0-07fea32d6260 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork | 3.2 - Pile Penetration
f7d0eb81-bdcf-5c25-9f7c-77d2578fd769 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork | AUTHORITY HOLDPOINT
2e1c8b52-e0c1-5de6-b4e1-87d852304524 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
5c115109-80cf-5114-ba9b-9f7414955f55 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 3.0 Formwork | 3.4 - Concrete jointing
2d86eacd-176f-5e4e-bb28-f0a3b19c53cb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 4.0 Reinforcement
8098b374-762e-528a-878d-4ad438556b2a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a9f24b72-3399-5ed1-a879-0c2f7f02751a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
1e31c21f-c3b1-5837-8787-71d7bf6504d4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour
12366f0e-8db0-53e7-b9e3-c7b25851accd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
b93dbf00-1f40-5ee7-9890-59f36882677c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
fb25a04d-cd94-5437-8d83-812440340d65 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.2 - Placement
2a0c8166-5e19-5029-9a94-a0ed973109b8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
8a59e6a4-c684-5ccb-8138-4efa2d4f41cf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
9cea068b-8336-52f9-949a-f515efe534a7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
b8aed726-2014-5ee7-90d1-949d2dfd8307 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d1ed66ea-7f68-509a-99ce-5befaca9db8b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
f6610ab3-93ea-5b41-ad5d-9a516d3a505a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
a14bb2d4-a8a2-561d-935c-7d4fab85f051 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
7c29d730-03e4-526b-9104-4e072daf0b11 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion
4c092da6-a0a3-57c6-bed6-6ebedf483b1b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | 6.1 - As Built
ebcabfcc-962c-51c3-a03e-509868ebe034 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | AUTHORITY HOLDPOINT
392b64f8-f62b-59bc-89c6-06bdc4b1b82b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | 6.2 - Concrete Test Results
9a679a8a-5dff-50c4-8cfa-8b7bfe7ed5b5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | 6.3 - Concrete cracking approval
571e502b-cba2-55fd-966d-4fb35ad843fc |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | AUTHORITY HOLDPOINT
7f5dadfc-6bd5-5b3c-8c25-ca4532784331 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | 6.4 - Concrete cracking repair
4a7a40b6-770b-5444-8d83-62238d0d76ab |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | AUTHORITY HOLDPOINT
5c98e775-a462-44cd-9ae1-0b03427bcba2 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | 6.5 - Leak Testing
86da64f3-31e0-5152-9167-217ba4d8f1d5 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-049 - PAR-01 PED1 Columns F1 | 6.0 Completion | AUTHORITY HOLDPOINT
c9015116-0bfe-4ff0-8b7d-ba0acf97c476 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2
af5a1ff7-f1fc-51f8-af87-5f74212038fc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 1.0 General
fd499b36-658e-5e79-a047-784d8fa97259 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 1.0 General | 1.1 - Material Submission / Approval
7bb90f9c-f8b6-525f-a014-f1ff1bb5bf90 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 1.0 General | AUTHORITY HOLDPOINT
4bb01a7e-8dc4-5be1-ba76-2c8b04f5ec22 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 1.0 General | 1.2 - Determine lot size
296f8a18-937f-5f31-8ffd-97f7a5b36cb3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 1.0 General | 1.3 - Permits
6ad1c10d-e6bc-58d9-870e-97f5f1d59666 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete
9346962d-0a22-5df8-b162-1d737025a90e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
e40ca392-4527-590c-9987-d943c601cfd3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
91d6609d-d801-5a4b-bea0-5a1c396d4e61 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
16e3efe4-1ee9-5130-82dd-6b190275c39f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
34664787-3b03-56fb-8b82-d4350cf2bf69 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
53217329-f1b2-58ce-bf7d-15a0047f4bd4 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork
e37d5851-23b9-511e-8941-30e52600284f |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork | 3.1 - Temporary works requirements
418d738b-1eb3-59c7-873f-6a638a53741c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork | 3.2 - Pile Penetration
4a85c81f-bb6c-51ec-ae08-c7e0f977c6cb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork | AUTHORITY HOLDPOINT
b09bdaa2-943f-58af-a961-630c744f176e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
77f07e9b-856a-529e-8ffe-d35cbdc2d92d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 3.0 Formwork | 3.4 - Concrete jointing
92be8f7c-c8b0-5db8-a0c4-637a048716ff |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 4.0 Reinforcement
83e0a13f-ecc4-5675-80eb-e3fbebe4b418 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a7ce4305-fd16-5a49-8223-37137ff3b4ea |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
0861f594-b069-5c1c-9cb5-09b005e42fd9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour
c5f305fe-9292-5601-9b0c-a8f99b526850 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
50ab4614-398a-51b1-bdfc-7517b7b24f04 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
fbc15772-dd20-5a06-a61d-df6cb8283402 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.2 - Placement
72a5e34e-bbfe-5478-87cb-74d58e1aa3b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
696a3a0e-11a5-591c-95f0-abbd844dcd64 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
afc5c9cc-7294-5811-be93-18f9af41bd21 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
b751ff4c-8c3d-5bc9-854b-865a465726bc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d9dc88bc-f3fd-5ccf-845f-de7a73e7e6fb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
4e81d371-388a-5c17-84ab-45c41c058089 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
b391bfab-d69e-5db0-ad93-a9ca0b8d4b74 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c49a1b73-2c09-5321-87d7-29324a32f646 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion
7ebe3011-c1b6-511c-a968-5d5127aed439 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | 6.1 - As Built
0be92c4c-7dae-5f32-ad47-e01a998bd990 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | AUTHORITY HOLDPOINT
2d80a9cd-fa24-50cd-854f-b33e870d69ef |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | 6.2 - Concrete Test Results
a0ee1950-a848-514c-acb6-fdae6bd3a9c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | 6.3 - Concrete cracking approval
530d40ea-2be3-525c-b644-ecdccaf7399c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | AUTHORITY HOLDPOINT
2612484e-0192-570b-b4d8-645be7e536e4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | 6.4 - Concrete cracking repair
74995f67-07ed-5c07-9c30-345f45fedba1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | AUTHORITY HOLDPOINT
39e5287a-dfc9-40bf-87e6-a444bcaee083 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | 6.5 - Leak Testing
f9a32403-1d1f-5602-9572-a451af27e710 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-050 - PAU-04 Pile Caps F1/F2 | 6.0 Completion | AUTHORITY HOLDPOINT
4356560f-99db-4ed3-b1b5-401297c55c26 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2
bd5193f3-24f8-586e-a2c2-6de9eb50c54a |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 1.0 General
37cdf809-cde4-5842-83dd-07e06a1682de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 1.0 General | 1.1 - Material Submission / Approval
4343b4a2-bf9a-5290-914d-7b68177eba76 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 1.0 General | AUTHORITY HOLDPOINT
8df5bfc9-067a-5749-b06c-7e8e5cb9ac57 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 1.0 General | 1.2 - Determine lot size
987571cf-fe4c-5155-839f-aee3f1f1505f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 1.0 General | 1.3 - Permits
7832694a-93e5-581f-809f-c97bc9d9c86f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete
11bd5fb0-af24-5dd4-b21e-d21af2628e40 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
a8691524-e787-5c3e-a99f-cbc92d8f76e9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
f9b41bee-a3ce-588b-ae7f-87d216db6a46 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
c5a98ba2-0be5-5cfe-b36f-a2545dbaba4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
06773d46-470a-51eb-9d46-51ff91792f54 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
6fe272d1-5b8a-5787-8f43-1213629dd261 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork
93d4e97a-d53f-56ae-9bed-537d841b1b1c |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork | 3.1 - Temporary works requirements
a7b5b828-94f3-572a-9c7b-075029f02820 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork | 3.2 - Pile Penetration
f519ef6c-d85b-5198-ad81-e4d1ecabd589 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork | AUTHORITY HOLDPOINT
9c139854-1644-592e-8863-01d97c921d3e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
9289c8bf-6363-5260-9b41-6e694822f522 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 3.0 Formwork | 3.4 - Concrete jointing
1dbcd7fa-ad51-5310-b3f5-197c293f9e44 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 4.0 Reinforcement
1dd10110-593f-5cb8-aa01-a81a9444e58d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
e88760c7-ad0d-5f96-8d31-843a23d46c7b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
59ca3259-7d3a-5422-ace0-61584d22d59e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour
26b4f8c4-692c-56c7-87ed-b4026257c220 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
b4fb8928-3e21-5f0f-96d2-847f1b118755 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c4c0d8dc-88e7-5fbb-9799-78b8263c6933 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.2 - Placement
4029dda6-f1a8-56d5-8d3a-96ec3c6daf25 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
3651c35e-3af7-5752-a566-9c17a8c94d58 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
ccd59a05-44eb-5889-8101-da05ea09c07d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
1f3c9e0b-0f73-5a9e-b944-0c61a32fdf69 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
67cb5c24-cfcf-507f-b017-bea66f59cd0b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
18084d92-3d06-56c6-af39-56bddf245ea0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
118dc0c8-62cc-5d80-9f3a-615a19f0a9d4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
89d956c7-c8d6-5b3c-af29-0c6089f84ade |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion
bde99fab-48eb-5813-8885-000db62ef2df |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | 6.1 - As Built
edbee24a-431f-564c-bb59-7892c6ff8310 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | AUTHORITY HOLDPOINT
83905455-2bdb-5ffb-8f2e-71d09b370cc5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | 6.2 - Concrete Test Results
41f36dbe-fb08-5fb5-b5dd-c9cc6f2d57a2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | 6.3 - Concrete cracking approval
40d0ab56-e082-56b8-a777-f3575b61e3fc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | AUTHORITY HOLDPOINT
4de7cd25-932a-58c7-aa5a-ecc3dd55da33 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | 6.4 - Concrete cracking repair
9fe60deb-14f0-5437-bcd2-7faef718b748 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | AUTHORITY HOLDPOINT
3c9a377d-57b1-4a85-8fc1-fd1bdd555bb0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | 6.5 - Leak Testing
dfe21ebc-8d6a-5638-9688-7dcd632612c3 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-051 - C5402/C5404 Tie Beam Ped 2 | 6.0 Completion | AUTHORITY HOLDPOINT
4fea84d2-9d7f-4e68-80a3-72c8fe69d733 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals
125ff801-9f1b-5dcb-b4b8-e394383858d9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 1.0 General
47ca7da0-b266-523f-8455-2f52a8b2c9e8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
6e7b4d9f-e9f6-5fd0-a8b6-057bb6bf0a64 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
249a8bc1-e9ee-5f7c-8bc0-97fb9d956526 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 1.0 General | 1.2 - Determine lot size
419a8d6b-9659-5977-b139-7790e24ae995 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 1.0 General | 1.3 - Permits
7e656e44-6907-504f-989f-1e43527a7285 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete
3866f929-56ee-5c13-9779-b549c2e6b150 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
32d8172b-2ce9-5ac1-adf6-8636254fb08f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
04be9458-fd58-5741-939c-b60a82a787c5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
85294998-477c-5111-bc1f-586488c0d68b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
8e5e132c-20f4-5f89-97f5-afb4aa4be3fc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
ffb68a67-0b32-5af2-82c8-6552603cc76f |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork
1267e877-46b0-558d-96f6-571124475db0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
d3047d4e-e89c-551d-86bc-ec145fcd23bc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
a8a89562-bae8-5118-9827-bd70727725f4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
fa5aa9c7-70ac-5d84-bfcf-5c9c4d9f385f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
1e8ff8ca-3461-54a7-a0bf-304c5891f84a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
35c2b35b-cdd3-54ce-8f5b-50ed1971c453 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 4.0 Reinforcement
8d650b5c-639b-5faf-b33c-159f4d1951b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
fcec6080-2070-5356-99af-63ebd0819164 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
d3dddb7a-fdab-5c10-8027-5cb3053e5e3c |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour
f5cdaae6-664f-5909-98c5-bda9a3953310 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
55ce839b-6def-5e3b-93ab-7b85a1635b1c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
afdb4993-f58d-5c40-9ad1-14f84b2c5e99 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
b39ac768-ee11-5035-97cf-8a725157e1a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
eafd4595-8e2f-5ae2-b395-53127038a719 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
f819876c-6ef0-5238-9058-72d84eedc0ee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
c215a317-cb65-5647-89fa-f3535c6e1d27 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
f347eba3-9837-57d0-b940-d5542c3bfa0c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
a7aa0aba-727d-571f-9c7f-f79a59d68916 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
e7212801-e93d-5b5f-94b0-91eee9d8d843 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
752945ba-ea7e-5962-9faa-1558f2169984 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion
9b33d42a-751d-5e90-8189-f76738132dca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | 6.1 - As Built
8289b107-fa5f-5bce-9de7-a2ae0c6ded1f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
e898b592-b67b-5656-99e2-9a914d4f71c2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
26f47a07-78de-5e94-98bb-c317a8c72ce8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
4d9a7828-8608-50b2-a028-dea2470a284c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
85042652-39ac-51cf-ade1-76a408868412 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
48a8a497-9df5-5b1f-825f-ec5731b73c68 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
cdcd1172-f49d-4427-8e0e-79d696540b3c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | 6.5 - Leak Testing
a23bfbe7-58ff-51f5-9472-08e3b630ac66 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-052 - PAU-02/03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
8f097674-74d2-44b5-93ba-02a042ead897 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall
70f8f931-77ec-5d75-a915-867f0cea65a8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 1.0 General
377cd3e7-5ce8-5ecd-b21d-f7a0b47f9a39 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 1.0 General | 1.1 - Material Submission / Approval
d8987f9f-0368-5504-916b-59c88561a44f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 1.0 General | AUTHORITY HOLDPOINT
ee172e05-1f05-5213-aa80-0fd4707041f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 1.0 General | 1.2 - Determine lot size
971798f9-3ae0-511f-a4f3-fe24edeab86d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 1.0 General | 1.3 - Permits
c1f93935-165c-5e5d-83e1-d945c1b72134 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete
47cba6ce-3215-5eb0-af49-5254f08053c4 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | 2.1 - Set out
946ac92d-efd8-505b-9b5b-855c7540f6f5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
7b67d811-f79d-504c-be7b-010a182e5429 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
448d3595-266c-55d3-8ef7-473037f6af85 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f1a65e40-507c-54b3-a816-d290cc6d709d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
848cbac3-e4c7-52b2-9b09-ea64937e7a24 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork
6c5fb045-0e0c-50fd-8642-c4f629889ba9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork | 3.1 - Temporary works requirements
06daaa69-8516-5042-8273-b2f869d4c1bc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork | 3.2 - Pile Penetration
cbbb2e5e-20b7-5084-b855-36e777788fb9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork | AUTHORITY HOLDPOINT
0c77aecc-0677-571b-a0da-1ad31f1351ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
fb781d39-4a6b-5acd-b6f3-754d4aa79a60 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 3.0 Formwork | 3.4 - Concrete jointing
aa015046-cf38-5334-b494-fca8fa489704 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 4.0 Reinforcement
3c5c461f-e81f-5f89-81d8-a6afcb250847 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
00493805-f804-5b81-88ab-58c2d8442575 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
4663d9c1-e43a-5e63-8950-5fdcd23bc29f |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour
70eab1ca-fcde-5006-b1f8-c2f27bdaabb3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
fea8a8e2-04f4-55ad-ae39-2820956abfe5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5ad271ef-2682-563a-ad2e-40a587a4e6c5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.2 - Placement
3cae9536-fbec-597f-9e46-432f327f955a |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.3 - Slump Test
deb98714-f3f1-5493-8dbf-9aee444f5af0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
d81b1e2b-0d16-5b4e-951f-021e8c9662e0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
73e3c3c7-9ab9-58fa-8d72-6c940ed75650 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
d31c91fd-267c-595c-aa21-68ac3494a481 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
cecf29cd-a30e-5d18-9fa5-be560068d4a0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
89e0e148-cefa-5d05-bfa2-333cf4b920a8 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
79d0708b-afb5-50ef-aec5-b31a99ab9989 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion
8b0a5d1d-3b91-5b5e-930c-aa15426935a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | 6.1 - As Built
70459895-121f-50d2-8d28-ff2dad5bbea5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | AUTHORITY HOLDPOINT
ac7aaf73-e034-579e-88b2-542f644e64ea |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | 6.2 - Concrete Test Results
cd80b0e6-2d50-57a8-94e8-efb143dac1c4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | 6.3 - Concrete cracking approval
cceaaf2d-b157-5c31-8bfd-9e2e02c1ec53 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | AUTHORITY HOLDPOINT
508b7c6c-e3ea-501b-80a7-8fab3d084294 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | 6.4 - Concrete cracking repair
fad83c2d-60ce-5859-b9fd-1a121793e920 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | AUTHORITY HOLDPOINT
e9405135-2969-4f41-bdbe-11971ed0798c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | 6.5 - Leak Testing
f2f587a3-b596-5856-a9fc-a66fe3a5ebcc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-053 - Firewall Wall | 6.0 Completion | AUTHORITY HOLDPOINT
5fff9f52-e18f-4951-9252-30d792c5be6c |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns
4e206d86-3783-58a3-a7df-48e19548b2fd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 1.0 General
9a603ed9-c745-5108-9ed5-f7fc20c5c113 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 1.0 General | 1.1 - Material Submission / Approval
1b215712-46ac-5fd7-b11a-a5259fb2dd08 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 1.0 General | AUTHORITY HOLDPOINT
1aa9d8c0-7670-5b98-bb2d-6df15f2cff7e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 1.0 General | 1.2 - Determine lot size
87f5705b-bfec-59ce-a80e-3c8db117a87b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 1.0 General | 1.3 - Permits
5d11c632-fc16-5903-8b7b-5d27bcd615a9 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete
d16df8ff-20b3-5c95-94f0-0db8cf74ad8e |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | 2.1 - Set out
cfea3655-f3cb-54c8-a3dc-ca4109983f11 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
4ddc4549-e2a4-5211-bec6-c10b06b83573 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
29535630-67ad-5080-b29c-cf0fa0c689b1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f4bbdbc3-c71f-5383-9d98-2541cf20c8e5 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f6741bec-ec8a-54e4-a010-b45f4cad7241 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork
70a75fa0-4c9f-5c05-b7ad-565934bca82c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork | 3.1 - Temporary works requirements
d322fd52-d49b-56ce-a487-4810075b2404 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork | 3.2 - Pile Penetration
8dec2436-24a9-5cb1-b3cf-e600d5b19341 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork | AUTHORITY HOLDPOINT
ca6874dd-7f3b-59a3-9589-03545d557241 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
2442b5ea-c48f-5bbc-922b-7d383a307a99 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 3.0 Formwork | 3.4 - Concrete jointing
d6be4f3d-b81b-5ed6-8a90-dbdda57c9818 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 4.0 Reinforcement
cbf7d277-9c24-5c4a-bd80-2fa2a462e125 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ccc3e1bf-e3b0-5d8a-8c82-e1ed3b43ea7d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
77cdca2f-f8b4-52d0-a0ec-97320df7fb5e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour
4fc884a1-cfdc-5947-a268-c7fb1aa2c4c3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
61f5153d-6f30-538c-8f59-3d4c1a49a75f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f15d0e5f-fffd-552d-86a3-011de247c42a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.2 - Placement
716130af-62d0-5f51-86db-a39df080a2e5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.3 - Slump Test
90ccfaa2-a1d4-5576-b2a0-61087e323707 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
6f045f1e-a164-52bf-89de-022bcb2d7ce0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
64801bdc-1717-5f1b-9c9d-6b4af105b478 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
47b3addc-d37d-50ee-baf8-cf197c89a3a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
4123e0e7-07a4-5d4e-bc4f-df21ff203821 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
4f0b2b7c-f193-5cae-aac5-184482f114c8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
acba1d1e-c63d-5be1-903f-859894b94913 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion
4cd056d6-1d85-5595-a667-99f25f53eb0b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | 6.1 - As Built
6365a84b-1cc0-5bd8-8074-970fd1af832a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | AUTHORITY HOLDPOINT
81c60e53-8410-576a-8042-dbba31532037 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | 6.2 - Concrete Test Results
d2802036-d9a8-5d29-946e-4f0f96ee0637 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | 6.3 - Concrete cracking approval
3e7eb7f0-1379-5f3f-b39f-f7c0380939c5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | AUTHORITY HOLDPOINT
618e0ffa-ee37-57ef-9536-37ac6d7e0c5c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | 6.4 - Concrete cracking repair
b3a86f5e-75e7-5daf-a1f7-cb2e699fa6bd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | AUTHORITY HOLDPOINT
afc32b55-bdea-4110-9692-d5aa75d81770 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | 6.5 - Leak Testing
fa233aec-651a-5a31-a482-0a71d617ca6e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-054 - Pulsating Pipe Support Columns | 6.0 Completion | AUTHORITY HOLDPOINT
0c098f22-e8a1-4ffa-94cf-1e811f7aaad8 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming
ba35a1a0-23db-5009-b1ae-f4a2658d0d5a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 1.0 General
c29b8ceb-6475-5a81-beea-189bd13911b1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 1.0 General | 1.1 - Material Submission / Approval
60c38646-f2dd-5beb-b338-938499695272 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 1.0 General | AUTHORITY HOLDPOINT
22b712f9-7ed9-5da8-adde-3094c2dbdd50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 1.0 General | 1.2 - Determine lot size
915ad832-0eac-5552-80c0-496a45a3d16b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 1.0 General | 1.3 - Permits
2b0a9b3b-58f5-5e06-b31d-cf16a4fb628f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete
7d886f88-56e1-590b-bc12-0d798873de13 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | 2.1 - Set out
562b8dde-dfca-5c12-a429-39ca0e2dac35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
00848cda-92b1-523b-b112-461d763db44b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
1f6a51b7-1f52-54d7-9851-18cc42899bec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
62a5c74f-28a4-522c-abb5-d7064dc73872 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
8f7190d1-3a53-5067-be00-a7ac62ad354b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork
ed4a6597-68d5-5b42-8b6b-534db157fb44 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork | 3.1 - Temporary works requirements
602dae9b-6755-5ceb-98b5-a98cdeeaeb2a |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork | 3.2 - Pile Penetration
f34e81f7-baa7-5b61-97bc-0928edffe774 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork | AUTHORITY HOLDPOINT
23905a95-6650-5423-9345-ca78d0abdfaf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
ed194d91-d069-535d-8970-8425ec78a4b8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 3.0 Formwork | 3.4 - Concrete jointing
0e8b9b49-e84d-5111-bcdb-45a29db0a6b8 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 4.0 Reinforcement
c89a7b15-ecd0-56d5-b0a9-edbbf7676e97 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
974a54e0-c9eb-5913-a345-a93b014d0971 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
f97a084c-2ca7-507c-8689-1e73f2a94215 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour
f6ad3870-2247-5fe1-9bd5-aa4a6a353436 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
cd4867c4-a7ae-5096-a6ac-eca5bfb37ecf |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d4302203-cd1d-5c10-b9df-85c7ea20503c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.2 - Placement
fa91aeac-d771-5fd4-936f-8d0fc0cb9ad1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.3 - Slump Test
915b2c9b-2d72-5b94-acbd-957e9d6a29e7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
7c53f396-48f2-563c-ba79-10ce0099cb87 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
229577f9-7bcb-5261-8aae-9a9894153417 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
1abe5022-85f4-5887-8a61-6c05d2b617d3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
bbeb08f4-9535-581a-9446-0c4549905bd6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
ce447fc4-7558-5727-9cee-4c528b27e582 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
67781819-8256-51cf-9a42-ecb6ea0ca854 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion
ba46cc7f-9115-56f1-b3c8-9869fb7c6540 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | 6.1 - As Built
618ad9df-5af7-5426-98bd-49e89f513a48 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | AUTHORITY HOLDPOINT
378f26b0-d0ad-5357-946a-706f810e0f8b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | 6.2 - Concrete Test Results
248fd5a0-a20c-5a44-b761-9f6927a2dd20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | 6.3 - Concrete cracking approval
6f99c0d4-77c1-5037-be57-45fc12fdcd78 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | AUTHORITY HOLDPOINT
8cd1dd92-8ad7-5d51-9011-ce94e9bee903 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | 6.4 - Concrete cracking repair
c874309f-85eb-58ca-addc-e53c15c528aa |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | AUTHORITY HOLDPOINT
b425d33a-f0f5-4583-9804-9ed0883ae375 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | 6.5 - Leak Testing
ddfb3d6e-f487-5131-a7f5-bfa1cc9a2444 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-055 - 201-MH-001, 201-CB-001, 201-CB-002 & Skimming | 6.0 Completion | AUTHORITY HOLDPOINT
d1afb568-2a80-43a9-baf7-3cb54ffa8c1f |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap
3a5fe68d-6bcc-55b4-91e6-f64d778ea97a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 1.0 General
d0885704-a235-5464-86ce-40aa1800a268 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
9ff1e63a-030e-50d7-861f-d8f15f31a2ad |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
7a592e04-b8e9-58e2-aaeb-b1143bc82caa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 1.0 General | 1.2 - Determine lot size
2e375f39-6e16-5abc-b110-1680cd4c3274 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 1.0 General | 1.3 - Permits
3aafd83a-0b9b-5264-9764-903f3867d788 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete
440799c6-7ef3-5232-a024-97b0fb526406 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
961c1296-8dd1-5cb2-94ad-62aa92d34d77 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
814245d4-e00c-50d8-b92d-d398cb269066 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
7992b7d3-a157-505a-86ee-61a7f10f85cf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f9fac7c0-4559-5edb-af2b-70dc1b3392fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
64f6b7ed-100a-5018-b8f1-c4a5a0c17a06 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork
f74543d1-46b8-5511-b622-d993e807c977 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
d98da0f1-ffe5-5709-801c-0e2e291afeb2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
893ad517-e1f7-58a2-9ed2-4ca08cfc4476 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
6211ffac-1522-51d8-a0a4-f0f6f1921baf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
0d7da4d9-fad4-54fe-9971-c9c97fa323c0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
066d6f07-6b67-5d18-9309-64abab69dddd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 4.0 Reinforcement
39f59b8a-757a-5b8d-9c6f-8fe2b4195797 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
812785ce-bfe0-561f-a335-42990b986da2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
bd0e96a2-1e92-5b9b-84bf-5210f807e22c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour
2ebc1643-82ec-5779-a239-7ba89522aaec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
ac512061-562b-55cd-84eb-84ae1e62be87 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d3ba92ba-f1e8-5c2e-b715-40282dde1494 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
472a4e42-1bf1-553c-b4a2-875834784fba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
c44274c9-4750-5523-ac9d-64c2006ff4f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
4ae8d9d2-b3f7-5200-8e3c-1d6ce7ed80ff |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
7cf337ee-23e1-55c5-8e05-7011d2695206 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
53ce3d43-9a8a-5033-b588-5f4426f63e95 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
94833300-b4c3-5b7c-afd7-8187f9102b35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
cf2d4d2c-e04d-5b1a-bb9c-21eae44a60ad |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
54ac930e-ffea-58dd-ac13-ccd5c5578552 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion
c22df0c6-958b-5e3d-99ef-81de74a36b32 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | 6.1 - As Built
d6b4010a-37ac-5beb-ad0e-1f62e2c75b3d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
39b32635-49c2-5054-a10a-10819ee806ba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
8e8d00de-e7bc-5e63-bdd1-eb36bbd9f496 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
bf3340b6-dcdd-5bb6-a88f-47ca2b8b77c0 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
b13fc947-bdc1-50ba-adfd-16d22af8f28e |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
fe54261e-0fb4-5c69-8423-4f21c55ebb7e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
e73549c6-608d-4326-b4d5-de991791792c |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | 6.5 - Leak Testing
27cbefb7-0c7e-5fb5-84d5-94812e198163 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-056 - F5401 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
1f0ae3ba-70f9-40c3-9fee-c8afe8f6dd5c |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1
1a77ea7e-8935-558e-8f25-a9ec27735365 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 1.0 General
f8799042-cff0-56c2-ace7-906b79047dae |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 1.0 General | 1.1 - Material Submission / Approval
04580fe7-0078-5110-b198-9e2976be3f30 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 1.0 General | AUTHORITY HOLDPOINT
c7f006d7-5575-5167-8019-0bd3f08bce63 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 1.0 General | 1.2 - Determine lot size
dd0b2bd2-0a7f-5e1b-bae1-86f503f64651 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 1.0 General | 1.3 - Permits
7dad657b-1030-5fc0-95ea-938cef345a72 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete
692979fd-0c90-5a77-9606-a936053ae76b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
dd8ec591-6999-50c5-b70e-2e3018070db2 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
da14b0ca-d6c4-50d1-a70a-f9373b667b1d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
2d083cba-5532-5ca3-b9c4-c585395f65fe |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
a2ed6a90-ff3a-5064-b589-aa0e19690fe1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
1f3e5a66-2fbd-5536-8dbc-24be0e534164 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork
8e09a4ef-9a4f-5b77-8472-379bcf24fb34 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork | 3.1 - Temporary works requirements
b9872e6e-5286-5aef-b839-4c85cccc7b7c |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork | 3.2 - Pile Penetration
232e1685-3b24-591d-98af-95ff99f4527d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork | AUTHORITY HOLDPOINT
d893d3c1-8141-533c-b610-1fab1542b769 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
8b8a6fe2-7905-54b6-a133-49184563b569 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 3.0 Formwork | 3.4 - Concrete jointing
a69be777-336f-52ed-82fe-97e497d91864 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 4.0 Reinforcement
91086d55-32ac-5c4b-b1ae-ffe08c3d296f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
5bd6e442-a189-5a7b-a88e-3fb544cc57ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
68820828-59ff-58e1-bd29-5c9635ab2c89 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour
8c215200-59b3-5237-98a1-8573c52bc7ef |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
2630d737-4d43-5df0-b481-986472f0a774 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
2ec1f751-2310-5257-b9ad-cea1165634a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.2 - Placement
b875a0f9-fa34-5af2-b453-2481d17302d9 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
5c5153b8-0d9f-5b5a-9ff6-44f6fe49725d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
61879347-c99a-510f-862f-0d4299d99b4b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
f9d7608b-f04e-5f5e-9ecd-d44111fd6617 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
867dd190-2f19-5806-bcd7-64ef9b1d2810 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
cc1cfaee-a7f5-5717-8d45-8f4a0ac07bed |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
f5e9d2de-11bf-58f3-b9a3-45721ba46cd8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
b5e7caf5-2594-5b9f-93ec-4b1f648c1898 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion
0be52150-e5fe-5ca8-82b0-e7767dee36c6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | 6.1 - As Built
3aaf52ac-1586-5017-8aa0-6d5132c2b73e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | AUTHORITY HOLDPOINT
abbdb8ab-fd5b-5f35-bc06-5fb71d8d88e0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | 6.2 - Concrete Test Results
ef5b3276-d7f3-591c-9c6f-f6f4a83c9aca |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | 6.3 - Concrete cracking approval
2b3efec6-690b-5ea7-958d-802152d4fe0c |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | AUTHORITY HOLDPOINT
2fef263d-d463-513a-a7ed-b8e7fd27f14f |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | 6.4 - Concrete cracking repair
7585bcc0-b49f-5d8c-999d-781dfd47e060 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | AUTHORITY HOLDPOINT
4cc2bbef-ef04-4663-9bf6-ff0d56652103 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | 6.5 - Leak Testing
b921c719-076b-55d9-89f0-4eb6ed195e8d |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-057 - PAR01 - TB1 | 6.0 Completion | AUTHORITY HOLDPOINT
d04a0f40-b214-4477-a0d1-04e1fbd7b1e0 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED
a440691b-dcf2-5a30-8333-ac5f9439b6f9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 1.0 General
3668870a-db56-552c-93ec-e79116d747a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 1.0 General | 1.1 - Material Submission / Approval
2bdb0f7c-5691-52db-91b5-74abb7152c64 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 1.0 General | AUTHORITY HOLDPOINT
5c10f0a8-f48f-58e5-9701-9d6713a837df |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 1.0 General | 1.2 - Determine lot size
1bbc1d86-cf2d-5358-b29b-3604ee8e507f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 1.0 General | 1.3 - Permits
8b9c7a0f-b342-565b-b2b0-b68ae1d94378 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete
ae787636-0f43-5291-a94c-7b391a5dd350 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | 2.1 - Set out
69c8f110-6817-54b3-8928-ad0e56068217 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
141fa5e7-ea6d-5546-859d-afb658af05b1 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
54601608-5a12-544c-9a51-d19114298251 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
89423b95-0567-54e8-8c07-0c3c8c164f78 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
d99feee8-59c7-5ea8-ae1c-3e8cb250bb4b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork
85fc60cc-b45b-5ed4-ae78-b9da78fe9bc4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork | 3.1 - Temporary works requirements
fb069aa1-cd7f-596d-ba34-627590963170 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork | 3.2 - Pile Penetration
a293d7b6-264e-531e-8df2-6a6ed06813fd |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork | AUTHORITY HOLDPOINT
421740f1-8279-5e12-a3d6-2761488c0879 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
6c777cf3-09c7-538c-bbea-024f6426710f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 3.0 Formwork | 3.4 - Concrete jointing
a699cc9c-6182-5858-b7cb-acce88ba53b0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 4.0 Reinforcement
a3fe4e53-535a-564b-9cb2-f37504e181d1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
4b6cfdff-0126-5f12-b4ff-0aec6e9621e6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
0afbb47c-d8ab-50bc-b755-6eb30a907b4d |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour
14e7a6f5-dde1-5a9d-b678-148beabb7c0e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
84a23179-4912-5594-af05-79094553b39e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d6de5a9a-1727-5c56-8f4d-5157df049a5a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.2 - Placement
dac99395-bb51-5f1c-a2ef-c6dbc96f0a17 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.3 - Slump Test
4ad2cfd3-6bc0-5551-9cb6-5dad467b9fd3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
f6a052cd-9dc8-5ad3-92a7-88076384181e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
6eb06868-ecaf-56ff-ba65-29ae2e392bbc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
230faa5f-0b6b-503d-8ef2-7914b311ad90 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
b26d9b49-5144-5a7d-a4ee-c8491805a0a7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
f85909c0-2dd7-5105-a048-fec82694bb96 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
7890d371-68a4-58c7-940c-6b533e63b035 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion
4edf05ab-bf8e-5ca8-bc7e-b160bbb264a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | 6.1 - As Built
311fb3b2-ea36-5bba-bf85-fab189264a58 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | AUTHORITY HOLDPOINT
282712e4-935f-5117-97a6-06170d7309e8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | 6.2 - Concrete Test Results
058f6a89-8964-583b-b2c2-b86b6c88c5c0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | 6.3 - Concrete cracking approval
4e87cd87-33b9-51ff-9db0-257be2cb0945 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | AUTHORITY HOLDPOINT
ca1bb427-24e1-56e8-a5a4-5a750bff04aa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | 6.4 - Concrete cracking repair
298d64e3-9d27-5ae3-ae54-52d941a56ed9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | AUTHORITY HOLDPOINT
775f548a-ea44-4013-8acd-07bbb53b8804 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | 6.5 - Leak Testing
a584d518-611f-541e-a119-02ede8895542 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-058 - Firewall PED | 6.0 Completion | AUTHORITY HOLDPOINT
87afa868-a51d-4e36-818a-2bc226bdf8f2 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal
565a766c-f5f8-5bb9-9f56-731ab838c900 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 1.0 General
047bb643-b478-5da5-a99a-90855597ab87 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 1.0 General | 1.1 - Material Submission / Approval
14bcf515-5f3d-5204-8155-d2e54a6dda84 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 1.0 General | AUTHORITY HOLDPOINT
06455942-3e55-514c-a8f7-f812b4d3278e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 1.0 General | 1.2 - Determine lot size
75e4fe69-3b0e-5218-9a61-015c379acbd1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 1.0 General | 1.3 - Permits
017dfbe2-f8a3-577e-b7f7-815da2012037 |  | not-applicable |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete
eb580698-5993-5951-a11b-0e81220de237 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | 2.1 - Set out
d6c664ca-ad24-5e28-a1a1-bc4c6d07897e |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
10f4e73e-b4f9-511d-b2cd-131e4101be93 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
bf56a3a9-a226-51d1-b16d-dcbd29255c07 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
0f89bea4-1f4e-569a-89de-bb90b011379a |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
1b82c8ff-756c-5aeb-9e1c-b196f44b8452 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork
e9742d11-ec36-5490-8102-92440023c30a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork | 3.1 - Temporary works requirements
3debc7b2-1763-59f8-97d5-0423e3f2223a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork | 3.2 - Pile Penetration
2cc6cf86-2bdc-5962-bc64-59094865be34 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork | AUTHORITY HOLDPOINT
0a073faf-d125-5ad9-96ea-4028ac810adf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
9f973837-65ef-5c9d-8837-a16b2d30a750 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 3.0 Formwork | 3.4 - Concrete jointing
ebf93d21-aa22-531a-aee2-11b79192743f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 4.0 Reinforcement
9ec55c5c-a440-5f4e-8a78-5c9bf6c3585a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
074258dd-9431-5afa-927f-7f7ef6e557fb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
6bd31b6a-675f-5354-bfd9-5930dffdc965 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour
41f53900-a749-5463-bdd8-fd6f95cb621f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
38e8ce76-fded-5848-9dd8-845a00764a49 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0fc8489b-8b3a-5b33-88f1-4a5223db7365 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.2 - Placement
34faf565-d0ac-535a-8a58-991911dfebcb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.3 - Slump Test
fe3a3e38-74c4-5d4f-bdcc-ca827cedc15f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
63840b25-6995-5607-a248-af445d60464f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
20b680a2-325f-54bf-a779-f091d45c5d1a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
04be4dd0-2b32-5887-abc8-d6b5edbab6da |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
ebd1b42f-f536-5b0e-8fb9-8085e2c14df7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
e8fadeb3-d254-5495-8eb8-df7ad4e602be |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
30f66f5e-2987-5131-a7f3-eafed3dee6e1 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion
a7021e8a-58bd-5c75-b782-dd0369398c06 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | 6.1 - As Built
c6eaba09-54b8-56e3-bc34-6fbcffe4a940 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
bc1031a0-7fb3-5fef-be96-10f859e431d8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | 6.2 - Concrete Test Results
4d5be212-2016-5804-9c4c-2173a6523918 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | 6.3 - Concrete cracking approval
4d43e7e2-a26a-5891-b9a5-baa94cd34994 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
7cfe891d-ea34-544d-835e-489369faffa5 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | 6.4 - Concrete cracking repair
f5a7ec4c-772a-5abc-9fe3-0f5bf0f42475 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
a3ef2145-e26a-461a-9643-672a54dde108 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | 6.5 - Leak Testing
a71b2869-9239-5022-93ef-abcddf031a4f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-059 - Heater South Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
290e8ab9-9990-44c6-8213-fd219554fc63 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports
f401fe3e-c14f-5cd2-bb1b-4f7f1d9440b9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 1.0 General
6be7fc51-c54b-5765-bac1-d5bdb7909cd5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 1.0 General | 1.1 - Material Submission / Approval
c7a22dfc-56fb-5d60-8dd6-2c60da574ff2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 1.0 General | AUTHORITY HOLDPOINT
5fa47dcd-1ec7-53d6-b186-97753a88a2ae |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 1.0 General | 1.2 - Determine lot size
a96ce975-02e6-5d5f-8d3d-e87e4b029351 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 1.0 General | 1.3 - Permits
5432cc74-c905-5475-9d37-bf47e0ce76de |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete
81b4e23c-c0c5-53f0-adaa-b1d6b00069e6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | 2.1 - Set out
31e7fd59-219f-55a5-b9d3-5b027ef9a8b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1f8d09aa-6c4a-5be6-aa84-9c74e873c13a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
a7eba328-0c03-5a80-b026-6838907e82d2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
abf3718b-5e22-5875-a535-d505e238217a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f074551a-3fc0-574d-b2d1-1e6680a64b16 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork
3945fb51-fb15-58aa-97f7-72d86c630174 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork | 3.1 - Temporary works requirements
15cda2bd-0fdd-512d-a6b4-7cc4fa106ab3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork | 3.2 - Pile Penetration
c194312a-6b88-5898-a635-2717001526fc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork | AUTHORITY HOLDPOINT
c7f0e5bb-5f04-5ba0-8d0f-bd47300ecfb9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
fe18eda9-5167-5be8-9b13-a04e0b5a66ec |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 3.0 Formwork | 3.4 - Concrete jointing
77003199-2465-5842-862d-0a681f1e53b5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 4.0 Reinforcement
a237e5d6-8e08-5124-a763-654caf74437c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
6a3b515e-3343-567e-8a6b-cb2c2a062d92 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
6b6bc73e-8a75-5dd0-9a60-d079af5522c9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour
9a9c2b4f-51b0-5b8a-83b1-7bd58b0090db |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
d2c22b03-7db1-57df-aaa3-31b573bd9c6d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
8199318f-9fe2-5f16-86da-609678b9a5b4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.2 - Placement
d750aae7-faeb-536f-9f79-4fb2e0eb545c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.3 - Slump Test
7b60a857-3809-5dd4-9669-e516f089ecbd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b96bd9e3-316e-5543-813e-cb757aa43006 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
ee2c1b21-cad7-51e8-a4a8-f61596315f27 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
028ea15d-019b-5e7b-8070-331a078c41d7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
c60fdc0f-6046-5ab4-80f1-60a7f18cbca5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
04bd042f-0e04-57ee-b7ed-a7eb12160ecb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
2aa900a3-c9b7-5c4e-a58d-cb70785db7cf |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion
be700c9c-c36a-579a-9886-5a7474b81b4a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | 6.1 - As Built
34f39621-540e-55d1-97b6-560bde70cce2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | AUTHORITY HOLDPOINT
f159a338-d400-5607-9114-a5ae7d97b255 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | 6.2 - Concrete Test Results
6d20c0db-e791-5d2f-a076-2a02050fb851 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | 6.3 - Concrete cracking approval
064ce763-f14f-5f25-b703-4ed06a76dccb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | AUTHORITY HOLDPOINT
87c5a555-4ae0-5ef2-8701-8e13010b4de1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | 6.4 - Concrete cracking repair
0c0f307e-da62-55cd-842f-715382d6d92c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | AUTHORITY HOLDPOINT
e8068739-789c-44ec-a632-6319b2b5b38b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | 6.5 - Leak Testing
bb25fc5e-491f-5d8b-ae72-5f66257f0783 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-060 - R5403/R5402 Reactor Supports | 6.0 Completion | AUTHORITY HOLDPOINT
1bc851f3-fffd-4da2-bc16-2b7158241c4e |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank
7dd500f6-8a12-5fc5-a639-1561efdb8e6d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 1.0 General
272df3a7-4fe2-596e-ac1c-3713fd5c0986 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 1.0 General | 1.1 - Material Submission / Approval
127b2221-6d35-5cf2-938d-09f44faaa340 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 1.0 General | AUTHORITY HOLDPOINT
924b9285-8133-5fea-9e17-87bac4de6abc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 1.0 General | 1.2 - Determine lot size
6fa21288-0e1e-55b3-bb8d-dac6fe5e3324 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 1.0 General | 1.3 - Permits
9ac2d55b-fec3-5b53-b0be-63963ea52bad |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete
a41e005f-2d2d-52c8-8360-76c380415a19 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | 2.1 - Set out
7d93b59f-f244-5e5d-ad85-3e0bd8087803 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
da780cdb-07e6-58ae-bad5-223be9f026dd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
2c8e8b88-a369-5b68-9037-e22821824f50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
82107aa5-d6ab-50aa-8fca-729d3a766caa |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
799eb6ca-953a-5add-9038-aa8dad4622fe |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork
c4158042-7db8-502d-80a6-7d39510b7ede |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork | 3.1 - Temporary works requirements
269435a7-acde-5903-94b5-96866f2eb9e5 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork | 3.2 - Pile Penetration
07243bb5-543e-55c3-9c95-ac43f08ebf39 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork | AUTHORITY HOLDPOINT
fffb90b0-0e34-5c40-9290-0dee9a775634 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
68e07992-e15c-5272-9c7f-201ae0389ca0 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 3.0 Formwork | 3.4 - Concrete jointing
15e23db7-65b9-5ea7-a689-ec6334d32f6c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 4.0 Reinforcement
4eed9a56-27fa-511b-96b1-15608bbe42e3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
535169ab-ef65-541b-ad26-513fdd760d3a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
c7d1e890-4964-5fce-9fbf-32c1739b32c0 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour
c1b1debe-10b8-5567-a62c-0ed8328d283c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
9299646e-a448-5db8-9329-00f8a47fdfe6 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
59973186-91f1-5fb9-b579-83c71e7d765b |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.2 - Placement
352e4737-730a-57a8-bc84-7c5d7bdaca0c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.3 - Slump Test
9b946eab-1921-5573-9187-1fbb7650ca6c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
dfdefbd4-edba-5f86-ba77-12ba92d9610c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
49528f82-038c-5c8b-abdc-f4a40568600f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
c4d558ee-c26f-5350-ba93-7d5075373785 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
25133572-e7f9-56f8-8bda-1bcb232d05e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
7ac85910-8f67-5d92-ae07-048cc1376727 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
098b6b94-8f90-5ac7-988f-8044a00e68d2 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion
1940dee9-d297-5d4b-ac72-39be63c40179 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | 6.1 - As Built
9e754b6b-c76f-5682-a37f-33ba729a1a86 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | AUTHORITY HOLDPOINT
fc8518a7-b0c5-5d2f-ac65-6bf09790c49f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | 6.2 - Concrete Test Results
36310798-b6eb-51c6-9fb0-52738c7fcc4d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | 6.3 - Concrete cracking approval
d811403b-46a9-5a5d-966d-819065bf2310 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | AUTHORITY HOLDPOINT
3bb641f4-3c4c-5ecf-96c3-97611d7c70ae |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | 6.4 - Concrete cracking repair
f06cb4a2-0d9f-5ddc-b92a-360135fab753 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | AUTHORITY HOLDPOINT
54c5f97d-de8c-4e31-a401-2a3f4f05dc40 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | 6.5 - Leak Testing
ee35e8de-78fe-532a-9379-91b9a8a4abba |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-061 - Duct Bank | 6.0 Completion | AUTHORITY HOLDPOINT
f6698911-d60e-4a38-90c3-f780e7fc83fb |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns
255520ce-c9b6-5876-b227-cffbe24319a0 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 1.0 General
43c1957c-4230-5e17-844e-f2287f341480 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 1.0 General | 1.1 - Material Submission / Approval
33a66101-028d-5fda-805d-023dfa6dd26a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 1.0 General | AUTHORITY HOLDPOINT
1183e410-26c6-528e-b75a-0a8904785d78 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 1.0 General | 1.2 - Determine lot size
dffa1b4e-ba30-51b3-96cd-01775a9842a0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 1.0 General | 1.3 - Permits
bf31cab7-9b5f-5d5d-a2c2-3e8997e7df03 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete
9988faab-2483-57f9-b183-a66f54d31ddc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | 2.1 - Set out
783d828f-de62-5fa9-b70b-3202a53bb95f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
87b4b535-98fb-5164-8005-17bd45208b34 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
91984ac1-594f-540c-ac76-f4a5042b42ee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
3234e491-1da5-55d1-a3db-91a048dc357d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
f57c25c3-33ff-55e7-8855-a2c24e3adf5d |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork
57deff46-0c1e-514a-b866-8fa992c3e888 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork | 3.1 - Temporary works requirements
4c6ac2d6-5fe0-5b45-a532-d234c8efe07b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork | 3.2 - Pile Penetration
e08158b5-887f-510a-bf15-3460b1c15768 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork | AUTHORITY HOLDPOINT
34d75429-d2c3-5830-8f2c-8f3b201eef89 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
c4cefc80-531e-5692-b264-37783f2500ac |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 3.0 Formwork | 3.4 - Concrete jointing
41920d46-44a8-5d60-acfd-549b06572394 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 4.0 Reinforcement
f74c9c68-d4e1-5a72-b00f-ba957f247a30 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
432f3e02-83ec-5626-a66b-09edf4fb0eed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
90d2660b-a8b0-50f8-ac00-814ed0e2044a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour
7b242a68-6c75-5dc2-ba8f-3d6fc46cdd21 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
2b89deba-7419-591f-8d76-2d34b918e349 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
59048422-73b0-588c-8e0c-4922f5c47463 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.2 - Placement
dac965f3-cdc3-510f-90b1-a3c0811afd63 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.3 - Slump Test
440a4180-a122-5fc8-8dee-6b62fb3ddd4b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
a93097a4-8641-541e-9e41-b56e08131577 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
09711a00-c877-584a-a3ef-5816221f42c3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
61cfb595-e4a4-5dbe-a7c6-4a822a3f3128 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
32d3894b-4dca-5c39-b635-b8d6ee91ff6a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9b6aecc5-b423-5302-9f86-4058ec3b3ec6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
33e27404-fc4e-5898-99dc-1672fc189544 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion
2aa458f1-4e5f-5042-b95c-e39ff3bf7b6f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | 6.1 - As Built
b117926b-c3ab-5db9-869f-e744d58ac5f9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
9f40d4d7-3b9e-52cf-aec9-d1014f7b7922 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | 6.2 - Concrete Test Results
735c0d04-e28d-5c21-a72e-71671db471c2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | 6.3 - Concrete cracking approval
10853342-e1fd-55be-92ad-b814c9db9ce4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
67711d29-de06-5f61-a3cd-35dd33976aca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | 6.4 - Concrete cracking repair
8802bdbd-ec9b-55d3-ad87-925447ef5535 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
1ff0b2c9-bc83-4e4a-8144-9f91da9f26d2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | 6.5 - Leak Testing
b811644a-94d3-569d-b734-1dc4f01e7db0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-062 - F5401 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
161e3a8c-c415-418f-9976-dc64b744475c |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap
a21fcd65-8e9d-54c1-aeee-0e328a8e5cd7 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 1.0 General
1326006c-ecdb-5c01-8ca0-eb9583f88eda |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
1830b4b0-c65c-53cf-9809-311b233b66e4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
74e46290-ef78-5192-9970-fc2dd03f8156 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 1.0 General | 1.2 - Determine lot size
f3256dd9-0616-518a-ac66-aa3174de6865 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 1.0 General | 1.3 - Permits
04fcd73c-93f2-51e8-a448-65c668c5f6d5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete
1bef045e-e2b7-56b5-bab3-489acdbc74f9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
d362557f-095b-5ed5-a680-eb515b6d70bc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
ddc5fb52-13ab-5f8f-a4f3-27990647842f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
bcae9387-4965-5941-9fe7-e00d1be84ef9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
28372a03-52e0-5e64-ac4e-32f8b8e5a4ed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
83eebd3c-5036-5a77-bf27-fbd0b20e0099 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork
bc7ec000-1c34-5021-b66f-d310a8cee65b |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
fcdcd042-8b8a-5e3c-bf34-0e11426d45f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
142d805a-4f5c-55f9-8543-7163d5054abf |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
5233823d-92bc-5bd9-a7da-ede49f0b1832 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
8e1b0baf-5382-594e-af0b-170c100f29f6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
a9a5c60f-cb19-51c4-9f84-e8309cf8673e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 4.0 Reinforcement
7447aea1-9f3e-5bcf-9792-c39e2bf91e8f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ba1f3fea-90b9-5dd2-9c90-440dd17d8189 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ce9399fb-aab4-5183-9a7a-055f29fcd5e9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour
75e9aa82-f1ba-5175-a3dc-621e5db58f4c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
74a62813-4eda-506e-856c-f3970bffe3b4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
0bf6fab9-abcd-55fa-9e07-77581c6b381c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
9609c58c-3010-5039-ae81-5c95fadd67a2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
d0a7cfdc-577c-5a70-a167-80753d109435 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
f2828605-3b84-5593-a728-45cab4f93c9b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
268dd347-8151-5a7e-a90e-3a53182985cb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
59baed1a-9e70-5155-871e-3aeacd8fa037 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
0caa9bf7-7ebc-575c-9ec4-271a2babd2a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
858d0a18-68c5-53c1-8afd-d0ef11948759 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
4303dc16-2705-59a2-bdf5-206606158bf1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion
27075454-bba8-55a2-a68a-61127e3d8a8f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | 6.1 - As Built
b693b174-e24f-5490-8d19-8a6d7f2eb471 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
0197a3fa-ea7e-5f44-b11b-5fd1489d1237 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
99b0df7a-b927-5cae-9c72-c59af5239764 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
b7438804-a881-565d-9d64-b1a7e7f5d87f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
a60c49f3-49f8-5399-8a07-7a0cde2acb78 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
38c6e129-3e59-5770-b588-2de99e02a84b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
2268c916-8940-4507-bc8e-333530159374 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | 6.5 - Leak Testing
bde55080-91f7-5d9f-9f15-2c4c5150dc84 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-063 - F5402 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
6541a527-0fc5-4821-a0d7-3b583decd335 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns
5a5659c2-ec8b-50e0-855a-54b13b6c98fa |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 1.0 General
bbe89db3-8f7a-5713-abbe-0f5c0b75e1c3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 1.0 General | 1.1 - Material Submission / Approval
d09e04e6-1d33-5aea-a955-203ebadd8124 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 1.0 General | AUTHORITY HOLDPOINT
7519beb9-1be8-584b-9c27-d46abe92cced |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 1.0 General | 1.2 - Determine lot size
f82f71a8-0be9-51d5-b0b0-5e85c48e7f26 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 1.0 General | 1.3 - Permits
5e55fbb0-de52-5285-a675-b9fda5d9f55f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete
e2aae81d-501a-58ea-a114-e729375f7b04 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | 2.1 - Set out
24284758-51d9-562a-ac55-d33e7057b8be |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
1e6e1582-53ee-543d-a52e-dfed5895e29a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
027d9fb7-c0c6-5abd-b71e-9dc658648d31 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
1bc02257-4a25-5295-9117-c78ad4f89f61 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
834b429a-bdff-5e2e-9e93-2360b7f22b1b |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork
43c50713-2cf8-56ee-8448-4d7e111cd838 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork | 3.1 - Temporary works requirements
089e66eb-0f05-53e9-a6c8-8db40b1bb1d5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork | 3.2 - Pile Penetration
9bc42671-3a48-5dbc-bc34-d672766c7260 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork | AUTHORITY HOLDPOINT
e41aa150-7ab4-5ffd-a2a8-7dc3afe0df15 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
c7fc3859-1b9e-559b-9732-8a3bad28668b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 3.0 Formwork | 3.4 - Concrete jointing
ffa13635-2cb5-539e-b611-15af62d232bc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 4.0 Reinforcement
0f507557-5c43-5717-981e-f0ec92e8b1cb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
09ae32ee-b1f6-573b-8c19-a317da7e61f2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
831b0f04-03f5-5f09-81d2-04be0a378687 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour
42832dd4-94eb-599c-bc41-32e2a2f001e7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
d8389a59-bd71-5b1d-af34-31bcdc95ad82 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9ac60ee9-c189-5428-ad39-840d7884490e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.2 - Placement
6cb6cc6f-ef63-5338-9902-88e11cd02068 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.3 - Slump Test
d4f4408e-af65-5376-9f3d-f24c296b4435 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
2e761cc5-84a8-5bea-b6bc-7a7cadc29d40 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
6bf7a8cf-297b-53b6-8e78-f76cdbee358c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
8b60b26c-56e8-51d0-b334-c8f8c2aac766 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
71f83403-b9a2-5a61-8363-e06e38c6eaf4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
d4bd53b1-bf7a-5eb9-8f4d-31dda836c940 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c5657aa2-209b-5b4c-8c24-7a8200631829 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion
aa8801dc-ccbb-5803-b47b-26c45de1eb6e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | 6.1 - As Built
b34726f9-401b-5a1e-869b-659edbdc529d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
94567d50-4ffa-56c5-bdfe-1ad1ff3904c2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | 6.2 - Concrete Test Results
708e4252-5dc4-5dae-bdc5-fbfd5bb67c10 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | 6.3 - Concrete cracking approval
a0625ff3-92aa-517d-be10-10c7dc3527e1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
bb26d868-812a-5375-af98-509bf7877a9f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | 6.4 - Concrete cracking repair
f0420dce-4916-56b0-aac4-71a527f41e3f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
39871365-b044-4992-b8bf-70bc61b267b1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | 6.5 - Leak Testing
27d89725-b96c-5917-9ed1-0f07e95fdde0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-064 - F5402 Columns | 6.0 Completion | AUTHORITY HOLDPOINT
cc725e82-88a0-4a70-9dd9-ffc1e46e0c63 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals
10eef3fa-f6ab-5d44-a15e-b7edfc8c5686 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 1.0 General
87275b54-7d31-5631-95e5-f1a4f6582d2b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
18ea2413-7827-565d-b7c5-16c70290f97a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
340d78fe-a475-5f54-b03d-73b414f5e52a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 1.0 General | 1.2 - Determine lot size
5e584533-7f32-5783-be88-21dd9bcc0ae4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 1.0 General | 1.3 - Permits
006e44eb-db95-5a88-a993-e36a15f4f0bd |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete
61407221-c8f8-5a30-ad2c-c8c7252d4b88 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
bfcbbcfb-1223-5749-a7f9-6d4c193a1da0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
d2c5e7f5-dc9a-5293-8de0-1bbf5d7a796a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
0396959f-1d3e-56d1-b285-e18134a366b8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
5397b199-d747-5eac-b6ee-82cf92174722 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
c9dfe0f6-0a74-5bff-a530-a6952aec32ad |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork
ebe16517-4c25-5c50-81bb-9231d443f564 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
19370666-04f0-5be3-aa47-8c80abffe46d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
7ffb37e2-be80-5525-a9b6-ddfc1612c456 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
a8606fd6-b0b8-5b22-b39f-fa75b7174815 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
d41a3622-9360-5178-aae8-a7bc0420b0f0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
4c5815f3-f882-55db-b325-c24e57de122c |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 4.0 Reinforcement
a693432f-3288-5766-a6b6-6073a41afd59 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
342d8a34-e728-52ea-9d0a-71c47074acef |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
4c5907ec-acc5-5adc-b484-d704a8aad408 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour
f2410bd4-7a56-53aa-b8c6-097a9da66118 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
32f998e7-7564-50f6-a2ec-8e35656aa877 |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
78d65924-e696-57b2-a2d8-884e9afd83ee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
72eea2e4-5a6c-50e6-9674-e2d8f7d4cb60 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
61b44b51-94cf-53b6-8a67-4216180058d6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
8037ea4b-cb03-5115-83fd-58487bf78171 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
8d0df8fe-9d66-58ff-a362-79b409715d31 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
fc9b7fed-ca2c-5eb3-90e5-453eea36340b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
d99e30d6-bb89-50ae-aefd-689df8205058 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
2c1448d0-1d19-5478-9620-1b06798ca1ec |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
026d0663-faca-59c6-a36b-d134af89cd29 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion
2a4ec8e4-589d-5288-8c1f-73f1e29f55e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | 6.1 - As Built
ddabdd96-215f-5a32-8cf4-25241206670a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
1f596c3c-6903-56ef-a1ab-96ef313553fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
92991997-58f7-520b-82e9-2064f711abca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
463c8e5f-9648-5bad-9f51-d285294e2d40 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
08c32cde-14da-560a-986b-e5b9cb9a820b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
05dff745-7eb1-5427-a68c-488cff262bf4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
63e037cc-9aad-4203-8b6d-080bc699c24a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | 6.5 - Leak Testing
425650da-86b2-5e61-9066-0b5d444259b0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-065 - R5401/C5401 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
3ae49ceb-6fdb-4c6c-81ca-dcae81a23cb9 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals
6c996a92-8c6c-59f7-a9cb-ac165c856d39 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 1.0 General
dc20b957-1946-5c85-ac3e-d8951b163493 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
70cb05f7-0125-5e2e-b33a-b9c51088a454 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
e6abaa44-8ad0-5877-b8e1-5f6c5505fbe5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 1.0 General | 1.2 - Determine lot size
5f2df386-244a-548c-b68a-3e11f9ba0818 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 1.0 General | 1.3 - Permits
a1c550cc-8827-5221-bf1d-c8d59099a42f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete
e47324f5-dcd9-5c31-8587-9221039641de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
29db13e5-754e-5a6b-a67d-f9018a078a56 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
17210196-a2c2-5527-80ac-5043e82ddebc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
7bfc3335-57c9-5b82-990a-ac0a0808adce |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
75560bca-a5b4-51b5-a72a-fc68865ea09d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
1ee7b88e-df2a-5497-aba4-417185c526c7 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork
83fd4426-9b2a-5c8a-9c07-8c2618497f09 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
a29e1d92-d935-5eed-9d87-2438fc330275 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
f636efac-1537-59aa-b3dd-dbd65d65cd5a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
d28e0475-2e9a-581a-9ab3-b7d8a0a81baa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
7e322513-f4bc-5e14-95c8-e95ef7634922 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
fdcf36e7-c889-5311-84ef-742785411b1f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 4.0 Reinforcement
7852e83e-81fa-57bd-b89e-76021820086b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
e0c902db-4085-542e-a70b-bde89e128153 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
22996395-0ab7-5286-b506-c554fd143e78 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour
a9a1c21d-d4b3-5304-a5ba-3d10ce2e237e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
a3115403-c45c-56b5-baa6-0a37730429fe |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e9554cb8-195f-56c9-8c10-0d7a4bcc6758 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
40772bf3-0e94-5bef-85c7-8737197fecf0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
bc6c5d4a-5888-5917-b80e-0de182b2d200 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
8d2986fb-3b41-5025-abc5-94d2a3a060b0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
bc3191ae-09a3-5d0d-a3aa-eca5d72e191d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
99317c4c-ee0e-5cf8-803b-e819db3d74b4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
75bacc16-2c9b-5477-8e1c-0384184c8605 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
52f81af8-eb83-55a6-8380-3e5f2b3eff37 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
06bb2a12-84ad-5e51-b0f5-11c84a91af2d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion
2aa530f1-ae38-567c-b4c9-12d42867fc0b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | 6.1 - As Built
c267c806-ba67-59a8-9713-80f36afbcf95 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
cd1f205b-043b-54bc-8fab-e950036f824f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
66cca0c3-6a1c-5d97-a72c-db18843ea148 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
054136c3-e507-571f-ac01-2316fba09df6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
d273529d-ba75-5870-9bbd-a6ff353fa8f6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
3b6f4287-3065-5929-9cc4-0b092af75fdc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
54104954-a0da-403c-a791-3739bd07355f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | 6.5 - Leak Testing
5c748d9f-b9fd-5b1f-a6d6-49a15263d6d6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-066 - PAU01 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
6c1e05a1-5496-423e-ae5c-0b7d748955e7 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals
95cdddc3-bd66-50ab-ae4b-21f7cba98266 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 1.0 General
4ac96110-53f3-52de-8f99-5f6443072951 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
58a01605-6f7b-5ed8-ba75-353484e07de4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
05142572-2114-5466-9f64-1f498232c98f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 1.0 General | 1.2 - Determine lot size
967cab7b-19e3-5ea1-81f3-2f6d6b8dd6a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 1.0 General | 1.3 - Permits
2585ff21-f79d-51bf-b5fe-362e0842c0be |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete
b63b3c46-982c-58ce-b84e-9ad5074b35c9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
bf678601-cd1f-5893-bbf5-cd30c32ef3a6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
375d5e19-e390-5df1-a8cf-807f9e6db573 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
50dd1c1b-6a7a-5053-a639-bec13569f96c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
f51da705-df8a-57e8-9d22-04ff62506074 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
0a97c40f-2621-5d44-8e31-3459a1f71f2f |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork
0ffed187-f9b8-5e5f-a6c0-7ab07625533a |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
1d9fd3bf-b202-53c0-b333-f6fe82fbb2da |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
3888bc20-55f5-5173-8ecb-573ecd233775 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
8d7ced21-cb4b-5b86-bf40-f315d54a3d5b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
2ca06483-80fc-5484-beae-81569e23ddd6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
2bb15b4f-c9c4-5351-aba7-90b24173c1a5 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 4.0 Reinforcement
8eaaa813-9169-5265-b954-bb4ce47804b5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
929b7bbd-283a-5b3a-becf-891aa3a7f073 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
687e423b-db9c-5a68-96a4-900d8a0984ba |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour
e56fa6be-234b-581f-8877-5f7f2dfd7331 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
58e18c22-6aba-53c4-8af7-99d95635de13 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9fa65a44-d876-5b2b-80ca-276a066fee65 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
e23cee3d-498c-5e00-b5da-52ed9d2526fa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
995b6383-a71f-56fe-8bd4-14f4cafc7d34 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
cd9491dd-6fbe-512b-afb4-23314e63b9b1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
1303f8e5-f521-56e0-a6d9-c715b6a50918 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
1b12e154-60f8-5af0-9df4-10ff954c2387 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
a6e3e530-2e5f-5f41-ae93-7a1b3fe7415b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
86bd9609-8abd-57bc-906d-76e6ceeadfdf |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
fd11d36f-2497-58b2-b8f7-1bc0edfe6f02 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion
77a3842f-40e3-5351-b3cc-dda69643c064 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | 6.1 - As Built
03914756-1573-51d2-ac61-e7365384089f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
4f7248de-3aae-5749-8d0a-25dee69c76b8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
0a015026-80c0-5d75-b8d8-88d2d8389711 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
33764c5d-9a98-5154-a290-f106e43867f5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
605efdcc-9176-5af6-a66a-41c9b1556d1d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
90c09acd-b317-523c-b2c6-03d09650489d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
758f1cd1-c2e1-4e93-a98e-6c6786f9cbdb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | 6.5 - Leak Testing
3dee9de2-b69c-5cdf-90c6-ecfcb097fbdd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-067 - C5402/C5404 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
2fb15e07-7ee7-4daa-b97c-f34ccf21cebb |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console
df9ba197-2c6f-58e9-8f13-897c06ce780f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 1.0 General
a51f223c-fc1e-5c99-981b-d200ab048ff8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 1.0 General | 1.1 - Material Submission / Approval
88fb7118-3192-5519-8145-5a2bc24b0f26 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 1.0 General | AUTHORITY HOLDPOINT
dd8280ef-c4e3-5260-8814-cab86b9f0159 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 1.0 General | 1.2 - Determine lot size
1fba6fd9-1424-5893-bebc-d8d4664e59a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 1.0 General | 1.3 - Permits
14d10f5c-cb8b-540d-84cd-3a152f6b0711 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete
6e9e95ce-74d2-5535-99e7-2c0de47aa2bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | 2.1 - Set out
ff97c10b-ed59-541c-9994-07d4bfbe27b6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
ef7573ac-ca9f-5bed-abd3-392c62c7c974 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
b7440021-8cc9-5445-b1bd-122f45d30de1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
2ea2bb31-808c-54b5-9766-ff546db160fb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
ab05b869-2d69-5024-9efa-342651f10491 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork
e884212f-9c23-522d-ba10-224fb5270f06 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork | 3.1 - Temporary works requirements
ff7fd032-d08c-5e65-9805-89b46851e5e1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork | 3.2 - Pile Penetration
e2c37fb6-b666-52f4-ace3-b65ad0db95f0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork | AUTHORITY HOLDPOINT
6a7613e5-e234-5826-bb59-da56cfb18c21 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
81923170-b170-5def-9bcc-6dabe25049a2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 3.0 Formwork | 3.4 - Concrete jointing
39ba640c-5d6d-5870-917f-3a13db68da5a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 4.0 Reinforcement
fd603b15-2649-5450-b729-4e20976ec5b1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
6c0e766a-8d30-54e1-b835-d365bdab8833 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
cf23bf48-e5a3-5981-b924-99328bff90cb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour
ffa0ff74-02e3-5be6-aba9-d60a92cd8dfd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
c1a6187c-f926-5ac5-be5f-2dd219e5814b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d0ec1786-b7b0-5011-bb06-6f98fe9e5e81 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.2 - Placement
766f1894-e144-5d5b-96eb-1dd4d22e13a7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.3 - Slump Test
8a44b7de-75f2-57bf-a559-f44ad7abfefd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
04206ba6-7025-534f-bb0a-1e4fa2f4c249 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
70aff10b-c78e-504f-a6a7-f56bbcaea839 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
f7e8be61-2693-5a38-9ae5-89163d182cda |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
c474d73a-0edc-546a-8c32-aabd5559a3b3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
0703047e-bcba-5849-ae93-fac988cf7ca0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
94c5b24c-34b8-5f5c-8476-ef479bc90a2b |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion
6cbae92e-1c25-5815-9faa-6afdda0a2c5e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | 6.1 - As Built
7e9f41cf-4914-52fa-8094-ba53257256cf |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | AUTHORITY HOLDPOINT
cf0ad2db-43bb-5c67-8375-ee5a04e739a3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | 6.2 - Concrete Test Results
20b528c7-d9d5-58b5-94b5-a79d445b2560 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | 6.3 - Concrete cracking approval
cdc125b2-0690-5c31-8a9e-c64efbc35610 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | AUTHORITY HOLDPOINT
08ad2be5-d347-512d-9831-267c932ba78d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | 6.4 - Concrete cracking repair
f9756133-6d0c-5d0e-92bb-5b6757ef9332 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | AUTHORITY HOLDPOINT
778afacf-099e-44c4-8d02-db5fca269c7e |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | 6.5 - Leak Testing
5f310aba-c9fb-5580-9715-fd2126be3177 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-068 - K5401A, K5401B & Water Console | 6.0 Completion | AUTHORITY HOLDPOINT
ebfd6556-7c46-4f00-926b-08e522aa24b9 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01
9803d2dc-7a42-51fe-8f9a-fa6ba60dae39 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 1.0 General
6b6c9a89-63c6-5115-9cc0-6e1382044e0b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 1.0 General | 1.1 - Material Submission / Approval
31ecf741-4b0a-5c7a-aff7-d9aad61196be |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 1.0 General | AUTHORITY HOLDPOINT
1de431b0-9c61-5504-b204-9ccbc1a12678 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 1.0 General | 1.2 - Determine lot size
60ff6bc6-a031-5992-8743-6e8cb0eca481 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 1.0 General | 1.3 - Permits
f1f5d441-5841-5834-8f1b-af89cf4cc3fc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete
d2c5eda4-7602-50d5-a79f-f329114b458a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
306f4ae0-4725-5a9c-88b6-df6453b27c8d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
82ee244c-507e-5339-a5cb-79b78b131830 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
39dde0ac-0497-5ffb-9416-1811bd022fe8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
53003e13-cf7b-50b1-b78a-2967b331d2a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
c6276f2a-a1e1-51ab-86cf-177b34ce286d |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork
006fd98f-7dc6-5d2e-b4ef-47379608870a |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork | 3.1 - Temporary works requirements
1e925ce4-7e60-558b-8d2e-906e7b0d3f59 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork | 3.2 - Pile Penetration
343dbe40-23b0-5f33-9958-87ce34488567 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork | AUTHORITY HOLDPOINT
ef6018b7-5e3f-5f43-bfdb-ecb3d2ff01de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
f08ae033-fa72-549d-846c-177957905355 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 3.0 Formwork | 3.4 - Concrete jointing
8e7924f4-0de0-5d82-9bd2-89d27117e9d3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 4.0 Reinforcement
94b6380b-e015-5d36-987f-9db88cf5ecba |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
57f6a089-8ada-5387-84d6-c64813cd193d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
ecce927b-2f79-51e3-8a5a-58ca4232b27a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour
f27034ab-0e18-57c2-b57e-2d6865b52b7e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
506d8a28-6dd0-5114-9552-bdb260fb01a4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
7af11efe-b396-50b1-9a2a-5dfcc476aea8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.2 - Placement
36e4d0ad-9884-5c85-87e0-d081aca01984 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
59b8fc46-dda9-5ba3-a876-126020a76df1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
d8f3b371-5379-5c6a-b4ca-c181a0899b32 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
8951d7af-445d-59a2-8205-9005d838a43b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
9dabb7b1-0c11-5b6f-a239-f63bc48ad91a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
ab98b053-bd6b-5f22-b8a0-6edeeca57e4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
b4c1230b-abd8-5738-a848-ebfdf6b0616e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
4ed06cf7-226f-5626-b180-2a89908f541b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion
6b07a6aa-d479-5830-bd6f-dc1d95fd8a1d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | 6.1 - As Built
de9ea919-e7a9-574a-90b0-9ee4c6448fed |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | AUTHORITY HOLDPOINT
a44af488-8bf0-5371-9763-79973db7691d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | 6.2 - Concrete Test Results
3ce69e2d-a370-55b8-95f6-8d2b089708b7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | 6.3 - Concrete cracking approval
1d1f6b12-e6d5-55e1-9b0a-2a1a6535ab7c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | AUTHORITY HOLDPOINT
7815533b-eee5-582c-b97e-d00b84733ce8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | 6.4 - Concrete cracking repair
0cba9a1c-9557-53b1-923b-6ed2a6b8e113 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | AUTHORITY HOLDPOINT
fecc1f52-1f9f-47b4-8d5c-eec9bb593d6e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | 6.5 - Leak Testing
73b1d93a-a4d9-51e3-842a-abdb504b7d2f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-069 - Load Bank, G5401, TR02 & TR01 | 6.0 Completion | AUTHORITY HOLDPOINT
fbf3a70b-250d-4027-ad22-4c62ce614d29 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap
d6e6dae1-7d1c-596f-a4ea-31732acdf80d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 1.0 General
1a648e74-d94d-524f-af5e-afa6513195b8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
a15a2921-eebd-5d76-a77e-144c4edf6eb9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
4dbce87b-7304-546d-b4e1-015ff2df0ddc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 1.0 General | 1.2 - Determine lot size
1f57a592-070e-5541-b47c-c5fb6353557e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 1.0 General | 1.3 - Permits
25e09d05-e5d6-5de6-830e-c9d4160ee0a0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete
673df4a1-63d9-58df-b2a7-7759174d7967 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
2380c790-d0e0-5f17-9a1f-76e4748e8230 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
2f86a964-7854-5ca7-89aa-a5550ed32321 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
858149c8-96ac-55c3-bf0e-3a8b25d9490c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
6373e003-e1e9-58c2-9b10-d73fa32528b9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
645688b3-b2e1-53f6-9ce3-693329e017e0 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork
1f668636-872c-5430-861a-734005f7eca6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
9bfd678a-6023-53a8-af34-abd8ff7b00c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
451660c8-3af5-59af-a7e3-39547e64a97b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
07a0678e-9a3f-59b4-a34a-c086d5d9937d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
60a99440-394b-5c4e-8940-8419742c7a0c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
dffd1e21-9f51-5f3d-b9ff-a1a3c003a953 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 4.0 Reinforcement
8b7454ba-a95a-5096-b789-d7524d5193d9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
651d3242-deae-5254-97c6-6f01cdb1547d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
cf3dd550-3016-545e-a659-bf166a48a43f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour
778ddefb-4e4a-56d4-98b4-9e7937227843 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
4739bf65-90d3-5096-995e-d7c1e2be6696 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5adce16b-8c06-59c8-92b2-a596f186dcc8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
3fc8a9d8-3562-5751-b771-880b2bdbd7d8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
576da91a-6817-5756-9656-04464e5620b5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
63efc31d-0a84-5be6-a248-a6e4cd2521e0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
8cf85210-22bb-51d3-b8ad-49edda103fc7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
14cd7aa9-3de4-5d23-bd13-11d0e987481d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
23ab5d4b-fa3a-5330-a3ea-0a23b486a581 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
c98ea942-2c46-5750-a9b9-c8232c36d91e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
253f60f7-1107-5684-aa31-4079692d642a |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion
f10ef56c-c8b1-55fa-85a4-9fa393703a12 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | 6.1 - As Built
0c194cd6-b3a7-5443-b872-c8eeba745af4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
4355115a-b405-590c-90af-e73e4940a7ad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
0ee9ff65-c3bb-5d69-aa89-af26c9899487 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
ac210b31-9b33-510b-8d8b-b3afccf67676 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
803a70b6-9f0c-5732-825c-a4fb290dcaf4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
13b665d6-a1d0-5e4c-98a7-0337c01107b6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
4aee0515-e205-40b7-bfe6-7125777f0803 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | 6.5 - Leak Testing
2c9fa526-b21b-5e1e-88ad-f019d06dcead |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-070 - Fan Stack - Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
672f0ade-985d-4528-a10b-44aef78936c9 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals
52644a9b-c9be-526e-b956-7a66be04e6a5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 1.0 General
267ced09-44f4-56d1-8ebc-32c37bcacb8e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 1.0 General | 1.1 - Material Submission / Approval
19e6a7ab-b053-53ed-89f1-21f0806e97e6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 1.0 General | AUTHORITY HOLDPOINT
7e63330f-172a-5f46-a022-5f737365f2f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 1.0 General | 1.2 - Determine lot size
86ad0f8d-9e75-59ba-9107-35cbf48d4699 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 1.0 General | 1.3 - Permits
08c5ccb9-db34-5a45-bc39-57554bb03d6b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete
881f6b6a-4094-54a5-8ca4-ade7dbeed4a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
d7c31625-cd3b-5521-a7c0-c42bd18ef944 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
14a2afaf-9008-586a-a55f-a33427136a36 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
98eb04b0-345c-5778-9621-9b61c3958e9a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
95b72706-2a48-5593-870d-9565286a6f40 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
8e9f227b-31a5-584c-b2ba-ecdc9e3cf87c |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork
cf756fa7-d21f-5065-b4fe-5ad17886df38 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
3b85bcd7-d848-510b-b42b-84c5fee42170 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
0d99ed9d-a38e-5ea9-aef0-5a47f60cf1b5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
cf0a070f-31fa-5098-88d9-3be9fbd2837d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
1402d939-0408-5a13-84aa-9653bf479664 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
b64315b6-3f6b-5cfa-9d49-04a0ddd8695f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 4.0 Reinforcement
613b4316-e457-5bb8-ad34-c55c09149550 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
8639f1e3-2bc9-5300-b262-06c0ae70c7f6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
13b7b083-b51f-56af-9469-89e6307355f5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour
553cff87-ce29-559c-92e7-fa211c9bff4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
936146c9-ee46-56f4-8ee7-3faa050050cf |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
28c94832-507c-5664-900b-e776584d0e3b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
8b60e806-8500-530f-b26b-2c299dac81ad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
9744d2b2-d066-5af0-82c5-089bebd38685 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
082dd197-5991-5049-a59b-caf293ce3424 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
2758988b-c233-55f8-84b5-354cef3aa9fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
e7e88f7a-d0d0-5483-8666-b1a2ed5f3f4a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
10456310-0bd2-5bda-9849-feeb0ed8583a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
a4406ca1-9665-5822-be04-42f523974194 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
92a9161a-2d7b-5396-a2e9-7977b56f3222 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion
5c66dc9a-c0b3-5612-ab94-104ae3a36e66 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | 6.1 - As Built
a48ce367-c213-5928-a177-955ad28d8e08 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
81c1ef08-63ab-598d-b175-df8df6522d5b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
48b06d81-65d2-5662-baff-175ff17d4232 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
7135ac6b-e9f5-53a8-bb22-a496728a1ed4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
127cfd7d-83ea-5b56-9d9d-332f3f1764b3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
42fb65fd-499d-5205-865f-b8b5d70767b2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
cb0b879a-1600-4fd0-bd9a-0f24eb11b071 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | 6.5 - Leak Testing
c0e17527-2a90-512e-b1c3-fd444f53edf4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-071 - Fan Stack - Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
827c7518-fcb1-4e7a-a190-f7770428f789 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals
10e666f1-49fa-524f-909d-578560fdebd8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 1.0 General
5da3afd1-492e-520b-9a19-933c891da434 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
6db287cd-f26e-5465-a9ef-00f8c02e8618 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
39a6dd8d-fad5-56b9-b2c4-aad8a1239e25 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 1.0 General | 1.2 - Determine lot size
ce63e10e-32f4-54ff-81de-1cbacdd50c88 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 1.0 General | 1.3 - Permits
ea63386e-36b3-55ee-bfe2-348c7fb74ee1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete
ae0fa7b4-d1b4-51fb-bbb2-465e0673955d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
a8a12f29-efd0-52a8-a6e5-db331ffe373e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
573757f5-7d3c-5ae0-bfd8-0b229c2a9dd8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
ca4e47d8-9aeb-57ca-aa9d-7612b66bfada |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
8a44b2a6-3aad-52ec-b46d-52444c87d8b0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
9ce15ba9-da22-5373-950f-d18a87cf1b00 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork
26436d35-9e82-5fd8-998b-e2d6e0161d3e |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
5fb8a3a4-973a-52e6-a5a3-8701a64bcd08 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
aa3c868b-c03a-5101-89bd-fb9584aca435 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
788a3213-f9e1-5086-83ea-5662a4278374 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
7995d614-e8de-51d5-8912-651bdbd9a0b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
a22321ed-e63f-5c9a-9aaf-5da6b79aa893 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 4.0 Reinforcement
45c071c9-160b-52cb-92b4-266751793777 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
6673829c-35b4-5c2c-9024-6896c937d0b8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
383a821d-c8b7-56f6-af44-82cbc50ce45b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour
24f62206-db5d-504b-9a3f-8721a0a195c6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
611c3d20-f81c-597e-a94c-e96037bda34e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
39fe9a8c-a128-5c34-8658-fd8242d20d3d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
89675cfa-a7d3-5ca3-a758-9d69640bb61e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
eb194563-f6d3-564a-abb9-8bcc3c5512e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
396e7211-99ce-5c1a-94c9-a399bfd87e4b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
6945739a-992d-57d1-baae-6b5a1519f749 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
690e258e-7b6f-59d3-add7-0cacf0f2fd25 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
3b419516-fa19-5d21-90b1-93b1ff66d89c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
9016df11-1656-5f3d-8bae-d9075adfafac |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
9e6f80ed-a4aa-5495-af73-5683f26f10a2 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion
62485f89-71c6-5dd4-8564-56f3b0d0d953 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | 6.1 - As Built
326bfd60-1473-5d58-9cbc-bb4b4af27d33 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
a193a162-b904-56bc-bc01-746ca97ef817 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
c4ee1f66-6393-55f7-a3fa-9e16729dbc02 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
138056fc-1f58-5c53-9cd0-3e3ee8d949a5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
f5743ba0-a5f8-52fe-b3a1-a79737d79e81 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
142912be-67aa-5356-a59b-686afd219d83 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
9633130d-4cfe-45ee-a44d-c8a10073e041 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | 6.5 - Leak Testing
fc500824-ce56-5e69-949a-4098e1c313f9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-072 - PAU03 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
caeb5709-4f0b-4f8a-95db-9ebe2b66c65f |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals
867460a3-9694-5980-ad03-9146522f8204 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 1.0 General
9a264f64-9130-52a0-b8b5-cad127275653 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 1.0 General | 1.1 - Material Submission / Approval
0faf9a42-e1db-5e93-9a8f-42740081c346 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 1.0 General | AUTHORITY HOLDPOINT
1c7196bb-e252-5a48-94ee-9734e94f9556 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 1.0 General | 1.2 - Determine lot size
3edf2cc0-aa87-52ca-9a51-c6bee5dbfac0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 1.0 General | 1.3 - Permits
4cc7e0fc-8aea-5bf0-9df5-e38898dd92e6 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete
43958e5e-211c-5b57-a7be-b1956ad44ea9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
1ccd17d5-339e-5b37-a268-2d7408002f89 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
c4fbce0d-e6be-57db-af19-e1211331beed |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
a7d4a85b-c8d9-5264-b96e-f7d05dc6699d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
0db1cbf6-b36b-5d2c-bd43-b5645e327a46 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
6e55082c-711a-5bcb-8a94-65a6f962abfa |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork
36277a01-ca30-50b2-85ed-a54ca895f6cf |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
3b37eedd-f251-547e-855c-a17094de58de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
b10bc1d8-8b98-59df-869a-59a46f3db789 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
fa3330ec-4fcc-553b-96e1-ed9d0efaf37f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
c69d40f2-c0e3-5838-996c-fd220ddda203 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
4fc614cc-f1c4-5c99-8719-5143b5807da3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 4.0 Reinforcement
1b6528ea-a8d8-544d-abef-bccfb4fd78e8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ed9fdbd5-3263-5c20-9af8-9f4d94e55486 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
787561aa-c341-5987-aa7f-b9b43f05f0e8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour
9ba0d6a6-5a1f-5320-aa72-1333f46b0b5e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
54d18d20-315b-558f-95f7-f9c15b76ce1a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
27386cbc-e357-5c2e-b121-076e93e0f01a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
9e50d0af-03bf-5b79-befb-0d6ec582b8f3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
37e5e257-b43a-53ee-bf32-8d823fd20585 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
860b04fe-7888-5422-aba6-a6dfef0282f8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
e825560f-2acf-54d0-8ed2-445d3088930f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
0a52a15a-d04e-5ad6-ae2c-248ebeeeb288 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
69eb7f57-1529-568e-841c-5e5ec46944d1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
4db54487-5e3f-5b44-8e67-dd920ea2dc51 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
796a1142-dd3a-570a-8379-cae08f5dcd75 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion
f76e8015-e591-502d-8832-c314589cf630 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | 6.1 - As Built
34f8c5de-5091-5639-87ab-32179e93ad86 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
8a7642ed-8aed-5808-897f-f71e7bf090d8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
4c370dfd-c1ff-5fd3-9143-ad9246211950 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
769c3dcc-2fdd-59ca-af10-c9e7decb91a6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
d0b53915-1430-5cb6-9c63-298e1006640e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
27dc0a57-0099-50c3-9844-97417f97e6d1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
2624985e-fd24-4796-9a8c-0fed96020f42 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | 6.5 - Leak Testing
caa7dc9b-b597-5852-803f-d3994bc15d81 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-073 - PAU-04 Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
162a2bf9-9dab-40a7-9340-5feffcf4f5c9 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap
bcfedd2b-cd6f-59b8-9a51-4a133d5a5618 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 1.0 General
447e4a73-e3fd-55d1-b9af-59b3d310bd72 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 1.0 General | 1.1 - Material Submission / Approval
77c1d094-22d6-56aa-bffd-47ac24d74b53 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 1.0 General | AUTHORITY HOLDPOINT
c2c347ac-c597-5bf8-b1fe-183118551f7a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 1.0 General | 1.2 - Determine lot size
b2fc3476-e12b-5e66-a928-acd33efef325 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 1.0 General | 1.3 - Permits
83ba19c4-2cae-5531-b388-728dc0e3ac48 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete
f647dab0-a414-5177-98e9-48bd43be3265 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | 2.1 - Set out
c4905a1c-828e-5035-8ed9-eabf016fb649 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
c1d611c4-cc9a-5e3f-94c4-cb0fa5095e4a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
0b295fbd-8491-5a25-97c9-3685a43d5465 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
6109be02-aaa5-571e-a4e8-bed1b13b8d24 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
050b6ccb-d5ee-55ce-a097-cf97a5efd664 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork
2ccf1e46-4129-57bf-bc3a-f05572a40057 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork | 3.1 - Temporary works requirements
1a2caf6a-2d41-54dd-865f-42bb960951c8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork | 3.2 - Pile Penetration
f5ce3960-4ddc-565b-b862-b0fb9473b4c2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork | AUTHORITY HOLDPOINT
262465ce-9176-52c1-b853-bacb55e7ec4d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
9a7a4a63-3c90-51c8-bfbb-ab7d43deac5f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 3.0 Formwork | 3.4 - Concrete jointing
2740c0b9-0ab6-5363-8fa9-c9bf6c887a3d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 4.0 Reinforcement
6c0725b5-9d51-5e3b-b2dd-3d08b8258105 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7af824ec-2480-54a8-a38b-27d21d23277b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
2d265084-c917-579b-a610-c642e461d834 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour
ae302cf6-6493-5278-a289-9c34f72b3e21 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
3acaca19-a21b-5887-9b7f-63eab90ee664 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
f1b1ad96-9afe-5f19-a935-c985b4001cd6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.2 - Placement
e61ef21e-0a3f-5888-9857-934034963911 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.3 - Slump Test
cbee4a51-285d-5a21-bf0d-471730a2b051 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
18d6bf7b-f28d-5c4e-b2c4-114009c62198 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
1c1598c7-13ad-5487-8445-6a24adb92e7b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
c820c865-2563-52cc-b1a9-5d44cba01663 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
19dcfdaf-4bfc-5dd1-a354-e14902bedb53 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
4bf3dca0-c940-5c6c-bbb6-ab5c240e6dcc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
20caae46-7feb-5922-9912-b35773a345c0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion
59c4f09d-1555-5316-81eb-f04485b98c9b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | 6.1 - As Built
5c266504-1591-5c2d-9cc7-98df699148f2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
c3102b16-5b39-54c4-8a34-e5c9136efdb9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | 6.2 - Concrete Test Results
ba4fbda9-8cf6-5e4e-aaa2-81872e341b42 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | 6.3 - Concrete cracking approval
e0e55267-1efc-5f8b-a9dd-9271925c0188 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
531a0709-49d5-5cdf-92fb-e79db0c0a0ad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | 6.4 - Concrete cracking repair
fcb80056-a48e-5019-93ba-de1209ca7532 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
8b4b8834-6d9d-4481-b248-af8e23e95ef4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | 6.5 - Leak Testing
13f92c0a-707c-58e1-b2ae-b3bf900c45f6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-074 - PAU05 Pile Cap | 6.0 Completion | AUTHORITY HOLDPOINT
34a94708-7c3c-42df-bec2-a53f0e4836e7 |  | not-started | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal
563e8022-ce4f-5262-b562-394af51f5a33 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 1.0 General
772a3401-d434-5c4b-a5b6-9ed94095fa9f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 1.0 General | 1.1 - Material Submission / Approval
238e635e-16cf-5d97-8e2c-8530562e9ad4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 1.0 General | AUTHORITY HOLDPOINT
1da3585c-c73a-5801-8948-90dae3d020d9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 1.0 General | 1.2 - Determine lot size
54d99ccc-33e8-5162-aa8d-f1749491ac2a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 1.0 General | 1.3 - Permits
25e93a2e-8caf-5e64-a0c5-48e54f00e380 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete
231d9df8-008b-515c-aab5-8a3760a7dbab |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | 2.1 - Set out
2df8069c-224b-5f30-b6f4-c698251d1ff4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
c5699ed5-7555-5001-8ed8-01bc10ab14dd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
5e457538-381a-537b-ba4d-8de1959d99ff |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
597be432-0ae5-5e9f-85eb-4e9da13d3cb4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
c2ec3aa6-f291-5bd2-8013-76aea3cc44c5 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork
415e79eb-c66c-5c4b-8ceb-d4faa2e57ca7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork | 3.1 - Temporary works requirements
f20b80f0-4090-5758-a064-818386d75cd0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork | 3.2 - Pile Penetration
9427b702-3757-571c-bf86-ddcd8cf133d7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork | AUTHORITY HOLDPOINT
cd97b12f-bb2c-5358-a01d-bbc3f7465e44 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
ce0ec0e8-fdba-5461-bc9d-969a94a9b650 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 3.0 Formwork | 3.4 - Concrete jointing
2a8278ff-7e43-5e94-a671-fdd5b68326f8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 4.0 Reinforcement
2e236dae-55ee-5aab-969d-110d45f1320e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
7d605eed-380d-5082-8746-2b2973bf87be |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
373c403a-50db-598c-9b93-b569e13fc0c7 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour
bd359db5-d415-521e-99ab-3f24140f597c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
97d780a0-1a0e-5ef0-b2b9-2a4b21e76dfd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d9102ce5-b6f1-5e6a-a573-c42d68bb3cae |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.2 - Placement
3151362b-1e78-57f7-9cbe-7253a1763c5a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.3 - Slump Test
1957b3b0-9f92-57c6-b5eb-0f05deadb6c9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
261bdd86-75db-5843-9102-5a69840b156e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
3464a424-d42e-5454-9514-3fa9f6ab81ed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
4f589c40-0709-5cb4-ba2c-cd6b997b9a78 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
11745d7f-3a30-5a46-8953-63ebd52a37bf |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
5ba5eb21-9476-521c-a7c2-0c6c53e0c122 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
cadbda8a-5abc-529c-b661-73a40434eb3d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion
a36d2e99-e900-5825-8506-263ae12acea3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | 6.1 - As Built
f2f0bbbd-5cd9-5c33-b9fa-4bb9a9f3686b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
2db493ab-ee86-5d31-a57b-37d19735e30b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | 6.2 - Concrete Test Results
8c815aab-d60a-5749-906a-93362790434f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | 6.3 - Concrete cracking approval
7e71bc28-5799-5748-aac0-1f00809cb078 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
cf9f381e-f140-5694-8670-a4c3b4ecee4a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | 6.4 - Concrete cracking repair
a703966a-92e4-564e-9686-df810b50fea4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
58130074-6155-4fbd-af95-719138a9c20f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | 6.5 - Leak Testing
396e6098-c5f7-541e-952d-a08403447d91 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-075 - R5403/R5402 Reactor Pedestal | 6.0 Completion | AUTHORITY HOLDPOINT
d46bf8a9-74d8-465e-a798-3895d311225c |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain
1e9560fc-3854-5409-b09f-5f25b4047cb4 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 1.0 General
7bece5e1-bc00-5b2b-8189-0598872193d8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 1.0 General | 1.1 - Material Submission / Approval
efc6eeba-b178-5a9c-985c-930c52c1c1ba |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 1.0 General | AUTHORITY HOLDPOINT
3f218390-0e9d-55ae-8e08-99b2c6084b1f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 1.0 General | 1.2 - Determine lot size
2e59422b-6f40-5d32-8359-1ed6c192b18c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 1.0 General | 1.3 - Permits
fa751db0-890f-5555-9dad-cbc2aaf17208 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete
d10a78be-e362-531e-b09f-942b6ccc2381 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | 2.1 - Set out
2d486e19-34e8-524e-93fc-e1e615401649 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
e596f182-4dc9-5432-a269-36a1c4a605c8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
f5fa9ae7-634a-5063-ab33-126b958ddea7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
44ac4e21-8ce9-5367-930d-1dcf4fa55e3e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
bcc75da1-e383-5668-8871-a8e0d24d32d8 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork
3f38b953-5cb7-5277-bffd-9c0d67dc7ad2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork | 3.1 - Temporary works requirements
2d1f5018-3541-5a85-bdee-fa377733f56a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork | 3.2 - Pile Penetration
ddf1b966-abdc-5fd4-98c7-a48d762107cb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork | AUTHORITY HOLDPOINT
09408a1a-b0f2-50d8-ae5a-d0de8f64d037 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
601f70a7-2840-50d7-b952-dfd8cbee1326 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 3.0 Formwork | 3.4 - Concrete jointing
9a58b2d3-7b58-5077-9415-f984abe1d6af |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 4.0 Reinforcement
fe15cda3-1426-58bc-9aae-334aa584f979 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
387561c2-5baf-54b4-9094-c2665fd7058d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
bf8b94b5-7869-5d14-a248-fee115202dca |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour
e6606226-268a-50b6-8760-d36968ae374f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
21535b99-045d-5974-952c-2ca02dc6a2b6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
88e9244b-15d5-5730-a900-eb25bc20b858 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.2 - Placement
251271d7-564d-54c1-9bc2-0cd5316f9664 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.3 - Slump Test
da258749-9ac7-5070-9547-45a004ec2e43 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
4779e28a-ec65-567d-9411-134bded9eed4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
c28ac212-7d13-5470-abc2-2e6b6b5b7856 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
ade828b6-f5a1-5616-bc74-2b9f85b05797 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
75acd44f-8973-50ca-a2e0-240c38a0c64e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
50b8e508-d684-5460-a65a-3785c95d211d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e7ae875b-9dc6-504d-bf53-fda4ddf88d27 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion
0de22ffd-c5a5-5fa7-a418-43af319386a7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | 6.1 - As Built
a2bea615-b0b6-5407-924e-dbb4739044ee |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | AUTHORITY HOLDPOINT
957b288a-e706-5335-9c1e-67c87218248c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | 6.2 - Concrete Test Results
b6cffaac-0dbb-560b-9173-36877b43e7d3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | 6.3 - Concrete cracking approval
171b1e85-1a5b-57dc-8910-b36c0dd30606 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | AUTHORITY HOLDPOINT
330429d1-7298-5290-9c3e-eefa9abd0157 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | 6.4 - Concrete cracking repair
01c66bb0-9d34-5e59-b926-ad3125ff1a5e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | AUTHORITY HOLDPOINT
c712f836-5e6e-441d-aab1-afc64f834794 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | 6.5 - Leak Testing
421f3df2-0805-5e93-9f3b-a6ee900a2e7f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-076 - POC Drain | 6.0 Completion | AUTHORITY HOLDPOINT
423450ef-b143-458b-8f1f-18fd754273de |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants
ebc737af-b206-598d-81f5-ff06ead9cf2e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 1.0 General
29b57a2a-5c73-54e0-a263-e9cbf2de2ff5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 1.0 General | 1.1 - Material Submission / Approval
5a6befe4-28b1-54a2-826e-e5c71b5b0a76 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 1.0 General | AUTHORITY HOLDPOINT
3cae9069-a3f2-5429-b0f6-b6ab54216dfa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 1.0 General | 1.2 - Determine lot size
0d974073-7f32-5fd6-b6f3-e39a312da8e0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 1.0 General | 1.3 - Permits
ced769a6-59e5-5629-8e12-ce65f24678bc |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete
8cfdcaf7-f16e-5a1e-b356-9a4e2dd769ca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | 2.1 - Set out
1e52deb5-5204-5b3f-9552-5336a5f3ad40 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
3cdab6d8-1bc6-5b3e-ba2d-7268bcb603a4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
41fca11a-069e-5f51-a118-6bfb07eda077 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
0ba25f2f-b2cc-5921-b39c-750e5bca31e6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
5d12b1af-a0a5-59fa-a21f-fd176f65b62a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork
87a79bd5-3f62-5574-8717-e19817c55356 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork | 3.1 - Temporary works requirements
6fd807ae-ed6a-5f54-9797-9d9a678a0ece |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork | 3.2 - Pile Penetration
0741db75-2b2b-5b42-b52f-8d1bc8dd0078 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork | AUTHORITY HOLDPOINT
949eb1bf-845c-5ff5-b624-021e18f18d0d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
d9bf58c7-1a55-5e10-b811-39ebcebdbf30 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 3.0 Formwork | 3.4 - Concrete jointing
c0ae5fd0-36b9-510d-8c11-840a8bf7da65 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 4.0 Reinforcement
4bae08a9-cae8-5913-84f8-552f1349e105 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
45d32895-5b3e-5595-9bcb-a032779bb007 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
33352527-9efa-5a34-996f-d961cb4fae75 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour
ca7db84a-65ee-5f4e-94d7-1045310807ea |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
a5dced60-79ee-528b-84a5-c2613ebc9ddc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
3c4d97a7-673f-58e2-91ba-82cd60557869 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.2 - Placement
2770f09f-5694-57fc-aacc-e939678bd882 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.3 - Slump Test
cbc90def-822f-577c-a76e-eb364aeaa546 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
2a2144d5-6a08-556c-afad-ddcf0907576f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
972f8bc5-82f5-5757-adaa-a7513ed3cd2b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
2d6f3407-f6d2-5c87-a2d3-4185076a7f2e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
e5cd9551-d47d-590a-aa5a-54119f3c5aee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
ce1e5b9b-ee0b-5d4f-92c1-4811bea9426e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
02a68af9-6979-59d3-8bc4-d63c0ea478f9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion
8628889a-527a-5dd5-bc51-3e2a6e64ded4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | 6.1 - As Built
e3d03dd4-2d9e-5d45-86bf-e9bc74a6a628 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | AUTHORITY HOLDPOINT
6a4a0f7d-8614-5e48-9b5e-655afbf0018b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | 6.2 - Concrete Test Results
7e113a02-4f8c-53ab-8151-cb865f2e5d6a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | 6.3 - Concrete cracking approval
65a4a6a0-7dad-54b8-903f-c009f19d2d63 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | AUTHORITY HOLDPOINT
7d80d606-c8c6-5756-90a6-6d7f7ef6b87c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | 6.4 - Concrete cracking repair
0e953209-e5c8-5718-9f75-6ea384259da5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | AUTHORITY HOLDPOINT
fe2c9067-e329-49b2-8e49-bc536296d194 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | 6.5 - Leak Testing
35487584-9918-54f8-8978-762933d397e2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-077 - Hydrants | 6.0 Completion | AUTHORITY HOLDPOINT
252acb04-dae8-4997-9be3-84541ab26ff1 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3
216f6b99-1e0c-59c9-ae82-2ae40de07070 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 1.0 General
205a1ca2-ebc4-57be-afe4-235ef133a857 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 1.0 General | 1.1 - Material Submission / Approval
b61ef6d4-bc3b-5afd-b992-8228a663517d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 1.0 General | AUTHORITY HOLDPOINT
826c250a-085f-500e-ba77-a98ce0d8f4d7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 1.0 General | 1.2 - Determine lot size
cfbc12fb-0a04-5d3f-8299-fa0844969798 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 1.0 General | 1.3 - Permits
f55e6d68-715f-5422-8259-7b5869aa1a27 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete
9b16d4c4-1a26-5486-aaaa-84bd5cf70754 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
b08b70e8-5722-58a8-bfbd-f4a03fd2ffff |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
a7327878-64fa-5ccb-81c7-662c3b0bf900 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
26ceec33-5409-51d2-9f54-e8b60dcf3485 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
fab2eb43-0880-5066-8a9f-9669350b79fd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
b4633e2b-a95e-5008-bcd9-d4be8282a9ff |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork
7770cbef-0b7d-5871-b178-274c0573aa39 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork | 3.1 - Temporary works requirements
456032c7-f76e-5706-9661-fb1bf68ca022 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork | 3.2 - Pile Penetration
78daf9a7-73b1-5698-bb55-3974275bcb10 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork | AUTHORITY HOLDPOINT
faa41206-592c-5737-8eb2-e328d1642732 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
21c6af04-d081-5f4d-8ffa-545d3f8da2d7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 3.0 Formwork | 3.4 - Concrete jointing
8aad9b8c-71fa-5e6d-8cca-b82dcfcea156 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 4.0 Reinforcement
109b3f09-2b86-5ea9-96d1-c48c06487287 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
a6c17d41-d61e-5b38-b63b-6d3639d1eed8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
4d6f10f0-7df8-5e8c-afda-25eab8b14a39 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour
200bd7f0-d677-5bba-abb8-cce1eac66e6d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
1c58ba75-a423-5913-992b-2390e82dd5b2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
e45c5964-1941-5d3b-b74c-a661beff269a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.2 - Placement
da09d3a5-2f1b-5a66-aa17-ffd28319943f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
025de356-00e6-5868-9d89-cc922eeb3f44 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
b3ed0cd6-4a36-560a-87ea-7b2635c1add3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
72a04489-31f4-5043-8a82-e3c08e5b17f2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
3b2f8b33-a26c-545d-8a98-47b4dcf7aa85 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
32af3b93-47f8-5eaf-a453-9ab32b81154b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
2bae7b27-275a-578c-ac92-937089a5a291 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
38250198-7344-508d-8db6-5e675da07e0e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion
e4b133c6-f3af-5ab9-ad7e-09a569267aa2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | 6.1 - As Built
d163cc12-7b14-5c6e-82ce-36c6358c203b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | AUTHORITY HOLDPOINT
11611fcf-5b26-57ce-91d8-442c27a2074c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | 6.2 - Concrete Test Results
c948e086-d2ba-5e7c-8db8-02670ed0ecd0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | 6.3 - Concrete cracking approval
26c68e25-0ef9-5af2-8627-bbe7a350605b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | AUTHORITY HOLDPOINT
a73c8b30-f430-515e-af24-612e59beebdc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | 6.4 - Concrete cracking repair
3ca3be01-5bc7-5821-ab04-9ce893ea2da6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | AUTHORITY HOLDPOINT
3105e8f5-6486-49e3-8ed0-9783034faa49 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | 6.5 - Leak Testing
42a00d1f-3b27-5223-b8be-b52d073c0ed0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-078 - PAU04 Pile Caps F3 | 6.0 Completion | AUTHORITY HOLDPOINT
0f602c74-19c5-4bec-8ee4-0a86ec84363b |  | not-started | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004
eb904372-2ea9-54e2-b7ea-87da548a0c3b |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 1.0 General
9a95ea1b-ecbf-52d5-8984-efeac016eae6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 1.0 General | 1.1 - Material Submission / Approval
c8c37096-f1bb-525c-b182-e5f62dcb4ce4 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 1.0 General | AUTHORITY HOLDPOINT
ccc5a6b5-e45d-5a79-8397-7f945e061dc9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 1.0 General | 1.2 - Determine lot size
f2b09215-d425-5e1b-b16d-5bca5f883ce1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 1.0 General | 1.3 - Permits
ead37f9a-2f73-5d94-8866-67b9a4ef5249 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete
6c08ba17-bbf3-55c3-a1c6-a15b53522d01 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | 2.1 - Set out
5a5a971c-31fb-5302-af5e-3bc4e766eb44 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
3ee0d8b6-b9ae-5f8b-bb5b-55932cf4054d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
90f1c997-3a4d-5d70-b2ac-8a9e9f39f736 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
6b831ac0-34a5-55d4-b617-19cdfabfb5dd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
04b0582c-c821-5dee-ae5f-a825a111fa4e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork
70d4df29-04d6-5bde-b377-f6d068d9094d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork | 3.1 - Temporary works requirements
54cd64ce-4976-55b7-9e42-5dee2e8907dd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork | 3.2 - Pile Penetration
be2b0960-3152-59d0-af13-ef304658b45e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork | AUTHORITY HOLDPOINT
295f8f9c-6cc1-5178-be88-a934efb5ebe8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
d0839b5d-f2c4-5d67-9af9-6af2a493cd08 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 3.0 Formwork | 3.4 - Concrete jointing
5860bd75-0dea-5a64-a72e-6fbe0dfa2544 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 4.0 Reinforcement
61b71f61-4ad5-5e8d-b3a2-684e03ee9eda |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
ffafcfbf-3e92-5b6f-add9-22a5d9455460 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
04e7d2d1-af22-5c2f-906c-146bbd43099c |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour
b4c21847-8231-523e-950c-da6fde271ef3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
f1a9e047-d68f-5b3c-a37e-bf470501ad67 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
5ba53142-a098-53b1-be80-7413e18b50d4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.2 - Placement
8ac73a05-e291-5653-812c-754074c4ce9d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.3 - Slump Test
4a5dc2fc-e81b-5c3d-92c6-7e9879ab52f7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
149d8002-beae-5315-b46d-255edee563cd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
6d994bca-6af1-5f29-b89d-b7669c281667 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
8864914d-2c59-595a-aba4-7844ff80db85 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
11012188-8875-5b6f-9d23-2239e9ce44e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
597e95a1-861e-56e5-aba8-f20a4dcf10b9 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
8ddaac77-2ed0-5cc5-8290-909421d9786e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion
6dc7c8be-1a65-5acf-b894-eab66fe0014c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | 6.1 - As Built
54b3e999-0ecc-596c-8683-9b6ccd731d8e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | AUTHORITY HOLDPOINT
c83d0bf6-9ffa-57eb-928c-2e9741128822 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | 6.2 - Concrete Test Results
5de72119-1ebe-5669-9f32-636e7d7ae9bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | 6.3 - Concrete cracking approval
f698a648-d10a-5f2a-9885-1038caa568bc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | AUTHORITY HOLDPOINT
613c769c-03d9-54eb-ab56-1d7ab343385c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | 6.4 - Concrete cracking repair
65ba9714-4c96-508b-a2f3-69c1a6eb831c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | AUTHORITY HOLDPOINT
812e1c11-09a7-5fee-a4a5-968e84706a22 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | 6.5 - Leak Testing
f99af509-7253-581d-bdaa-259d58d45596 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-079 - 101-CB-009, 101-CB-008, 101-MH-003, 101-MH-004 | 6.0 Completion | AUTHORITY HOLDPOINT
6770098b-93d3-43c0-ae1e-f2c2f5a09bc4 |  | work-in-progress | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings Rev 3 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals
9ce04dad-0796-5956-97e6-6826559aa01d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 1.0 General
82755544-d4e4-53a5-ba2f-b8f0a2b6f692 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 1.0 General | 1.1 - Material Submission / Approval
aa54cbf6-4ec7-5adc-822b-edfbc10c0bd5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 1.0 General | AUTHORITY HOLDPOINT
14a798fd-b6cd-5fed-a46d-59de3a5e694b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 1.0 General | 1.2 - Determine lot size
1d718c6b-05df-5da8-af78-4e1b408b0003 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 1.0 General | 1.3 - Permits
b9fe739d-cc59-58f4-8885-18a2ae01a80d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete
fcacd103-af13-5352-bf52-954319cdb708 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | 2.1 - Set out
a1a7c289-a605-52cf-b20b-9f2d96f55f18 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | 2.2 - Pre-Pour Inspection
4a6f3257-39aa-5f1e-b6c6-54b916c87bdb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | AUTHORITY HOLDPOINT
8b3ad0bc-5beb-54cd-b0fd-267f9cefe53d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | 2.3 - Lean Mix Concrete
3c8782e2-c4fe-51cf-89d9-9022f76c9b9b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 2.0 Blinding/Lean Concrete | 2.4 - Placement of Lean Mix
6967b1e0-f44c-51a7-8e55-c28369982022 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork
706cfe1e-85c7-5e1c-a7f8-f4fb98ad2734 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork | 3.1 - Temporary works requirements
28218f89-c86f-5bd0-8ef2-a1dade87d26d |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork | 3.2 - Pile Penetration
d8bc1c87-09fc-537d-9c89-aa642e0045ad |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork | AUTHORITY HOLDPOINT
9448ee07-a387-5774-a2ee-a52be9409e6a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork | 3.3 - Formwork Setout and positioning correct
70b06537-0f16-57c0-99c9-e15439b7364b |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 3.0 Formwork | 3.4 - Concrete jointing
2294eb11-5b7f-5c0e-9369-f7ae6c89b4d2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 4.0 Reinforcement
b500bfa6-0d89-516f-874b-191638ac4b14 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 4.0 Reinforcement | 4.1 - Steel reinforcement supply
797def07-146f-5e7c-a733-2e46b32fe74f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 4.0 Reinforcement | 4.2 - Steel reinforcement installation
edd562f8-6e72-57e6-a9d5-a03c6cc7500a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour
93974646-bdf8-58eb-994f-9a5fe5cba835 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.1 - Pre-pour Inspection
eac27663-59b1-588e-a2a8-db5b55bae430 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
c5bb7063-533e-56f4-aef8-a5868c79d1e2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.2 - Placement
1ab70390-d6ef-54c2-b6c7-bcfe01d99d71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.3 - Slump Test
76ff6a72-b88a-52d5-b767-39e596ab1a47 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.4 - Strength Testing
eefc889f-e4b2-588f-8764-d19edf4c8f20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.6 - Curing of Concrete
317e17b4-b375-5268-9448-beee2ecb1c42 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.7 - Concrete Finishing
4baa8c9f-51a3-59b9-8092-a656f71887e6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.8 - Formwork Stripping
79172811-36c6-5257-adb2-39142ccaebe3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | 5.9 - Post Pour inspection
3bef0bd2-eab1-555b-9bd8-bb417542d03a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 5.0 Structural Concrete Pour | AUTHORITY HOLDPOINT
d138c74d-2461-5a2d-a5b3-ef3b88a82954 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion
5e5ba4c9-9fa4-5c3c-ae93-2f35ae5c6dd4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | 6.1 - As Built
214f033f-0e6d-508e-8dce-1053d64b7e78 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
889f9a7f-016b-5641-aff2-c658d87474c3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | 6.2 - Concrete Test Results
bb5ac729-58a9-5859-a279-2ed516c483ee |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | 6.3 - Concrete cracking approval
a17afa07-528c-58c8-9be0-8501d441ca79 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
e14ff6d4-1989-5c86-8da8-b501c42a0609 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | 6.4 - Concrete cracking repair
cf80a8a2-c2b0-51d4-971d-5de22e6500dd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
b8bf3815-b2dd-5741-be9a-5da28d33d51e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | 6.5 - Leak Testing
d08ce9c8-46da-5899-b6a7-b1aef16efce0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-031 Blinding, Pile Caps and Slab Footings | VIVA-FRP-031-080 - Gravel Pedestals - Gravel Pedestals | 6.0 Completion | AUTHORITY HOLDPOINT
11107674-27df-4102-b1ca-16c2839f626e |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation
cd177760-f86d-4565-9338-725264ac529e |  | work-in-progress | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External
6256393f-ebb4-5601-b195-f9d3469cc681 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries
bc771d56-2a0d-57e9-8510-f8d3b0d7424b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.1 - Set out
519a570c-f2d6-5f11-a074-6068835494ec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
41362eb6-d703-5f85-b36f-c1db4c81162e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
84d94378-8593-5436-a9b6-69457ebbe003 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.4 - Permits
04668b9f-de18-5a59-a772-b32224d7dca8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.5 - Determine Lot Size
fbd30b1e-b254-5a29-a5e9-a26bb2a54dfb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
a22f0929-56ea-5b3c-9d5e-2abe59cbd5d4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | AUTHORITY HOLDPOINT
851ff343-f3fe-54ac-94c2-8c6fe43dd62b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 1.0 Preliminaries | 1.7 - Material Approval
7c4ff822-437d-523f-a29b-7ed7cbff8b5a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 2.0 Excavation and Bedding
58dd2bd3-d8c9-5875-a905-c843160c8a4f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 2.0 Excavation and Bedding | 2.1 - Service Locating
3b70c9e8-4fa4-560d-8a1c-9a17541af150 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 2.0 Excavation and Bedding | 2.2 - Excavation
af84e645-afb3-544f-aec3-1a3c3c846760 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 2.0 Excavation and Bedding | 2.3 - Bedding
3e9715ce-bb95-5b85-aa05-2bc6ccf05f55 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying
d22ab26e-3426-5ad3-8be2-abab5d01212d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
b0ab2260-5431-53bd-a730-8b52ba535761 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying | 3.2 - Lifting into trench
0d259793-ebce-5a89-8ecb-f50e346218eb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying | 3.3 - In ground fabrication
f7004ad1-48c1-56be-b04d-4f0472992c56 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying | 3.4 - Haunching
d6519821-ba80-51f2-a802-27d69aaa4ff3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 3.0 Bonding & Laying | 3.5 - Survey Pickup
ccbcbfec-a8d5-5000-8c74-e5de56e40b37 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check
be27d0aa-b3ca-5ed3-a91b-16962910d5a3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | 4.1 - Test Pack
84754a6e-07d9-5450-ba1f-b63e79f0e82b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
ef9a8ce4-80c9-55a6-906c-fb743033a463 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
1957f46f-a3cf-5804-8e13-e4f1dbe75751 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
d1cf24d9-7a96-56a5-a248-26ba23389d6b |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | 4.3 - Repair
09189bb8-b183-5e79-be83-f6db4e79a949 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
a823576a-efde-5add-b6de-ba425c389730 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Backfill
a434f18e-b7fb-598f-99cd-55e62fc6a10d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Backfill | 5.1 - Sand Backfill
e2a96eae-22d7-5b22-a6d0-840c7850d60f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Backfill | 5.2 - Select Fill Backfill
04821290-439f-554f-b79f-eaa3b173e40e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Backfill | 5.3 - Compaction Testing
dec88017-3a18-5b74-b3c2-f6e18d5f5b1a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Documentation Submission
bf8da30d-88be-592b-bd00-e590db40438a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-001 - Western External | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
41a5288b-8566-4c47-8006-9c292d914b44 |  | work-in-progress | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run
90d6a3af-47a3-513d-b9b4-61357a5311c5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries
d458dd40-588b-5cc7-a655-b894db0a3e11 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.1 - Set out
455f7bb9-fdf2-58f0-aa7d-94a3e009d30b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
cb15852a-15f0-5823-8393-83428e3bedfc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
28543250-479c-55a5-8f0a-371bf9125686 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.4 - Permits
88aa031a-e4a6-5d75-8934-cbf9f0d14135 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.5 - Determine Lot Size
1bab229f-ca3b-58d8-87ff-2edb7f0752a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
6b2ef5b8-7e8c-5647-a052-14025da19ddf |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | AUTHORITY HOLDPOINT
ab346fe4-a288-527b-bbe1-49605776717a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 1.0 Preliminaries | 1.7 - Material Approval
80291cf2-e89e-521d-b102-becc1d131542 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 2.0 Excavation and Bedding
80cccf16-2154-5889-8089-353e01b0bf9c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 2.0 Excavation and Bedding | 2.1 - Service Locating
f8b26232-d278-50ae-beee-58b6e550d3fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 2.0 Excavation and Bedding | 2.2 - Excavation
956c5d93-bdf0-5ad3-bd54-aab2961ce981 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 2.0 Excavation and Bedding | 2.3 - Bedding
79e204d6-48b5-5692-ba1f-8cd1a1762b96 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying
8bae9d83-936f-5b28-8f13-73541608480a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
88a51675-71cf-5414-aff0-8849e792a8ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying | 3.2 - Lifting into trench
e7d2ed00-009e-5dc8-abb9-0b8ff0260c21 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying | 3.3 - In ground fabrication
416fa721-a549-5d0e-b3da-2ecd8a01580b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying | 3.4 - Haunching
5aeaec25-c178-57ea-912a-9f23af78a58a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 3.0 Bonding & Laying | 3.5 - Survey Pickup
5492c496-12bb-5436-aa24-96a0735fade0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check
16fc09ef-8d92-57c5-a613-9a032749ea4b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | 4.1 - Test Pack
f527ddcc-836e-57d5-8903-f39815d34ec1 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
bffd9ad8-24a6-5700-b41d-f84a08e40514 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
c3595739-d8eb-5a55-8dcb-e38a0315f1fd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
e97e3c6e-5076-546a-8b76-34e57819b429 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | 4.3 - Repair
2e908f18-216b-5f21-8557-c487287caa19 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
b4b73c9f-0e8d-5617-a4cd-47e005225fb9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Backfill
768bb85a-5dfc-5947-be6d-1a9d5df5f617 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Backfill | 5.1 - Sand Backfill
3865c757-bb61-552e-bfa9-1ea2eae99203 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Backfill | 5.2 - Select Fill Backfill
61af8c66-8795-57d0-b80c-3747c194b586 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Backfill | 5.3 - Compaction Testing
167cca24-5990-58db-958c-5c56d16a593f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Documentation Submission
e3714b83-d865-5182-9953-f01b2ba7b594 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-002 - Northern Brownfields Run | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
c97d67bb-916b-4ece-ab46-4eb1b93cfb61 |  | work-in-progress | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal
452b7ee8-0dbc-5af6-aa55-a87dc869ddd1 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries
36deba61-5e0f-5022-a162-ac7a54e86fcc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.1 - Set out
6a54f171-e2d8-5477-ae81-cb246b1d3de2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
d225a2a1-a7f0-5eb1-8bc4-51c4a09341e4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
848cb328-7cf3-5c29-80ae-f492d0ec38c2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.4 - Permits
6eb44c8a-ae60-5aa3-9b18-baaa89fc6638 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.5 - Determine Lot Size
d73def3e-8d48-5da9-b564-570e530806a7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
c44bafc6-5f92-588d-afdb-cd1c17c7fd26 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | AUTHORITY HOLDPOINT
b882872d-24dc-5ee7-9767-e48beaef8394 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 1.0 Preliminaries | 1.7 - Material Approval
0948b72d-93b8-58d2-ab38-fb155f7f545c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 2.0 Excavation and Bedding
951e6a7d-c21c-56ad-922a-57f25655fe3e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 2.0 Excavation and Bedding | 2.1 - Service Locating
e5cd0b89-0d94-5cd9-87e2-ec4784643c50 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 2.0 Excavation and Bedding | 2.2 - Excavation
b4457697-0185-5f36-b090-3560aa90be20 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 2.0 Excavation and Bedding | 2.3 - Bedding
fc034cc2-2180-5bb2-bf69-4606a8d92c61 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying
7ea6e260-7007-5a06-9073-8ccdeb0a873e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
792404fd-1053-5683-8453-fa56134e8a71 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying | 3.2 - Lifting into trench
75761c6f-7676-5da1-a720-78c07fb62142 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying | 3.3 - In ground fabrication
2f4216ca-a672-531b-afbe-816a0e03d000 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying | 3.4 - Haunching
ebde73bd-00ab-5097-b683-96020a5ba117 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 3.0 Bonding & Laying | 3.5 - Survey Pickup
adb6c8e8-e70e-5e76-a71f-2ec0379f4696 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check
2446d8ba-ad7b-5de4-826b-c82a9ee30a79 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | 4.1 - Test Pack
5fd2ab07-aec1-57e7-86c7-e3eb65c276f8 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
9b6c784c-c24a-5eb1-b531-749fccb9c4e6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
3dddd4c9-9560-52ba-8ecf-0fd011881f09 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
5633f3b5-889e-5adf-9df1-8683e7d73fc5 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | 4.3 - Repair
150bb219-ac4a-5645-a026-bb8ec3a6378f |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
87a38401-8e13-5211-8fd8-20e827323801 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Backfill
b3068802-5c39-5958-9557-34b50377dc35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Backfill | 5.1 - Sand Backfill
40bc1336-cfe5-5e6a-bd8d-b0ed99c38312 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Backfill | 5.2 - Select Fill Backfill
cb8946ae-efed-5d21-852a-031f70796e5a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Backfill | 5.3 - Compaction Testing
9a92dcca-7c75-5f08-8227-6648ea441624 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Documentation Submission
af2385f7-b31d-59f4-bd05-a0413a977d29 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-003 - West/South Internal | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
696fbafd-a821-4813-b124-8109c1b3b9da |  | pass | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54)
46ad2c94-a698-5c2b-9cba-9567ffe5932a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries
9974ea9e-28fc-5978-b271-b6062c9d06dd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.1 - Set out
2baf8049-04a9-5279-88c0-e7ef2bbae9a4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
58c9e900-679e-532d-9145-c31f9675905f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
b2ee1431-aac3-556b-b158-bbc664e997a1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.4 - Permits
b770ccc5-b3a3-50db-b300-ad4dabcb157f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.5 - Determine Lot Size
d6c41fbe-995e-57a6-bced-0cab48b4f340 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
54dc28a0-1315-5036-a0ac-dc4e7e94696b |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
986fa5fb-5dfd-5565-81d0-ca11c61a17e0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 1.0 Preliminaries | 1.7 - Material Approval
35c5a10e-735a-57fe-84b3-e93ac664898c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 2.0 Excavation and Bedding
a70ca84c-eb3d-5f75-b1ef-a3979a4e6e72 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 2.0 Excavation and Bedding | 2.1 - Service Locating
466ba8f1-2e0d-577d-884b-d7f6d691e37d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 2.0 Excavation and Bedding | 2.2 - Excavation
ab6f7b28-c781-5423-bd60-e6a5e50f4560 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 2.0 Excavation and Bedding | 2.3 - Bedding
3617b32a-4e0f-5189-a1c9-27f53a20fcdb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying
a2555ff1-d06d-5d3e-b870-5338d3e67ee4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
207a7b87-6a51-51e3-8aa1-0713a1c16d4d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying | 3.2 - Lifting into trench
01460955-b4c0-5289-b15c-bc3938536422 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying | 3.3 - In ground fabrication
c5b8c5cf-3c18-5e7a-ac1d-f3d8ee12b848 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying | 3.4 - Haunching
4831bff0-11ea-5450-9700-19b127f188b4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 3.0 Bonding & Laying | 3.5 - Survey Pickup
86a8b122-b88a-5515-adde-5ed8ae851e1f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check
2c9b3e52-03a1-5583-a17d-99911de61171 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | 4.1 - Test Pack
a2e4fa15-8768-5e8b-aa95-a18a9b7c035d |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
13ccdd22-21d2-5251-98b6-c7b7db1ebc85 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
1056d5b8-9d51-5848-80ff-95ac380ce765 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
38a42bc9-9ec0-5247-ae24-2ccbfdedfa37 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | 4.3 - Repair
6ee621ae-7634-5417-a834-e6d405a66274 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
655327ae-448b-5b0f-acd2-d6c1e9dd0132 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Backfill
5a92a7f7-17e4-57ce-a386-09b967d57e9d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Backfill | 5.1 - Sand Backfill
6167ff9f-e705-512f-9811-bd2581ee9a72 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Backfill | 5.2 - Select Fill Backfill
44a46411-320c-5b4e-8cc0-e76b7166e4e1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Backfill | 5.3 - Compaction Testing
077d4556-42aa-5142-bdca-a73e3da571f4 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Documentation Submission
77985da7-a8b4-57e8-a387-b7c74d222e0c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-004 - GRE East (to POC54) | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
a786b0db-628f-4b84-8a7a-62103dad98b4 |  | work-in-progress | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields
cf46cf4e-7879-5c03-9838-926fee83a468 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries
f77b21fc-a45f-513a-9d34-26849b047f8d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.1 - Set out
742b5f91-78b6-5bfc-9a7b-387a404b58a6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
664d01ca-5e26-5616-a1c1-c9bae2711eac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
94ebf172-7645-584b-bbce-eab7fa8fcd6f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.4 - Permits
8ed1b7e9-c6b2-524b-be1a-c7a0f653d615 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.5 - Determine Lot Size
30fe06dd-952c-5314-a699-53ffe8b7ff51 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
52dbc30c-0bab-5994-beee-747b6765137e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | AUTHORITY HOLDPOINT
9dbfa870-43f1-54ee-b3bb-570295cc9562 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 1.0 Preliminaries | 1.7 - Material Approval
be2eb96a-61cb-5eb4-aae3-42df305ee3d9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 2.0 Excavation and Bedding
099d5a45-eb78-5096-bd74-3137fda4863b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 2.0 Excavation and Bedding | 2.1 - Service Locating
b11bb775-7f7c-52c3-a6a9-2fb4e131f49e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 2.0 Excavation and Bedding | 2.2 - Excavation
92ec1fd4-d935-52a5-96bc-41a0fcb4f3e3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 2.0 Excavation and Bedding | 2.3 - Bedding
26bf1ef2-2092-5a1c-a8da-91b58119ef86 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying
9dc563e0-c818-5721-b6f6-245133943f40 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
d6c28671-ef33-59bb-b0ab-5e6e920ce254 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying | 3.2 - Lifting into trench
8c33afa3-5fbd-5aef-9935-dc76a25798e7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying | 3.3 - In ground fabrication
69fd0eac-c925-53b9-883c-078b6674c2ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying | 3.4 - Haunching
38365ace-3254-52c8-af26-3517178b70b1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 3.0 Bonding & Laying | 3.5 - Survey Pickup
d8437a5c-581f-5be1-ad49-bee5f57ae22d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check
d8d74e42-cb76-517e-a768-3e37e7214862 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | 4.1 - Test Pack
b7d5aff3-02dd-5921-8d53-7c44c95e8501 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
a5fe7e21-6f05-5af3-9363-42379138bc85 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
64826da7-7e3d-5249-8ddb-ab619e650303 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
41ed33e0-c6b4-5e75-ad77-902a093f39a5 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | 4.3 - Repair
3344ca49-63f0-5b92-bd50-186c6876ab9a |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
3e51d419-27f1-5d84-b712-e7cc5d916bff |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Backfill
de1b1293-f602-5b6b-8384-6020baedb7ca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Backfill | 5.1 - Sand Backfill
edcf2c2d-5c42-56ad-a34b-9f1b8441f98f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Backfill | 5.2 - Select Fill Backfill
6f30fa83-fccd-5f24-b615-76202ddec858 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Backfill | 5.3 - Compaction Testing
d73170a7-418d-59a3-9b96-1affc0eeb1bb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Documentation Submission
7b441301-5583-5b2f-9de0-2b6e84ff2856 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-005 - Eastern Brownfields | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
8fd5db32-282d-479f-8ded-1d8e17c766b5 |  | pass | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower
0c9ed1a8-62dd-5c96-ada6-541360ddb77f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries
a1398e1c-feee-562c-9157-6cce12e74a68 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.1 - Set out
f0cf867d-cc2d-5881-bc18-c4007e90ff7d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
0c2936bc-6161-5936-8410-66ae741ebb16 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.3 - GRE pipe confirmation
01adebf0-faa3-5d22-a403-7904d6bbe54b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.4 - Permits
f8e77975-0f0d-524d-a826-f3b329c040a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.5 - Determine Lot Size
0368595c-51df-540c-9311-d772517bde5b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.6 - Joint Pre-Qualifications
e69ba041-1625-5421-ae4c-5b21e15368c9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | AUTHORITY HOLDPOINT
db9f16f8-2951-5d74-b680-7adcac4828b4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 1.0 Preliminaries | 1.7 - Material Approval
009a0666-982c-55d7-b48a-2f3a9ba3de07 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 2.0 Excavation and Bedding
1782568e-ccef-5ee3-8f31-0ab0db8bc26b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 2.0 Excavation and Bedding | 2.1 - Service Locating
f7761f6d-dfca-58b1-a522-105182f5601a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 2.0 Excavation and Bedding | 2.2 - Excavation
0dabab4b-dd87-5670-a078-9da58f63c645 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 2.0 Excavation and Bedding | 2.3 - Bedding
394a82b6-bce6-53bc-afca-c324b88b31a3 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying
ab7d6a66-4551-5c50-ae61-c3f7f15b233a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying | 3.1 - Above ground fabrication
b97c74af-1579-5463-aac2-77f088f3068f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying | 3.2 - Lifting into trench
309fb119-bb6c-514f-8cba-35a48d0e254f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying | 3.3 - In ground fabrication
6b2079bc-72ed-5861-8e39-28cafaa389c9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying | 3.4 - Haunching
66dd7b72-5c93-5024-ae02-da91ffb6b7de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 3.0 Bonding & Laying | 3.5 - Survey Pickup
ee4e62fd-60bc-54eb-b967-50b028927911 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check
9b81c5c7-1147-542e-9e17-6fed24848fb1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | 4.1 - Test Pack
5ca9e9e2-71bb-5842-aa41-1a3a9659acb5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
db8aa84c-d1b2-546d-823e-0dbbd5787ac4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
140e5348-b409-5059-8a6d-1360dbd15c23 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
3794a78d-fb45-5b6a-8275-dc7b6efae252 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | 4.3 - Repair
abcbd8d3-5b6c-57ec-a8c1-d474752cf9d5 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
76f4820e-ebdf-5d68-b7ed-aecb23e23061 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Backfill
89f1c265-e21b-5f16-93c3-a9e551ecfd6a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Backfill | 5.1 - Sand Backfill
a9e7d4f5-8246-5953-bd71-cb92cb079a38 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Backfill | 5.2 - Select Fill Backfill
26f1ff50-b203-5303-82a1-3301925b7216 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Backfill | 5.3 - Compaction Testing
eb84aa3a-b067-5a59-8a5d-cdd2ccfe2a98 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Documentation Submission
4b1c92bf-e23d-5b07-92c2-fe386bcc1f36 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-032 GRE Installation | VIVA-GRE-032-006 - Cooling Water Tower | 5.0 Documentation Submission | 5.1 - Subcontractor ITP
a60addcb-1e25-4dc9-b344-4d812eb6f26e |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation
f5f4ac1e-ba42-4726-aff3-19c1ca26d5e4 |  | work-in-progress | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002)
223ea6ae-65fd-5147-a971-ae2525a50b47 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries
f1b42579-6ff6-5ca1-b504-0d8e66c90441 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.1 - Set out
6c3f82d6-7083-56a9-8cc9-b52f8e7328eb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
f29d1ee5-edb2-55d7-9753-ff3bbca46751 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
7f743b5b-7716-580b-a004-6783bfb952ee |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.3 - Permits
fcb27d66-8d48-5ff2-91b9-988e1d9c6dc2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.4 - Determine Lot Size
919f0b54-06c8-559e-bede-e4c5a8af40b5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.5 - Free Issue Materials
a020b19f-5c57-5b38-81b9-98d87668b964 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
cf75eb48-9f2d-5992-92f5-a3f8a78965ca |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
5899e276-d0eb-571b-a555-fe3a7676b9de |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
b05ee1e8-aa28-5346-9f42-8ef72a900215 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
491c78ce-cebc-59d9-bedc-0ac2999617aa |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 2.0 Excavation and bedding
21748d27-f994-5aef-811e-95d8ac47d9cb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 2.0 Excavation and bedding | 2.1 - Service Location
6556355f-4834-5c12-998f-791a3c01c5f9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 2.0 Excavation and bedding | 2.2 - Excavation
f0f0e691-aba1-59de-8f8b-6c100173d8c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 2.0 Excavation and bedding | 2.3 - Bedding material
a005f7ec-0eb8-5829-8978-204bb38a3cb2 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill
a35a5b92-f6f2-584f-b0ea-e3f658d5cce3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
dda6244e-27e2-5314-8455-547aa4e01955 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
328b9c8a-3f73-5c69-9403-6fc2139e25cd |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
b78dab64-e225-5ae0-882f-9e9c97a3391e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
55d8ee74-910a-555e-9387-da748603e4fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
4ae286af-2f84-5ab1-9736-99f0e47bd794 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
2fc59662-3560-502f-971a-6d07fda0ddf0 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check
de125933-898d-5af8-aa0b-5f2c7a2cda0c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | 4.1 - Test Pack
80f9f350-09c1-5eae-9e47-0427d6500cc9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
3c49b73d-aaaa-5571-8ce8-abe649087b63 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
d23f9184-0af9-5485-8199-a6d7e2305472 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
17176aa2-5ca4-5fec-85c2-916c7ae944f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
12d99dd8-ccfc-5e42-9bfa-ab2fad197831 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
69ac495f-af24-5ddd-912d-86e739a3311b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-001 - HDPE West (101-CB-001 to 101-CB-007 & 101-MH-001 & 101-MH-002) | 4.0 Testing and Conformance Check | 4.4 - Survey
e12175fa-7e28-41f2-8d45-5cd7aa238519 |  | work-in-progress | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line
a1fe5cd0-9ec7-5991-9981-cf2b9d0ce79d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries
14cc8ee8-24ee-5e4e-9eef-cfe0566e6974 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.1 - Set out
8fbff1c5-9acc-5aed-bd56-36a3a2edadd5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
761063bb-f3de-5020-9b19-647534927fa9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | AUTHORITY HOLDPOINT
546f38f7-b8a9-5f05-be6d-a6e5e3bded7a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.3 - Permits
2cb6a26e-0655-55c8-9795-cad96dfa5ddb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.4 - Determine Lot Size
27b9a057-1d2b-5835-b833-99227566beeb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.5 - Free Issue Materials
6e9e277f-83c7-5ea5-8fcf-07a0b5cf072d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
fba2421a-cf5a-5eaa-b32c-649608f03621 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | AUTHORITY HOLDPOINT
8bf6724d-3104-52cc-9f7c-3c4ef755793d |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
abe33124-1bdd-50b7-8f0f-1aae1cde62bd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 1.0 Preliminaries | AUTHORITY HOLDPOINT
6def389d-f4ce-5eb7-8498-509d85ad5558 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 2.0 Excavation and bedding
19cb763a-305d-5fe2-a58a-6f8b748acde1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 2.0 Excavation and bedding | 2.1 - Service Location
aaa2d79f-9198-5de8-8e10-72e0e851aea6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 2.0 Excavation and bedding | 2.2 - Excavation
a57807c2-af04-574e-94dc-1342f76977ca |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 2.0 Excavation and bedding | 2.3 - Bedding material
3c9b1d73-37c8-5bb7-b3ed-07a2efc80044 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill
79088689-fa1d-544a-8055-a0ab88daa951 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
9e8782fd-209c-532d-90c5-edeff7973277 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
3675c1f7-cc83-54a9-a4d4-16c4e1694b58 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
a491d074-36b8-5925-be77-cda19513fde6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
6ab4a714-4309-5915-babb-216e9ebdbd55 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
6514bb90-52fb-56f6-9a00-ea395b989ad0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
d56bb0db-c577-5be8-8f32-7f6c9e65faae |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check
7e782414-b9d6-52cf-9d1c-3401062346db |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | 4.1 - Test Pack
ab459c18-1be9-569d-9dac-d4d70a3cc603 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
64bd9012-257f-53d5-84b0-b24a5e00970a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
6ba7c26a-09ca-5a4c-a7b6-4fbd76f95ca9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
40a9685e-4805-5367-85d7-80d9e9d2631f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
e8e1d3ed-bb39-5fa4-a819-c04a7b9502da |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
a86750bc-9158-5d62-9bfe-a8775fcb03d3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-003 - HDPE Cooling Water Line | 4.0 Testing and Conformance Check | 4.4 - Survey
866e1c23-8c34-4e7a-ab09-bbb3c9a68b2c |  | pass | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC
bad26b5d-bb78-5ac4-9fa1-ce7bf2e21183 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries
622a8f88-e394-515e-a6f2-cd60cb3dd3f0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.1 - Set out
6fe3ed13-f54e-5f37-910f-bd65d5bd41f6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
2ea0c4f4-7ea9-5962-a8bf-19dee2642e79 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | AUTHORITY HOLDPOINT
f51d854b-f1e0-5040-90df-84c11f153734 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.3 - Permits
a824282a-c43e-55ca-8753-4342e550eef3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.4 - Determine Lot Size
1510f025-0920-5bbb-a44d-a651543fc314 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.5 - Free Issue Materials
fb457bc2-f4bc-5e24-9d26-15a45cdab1c8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
5e1fe102-5458-56a5-84dc-3b112c6239b2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | AUTHORITY HOLDPOINT
ab352209-8f1a-5dcd-a7ce-27ceb135e3ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
3e4589a8-e62d-58c7-bd75-b45d954bb7ea |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 1.0 Preliminaries | AUTHORITY HOLDPOINT
2f884468-4c7d-5363-8fe2-2901af91954b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 2.0 Excavation and bedding
62efd3a6-a812-572a-b0f3-f0b316934749 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 2.0 Excavation and bedding | 2.1 - Service Location
50334e61-93c5-5b74-8361-6c6d63757698 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 2.0 Excavation and bedding | 2.2 - Excavation
c23b2767-c739-5d07-9546-0b55f8057e60 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 2.0 Excavation and bedding | 2.3 - Bedding material
585bf796-dd24-5086-ae35-eba37141eacd |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill
422ce745-a450-56ac-917d-865c4dcad17c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
cb3df44f-e8da-51f3-b5d8-8d10732f3a3f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
901f761b-bc5d-5caa-8a04-10fb737ae037 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
c9bd5cfd-385c-5a1d-a9c3-197e883e521f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
8d357634-a46e-5ba7-a952-52abe6c255bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
69fb1d86-d17b-5373-a27d-0087e1632186 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
beda90a4-2873-5e7c-97a4-1c075dea14d7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check
6496234a-8f85-5ead-97df-bdc899c02d62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | 4.1 - Test Pack
e0636664-5792-55ec-88e8-d02f30bcffd7 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
750641a2-402c-584c-b766-c23bb35e394c |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
b35a36c5-4963-5076-9b90-903a57bdbdb5 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
d8a2bcdd-f12b-513f-b8b0-499e6a71b6ac |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
155d5a65-9ea8-5576-95a5-d4af5f1abace |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
695b5b0e-5b93-5692-8ad8-61af71351f81 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-002 - HDPE East AOC | 4.0 Testing and Conformance Check | 4.4 - Survey
0ebc1977-d446-4435-bf01-c8eb1da95da7 |  | pass | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines
5d7afa5d-b4eb-5882-a509-0abec8760305 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries
a1ab5643-46d3-5837-8809-541b18d2b1d2 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.1 - Set out
35e2e4f2-42f8-51c0-afcd-bda2ba62c367 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
8270a77a-a067-59c5-9bb7-09c2babdb4e1 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | AUTHORITY HOLDPOINT
513b121c-5ada-530c-8117-25dbe517bc08 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.3 - Permits
e21f1fe8-e2b4-5462-ad6f-66954c4e73bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.4 - Determine Lot Size
78fbd14e-af54-599e-975f-506e3469f036 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.5 - Free Issue Materials
5511002d-f32b-51c6-af75-45508f2e724b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
2f25c980-4df0-55f5-9fdf-d8a65080cab5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | AUTHORITY HOLDPOINT
40c16666-daf8-5022-ae3e-1181f52a3137 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
c67bdf7d-bea0-5bad-88d8-46539670172f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 1.0 Preliminaries | AUTHORITY HOLDPOINT
803c431b-44d3-500c-af2b-b28184c10594 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 2.0 Excavation and bedding
3263d035-a8dd-5349-9370-a7e79e363dda |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 2.0 Excavation and bedding | 2.1 - Service Location
eee21018-3292-5372-8303-a3d20527b755 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 2.0 Excavation and bedding | 2.2 - Excavation
4f7e3077-f1ca-524c-afa5-843555708d3b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 2.0 Excavation and bedding | 2.3 - Bedding material
d30f3e9e-d0c6-5f3c-96bf-2af95fe8fc0d |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill
7bbcecad-b97c-55ed-ab10-9abeb6dd0be7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
5d6ade14-32ed-59d6-92c6-957f0261bf58 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
3fae5656-50ee-52f9-befd-e62eadf70711 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
8450dea3-13df-56ce-97a6-1ff33c126db9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
eca0bb59-bbd7-54b6-a428-1ad6fa78b989 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
2d59b557-8fd1-508f-8dfa-3f6e7601aa63 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
0be7c7d9-0259-5c1f-b126-cb8af2158f49 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check
215bce11-f348-5405-8a92-459072b8860f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | 4.1 - Test Pack
a52f2188-3249-5a5b-a8db-12b199cd2c5e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
01b32571-edbb-5f70-85dc-f65c081874c1 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
4579ab94-12af-5750-8aef-20bf3f538443 |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
17a52298-0265-5b64-af30-729d12a42153 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
4ab8878b-2af2-5bda-a71a-d148c8c13eb2 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
c07e06b3-7e50-59ed-9503-3d957960583b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-004 - Cooling Water Tower Atmospheric Lines | 4.0 Testing and Conformance Check | 4.4 - Survey
74d75005-b7fe-4d0f-a947-caae52aa03d7 |  | work-in-progress | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East
f4be5347-7291-5215-a6ce-09d54623534c |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries
b60db94b-bfa1-5142-8710-014ab0ff0954 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.1 - Set out
d8db113e-0881-5a8c-b4cb-2714d4b07282 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
c86e9f4f-ed3b-541d-9d29-7311f0f4cdaf |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | AUTHORITY HOLDPOINT
85df7b29-e4ad-5871-987c-5b5b12d18f97 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.3 - Permits
668dbdf2-2ee6-53d1-9bde-67ae7c4f0f90 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.4 - Determine Lot Size
ff54b9e4-7dd2-5e74-a5f1-eb73679dad45 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.5 - Free Issue Materials
ae679c11-038f-54ff-aa4e-c548bcc6638a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
5ed0ea0d-7f8e-5009-a891-7bade00ba9a9 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | AUTHORITY HOLDPOINT
efeec568-34bb-5e94-bdcf-fe967bdfc788 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
1ce81436-ac56-5d90-b642-4dd1f010b174 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 1.0 Preliminaries | AUTHORITY HOLDPOINT
bfd42716-0fd5-57bf-8054-0981b7e1772a |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 2.0 Excavation and bedding
9e18afba-8734-5cc9-8997-b03714d2cc11 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 2.0 Excavation and bedding | 2.1 - Service Location
1364a8f7-69d8-54aa-9759-8c701ba0911f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 2.0 Excavation and bedding | 2.2 - Excavation
5e92ca97-455c-5cff-bf82-94065454dcf6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 2.0 Excavation and bedding | 2.3 - Bedding material
5c1d9489-31d2-5afd-942a-c4db84f8c7ac |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill
decf6721-7a78-50c7-a424-3b4c05ca1a65 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
8ebf36f3-0686-5663-9209-c36fb2a6a25e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
590292bb-8630-5971-bc33-ff1e2febf761 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
47ed7bbc-a55d-5d82-9c1c-fd653ced9f92 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
691383e2-15c2-534d-b406-7bdc6016995c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
6e5e5f16-0c94-5cc9-b99f-70a62327d15d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
f6ead480-1856-525d-ad27-bd2f8af53984 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check
dee8b2d8-00f8-5456-b793-d0c89a0ae8c1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | 4.1 - Test Pack
a116cd67-bcbf-548e-a034-fd9bd23fdcb2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
fc718b3a-6dff-5862-9b7e-d00ad39c18af |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
17584f88-66c1-558a-8e96-9d8c95979051 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
cbcb5201-b51e-58c8-977e-256191e1065c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
2040c4ab-da55-53f9-8e6d-6985d079cd85 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
11871d23-597b-5f0a-bef8-70316f2094a7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-005 - HDPE South East | 4.0 Testing and Conformance Check | 4.4 - Survey
959d3d0f-c46b-464d-aa57-664c4a73b4fc |  | pass | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651)
39e6c58d-d732-5b50-8bfd-401186603d9f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries
e198d22c-1aad-5939-872e-c8002df5df02 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.1 - Set out
8e53ab42-a47c-5ccc-ae2b-026019a7119f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
304323b4-d6ae-5539-bf83-c0798ce8737e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
721611c4-38d6-503f-84c4-c33a2876b960 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.3 - Permits
6d672586-4c6e-54a3-bda3-e334f4cbb352 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.4 - Determine Lot Size
ab49d8d5-0b64-5cae-aa28-4a2667f7a263 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.5 - Free Issue Materials
24761d85-dd98-5012-a2fb-a56244b5edd0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
2798757d-6b4b-5b4a-a970-2797d021ddff |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
6fc91b81-cec8-5dcc-8d5e-71d887b8e8d6 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
037dd4fb-fce9-56b3-85f0-84b050b6baf0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
e24463af-7b42-5794-a736-c53a239000ed |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 2.0 Excavation and bedding
c994f639-2b28-505e-b476-29b55346321e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 2.0 Excavation and bedding | 2.1 - Service Location
e56dc847-8f89-5956-832b-432060abe928 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 2.0 Excavation and bedding | 2.2 - Excavation
05c0f767-02c9-5e47-819e-16b3b206e241 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 2.0 Excavation and bedding | 2.3 - Bedding material
18d842ee-e5b9-57b1-9b49-598281ef95e9 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill
e0f9a332-fef4-5c39-ba2c-dc1e0ec3ac70 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
6ae038a6-bd8e-5091-a6fc-2d5f7f8412bd |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
fe4a2554-f9e9-50db-a7f2-b577c3392d16 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
689a9e1e-304a-56d6-bd3b-ddc37afb9423 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
a3a350e1-f119-5ba5-aa77-9acd17eed8a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
08a4a46e-0ac1-5c37-8527-2ed7ed4d3e47 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
c422c602-0a76-52c8-a3fe-3fd0e31669f5 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check
19559215-85ff-518b-8d4f-79b0b07c2c55 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | 4.1 - Test Pack
aeb31c69-0266-5234-a108-ec3151574c7f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
5da9f049-b59c-5866-865a-204deff0afd8 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
6dff4f15-3183-5652-8d1b-80968cf23d94 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
d45ad45b-55ed-5d5a-abd1-44fe8cc54c65 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
be233e7d-e3df-5102-a550-f94da3b4c19e |  | not-applicable |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
e6841266-5ba8-5cec-890f-ffaf5cc12cec |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-006 - HPDE CWT Pressurised (W54651) | 4.0 Testing and Conformance Check | 4.4 - Survey
f01c1073-cb1e-4698-9f90-175532a0e3c4 |  | work-in-progress | INF-HSEQ CC0398-ITP-033 HDPE Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101)
c1ae4d12-8a07-52be-899e-2ac7254025db |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries
c0b01df8-d2c3-5cf4-a341-b58fb6aeacf8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.1 - Set out
9c8e35ae-bcd7-53b4-a1ac-7b7baf3031ba |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.2 - IFC Submission & Approval
8b108576-7f3d-53d0-9a3e-15eaf1c3fd77 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
3c9e898e-e190-59bf-8097-a5b0a4519113 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.3 - Permits
60730781-b922-59c7-a076-e12ee98fcd70 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.4 - Determine Lot Size
cc0e2e23-9fa3-5174-a458-376dc9bc8aeb |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.5 - Free Issue Materials
9b7b75c2-164b-5570-a2fb-b287156e8905 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.6 - Welding Pre-Qualification
cede9e68-7ab4-514e-a6a3-2807da3903a0 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
15c77323-f56b-5c01-ac12-8538be0d8163 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | 1.7 - Bedding and Backfill Materials Approval
f5fd2408-fc24-55c3-aefd-769d30655043 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 1.0 Preliminaries | AUTHORITY HOLDPOINT
fe897f49-4646-5692-b995-e1d1811177b8 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 2.0 Excavation and bedding
2ad01c84-d667-59ac-8151-a948f8af907a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 2.0 Excavation and bedding | 2.1 - Service Location
09b47534-f658-5865-815a-4c5df12f3cf7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 2.0 Excavation and bedding | 2.2 - Excavation
b8c172a3-0f1d-5b17-a9cc-3d392f11ea05 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 2.0 Excavation and bedding | 2.3 - Bedding material
dfbea575-61e1-5200-9c50-4db89c92a0c3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill
d94b05e7-efab-508a-8c85-8c05818a4db7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.1 - Above ground fabrication
2a3c9058-597a-5f11-b761-90cd8b5e7341 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.2 - Lifting into trench
237bfe18-9b14-5ce5-b4be-74a6bf7ebd20 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.3 - In ground fabrication
de575cf1-5ea6-5b4d-87de-81d3f1929051 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.4 - Haunching
1d034483-905c-52f2-acea-0ea46c6ac603 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.5 - Back fill
d7767b28-d2d5-56c4-8bde-367617f5854d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 3.0 Welding, Laying & Backfill | 3.6 - Compaction
80b0bb56-c663-5c73-bac3-444736ef7981 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check
58eaaabe-4337-575a-a984-fab47220679d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | 4.1 - Test Pack
7ea1dab7-986d-515b-8aba-fb0c670273e5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
11c61913-6316-53ad-9a5b-5c619ea6abc4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | 4.2 - Hydrostatic Testing
79c85c75-7325-572d-a775-54e1bb6133b8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
4bb4db60-f7d5-5599-9906-2071f7bc3507 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | 4.3 - Leak Testing or Air Testing
c1a41587-34f9-5895-ba69-270ba55036d2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
31bc2ee9-877d-5966-aea1-950f512f90fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-033 HDPE Installation | VIVA-HDPE-033-007 - HDPE Miscellaneous Tie Ins (Main Plot 101) | 4.0 Testing and Conformance Check | 4.4 - Survey
bcfa88ef-37ea-440e-9eb8-523e0c9d4c2f |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation
434d1f94-d920-4d6a-8c02-0b02649c8316 |  | work-in-progress | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map)
34529795-a38d-5b46-8ef6-10e014a832e6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities
e111d47d-76cb-535e-8674-08ca2be58815 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.1 - Set out
97009252-1cc4-5f51-9807-1d55414848c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
dc522046-14c7-5c30-9981-cf041a64b89a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
afe236d6-92a8-50af-8f2e-3cc26e9ea8a9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.3 - Permits
ec6dc960-72cd-59dd-ac7e-d26c5a8cc32c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
a216884d-db53-5440-a0c3-808764c91a3c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.5 - Free Issue Materials
02154dac-bb1c-5c46-9a2e-6a9825f0b89b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.6 - Pre-Qualifications
e39b02a2-3b46-529b-9480-bf54603fac3a |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
2d2598ee-714f-526c-9c15-cce062ebcada |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
0d806a7c-d26a-5abc-b123-cffeede6412e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
96313ccc-c62e-5453-b5ba-ffe5d0f85733 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 2.0 Excavation and bedding
060a8224-ef18-5d48-98be-e736c8040ce3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 2.0 Excavation and bedding | 2.1 - Service Location
b3634deb-0259-5e09-a53b-0bb0994a3bbf |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 2.0 Excavation and bedding | 2.2 - Excavation
750dd5c1-7a5e-5079-b02f-719135643082 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 2.0 Excavation and bedding | 2.3 - Bedding material
3e9a7585-87f9-52aa-8591-5cb9bca431e6 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 3.0 Fabrication
813fc089-1868-5f99-83ec-2e3614a4815c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 3.0 Fabrication | 3.1 - Welding
2b3284a3-39a5-53f1-a389-efacdf32f470 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 3.0 Fabrication | 3.2 - Non-Destructive Testing
6b36d2f4-ed6c-5820-b851-b853766fdaaf |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 3.0 Fabrication | 3.3 - Coating and wrapping
c47cb4ab-7d31-561b-87f1-b7c5cbab13c0 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying
b48ad003-9a20-57ff-bd4d-e37e2afd0c01 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying | 4.1 - Lifting into trench
c6199dc8-fb36-53f4-af80-3d53a8237773 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying | 4.2 - Haunching
814b0e45-b920-5360-9d84-178261aaf027 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying | 4.3 - Pressure Testing
cd366d66-d722-5e77-b7bc-583ca258ba2b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying | 4.4 - Backfill Materials
61891b83-7467-5bec-ad3d-40d17f0c108d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 4.0 Laying | 4.5 - Backfill and Compaction
f2c977d3-3d77-5294-a076-0d41c6c1297f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check
1b79f502-484a-5d7b-b3a7-73d2a29aa35f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check | 5.1 - Test Pack
b5479234-ecd1-581a-bbfe-73e4f6148f1b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
4d64a508-8e21-58c8-b992-218f57580793 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check | 5.2 - Survey
80aa7356-490e-5c89-a356-299c684feb7c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check | 5.3 - Quality Submission
2b347813-8c91-55d5-86c7-889846fdcb13 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-001 - North CS (Refer Lot Map) | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
320210e2-8d2e-442e-972b-8edcd5762115 |  | work-in-progress | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections
a18f322b-b851-5731-a1dd-431000270385 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities
1d592557-4b1e-52e3-9c6a-52483c3fa432 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.1 - Set out
edaee2e4-a302-5d63-a5fd-cce8ed48939c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
754be6de-a604-5d2f-9901-12f235469c3f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
82c161ac-ae8c-5ade-a708-e30f646c8b6b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.3 - Permits
b20568b2-2ccc-508e-aad2-c9431f296896 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.4 - Determine Lot Size
6ce10224-c1dc-509b-9275-a9dd09184498 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.5 - Free Issue Materials
591b0e36-524a-5118-bc55-6ec3293ad06d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.6 - Pre-Qualifications
73799e7d-4a02-5989-b9d4-f200240fe318 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
8e2ce445-c0a9-5f44-8f0c-58115b842e4c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
2649b9f7-2d82-536d-b8c4-c66cf08857b2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
08ccb495-9647-5e15-83cb-9cfd61a516d7 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 2.0 Excavation and bedding
f830441b-8e9c-56c9-b806-1050112e9e92 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 2.0 Excavation and bedding | 2.1 - Service Location
e07dc425-3151-5be4-8290-735659cc4713 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 2.0 Excavation and bedding | 2.2 - Excavation
61d00015-493d-540a-8489-99010727c7b4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 2.0 Excavation and bedding | 2.3 - Bedding material
a6840ce2-5fa5-5f51-aecc-c11b86ec56d7 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 3.0 Fabrication
4184a949-0f9f-5ad6-8abe-ac65d62362be |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 3.0 Fabrication | 3.1 - Welding
ca39e0c7-add9-5997-828a-b1657412eb81 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 3.0 Fabrication | 3.2 - Non-Destructive Testing
22e34378-e998-5be7-94f4-057aab1739eb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 3.0 Fabrication | 3.3 - Coating and wrapping
e7b8ddb1-a226-5738-a757-76b44a6d7350 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying
f7bb096a-073f-5f14-a281-ed7784007e9b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying | 4.1 - Lifting into trench
31d6be96-10b1-5a41-8550-a3c6924c816a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying | 4.2 - Haunching
884ae0ba-0706-5f60-96b6-84600f678bb6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying | 4.3 - Pressure Testing
27c9ae58-a861-59f5-92a1-def422c092c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying | 4.4 - Backfill Materials
c0771fdb-a4c0-5c04-add7-05488ec793ed |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 4.0 Laying | 4.5 - Backfill and Compaction
d8bd9a12-c55d-5fe1-994f-0b4dc9265bd9 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check
9f8e04ac-460c-569b-b156-9a2f506cf3f1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check | 5.1 - Test Pack
4ebaca02-2b91-5925-9557-14253b08584f |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
db207a26-1eaa-5063-bd74-f04aa800d22e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check | 5.2 - Survey
7aa1e14a-7c2d-5af2-8fc6-89375c07aa28 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check | 5.3 - Quality Submission
25a16d95-bb10-5347-ae83-19c56593e3e1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-005 - South MH Connections | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
cb21357d-1397-40b4-8d32-394ed3815f5c |  | work-in-progress | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches)
901980e8-63e1-5214-b8d9-8845a055dc57 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities
d24e764c-fdf2-5719-a5f8-488a55dae6ff |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.1 - Set out
1359baff-34ac-5ffc-8c2e-eced6776b3ce |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
b2207d67-6049-5872-b0c6-bc91b9050529 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
fd936bfd-11e5-55e5-b3a6-b82561fc6bd1 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.3 - Permits
a8c1bf53-b88e-5ff4-926f-d3435098e62c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
a7f731e9-eb52-59bc-aded-c8265f8c1e1e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.5 - Free Issue Materials
424ff963-6b2f-5051-999c-dc54ea4ab39a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.6 - Pre-Qualifications
3199de8d-b556-5fa6-b87a-9ed20c97e9bd |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
672be10c-6be7-51c3-886b-039b7fb690d4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
f0c54c4b-ecdd-518b-8198-ec6b691a9976 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
87a39965-c374-5c1d-924d-586afe27920e |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 2.0 Excavation and bedding
60e2721d-1544-5117-9d7f-dc5905685fb4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 2.0 Excavation and bedding | 2.1 - Service Location
80b36213-9504-5bee-9738-7761023d4e4a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 2.0 Excavation and bedding | 2.2 - Excavation
1b0a5c22-8de7-5cc6-b4d7-5e56b38e68e1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 2.0 Excavation and bedding | 2.3 - Bedding material
365433ca-9e91-577d-bfe6-45a28d8555da |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 3.0 Fabrication
1f3dbc80-3bd6-5b48-a6d4-2284dcbf3e35 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 3.0 Fabrication | 3.1 - Welding
b25e325e-ed46-5cc1-9cf9-79b58d29c8b2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 3.0 Fabrication | 3.2 - Non-Destructive Testing
b1f80c81-cd9e-5992-902b-bd634bf808ab |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 3.0 Fabrication | 3.3 - Coating and wrapping
55f08b02-ad4f-5a2d-af95-152f6b5ed102 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying
2d91514e-72c2-5618-9c1a-1384fb42f36b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying | 4.1 - Lifting into trench
6c289df8-8c4b-527f-82aa-3541aebbe7a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying | 4.2 - Haunching
7a25d8e7-6fc3-53bb-a383-59134e17d9a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying | 4.3 - Pressure Testing
aafa7dec-8222-53e7-b2c6-46e36fdd00c1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying | 4.4 - Backfill Materials
17155ab3-8c86-59cd-be9f-d30ebcccc338 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 4.0 Laying | 4.5 - Backfill and Compaction
c07e8f22-c820-55de-9bf9-0a1aa5c82e89 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check
7219d7f3-027a-5888-8551-e74d532b1f6c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check | 5.1 - Test Pack
4ed29b1f-bd1a-5ec3-8684-eb5944cd8fb2 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
f3be1fa2-8970-584f-9520-6dc534e78c75 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check | 5.2 - Survey
ce2d8e84-6b08-5293-904e-80a604b51222 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check | 5.3 - Quality Submission
a0f027ee-7487-5742-81a8-35c526a73571 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-002 - North Misc Carbon Steel (D54981 & Branches) | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
bcd2ab44-8b8d-4401-936b-d5505c5adf2d |  | work-in-progress | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower
86b87a76-819f-525b-9e96-d20375eeef03 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities
1e874b4a-c848-5144-b2d3-d328d67e9770 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.1 - Set out
761fb2cc-2283-524e-9cba-190389ebfa8c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
fb8db6ae-f8d7-5776-ada0-c4a6567a4d35 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
53337b1d-2b86-523e-b4b0-e28379facc82 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.3 - Permits
7143cbed-0f26-514a-bbd6-6e8cd42da401 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.4 - Determine Lot Size
8b4ff591-0d62-56e7-ad2a-f71f58f3756c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.5 - Free Issue Materials
016c9917-6d2a-59e7-a5f6-d0e128e80398 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.6 - Pre-Qualifications
1d69845f-247b-55c4-9746-dcbcd8c30dda |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
e6d27328-c15b-5160-ad9f-58f3165c5059 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
c2e8e9e3-62b3-5a43-8e82-b5361ec3d78e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
48abf9e5-766e-5922-8372-f7c007852dc1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 2.0 Excavation and bedding
32005e60-6510-5022-a6be-ba51f8e520fe |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 2.0 Excavation and bedding | 2.1 - Service Location
f1164893-38b0-5fa1-a05d-8e647b54c068 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 2.0 Excavation and bedding | 2.2 - Excavation
8fa86fa9-b4de-5f8c-82fa-44e5e95792e2 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 2.0 Excavation and bedding | 2.3 - Bedding material
bc5869ee-d2e7-595a-b537-8630371bd629 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 3.0 Fabrication
d9878a1a-b94c-589c-9ec3-f98b73916618 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 3.0 Fabrication | 3.1 - Welding
3a558963-5afa-5b02-a5c6-c05660705c59 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 3.0 Fabrication | 3.2 - Non-Destructive Testing
8e15b395-6b4f-506d-9c08-2b5e9062c091 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 3.0 Fabrication | 3.3 - Coating and wrapping
5281cbfc-0a6c-5790-a3ab-d12d547f5c3f |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying
2b521607-8e2d-59ba-8777-a60048e3b52f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying | 4.1 - Lifting into trench
4d5e13d8-4daf-5dfa-871b-bfba73130f8d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying | 4.2 - Haunching
87151226-23cf-5b4d-9604-4d5630f25fcc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying | 4.3 - Pressure Testing
311fcdc6-b4d7-55f0-957a-054c9bd56a12 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying | 4.4 - Backfill Materials
57bd660c-24dc-5976-90ce-cc4705d01cb5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 4.0 Laying | 4.5 - Backfill and Compaction
94afa3b1-fdd6-5859-9492-d4f12261a8fb |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check
d09c66eb-d441-5426-9a4a-262b6f0208de |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check | 5.1 - Test Pack
278e865e-eb3e-534d-9eb2-e4440bcfab11 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
ec10d69a-3ba6-5d10-a81d-28148344724d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check | 5.2 - Survey
9a6b35d3-bf3a-59b9-a594-18812d02adcb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check | 5.3 - Quality Submission
e18cf0bb-6dfb-5c95-a800-0160527cd8ab |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-003 - Cooling Water Tower | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
a76bcb59-efa7-4482-b03c-2d089ea93069 |  | work-in-progress | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West
353ccb75-02a2-5215-981c-6c693881cf3b |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities
942b04e8-1542-5009-a715-4d61fbc369fe |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.1 - Set out
1de8a22d-0a02-56bb-9319-c8d89161e4e4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
2c067b03-dc55-57e0-834f-aa8ef88e3ed6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
d8b4e8ef-7470-55e5-9ce3-ccf781611dcd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.3 - Permits
2e383796-ca81-55c4-a4f2-3001333a3440 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.4 - Determine Lot Size
9e175466-946c-5ff0-bb64-2cc511d7f418 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.5 - Free Issue Materials
2560678e-61d6-5165-b537-0e12b9e17308 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.6 - Pre-Qualifications
25edada4-649b-5db7-a07c-a2e786529380 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
896c2763-c320-5266-b364-9813bddc30ca |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
83088796-448f-5ace-8ba1-4ce7e82aee9b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
9d9ddd51-d8bc-5fdb-aa69-5a23f5b0f590 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 2.0 Excavation and bedding
869a697b-ba55-571c-938c-33b20c395c69 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 2.0 Excavation and bedding | 2.1 - Service Location
35d56a4f-3668-5cae-bff1-b30a3fa6ed16 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 2.0 Excavation and bedding | 2.2 - Excavation
4168f9df-0951-55d1-9101-ab88c69b1751 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 2.0 Excavation and bedding | 2.3 - Bedding material
c08105ae-b7c4-55df-ae2f-6f1ef1a15541 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 3.0 Fabrication
8841ed01-219e-517d-8153-34d426262f7e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 3.0 Fabrication | 3.1 - Welding
648b7f6f-02b8-54b7-967f-9fedbc5cc5f4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 3.0 Fabrication | 3.2 - Non-Destructive Testing
3f682fc3-115b-522b-8c42-5ca69fe06e5b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 3.0 Fabrication | 3.3 - Coating and wrapping
784120c5-dd11-5d59-b7ed-5d5ba492c91d |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying
17641a00-5015-5326-b1f8-1b11c7109f8c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying | 4.1 - Lifting into trench
6f7091e3-7e14-59f0-99ea-ff7ce246d369 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying | 4.2 - Haunching
af391f99-70c5-5a21-bc24-adc2198bc982 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying | 4.3 - Pressure Testing
7e3b0d82-9b8c-537b-86e9-496a9aa58b9c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying | 4.4 - Backfill Materials
6ceae3b0-ac7c-5f18-9641-e503d4f7a6cd |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 4.0 Laying | 4.5 - Backfill and Compaction
9c3d23e8-bda2-56c3-85a5-b3b123bb6c72 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check
9493b529-cc0d-55a2-8731-ad11d573b9eb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check | 5.1 - Test Pack
78e4acce-a356-510c-a9a9-dc51f72fa3ad |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
82826dd7-9af0-5d18-b92b-7b6d7e4095e6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check | 5.2 - Survey
86faedd9-674e-5d0c-ac6b-dfd3eda19d00 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check | 5.3 - Quality Submission
f8259503-8526-51a5-a9aa-e365869ae029 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-034 Carbon Steel Installation | VIVA-CS-034-004 - South West | 5.0 Testing and Conformance Check | AUTHORITY HOLDPOINT
25820584-bb3d-47d1-a93d-de84a906a66f |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping
931b9bcc-1617-4f15-8a59-316ffc078e34 |  | work-in-progress | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping Rev A | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001
e17dbb25-c0d4-54ec-8246-1df65daa082f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 1.0 Preliminaries
6c6d92d6-5925-5f92-955f-d3486c177717 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 1.0 Preliminaries | 1.1 - Starter Bars
17a6ed27-aa2c-5cbb-8099-23153c4af6af |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 2.0 Pile Cropping
fa1fb93c-1f20-55bb-a256-f8ac3d3f8a0f |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 2.0 Pile Cropping | 2.1 - Set out
35d53e27-c1d8-573c-baa5-dde285b34239 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 2.0 Pile Cropping | 2.2 - Pre-Cutting (if required)
8713a66e-9b63-540b-9336-62a50ec2285b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 2.0 Pile Cropping | 2.3 - Irregular Concrete
440a3b51-63ee-58cb-a7e1-b5906710033f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 3.0 Conformance check
8fbbc420-5159-53a0-ab21-136048829ff3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 3.0 Conformance check | 3.1 - Tolerance
d1ed8046-85bb-527f-a9e6-13b61a507058 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-001 | 3.0 Conformance check | 3.2 - As Builts
735572b0-2e18-4f8f-bd3e-045badbb3764 |  | work-in-progress | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping Rev A | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002
8b648c75-4a3c-5302-a4ff-7bdee69d9ce7 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 1.0 Preliminaries
1a163491-af97-5600-a5ff-bc40fc983f6a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 1.0 Preliminaries | 1.1 - Starter Bars
d5d41e01-89ee-574a-81c4-3db634050b9f |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 2.0 Pile Cropping
5ee5ad71-e94d-52c7-830e-1652eba7c3c0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 2.0 Pile Cropping | 2.1 - Set out
f7ff5cb9-8fdc-59ef-b9ce-ce3324772905 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 2.0 Pile Cropping | 2.2 - Pre-Cutting (if required)
bb300c27-bc9c-5027-baca-02dd8bc9a061 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 2.0 Pile Cropping | 2.3 - Irregular Concrete
73d4f83f-0cb9-5f62-8258-a7fa1193ba0a |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 3.0 Conformance check
a2d675a8-9787-5bda-a04b-ba4c8e7b6238 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 3.0 Conformance check | 3.1 - Tolerance
48650952-6e2d-5c09-a088-22f64c8da03e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-002 | 3.0 Conformance check | 3.2 - As Builts
bcbf0970-5f99-404a-94c0-05a4471db9da |  | work-in-progress | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping Rev A | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003
54d12a6e-71ac-5110-8b98-f3030ecc7a13 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 1.0 Preliminaries
af68909e-e490-546c-b9ef-d49d4e6ebf31 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 1.0 Preliminaries | 1.1 - Starter Bars
3ece1486-8a58-5902-ae49-0332eaf46c29 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 2.0 Pile Cropping
38541608-e138-596c-8250-082f68da3e62 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 2.0 Pile Cropping | 2.1 - Set out
cb24065f-b798-53e4-b05c-668e03038f35 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 2.0 Pile Cropping | 2.2 - Pre-Cutting (if required)
3f59c42c-ca4a-5aeb-b6fd-79ce7cb5f53a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 2.0 Pile Cropping | 2.3 - Irregular Concrete
ef111562-b7a5-5c42-96e6-2941714d9d43 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 3.0 Conformance check
d80497bd-112b-5c14-a6ea-a8ca6ef7c94c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 3.0 Conformance check | 3.1 - Tolerance
a36c07d2-c6d1-5ef3-b268-7f8bc7b8da99 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-003 | 3.0 Conformance check | 3.2 - As Builts
2e23d5fe-f4d9-4cd8-9fc9-a8b45001fc2e |  | work-in-progress | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping Rev A | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004
848e7686-2ec6-5fcc-9afb-db1ef23bf7eb |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 1.0 Preliminaries
40d33658-5d2d-5da7-9052-da02e4c5bced |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 1.0 Preliminaries | 1.1 - Starter Bars
bf69653e-3143-5f90-aa3a-94b2577dbb46 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 2.0 Pile Cropping
117a5f8f-a1c3-5819-a37f-e2574209a755 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 2.0 Pile Cropping | 2.1 - Set out
b010a5f8-f691-54e0-acea-e85049d0c3fd |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 2.0 Pile Cropping | 2.2 - Pre-Cutting (if required)
ec5a4297-ec3a-5f86-b9eb-071a0725f244 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 2.0 Pile Cropping | 2.3 - Irregular Concrete
7844938a-4704-52c3-851d-1c5e5c89e55b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 3.0 Conformance check
6426c2f3-fc81-5354-b1a3-aac27a09972a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 3.0 Conformance check | 3.1 - Tolerance
e9b82bfa-3c97-547c-b2e3-33152f99ab78 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-004 | 3.0 Conformance check | 3.2 - As Builts
aef02aa3-7da0-482c-8893-515360cfe98b |  | work-in-progress | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping Rev A | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005
3d9fdf05-b457-5a00-a5b3-a2e10716d1b6 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 1.0 Preliminaries
85fe0d63-497c-52ef-9d1c-3693939fb79c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 1.0 Preliminaries | 1.1 - Starter Bars
e8e1c73a-9f75-5f25-9bb3-122ba5f6ec41 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 2.0 Pile Cropping
921f82f9-5d94-5533-a831-c0dc1f81dcb3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 2.0 Pile Cropping | 2.1 - Set out
2da506d9-2e75-5ce3-a82e-bedda9d72b72 |  | not-applicable |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 2.0 Pile Cropping | 2.2 - Pre-Cutting (if required)
13476d83-2052-5320-900f-e6ac6191c364 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 2.0 Pile Cropping | 2.3 - Irregular Concrete
8be7136e-7103-51c8-bfac-b8e397b1268b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 3.0 Conformance check
825f1c92-1fad-533d-aa41-b702bd3cfaf4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 3.0 Conformance check | 3.1 - Tolerance
09ed6728-9dda-57f6-abc8-6e164e8319b7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-035 Concrete Pile Cropping | VIVA-PCR-035-005 | 3.0 Conformance check | 3.2 - As Builts
411e5aa6-7d01-455a-a8f5-5b81358954d3 |  | work-in-progress |  | folder | TRUE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation
e2a7d43d-da05-436d-b4ec-48b5d44555c0 |  | work-in-progress | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower
0456e75f-fb57-505f-a70e-e43332f09fb2 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities
7c7f7ed1-a05e-5beb-a7ff-483d245e4cfa |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.1 - Set out
61361677-1adb-5f69-9dba-b1ee0a2061e3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
26441510-2aa6-563d-91aa-1875193ef2f4 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
5fc5f514-13ff-5fe4-8282-2e6964169e65 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.3 - Permits
95fe710f-a3cd-5874-90c0-f91c4b9285a0 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.4 - Determine Lot Size
be76939c-9846-52e1-a76e-ddecaaef4a73 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.5 - Materials
dc2129e5-4940-5026-90c0-97ab0cd9b26a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
29dacdf0-0489-518c-9c91-bee34966299c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
605295ce-8af3-5861-9286-cdce614684d7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
c556d9d8-72d8-5bef-8e9e-a203c876bd47 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
1ef7ad37-d9df-5656-8879-e34af7263637 |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 2.0 Excavation and Bedding
ebbbf806-4ba3-547a-b63c-888c010d0bae |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 2.0 Excavation and Bedding | 2.1 - Service Location
0a2be9fe-113c-57f5-a1b0-5503791fc158 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 2.0 Excavation and Bedding | 2.2 - Excavation
35704c37-b3cf-5807-9a4f-45c7e1af3777 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover
926caa14-f709-5866-b65b-8f82c967b3f4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
f28526e6-8fa7-53b1-be52-018323653d0a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
c0ccea01-d67c-589e-925b-faba53b72a8a |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
dc3fce81-bfec-502d-8a30-373258d36541 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
f5cbe7b0-0b8c-50bc-be6e-236fd4736468 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
3547961d-5b8f-5c9d-840c-53b538ccf338 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
199f5dbc-0b6d-54cf-99e2-0c52896bf060 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.5 - Backfill
a12895a8-793a-5555-8bc8-23df10824f76 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
fe98f0c9-1b08-50a4-9110-7c2d149a85c3 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
0527c735-519e-5f35-a360-837ae2e133b3 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
a285dd13-7afb-544e-827b-383836ad4844 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
e32f6dc4-9913-564c-abb4-816abb30edc5 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
212cdb0b-1224-5b54-9e09-82ffa7e0f48f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
6da67d0c-a38f-51e0-aef1-16689735a653 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-001 - Cooling Water Tower | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
a160c368-b6be-4a91-b098-58c942fc9816 |  | work-in-progress | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111)
6ecd50df-26c7-56cd-9450-5ae4b3f756b5 |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities
3b200c9a-58d5-55da-922e-79af2b8baab7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.1 - Set out
e5d5d706-29f9-5ee2-905a-a8040cb8b2a5 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
fd4b1047-01ce-54b6-960a-5fc59f499b4e |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
52f687b0-b37a-55c6-9bd2-fa37d8bec10c |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.3 - Permits
64bb6ebe-6417-54af-9116-5f9a027f2d1b |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
fa6d9748-dd38-56ec-84bd-b41cfa0428f6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.5 - Materials
e2e93a2f-e90d-55fc-8980-bd1e54a86bef |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
0fa8a25c-a41f-5b66-9f6c-1af2c0572642 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
ea590dab-bb55-52ab-8f74-94b8a9d156ab |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
2a85108d-04ab-5571-a0f0-cef981c63f7c |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
e638bdd0-b0a5-5be6-9cbc-324cc18f074b |  | pass |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 2.0 Excavation and Bedding
bd799c64-5f3d-5cbe-a001-a32feab30c23 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 2.0 Excavation and Bedding | 2.1 - Service Location
282acd53-874f-515c-911d-675e3ab5f0ea |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 2.0 Excavation and Bedding | 2.2 - Excavation
861e1efb-a8f2-5474-b37d-6c387a339f1c |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover
dd4b1f1f-1526-5aff-a04b-25b52c4e6863 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
09c56fd4-2c96-5f03-bb4b-f8ceb313d958 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
84f57d53-1a52-5d81-99d4-f4c40005d9b8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
874b3d7f-7295-5d8d-851f-b20e349e88ff |  | work-in-progress |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
f6330713-70ca-5aa2-bb72-c750bfccd4d4 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
70140f56-80ed-540d-a11e-d98cc60d5e55 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
d7cfbce7-a321-5d1e-af18-5eaab3bc299c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.5 - Backfill
3fe2995e-17e2-510c-9d94-2cbd3579c382 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
f8909130-9378-5f0d-9b2f-342807b2189e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
6d8ac12c-fd98-5e63-a058-55907ff51d49 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
e0ec3248-360b-55c1-84b1-c3995c7c4b7c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
c28ba749-43e1-5689-87b8-73789c26d9dc |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
bbebdb04-b33f-5c60-8903-2cb10c4b5a05 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
ec99287f-fa18-5c94-99ef-41afececc597 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-002 - North Earthing (CWA111) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
14a05ef1-a220-4d54-b23b-b4ebd036f0e1 |  | work-in-progress | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation
569e834c-f76b-51a2-a97f-ddfe83c8a82d |  | work-in-progress |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities
04524e38-267a-55d9-a5e3-edb2a33433dc |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.1 - Set out
235af901-8beb-5a41-98e1-982c4c662299 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
66525fa5-17dc-5d36-83e8-0098b931ce0f |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
d2624563-7b04-5986-877d-aa6df9c1eda9 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.3 - Permits
7ab9f4d8-d404-5246-8a1d-dd3e58f33bb7 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.4 - Determine Lot Size
0c6ff371-31c6-54cb-bba1-29f9a6e57116 |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.5 - Materials
01f4bc78-4c41-54b4-acb8-13e25f8e942e |  | pass |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
d97a235b-3253-5ff7-a9bf-ebb22158ef14 |  | pass |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
126ab904-3308-59b3-9509-d5c9befef10d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
968f8adf-454e-533b-92c6-a18b6e0a488b |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
5bf20145-ee32-5db5-b77d-9a32f8c08d19 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 2.0 Excavation and Bedding
0222394a-06e8-5124-9c37-f17b2e4d605e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 2.0 Excavation and Bedding | 2.1 - Service Location
440c235c-f995-59ad-8f76-536fb0af4348 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 2.0 Excavation and Bedding | 2.2 - Excavation
c78e5ac4-4e81-5fdd-afef-03296a13ccbf |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover
ebdca763-6a22-5ce9-8419-a08b3fab8aa4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
db46edc9-e154-5212-ab67-e3b1a9087fe6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
12f3f883-962f-5bbb-96d6-f7d207bd076a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
b1a4c312-3f75-59ad-8042-35f699f7b9f8 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
06ae5826-7e8d-563e-83e0-f8b43bee7417 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
a7d29321-946e-560f-8e79-ba2a9401c0d7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
a997917b-8c22-5a74-836b-737bc76e1eaf |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.5 - Backfill
05668149-2c46-5f6e-9985-3ff56353236b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
7947e76d-a89f-5f6f-a02f-4d506655c79d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
f7b436d9-d304-56eb-8443-41aa815fc166 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
50da22e4-e918-537c-82d7-2855d3263581 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
647654ee-09e2-5720-ae74-4016839d9055 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
6d475809-656e-5880-a534-2e3213cbfea4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
5368ceeb-d507-5ac3-b7d6-473db8f12d6e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | VIVA-EGD-037-003 - Earthing Substation | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
1012c107-81f6-4989-bec2-96bf1f162a8f |  | not-started | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map)
3c93b0dd-5ccf-506c-9d96-66a5a1d03cf3 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities
1c2b2515-6fee-594b-bced-0713fd376eb9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.1 - Set out
2b10bd58-98fa-5575-8bf3-0962e9139ff8 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
c0aacf2a-9325-5fab-9b15-7745c349641e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
cb553696-7eb4-51de-9069-183cfa8eb9ef |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.3 - Permits
fccdca1a-d6f8-5ff1-8bef-04f8175b8385 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
b501bc9a-b646-52e0-ab6b-fcac546c314b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.5 - Materials
0140dead-871f-5975-ab48-3a430a4fb5e4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
379d62d6-00ba-50ed-8b84-725d32b35ee6 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
2a6fe11e-7ff4-523b-a6a5-df3c4e8128bb |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
726b8415-a696-5100-b2ba-5fe6fef43d5d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
b08c650f-e4d5-5e87-a931-bd1f83e60049 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 2.0 Excavation and Bedding
cf25f77e-0865-5f00-9c0f-dbda311098a3 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 2.0 Excavation and Bedding | 2.1 - Service Location
a3b5e1bc-2a4c-5e7f-8066-ae341fe5624d |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 2.0 Excavation and Bedding | 2.2 - Excavation
f1ec7ecf-0efb-517a-bb43-dc9f320ed3b2 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover
89c8ad53-e304-527a-ba4a-fc36590357fc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
9ce4c6a9-3051-519d-8d2c-13649f4478c5 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
dee147b1-7da4-5211-b72c-6e2cad71b5c0 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
4f722989-2fb9-522c-9762-9328b163e4e7 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
d801d2b4-2976-5ae2-bcc6-c746c35bf7f1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
254becde-d6ed-55ed-8898-956b90692a70 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
ac2d0c60-a859-53ae-aab1-aa0a2d89c490 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.5 - Backfill
54e3eaf2-615a-52af-b6b7-8fbb428dbfd4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
8c733a83-7385-51e9-b5ea-8833b4cae81e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
74201888-0869-59e0-ada1-aa41b9669d44 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
3f2edf3d-0433-58b6-8423-2bf56a8d7a5f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
aa5658a2-1bfa-5771-91c2-9ad91b8058ba |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
90effd43-be16-5d6c-bc5a-7ea4f16fe2c4 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
10233197-e2e7-5236-a930-d15fc45e619d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-004 - Central (See Lot Map) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
7d452f1b-abda-4ce2-ac0c-8450ab2d5b97 |  | not-started | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114)
406747a0-ce6b-515d-a2eb-5a2a0c964b71 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities
019bec98-96de-5ebb-a725-df1c29430860 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.1 - Set out
dd034e8e-7100-5200-b1ad-907123c9467c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
229d8696-31ab-53c6-a79b-6a8a4a2736a3 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
6685ff79-6fbd-5b02-abdd-de9b6bdd840b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.3 - Permits
a9d4ebe3-0b0f-5615-a869-ff144cd90004 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
7efb4147-ffb9-5b9b-97db-0c6b4d09d667 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.5 - Materials
7ba888fd-2e02-5b85-b6c8-aaa1133aa262 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
8a86e145-7a78-52ba-a72c-575c6781874a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
64ee54f2-dcb8-5e1e-8ea6-0b91b647703a |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
e9a5cb13-2505-50f0-aa73-fa24bc264c7e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
8bc93127-6a43-5005-9f5a-426cc569eca0 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 2.0 Excavation and Bedding
120b52e3-6538-5e67-8cfc-a455aad4307e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 2.0 Excavation and Bedding | 2.1 - Service Location
7d29408e-2bb9-5de3-8138-a85296a4291f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 2.0 Excavation and Bedding | 2.2 - Excavation
c0a516e3-d5f7-5983-982e-3a44428e9e52 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover
aabdf209-4470-5fde-bae5-e4f381c9a0a1 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
3bba3cea-1adf-5da0-9b4f-24a0924bc70e |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
1ad4606a-6d8a-57c4-9333-95fb57aab0ac |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
615d079c-c11f-5a27-a8ea-080e69f5204a |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
98d24303-dd8b-525b-928e-3ed0fc472cab |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
5a79b5c8-f777-5e7a-b82a-36ff49e1a82d |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
f9c399a9-ff68-5f44-b98f-e97d3bc2c4d7 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.5 - Backfill
ccfee231-e998-5412-9903-75f9b3c8b98c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
9987c361-6315-5362-95ad-03551e151576 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
f36ecf05-9970-5aec-8453-8af7cc10a390 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
f23d5bfc-cd6d-52c5-8522-065c10489212 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
9cec82c0-f198-53ab-a159-b729ed570d45 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
a9feac6e-4278-5c59-bc6c-a0233d0fe2fa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
3944ffa9-5871-5f6b-9ed5-019b6310edd0 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-005 - South West (Areas 113/114) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
b477df73-c637-463f-a47d-20083b89d81a |  | not-started | INF-HSEQ CC0398-ITP-037 Earthing Installation Rev C | checklist | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05)
0965a7be-ac5e-581c-ad16-74add41e6a9c |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities
255e277f-c8f8-5610-acb1-d38b02952c3b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.1 - Set out
313746c8-82ab-51d4-8d04-9697415b49b9 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.2 - IFC Submission & Approval
76557711-0e14-59e3-a056-e4225b65f1b1 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
04dd310f-c851-5aa1-9bfa-6fa943a92a94 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.3 - Permits
cefa01a7-aae8-5066-abc9-b2df4ce23719 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.4 - Determine Lot Size
4bc48948-e368-53ae-bf19-a74837f7ca28 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.5 - Materials
babc3f3b-8105-5d45-a20b-c4f472d2c76c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.6 - Electrical and Earthing Pre- Qualification
d0b4adc7-d61b-51c9-9e2e-887fb6079fe5 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
76cf66d4-8bb4-5a05-a516-9da3b6c1ebad |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | 1.7 - Bedding and Backfill Materials Approval
359bdeae-b88c-54b2-9b05-d574a4c7da46 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 1.0 Pre-start activities | AUTHORITY HOLDPOINT
e3a6f8e8-5da6-5bd2-ab9e-9c7c44caaae1 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 2.0 Excavation and Bedding
af6915bd-02ea-5681-9c49-15e37dd3e033 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 2.0 Excavation and Bedding | 2.1 - Service Location
b90b3f03-8cbc-5dbb-9d9d-152900130f20 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 2.0 Excavation and Bedding | 2.2 - Excavation
ccb14e76-fd61-5cbe-a0f1-73eff1121f50 |  | not-started |  | section | FALSE | FALSE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover
52d66903-4a2d-51c1-baed-81d5e889e751 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.1 - Earthing Installation
41f12b59-3e8e-51d5-b08a-b8fbe2ce770c |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.2 - VIVA electrical inspection
48fa05c5-488e-55b0-949f-9bc92e5e603f |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.3 - Earthing Network
b0b49724-7cdc-575b-b566-d55eb7d2610c |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
eecb27ac-e955-5235-ad17-4ac8fef996dc |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.4 - Electrical Earthing by Area
840418a7-deb7-5697-9733-ed267c8e954e |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
fc8f33ee-13fc-5288-882c-8ab394e3f52b |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.5 - Backfill
ea10df77-29ce-5442-b539-651fc3803745 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.6 - Clean-up of site
d91f9a04-a39e-5766-a5df-8f64b85574aa |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.7 - Identification and recording
d44fb996-0952-50eb-a621-efdc94e535cd |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
a40d9f6c-f872-5ded-a3bb-0a23d09bf8b6 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.8 - Work is complete and complies with design plans / drawings / specs
ead0fb1e-e4b9-58a3-9c30-e9f99a77fa10 |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT
baeed298-0df4-543e-a12c-a4defd491e98 |  | not-started |  | checkpoint | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | 3.9 - Certificate of electrical safety
9bc7dd35-0fca-56fe-8b79-2af6a882d3cb |  | not-started |  | signoff | TRUE | TRUE | INF-HSEQ CC0398-ITP-037 Earthing Installation | CC0398-037-EGD-006 - East (Around Ks/ PAU-05) | 3.0 Laying/Welding/Handover | AUTHORITY HOLDPOINT