## Folder Structure
CRL Porcelain Cladding QA
Aotea Station
| WST L0 Entrance North | External Tile Cladding Checklist
| WST L0 Entrance South | External Tile Cladding Checklist
| WST B1 Escalator | External Tile Cladding Checklist
| VST East Entrance South | External Tile Cladding Checklist
| VST East Entrance North | External Tile Cladding Checklist
| VST B1 Entrance South 02 | External Tile Cladding Checklist
| B3 Platflorm Escalator 006 & 007 - Elevation 1 | External Tile Cladding Checklist
| B3 Platflorm Escalator 006 & 007 - Elevation 2 | External Tile Cladding Checklist
| B3 Platflorm Escalator 006 & 007 - Elevation 3 | External Tile Cladding Checklist
| B3 Platflorm Escalator 008 & 009 - Elevation 1 | External Tile Cladding Checklist
| B3 Platflorm Escalator 008 & 009 - Elevation 2 | External Tile Cladding Checklist
| B3 Platflorm Escalator 008 & 009 - Elevation 3 | External Tile Cladding Checklist
| B3 Platflorm Escalator 010 & 011 - Elevation 1 | External Tile Cladding Checklist
| B3 Platflorm Escalator 010 & 011 - Elevation 2 | External Tile Cladding Checklist
| B3 Platflorm Escalator 010 & 011 - Elevation 3 | External Tile Cladding Checklist
| B3 Platflorm Escalator 012 & 013 - Elevation 1 | External Tile Cladding Checklist
| B3 Platflorm Escalator 012 & 013 - Elevation 2 | External Tile Cladding Checklist
| B3 Platflorm Escalator 012 & 013 - Elevation 3 | External Tile Cladding Checklist
K Road Station
| BSQ L0-B2 North | External Tile Cladding Checklist
| BSQ L0-B2 South | External Tile Cladding Checklist
| BSQ L0-B2 West | External Tile Cladding Checklist
| BSQ L0-B2 East | External Tile Cladding Checklist
| BSQ Bulkhead | External Tile Cladding Checklist
| BSQ B2-B6 North | External Tile Cladding Checklist
| BSQ B2-B6 South | External Tile Cladding Checklist
| BSQ B2-B6 East | External Tile Cladding Checklist
| MLA L0-B6 North | External Tile Cladding Checklist
| MLA L0-B6 South | External Tile Cladding Checklist
| MLA L0-B6 West 1 | External Tile Cladding Checklist
| MLA L0-B6 West 2 | External Tile Cladding Checklist
| MLA L0-B6 East | External Tile Cladding Checklist
| MLA bulkhead | External Tile Cladding Checklist
Mt Eden Station
| FOH - L0 Zone 2 - Paid Concourse | External Tile Cladding Checklist
| FOH - L0 Zone 2 - Ticket Window | External Tile Cladding Checklist
| CRL Platform - Egress Stair V72 -Elevation 1 | External Tile Cladding Checklist
| CRL Platform - Egress Stair V72 -Elevation 2 | External Tile Cladding Checklist
| CRL Platform - Egress Stair V72 -Elevation 3 | External Tile Cladding Checklist
| CRL Platform - Stair V63 -Elevation 1 | External Tile Cladding Checklist
| CRL Platform - Stair V63 -Elevation 2 | External Tile Cladding Checklist
| CRL Platform - Stair V63 -Elevation 3 | External Tile Cladding Checklist
| CRL Platform - Escalator-Elevation 1 | External Tile Cladding Checklist
| CRL Platform - Escalator-Elevation 2 | External Tile Cladding Checklist
| CRL Platform - Escalator-Elevation 3 | External Tile Cladding Checklist
| CRL Platform - CRL Rail System -Elevation 1 | External Tile Cladding Checklist
| CRL Platform - CRL Rail System -Elevation 2 | External Tile Cladding Checklist
| CRL Platform - CRL Rail System -Elevation 3 | External Tile Cladding Checklist
| CRL Platform - CRL Rail System -Elevation 4 | External Tile Cladding Checklist
| NAL Platform - Comms Node-Elevation 1 | External Tile Cladding Checklist
| NAL Platform - Comms Node-Elevation 2 | External Tile Cladding Checklist
| NAL Platform - Comms Node-Elevation 3 | External Tile Cladding Checklist
| NAL Platform - Comms Node-Elevation 4 | External Tile Cladding Checklist
| NAL Platform - Escalator-Elevation 1 | External Tile Cladding Checklist
| NAL Platform - Escalator-Elevation 2 | External Tile Cladding Checklist
| NAL Platform - Escalator-Elevation 3 | External Tile Cladding Checklist
| NAL Platform - NAL Stair-Elevation 1 | External Tile Cladding Checklist
| NAL Platform - NAL Stair-Elevation 2 | External Tile Cladding Checklist
| NAL Platform - NAL Stair-Elevation 3 | External Tile Cladding Checklist

## Checklists
Type | Name | Values
Checklist | External Tile Cladding Checklist
Section | Substrate inspection
checkpoint | Check for visible cracks
Services penetration done by others
Assess if wall out of plumb/square and if packers can accommodate the issue
Check for seismic/ control joint location
No damage on waterproofing
Section | Setting Out for Substructure
Checkpoint | RL provided by main contractor
Label | Cavity gap (insert)
Checkpoint | Control of horizontal and vertical lines
Checkpoint | Control of Plumb Line
Checkpoint | Setting out follows shop drawings
Section | Sub-structure Installation
Subsection | Select Type of Substrate (can be checked or left empty)
Tick box | Timber
Tick box | Concrete
Tick box | Blockwall
Tick box | LGS Framing
Tick box | Structural Steel
Label | Others - please specify
Subsection | Fixing bracket to Substrate
Tick box | Concrete - M10 Anchor / Min Embedment 65mm
Tick box | Blockwall - M16 Anchor Chem Set / Min Embedment 85mm
Tick box | LGS Framing - 14G x 65 SDS
Tick box | Structural Steel - M10 Hollowbolt
Label | Others - please specify
Subsection | Bracket Installation
Max 500mm Vertical Spacing
Max 500mm Horizontal Spacing
Checkpoint | Material selection as per M-A-R
Checkpoint | Max Cantilever 250mm
Label | Others - please specify
Subsection | Fixing vertical rail to brackets
Material selection as per M-A-R
Min Edge Distance 13mm
Subsection | Fixing NV3 rail to vertical rail
Max Vertical Spacing 500mm
Max Vertical Spacing 450mm (for perforated panel)
Subsection | Joint Closer
Check alignment of NV3
Subsection | Acoustic Insulation
Checkpoint | 50mm Black acoustic installed
Checkpoint | Pin installed & secured
Section | Panels Installation
Checkpoint | All interfaces by other trades are finished
Checkpoint | All services by others are finished
Checkpoint | Setting out according to shop drawing
Checkpoint | Panels no chipping / damage / crack
Checkpoint | Panels installed are fix properly and not moving or rattling
Checkpoint | Fixing lock screw on top hanger
Section | Final Clean
Checkpoint | Clean all debris and stain
Section | Sign Off
Check Point | Sign Off and Handover