## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Whangarei Odour Control Plant Upgrade Sewpercoat Spray | itp |  |  |  |  | ITP - Whangarei Odour Control Plant Upgrade Sewpercoat Spray
section | Pre-construction
checkpoint | 1 - Construction drawings and specifications from Designer(s)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Construction drawings and specifications from Client/ Engineer
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
label | Conformance Criteria - confirmation in writing
label | Records - Drawing Transmittal
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
holdpoint | HOLD POINT
checkpoint | 2 - Pre-construction meeting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prior to commencing works, a pre-start meeting to be held with client to confirm
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
label | Conformance Criteria - sewage isolation process agreed signed off
label | Records - Meeting Minutes/signed-off documents
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
holdpoint | HOLD POINT
checkpoint | 3 - Pre-works Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Contractor to arrange a joint inspection of the relevant areas, within and outside the working areas, with Engineer, Principal and relevant landowners/ occupiers
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
label | Conformance Criteria - Confirmation in writing from all parties that the record is a true representation of the inspection
label | Records - Marked up Drawing
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
checkpoint | 5 - Site access (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - United Civil to grant site access to Contech
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
label | Conformance Criteria - Access Permits.
label | Records - Signed-off documents
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
holdpoint | HOLD POINT
checkpoint | 5 - Site access (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - United Civil to erect a scaffold no more thsn 400mm from the workface
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
label | Conformance Criteria - signed off ready to use
label | Records - signed off documents
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
holdpoint | HOLD POINT
checkpoint | 6 - Work instruction signoff
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Work Instructions produced for works
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
label | Conformance Criteria - Staff to sign onto the JSA prior to commencement of work onsite
label | Records - Signed-off documents
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil /Contech
holdpoint | HOLD POINT
section | Materials and Procurement
checkpoint | 8 - Sewpercoat ordered and compliant, and delivery to be timely
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet quality; be the right quantity and delivered on time
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Testing
label | Conformance Criteria - Cube Strength Results to be supplied
label | Records - Lab Strength Testing Report
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
checkpoint | 9 - Sewpercoat on site, and correctly stockpiled/Stored
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to be stored on site in a dry area
label | Frequency / Timing - Pre-construction
label | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
label | Conformance Criteria - Material stored in Contech Warehouse until Required on-site, then Stored in Covered Location on-site
label | Records - Photos
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
section | Construction and Installation
checkpoint | 10 - Concrete surface preparation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete surface preparation with hydroblasting to have an adequate profile roughness.
label | Frequency / Timing - Before start spraying
label | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
label | Conformance Criteria - The concrete surface must be prepared to have a minimum roughness equivalent to CSP 5 (ICRI)
label | Records - Photos/Videos/ Record sheet
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
holdpoint | HOLD POINT
checkpoint | 11 - Sewpercoat lining thickness
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Sewpercoatlining thickness
label | Frequency / Timing - Continuous Monitoring
label | Inspection / Test Method submission, visual inspection, testing, measure, - Measurement
label | Conformance Criteria - Thickness tests using caliper depth measuring blade, average thickness of 25 mm, no measurement less than 25 mm, above substrate (concrete surface)
label | Records - Photos/Videos/ Record sheet
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
checkpoint | 13 - Pull-off (adhesion) testing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - In situ Pull-off tests according to the Standard Test Method for Tensile Strength of Concrete Surfaces and the Bond Strength or Tensile Strength of Concrete Repair and Overlay Materials by Direct Tension (Pull-off Method) -
label | Frequency / Timing - 2 tests in each structure
label | Inspection / Test Method submission, visual inspection, testing, measure, - Testing
label | Conformance Criteria - Pull-off test to achieve a minimum of 1 MPa
label | Records - QA Sheet, photos
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
checkpoint | 14 - Post Sewpercoat lining Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - video survey of the Structure to be undertaken post application of sewpercoat
label | Frequency / Timing - After supepercoat application on each chamber
label | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
label | Conformance Criteria - Survey complete
label | Records - Photos/Videos
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
holdpoint | HOLD POINT
section | Handover, Commissioning and Completion
checkpoint | 15 - Close out QA/QC
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all QA/QC is complete are closed out and recorded
label | Frequency / Timing - After completion
label | Inspection / Test Method submission, visual inspection, testing, measure, - Review
label | Conformance Criteria - QA/QC Documents delivered, ITP Signed and Submitted
label | Records - Signed-off ITP, technical reports
label | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
checkpoint-no-status | Comments and Non-conformances
textbox | Reference Documentation:
checkpoint | Acceptance of ITP
label | Author
date | Author - Date:
textbox | Author - Name:
label | Project Manager
date | Project Manager - Date:
textbox | Project Manager - Name:
label | Client
date | Client - Date:
textbox | Client - Name:
holdpoint | Signature
checkpoint | Authorised Signature and Initials Register
textbox | (1) Name:
textbox | (1) Initials:
textbox | (1) Organisation:
date | (1) Date of Final Sign Off:
textbox | (2) Name:
textbox | (2) Initials:
textbox | (2) Organisation:
date | (2) Date of Final Sign Off:
textbox | (3) Name:
textbox | (3) Initials:
textbox | (3) Organisation:
date | (3) Date of Final Sign Off:
holdpoint | Signature