## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Commisioning |  | Commisioning | 327b1920-e19e-4ed0-a048-7617d07482a3
| section | Details
| checkpoint | Bulk Hot Water
| checkpoint | Test RPZD
| checkpoint | Test Hot Water Temperature
| checkpoint | Test Waste for leaks
| checklist | Corridor |  | Corridor | 433ea6c5-1f3c-41d0-b43f-5a630092da8e
| section | Details
| checkpoint | Hose Reel Line
| checkpoint | Hot Water
| checkpoint | Hot Water Lagged
| checkpoint | Cold Water
| checkpoint | Test Hot Water
| checkpoint | Test Cold Water
| checkpoint | Fire Caulking (Corridor)
| checklist | Drains |  | Drains | 50ce03dd-f477-45f0-b0e0-960f2c33aa8d
| section | Details
| checkpoint | Drains
| checkpoint | Smoke Seal Penetrations
| checkpoint | Fire Collar
| checkpoint | Acoustic Lagging
| checkpoint | Testing (Water/Air)
| checklist | Fit Off |  | Fit Off | 46cef60b-6223-43ea-8753-42ca2931b8c0
| section | Details
| checkpoint | Vinyl Floor Waste
| checkpoint | Hand Basin
| checkpoint | Shroud installed
| checkpoint | Scrub Trough
| checkpoint | Ministops/ Ball Valve
| checkpoint | Fixture Waste
| checkpoint | Mixer installed
| checkpoint | Dishwasher
| checkpoint | Sink
| checkpoint | Trough
| checkpoint | Fire hose Reels
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checklist | Inground Works |  | Inground Works | ddac9f56-3294-4505-8b18-06e9c15874b1
| section | Details
| checkpoint | Top of pits installed to correct height
| checkpoint | Testing of drains
| checkpoint | Correct loactions of all pits / drainage points
| checkpoint | Fire Hydrant Supply
| checkpoint | Cold Water Supply
| checklist | Penetrations |  | Penetrations | b04995d7-c70c-4ca1-b326-968c70fd2cec
| section | Details
| checkpoint | Set Out
| checkpoint | Fire Collar Installation
| checkpoint | Scanning
| checklist | Plant and Equipment |  | Plant and Equipment | 999ddc8f-d3fe-48a9-af21-8c69e7c12dce
| section | Details
| checkpoint | Hot water system
| checkpoint | Heat pumps
| checklist | Rough In |  | Rough In | 016a4c25-6d84-4aa4-adee-31d213a7c630
| section | Details
| checkpoint | High Level Rough In
| checkpoint | Noggins Marked
| checkpoint | Wall Set Out
| checkpoint | In-Wall TMV
| checkpoint | In-Wall RPZD
| checkpoint | Wall Rough In
| checkpoint | Waste Rollovers
| checkpoint | Test Water