## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Commisioning |  | Commisioning | a98ae8f2-1b63-4eef-8c0d-df882f597d4f
| checkpoint | Bulk Hot Water
| checkpoint | Test Hot Water Temperature
| checkpoint | Test Waste for leaks
| checklist | Corridor/Shafts |  | Corridor/Shafts | caae1443-824b-43ab-9c9a-bce03d85f42d
| checkpoint | Hot Water
| checkpoint | Hot Water Lagged
| checkpoint | Cold Water
| checkpoint | Test Hot Water
| checkpoint | Test Cold Water
| checkpoint | PRV'S installed
| checkpoint | Fire Caulking to Apt
| checklist | Drains |  | Drains | 20ab26d1-a3b3-43bd-adc7-afe7648643e9
| checkpoint | Drains
| checkpoint | Smoke Seal Penetrations
| checkpoint | Acoustic Lagging
| checkpoint | Testing (Water/Air)
| checklist | Fit Off |  | Fit Off | aea657fa-7980-414e-ae4b-afd61c309c58
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checklist | Plant and equipment |  | Plant and equipment | eb8de2a9-dbc0-4dca-8147-b3b92eda9434
| checkpoint | Hot water system
| checkpoint | Cold water pump
| checkpoint | Cold water break tank
| checkpoint | Rainwater pump
| checkpoint | Rainwater tank / Diversion valve
| checkpoint | Water meter assembly
| checkpoint | GIT
| checklist | Rough In |  | Rough In | eb644cf7-c403-4063-bf58-f2f537cf106a
| checkpoint | High Level Rough In
| checkpoint | Wall Set Out
| checkpoint | Wall Rough In
| checkpoint | Waste Rollovers & AAV'S
| checkpoint | Test Water