## Sheet1
1 | Construction drawings and specifications from Designer(s) | H | Construction drawings and specifications from Client/ Engineer | Pre-construction | Document Review | confirmation in writing | Drawing Transmittal | United Civil | 1 - Construction drawings and specifications from Designer(s) | ACTION (Hold, Monitor, Witness) - H | Detail - Construction drawings and specifications from Client/ Engineer | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review | Conformance Criteria - confirmation in writing | Records - Drawing Transmittal | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | 1 - Construction drawings and specifications from Designer(s)
2 | Pre-construction meeting | H | Prior to commencing works, a pre-start meeting to be held with client to confirm | Pre-construction | Document Review | sewage isolation process agreed signed off | Meeting Minutes/signed-off documents | United Civil | 2 - Pre-construction meeting | ACTION (Hold, Monitor, Witness) - H | Detail - Prior to commencing works, a pre-start meeting to be held with client to confirm | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review | Conformance Criteria - sewage isolation process agreed signed off | Records - Meeting Minutes/signed-off documents | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | ACTION (Hold, Monitor, Witness) - H
3 | Pre-works Inspection | W | Contractor to arrange a joint inspection of the relevant areas, within and outside the working areas, with Engineer, Principal and relevant landowners/ occupiers | Pre-construction | Visual Inspection | Confirmation in writing from all parties that the record is a true representation of the inspection | Marked up Drawing | United Civil | 3 - Pre-works Inspection | ACTION (Hold, Monitor, Witness) - W | Detail - Contractor to arrange a joint inspection of the relevant areas, within and outside the working areas, with Engineer, Principal and relevant landowners/ occupiers | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection | Conformance Criteria - Confirmation in writing from all parties that the record is a true representation of the inspection | Records - Marked up Drawing | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | Detail - Construction drawings and specifications from Client/ Engineer
5 | Site access | H | United Civil to grant site access to Contech | Pre-construction | Document Review | Access Permits. | Signed-off documents | United Civil | 5 - Site access | ACTION (Hold, Monitor, Witness) - H | Detail - United Civil to grant site access to Contech | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review | Conformance Criteria - Access Permits. | Records - Signed-off documents | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | Frequency / Timing - Pre-construction
|  | H | United Civil to erect a scaffold no more thsn 400mm from the workface | Pre-construction | Visual Inspection | signed off ready to use | signed off documents | United Civil | - | ACTION (Hold, Monitor, Witness) - H | Detail - United Civil to erect a scaffold no more thsn 400mm from the workface | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection | Conformance Criteria - signed off ready to use | Records - signed off documents | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
6 | Work instruction signoff | H | Work Instructions produced for works | Pre-construction | Document Review | Staff to sign onto the JSA prior to commencement of work onsite | Signed-off documents | United Civil /Contech | 6 - Work instruction signoff | ACTION (Hold, Monitor, Witness) - H | Detail - Work Instructions produced for works | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review | Conformance Criteria - Staff to sign onto the JSA prior to commencement of work onsite | Records - Signed-off documents | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil /Contech | Conformance Criteria - confirmation in writing
8 | Sewpercoat ordered and compliant, and delivery to be timely | W | Material to meet quality; be the right quantity and delivered on time | Pre-construction | Testing | Cube Strength Results to be supplied | Lab Strength Testing Report | Contech | 8 - Sewpercoat ordered and compliant, and delivery to be timely | ACTION (Hold, Monitor, Witness) - W | Detail - Material to meet quality; be the right quantity and delivered on time | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Testing | Conformance Criteria - Cube Strength Results to be supplied | Records - Lab Strength Testing Report | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | Records - Drawing Transmittal
9 | Sewpercoat on site, and correctly stockpiled/Stored | W | Material to be stored on site in a dry area | Pre-construction | Document Review | Material stored in Contech Warehouse until Required on-site, then Stored in Covered Location on-site | Photos | Contech | 9 - Sewpercoat on site, and correctly stockpiled/Stored | ACTION (Hold, Monitor, Witness) - W | Detail - Material to be stored on site in a dry area | Frequency / Timing - Pre-construction | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review | Conformance Criteria - Material stored in Contech Warehouse until Required on-site, then Stored in Covered Location on-site | Records - Photos | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
10 | Concrete surface preparation | H | Concrete surface preparation with hydroblasting to have an adequate profile roughness. | Before start spraying | Visual inspection | The concrete surface must be prepared to have a minimum roughness equivalent to CSP 5 (ICRI) | Photos/Videos/ Record sheet | Contech | 10 - Concrete surface preparation | ACTION (Hold, Monitor, Witness) - H | Detail - Concrete surface preparation with hydroblasting to have an adequate profile roughness. | Frequency / Timing - Before start spraying | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection | Conformance Criteria - The concrete surface must be prepared to have a minimum roughness equivalent to CSP 5 (ICRI) | Records - Photos/Videos/ Record sheet | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | 2 - Pre-construction meeting
11 | Sewpercoat lining thickness | M | Sewpercoatlining thickness | Continuous Monitoring | Measurement | Thickness tests using caliper depth measuring blade, average thickness of 25 mm, no measurement less than 25 mm, above substrate (concrete surface) | Photos/Videos/ Record sheet | Contech | 11 - Sewpercoat lining thickness | ACTION (Hold, Monitor, Witness) - M | Detail - Sewpercoatlining thickness | Frequency / Timing - Continuous Monitoring | Inspection / Test Method submission, visual inspection, testing, measure, - Measurement | Conformance Criteria - Thickness tests using caliper depth measuring blade, average thickness of 25 mm, no measurement less than 25 mm, above substrate (concrete surface) | Records - Photos/Videos/ Record sheet | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | ACTION (Hold, Monitor, Witness) - H
13 | Pull-off (adhesion) testing | M | In situ Pull-off tests according to the Standard Test Method for Tensile Strength of Concrete Surfaces and the Bond Strength or Tensile Strength of Concrete Repair and Overlay Materials by Direct Tension (Pull-off Method) - | 2 tests in each structure | Testing | Pull-off test to achieve a minimum of 1 MPa | QA Sheet, photos | Contech | 13 - Pull-off (adhesion) testing | ACTION (Hold, Monitor, Witness) - M | Detail - In situ Pull-off tests according to the Standard Test Method for Tensile Strength of Concrete Surfaces and the Bond Strength or Tensile Strength of Concrete Repair and Overlay Materials by Direct Tension (Pull-off Method) - | Frequency / Timing - 2 tests in each structure | Inspection / Test Method submission, visual inspection, testing, measure, - Testing | Conformance Criteria - Pull-off test to achieve a minimum of 1 MPa | Records - QA Sheet, photos | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | Detail - Prior to commencing works, a pre-start meeting to be held with client to confirm
14 | Post Sewpercoat lining Survey | H | video survey of the Structure to be undertaken post application of sewpercoat | After supepercoat application on each chamber | Visual inspection | Survey complete | Photos/Videos | Contech | 14 - Post Sewpercoat lining Survey | ACTION (Hold, Monitor, Witness) - H | Detail - video survey of the Structure to be undertaken post application of sewpercoat | Frequency / Timing - After supepercoat application on each chamber | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection | Conformance Criteria - Survey complete | Records - Photos/Videos | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech | Frequency / Timing - Pre-construction
15 | Close out QA/QC | M | Ensure all QA/QC is complete are closed out and recorded | After completion | Review | QA/QC Documents delivered, ITP Signed and Submitted | Signed-off ITP, technical reports | United Civil | 15 - Close out QA/QC | ACTION (Hold, Monitor, Witness) - M | Detail - Ensure all QA/QC is complete are closed out and recorded | Frequency / Timing - After completion | Inspection / Test Method submission, visual inspection, testing, measure, - Review | Conformance Criteria - QA/QC Documents delivered, ITP Signed and Submitted | Records - Signed-off ITP, technical reports | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
Conformance Criteria - sewage isolation process agreed signed off
Records - Meeting Minutes/signed-off documents
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
3 - Pre-works Inspection
ACTION (Hold, Monitor, Witness) - W
Detail - Contractor to arrange a joint inspection of the relevant areas, within and outside the working areas, with Engineer, Principal and relevant landowners/ occupiers
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
Conformance Criteria - Confirmation in writing from all parties that the record is a true representation of the inspection
Records - Marked up Drawing
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
5 - Site access
ACTION (Hold, Monitor, Witness) - H
Detail - United Civil to grant site access to Contech
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
Conformance Criteria - Access Permits.
Records - Signed-off documents
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
-
ACTION (Hold, Monitor, Witness) - H
Detail - United Civil to erect a scaffold no more thsn 400mm from the workface
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
Conformance Criteria - signed off ready to use
Records - signed off documents
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
6 - Work instruction signoff
ACTION (Hold, Monitor, Witness) - H
Detail - Work Instructions produced for works
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
Conformance Criteria - Staff to sign onto the JSA prior to commencement of work onsite
Records - Signed-off documents
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil /Contech
8 - Sewpercoat ordered and compliant, and delivery to be timely
ACTION (Hold, Monitor, Witness) - W
Detail - Material to meet quality; be the right quantity and delivered on time
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Testing
Conformance Criteria - Cube Strength Results to be supplied
Records - Lab Strength Testing Report
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
9 - Sewpercoat on site, and correctly stockpiled/Stored
ACTION (Hold, Monitor, Witness) - W
Detail - Material to be stored on site in a dry area
Frequency / Timing - Pre-construction
Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
Conformance Criteria - Material stored in Contech Warehouse until Required on-site, then Stored in Covered Location on-site
Records - Photos
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
10 - Concrete surface preparation
ACTION (Hold, Monitor, Witness) - H
Detail - Concrete surface preparation with hydroblasting to have an adequate profile roughness.
Frequency / Timing - Before start spraying
Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
Conformance Criteria - The concrete surface must be prepared to have a minimum roughness equivalent to CSP 5 (ICRI)
Records - Photos/Videos/ Record sheet
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
11 - Sewpercoat lining thickness
ACTION (Hold, Monitor, Witness) - M
Detail - Sewpercoatlining thickness
Frequency / Timing - Continuous Monitoring
Inspection / Test Method submission, visual inspection, testing, measure, - Measurement
Conformance Criteria - Thickness tests using caliper depth measuring blade, average thickness of 25 mm, no measurement less than 25 mm, above substrate (concrete surface)
Records - Photos/Videos/ Record sheet
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
13 - Pull-off (adhesion) testing
ACTION (Hold, Monitor, Witness) - M
Detail - In situ Pull-off tests according to the Standard Test Method for Tensile Strength of Concrete Surfaces and the Bond Strength or Tensile Strength of Concrete Repair and Overlay Materials by Direct Tension (Pull-off Method) -
Frequency / Timing - 2 tests in each structure
Inspection / Test Method submission, visual inspection, testing, measure, - Testing
Conformance Criteria - Pull-off test to achieve a minimum of 1 MPa
Records - QA Sheet, photos
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
14 - Post Sewpercoat lining Survey
ACTION (Hold, Monitor, Witness) - H
Detail - video survey of the Structure to be undertaken post application of sewpercoat
Frequency / Timing - After supepercoat application on each chamber
Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
Conformance Criteria - Survey complete
Records - Photos/Videos
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
15 - Close out QA/QC
ACTION (Hold, Monitor, Witness) - M
Detail - Ensure all QA/QC is complete are closed out and recorded
Frequency / Timing - After completion
Inspection / Test Method submission, visual inspection, testing, measure, - Review
Conformance Criteria - QA/QC Documents delivered, ITP Signed and Submitted
Records - Signed-off ITP, technical reports
Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil