## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
0269a85f-808a-4438-b973-6bdb3aef3423 | checklist | ITP - RAC Bedheads | itp | RAC Bedheads
f51e0b76-d0bd-45b0-80a7-2d78f2f57a2e | section | Details
193425e6-2a82-44ae-823c-a4d91ed3a7b2 | checkpoint | Joinery Installed Level
7319d046-f49a-418e-8ab8-bb9fb2916a9f | checkpoint | Doors adjusted
982b1034-a256-4b0c-80f0-e9f8ef2cb67b | checkpoint | Benchtop installed
286131e1-5c52-41ec-8de6-bfd801364cb9 | checkpoint | Corian site measured
cab0b1b1-c417-4af8-9c84-cd63d13c3e0d | checkpoint | Shelving installed
1000004c-8ffb-44e6-81be-d255ea8c937d | checkpoint | Gap filled
94c55e9c-937f-42d6-b9ba-0a7013d61601 | checkpoint | Screws capped
89aa3b99-fc92-4e6b-9c18-ee8e6ddec814 | checkpoint | Bulkhead/Filler installed (if required)
e4c63d8f-308e-4b70-8de5-0117821e8037 | checkpoint | Glass splashback measured after installation
669d8c21-4cee-4b35-be7c-d96a5e19207e | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
702c7e4c-d7e2-4b98-b7b8-8c70c1c22a28 | checkpoint | Any damage to finished joinery
547ef11c-df76-4848-805a-9b70c3484130 | checkpoint | Setout location accurate
8ad8478c-356a-4192-9857-652c931903d5 | checkpoint | Aluminium trim installed
1fbbd044-c919-437a-8d16-cd4041eb9410 | checkpoint | Pinboards installed
f7363a32-ecfe-472d-b80d-fa8e62642e59 | checkpoint | Site conditions preventing completion of unit
952615c0-83e2-440b-a4d4-210d4461b7bc | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
54deab5b-0ba1-48d3-828f-1a124c9273fe | checklist | ITP - RAC Memory Box | itp | RAC Memory Box
1c5243f5-05aa-45ac-8d65-b78f875627aa | section | Details
ec2afecc-f741-45db-be44-c39a92c50573 | checkpoint | Joinery Installed Level
ccaefdad-6418-4cf8-91ea-2f821abe5bf1 | checkpoint | Doors adjusted
d6c46bd3-0ba4-4276-a8bc-70de3419368f | checkpoint | Benchtop installed
6a5fad64-21e2-4a0c-83ae-7ef88c258bb2 | checkpoint | Corian site measured
87da76b4-bd67-4e19-a994-064c8dd1316a | checkpoint | Shelving installed
17997ac3-1173-424f-a290-6a2951b48ce1 | checkpoint | Gap filled
76b3474e-e5a7-4ad2-8433-dd62ac208269 | checkpoint | Screws capped
24129b0c-62fe-4341-94f2-446ca661a6c5 | checkpoint | Bulkhead required
78655ad1-169b-4e9e-a454-b5f6a5277a25 | checkpoint | Glass splashback measured after installation
c2988fa5-7531-41b9-9326-373ed7bf684b | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
11b9222a-9838-423a-aab1-96f15d2e527a | checkpoint | Any damage to finished joinery
b0ac2750-f7ad-4a37-8018-cbd1bc75e292 | checkpoint | Setout location accurate
4c19ed7f-b0d4-498c-ba96-e7b24ac98a4c | checkpoint | Aluminium trim installed
58bbf446-eebd-4a02-9361-45ba1b8c5acc | checkpoint | Pinboards installed
d0e99d1b-1964-42b9-b81f-29cf70d49420 | checkpoint | Site conditions preventing completion of unit
5db6da7d-ae6d-4e9d-8242-6a58719ccbb4 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
70b5eb8c-fac6-47c8-97a6-f7f21d154576 | checklist | ITP - RAC Robes | itp | RAC Robes
c8bcaf2c-e44e-4258-8a0e-6db13e1996b7 | section | Details
539333c8-cb88-4fca-91a1-34cd26ba1b57 | checkpoint | Joinery Installed Level
fe336975-730b-4b39-8daa-cc8189b99fc5 | checkpoint | Doors adjusted
4f3f2db1-fc1a-4218-89e3-34d367007716 | checkpoint | Benchtop installed
15f978e0-b88a-4000-8e78-6280ab7df933 | checkpoint | Corian site measured
420bc32e-130b-4ad1-ab94-a770cfe6e579 | checkpoint | Shelving installed
fe7b76f3-d522-4cb7-b624-e7927a236217 | checkpoint | Gap filled
1fa3b2a1-57b1-42bb-a8a2-9c8f1e2371c0 | checkpoint | Screws capped
60261301-ad7f-41a8-bf6e-54ba188349f7 | checkpoint | Bulkhead/Filler installed (if required)
f81b1b23-2e75-482f-bb17-cde8eb21b127 | checkpoint | Glass splashback measured after installation
239ad7a1-062b-4509-b2c3-dd9509355e5c | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
950d3642-756e-4efb-96fa-da1c5c3577e4 | checkpoint | Any damage to finished joinery
b70a895c-3229-44a8-a23f-0fcc9a72ee67 | checkpoint | Setout location accurate
0e3e7063-4f2f-4488-94d5-f56e94094c60 | checkpoint | Aluminium trim installed
c22cbd71-e2c8-4b35-af77-1201396049f3 | checkpoint | Pinboards installed
842abcd2-9e71-4a85-9da6-590d80368c1f | checkpoint | Site conditions preventing completion of unit
7a6777a5-7f23-4d66-8867-ab70d9607cdb | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
daa50ba1-c65b-4674-bd99-ec7cfe767ce9 | checklist | ITP - RAC Vanity | itp | RAC Vanity
77900a56-99e9-47f4-a5fe-c3a474d01233 | section | Details
a181c63b-cd1e-4ee7-8899-c1f5ef9e0258 | checkpoint | Joinery Installed Level
acb62846-a5d1-48a6-b811-46b08991d031 | checkpoint | Doors adjusted
b8ef71a8-4abf-40c2-9d92-27049b6f235b | checkpoint | Benchtop installed
0230c9fb-e934-4a37-8b2e-101b8309c340 | checkpoint | Corian site measured
fc682842-d194-45d7-bcd9-63480232a459 | checkpoint | Shelving installed
221aecbf-b9b6-4aa3-8843-1a45691fa931 | checkpoint | Gap filled
3d4ec39f-b92d-4cbf-a354-77de1a659f5b | checkpoint | Screws capped
0eb2c093-aea4-4d77-ae8c-2465bb9961ef | checkpoint | Bulkhead/Filler installed (if required)
26c205bd-6250-4779-a560-d928ded1fc6d | checkpoint | Glass splashback measured after installation
ef742fe9-7c79-49e3-a9da-42a7543c7572 | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
e5e1e9b6-0b85-4879-b645-2b166fd75c54 | checkpoint | Any damage to finished joinery
8424b90a-c824-4977-a33f-46680665c590 | checkpoint | Setout location accurate
37aa0f24-5c02-4ac4-9bca-f332210a7771 | checkpoint | Aluminium trim installed
e18e1b51-cf2f-4836-8f13-78e7ece48adc | checkpoint | Pinboards installed
58e6bdec-18d5-4ab4-a4d3-be97a8d40438 | checkpoint | Site conditions preventing completion of unit
c02bd0af-cfe2-40c0-94df-a417af103ff4 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
36f583ba-b085-4325-a553-6e9fdddd830b | checklist | ITP - RL Bath | itp | RL Bath
f33190aa-7680-469d-acef-5324184932e0 | section | Details
5bb35eee-1671-47ed-8d97-1e2ff4abecc9 | checkpoint | Joinery Installed Level
50fc8cf5-a081-4f0f-8f77-fe6080943b65 | checkpoint | Doors adjusted
538dfccb-aff8-4a86-8799-6ef5751d69f0 | checkpoint | Benchtop installed
e33f5b8c-df87-4902-8ac9-aa12912af55b | checkpoint | Corian site measured
6e005961-f40f-403d-8f12-0fd462312f42 | checkpoint | Shelving installed
91d866d4-d5dc-4157-8249-175d1df0bc71 | checkpoint | Gap filled
3393fe22-b95d-4764-9d58-f3598c1b121a | checkpoint | Screws capped
8272a02a-5dc8-4889-98f2-8d06a5ea7e1d | checkpoint | Bulkhead/Filler installed (if required)
566038b7-11a8-4e58-84a5-c1cf6417e7d8 | checkpoint | Glass splashback measured after installation
e3b6f439-a257-4e03-bc30-7d7dd784f51f | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
4fe7ce4b-535f-443b-b61c-a8bd8d4ef19f | checkpoint | Any damage to finished joinery
4b44b94b-eb53-43b7-b4e2-d26e03f3c3ad | checkpoint | Setout location accurate
8e44e5b5-76e7-4fc7-b740-61cf56631b43 | checkpoint | Aluminium trim installed
5dfe6d4b-871a-49c7-98f2-6f84edfaae88 | checkpoint | Pinboards installed
970b9a74-cbc1-4b39-81ad-ab155e556769 | checkpoint | Site conditions preventing completion of unit
b64d103c-b2ca-4f67-969a-458dccd78e2a | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
19ff0b8c-e636-4a23-a346-63830c392c26 | checklist | ITP - RL Kitchen | itp | RL Kitchen
4259f14b-4462-4a81-85fe-db3823f6d3c7 | section | Details
2939c5e7-5fdc-4d6d-918b-a49c40f2e534 | checkpoint | Joinery Installed Level
898749d8-5d7e-4062-acf1-a4ea421cf2d6 | checkpoint | Doors adjusted
2f4f5c23-1eb4-4ba3-bf64-ccf756cf0b32 | checkpoint | Benchtop installed
663249c6-6536-43e4-998d-c0300e50eebc | checkpoint | Corian site measured
1e513a51-f35d-48c9-b14d-c235a3e239df | checkpoint | Shelving installed
4cede679-22f6-4358-a7e7-d0959eefa53d | checkpoint | Gap filled
fc972084-840d-459f-a095-d730a86ca3e5 | checkpoint | Screws capped
aee8f96c-fd39-4e36-95ab-95aca92fc668 | checkpoint | Bulkhead/Filler installed (if required)
e4b6f5ed-378b-47a6-81a0-4ef990517fc2 | checkpoint | Glass splashback measured after installation
dba6f098-4173-49d4-8629-cad255f9b2a7 | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
7d41f228-ee8f-4c73-acd6-de8bad89b066 | checkpoint | Any damage to finished joinery
74e88fe6-428a-47d7-84ad-846980aeae1c | checkpoint | Setout location accurate
4d64a63d-e955-4b56-9a7e-18a835131fcf | checkpoint | Aluminium trim installed
73f5fadd-db80-4191-bed4-a8725d45adbe | checkpoint | Pinboards installed
4d27a4d6-a5a1-4f51-82df-994f6d84e2c7 | checkpoint | Site conditions preventing completion of unit
d6b7fd5d-6f94-4ccf-957f-93015b6f053f | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
f739d2c8-8dd4-4082-aa52-bdf3970db4a1 | checklist | ITP - RL Laundry | itp | RL Laundry
41f48cda-66e1-4bd5-b568-27e95ac3c81b | section | Details
baeedc4b-b230-4c36-8a01-bb644c174527 | checkpoint | Joinery Installed Level
e3d2807c-1c49-40f0-a431-8bef61a212e1 | checkpoint | Doors adjusted
93d12010-fcd3-4a36-8cf2-2540db8d23bb | checkpoint | Benchtop installed
7667a4f1-b95e-41e2-9ad1-cfafb20f0b93 | checkpoint | Corian site measured
7b6e318b-66a5-4ee2-8f62-dd01c9b853dc | checkpoint | Shelving installed
a58c0040-c5cf-48e1-a803-976c8d8263a8 | checkpoint | Gap filled
c84e33a8-917a-47ba-97b2-5d3c28df1dcf | checkpoint | Screws capped
f8e5c6a9-72dc-4e68-9bec-5545bebc1a7c | checkpoint | Bulkhead/Filler installed (if required)
bc11e1c7-19de-487b-85e1-0538dd2db32d | checkpoint | Glass splashback measured after installation
3db0f77d-5f23-4264-9e30-94bb6dfb1428 | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
10f793c4-ef32-4024-b2fa-dbe0ddb7324a | checkpoint | Any damage to finished joinery
84242677-20ab-459d-aa58-f0ec54dbaff3 | checkpoint | Setout location accurate
6ed16447-695a-4c2b-8755-24b661cd46d0 | checkpoint | Aluminium trim installed
f904b9a3-2300-4d8e-b932-c593b93b90e5 | checkpoint | Pinboards installed
99880a58-c35d-4e57-9f60-bc997cb998c3 | checkpoint | Site conditions preventing completion of unit
8ea98560-76a2-4ff0-b1e1-a7554f24de53 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
e7007dcb-c210-4dbd-8357-ccd9585a699c | checklist | ITP - RL Robe & Storage | itp | RL Robe & Storage
854f03f6-8607-4d2a-afd0-638520db0d31 | section | Details
e4735461-082d-4bf9-9968-2ed988e14c1f | checkpoint | Joinery Installed Level
1b73e47f-73ce-43ae-b318-6373fdeab0fa | checkpoint | Doors adjusted
ad037801-c132-4490-a8e8-d6a00b66072c | checkpoint | Benchtop installed
fc9a7897-4f02-4609-a8cc-f65857f219c4 | checkpoint | Corian site measured
52b54d66-eb2f-4b3c-acb6-bbb0b152b335 | checkpoint | Shelving installed
f4347166-4180-4115-a56c-866e34dbf8b6 | checkpoint | Gap filled
664d5ddc-7dd3-4ef5-a5b5-c5b4b2e876c5 | checkpoint | Screws capped
fb99b3d6-99e4-44fc-b385-27f7b05fe523 | checkpoint | Bulkhead/Filler installed (if required)
36a68636-5223-4bcd-b5ef-5586d5751ac5 | checkpoint | Glass splashback measured after installation
afed6aa4-25ee-497e-8505-0d5c8b61ae6c | checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
f5eb7e15-5867-4543-b145-f5e1d116907a | checkpoint | Any damage to finished joinery
0140e75c-5477-4c2c-90e5-19ec5f0c4890 | checkpoint | Setout location accurate
21e765e3-762c-4e4f-a3b8-2e4019b54ffd | checkpoint | Aluminium trim installed
ae7d5125-2738-4aab-b0b2-828683ffdecf | checkpoint | Pinboards installed
5bfb6da5-3831-4f4a-ab3b-470ea02d44a2 | checkpoint | Site conditions preventing completion of unit
0165806d-a809-42b6-8729-e38b357bdbc8 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
60ae3973-e44c-4054-b1f3-1ea5883185af | checklist | RAC Checklist |  | RAC Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c2c17312-a4af-48d9-94dc-3386d2503794 | checkpoint | Bedhead installed
0a3f1fed-71af-5a78-86b1-5343c85b0fb2 | note | Joinery Installed Level
0170ec78-3c9b-545e-ae58-a9725685bdb3 | note | Doors adjusted
608b4624-4421-5fad-a301-bdf9cb821ae6 | note | Benchtop installed
43d27032-3f9c-56e1-a950-0844a8f8233d | note | Corian site measured
71368350-ec0a-5029-8190-65427504d65d | note | Shelving installed
d0acb861-4c1c-560b-966a-9ae9113ddeff | note | Gap filled
1113ad12-092c-5151-8f15-625a1593882f | note | Screws capped
3b2e11ae-3618-5d4f-b8a0-683ffe7d7b5d | note | Bulkhead/Filler installed (if required)
cefb1159-4ebd-5dc4-bd8e-5ede7e971f7a | note | Glass splashback measured after installation
9c2734b8-d3f6-5414-8446-f777b94efe7f | note | Power point locations on glass splashback have been confirmed prior to ordering
9eb6341f-8a87-58ae-b2e9-32708577660f | note | Any damage to finished joinery
5c690d73-7661-55f2-b361-7c28cd4d5cb7 | note | Setout location accurate
ba64d9c7-6561-556e-b088-f2d35e3ecb82 | note | Aluminium trim installed
f3bd4e21-e1e2-5bb5-81d9-b917a1dc13b3 | note | Pinboards installed
9889593c-003c-4c92-b744-20f9de859db9 | checkpoint | Memory box installed
3eb9df62-d951-5a04-8272-35bd35fe0ac5 | note | Joinery Installed Level
5bee1e4b-1ef5-5d90-8700-f8ece3f7e9b4 | note | Doors adjusted
6e6d6d9f-7711-5c88-9005-d35bfe2bd5f2 | note | Benchtop installed
d073727e-6dce-52fa-ae25-1a3023c23ff3 | note | Corian site measured
119c2068-367a-5405-b5c6-ee6f83082fe6 | note | Shelving installed
49e9db60-7829-519c-a5c4-5b105f2dec89 | note | Gap filled
6e9cf985-2ada-5509-93a4-e19a4b0959b9 | note | Screws capped
61648b21-d44a-54f4-a030-59b8d5543991 | note | Bulkhead required
8bf54527-1222-546d-b70c-c0e039c1d1ce | note | Glass splashback measured after installation
8aee3b87-1212-5872-94d5-c808e5659f30 | note | Power point locations on glass splashback have been confirmed prior to ordering
e3a0f9c8-fd91-5488-87a9-525d0a894353 | note | Any damage to finished joinery
8543ce02-8c90-58db-b711-ec559ae446e1 | note | Setout location accurate
6cd12c1d-c16c-53a1-b850-7abfca5a1225 | note | Aluminium trim installed
942f9131-37f4-56a0-a70a-f8aeba189c5e | note | Pinboards installed
bd2efe02-4154-4de0-9e4c-958e2e8afe61 | checkpoint | Robes installed
d2752bef-0c1a-506d-9313-2baad3d66828 | note | Joinery Installed Level
1d1e942f-20b5-5822-9994-a6da8318b9b5 | note | Doors adjusted
0b76c48f-d094-5cce-ace9-a1434c5fe9ea | note | Benchtop installed
c2a31c58-e3dd-59c2-b025-8d3290fe4c07 | note | Corian site measured
caaa604c-38d2-595c-9bec-1753ae08b851 | note | Shelving installed
401342a0-2ba1-52a9-a590-7f855b4b51b2 | note | Gap filled
399ffdf1-c342-5f82-a371-841e04fdb960 | note | Screws capped
87f5bfc4-2029-53cd-b05d-b14dfe7b523e | note | Bulkhead/Filler installed (if required)
0dda24f6-5852-53cb-9e56-8ced99046367 | note | Glass splashback measured after installation
5736618f-025e-5e49-95eb-0c91f5d92f99 | note | Power point locations on glass splashback have been confirmed prior to ordering
9c5eb8df-19ca-55f2-8a97-d8c9e8079831 | note | Any damage to finished joinery
3f52d38c-522a-5502-8eab-bc08a93da520 | note | Setout location accurate
1bce30b9-86d4-5537-8172-bb2cf02c1d79 | note | Aluminium trim installed
d0b9a2fb-dbb1-5d77-a14a-f4fc7754855b | note | Pinboards installed
19b2ceb9-ec6f-4d5d-9ac7-6003614de690 | checkpoint | Vanity installed
71fad893-5e05-5775-8b28-6ef6e29179c2 | note | Joinery Installed Level
7f6055be-4d52-50bc-b41c-e8d198a734c0 | note | Doors adjusted
cf6ed64e-1e17-54e3-86f2-415dbbf73a3b | note | Benchtop installed
cafda289-7ea0-585a-bf31-aa3d0168fd4a | note | Corian site measured
729d99d4-f619-5d5d-90be-09192a9fddeb | note | Shelving installed
b1436b57-8429-596a-bdd0-278289cfaa75 | note | Gap filled
2db76a1a-7de3-572e-b4b4-e00f7292a751 | note | Screws capped
2462f090-e9b6-55af-9980-4dd88ba94fad | note | Bulkhead/Filler installed (if required)
abdf5b31-c61a-5fb3-bf97-12d689d788c9 | note | Glass splashback measured after installation
6478b415-e4d5-5bc4-839d-566e389986d7 | note | Power point locations on glass splashback have been confirmed prior to ordering
f3000e49-c76d-51ac-a5a2-fe8f966b6e64 | note | Any damage to finished joinery
6125fdc4-d2e0-5964-9218-704cea6b1b5e | note | Setout location accurate
a63ae22e-8ad3-57b1-9f72-7cde286157d5 | note | Aluminium trim installed
ab2e348c-313b-5480-8ce0-2c69e526732d | note | Pinboards installed
2c5a1404-a74a-45f0-acb4-d430ae0c120f | checkpoint | Site conditions preventing completion of unit
b224af66-370f-4903-a2a3-2414cef315d6 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
64b785a2-4014-4def-9eca-8e0d9a8aed37 | checklist | RAC Checklist V2 |  | RAC Checklist V2
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
de5fefa7-45c2-4f89-8099-e7a15717bfbf | checkpoint | Bedhead, Memory Box, Robes, Vanity installed. Upload photos
0406b8ef-006e-5e8e-a064-743cc33fa4fb | note | Joinery Installed Level
1aa608e8-1a4c-52e7-9b7d-802b003ac746 | note | Doors adjusted
c33eabb8-8afa-5ccd-84c6-5dd676e5b816 | note | Benchtop installed
119f4f2d-ec58-5e95-b803-bee9f56fb3d1 | note | Corian site measured
51dc537d-0e26-5f52-ab69-a82eb96c3151 | note | Shelving installed
7917b67b-a467-599f-8f8b-b88cd5a8c790 | note | Gap filled
aef2a662-f14d-54cd-911e-5f72e689b895 | note | Screws capped
32d931d3-c28f-58f7-b7c1-8c3aae274a7b | note | Bulkhead/Filler installed (if required)
de06b8ca-6cf0-5ce1-b298-933ded7e65af | note | Glass splashback measured after installation
e8ed6c1c-9e88-5466-b46c-56fb117fd1f2 | note | Power point locations on glass splashback have been confirmed prior to ordering
9454f40d-76fa-5a40-80b3-a6cadfad4033 | note | Any damage to finished joinery
79812864-f6ff-540b-a37b-c76ec84a78d5 | note | Setout location accurate
8466ac53-c9b4-5d69-b89c-523372664a60 | note | Aluminium trim installed
5849baa2-f2b8-5613-9ce3-9e19847ce7a9 | note | Pinboards installed
e95afa8b-79ed-48c1-bf36-954d2b7472e3 | checkpoint | Site conditions preventing completion of unit
34dfb231-a597-49dd-b498-394eb584fb81 | checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.