## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP - Pavement Rehab - SH 36 - Awahou to Central | itp | ITP - Pavement Rehab - SH 36 - Awahou to Central |  | 358f4e0c-3822-458d-9b4f-806602aaee1f
| section | 1. Procurement
| checkpoint | Design - Geometric Design
eb5d570d-4c5c-53bb-9937-649ed6aa10f6 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
9b3171ca-2016-58a3-afff-d9cc4a0afa1c | note | Acceptance Criteria - Principal Approval
45e5ba71-e0d6-5d96-b99f-ca0998c5082c | note | Method - Contractor and Principal peer review
38a8fe85-bd6b-5bfb-8066-5487366c9b15 | note | Frequency - per design revision
3eaaf82e-e059-5d9e-83f9-cdad59420846 | note | Conduct - C or S
e0a99a16-7c4b-5f1c-bcef-00f9fc666ae9 | note | Produce Record - C
e4ccf28c-554d-5b28-a4d6-a2af62557c9a | note | Approval - E
5dc6ba6f-7bfc-5f0d-a732-da10141c6b8b | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Design - Pavement Treatment Design
dcb79c3c-ff05-5858-a4b4-daeb0f2fc417 | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
823884c1-7db2-5931-985b-fe01e4857437 | note | Acceptance Criteria - Principal Approval
1946f8f4-086d-5f75-a3b8-4eaa636bfe3e | note | Method - Contractor and Principal peer review
5d660a39-3636-58cf-bfbf-969990be644c | note | Frequency - per design
c4e89535-1d09-548e-8840-a3482694dde9 | note | Verifying Document - Pavement Rehabilitation Design Report
2212bdd1-73c9-5d4e-9278-a0484bbc9af0 | note | Conduct - C or S
29a83fa7-c738-56d9-877c-51d6c62c25a4 | note | Produce Record - C
e89aa07d-fca5-5ee6-80d3-607773afcfea | note | Approval - E
63058135-f3a3-523b-b2b9-4e7cf2f93ce9 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Subbase Material - Aggregate Sampling
e8f1245d-c23f-57ce-9982-bcb3ec8fc896 | note | Verifying Document - Sampling Worksheet
d18277b1-7647-573b-8f38-28cc30a3e4ba | note | Conduct - C or S
2d83a991-ed05-533a-b28e-9b035b6c1cd5 | note | Approval - S
| checkpoint | Materials: GAP 65 Pre-treatment Material - Source Property Test
3312dddb-f0b0-5b47-af2f-f7b50894b028 | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
bd147bff-f54a-5731-a129-aa8bb9340c17 | note | Acceptance Criteria - Soaked CBR ≥ 40
b582e548-57f5-5ba5-819c-3c33c043454b | note | Method - Soaked CBR test (NZS:4407:2015:3.15)
750d514d-2998-500a-a525-aa996008c9a9 | note | Responsible Person - Supervisor
fdb9522b-78db-5ecc-9ee1-d74e5224eace | note | Verifying Document - Test Report
4ea65e7a-f2a5-5c4d-a2e8-a164e213ed53 | note | Conduct - Sp or C or S
481e22f0-b5aa-5b13-ba45-a4a46b5db012 | note | Produce Record - Sp or S
2692b0f5-0bd7-5ce0-be44-ba7ff42f763f | note | Approval - E
b8398973-d28a-5e8c-a233-844b8e4f0578 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: GAP 65 Subbase Material - Production Property Test
a5a68012-ed57-50fa-837b-8b65b58d6939 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
547fbdbb-d406-5348-846b-fc54cc84cb77 | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
381a526e-aad6-5df3-bfd6-0cb1c584a501 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
f1163d70-cada-54fe-86bf-cc186a178393 | note | Responsible Person - Supervisor
b08017d3-2cb3-5a2f-b4a2-ead84f16a348 | note | Verifying Document - Test Report
ca8ccc52-a120-5713-b3d2-000c5ab6f376 | note | Conduct - Sp or C or S
097922ae-78a9-5f35-8d18-50b9369b55dc | note | Produce Record - Sp or S
c03fec90-961a-5bfd-91a2-60a630d67e55 | note | Approval - E
36267686-a3f4-59c3-8122-aad009dd9685 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Aggregate Sampling
3b761e8c-afbc-5183-8010-8397c47cde1d | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
1e8196f8-6671-5e69-b8c2-25c75739aee8 | note | Verifying Document - Sampling Worksheet
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (1)
6e2fdcff-c1d6-5b86-b31f-85a59ec2efab | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
110517be-e8f1-5b91-b651-43128e11e8fe | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
53554b0e-2e19-5570-af07-89d031e69a79 | note | Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
03ca2d88-dc75-5ddc-985f-7b29a4685cd2 | note | Frequency - One test for every 10,000m³ of source material
3830adb5-d824-5b83-a28a-c9389a008ce0 | note | Responsible Person - Quality Controller
1ea6545c-55f8-5348-a540-590ff1bc7c37 | note | Verifying Document - Test Report
77560bcd-d8eb-59e7-a7b9-b028e9b731c9 | note | Conduct - Sp or C or S
532d2c60-69bd-56dd-bc74-dc0f509ca506 | note | Produce Record - Sp or S
6ab942b9-3524-5406-83cb-1d84da5b6e52 | note | Approval - E
0ef2edf6-4086-5c68-9f59-895a05a6041e | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (2)
adf81c47-c9ab-5e2b-93cb-10bc778ad900 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
231f7be7-aebc-59e8-8d7b-c5580e3ab12a | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
3c88e1ea-75e0-5df0-b761-048454b3d595 | note | Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
30390df2-b1a1-5c81-8612-dc6463c522ee | note | Frequency - One test for every 10,000m³ of source material
1f607dd4-a19e-56ae-ba55-39b265cf1316 | note | Responsible Person - Quality Controller
f5a735cc-8b72-56b6-8875-fa87f91b987a | note | Verifying Document - Test Report
488f1241-d812-5668-a4a7-4dc89a614a11 | note | Conduct - Sp or C or S
c2be2436-c40b-50a8-8eca-f8622b2b5c57 | note | Produce Record - Sp or S
6908e46d-8a2b-5332-8929-6eb4ef254b50 | note | Approval - E
f5f16783-fc57-5111-a013-182ead9587e0 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Source Property Test (3)
5f86381b-1d41-53ce-b561-58bbc363dd91 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
ae189dd9-70e0-552f-ac6a-1e8bee94a4c2 | note | Acceptance Criteria - Soaked CBR ≥ 80%
858f179e-4740-5243-a776-953a26208ea3 | note | Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
da2389cd-5c54-56c3-9b00-e6c3fff12e30 | note | Frequency - One test for every 10,000m³ of source material
62d56026-9c63-5411-8e12-6c82d06ab268 | note | Responsible Person - Quality Controller
6680c5ac-2a72-516b-b933-cbfde3bb6303 | note | Verifying Document - Test Report
532c6ee0-cf9f-540d-918c-a6b9392b8f6e | note | Conduct - Sp or C or S
41dc0c05-e932-58a4-9ff9-8a74fc866066 | note | Produce Record - Sp or S
10bc4669-70f8-5687-a810-3843ba280206 | note | Approval - E
f5279df7-3fde-5898-9a13-0e95dd6a2890 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (1)
d95258d9-e8e7-50dc-a58e-de88f197067f | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
9ddba53a-6645-5962-8a0b-a72233a19aca | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
98b4c9a5-f2f7-55f8-9475-af0034752103 | note | Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
dcd08a75-0d00-5e2c-ae09-bccb2a3857a8 | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
0f15a52c-f018-51e9-9187-646f32414f6d | note | Responsible Person - Quality Controller
a3434be4-2de9-5277-b452-1631b99fd191 | note | Verifying Document - Test Report
ce610b28-f22a-5d6c-b300-a50a6cc98df3 | note | Conduct - Sp or C or S
c7ed8fce-8637-5cc7-99e4-2e337e9a8f3a | note | Produce Record - Sp or S
cd96ea76-a07e-5e89-8ab9-669ef775a2c6 | note | Approval - E
4cc81fa6-60e0-5f90-a92f-f4c4e90a712f | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (2)
e42c4cb4-be2c-535f-a34b-56e5ee30f0ef | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
c16567a3-ab1b-5385-9197-6baee82fac71 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
94deb2b0-3d56-5f25-8570-379dd5541dff | note | Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
dfbbdcdc-48ae-5216-88a3-450224378add | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
a0d73925-3c27-51af-9cc6-82dbc0f3e9b9 | note | Responsible Person - Quality Controller
5818f5cc-ea4e-5c7d-b6c5-28b94d98ce3c | note | Verifying Document - Test Report
286904e0-047b-53aa-ace4-007f272ed373 | note | Conduct - Sp or C or S
68c52959-bfdf-58c1-8d2e-0b822e06b6a4 | note | Produce Record - Sp or S
c2f49c9e-ef75-5295-a3f2-712a544ff12a | note | Approval - E
e31eb6c3-c44c-521e-b7b3-7786a180fe29 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: M/4 AP40 Basecourse Material - Production Property Test (3)
2396121d-3407-51ed-b67f-2348b7428bff | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
0dc5f51f-3bce-5bda-a176-d0e0e441c1cf | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
7648e7c8-715a-5c67-92cd-1ffae181e800 | note | Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
c15602a1-a9b6-59c3-9c0c-c39c5c02233e | note | Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
50652d63-97b5-5a06-8249-eaa8d6543300 | note | Responsible Person - Quality Controller
1643f3c4-c4c4-58c6-9052-4a0d6c065bbb | note | Verifying Document - Test Report
789267f8-ad13-510c-8130-52367403ea5b | note | Conduct - Sp or C or S
dbe47d0f-dd29-5467-9c17-7cb0720aa803 | note | Produce Record - Sp or S
cb158389-aa6c-53f8-a6ca-ab14180bdf01 | note | Approval - E
cdb190df-1512-5933-a557-3a3e9f7279b3 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Materials: Cement - Stabilising Agent Selection
0c012fee-9e00-58c8-9ddf-c3c1ac3796ce | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
f18e6c84-49f5-5dd6-834f-36ff89965f7b | note | Acceptance Criteria - GP
d35d8547-607c-5489-8c1a-626a3104b812 | note | Method - Visual inspection of supplier docket
ece98410-a8d7-5c52-8efc-186cf14382a0 | note | Frequency - per truck load
b4aa9048-d2ab-5a9b-b559-74f2a6b7cb52 | note | Responsible Person - Quality Controller
6b48180b-c262-50d0-b6b1-0d1084a173c8 | note | Verifying Document - Supplier Docket, Supplier Cert
37a467a0-c257-517f-878d-f04c1e7a2f30 | note | Conduct - Sp or S
e97ba1ec-0141-5db1-b915-29b0fc92a9c8 | note | Produce Record - Sp or S
dc2024d1-093e-54aa-b91b-09d46ca11362 | note | Approval - C
9c71249b-9f09-5ecf-b524-13711cc79ec5 | note | Witness Point Y/N - Y
| checkpoint | Materials: Water - Water draw for stabilising
3b287b5f-4b86-50de-b669-2a873791b3b6 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
19cc44c3-cfdd-5ca5-afba-334b44779484 | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
33c79b53-1886-55b5-a9c2-481e9d1259fa | note | Method - Visual inspection
73ea0ff9-151b-51cc-b66d-7d85b466da4e | note | Frequency - per truck load
6c8572c6-ee1e-5d4e-b9c5-e8299fbc52a4 | note | Responsible Person - Quality Controller
66a02040-2962-516e-8eb8-154ed20e02af | note | Verifying Document - Hydrant use form
13580efc-a387-513a-8ba8-851a4a746fef | note | Conduct - Sp or S
3697ec19-9a33-5f00-8e30-5276e6d39288 | note | Produce Record - Sp or S
e41aed75-1ddc-565e-9573-a199089afdec | note | Approval - C
cb463d89-755d-51fc-ab69-37a77d20c550 | note | Witness Point Y/N - Y
| checkpoint | Materials: Geotextile - Geotextile (Strength Class C) A29 or greater
88cf8b6c-4ebc-574a-a711-361f57493270 | note | Controlling Documents - TNZ F7 Specification
4399b716-6767-574c-b4d7-5c42122fe41a | note | Acceptance Criteria - Details on Docket
d3e9ea32-6e40-5147-8fa9-2253a28d170f | note | Method - Visual inspection
5860a242-732b-57cd-a56f-7c43ee309447 | note | Frequency - Per Delivery
9358ec4d-d8af-5fe5-ae0e-52a900dc168e | note | Responsible Person - Quality Controller
f8e175f1-d712-5f3f-9c2c-6e78325831a9 | note | Verifying Document - MDS
d8b56b17-79bc-58e8-8984-cf0017d6bb06 | note | Conduct - Sp or S
9bbb2cd9-008b-576c-a8b7-5c1b14ba39e8 | note | Produce Record - Sp or S
fc178143-f68f-5021-8939-7bfadbd5b035 | note | Approval - C
e3d4e1e6-ef30-5002-8049-97a2b97c09ea | note | Witness Point Y/N - Y
| checkpoint | Materials: Geogrid - Geogrid secugrid 30/30 Q1 or similar equivalent
3b300327-8190-5ab3-a4f3-7a0f317069ce | note | Controlling Documents - As per NZTA list of approved materials/suppliers
8c01fa3a-6cd0-52d1-99e1-063acb0b5f9c | note | Acceptance Criteria - Details on Docket
46c2771b-5b3c-5b1d-a3c1-70d7b330a2fa | note | Method - Visual inspection
5bc72f1b-d688-545f-bd40-2efb84ccc6fa | note | Frequency - Per Delivery
0eb2d412-8b4e-55f3-a322-a652d4ffb9e8 | note | Responsible Person - Quality Controller
14454438-0bf4-523c-8280-847d20e10b14 | note | Verifying Document - MDS
1881aaf8-1552-53ce-bd17-5810272039f0 | note | Conduct - Sp or S
7e39a9bf-a5ea-58a4-be49-bd6316c9ab3e | note | Produce Record - Sp or S
ea4ed84b-0ca1-5c9e-ae59-1020f3624f58 | note | Approval - C
285af570-f3dc-5616-9c69-f3ebff1d6c36 | note | Witness Point Y/N - Y
| section | 2. Pre-Implementation
| checkpoint | Production Testing of stabilised material - OMC/MDD
ab88e9d6-f46e-5b50-aff2-20b8cb730ae6 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
c6d8d75e-fc55-59a3-a014-331fa3f18864 | note | Acceptance Criteria - To obtain OMC & MDD
e500e350-b1a6-5841-9887-082be741c671 | note | Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
dbc3e78f-0cf3-57e1-a2bf-2c2dc3f9d999 | note | Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
b235e127-2612-5fbe-8287-0c86919b09e1 | note | Responsible Person - Quality Controller
6b1d4348-5342-5cbb-84a3-a3e787135e3b | note | Verifying Document - Test report
f3ac426c-0484-5cc4-8921-340f9745823a | note | Conduct - S or C
e168769e-c676-5c40-9059-af21286d377d | note | Witness - C
8619518d-f78e-5668-9901-fb2572df6cb9 | note | Produce Record - S or C
39d4e0fe-9696-5c1a-af0c-8c438e08d38c | note | Approval - C
b957c5d7-f8e6-5952-a71d-671877be12c8 | note | Witness Point Y/N - Y
| checkpoint | Production Testing of stabilised material - Solid Density
5409e6a6-0623-5237-ae1f-fc176a112eb3 | note | Controlling Documents - TNZ B/5 section 7.7
79edc855-b683-51d2-91e5-0939345d5e62 | note | Acceptance Criteria - For info. and use in MDD calculation
58eae3c3-7306-52d1-826f-12a3872a7a8a | note | Method - NZS 4407; test 3.7.1
e247fe19-0dcd-54ec-acd4-bd8481022e1d | note | Frequency - Once on commencement and if any materials change
4018396a-3594-5dec-a3b9-ae20872e7ce0 | note | Responsible Person - Quality Controller
2d4da368-3fe7-5d04-9ce2-6a2f72f12f30 | note | Verifying Document - Test report
68c69eac-b698-50b0-83b5-5f880df215df | note | Conduct - S or C
ae418709-e698-5c59-9d41-766387affbb8 | note | Witness - C
118dce52-9f16-55c9-8e0a-731a487c09f7 | note | Produce Record - S or C
8cab3c96-aa6f-57d1-903c-42701b39ee0c | note | Approval - C
bddcb5db-e8d2-5e3f-b760-925e78f3b380 | note | Witness Point Y/N - Y
| checkpoint | Project survey setting out
4179a253-a4a6-57e1-b1dd-4b01846fc105 | note | Controlling Documents - Reference from Project Drawings
af44c858-6da6-592f-8425-5a6f903d86b5 | note | Method - Survey/Mobile Roads, Marks with Dazzle
0396b186-b124-5858-b4ac-9141d392d349 | note | Frequency - Chainages for every different pavement sections
ae3e80d4-366f-5ea8-9cdd-e718e9c60a30 | note | Responsible Person - Subcontractor/ Engineer
2cbd8fb4-274b-50c7-9dfc-2eb6484838c3 | note | Verifying Document - Construction drawings
752fff65-5add-5777-af20-165e9b634809 | note | Conduct - S or C
601778dd-7b23-5842-98f7-9a2ca709a51f | note | Witness - C
4c28e685-31e8-5e57-8534-95ad7a67a7fe | note | Produce Record - S or C
4469d575-2601-5938-adb3-65a1d8096d71 | note | Approval - C
e0562ac6-10f1-591a-a913-01674d6c2a24 | note | Witness Point Y/N - Y
| section | 3. Construction - Pre-treatment Digouts
| checkpoint | Pre-treatment Repair Method Selection
cd7ad103-d8eb-5ab6-8aa2-acf577a9a9ea | note | Controlling Documents - Site specifics to be confirmed
524db947-6c4b-54ad-983c-987c29f14ab5 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
506ca678-fe33-57db-8dbf-e9c0b1838574 | note | Method - Scala Penetrometer on Excavation Floor
62955303-8ca7-5b23-8f8b-1d606b6df61a | note | Frequency - As required
c7a1d6e4-1312-518b-80a5-fae9d4accee2 | note | Responsible Person - Quality Controller
58a11b2c-a018-5405-acbf-8a15ce128b5b | note | Verifying Document - Agreed treatment plan
b1f2ff35-607c-5181-91bc-9ceed6a2fef4 | note | Conduct - S
508f7e56-a052-55a3-a7fc-f87bd2ecc0f0 | note | Witness - C
09c13f5f-9bb1-569b-8d63-506586d06e41 | note | Produce Record - S
91da0cfc-1465-5d6d-b7ba-00c260659098 | note | Approval - E
ee7f3b34-50dd-5c40-9900-f43777e1a8c3 | note | Witness Point Y/N - Y
| checkpoint | Digout of Patches to repair
885bc306-fedf-51b1-b4f8-0328e04ca5d5 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
ba60d11b-74d4-55c8-a36e-70043933efa5 | note | Acceptance Criteria - 250mm deep unless specified
5c5d79cd-bd72-5015-ba02-c63262560408 | note | Method - Visual inspection
c882511a-d15f-5dd2-b732-ce1b643d1102 | note | Frequency - As required
fd1564ca-d80f-57d8-a49f-726e09dad58e | note | Responsible Person - Quality Controller
22077275-f776-5cc9-96a0-c3767434d15e | note | Verifying Document - Dig out site records/ Asbuilt
cc9ab00f-f6e2-5828-83f1-66c2e2d59307 | note | Conduct - S
e1e0893d-049f-5240-9767-8e9e55d91ee7 | note | Witness - C
6a213dba-feb9-5587-b9f9-c5bcba742863 | note | Produce Record - S
40a192a0-43ae-5d7a-9f11-325832ee2693 | note | Approval - C
515530e6-8fb6-52eb-851f-e4169808121a | note | Witness Point Y/N - Y
| checkpoint | Subgrade material hardness, Check base of excavation
7e17bb2d-28bf-5e86-b512-577183a50954 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
65506d61-8786-5120-9943-9bb8e0302713 | note | Acceptance Criteria - Scala > 3 blows per 100mm or Proof roll <5mm
9d2894c5-fc05-5fdd-803b-a77d81c015c1 | note | Method - Scala Penetrometer test on base of digout or Proof roll where scala unsuccessful
f6730bda-0d00-52c2-a15b-6aa8516d1134 | note | Frequency - As required depending on size of digout
2bec60aa-0775-546d-947c-50c6aa19cbf4 | note | Responsible Person - Quality Controller
cedac27d-2b7b-5509-974d-798f6b930cc3 | note | Verifying Document - Test report
a84a637f-c324-5234-8053-d4f55400d5b9 | note | Conduct - S/C
f8af45c6-dce6-5e52-b0f6-a3cde39b0f3c | note | Witness - C
dae0ecae-061a-5067-b48c-211b9aa77eeb | note | Produce Record - S/C
a87b7d9d-0fa5-5c5f-ad3e-fb3574a6495c | note | Approval - E
cd35489c-5801-57cb-b8a8-ac157b22d60e | note | Witness Point Y/N - Y
| checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
2074a827-f9a2-5633-be8f-6b720f7418d8 | note | Controlling Documents - TNZ F7 Specification
e98f7159-8bfb-5c5f-9216-e0fbb2bbcf01 | note | Acceptance Criteria - Meet TNZ F7 Spec.
c6b983e9-5005-5d13-864f-41d3313bbce0 | note | Method - Visual inspection
569f625e-ab17-5260-86e7-52922a28a237 | note | Frequency - Per Delivery
4ce4381c-d385-5606-894a-faee519fb50c | note | Responsible Person - Quality Controller
31436db4-08c9-558f-bf7f-ce63b6aadcd1 | note | Verifying Document - Certificate of conformance
befbcb31-84fb-500a-893d-f414c67de295 | note | Conduct - Sp or S
3c8f24f3-7dc3-544a-8b3a-cba83952f30a | note | Produce Record - C
fb3159d3-5be8-5ec6-9c86-e740734b4e18 | note | Approval - C
f52a8f73-cf11-53b9-a261-ceaccdec01ee | note | Witness Point Y/N - Y
| checkpoint | Geogrid secudrid 30/30 Q1 or similar equivalent beneath treatment layer (if rqd)
6b0c46a0-24c1-5b68-9498-3aef77feda23 | note | Controlling Documents - As per NZTA list of approved materials/suppliers
d22ca2b6-5937-599f-98e8-d488ffcc364b | note | Acceptance Criteria - On the list of approved materials/suppliers
c181dcc1-3ca9-5da2-a9fa-b2237d0bb0d5 | note | Method - Visual inspection
898f7ce7-a848-5895-a670-1ef1e1fd77f6 | note | Frequency - Per Delivery
2dcc63eb-3dfe-5abe-b104-45b501bdc779 | note | Responsible Person - Quality Controller
461c9734-d93f-533b-a2b7-fa0a74821e87 | note | Verifying Document - Certificate of conformance
af322b91-d1f1-5255-9451-7c647468a05b | note | Conduct - Sp or S
3bc1b341-d19d-51e7-8a44-6adf4cd6ff5f | note | Produce Record - C
2d1d2b6b-3fe9-51cb-8c7b-8b84be25c393 | note | Approval - C
6ed98bf2-cc8d-5fe8-b000-84fd75b873a6 | note | Witness Point Y/N - Y
| checkpoint | Place and compact GAP65 in digout area
1b6f7132-0a9e-5292-ad8b-57e3c35a6610 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
05bd3471-e063-5924-891b-bff42b9f2f76 | note | Acceptance Criteria - Clegg value > 45
6858380e-2b5d-5c65-ace8-bdf18ca0c6fa | note | Method - Clegg Test
6e443a4c-bc87-5501-890b-5dccd2da06f9 | note | Frequency - Min. 2 per digout
218d4475-dcb2-5ebf-8139-6aa97fca3a4b | note | Responsible Person - Quality Controller
35830c22-79ea-5665-8f03-5d434e2e8886 | note | Verifying Document - Test report
50f54a26-7dd0-5ae7-9c07-21ae256bc1bb | note | Conduct - S/C
9d1b76b2-18bb-51d5-abbc-1ce7874991fb | note | Witness - C
cbaa0694-c6c9-5586-bf68-7ebd4fdae660 | note | Produce Record - S/C
228262fd-d570-54c1-8858-c6e36bcf8dd2 | note | Approval - E
c111cea4-9ab3-59ba-a036-4461902e6500 | note | Witness Point Y/N - Y
| section | 4. Construction - Granular make up and In-situ Modification
| checkpoint | Place GAP 65 Subbase Material
6cd9aac9-56eb-52a4-a8f3-6f1dfa3c830f | note | Controlling Documents - TNZ B/5 (section 7)
caf9a076-5ddc-5ffa-a719-585b3fc88664 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
72ce2125-8b04-59f0-ab69-8fb96690f8a2 | note | Method - Visual Inspection
4bc7eeea-ab68-521a-a102-e1b8c7935790 | note | Frequency - On completion of placement
706d4ba9-052d-56c1-86ad-b44e505ba57f | note | Responsible Person - Quality Controller
236fd54e-19cb-5037-8ca1-50bdf6c65b42 | note | Verifying Document - Photographs and Daily Site Record
33e53dc2-2a99-5e0d-be8a-662e918bd1ac | note | Conduct - S or C
c43b986f-b574-5db6-9b80-354b174eaee9 | note | Produce Record - S or C
5da1a737-1e84-5116-9a0b-e9bbb6ed6440 | note | Approval - C
7490dc33-9f26-5bd9-a3d7-33c9a9924885 | note | Witness Point Y/N - Y
| checkpoint | Spreading of Cement
5f0533d6-fda6-5ed7-b9f4-40e4899f677d | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
ea65be8a-cb74-5400-bcf0-467e71c2bf3e | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
33ac3b81-aefe-53b6-8dcd-67720ab407f1 | note | Method - Mat test (1m² canvas) and Average Usage Test
5d9b1eee-d059-5f78-9a47-cda2767b188e | note | Frequency - per 400m² and upon emptying the spreader
cb8198cb-5389-5dcc-9535-2ff5aed35a70 | note | Responsible Person - Quality Controller
c7fc24ef-1ddc-5ca5-a159-2a2e8781b460 | note | Verifying Document - Mat Test Form and truck dockets
a31adf13-b58d-5873-a8fc-da7bf1cf50ff | note | Conduct - S or Sp
fb3fe51b-25c0-5f42-9551-e43d43af57a4 | note | Witness - C
0d6d7fc0-d60d-58f2-b63e-46b2bbadbb68 | note | Produce Record - S
aca67e9b-3095-5b5e-b721-3cfbd35d2dbe | note | Approval - E
f3e054f5-6677-5d26-9f57-d077fb0960e2 | note | Witness Point Y/N - Y
| checkpoint | Addition of Water
27aac6d2-59b2-5e1c-8f86-7e7b335e62df | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
e061c204-6d7f-52e9-bdc4-1e838d6d544d | note | Acceptance Criteria - 90-100% OWC
c4449c0c-c7a9-5e92-93aa-fd050890abf9 | note | Method - Nuclear Densometer Testing prior to Stabilisation
cea5e0ce-e8c9-5945-8a03-8adc3979d270 | note | Frequency - ≥1 per 1000m² lot
33f62886-e6e9-5fc1-8c05-fae15637264a | note | Responsible Person - Quality Controller
fe5e4298-d8d4-5aa5-97da-618f97e11d70 | note | Verifying Document - NDM Record
ccc72751-6c35-5dd4-bb5f-8dbb5f777672 | note | Conduct - S or C
b78263fa-85d2-56ca-ae5c-e5911bc3b970 | note | Produce Record - S
ec3804e8-62f3-5454-9694-7601ee2d3f13 | note | Approval - S or C
a6f9dbb1-fcf2-5e84-bb10-9a74f425bf36 | note | Witness Point Y/N - Y
| checkpoint | Cut Depth
dac91828-22c9-556e-ac8d-b410ae4cd259 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
5244082c-2a98-56ab-8db6-cce0ff79fcb3 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
e01153ba-3804-5711-80ea-2fa81d31bdb3 | note | Method - Physical Measure and Visual Record
fd565e3f-381a-5711-8d15-f6c0b9c92048 | note | Frequency - ≥1 per 200m of cut length
717c0ddb-4210-5602-ab37-24b3226db05d | note | Responsible Person - Quality Controller
fbb2fb9b-c704-525c-a375-bc35df8c45b5 | note | Verifying Document - Photographs and Daily Site Record
0adca4fd-4a28-5b5e-b2cc-c0031beabc0e | note | Conduct - S or C
bb74dcf2-16a4-5268-b470-3a10a0309250 | note | Produce Record - S
7619bfe7-3eb1-5bba-9437-2d73cae09f43 | note | Approval - S or C
113f31d1-4290-5aaa-9f95-28d5c7815c22 | note | Witness Point Y/N - Y
| checkpoint | Longitudinal Joints
c0581198-b670-5409-9457-16156bdec762 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
b42bade6-f14e-5e43-bd73-b59e9479087a | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
0a70738a-f434-58cf-aa98-4bbd32c5f3a0 | note | Method - Visual Record
0fa240e6-46b1-5a0c-9d23-07e9ff7c93c3 | note | Frequency - per sucessive cut
5e65f2b2-4bfe-5ed9-a9f1-7ab41e07e543 | note | Responsible Person - Quality Controller
d1cb4740-55cf-54be-9299-b96730bd6e7f | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
8692a74b-c0ff-52f8-8b41-4deacc2dafc8 | note | Conduct - S or C
4b7ea3d3-70ac-5b2b-b773-fa5b47978d6e | note | Produce Record - S
25b9e823-a15d-595a-97b3-c3112a47d593 | note | Approval - S or C
b026672a-e8a0-50db-bb83-2e99aa02e1a2 | note | Witness Point Y/N - Y
| checkpoint | Continuity of Layer
f1b47556-9bf0-5ee6-b477-867909ef7996 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
02d86085-2b25-52ca-a840-4628e30f3b47 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
05a8da2a-b811-5f3d-a0a1-4fd8ea1081af | note | Method - Visual Record
39dcfba2-e39a-538c-b6d2-59397f3c525c | note | Frequency - per sucessive cut
863d9550-5e30-5799-bfb5-b5ba468c9c85 | note | Responsible Person - Quality Controller
195b8f99-9d6a-557f-ae23-f2b75f1174ae | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
c825b745-13fb-52e9-a18e-aa4dddf5a633 | note | Conduct - S or C
0885ba3e-b2d1-5c77-b6d8-80ead51920ec | note | Produce Record - S
193dc919-c4b3-556d-8038-99d9d9751c6a | note | Approval - S or C
fbe15ab4-f710-5935-a1d0-13347306e7ab | note | Witness Point Y/N - Y
| checkpoint | Stabilised Material Particle Size
b1d37bb7-a3f0-5227-8cb6-ee65e5de7252 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
89b2cf1c-66b5-5cc2-9334-9624628f3fd4 | note | Acceptance Criteria - No excessive breakdown of stabilised material
ba34b99b-fc20-593b-92a4-d8f170269d02 | note | Method - Visual Record
8656b1e0-3e9b-5b85-8724-67e94aa286e0 | note | Frequency - within 20m of each section and then regularly based on material variability
b431db6c-c131-5414-a76f-f5a2ecb29abd | note | Responsible Person - Quality Controller
026311ab-5f81-50f9-b162-73ce7a67f94e | note | Verifying Document - Photographs
50d213df-37f3-5d03-b686-590d557399db | note | Conduct - S or C
47e5309f-ffce-5069-ac0b-f8a4549bb959 | note | Produce Record - S or C
4ed990b2-4c3d-57ac-8190-a30a5a614f6d | note | Approval - C
6b4c886b-659c-5b6b-bc67-96eef723bbb2 | note | Witness Point Y/N - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
766ed23d-c75b-5407-8dad-45d6c2677eda | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
7e8a3b3d-52e4-5585-958a-a8609a5bedac | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
716ebbd0-fd36-5a84-b875-8d32bc6300e9 | note | Method - Plateau Density Testing
c9771adf-21bb-5da6-82b7-59063f817780 | note | Frequency - 1 time, or additional tests when material changes visually
3833e2ef-cf1e-5289-b31c-63b1c1c0deea | note | Responsible Person - Supervisor
f41e57d9-f318-5eaf-912e-95352052586c | note | Verifying Document - Test record
251c23da-c0f8-599d-86f7-6307f2fc5e7f | note | Conduct - S or C
c76c009e-f433-581d-8817-3c2455515c1f | note | Produce Record - S or C
2b66fcb9-a355-597f-995f-d82e819cd1a3 | note | Approval - C
1d33ce63-a973-5739-a807-810c8e023fa2 | note | Witness Point Y/N - Y
| checkpoint | Establish Compaction Target
cb50cac6-b0f9-5eae-91ba-ff1a4ff521c9 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
3fc77614-0402-549c-9eaf-6441f8c424bd | note | Acceptance Criteria - To provide MDD for NDM testing
d1044f2a-2ce5-5d6b-98d1-b72142d58223 | note | Method - Plateau Density Testing
5482c426-78a1-57b9-93d5-b5008a973254 | note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
f0612776-ea38-5c01-9263-70c3af80adae | note | Responsible Person - Quality Controller
bfe61203-3980-5af7-a3c0-c31b2dab35e7 | note | Verifying Document - Test Record
2b6cd358-3406-5c1a-b878-e579129255a1 | note | Conduct - S or C
f344a7d1-1a25-5690-a323-70198b309368 | note | Produce Record - S or C
ff5846f6-7e1f-5cd9-a681-6b37752decaf | note | Approval - E
c0e7b1ae-cc22-5956-96d9-a5e7bcdd04b7 | note | Witness Point Y/N - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
385f7b0b-fb30-5453-a811-89db57744f46 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
503cd0ec-5f43-5d74-8cae-22f81670c2db | note | Acceptance Criteria - To provide MDD for NDM testing
d3ae7089-5315-5f51-a179-e1e5a67951d1 | note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
c5d22ab1-e8e9-500c-9332-34f366997e03 | note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
96770105-8fdd-56d4-8430-34ba4abda53f | note | Responsible Person - Quality Controller
1a892666-20f7-57a0-b2dd-e77307f755a0 | note | Verifying Document - Test Record
14730010-79f7-53d3-8895-7e215fcc92df | note | Conduct - S or C
4a59426f-5e8d-5ea2-8a8d-b3b2c8f8bc27 | note | Produce Record - S or C
3a25a000-32d2-570e-adcd-d32e4c1c5e58 | note | Approval - C
92be42d3-4636-5f13-ab93-9ab48d1281a9 | note | Witness Point Y/N - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
1fa83a87-4024-58c5-9855-61078afadbf2 | note | Controlling Documents - Higgins 'Interim Pavement Layer Compaction Guide' - Technical Note, Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
6664015d-de55-5ac5-b042-2cc7aaecc8ba | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
efaf700d-c0c6-5a09-b359-202077aef76f | note | Method - Plateau Density Testing, Lab. MDD
f755f515-c822-5150-ad6f-2ed5b2fd6043 | note | Frequency - At commencement of construction and whenever materials change
93ce4b39-8eab-583e-bf07-196020d04ad8 | note | Responsible Person - Quality Controller, Engineer
e5e23534-58fa-5c50-acf0-10dd75124320 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
463e7a5c-cec4-5da8-a4c5-dd52a0a3d064 | note | Conduct - S or C
4d8b8096-058a-51c0-bddf-67e5cf3e7c9f | note | Produce Record - S or C
85434f21-d3be-54b1-9ebd-3bf669e1bf90 | note | Approval - E
0205cfd8-829f-5b0c-9464-819ae3549976 | note | Witness Point Y/N - Y
| checkpoint | Compaction Acceptance
f2927a50-5d05-5249-a368-2d906b4b0d60 | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, Acceptance criteria for pavement layer compaction (7.6) - TNZ B/2: 2005
987a412a-cf07-533f-924c-250d7deaca88 | note | Acceptance Criteria - Mean value ≥ 95% and Minimum Value ≥ 92%
7524ceb3-3b1d-55ae-a8c6-22af890ff889 | note | Method - Nuclear Densometer Testing
20e5f16b-cbc2-5dbd-bab8-80ffdb1633fb | note | Frequency - ≥ 5 tests per 1000m² lot
9fbadf58-ec25-586a-89bf-2b57053a4cf1 | note | Responsible Person - Quality Controller
d43ac756-58dd-5971-9211-965825fddf7c | note | Verifying Document - NDM Record
c55792d0-8b6a-59d4-af66-8047b9084d03 | note | Conduct - S or C
03343584-95ce-5d64-aec3-42a6cb1c7624 | note | Produce Record - S or C
82bfd9bb-738d-5b1a-a061-1ec09f42501e | note | Approval - E
99d5aeb8-499e-5d32-9b15-9f6869ef58fa | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Control Testing (if required)
051abecd-0e29-5fe5-87ee-9d3807fa5c75 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
cc19c1aa-efc6-5d4e-830d-6102a05b8b99 | note | Acceptance Criteria - Nil
9c063f1e-6fcf-59a4-a6e7-acce0f75bba5 | note | Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
b0ebad7b-6c12-55a5-b565-7ed3ce5d0652 | note | Frequency - when agreed with the Engineer
3844f92c-a3e1-585a-974a-df111c9040b3 | note | Responsible Person - Quality Controller
cedf4377-9381-5c00-ab35-8ac38c7e9e88 | note | Verifying Document - Test Report
dd09cc04-b3aa-5b8a-ac15-ed5dbb867344 | note | Conduct - S or C
723def10-057a-5887-a587-35beab6a7939 | note | Produce Record - S or C
d62f01a2-e9eb-5dc7-ae22-0d0cd6677083 | note | Approval - E
9eb00595-2dc5-53a3-b838-edbc0eddb20f | note | Witness Point Y/N - Y
| checkpoint | Surface Shape
93b45f3e-2065-5010-addb-d5a3039f2204 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
69f93476-7449-54e1-a75e-2553576aaddf | note | Acceptance Criteria - Between -25mm and +5mm
3249f23c-4aaa-59a6-bbee-5c3a9f43cede | note | Method - String lines or Survey Asbuilt
d3101fb6-effa-5819-befc-c57746b577da | note | Frequency - during construction and prior to seal
89ffe969-be37-5e22-8b75-3ba84ca2d170 | note | Responsible Person - Supervisor
d2651522-904c-5611-9e85-69801b65fbbd | note | Verifying Document - String Sheet/Survey Asbuilts
9ad27452-f66e-50ac-84d3-fd8a3805a46b | note | Conduct - S or C
6f153a24-92e5-55fb-92e6-582ff26c45c1 | note | Witness - C and E
22440550-81b6-5633-b9c1-bd006f1713da | note | Produce Record - S or C
55dc97ac-7ebd-5823-9772-a8a735e19db5 | note | Approval - E
50b09a8e-caa2-55d1-b39c-441ace88b8a8 | note | Witness Point Y/N - Y
| checkpoint | Cross Fall
0171fab1-f8b6-5323-a892-28b9796ead0e | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
0c4f2c6d-b15f-5d19-b427-ab41a6659547 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
4d294284-7b5d-5f53-9d8a-35ab665231a7 | note | Method - 3m straight edge or Survey Asbuilt
00a36e15-9497-5d22-9d77-b7247edda7ad | note | Frequency - during construction and prior to seal
181562d6-573b-5519-8329-49033046b9d7 | note | Responsible Person - Supervisor
11580fc4-09e0-53ce-adc4-2aa7869353d0 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
7b9d842f-25bc-57ed-92b6-23a4a7dade57 | note | Conduct - S or C
011e990e-27a2-52b7-a0a8-c7b7206231b3 | note | Witness - C and E
71bcaefe-3ec5-559d-9002-c997f43a9cec | note | Produce Record - S or C
d1544e63-cf2d-501d-b663-ff332528b152 | note | Approval - E
337d222c-9a8f-5b2d-90c4-1cfd60614b6e | note | Witness Point Y/N - Y
| checkpoint | Degree of Saturation, DOS
cd87e2cd-2f01-58f5-9aa5-6af4ace06703 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, Pre-sealing requirements (9) - TNZ B/2 Notes: 2005
f8e01080-67ea-5028-bc66-449a691b25e7 | note | Acceptance Criteria - ≤80%, however 65% is ideal
a0abbe7c-e01f-5755-80ed-e7a91f850b2f | note | Method - Nuclear Densometer Testing
cd28e498-b55f-5472-9048-d7c24be1a65c | note | Frequency - ≥5 tests per 1000m² lot
93fe709a-7291-5958-9b13-f4abcdc92b2d | note | Responsible Person - Quality Controller
d09770df-a060-53ad-ab17-5da0a3110de0 | note | Verifying Document - NDM Record
bec59297-6b36-59ef-8dd8-f6242a0bfa6e | note | Conduct - S or C
e2d87d04-f233-5851-81c2-4e7942e73905 | note | Witness - C and E
e1db5394-9b5d-5101-bf90-550cce463502 | note | Produce Record - S or C
c264121e-c036-59c8-bb96-b9506aabd4e1 | note | Approval - E
9b5705fb-b264-551a-917b-ddf0a7876749 | note | Witness Point Y/N - Y
| checkpoint | Place M/4 AP40 Basecourse Material
| note | Controlling Documents - TNZ B/2 section 7.2
| note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
| note | Method - Visual Inspection
| note | Frequency - On completion of placement
| note | Responsible Person - Quality Controller
| note | Verifying Document - Photographs and Daily Site Record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - C
| note | Witness Point Y/N - Y
| checkpoint | Addition of Water
| note | Controlling Documents - TNZ B/2 section 7.5
| note | Acceptance Criteria - 90-100% OWC
| note | Method - Nuclear Densometer Testing prior to Stabilisation
| note | Frequency - ≥1 per 1000m² lot
| note | Responsible Person - Quality Controller
| note | Verifying Document - NDM Record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - C
| note | Witness Point Y/N - Y
| checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
| note | Controlling Documents - TNZ B/2 section 7.5
| note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
| note | Method - Plateau Density Testing
| note | Frequency - 1 time, or additional tests when material changes visually
| note | Responsible Person - Supervisor
| note | Verifying Document - Test record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - C
| note | Witness Point Y/N - Y
| checkpoint | Establish Compaction Target
| note | Controlling Documents - TNZ B/2 section 7.5
| note | Acceptance Criteria - To provide MDD for NDM testing
| note | Method - Plateau Density Testing
| note | Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
| note | Responsible Person - Quality Controller
| note | Verifying Document - Test Record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (1)
| note | Controlling Documents - TNZ B/2 section 7.6
| note | Acceptance Criteria - To provide MDD for NDM testing
| note | Method - Laboratory MDD at OMC, NZS 4402 test 4.1.3.
| note | Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
| note | Responsible Person - Quality Controller
| note | Verifying Document - Test Record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - C
| note | Witness Point Y/N - Y
| checkpoint | Degree of Compaction MDD to obtain target for NDM testing (2)
| note | Controlling Documents - TNZ B/2 section 7.6
| note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
| note | Method - Plateau Density Testing, Lab. MDD
| note | Frequency - At commencement of construction and whenever materials change
| note | Responsible Person - Quality Controller, Engineer
| note | Verifying Document - Notice to Contractor/ Notice to Engineer
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Compaction Acceptance
| note | Controlling Documents - TNZ B/2 section 7.6
| note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
| note | Method - Nuclear Densometer Testing
| note | Frequency - ≥ 5 tests per 1000m² lot
| note | Responsible Person - Quality Controller
| note | Verifying Document - NDM Record
| note | Conduct - S or C
| note | Produce Record - S or C
| note | Approval - E
| note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Surface Shape
| note | Controlling Documents - TNZ B/2 section 7.7
| note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
| note | Method - 3m Straight Edge
| note | Frequency - during construction and prior to seal
| note | Responsible Person - Supervisor
| note | Verifying Document - Photographs
| note | Conduct - S or C
| note | Witness - C and E
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Cross Fall
| note | Controlling Documents - TNZ B/2 section 5.1
| note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
| note | Method - 3m straight edge or Survey Asbuilt
| note | Frequency - during construction and prior to seal
| note | Responsible Person - Supervisor
| note | Verifying Document - Cross Fall Records/Survey Asbuilts
| note | Conduct - S or C
| note | Witness - C and E
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Surface Finish
| note | Controlling Documents - TNZ B/2 section 7.8
| note | Acceptance Criteria - Tightly bound matrix post sweep
| note | Method - Visual inpsection
| note | Frequency - prior to seal
| note | Responsible Person - Supervisor
| note | Verifying Document - Pre-seal inspection sheet
| note | Conduct - S or C
| note | Witness - C and E
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Degree of Saturation, DOS
| note | Controlling Documents - TNZ B/2 section 12
| note | Acceptance Criteria - ≤80%, however 65% is ideal
| note | Method - Nuclear Densometer Testing
| note | Frequency - ≥5 tests per 1000m² lot
| note | Responsible Person - Quality Controller
| note | Verifying Document - NDM Record
| note | Conduct - S or C
| note | Witness - C and E
| note | Produce Record - S or C
| note | Approval - E
| note | Witness Point Y/N - Y
| checkpoint | Roughness (NAASRA)
db01c763-a4f5-540e-8c24-75d388004576 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
aa1db764-a9a4-552c-93fa-5e2354177447 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
3d04b594-4580-53ed-9a6b-da762f9f0831 | note | Method - NZTA Maintainence specification section 6.1.2
79eff727-9780-5447-8cf3-2c0e9ec13b97 | note | Frequency - Average of three replica runs for each lane reported at 20m intervals.
7538d6ca-4c08-5934-8dfc-9087ba38693c | note | Responsible Person - Quality Controller
faae05d4-9e48-5d34-bbca-b2b86d8d1e5d | note | Verifying Document - Test Records
32668344-236d-568c-be25-deae334d3878 | note | Conduct - S or C
17119a05-6c66-56e8-81d4-93195eb4fbd0 | note | Witness - C and E
2f02ce29-1c6f-5976-9222-ca34a5fdab6c | note | Produce Record - S or C
c7047cb2-75ab-51fb-9aec-709a38b275bb | note | Approval - E
d6ed1d48-beca-5384-a2ef-0afed89f5ead | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| section | 5. Chip Sealing - 5.1. Procurement
| checkpoint | Binder - Penetration Grade
106bfefa-2d3d-5e2f-a702-f648dcf8e063 | note | Controlling Documents - TNZ M/1
93e0b427-df7e-50b3-9e18-3ac200651925 | note | Acceptance Criteria - Table 1
91327dcd-f1c1-5091-9de0-10bd77559040 | note | Method - Property Test
ca627b73-98c8-5262-aef0-a5c029de159c | note | Frequency - Annual
d8370045-811f-55c1-b2ae-f63a4e53c4d8 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
1842c9d1-12c7-534a-b5d1-29abad9744ab | note | Verifying Document - IANZ Report's
4caeda29-979c-5d43-b9ef-e27b0398e9eb | note | Conduct - C
bf565a17-1e1d-50a2-baa5-228fe386cd92 | note | Produce Record - C
1da30360-988d-5dec-a2ca-079d7a95a1a6 | note | Approval - C
0a0c1060-1e11-58b6-9eb6-de8ecc08a61a | note | Witness Point Y/N - Y
| checkpoint | Binder - Polymer Modified Emulsion
34635e83-e838-570a-9072-9da1f91490e0 | note | Controlling Documents - Higgins Internal Specification
493487cd-ee1d-5fc8-a69f-fa20364d6de9 | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
45734de5-39c5-535f-8653-c34fa0912c4b | note | Method - Property Test
a6546f4b-4b19-562d-8d19-d19986ea4341 | note | Frequency - 1/100,000 litres supplied
d177643f-0166-50bd-9a20-7f28d9dc1227 | note | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
0b5e8fc9-3f08-5d50-86f6-974bb9e66955 | note | Verifying Document - IANZ Report's
8962ff59-7237-5b9c-aa22-5aaeedbf3c4f | note | Conduct - C
679253ef-b996-5cc6-8b88-d13a8b241270 | note | Produce Record - C
e713409a-102b-5ef8-9d42-73b3712e90b1 | note | Approval - C
d6261fdd-9f26-5052-9894-ff2969f21567 | note | Witness Point Y/N - Y
| checkpoint | Source Property - Coarse Aggregate - Crushing Resistance
e96a9f9f-c5ae-58c5-b5fd-70989cf03109 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
74f7a3e7-3d97-57c8-90f8-94669f249a00 | note | Acceptance Criteria - <10% fines under 230kN minimum
cf11763d-b01e-5686-bdd6-bef9343444e8 | note | Method - Sample Test - Crushing Resistance, NZS 4407 Test 3.10
8e483655-0924-54e5-9001-a79b974ee0c3 | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
9b446521-035d-58fa-ac07-8fd36d218d26 | note | Responsible Person - Surfacing Project Manager
00918bad-eb2b-507f-8edc-3bb93946a861 | note | Verifying Document - IANZ Report's
d52bcc1d-5b15-5e06-8207-a795dc2dad7d | note | Conduct - C
290b0b37-1035-599e-ace7-bccc181f6806 | note | Produce Record - C
fbb1d986-0201-5987-a633-f855e90faeac | note | Approval - E
d9a9b99a-4115-5962-95c9-8cbe8940f3ed | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Source Property - Coarse Aggregate - Weathering Resistance
8c13ddfd-caf3-5de0-8f57-7f24a83f31b8 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
9627d1dc-09eb-5ff1-8547-e85aa1cb85b1 | note | Acceptance Criteria - AA or BA
3bdb9071-4b01-5642-8066-0ab1849b6b9b | note | Method - Weathering Quality Index, NZS 4407 Test 3.10
ef87ba8e-3293-59a0-879e-16fd8ae70d6c | note | Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
e6633395-f812-523f-9643-cd91b8dfdb27 | note | Responsible Person - Surfacing Project Manager
5f30435c-0aad-5b51-a628-447b079b03d9 | note | Verifying Document - IANZ Report's
69937f97-4b43-5e9e-b75f-e82a3106790d | note | Conduct - C
b87c0174-0287-5074-9af2-832d5ea311f5 | note | Produce Record - C
3528713e-9090-5f73-a010-66da617e3334 | note | Approval - E
2d7dd1ca-7297-52b8-a44e-f370f6bb4454 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Source Property - Skid Resistance
c09c96e9-b583-5e1d-9e90-a08dc889fcf4 | note | Controlling Documents - NZTA T/10
4b977c22-5c5e-520e-bba7-1925e2837f90 | note | Acceptance Criteria - Meet Skid performance Requirement
75f65ad5-c867-5864-b3ad-2efa2e3246e8 | note | Method - Aggregate Perfomance Method, TNZ T/10 section 12.3
f509c758-436c-5cad-a1a7-0a5883731bee | note | Frequency - Each Site
7c33239c-7340-5757-9f5a-d3c2fad02b36 | note | Responsible Person - Surfacing Project Manager
6f0e4a50-4083-5b1a-90ff-879367ed88ab | note | Verifying Document - IANZ Report's
a35db03b-2e7d-52de-b3f0-3262bfc6a3d3 | note | Conduct - C
e86376e8-c38c-59bb-8189-43b1c1b2ecaa | note | Produce Record - C
bbc6b528-8cd4-598a-942e-a2f5bfbc0c08 | note | Approval - E
3f295b0c-aaf8-5025-bf5e-7dc7971f71b1 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Cleaness Value
900248fe-96b0-5f93-a8f7-1452facc6b79 | note | Controlling Documents - NZTA P/17, M/6
d48ec4f7-59a1-5d1c-a83b-4a14c6b5e25e | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
7fd32ad0-fde0-53eb-bed0-b240c3fc85d8 | note | Method - Sample Test - Cleaness Value, NZS 4407 Test 3.9
22ded9dc-70f6-5f6c-8e78-62051ae5bfea | note | Frequency - Per Stockpile
9527adaf-93c8-5be9-9f7b-3f5cec601cd0 | note | ○ <100m3 - 1 Sample
28be1ca0-f11c-5dbf-9387-4448d653ffdb | note | ○ 100-500m3 - 2 Samples
567a0512-c6d1-5352-85e5-370f08f96131 | note | ○ >500m3 - 3 Samples
9b86177d-2eca-5799-8202-5cc611aa1ab8 | note | Responsible Person - Surfacing Project Manager
688a5437-5065-5776-9994-2b0f14356c0e | note | Verifying Document - IANZ Report's
7d922941-3ab8-5bfe-9a22-6fd446228927 | note | Conduct - C
6da0872a-9869-54f0-a284-e23928a30798 | note | Produce Record - C
303dc5e9-526a-5bcc-8f9b-ff6f51634f37 | note | Approval - E
04b90094-467f-56b3-a475-e76d60e437ed | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Particle Size/Shape
b7eeef70-2d05-5844-b10b-4667b5e7e4f1 | note | Controlling Documents - NZTA P/17, M/6
299a2b37-d08c-56ac-a937-29c8ccd70aa6 | note | Acceptance Criteria - As per Table 3 NZTA M/6
034e181f-127a-55bc-8d72-2a9e62ee071e | note | Method - Sample Test - Particle Size/Shape, NZS 4407 Test 3.13
a5af50c4-788b-5a6e-a4a4-3e67a86402da | note | Frequency - Per Stockpile
c41bbe30-1fbb-535f-89d0-5a3c1aeeb149 | note | ○ <100m3 - 1 Sample
04a2f188-5ae6-5875-b6a6-95b99b1de411 | note | ○ 100-500m3 - 2 Samples
c40cbcd5-ed0d-5f60-99c8-2e8a86827757 | note | ○ >500m3 - 3 Samples
0ac15e4b-bbe4-56e3-98b5-ef68d6b3d94d | note | Responsible Person - Surfacing Project Manager
b0fd733a-eaaa-504c-a3e8-ed27a294a068 | note | Verifying Document - IANZ Report's
96071617-ec9c-5eed-aa8a-af4248bcf30e | note | Conduct - C
28264bd6-5540-569a-b24e-cd430739bf87 | note | Produce Record - C
ee1d438c-6fcf-5c74-a9b4-3d9da24ffe40 | note | Approval - E
737cc71a-4d3b-5b13-aa3f-430dda7764f3 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Production Property - Broken Faces
aa5f68af-9f43-5b0b-a357-a9087812716d | note | Controlling Documents - NZTA P/17, M/6
2ce185ec-da2e-5838-a606-a9f0105b5474 | note | Acceptance Criteria - Min. 98%
d850a165-7b0f-5570-8331-b93cc78acbe3 | note | Method - Sample Test - Broken Faces, NZS 4407 Test 3.14
54ba0df6-d9af-54f2-a0ff-810a2f3129c3 | note | Frequency - Per Stockpile
1464e7e8-14c6-5fca-8271-54e88545421e | note | ○ <100m3 - 1 Sample
93716464-3a91-5cfe-8042-c1f0f7f01e4e | note | ○ 100-500m3 - 2 Samples
5668943b-29bb-5b9b-93d8-39607e479da3 | note | ○ >500m3 - 3 Samples
75a03c2b-d37e-5e8b-8732-4e951453102e | note | Responsible Person - Surfacing Project Manager
39376965-bfd4-5d29-b022-c56a51df71e1 | note | Verifying Document - IANZ Report's
fe82d55d-5467-59e0-acd1-bb03a0fbdf82 | note | Conduct - C
ac668177-0312-541a-8582-30d8b4e9c302 | note | Produce Record - C
52840833-745f-5138-96b8-1344bec5afd9 | note | Approval - E
f98dc905-57ac-5027-ae8a-59ca433a293c | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Chipseal Designs
773c5a97-db24-5183-aca8-50f9fe1065b6 | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
5b0dc83d-5bc3-5fa7-bc3a-f719ec7bfdbc | note | Acceptance Criteria - Client Approval
572b2a27-7775-543a-9e53-8e8ff79f875c | note | Method - Review
6d9be3ff-47ef-5f02-a4ae-955b5122c83a | note | Frequency - Annual
3c73a5ea-3f08-5ba3-b39e-0a4a6923cfde | note | Responsible Person - Surfacing Project Manager
fc8b3c5c-aafb-5255-8ff4-517be60d2d17 | note | Verifying Document - EBOP NOC Design Report Acceptance
46bb3865-4575-50e7-9b54-9ffeba7b4e10 | note | Conduct - C
6f5fc6a6-7e40-52a6-bfed-9a3c82743b75 | note | Produce Record - C
f8f9941c-ca46-5c7c-814f-bf4c6e36797e | note | Approval - E
3bd94641-db9f-5b6a-88c6-4a177e3ffd25 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| section | 5. Chip Sealing - 5.2. Construction
| checkpoint | Ensure limits of site are marked
83b9af8f-6cda-5ccd-b706-5f6e25736772 | note | Controlling Documents - EBOP NOC Design Report
10afed5f-cac6-5b5e-baf1-313c6bacc46d | note | Acceptance Criteria - Visual Inspection
06bffddd-dadb-59c4-ada5-ee8b0adc0bb5 | note | Method - Visual
be7f5202-f060-55d2-89d8-fca49c0c14a1 | note | Frequency - Prior to start sealing each site
79f2ea97-3f93-5dd2-9792-73f8a4377ba4 | note | Responsible Person - Surfacing Supervisor
7aeb5c8f-920e-5a7e-9773-ea66a558dab3 | note | Verifying Document - Chip Sealing Quality and Site Record
834ab158-c757-53e0-ae82-b8e504b76b9e | note | Conduct - C
68c11a34-e7fb-5077-9262-0e000d69a0ef | note | Produce Record - C
f9a3ae95-2f70-5240-945e-7f9406b2f7c5 | note | Approval - C
6b6d646c-7e66-53df-87c0-48f2cf57e2f1 | note | Witness Point Y/N - Y
| checkpoint | Sweep surface clean of deleterious material
0dcf653c-dbac-5ba1-b0d3-88ea8889d10c | note | Controlling Documents - P/17
bc224447-b472-5ade-be2d-3b366d54506e | note | Acceptance Criteria - Visual Inspection
0c9789d2-6466-55f9-a2d5-76e755de4d69 | note | Method - Visual
2b74c182-e597-59a3-ad41-779ecc352d85 | note | Frequency - Each site, prior to start of sealing
84ab21b4-b2a3-53b9-9888-e7c854bdcf23 | note | Responsible Person - Surfacing Supervisor
fa6f52d3-c899-50c8-bf9c-2c0100d43b6d | note | Verifying Document - Chip Sealing Quality and Site Record
ff3a4b8c-6bdb-502e-b9ad-9375b1526b5b | note | Conduct - C
e5c01e48-37eb-5dbb-9e64-2c430354daff | note | Produce Record - C
36a04b4c-1965-510d-a2c2-ab65757df0cb | note | Approval - C
0536b12b-d8c8-5522-8e8b-21d6bedc5c2f | note | Witness Point Y/N - Y
| checkpoint | Record ATP's on site
3dc78d41-502a-5450-b564-20319728751d | note | Controlling Documents - N/A
de708775-6c79-54b4-8b31-ad7ce145c22f | note | Acceptance Criteria - Visual Inspection
967493ac-7971-5811-bcc9-6d76f392847b | note | Method - Visual
fb61febf-a208-5a85-9ee6-ff8cb6b026b4 | note | Frequency - Each site, prior to start of sealing
83cc63fb-e08c-5655-bf25-c713dd7c3761 | note | Responsible Person - Surfacing Supervisor
2fad295a-2362-5863-a192-d9bbe0ddb5a2 | note | Verifying Document - Chip Sealing Quality and Site Record
24d9dec2-ee9a-5167-8424-cf4e7e7f28aa | note | Conduct - C
c071fd57-18cf-5339-af50-74176e128de9 | note | Produce Record - C
e3e52af0-e35c-542c-9804-7954136f3231 | note | Approval - C
8c472a9d-74fc-55b5-9bf3-efad4302cdcd | note | Witness Point Y/N - Y
| checkpoint | Confirm correct treatment(s) and chip
3fc8d859-c773-59b2-aa61-f9b262d9734d | note | Controlling Documents - EBOP NOC Design Report
b111173a-d676-5d2c-8713-02da934044f6 | note | Acceptance Criteria - Details/chip correct
d5d0f92b-1555-5cf8-adc3-8a657e370f57 | note | Method - Visual
b90731b8-bd67-5cae-a01c-03762cf10d62 | note | Frequency - Each Site
9226b789-1ce9-52b8-bc98-213eb27627b1 | note | Responsible Person - Surfacing Supervisor
506cda9d-0fdc-596a-bef3-4170758b496d | note | Verifying Document - Chip Sealing Quality and Site Record
274b497f-fdf5-5183-9111-75d1e40a882d | note | Conduct - C
221b7a94-5ffe-5aba-9c8b-0aeb4f36964b | note | Produce Record - C
3af54043-a32a-5af2-9c49-210f0862116b | note | Approval - C
910cabee-f3e3-5751-9932-e4f5bae42939 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Cutback Bitumen Blend
988f5889-3d64-5784-9254-e779de78b31c | note | Controlling Documents - RNZ 9803_0513
4b048d46-47bc-56e7-944f-5d484537d586 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
3acfdd2d-d76c-5888-9254-3348451160ee | note | Method - Sample and test
b26e18fa-a68f-55aa-a619-8481a3cf5a8b | note | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
1ad3507c-6cdf-509a-af6b-715f4ea60c60 | note | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
64ba1057-b3e5-5b3b-a67d-a87ddd9f489d | note | Verifying Document - IANZ Report's
1d62e4c9-f616-5bb8-9f53-229783fbabb3 | note | Conduct - C
13ad352f-a2c1-5cd1-a623-78c77850e59e | note | Produce Record - C
3e784a99-6b5c-56c0-9ead-f66b203d49e7 | note | Approval - C
f1b890f2-1eb9-588e-8d05-89711c651272 | note | Witness Point Y/N - Y
| checkpoint | Bitumen Application Rate
7fd99544-0377-5f93-8050-a10c8d633385 | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
4bc75e23-ce7c-5059-88cb-1b51b0d2a6aa | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
982202ff-1b71-5a62-a0f4-c140512d7eca | note | Method - Test, Review
53e08aae-2453-5d38-96cd-b1f2900ab452 | note | Frequency - Per Sprayer, Per Site
ba253db4-7e95-5f77-842d-7bbeca078e13 | note | Responsible Person - Surfacing Supervisor
7a7cf6ec-9bff-56de-959c-5081d0c220cc | note | Verifying Document - E/2 Certificate. Spray Sheets
74911001-9877-542f-81de-b3890b2d78d9 | note | Conduct - C
e1776c08-90e0-5be5-b603-4124f1c73ed8 | note | Produce Record - C
573a5774-6e15-57a4-9a5f-f86ab8ea73d8 | note | Approval - C
10eb03c4-7ce9-5b63-8cfa-b8461f9e9fa5 | note | Witness Point Y/N - Y
| checkpoint | Chip Application Rates
977caac1-d785-5020-aba0-3c15cdcba6d4 | note | Controlling Documents - Chipsealing in NewZealand
0864d9bd-5327-52e9-b417-e27065f3bb77 | note | Acceptance Criteria - As per Chipping Guide
b2c6f21b-8537-517e-961e-33979a021f89 | note | Method - Visual
49cd8409-b273-5c90-92bd-8293739a98e4 | note | Frequency - Each Site
048f8209-510f-5c13-b432-ba0d9e04f12a | note | Responsible Person - Surfacing Supervisor
a2d91f66-efba-5002-ad54-af513fdaf544 | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
397fea85-60d8-5407-bf05-965cccdfff4f | note | Conduct - C
ae92843f-ba18-5c72-ad9b-5199cbcf63d6 | note | Produce Record - C
cd0b0839-7f9c-5029-b3a5-7c825bb26e2c | note | Approval - C
a0d4417e-f3fb-5ccd-a4e1-07f867967cfe | note | Witness Point Y/N - Y
| checkpoint | Rolling
a654d364-c3a8-5b67-b346-b959f3649894 | note | Controlling Documents - Chipsealing in NewZealand
36251c0f-ad37-5be1-810e-c9bedeeb825b | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
46918674-2395-55be-9d75-37126d6f1ebf | note | Method - Visual
30ed342f-0819-5d68-9618-07fd5acac87a | note | Frequency - Each Site
1d382f0e-d787-5f0f-aa49-bc2745f4bac2 | note | Responsible Person - Surfacing Supervisor
d08447a9-9e1c-5e9b-8a8e-59b6bf1fc594 | note | Verifying Document - Chip Sealing Quality and Site Record
2a4344e7-e5e9-5216-a58d-fb1e6700f8be | note | Conduct - C
87a05e2e-4db3-5570-b1c4-fe6eff4161d9 | note | Produce Record - C
faad68ce-8875-59eb-ac28-1e7c5dbaa3e8 | note | Approval - C
96c5b7aa-4829-5512-8bb4-72ab5d8a3864 | note | Witness Point Y/N - Y
| checkpoint | Cleanup
33afa5e4-b921-5b67-bf46-527867654857 | note | Controlling Documents - Chipsealing in NewZealand
c39be899-7be9-5aa6-b31b-b3c77b32026a | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
03d278a3-6ea4-51b4-aa4b-41e396f904bb | note | Method - Visual
23b6a573-5d5a-54e8-b4d5-e538a6a2db90 | note | Frequency - Each Site
c2447066-fe88-5011-8c0b-7741bab686c6 | note | Responsible Person - Surfacing Supervisor
6f184dd1-8cd3-5a2c-a62a-d4f62f6707f4 | note | Verifying Document - Chip Sealing Quality and Site Record
ecef6417-11aa-5fca-83ff-188d48e243fd | note | Conduct - C
b313a2cf-db20-5644-a313-ed040df429a8 | note | Produce Record - C
bf544032-3363-5bed-acf0-383b79ddfcce | note | Approval - C
98cec6f8-ad2a-58af-86cb-7c33798a2552 | note | Witness Point Y/N - Y
| checkpoint | Post Sweeping
5927cbac-304d-5b30-861a-2bfa85416e43 | note | Controlling Documents - Chipsealing in NewZealand
6dfa25a3-4b66-5d07-b730-0b26e33b9850 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
a5fa5613-f862-5bd6-8cd4-a439e1b3427f | note | Method - Visual
832777a6-ebd0-517c-96db-6d803f0fbccb | note | Frequency - Each Site
829d6670-7d8c-546a-8776-da79db296991 | note | Responsible Person - Surfacing Supervisor
9de8bd14-08b5-5b95-b9c5-9b5ce4b697a0 | note | Verifying Document - Site Record
800ec965-519d-5c30-a33a-0af6c37c4d9f | note | Conduct - C
1aa60f63-0e21-5da0-97b1-79df72056480 | note | Produce Record - C
424a8242-21c5-5b07-8011-8c8d8dfe096c | note | Approval - C
a366d32e-c084-565d-b97a-23004d64355d | note | Witness Point Y/N - Y
| checkpoint | Linemarking and RRPM Reinstated
eb222bbc-dbaa-5d93-9afc-15479fdae1b7 | note | Controlling Documents - MOTSAM
cb11433c-60af-5af6-bd38-87dab6c4981b | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
748d47db-eac4-5b02-a7f6-f881d89919a9 | note | Method - Visual
5c128e1d-8767-56f5-b136-9f1911a677b6 | note | Frequency - Each Site
8da71cd3-642a-57a5-b196-202cead79706 | note | Responsible Person - Surfacing Supervisor
b845cfb2-4a3d-5539-b566-c29dd7dea456 | note | Verifying Document - Site Record
e2978566-2d03-592a-810e-818b0409f6fa | note | Conduct - C
0869f03b-8352-543f-ad61-ec408a96af33 | note | Produce Record - C
fb471c14-60a8-505a-87ab-4775b6a2cd66 | note | Approval - C
3df3d75a-44f0-52e6-b24b-6386be9c6fd9 | note | Witness Point Y/N - Y
| section | 5. Chip Sealing - 5.3. Post Construction
| checkpoint | Post Construction Walkover
f3bae9b0-cffa-53bb-aa58-804783cfb983 | note | Acceptance Criteria - Formal Agreement
571b05ba-4eeb-567b-a767-5ceb968bd444 | note | Method - Visual Inspection
cfb88bd9-74e8-5364-9ac3-49a5774fcf4c | note | Frequency - Post seal sweep
609545cf-efc1-5686-b7e0-54d46157ccdf | note | Responsible Person - Quality Controller, Supervisor and Engineer
3a935f3d-cd39-5e41-bdc6-190b88843f66 | note | Verifying Document - Meeting Minutes
5d18cc9a-a669-551c-aedf-4feb663f115c | note | Conduct - C
fc871a13-99ed-528a-a5d7-1de8b646c917 | note | Witness - C, S and E
713ced36-2c0a-5466-b45e-f93b9b2a660b | note | Produce Record - C
8a3c5b29-ad9c-58ad-a888-abc7b7951415 | note | Approval - E
3f20c9f0-9148-50ed-87da-1dc37d2a72c9 | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| checkpoint | Resurfacing Construction Completion report
a8719cf7-e163-56b8-8168-acc1e9552819 | note | Controlling Documents - NOC; MS 6.1.3
5a54e316-cce3-5545-aace-a5a4c4b1b557 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
39a9d47d-e48a-576b-855f-1fc999f5bfe8 | note | Method - Record
167602ff-f167-5c97-b7e0-b03ff3b5790c | note | Frequency - Within 2 months of completing the annual resurfacing programme
e2c0a9a6-caa9-561d-84b5-80adbe00e655 | note | Responsible Person - Surfacing Manager
8640257c-3ae7-5fe5-8134-e944106d0529 | note | Verifying Document - Construction Completion Report
4e3ebea8-4ff5-532f-9d9d-c5090b83ef39 | note | Conduct - C
f3840b11-ec73-543f-a39f-72742f27e866 | note | Produce Record - C
179b928f-fd75-515f-8eee-2ec50509ef83 | note | Approval - C
922c0796-1134-5ee7-b903-3ef81494aadc | note | Hold Point Y/N - Y
| signoff | HOLD POINT
| section | 6. Close Out
| checkpoint | Pavement Rehabilitation Construction Completion Report
a3afcae1-802d-5a4f-9abc-4bef5880e007 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
4da15e35-c6e7-5767-bf9a-abc1a4cd78e8 | note | Acceptance Criteria - Engineer Approval
fde4e76c-08b7-57e6-ae03-e0643a0c8c4b | note | Method - Visual Inspection
9b5dcc39-1467-5a29-b0e3-4aa921bbc2ff | note | Frequency - ≤2 months of 1st Coat Seal
a59ad839-8f56-5440-8278-11f4c2042d07 | note | Responsible Person - Quality Controller/ Contract Manager
7e60e1ae-c5ff-511c-af01-c01212fa430f | note | Verifying Document - Signed Report
84d52170-ba47-533c-b4e6-f9bcc31a555c | note | Conduct - C
ba5a9d79-ae08-5925-902b-6cd2705fa82a | note | Witness - C, S and E
df56814d-1fb7-5015-91e4-c618e8f55529 | note | Produce Record - C
0f75c79e-3692-520e-9b22-913726cd4ee2 | note | Approval - E
0bb903c8-29b0-5313-9b7f-b8f23095c818 | note | Hold Point Y/N - Y
| signoff | HOLD POINT