## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-215-CIV-HOP- Rail Delineation Fencing
ITP Description: |  | Rail Delineation Fencing
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-10-18
ITP created by: |  | Cedric Guico
ITP approved for use by: |  | Pradeep TALASILA
Special Notes to ConQA Team : |  | ITP for Hopkins Road
Inspection & Test Plan - Rail Delineation Fencing
[9 empty] | Revision: | 0
[9 empty] | Date: | 2024-10-18
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | FH01 Hopkins Barrier Alignment | Mark Up | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Hopkins FH01 Occupation Works Mark Up | Mark Up | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | MRP-DPK-102-00-CPW-0061 | IFC Drawing | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Rev 1, SAST-3281 Rev 1, and AS 1725 Chain link Fabric Fencing Security Fences and Gates | Standard | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Materials
2.1 | DB80 Concrete Barrier & Gawk Screens | IFC Drawings | Delineation fence to be DB80 Concrete Barrier & Gawk Screens | Document Review | Each Fence | IP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Class 3 Crushed Rock | IFC Drawings | Class 3 Crushed Rock to be installed for barrier foundation and crane piling pad | Document Review | Each lot | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Removal of vegetation | Environmental control plan | As per environmental controls | Visual | Each Lot | IP | SE/PE | This ITP
3.2 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, refuge bays and fence start and end points. Offset checked against the running edge prior to installation of barriers. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings | Excavation completed by mechanical plant and hand tools. Follow asset owners guidelines for work around their service. | Visual | Each fence footing | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Install fence foundation | IFC Drawings | Excavation of 300mm from ESL. Install Class 3 Crushed Rock as per set out requirements The foundation shall have a minimum bearing capacity of 100kPa | Visual | Each post | HP | SE/Site Supervisor | Geotechnical test report
4.3 | Fence Installation | IFC Drawings | Concrete barriers (DB80 F Shape) to be installed as per survey set out. - Installation to of fence to be 2.588m offset from outside edge of rail to the inside of the barrier. Barriers to be installed with 3x interconnected barriers between refuge bays (18m) Install gawk screens compatible with concrete barriers. | Measure | Each Fence | IP | SE/Site Supervisor | This ITP
4.4 | Refuge Installation | IFC Drawings | No concrete barriers to be installed at locations of refuge bays. Refuge bays to be 1200mm wide at intervals of 18m. Install additional refuge bays or reduced spacing to allow access to rail assets 50mm dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. Refuge access to be 1200mm wide Refuge bay signage installation halfway between each refuge bay | Visual/Measure | Every 18m MAX. | IP | SE/Site Supervisor | This ITP
4.5 | Limited Clearance Sign | IFC Drawings | Limited clearance signs to be erected at all refuge locations and at each end of Delineation Fence Sign to read "DANGER LIMITED CLEARANCE DO NOT OCCUPY DURING PASSAGE OF TRAINS" | Visual | As required | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | Fence Height and Track Clearance | IFC Drawings | Inside face of concrete barriers clearance from rail to be physically checked with tape measure. All corners to be checked with Engineer and Foreman | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /