## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-214-CIV-Hop-Piling Pad (Supply and Install) | itp |  |  |  |  | ITP-214-CIV-Hop-Piling Pad (Supply and Install) Rev 0 (FH01)
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-214-CIV-HOP-Piling Pad (Supply and Install)
label | ITP Description: Piling Pad (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 18/10/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep TALASILA
label | 1.1 - Non Dependent
label | Reference - VicRoads Standard Section 204 (Dec 2015)
label | 1.2 - Non Dependent
label | Reference - VicRoads Standard Section 173 (Oct 2008)
label | 1.3 - Non Dependent
label | Reference - Temporary Works Design - Crane Piling Pad Design
label | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Class 3 Crushed Rock
label | Reference - IFC Drawings
label | VicRoads:
label | ○ Section 204
label | ○ Section 173
label | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL ,MMD & OMC
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - Temporary work design Drawing
label | VicRoads:
label | ○ Section 204
label | ○ Section 173
label | Acceptance Criteria - Survey to set out extent of crane piling pad requirements.
label | ○ Survey pegs in place and clearly marks out the limits of works.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Check location of underground and above ground utilities
label | Reference - DBYD, QMP
label | Acceptance Criteria - Ensure that:
label | ○ Dial Before You Dig
label | ○ Services isolated
label | ○ Permits obtained from internal and external authorities
label | Method - Visual and Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Preparation of piling platform foundation (proof Roll)
label | Reference - Temporary Works Design Drawing
label | VicRoads:
label | ○ Cl 204.12
label | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shall be rectified. Nominated Authority to be present during all test rolling.
label | ○ Temporary work Design Drawing and equipment design requirements. No waving indication.
label | Method - Visual
label | Frequency - Each fence footing
label | Category - HP
label | Responsibility - SE/Site Supervisor, Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Fill, Compaction and testing
label | Reference - Temporary Works Design Drawing
label | VicRoads:
label | ○ Cl 204.10
label | ○ Cl 204.13
label | Acceptance Criteria - Bearing Test to support piling rig (as indicated in temporary works design). Target 100kPa.
label | ○ Testing and acceptance of compaction and moisture content as per VicRoads Cl 204.13
label | ○ Attach: compaction test results
label | Method - Test
label | Frequency - Each Pad
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - NATA Bearing Test Report, Compaction Test Results
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Verify survey conformance
label | Reference - Temporary Works Design Drawing
label | VicRoads:
label | ○ Cl 204.03
label | Acceptance Criteria - Construction Tolerances finished ground level ± 40mm or equipment requirements
label | ○ Attach: Survey report
label | Method - Visual
label | Frequency - Each Pad
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-215-CIV-HOP Rail Delineation Fence | itp |  |  |  |  | ITP-215-CIV-HOP Rail Delineation Fence Rev 0 (FH01)
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-215-CIV-HOP- Rail Delineation Fencing
label | ITP Description: Rail Delineation Fencing
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 18/10/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep TALASILA
label | 1.1 - FH01 Hopkins Barrier Alignment
label | Reference - Mark Up
label | 1.2 - Hopkins FH01 Occupation Works Mark Up
label | Reference - Mark Up
label | 1.3 - MRP-DPK-102-00-CPW-0061
label | Reference - IFC Drawing
label | 1.4 - Rev 1, SAST-3281 Rev 1, and AS 1725 Chain link Fabric Fencing Security Fences and Gates
label | Reference - Standard
section | 2. Materials
checkpoint | 2.1 - DB80 Concrete Barrier & Gawk Screens
label | Reference - IFC Drawings
label | Acceptance Criteria - Delineation fence to be DB80 Concrete Barrier & Gawk Screens
label | Method - Document Review
label | Frequency - Each Fence
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
checkpoint | 2.2 - Class 3 Crushed Rock
label | Reference - IFC Drawings
label | Acceptance Criteria - Class 3 Crushed Rock to be installed for barrier foundation and crane piling pad
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Removal of vegetation
label | Reference - Environmental control plan
label | Acceptance Criteria - As per environmental controls
label | Method - Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, refuge bays and fence start and end points.
label | ○ Offset checked against the running edge prior to installation of barriers.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation completed by mechanical plant and hand tools.
label | ○ Follow asset owners guidelines for work around their service.
label | Method - Visual
label | Frequency - Each fence footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Install fence foundation
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation of 300mm from ESL. Install Class 3 Crushed Rock as per set out requirements
label | ○ The foundation shall have a minimum bearing capacity of 100kPa
label | Method - Visual
label | Frequency - Each post
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Geotechnical test report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Fence Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Concrete barriers (DB80 F Shape) to be installed as per survey set out. - Installation to of fence to be 2.588m offset from outside edge of rail to the inside of the barrier. Barriers to be installed with 3x interconnected barriers between refuge bays (18m)
label | ○ Install gawk screens compatible with concrete barriers.
label | Method - Measure
label | Frequency - Each Fence
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Refuge Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - No concrete barriers to be installed at locations of refuge bays.
label | ○ Refuge bays to be 1200mm wide at intervals of 18m.
label | ○ Install additional refuge bays or reduced spacing to allow access to rail assets
label | ○ 50mm dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | ○ Refuge access to be 1200mm wide
label | ○ Refuge bay signage installation halfway between each refuge bay
label | Method - Visual/Measure
label | Frequency - Every 18m MAX.
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.5 - Limited Clearance Sign
label | Reference - IFC Drawings
label | Acceptance Criteria - Limited clearance signs to be erected at all refuge locations and at each end of Delineation Fence
label | ○ Sign to read "DANGER LIMITED CLEARANCE DO NOT OCCUPY DURING PASSAGE OF TRAINS"
label | Method - Visual
label | Frequency - As required
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - Fence Height and Track Clearance
label | Reference - IFC Drawings
label | Acceptance Criteria - Inside face of concrete barriers clearance from rail to be physically checked with tape measure.
label | ○ All corners to be checked with Engineer and Foreman
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-217-CIV-HOP-Subgrade Preparation - Road | itp |  |  |  |  | ITP-217-CIV-HOP-Subgrade Preparation - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-217-CIV-HOP-Subgrade Preparation - Road
label | ITP Description: Subgrade Preparation - Road
label | Discipline (e.g. CIV/STR/RAIL): 217-CIV-HOP
label | Revision Number: 0
label | Revision Date: 28/10/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Tisala
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
section | 2. Preliminaries-Materials
checkpoint-no-value | 2.1 - Non Dependent
label | Reference - N/A
section | 3. Preliminaries-Documentations
checkpoint-no-value | 3.1 - Non Dependent
label | Reference - N/A
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | Method - Verify
label | Frequency - Prior to commencement of excavation
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | ○ Assigned CBR ≥ 2.5%
label | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type A fill Lot Number:
label | Method - Verify-Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - This ITP/Test Report/Referenced Lot number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Material classified as silt
label | Reference - Section 204.04 b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | Method - Document Review
label | Frequency - Prior to commencing
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | Reference - Section 204.06 f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | Method - Site Inspection/ Document Review
label | Frequency - Prior construction of the regulating layer
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Unsuitable Material
label | Reference - Section 204.07 d)
label | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Groundwater
label | Reference - Section 204.06 h)
label | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Cut to Fill Zones
label | Reference - Section 204.06 g)
label | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | Method - Site Inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.7 - Proof Roll
label | Reference - Section 173
label | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Site Engineer/Superintendent
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Compaction Testing
label | Reference - Table 204.131
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | ○ Scale B: Standard Compaction 98%.
label | ○ Attach: Compaction Test Result:
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Test Records, Lot Register
date | Date Completed:
checkpoint | 5.9 - Post Compaction Material Property Testing
label | Reference - Vic Roada 204.04 Table 204.141 Section 204.14 a) or b)
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | ○ CBR ≥ 3% and Swell ≤ 1.5%
label | ○ Max Permeability = 5X10-9 m/s
label | ○ Grading:
label | • 75.0mm 100%
label | • 4.75mm 40-80%
label | • 0.075mm 10-40%
label | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale B:
label | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | Date Completed:
section | 6. Post Construction Activities
checkpoint | 6.1 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances (Scale A):
label | • Range x = +5, -15mm
label | • Max S = 12 mm
label | • 80 measurements per lot
label | ○ Level tolerances (Scale B):
label | • Range x = +5, -25mm
label | • Max S = 15 mm
label | • 40 measurements per lot
label | ○ Level tolerances (Scale C):
label | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Review Document
label | Frequency - Each lot
label | Category - SCP
label | Responsibility - SE/Surveyor
label | Verifying Documents - Sign ITP, Attach Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-218-CIV-HOP-Type A Fill - Road | itp |  |  |  |  | ITP-218-CIV-HOP-Type A Fill - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-218-CIV-HOP- Type A Fill - Road (Supply and Install)
label | ITP Description: Type A Fill - Road (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 218-CIV-HOP-
label | Revision Number: 0
label | Revision Date: 28/10/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Tisala
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | VicRoads Standard Section 176 (Sept 2008)
label | VicRoads Section
label | 204 (Dec 2015)
label | Code of Practice RC500.20
label | Code of Practice RC500.5
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Conformance
label | Reference - Section 204.04 b) Table 204.041 IFC Drawings
label | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | ○ Assigned CBR≥8%
label | ○ Swell ≤ 1.5%
label | ○ Permeability ≤ 5X10-9 m/s
label | ○ Grading:
label | • 75.0mm 100%
label | • 4.75mm 40-80%
label | • 0.075mm 10-40%
textbox | Reference: Material approval in Teambinder:
label | Method - Document Review
label | Frequency - Once, for each material type
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Supplier Material Conformance Certificate
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Pre-Commencement of Fill Works
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
textbox | Reference: Subgrade Preparation Lot Number:
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1 - Survey Set Out
label | Reference - Design Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Signed ITP, Lot Map
date | Date Completed:
checkpoint | 5.1 - Placing of Fill
label | Reference - Section 204.10
label | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | Method - Visual
label | Frequency - Each Lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.2 - Test Roll
label | Reference - Section 173.03, Section 204.12
label | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | Method - Test Roll as per 173.03
label | Frequency - Each Lot/Layer
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Compaction Testing
label | Reference - Table 204.131 Section 204.14 c) Table 204.142
label | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | ○ Standard Compactive Effort
label | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | ○ Compaction and Moisture content
label | • Scale B: Standard Compaction 98%.
label | ○ Lot size - the leser of one day's production or 5,000sqm
label | ○ ATTACH: COMPACTION TEST RESULTS
label | Method - Review Document
label | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP, Attach Compaction Test Report
date | Date Completed:
checkpoint | 5.4 - Preparation of final surface
label | Reference - Section 204.15, 204.03 (g)
label | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | Method - Measure
label | Frequency - Top layer
label | Category - IP
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint | 6.1 - Post Compaction Material Property Testing
label | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | ○ CBR ≥ 3% and Swell ≤ 1.5%
label | ○ Max Permeability = 5X10-9 m/s
label | ○ Grading:
label | • 75.0mm 100%
label | • 4.75mm 40-80%
label | • 0.075mm 10-40%
label | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale B:
label | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | Date Completed:
checkpoint | 6.2 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances Scale A:
label | • Range x = +5, -15mm
label | • Max S = 12 mm
label | • 80 measurements per lot
label | ○ Level tolerances Scale B:
label | • Range x = +5, -25mm
label | • Max S = 15 mm
label | • 40 measurements per lot
label | ○ Level tolerances Scale C:
label | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Document Review
label | Frequency - Top of Type A/Verge
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP, Survey Conformance Report
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-219-CIV-HOP-Type B Fill - Road | itp |  |  |  |  | ITP-219-CIV-HOP-Type B Fill - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-219-CIV-HOP-Type B Fill - Road (Supply and Install)
label | ITP Description: Type B Fill - Road (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 219-CIV-HOP
label | Revision Number: 0
label | Revision Date: 28/10/2024
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - Reference Documents:
label | IFC Drawings
label | VicRoads Standard Section 176 (10/9/2008)
label | VicRoads Standard Section 204 (29/12/2015)
section | 2. Preliminaries
checkpoint | 2.1 - Material Supply
label | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
label | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
label | Method - Doc. Review
label | Frequency - Prior to Commencement
label | Category - HP
label | Verifying Documents - NATA Test Certificate
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set Out
label | Reference - Design Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint | 3.2 - Pre-Commencement of Fill Works
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Placing of Fill
label | Reference - Section 204.10 (d) (iii)
label | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
label | Method - Monitor
label | Frequency - Each layer
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint | 4.2 - Keying of Layers
label | Reference - Section 204.10(d)(i)
label | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | Method - Monitor
label | Frequency - Each layer
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint | 4.3 - Test Rolling
label | Reference - Section 204.12, 173.03
label | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
label | Method - Measure
label | Frequency - Each layer
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Post Compaction Testing
label | Reference - Section Table 204.131, 204.13, 204.14
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | ○ Scale B: Standard Compaction 98%.
label | ○ Attach: Compaction Test Result:
label | Method - Doc. Review
label | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
label | ○ Placed within 400 mm of top of Type B: Test every second lot of like material and work
label | ○ Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
label | Verifying Documents - NATA Test Certificate
date | Date Completed:
checkpoint | 4.5 - Preparation of final surface
label | Reference - Section 204.15, 204.03 (g)
label | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | Method - Measure
label | Frequency - Top layer
label | Verifying Documents - Signed ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - Survey Conformance As Built
label | Reference - Section 204.03 (e, g & h), 206.16
label | Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
label | ○ The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Scale B:
label | • Min. No. of Measurements Per Lot: 40
label | • Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | Method - Review
label | Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
label | Verifying Documents - Survey Conformance As Built
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP