## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | First Fix - 2JS
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - 2JS
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - Ca
section | Details
checkpoint | Cable Rough In - Run patch lead from structured cable port to clock location as per elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | Materials align with spec/submitted products
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - Ca
section | Details
checkpoint | Clock fixed onto correct location per room elevations
checkpoint | Patch lead connected from structured cabling port to clock
checklist | First Fix - EC
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - EC
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | Second Fix - HMF
section | Details
checkpoint | Install MFH Cradle to wall location
checkpoint | Plug in MFH into master device
checkpoint | Materials align with spec/submitted products
checklist | Second Fix - H1Bj
section | Details
checkpoint | Install H1Bj Cradle to wall location
checkpoint | Plug in H1Bj into master device
checkpoint | Materials align with spec/submitted products
checklist | First Fix - NC
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - NC
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - PC
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - PC
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - SA
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - SA
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - SP
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - SP
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - CLc
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Corridor Light cut out in correct location as per Shop Drawings / RCP
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - CLc
section | Details
checkpoint | Cables terminated at T-Tap correctly
checkpoint | Corridor Light Fit Off & Installed (Back plate facing correct direction)
checkpoint | Service loop neat, taped and no more the 2m long
checkpoint | Addressed (Dip Switches)
checkpoint | Station M-Net runs connected to correct ports (R5)
checklist | First Fix - CLmc
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Corridor Light cut out in correct location as per Shop Drawings / RCP
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - CLmc
section | Details
checkpoint | Cables terminated correctly
checkpoint | Mini Corridor Light Fit off and Installed
checklist | First Fix - EPS
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - EPS
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - NCAP
section | Details
checkpoint | Cable Roughed In through ceiling & coiled at Annunciator location per the RCP/NC Shop Drawing
checkpoint | Cable terminated with RG-6 Compression Crimp
checkpoint | Cable dressed into nominated Comms Rack and Labelled per the NC Shop drawings
checkpoint | Materials align with spec/submitted products
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - NCAP
section | Details
checkpoint | Ceiling Mounted Bracket & Ceiling Rose Installed following correct installation procedure
checkpoint | 24" Annunciator with SMA Kit Installed to Wall/Ceiling Mount Bracket
checkpoint | Coax and Power feed cables connected
checklist | Second Fix - NCC
section | Details
checkpoint | Install patch lead from structured cabling port to NCC
checkpoint | Install NCC to location as per NC Shop Drawing / Elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checklist | First Fix - SSd
section | Details
checkpoint | Install backbox housing at clock location as per elevations.
checkpoint | Cable Rough In - Run patch lead from structured cable port to clock location as per elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - SSd
section | Details
checkpoint | Clock fixed onto correct location per room elevations
checkpoint | Patch lead connected from structured cabling port to clock
checklist | First Fix - SSda
section | Details
checkpoint | Install backbox housing at clock location as per elevations.
checkpoint | Cable Rough In - Run patch lead from structured cable port to clock location as per elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - SSda
section | Details
checkpoint | Clock fixed onto correct location per room elevations
checkpoint | Patch lead connected from structured cabling port to clock
checklist | First Fix - P
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - P
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - WFT
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - WFT
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - DCV
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Corridor Light cut out in correct location as per Shop Drawings / RCP
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - DCV
section | Details
checkpoint | Cables terminated at T-Tap correctly
checkpoint | Corridor Light Fit Off & Installed (Back plate facing correct direction)
checkpoint | Service loop neat, taped and no more the 2m long
checkpoint | Addressed (Dip Switches)
checkpoint | Station M-Net runs connected to correct ports (R5)
checklist | First Fix - MNet
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at MNet location
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checklist | Second Fix - MNet
section | Details
checkpoint | Cables terminated at MNet correctly
checkpoint | MNet device fixed in ceiling space
checklist | First Fix - AE
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - AE
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - PI
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - PI
section | Details
checkpoint | Cables terminated at T-Tap correctly
checklist | First Fix - PI2
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checklist | Second Fix - PI2
section | Details
checkpoint | Cables terminated at T-Tap correctly
checklist | First Fix - ECw
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - ECw
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | First Fix - NCw
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - NCw
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)
checklist | First Fix - SAw
section | Details
checkpoint | Cable Rough In - Ceilings
checkpoint | Cable Rough In - Walls
checkpoint | Cable at Corridor Light/DCV Location
checkpoint | Station Cut out / Flush box in correction location per room elevations
checkpoint | Materials align with spec/submitted products
checkpoint | Minimum of 50 mm separation from parallel power cables and data cables (excludes ELV)
checkpoint | All cables have slack either side of full height walls
checkpoint | All flush boxes in acoustic walls do not degrade acoustic performance either by positioning or acoustic treatment.
checkpoint | Fire rating applied to all flush boxes in FR walls
checklist | Second Fix - SAw
section | Details
checkpoint | Cables terminated correctly
checkpoint | Station Fit off and Installed
checkpoint | Station sealed with silicone (wet locations)
checkpoint | Station Addressed (DIP Switches)