## Table 1
We Build Foundations Pty Ltd PO BOX 3011 Balgownie, New South Wales 2519 P: 0407-421-255 Inspection: Frames and Trusses #3 | [6 empty] | Project: MH-0002 9 Point Street Bulli 9 Point Street Bulli, New South Wales 2516
0/7 Items Inspected |  | 0 Conforming |  | 0 Deficient | 0 N/A |  |  |  | 0 Neutral
Type | Commissioning |  | Status |  |  | Open
Trade | Carpenter |  | Location |  |  | 9 Point Street
Spec Section |  |  | Created By |  |  | Paola Herrero
Linked Drawings
Description Ensure structural integrity, compliance with engineering designs, and adherence to safety standards during the installation process.
Attachments
Inspection Details Inspection Date Due Date Point of Contact Responsible Contractor Assignee(s) Paola Herrero
Frame Erection 0 Neutral 0 Conforming 0 Deficient 0 N/A
1.1 Check that all wall frames are plumb, level, and square. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
1.2 Verify that fasteners are properly placed and secure. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
1.3 Ensure openings for doors and windows are correctly framed. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
Truss Installation 0 Neutral | [5 empty] | 0 Conforming |  | 0 Deficient |  | 0 N/A
2.1 Confirm that trusses are installed according to the design plan. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
Inspection #3 - Frames and Trusses Project: MH-0002 9 Point Street Bulli
Structural Integrity 0 Neutral 0 Conforming 0 Deficient 0 N/A
3.1 Ensure that load-bearing elements are correctly supported. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
3.2 Verify that trusses are not damaged and are aligned correctly. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A
3.3 Confirm that all structural elements meet safety and design standards. Details: ACCEPTANCE CRITERIA: As per Australian standards for Frames and Trusses Carpentry AS 1684 | [5 empty] | Pass |  | Fail |  | N/A