## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
b21ee47c-c85a-4a83-8daf-326932b855da | checklist | External Paving (Pods & Pavers) ITP | itp | External Paving (Pods & Pavers) | d6f8f089-3d99-441d-8f55-c7588c0a67cc
d3284722-d066-4920-a6ed-bdffecefc7bb | section | Details
8716429f-131f-44b9-b784-0cd550379205 | checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
1a570365-585d-504a-aac6-d4e3133ca3e3 | textbox | Drawings in use:
dda01f74-d3d6-49fd-a64b-25aad726c42f | signoff | HOLD POINT
9a9acaf8-d8d6-4aed-977f-28ed2783157f | checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
333a6515-d869-48ec-ac39-8c019147af8a | checkpoint | 3. Install Pedestal System & Lay pavers
fdb976eb-8ba5-4e47-884a-c464751c6b9a | checkpoint | 4. Install Windproof Locking system where required (P8 Pavers)
67225f86-0daf-4146-8430-f3ba5570ee68 | checkpoint | 5. Clean area
54d395f5-6d2f-484f-9bf4-b70dfa254cf4 | checkpoint | 7. Final Inspection and acceptance by MPX
f88682bc-dc67-4980-b217-e5174964ce61 | checkpoint | Wetspot Supervisor signature
| checklist | Internal Tiling checklist |  | Internal Tiling checklist | a6c07f11-a458-4dfc-af56-0ecdb82ffd03
| checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
0c051b15-aa58-5d21-9c47-e5515b0ba8cb | textbox | Drawings in uses:
| signoff | HOLD POINT
| checkpoint | 2. Apply Mudfixing Mortar under Terazzo Tiles
| checkpoint | 3. Apply Approved Tile Adhesive - Ultralite S1
| checkpoint | 4. Lay Floor and Wall Tiles
| checkpoint | 5. Grout - Mapei Keracolor FF
| checkpoint | 6. Apply Anti-Slip Sealer to Terrazzo Floor Tile
| checkpoint | 7. Inspect Waste Blockages - Provide Photo/s
| checkpoint | 8. Clean Area
| checkpoint | 9. Caulking - After builders clean
| checkpoint | Wetspot Supervisor signature
| checklist | Internal Waterproofing checklist |  | Internal Waterproofing checklist | f86f7fde-fc12-40b2-b370-2d6e06c3512e
| checkpoint | 1. Inspect substrate including wall junctions. Do not proceed works if substrate is unsatisfactory. Report any issues to MPX for rectification.
94a68f9d-552a-5e86-bf43-5dbf309aca14 | note | Record Moisture content test and provide photo of gauge. Reading must be 5% or less.
| checkpoint | 2. Preparation
6885b56c-9fca-5d6c-9a34-8069d0cd71c8 | tickbox | Clean substrate with moist sponge to ensure free of debris and dust.
2f374082-8a13-5eb4-ae00-6d7d92a08edc | tickbox | Ensure drain points are protected.
c99366b8-bdbf-5c64-a130-2ac22ede11ae | tickbox | Apply approved primer - Mapei Primer G
| checkpoint | 3. Seal junctions and glue down angles with polyurethane fillet - PascoflexPU25
ba7d5be8-3e7c-5a78-ad65-b7e26091eb28 | note | Minimum 12mm thickness. *Waterstop angles installed to shower entry, bathroom entry, laundry entry *
| checkpoint | 4. 1st layer of Waterproofing: - Apply 2 coats of min 1mm Mapelastic Smart membrane to achieve min 1.6mm DFT including turn-ups to wall - Measure and record DFT. Provide Photo/s of guage
d470a9e2-4d65-5662-aeb3-6f74c17377c5 | note | Allow minimum 5 hour wait time inbetween coat applications. Immerse reinforced bandage into membrane on all wall/wall and floor/wall junctions during 1st coat.
| checkpoint | 5. Conduct Flood Test. *Minimum 2 x showers per level* Provide Photos.
| signoff | MPX Co-Sign
| checkpoint | 6. Apply Screeds.
08438849-c563-5fe7-b520-51daeb7c34fc | note | Standard sand & cement screed up to 60mm.
7d88adb3-5881-5e5f-89e5-fad98d8db05e | note | Create Drainage Falls towards waste as per standards: 1:80 shower bases achieve with screed & Bathroom floors 1:100 achieve with adhesive
| checkpoint | 7. 2nd Layer of Waterproofing (Where Required)
59f4470b-ac12-5bba-a737-f27d6cea4b64 | tickbox | Apply Primer above screeded areas and seal junctions with polyurethane.
30a38db0-9457-5801-b6be-bdce00f437c2 | tickbox | Apply 2 coats of minimum 1.0mm Mapelastic Smart membrane to achieve minimum 1.6mm DFT including turn-ups to wall.
c6dd9458-26f4-59d0-aa35-eeb8af02b6ab | note | Allow minimum 5 hour wait time inbetween coat applications.
| checkpoint | 8. Manufacturers Inspection by Mapei and acceptance
9b9c0db1-0b4d-5469-877a-45c9f39a4cef | note | Inspections of works at to occur throughout multiple stages of the waterproofing system (one inspection per levell for each building). Wetspot to schedule inspections with Mapei - MPX to be notified prior.
| signoff | HOLD POINT
| checkpoint | Wetspot Supervisor signature
6cccd979-c9e4-4957-82d9-fe5cd65c067b | checklist | Village Green Paving ITP | itp | Paving | dd78b4b0-56e7-453f-b166-46be8862885b
0939246a-a040-4cfa-a403-557d0059fb7d | section | Details
b2b5b961-5fa3-4bfc-b181-37abc2d97983 | checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
3659e8d6-82f6-5a29-8348-3f1f99887f9b | textbox | Drawings in use:
09f51d86-07c7-4d30-b78b-a78e1c12e913 | signoff | HOLD POINT
d25a3a1a-d641-4f53-bf19-a2d1b650d88f | checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
dcef2344-3b94-4e30-bddd-f0fa0275d5fa | checkpoint | 3. Set out Pavers
903b7b2d-73ea-40d8-b20f-bc9bcbb5ee93 | checkpoint | 4. Apply Mudfixing Mortar
73aacc8d-cc25-5ebb-8614-7532026b84f8 | note | Maximum 60mm only to courtyards and public realms
7c53c2b8-25cc-57b5-9501-e5b0a7a71295 | note | Maximum 120mm Sand & Cement + Planicrete mudfix mortar in lieu of binding slab
6ef568e1-cfaf-4219-bbab-41ce71edf0e8 | checkpoint | 5. Lay Pavers
9ba581f4-3b22-43df-896e-fc953c3a918e | checkpoint | 6. Apply Grout
7f731c6b-d5dc-4f71-971c-bc0f770d2376 | checkpoint | 7. Inspect Waste Blockages - Provide Photo/s
2858f61d-2aec-4808-a30e-5a67d8f5c5f6 | checkpoint | 8. Clean area
f3e3317d-d8a3-4a45-a877-21c8a660f2f8 | checkpoint | 9. Final Inspection and acceptance by MPX
a2aec003-a6e4-40ba-b650-5d4b84f325f3 | checkpoint | Wetspot Supervisor signature