## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | External Paving (Pods & Pavers) | itp |  |  |  |  | External Paving (Pods & Pavers) ITP
section | Details
checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
textbox | Drawings in use:
holdpoint | HOLD POINT
checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
checkpoint | 3. Install Pedestal System & Lay pavers
checkpoint | 4. Install Windproof Locking system where required (P8 Pavers)
checkpoint | 5. Clean area
checkpoint | 7. Final Inspection and acceptance by MPX
checkpoint | Wetspot Supervisor signature
checklist | Paving | itp |  |  |  |  | Village Green Paving ITP
section | Details
checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
textbox | Drawings in use:
holdpoint | HOLD POINT
checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
checkpoint | 3. Set out Pavers
checkpoint | 4. Apply Mudfixing Mortar
label | Maximum 60mm only to courtyards and public realms
label | Maximum 120mm Sand & Cement + Planicrete mudfix mortar in lieu of binding slab
checkpoint | 5. Lay Pavers
checkpoint | 6. Apply Grout
checkpoint | 7. Inspect Waste Blockages - Provide Photo/s
checkpoint | 8. Clean area
checkpoint | 9. Final Inspection and acceptance by MPX
checkpoint | Wetspot Supervisor signature