## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
b21ee47c-c85a-4a83-8daf-326932b855da | checklist | External Paving (Pods & Pavers) ITP | itp | External Paving (Pods & Pavers) | d6f8f089-3d99-441d-8f55-c7588c0a67cc
d3284722-d066-4920-a6ed-bdffecefc7bb | section | Details
8716429f-131f-44b9-b784-0cd550379205 | checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
1a570365-585d-504a-aac6-d4e3133ca3e3 | textbox | Drawings in use:
dda01f74-d3d6-49fd-a64b-25aad726c42f | signoff | HOLD POINT
9a9acaf8-d8d6-4aed-977f-28ed2783157f | checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
333a6515-d869-48ec-ac39-8c019147af8a | checkpoint | 3. Install Pedestal System & Lay pavers
fdb976eb-8ba5-4e47-884a-c464751c6b9a | checkpoint | 4. Install Windproof Locking system where required (P8 Pavers)
67225f86-0daf-4146-8430-f3ba5570ee68 | checkpoint | 5. Clean area
54d395f5-6d2f-484f-9bf4-b70dfa254cf4 | checkpoint | 7. Final Inspection and acceptance by MPX
f88682bc-dc67-4980-b217-e5174964ce61 | checkpoint | Wetspot Supervisor signature
6cccd979-c9e4-4957-82d9-fe5cd65c067b | checklist | Village Green Paving ITP | itp | Paving | dd78b4b0-56e7-453f-b166-46be8862885b
0939246a-a040-4cfa-a403-557d0059fb7d | section | Details
b2b5b961-5fa3-4bfc-b181-37abc2d97983 | checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
3659e8d6-82f6-5a29-8348-3f1f99887f9b | textbox | Drawings in use:
09f51d86-07c7-4d30-b78b-a78e1c12e913 | signoff | HOLD POINT
d25a3a1a-d641-4f53-bf19-a2d1b650d88f | checkpoint | 2. Inspect substrate surface. Do not proceed works if substrate is unsatisfactory and report any issues to MPX for rectification
dcef2344-3b94-4e30-bddd-f0fa0275d5fa | checkpoint | 3. Set out Pavers
903b7b2d-73ea-40d8-b20f-bc9bcbb5ee93 | checkpoint | 4. Apply Mudfixing Mortar
73aacc8d-cc25-5ebb-8614-7532026b84f8 | note | Maximum 60mm only to courtyards and public realms
7c53c2b8-25cc-57b5-9501-e5b0a7a71295 | note | Maximum 120mm Sand & Cement + Planicrete mudfix mortar in lieu of binding slab
6ef568e1-cfaf-4219-bbab-41ce71edf0e8 | checkpoint | 5. Lay Pavers
9ba581f4-3b22-43df-896e-fc953c3a918e | checkpoint | 6. Apply Grout
7f731c6b-d5dc-4f71-971c-bc0f770d2376 | checkpoint | 7. Inspect Waste Blockages - Provide Photo/s
2858f61d-2aec-4808-a30e-5a67d8f5c5f6 | checkpoint | 8. Clean area
f3e3317d-d8a3-4a45-a877-21c8a660f2f8 | checkpoint | 9. Final Inspection and acceptance by MPX
a2aec003-a6e4-40ba-b650-5d4b84f325f3 | checkpoint | Wetspot Supervisor signature