## Sheet1
2.1 | Material Supply | General Notes on IFC Section 204.4 c), 204.06 e) | Free of topsoil, deleterious CHAR(AMP)/or perishable matter and maximum particle size ≤ 150mm. Swell CHAR(LESS) 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B. | Doc. Review | Prior to Commencement | HP | NATA Test Certificate | 2.1 - Material Supply | Reference - General Notes on IFC Section 204.4 c), 204.06 e) | Acceptance Criteria - Free of topsoil, deleterious CHAR(AMP)/or perishable matter and maximum particle size ≤ 150mm. Swell CHAR(LESS) 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B. | Method - Doc. Review | Frequency - Prior to Commencement | Category - HP | Responsibility - | Verifying Documents - NATA Test Certificate | Date Completed: | 2.1 - Material Supply
3.1 | Survey Set Out | Design Drawings | Set out pegs in place and clearly mark out limits of works. | Visual Inspection | Each lot prior to commencement |  | Signed ITP | 3.1 - Survey Set Out | Reference - Design Drawings | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works. | Method - Visual Inspection | Frequency - Each lot prior to commencement | Category - | Responsibility - | Verifying Documents - Signed ITP | Date Completed: | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
3.2 | Pre-Commencement of Fill Works | Section 204.10 (b) | Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent. | Visual Inspection | Prior to commencement of fill works | HP |  | 3.2 - Pre-Commencement of Fill Works | Reference - Section 204.10 (b) | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent. | Method - Visual Inspection | Frequency - Prior to commencement of fill works | Category - HP | Responsibility - | Verifying Documents - | Date Completed: | Acceptance Criteria - Free of topsoil, deleterious CHAR(AMP)/or perishable matter and maximum particle size ≤ 150mm. Swell CHAR(LESS) 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
4.1 | Placing of Fill | Section 204.10 (d) (iii) | Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent. | Monitor | Each layer |  | Signed ITP | 4.1 - Placing of Fill | Reference - Section 204.10 (d) (iii) | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent. | Method - Monitor | Frequency - Each layer | Category - | Responsibility - | Verifying Documents - Signed ITP | Date Completed: | Method - Doc. Review
4.2 | Keying of Layers | Section 204.10(d)(i) | Each layer of fill shall be keyed into the layer above by creation of a textured surface. | Monitor | Each layer |  | Signed ITP | 4.2 - Keying of Layers | Reference - Section 204.10(d)(i) | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface. | Method - Monitor | Frequency - Each layer | Category - | Responsibility - | Verifying Documents - Signed ITP | Date Completed: | Frequency - Prior to Commencement
4.3 | Test Rolling | Section 204.12, 173.03 | All layers of fill and cut floor level to be test rolled in accordance with section 173. | Measure | Each layer | HP |  | 4.3 - Test Rolling | Reference - Section 204.12, 173.03 | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173. | Method - Measure | Frequency - Each layer | Category - HP | Responsibility - | Verifying Documents - | Date Completed: | Category - HP
4.4 | Post Compaction Testing | Section Table 204.131, 204.13, 204.14 | All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level Scale B: Standard Compaction 98%. Attach: Compaction Test Result: | Doc. Review | Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142: Placed within 400 mm of top of Type B: Test every second lot of like material and work Placed more than 400 mm below top of Type B material: Test every third lot of like material and work |  | NATA Test Certificate | 4.4 - Post Compaction Testing | Reference - Section Table 204.131, 204.13, 204.14 | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level Scale B: Standard Compaction 98%. Attach: Compaction Test Result: | Method - Doc. Review | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142: Placed within 400 mm of top of Type B: Test every second lot of like material and work Placed more than 400 mm below top of Type B material: Test every third lot of like material and work | Category - | Responsibility - | Verifying Documents - NATA Test Certificate | Date Completed: | Responsibility -
4.5 | Preparation of final surface | Section 204.15, 204.03 (g) | The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water). | Measure | Top layer |  | Signed ITP | 4.5 - Preparation of final surface | Reference - Section 204.15, 204.03 (g) | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water). | Method - Measure | Frequency - Top layer | Category - | Responsibility - | Verifying Documents - Signed ITP | Date Completed: | Verifying Documents - NATA Test Certificate
5.1 | Survey Conformance As Built | Section 204.03 (e, g CHAR(AMP) h), 206.16 | Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Scale B: Min. No. of Measurements Per Lot: 40 Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm | Review | Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2) |  | Survey Conformance As Built | 5.1 - Survey Conformance As Built | Reference - Section 204.03 (e, g CHAR(AMP) h), 206.16 | Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Scale B: Min. No. of Measurements Per Lot: 40 Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm | Method - Review | Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2) | Category - | Responsibility - | Verifying Documents - Survey Conformance As Built | Date Completed: | Date Completed:
3.1 - Survey Set Out
Reference - Design Drawings
Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
Method - Visual Inspection
Frequency - Each lot prior to commencement
Category -
Responsibility -
Verifying Documents - Signed ITP
Date Completed:
3.2 - Pre-Commencement of Fill Works
Reference - Section 204.10 (b)
Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
Method - Visual Inspection
Frequency - Prior to commencement of fill works
Category - HP
Responsibility -
Verifying Documents -
Date Completed:
4.1 - Placing of Fill
Reference - Section 204.10 (d) (iii)
Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
Method - Monitor
Frequency - Each layer
Category -
Responsibility -
Verifying Documents - Signed ITP
Date Completed:
4.2 - Keying of Layers
Reference - Section 204.10(d)(i)
Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
Method - Monitor
Frequency - Each layer
Category -
Responsibility -
Verifying Documents - Signed ITP
Date Completed:
4.3 - Test Rolling
Reference - Section 204.12, 173.03
Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
Method - Measure
Frequency - Each layer
Category - HP
Responsibility -
Verifying Documents -
Date Completed:
4.4 - Post Compaction Testing
Reference - Section Table 204.131, 204.13, 204.14
Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level Scale B: Standard Compaction 98%. Attach: Compaction Test Result:
Method - Doc. Review
Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142: Placed within 400 mm of top of Type B: Test every second lot of like material and work Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
Category -
Responsibility -
Verifying Documents - NATA Test Certificate
Date Completed:
4.5 - Preparation of final surface
Reference - Section 204.15, 204.03 (g)
Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
Method - Measure
Frequency - Top layer
Category -
Responsibility -
Verifying Documents - Signed ITP
Date Completed:
5.1 - Survey Conformance As Built
Reference - Section 204.03 (e, g CHAR(AMP) h), 206.16
Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Scale B: Min. No. of Measurements Per Lot: 40 Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
Method - Review
Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
Category -
Responsibility -
Verifying Documents - Survey Conformance As Built
Date Completed: