## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add NCR |  | NCR | c8b0fc28-da86-4a8f-978d-255243762067
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Non-Conformance Report
576af39a-9a77-5595-91d6-357624bf52fa | note | Attach NCR form and any relevant documents, photos, etc.
6d9a7d57-118c-5fa8-9cbd-baf9d0c49a68 | note | Issue to Client for their approval and sign off.
9af7224a-640a-5212-8ae6-c64f3f158603 | textbox | NCR Number:
214c8fa8-67d6-5607-9421-dee99c156fb1 | textbox | Lot Number:
8f7b07b5-a395-5a19-8b75-cd6006bac9b4 | textbox | NCR Description:
30278478-8d46-5a4d-be3e-6ec3207e0015 | textbox | NCR Resolution:
| signoff | NCR SIGN OFF
| checklist | B54 ITP - Piling Operations |  | B54 ITP - Piling Operations | c6fe5a01-dfc1-4a14-9452-80f55a61f0ff
| section | Lot Information
| checkpoint | Lot Information complete
265a442d-306e-4229-924e-f84c1fd1b8d8 | textbox | Lot Opened On
e454546c-9738-4386-b1d1-5db3d43b3603 | textbox | Date of Works
7362bebe-5268-45ff-95ae-640cdc568cd9 | textbox | Lot Type
ce410dfe-1ac0-487e-b4a2-be9a0c5c6c03 | textbox | Start Chainage
42438e2d-11a3-4d7b-b57b-cb9a0a6d39fe | textbox | End Chainage
680836a6-4ddd-4858-86ab-e5cf9c21b4ce | textbox | Offset
dfe13069-eb70-59d7-a8f0-3b46e76490c2 | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
8680fa9d-6094-5aee-a17c-2deaff6df9f8 | note | Document Reference / Applicable Standard - Preliminary Works (Piling) ITP
5c61cc59-d4a9-5898-ad81-4311fe02881b | note | Acceptance Criteria - Sign-off of ITP-B1.P Piling Preliminary Works ITP
db8f0574-e7d4-5169-9bb7-fd64b54295bd | note | Frequency/ Process Held - Once / prior to construction
aaa7d59b-ca78-59d5-8e18-b94a4c46f638 | note | Inspection - ACPL - H
dbf0a080-0c8c-5e26-bdf1-1d8225667b0e | note | Inspection - Client - H
627023c7-d7c4-5052-9f9c-a8a9d92ea55d | note | Verifying Records - Preliminary Works (Piling) ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Check Drawings are IFC and current
57958910-82d9-56a5-8374-742a512564e6 | note | Document Reference / Applicable Standard - A182600-JAC-DD-BR-DRG-1001 - 1013 AS5100
cc901f8e-d4be-5c89-8ca7-96b016187cfe | note | Acceptance Criteria - Drawings IFC, Current and Correct
0509e821-216e-55fe-b854-963365cf05f0 | note | Frequency/ Process Held - Once / prior to work commence
787fcfa4-7a2c-530c-8123-9078db616144 | note | Inspection - ACPL - W
1904187a-7cfc-5ee0-865e-0c2548bd57b4 | note | Inspection - Client - S
51e9a813-a13a-5b8f-8836-8bae971da4e2 | note | Verifying Records - This ITP Drawing register
| checkpoint | 1.3 - Transport of Fabricated Steel Items to Site
b4c0beca-e1e7-552a-94ce-82af8ffa8eab | note | Document Reference / Applicable Standard - B201 Cl 6.11
cb9de414-4a4e-5f59-93cc-87640c3f8219 | note | Acceptance Criteria - As agreed, QA checksheets can be submitted to release transport of casings, with FDRs submitted afterwards. See below table for sign-offs of all casing sections.
fbf99a6b-8de2-5824-a4c0-38419f103a74 | note | Frequency/ Process Held - Per Delivery / 1 day prior to deliver
d114acbb-04c3-56c7-a589-cdea31412462 | note | Inspection - ACPL - W
f54fec73-e9f4-573c-abab-e11fc65c5846 | note | Inspection - Client - W
3a860495-1de0-5088-9d20-765f076dbb81 | note | Verifying Records - QA Checksheet
| checkpoint | 1.4 - Certification of Completion of Fabrication
1720d3b1-25bf-5249-92c2-47bfffacdabe | note | Document Reference / Applicable Standard - B201 Cl 15
e1b2ae7e-c75b-5772-b99a-c72ddb2457a6 | note | Acceptance Criteria - Fabricators Data Report submitted for relevant casings prior to work commencing. Refer to table below for sign-offs of each casing section.
c5ae4ed7-2a96-526a-9d18-4a526891fc02 | note | Frequency/ Process Held - Per Casing / prior to driving
85610d5c-0f09-58a4-b8b5-5f824a3d0b68 | note | Inspection - ACPL - H
64347710-768d-52c1-93d9-89cec2c53359 | note | Inspection - Client - H
9ab2658a-4649-56d9-be37-1b05d2d209e0 | note | Verifying Records - Fabricators Data Report
| signoff | AUTHORITY HOLDPOINT
| section | Lot Verification
| checkpoint | Lot Verification complete
7467f68e-5a9e-5ed6-ab82-e887991682f3 | textbox | Lot Verified By:
b019a0be-65ff-56e4-a516-c6e91624f151 | textbox | Lot Closed Date:
09beea06-1c9d-5cfe-894e-d343386a60bb | button | Submitted to Client | Yes, No, N/A
24834138-48b1-5762-815e-356f28df5957 | button | Reviewed by Client | Yes, No, N/A
a5233666-ac4a-559b-a69a-d1cbef95392a | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | B54 Piling ITP - Piling Operations | itp | B54 Piling ITP - Piling Operations | 270409a1-6e6e-44d6-a2d9-e335ee4a8772
| section | Lot Information
| checkpoint | Lot Information complete
69d5abe6-88c5-4125-8d17-b9163fb27f1d | textbox | Lot Opened On
62be0488-0362-47bb-95ee-b70bbbdf4d02 | textbox | Date of Works
bec81536-be09-4586-888f-3161f27c015c | textbox | Lot Type
dc320d42-2806-41d7-8780-80ea2bb10bde | textbox | Start Chainage
4df4c93a-0181-4f55-b2d2-d25554a14646 | textbox | End Chainage
6cc68ba5-e471-40ab-b2bc-45ee2b28e037 | textbox | Offset
46b1bd62-b4eb-5b4c-8b69-6d8d993544d8 | textbox | Control Line
| section | 1. Construction
| checkpoint | 2.1.1 - Marking of Piles
f0c75fdc-021b-55a9-a983-26bc0331ad88 | note | Document Reference / Applicable Standard - B54 Cl 2.9
a71df1b5-cbb8-5c4a-8b47-13dd58bef722 | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
87eaeff8-27f2-51bd-b1f2-fd21edf8ee56 | note | Frequency/ Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
aba81cc4-b8b4-5720-b06f-119e25cf9f34 | note | Inspection - ACPL - S
9b169bc9-e0d1-542f-b30a-bef2885a892f | note | Inspection - Client - S
a058cb9f-a27e-52e5-a9cf-d06f31c4f3e7 | note | Verifying Records - This ITP Photos
| checkpoint | 2.1.2 - Survey set out
6a0478c8-f8eb-51d0-9b02-aabc65660dcc | note | Document Reference / Applicable Standard - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
dfcc2bb0-89c6-5b81-b3a5-bfeeffb6bc5c | note | Acceptance Criteria - Survey set out as per design drawings
cc18a1da-eeef-5c3d-8847-2e2825b8757f | note | Frequency/ Process Held - Each Pile / prior to driving operations
903133aa-0807-5fa6-a16b-227ef00fecd3 | note | Inspection - ACPL - S
7ab2adb5-93ec-5f83-b61e-418a19efedb4 | note | Inspection - Client - S
d9ccd4ca-da47-52d0-9aa5-e3852400acc0 | note | Verifying Records - Survey Report
| checkpoint | 2.1.3 - Verify Correct Casings prior to Driving
4185a980-1955-5ab3-8907-119fd73bc987 | note | Document Reference / Applicable Standard - IA 82600-JAC-DD-BR-DRG-1012-1013
4e6ee701-96c5-522e-9916-33ec78358ba1 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
8498e6fa-543e-5a61-adc8-97a42ea11ef9 | note | Frequency/ Process Held - Each Casing / prior to lifting of casing
a3a8ae10-6870-54fe-be8f-95b4a4f9bc63 | note | Inspection - ACPL - S
4cf8514b-b5ee-5f87-ae13-6cbc47a0492f | note | Inspection - Client - S
d0838a6e-ce13-5ce9-ab6b-0e950cae489d | note | Verifying Records - This ITP Photos
| checkpoint | 2.1.4 - Pile Driving
e1059204-7e14-5b5e-b843-44719706a884 | note | Document Reference / Applicable Standard - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
a56ef090-f274-54c1-9117-71c14efc32c6 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile.
c4355ced-c252-552a-ad91-e4d6768d902f | note | Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 50) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
d59cb36b-8a33-53d6-81da-1f9179744827 | note | Frequency/ Process Held - Driving of each pile / one day prior to driving each pile
80236e39-7bfe-57cb-a21b-7fb95de61d1f | note | Inspection - ACPL - W
16a0243a-ef00-5ca5-bca0-7b041cfd0ef7 | note | Inspection - Client - W
98836d2d-f3da-5f0e-b10d-19c56e0cadb8 | note | Verifying Records - Driving Record Sheet
| checkpoint | 2.1.5 - Splicing of Piles
b43609bb-a049-5a38-9f58-53a921dc2756 | note | Document Reference / Applicable Standard - B54 Cl 2.6 B201 Cl 13.2
21055410-67a3-5d6d-940d-4d1b7db30f2a | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
91d33e74-c6a7-587e-909d-b49711866922 | note | Frequency/ Process Held - Each length of Pile for each Pile / prior to driving Following section
b208771f-7739-50a0-aadc-939e4db7e5cc | note | Inspection - ACPL - S
285fe7cc-9b89-5f6a-b945-16dec7b33609 | note | Inspection - Client - S
a642301c-59a8-51bd-996d-4526a8c30647 | note | Verifying Records - Weld Test Results
| checkpoint | 2.1.6 - Backfilling of Pile shaft
b818f063-8473-548b-b4aa-0ddc5fd6fa25 | note | Document Reference / Applicable Standard - B54 Cl 11.1
40b0c05b-0d14-5e73-bee6-828e29e21573 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole.
02550b13-9f2a-572c-8eb0-1d02fe7f4ec7 | note | If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
f609f3f2-a9d2-568e-9c43-a35a46fe83d7 | note | Frequency/ Process Held - Each Pile / prior to placement of concrete plug
6f13e53b-4ee4-5fe8-b4ce-69b0ccea99f6 | note | Inspection - ACPL - H
eea96059-22c0-59b1-8e3a-d7d0d3ade60c | note | Inspection - Client - H
2d4f54a2-675a-594c-8737-6eba119914e5 | note | Verifying Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.7 - Placement of Mass Concrete Plug
4ee845ea-1f8b-5955-b264-0117f955a443 | note | Document Reference / Applicable Standard - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
8be085a7-b6b5-5519-93d8-446536787345 | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
d273422a-45bd-52f9-be45-5d88eb0c5fa4 | note | Frequency/ Process Held - Each Pile / prior to lifting of reinforcement cages
6139860d-1ad0-5b8b-a556-fb7336085727 | note | Inspection - ACPL - S
22a2ff66-1feb-5d8e-a915-0e09e1e88064 | note | Inspection - Client - S
dbbcc9e0-6bdc-5989-b286-55d08e09fc8c | note | Verifying Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.1.8 - Assembly, lifting and transport of reinforcement cages
b94357a4-209b-5825-87db-833a4ed20a56 | note | Document Reference / Applicable Standard - B201 Cl 6.6.2
d4375eee-0de3-5fca-8f3e-58bd6991675f | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
72a8218e-de16-5a7f-a766-3780d75e9d51 | note | Frequency/ Process Held - Once / At least 2 working days prior to transport to site
6a11aecf-6542-5120-8146-67fbff53f314 | note | Inspection - ACPL - W
9c443731-1c61-5816-aad6-b4fbb6ccfd8c | note | Inspection - Client - W
6fb4a4aa-c92b-5422-a1a1-712eaa5eb7e2 | note | Verifying Records - Certificate of Conformity
| checkpoint | 2.1.9 - Placement of reinforcement
c09905c7-b006-5bd7-aa7c-2c8897a2f689 | note | Document Reference / Applicable Standard - B54 Cl 11.2
7b80501d-8b0d-52d7-9382-310216610295 | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material
82648b5a-efcf-53ec-ab90-1078a60fa7e3 | note | Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement.
522f16cb-338a-58fb-b699-2121968fe15d | note | Cover to reinforcement nearest to the concrete surface to be 50mm
e469b199-e480-5aa8-8299-65d6d3cc9ed4 | note | Reinforcing bars to be grade D500N
7a144878-821a-528e-a969-078925cb049d | note | Clear distance between lapped bars must not exceed 3x bar diameter
44fa9e2d-f1dc-5f96-aaf2-367eb0eeab3b | note | Frequency/ Process Held - Each Pile / prior to concrete placement
113db3d7-d4ed-5af4-9c74-bd2dbe225cb5 | note | Inspection - ACPL - S
efc9f1fd-10f3-523d-a56b-c525218d2d9e | note | Inspection - Client - S
d0e5630c-13e0-5f09-87a6-7fbf777b2f85 | note | Verifying Records - This ITP
| checkpoint | 2.1.11 - Certification Prior to Concreting
4b64c16a-1163-508a-a3b4-984d9b16eecc | note | Document Reference / Applicable Standard - B80 Cl 7.5.1
495a422d-fffe-5cd0-ac12-153412c3f1b3 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby.
8cb44d5b-ed07-5ed9-8a53-fe7c28864626 | note | At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
8bea802e-f93b-5031-8e4d-d8ef0d351c29 | note | Frequency/ Process Held - Once / 2 days prior to each concrete placement
ea0d083d-abae-53d4-8033-7220f70333c8 | note | Inspection - ACPL - H
0abf1ce0-868c-5dc1-bda1-7c55ad12f5f0 | note | Inspection - Client - H
07722804-79a0-5f62-a7d0-d748177881a4 | note | Verifying Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.10 - Concrete Sampling
873b0de8-98c7-5243-8a7d-97e4113674e8 | note | Document Reference / Applicable Standard - B80 Annexure B80/L
a2ca53ce-0c4f-57ce-9472-fb2303bb5c73 | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
712f7ef0-95b0-5827-9e05-2bfa62e4a05d | note | - Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
e5559baa-f396-58c2-9880-a054866e87c6 | note | - 1no. slump test per batch of concrete 550+/- 50mm
7ac7877e-46ef-5b59-bae8-ebe84876369e | note | Frequency/ Process Held - Each Pile / prior to concrete placement
57d80e34-1a87-5c8e-b21e-1cbd1dcd86cb | note | Inspection - ACPL - S
552f0ec7-31fb-535c-ac0a-39a9efd71652 | note | Inspection - Client - S
1235361f-da37-5001-b9c8-31c706b0e96c | note | Verifying Records - Test Results
| checkpoint | 2.1.12 - Concrete placement
ad6079f0-b859-5aa3-b4b7-26821126e0db | note | Document Reference / Applicable Standard - B80 Cl 7
f55dfc4c-2f7c-5f69-a474-d86c06730614 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C
5dad4b7c-c7d6-5d7f-a352-f54b6ac4d3b3 | note | Ambient temperature must be 5-35C
8a4f0506-ada6-5575-b617-c1df33e01deb | note | 40MPa Concrete
03d82a6a-5bf3-5cfe-ae09-38fa6005382b | note | Concrete placed in piles to be carried out in one continuous operation.
0a88480d-f630-5f28-b99e-ba8232dde4e0 | note | Frequency/ Process Held - Once / prior to cutting of concrete casing
c77dca1b-532e-5a2b-bf73-3542b8993731 | note | Inspection - ACPL - S
fa61f183-cb0f-5c80-b973-450e14851195 | note | Inspection - Client - S
786e16c4-cfcd-5e6c-bc0f-a591e4f75e00 | note | Verifying Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.1.13 - Cutting of casings
213667ec-ee4a-5c0b-a351-b7c346fc5dc2 | note | Document Reference / Applicable Standard - B54 Cl 12
1068bc32-c549-59cd-a6a2-d56e6469194b | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
a9f7f1e6-4ce4-5981-88a9-e3a41f248880 | note | Frequency/ Process Held - Each Pile / No less than 24hrs after concrete pour
dda42532-5879-5ef2-afe6-d7c2331a0a2b | note | Inspection - ACPL - S
97aff98d-135b-5584-bd18-81af78f53750 | note | Inspection - Client - S
3b0b283e-bbdd-5988-ba2a-847618cc61cf | note | Verifying Records - Photos
| checkpoint | 2.1.14 - Concrete curing/Sign off
3644d2d7-b29c-5c5e-83aa-680c2edff081 | note | Document Reference / Applicable Standard - B80 Cl 8
02844a47-91ce-5314-b9f8-f6f66918a51a | note | Acceptance Criteria - Min 40mPa at 28 days
9fc614d9-f80c-5661-9135-7b8b54aa2127 | note | Frequency/ Process Held - Once / Pile Cap FRP
135cb371-1f0f-5f55-8490-d22643991f21 | note | Inspection - ACPL - H
8d5661f9-b41f-5e7e-887d-32eec5da979f | note | Inspection - Client - H
fbf79169-7b6d-59b3-93ad-f7ee5b9e0708 | note | Verifying Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section-nested-checklists | NCR
| checklist | B54 Piling ITP (Representative) - Piling Operations | itp | B54 Piling ITP (Representative) - Piling Operations | 44a7f7dc-0944-4277-bfba-85cf5b5308a9
| section | Lot Information
| checkpoint | Lot Information complete
ecf89b9c-01c0-4960-9970-73371c6a385f | textbox | Lot Opened On
1eec4747-d8dc-4f3f-b4b9-b6c6dfbe7956 | textbox | Date of Works
3e31378a-5bad-414f-b250-bf865c5da29e | textbox | Lot Type
1a351ef7-4262-45e5-a0d2-a182162fa074 | textbox | Start Chainage
9479f3bc-58f4-4c42-89e8-20e53fff0df4 | textbox | End Chainage
9b30d084-25fa-4939-8b3d-33b82914edf7 | textbox | Offset
a0c6cc92-bcd0-525e-8d53-4814bfcc595e | textbox | Control Line
| section | Representative Pile
| checkpoint | 2.2.1 - Marking of Piles
69cf8f5a-ccce-5f4b-a4b8-449c17d4c4e2 | note | Document Reference / Applicable Standard - B54 Cl 2.9
dedf4cea-a120-5384-a0cd-443537efeca0 | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
11ba8da4-1e04-50ad-a538-ecc33c14adf7 | note | Frequency/ Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
8b5a4718-ac06-5106-b90f-04b1898f5eee | note | Inspection - ACPL - S
3895bb1a-d6cf-5c6e-9d0a-118ecb9b38df | note | Inspection - Client - S
fe16a263-c3ab-5160-b496-22cb4d01529e | note | Verifying Records - This ITP
| checkpoint | 2.2.2 - Survey set out
d6b5d2e8-d240-5954-8a0e-3a2e4e6b68cd | note | Document Reference / Applicable Standard - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
cd840aaa-e6c4-5a5e-ba21-739d6e8a792f | note | Acceptance Criteria - Survey set out as per design drawings
26aae5ba-d080-5507-96c2-4e314884952c | note | Frequency/ Process Held - Each Pile / prior to driving operations
bd6b4119-c2c6-5c59-b6da-ed79224c1f66 | note | Inspection - ACPL - S
008f31e3-5ed2-5fb4-ab3e-262fcf64f0e5 | note | Inspection - Client - S
e1bfb212-ab04-59cd-add7-157dcf9f2656 | note | Verifying Records - Survey Report
| checkpoint | 2.2.3 - Verify Correct Casings prior to Driving
2c76e18a-6791-5978-b205-3c6b740e30f4 | note | Document Reference / Applicable Standard - IA 82600-JAC-DD-BR-DRG-1012-1013
c11dff9e-43d4-58aa-9dbd-30b1d165c279 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
47e9d201-3c27-5391-ad29-ed9fa8f5bd7b | note | Frequency/ Process Held - Each Casing / prior to lifting of casing
96b0015d-4131-54c1-b08f-407ae0ac8fd4 | note | Inspection - ACPL - S
873b8e61-22a3-500b-a323-7c58375057a3 | note | Inspection - Client - S
0851aff8-d99c-56e2-bc05-640569cb0a0c | note | Verifying Records - This ITP
| checkpoint | 2.2.4 - Driving of Representative Pile
2133359b-e488-503a-9bd2-603d2341cc25 | note | Document Reference / Applicable Standard - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 8
46f4e5c7-c920-5182-92f0-a04b6d6f7a24 | note | Acceptance Criteria - Notification of the time and location of the driving of each representative Pile.
dc13b5a9-4598-5b07-856e-5808ba149132 | note | Representative pile driven to nominal refusal in rock
421c216a-8a69-5557-b1cb-9110e326df6b | note | Record number of blows per meter over the whole driven length. For the last 10 blows, record the final set in mm and the average Temporary Compression per blow.
c7aaa057-7d4a-5bd4-ab88-e8a5b37ead96 | note | Perform Dynamic Testing over whole length of driven length of Pile
17c67f89-be8e-553d-ac76-1547e0cdd8ae | note | Frequency/ Process Held - Each representative pile / prior to restrike
35eff4e6-1c99-541c-a302-d71cd33066a5 | note | Inspection - ACPL - H
541c275d-a223-599a-8815-4b207078bb56 | note | Inspection - Client - H
53f1f0bb-4268-5e26-9a89-a57c80bd9c75 | note | Verifying Records - Prior Notification of Driving Driving record Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.5 - Restrike
49f97180-a007-550d-a3e3-7edf14dce6c0 | note | Document Reference / Applicable Standard - B54 Cl 13.3
6c5f8623-8b30-5be8-aca7-ffa54876f893 | note | Acceptance Criteria - Restrike required on all test and representative piles. If restrike fails, perform additional restrike no sooner than 7 days after completion of piling and prior to any concrete infill
c9ebf0d1-393a-5fdb-9e6e-6475cec005e2 | note | Frequency/ Process Held - Each representative pile after 24 hours / prior to splicing of piles
9f11e7b6-415a-5ef1-8deb-46b25fda5d8e | note | Inspection - ACPL - S
e14c8e56-7d85-5c50-8e37-609eb17ccca3 | note | Inspection - Client - S
b4050b28-4e71-54bc-bf58-793a931abdc2 | note | Verifying Records - Driving record sheet
| checkpoint | 2.2.6 - Splicing of Piles
61a75e96-3172-557a-ab11-97dac774905c | note | Document Reference / Applicable Standard - B54 Cl 2.6
9e82d1d0-4d86-5b65-9bd5-877aa8209caa | note | Acceptance Criteria - Where pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
6dd9e7b9-9ca6-5dbf-ad97-d153fb2c728e | note | Frequency/ Process Held - Each length of Pile for each Pile / prior to driving Following section
e66465dd-c76a-5a98-a237-e9752ad71989 | note | Inspection - ACPL - S
60814cc3-68e3-5f35-ad49-d19b0780a46c | note | Inspection - Client - S
3260f5e9-ecb8-51d4-891a-7f04b735c94d | note | Verifying Records - Driving record sheet
| checkpoint | 2.2.7 - Backfilling of Pile shaft
5cb093df-bc49-568b-94ae-606abb34ab40 | note | Document Reference / Applicable Standard - B54 Cl 11.1
60551782-b675-5137-a0ed-5257ae483708 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole.
35405b9d-60c5-5459-b8cd-2a259b233dde | note | If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
7d420e57-a9eb-5341-98ee-80d59fe58672 | note | Frequency/ Process Held - Each Pile / prior to placement of concrete plug
09de57c9-5007-51aa-a988-6280ac759e1c | note | Inspection - ACPL - H
4420deb7-8f57-53f4-9b16-8f466ccf67d6 | note | Inspection - Client - H
da9ebb47-355a-5fdf-a799-21100d51d792 | note | Verifying Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.8 - Placement of Mass Concrete Plug
3330fa11-37aa-54e7-9e33-a9b26fe4a074 | note | Document Reference / Applicable Standard - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
bd05ad1e-dbcd-5c6f-84dc-1377afdd5f2f | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
c44e8007-2965-5e32-94b9-de5468135f51 | note | Frequency/ Process Held - Each Pile / Prior to lifting of reinforcement cages
6fa4203d-0a33-532b-a900-b013ca545bd0 | note | Inspection - ACPL - S
fa34404a-0a1f-53ae-b538-721a0b5c9b80 | note | Inspection - Client - S
c82b85e2-2466-5bb9-8e7c-46165c0fe7e6 | note | Verifying Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.2.9 - Assembly, lifting and transport of reinforcement cages
05b0767a-acd0-5e76-81c6-2f5975111feb | note | Document Reference / Applicable Standard - B201 Cl 6.6.2
807d2e1d-d2ad-59de-9dca-bddae100b712 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
5a4ab341-3b78-5bf1-97c0-180c41f36506 | note | Frequency/ Process Held - Once / At least 2 working days prior to transport to site
b505c85c-0b52-5c0d-bf41-bbbffba84569 | note | Inspection - ACPL - W
419713c7-8e49-5184-9544-869090bfbcac | note | Inspection - Client - W
cab71bdb-5117-5851-9d97-b19a563186f4 | note | Verifying Records - Certificate of Conformity
| checkpoint | 2.2.10 - Placement of reinforcement
c039d34a-faf8-5bed-aa82-e48787efaf8d | note | Document Reference / Applicable Standard - B54 Cl 11.2
93ea3ce9-4a70-51ef-913a-847389b78496 | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material
e0d436ad-f2e2-5fc2-8192-d19bd486d302 | note | Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement.
28c7909d-76ae-5bfe-b2bc-168545e138e4 | note | Cover to reinforcement nearest to the concrete surface to be 50mm
91a7e803-94d6-52a4-ab9b-41b9fa3e0767 | note | Reinforcing bars to be grade D500N
e9026ca0-d9b8-5c0e-bf93-d56f36ca9324 | note | Clear distance between lapped bars must not exceed 3x bar diameter
2e0858e9-4688-53e4-8908-6f0902ac4680 | note | Frequency/ Process Held - Each Pile / prior to concrete placement
e9cde95a-b815-5aca-8624-506fe08d7518 | note | Inspection - ACPL - S
305550fe-b0ce-580e-bc51-6f877c5a291c | note | Inspection - Client - S
7ea85991-5507-504c-86b1-25fcf307e57d | note | Verifying Records - This ITP
| checkpoint | 2.2.11 - Certification Prior to Concreting
e4b76c74-b73e-5be3-b873-b07b5e31dabc | note | Document Reference / Applicable Standard - B80 Cl 7.5.1
a3421515-0ba5-5314-ac28-944a9a676015 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
ee9083f3-3b45-5e28-9aa5-bd9fdef965cc | note | Frequency/ Process Held - Once / 2 days prior to each concrete placement
eedf9bdf-6747-58ee-bfd7-782bb63d3381 | note | Inspection - ACPL - H
d815de63-b903-5e3a-bdeb-8cad762236e8 | note | Inspection - Client - H
bf127e3b-6a20-58c3-b1b3-f0d0835cc823 | note | Verifying Records - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.12 - Concrete Sampling
f5303208-17d2-562e-a757-db047612e815 | note | Document Reference / Applicable Standard - B80 Annexure B80/L
165ca2ee-b86a-5fd7-876d-b90bd584ef66 | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
58d07d16-faec-502b-9f5e-4d9c80ba5cbc | note | - Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if >25m3)
adbf875e-169c-5396-81dc-9f7905ad31c7 | note | - 1no. slump test per batch of concrete
9c34ecbe-2c64-5e1d-8aee-0d7e8b709bb8 | note | Frequency/ Process Held - Each Pile / prior to concrete placement
56c8af0f-4877-5e82-b0cf-487f83ecd8c2 | note | Inspection - ACPL - S
e407e64a-2947-5168-8942-894602b1d85e | note | Inspection - Client - S
5819f0d9-b559-59b0-b19d-d91d3d5df317 | note | Verifying Records - Test Results
| checkpoint | 2.2.13 - Concrete placement
dcff2b05-e730-5ed2-aa57-c5cf91f820fd | note | Document Reference / Applicable Standard - B80 Cl 7
fde7b50a-e35e-5254-93f1-ff3af99aa4d6 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C
cacd048e-5fbe-50f9-b5ee-36068b0df6ad | note | Ambient temperature must be 5-35C
4feafed9-e254-52cc-adef-a477aa661523 | note | 40MPa Concrete
1cc53b76-6aac-58bd-90fd-2943b174bed1 | note | Concrete placed in piles to be carried out in one continuous operation.
352ddd7e-bb85-5585-b14f-5bd9eca37a44 | note | Frequency/ Process Held - Once / prior to cutting of concrete casing
459241f4-9998-5d29-9040-70419d155bac | note | Inspection - ACPL - S
d7b20180-109c-55b9-bf06-098592cb1d9e | note | Inspection - Client - S
4cf928ca-d202-5a24-a997-7927e52c07f4 | note | Verifying Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.2.14 - Cutting of casings
208fd2f2-b8ef-5ec2-bde7-df4ceaccd46a | note | Document Reference / Applicable Standard - B54 Cl 12
ab70f0ed-bba0-5603-bac4-5973764625bf | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
d8696d82-a4e5-5306-8842-a697db7ab849 | note | Frequency/ Process Held - Each Pile / No less than 24hrs after concrete pour
18a63345-a5d5-55b7-9a05-fc2b7590957d | note | Inspection - ACPL - S
ca5181df-0ddb-5403-989f-f471a6590207 | note | Inspection - Client - S
| checkpoint | 2.2.15 - Concrete curing
37abeefe-136a-5571-bc84-58e4096ff902 | note | Document Reference / Applicable Standard - B80 Cl 8
cfd789ec-6bc9-5c97-b5d5-80af57ff6d70 | note | Acceptance Criteria - Min 40mPa at 28 days
8f70b951-06e0-55ae-bc1e-a25eabc94707 | note | Frequency/ Process Held - Once / Pile Cap FRP
0ce4dd9f-d027-5434-a5b4-4258cb9301e0 | note | Inspection - ACPL - H
04d9e25d-d71c-50a2-8a14-ce72ed544168 | note | Inspection - Client - H
4399588b-fd59-5b95-90a6-5ff387ec5ceb | note | Verifying Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | Lot Verification
| checkpoint | Lot Verification complete
0406028f-ee7a-5d78-9764-47676dc24bc5 | textbox | Lot Verified By:
117dfed2-7735-5a4d-a1e2-2b536e8d4ca0 | textbox | Lot Closed Date:
c9914303-8a01-5ff2-8dca-46586a3091fd | button | Submitted to Client | Yes, No, N/A
f64e6705-b45a-54d0-be64-b83b46106572 | button | Reviewed by Client | Yes, No, N/A
a4fcaa87-c573-5cee-92e4-3d051355d207 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 01 - G40 Clearing and Grubbing (G40) Rev 1 |  | ITC 01 - G40 Clearing and Grubbing (G40) Rev 1 | d4a538b3-8ff3-49f0-a12d-d2e9d8529619
| section | Lot Information
| checkpoint | Lot Information complete
a250b684-6c90-5c6c-9a95-5bfa4cfad659 | textbox | Lot Opened On
30c78ff4-9dba-57c3-b596-1720bf3c2b46 | textbox | Date of Works
0b440902-9d66-5d06-a7ca-cfd25fbd45d4 | textbox | Lot Type
31c030ad-0a9a-5d5e-8251-1e403ee30916 | textbox | Start Chainage
997d64a8-c496-5e6a-8b2c-4c66384e3016 | textbox | End Chainage
7b69230b-5c30-53ed-8887-a4e2ded56b50 | textbox | Offset
22074aa9-780b-58aa-bddc-b2a791a02b6c | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
845e01d6-d582-50a8-b13b-fba68bb28c8c | note | REQUIREMENTS / REFERENCE - Project Safety Plan
fad15500-f847-5fde-9de4-9727e235b3d5 | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural)
bcfa5377-3066-5bba-92be-b6d6ee03f749 | note | Required Safe Work Method Statements completed and signed
f2b202cc-d2fb-5524-a26b-4e2db5f050c5 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
c97daabf-4ba3-5b28-bd78-4cedf8846438 | note | REQUIREMENTS / REFERENCE - Project Environment Plan G36 CL 3.1 G38, G40
7c987c84-fc1a-560f-be0d-0233cafb8ef2 | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
a7484d08-b912-5ddb-b10a-bed4467d9a83 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Services
| checkpoint | VERIFICATION
8faaec68-9a98-5736-9c4d-38ef4945f2a1 | note | REQUIREMENTS / REFERENCE - DBYD drawings
3cb9beb3-e470-5080-9465-c4d6bfcc4051 | note | ACCEPTANCE CRITERIA - Existing services to be located and relocated or protected prior to Clearing and Grubbing works commencing, where practical to do so
| section | 4 - Clearing Approval
| checkpoint | HOLD POINT
9e028853-9808-5c1b-b9ab-1f09029b1bed | note | REQUIREMENTS / REFERENCE - G40 CL2.4.1
3a9689be-2d21-53ee-95e4-3a15847b0bc6 | note | ACCEPTANCE CRITERIA - Prior to undertaking any clearing, prepare a site-specific Clearing and Grubbing Environmental Work Statement to cover the environmental management of works under this Specification (see Annexure G40/D and TfNSW G36 Clause 3.2.4). Include in the Clearing and Grubbing EWMS all the controls required by the Flora and Fauna Management Sub-Plan, Heritage Management Sub-Plans, Noise and Vibration Management Sub-Plans and the Soil and Water Management Plan for the Works. Outline in the EWMS how clearing limits will be progressively maintained and how to ensure that no person, plant, equipment or material goes beyond these limits.
5709fa21-ce53-5157-8cbf-389e23f7e7b8 | note | Also provide a report, prepared in consultation with the Ecologist, and to be incorporated into the CEMP, which covers the requirements of Clauses 2.4.1 (a) to (c).
0c591c55-2dea-5709-9345-b3ba1e2bca25 | note | Prepare a pre-clearing survey procedure and have the Ecologist undertake a pre-clearing survey to identify and mark any habitat trees within the clearing footprint and advise on the presence of any fauna
93d3b5c5-4013-5c11-a559-f12c6d7a98db | note | HOLD POINT – At least seven days prior to starting any clearing, submit Clearing and Grubbing Plan, Environmental Work Method Statement (Annexure G40/D) and report on all locations of environmentally sensitive areas, measures to reduce clearing in environmentally sensitive areas, the presence of weeds and unsound trees, together with written notice that limits of clearing and areas of weed infestation identified in the ecologist report (Clause 2.4(a)) are marked. The Principal will consider the documents and will inspect trees or built structures marked for preservation, including the set out clearing limits, prior to releasing the Hold Point.
3bc5a163-ccd0-5bce-b9e6-3f9e454f3a57 | textbox | HOLD POINT NUMBER:
03de8eb8-beed-5b60-9f60-4184185acb54 | textbox | DATE SUBMITTED:
5c1bdacc-0d39-5787-9b0a-d29dd3b91ec9 | textbox | Work Start Date:
39f584d1-7d88-5952-91b6-563a8bfec0a3 | textbox | SUBMITTED BY:
a699d4a3-bf4f-5666-94f3-a76902be345c | textbox | SPECIFICATION AND CLAUSE:
99f2205a-0e26-529f-af04-84bfa76464e2 | textbox | HOLD POINT DESCRIPTION:
a343289e-f07e-5fcc-bf4d-546abbc4eb36 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Progress Reports
| checkpoint | VERIFICATION
25808153-5470-5516-b6a4-7aab857cd15c | note | REQUIREMENTS / REFERENCE - G40 CL 2.6
70e2f30b-1b93-554f-b103-572ee13c5731 | note | ACCEPTANCE CRITERIA - Provide to the Principal progressive Clearing Reports providing a summary of the results of surveys, fauna rescues, fauna injury and mortality, at weekly intervals during clearing activities. Include details as per G40 Cl 2.6
4b1afb14-911a-53c8-9e42-d4e598242bd4 | note | Provide the Principal with a Post-Completion Clearing Report within 21 days from the completion of substantial clearing (as determined by the Principal) providing a final summary of the progressive Clearing Reports
76d89319-7168-5091-a9a3-70ba49d4b453 | note | Progressive Clearing Reports
9ba937e1-bd0a-5848-b475-e2b8d0405517 | note | Post-Completion Clearing Report
cd2b7b9b-7f5e-5b6f-a299-839de7617f3d | note | Comments / Attachments / Records - Progressive Clearing Reports
b94d28a3-1d57-5da5-b3eb-204265446664 | note | Post-Completion Clearing Report
| section | 6 - Weed Management and Implementation
| checkpoint | HOLD POINT
c6266ca3-605c-51f2-b80b-a3ec21a4f18d | note | REQUIREMENTS / REFERENCE - G40 CL 6
392dd1c2-3397-5346-ad5b-699614f9f909 | note | ACCEPTANCE CRITERIA - HOLD POINT – At least seven days before starting any clearing, submit to the Principal the Weed and Pathogen Management Sub-Plan together with written notice that areas of weed infestation identified in the Ecologist / Dubbo Regional Council Weeds Inspector’s report (Clause 2.4.1) are marked. The Principal will review the documents and inspect marked weed infestation areas prior to releasing the Hold Point
ba06d4a5-a2df-59ae-b480-e67ef4515ce4 | textbox | HOLD POINT NUMBER:
4d826675-aef5-5420-bec9-641e86aaf6f4 | textbox | DATE SUBMITTED:
3fc6fdd9-fd6c-5df4-876b-b7193c821ee4 | textbox | Work Start Date:
9d989655-def6-5dd4-81c0-c5fc34c90695 | textbox | SUBMITTED BY:
d0254e31-4d23-5887-b3da-71b0900f233b | textbox | SPECIFICATION AND CLAUSE:
56007a72-6fb8-5c51-acc9-7e4bf8b78b06 | textbox | HOLD POINT DESCRIPTION:
4c308c32-5329-5a55-ac1c-a31bd5627301 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Post clearing Inspection and Rehabilitation
| checkpoint | VERIFICATION
3c594593-ff14-54f3-ad56-dc3df1579b8c | note | REQUIREMENTS / REFERENCE - G40 Cl 7
95b93e36-19e8-56f7-bf2e-53a28cd40469 | note | ACCEPTANCE CRITERIA - ACPL to walk site after clearing has been completed to identify any further trees / stumps that require removal
d3807673-9383-5be0-8a9a-7d6424acf503 | note | After the completion of any clearing and/or grubbing ensure that any native vegetation required to be re-established is done in accordance with the TfNSW Biodiversity Guidelines, Guide 3: Re-establishment of native vegetation. Also refer TfNSW R178
| section | Identified Records
| checkpoint | Please upload any Identified Records here
| section | Lot Verification
| checkpoint | Lot Verification complete
e385ba18-e7fa-5cbc-84ef-3c08e9f9dd26 | textbox | Lot Verified By:
b3c727c2-cee8-593a-9e2b-b32260ef2c0b | textbox | Lot Closed Date:
c9f513d2-8d0d-562b-a1e8-c10b3454398a | button | Submitted to Client | Yes, No, N/A
a865e030-c5a8-5ca2-b9ba-ab8bb5121904 | button | Reviewed by Client | Yes, No, N/A
744b689c-0210-5e2f-9ed1-3be133850b5c | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 02 - R11 Stormwater and Drain Installation (R11) Rev 1 |  | ITC 02 - R11 Stormwater and Drain Installation (R11) Rev 1 | b8871dd2-9368-426c-9d50-217ddb77e226
| section | Lot Information
| checkpoint | Lot Information complete
fff8c3f9-2fd0-5f27-9677-bfd4803c32c1 | textbox | Lot Opened On
dce60d5a-7cd6-5528-8302-e9b166e43703 | textbox | Date of Works
864d2df6-7332-591e-847c-c0c93ecd1f91 | textbox | Lot Type
826a26a6-c781-5465-ba3e-234ed32b25bc | textbox | Start Chainage
6d0bf65b-b4f1-5d5d-835f-c22dd88bd16d | textbox | End Chainage
8478727d-7b2c-555e-a1f8-1ebf240b2b9f | textbox | Offset
7b81df77-5978-5926-b17a-9b05c1ebaf92 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
3c46ee8a-152f-5372-9699-2cca6165e7bb | note | REQUIREMENTS / REFERENCE - Project Safety Plan
c3e85edc-d0e6-591b-80fd-8dcc96335519 | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural)
63002b4f-1563-513c-834b-e5fd458cb028 | note | Required Safe Work Method Statements completed and signed
a245ef69-9ee5-5185-9b27-bdddbe4d6a3e | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
00a06390-845f-5f3d-b7cb-ce52b981f017 | note | REQUIREMENTS / REFERENCE - Project Environment Plan
5153b7a9-99c8-5298-a306-19c59257fc2e | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs / G38. | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs / G38.
d9044f11-ab8f-56cd-b75b-718385192344 | note | Air quality to be visually monitored for dust etc. as a direct result of construction activities.
| section | 3 - Supply of Precast Concrete Members subject to traffic and/or Earth Pressure
| checkpoint | HOLD POINT
14be60d2-065c-592c-9316-726ebf874aba | note | REQUIREMENTS / REFERENCE - R11 Cl 2.4.1
c65b0dff-423b-5a06-b05f-822c61e610c7 | note | ACCEPTANCE CRITERIA - Submit to the Principal:
05200fbf-2095-5ced-bacd-b62d1efbbda8 | note | Product Drawings Including
3c80120a-0ca7-5618-8fd1-c91ddc7cb3ea | note | Full product dimensions
c480b776-a5c0-56d9-b786-4bc6d680b8ad | note | Reinforcement details
5d7cab95-f5e4-5ced-9827-52cf7782d28a | note | Cover (if reinforced concrete)
48d96a7b-8852-566d-85dc-d8d5cd730338 | note | Design lifting points
eadeb0e3-6c76-51f4-91a6-ee426bda0d52 | note | Recommendations for attachment to adjoining structure(s) (if applicable)
76b78957-672c-5f64-b7fb-6f3e30ad211b | note | Certification by Structural Engineer.
90318c7a-0d30-5669-9fea-935b9a0aa0c9 | note | Details of methods of manufacture, testing & installation etc.
e2520ef7-853a-595c-9ada-ec8dcbcc6916 | note | HOLD POINT: Submission of all quality documents specified in clause R11 2.4.1 at least 7 days prior to date of delivery, for precast concrete members subject to traffic and / or earth pressure loading, and water retaining structures with capacity greater than 25 000 litres | HOLD POINT: Submission of all quality documents specified in clause R11 2.4.1 at least 7 days prior to date of delivery, for precast concrete members subject to traffic and / or earth pressure loading, and water retaining structures with capacity greater than 25 000 litres
76ec9cf2-fe35-54e4-a16d-bd89b9b74c2c | textbox | HOLD POINT NUMBER:
ece81e14-0fc3-5cc0-afb1-4d411fe59b1a | textbox | DATE SUBMITTED:
5927d3a7-b030-58cd-a026-2e7b741dc32e | textbox | Work Start Date:
28018c20-ee72-5b75-b3db-127a65f0850c | textbox | SUBMITTED BY:
9900201e-5331-5c73-a311-1aef19775300 | textbox | SPECIFICATION AND CLAUSE:
0a2f11ab-4f32-5678-9954-0837b9784108 | textbox | HOLD POINT DESCRIPTION:
4139a7ee-7cf3-52fa-b697-5c7e98b31a82 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 4 - Certificate of Conformity
| checkpoint | HOLD POINT
41ae64db-5350-5125-a67f-51e3043ffec4 | note | REQUIREMENTS / REFERENCE - AS 4058 R11 cl 2.6
af5b05f8-59ba-56ed-b2f4-f7236b67de54 | note | ACCEPTANCE CRITERIA - Signed certificate stating that the materials used in the finished product conform to the requirements of AS 4058, and must describe the item and identify the inspection and test records that verify conformity | ACCEPTANCE CRITERIA - Signed certificate stating that the materials used in the finished product conform to the requirements of AS 4058, and must describe the item and identify the inspection and test records that verify conformity
612c30cb-a4d9-5892-bf9b-1b0d9e87dad4 | note | As per Clause 2.7, where shown on the drawings, supply CMP Manufacturing half round corrugated steel pipe (or Principal approved equivalent) for batter drains. CoC is required for this product | As per Clause 2.7, where shown on the drawings, supply CMP Manufacturing half round corrugated steel pipe (or Principal approved equivalent) for batter drains. CoC is required for this product
dbe9c600-240a-5c1c-90c4-af52e0768b89 | note | HOLD POINT: Certificate of conformity
1844e413-c05c-5fee-885e-6bfb0ef1b404 | textbox | HOLD POINT NUMBER:
68b2b86b-adc9-58ce-8bbf-c07585da9c17 | textbox | DATE SUBMITTED:
def1fa77-47dd-5477-b7e2-71fc991b94dc | textbox | Work Start Date:
fa9c2145-c704-5534-bfb2-8daff39fc923 | textbox | SUBMITTED BY:
6a5b2925-50dd-50b5-a21d-1c7371fe061d | textbox | SPECIFICATION AND CLAUSE:
93a74234-9a0b-508d-9cd6-7ba361f6fc32 | textbox | HOLD POINT DESCRIPTION:
22d9259c-c043-5001-b3cf-742a59ff2f57 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Supply of bedding and support fill material
| checkpoint | VERIFICATION
48860caf-eea2-5af2-8501-e6cbff5b0176 | note | REQUIREMENTS / REFERENCE - R11 cl 3.1 AS 3725 - Table 6 AS 1597.2 – Table 5.1
475da5c2-90c9-5e2c-be22-d5975835e500 | note | ACCEPTANCE CRITERIA - Bed, support and backfill all pipes with non-aggressive material (pH > 5.5, SO4 < 1000 mg/Kg (ppm) and chloride < 1000 mg/Kg (ppm)) | ACCEPTANCE CRITERIA - Bed, support and backfill all pipes with non-aggressive material (pH > 5.5, SO4 < 1000 mg/Kg (ppm) and chloride < 1000 mg/Kg (ppm))
4982be74-b5b5-53b3-8b95-6df154fec8c4 | note | Bedding and Haunch Zones must have particle size distribution within the limits set out in Table 6 in AS 3725 or table 5.1 in AS1597.2, and a PI not more than 6 | Bedding and Haunch Zones must have particle size distribution within the limits set out in Table 6 in AS 3725 or table 5.1 in AS1597.2, and a PI not more than 6
e1538199-710b-52a1-af50-6859c6f9c2e4 | note | Side and overlay zones must have a maximum particle size of 53mm and a PI between 2 & 12
993b0d50-57ab-511b-93d0-62ef0c4a8fcb | note | Fill Material for Embankment in Open Drain must be graded and compacted as required
9cc9a221-36be-56bb-bda6-352d091d9fac | textbox | HOLD POINT NUMBER:
deee5530-2030-57cc-b7a7-e203c6296da5 | textbox | DATE SUBMITTED:
c92c5f78-b4a4-50e6-9443-f9142ece609a | textbox | Work Start Date:
66db27f3-90f4-5ce0-95ea-69baa52d1dac | textbox | SUBMITTED BY:
57c4525b-91e8-50c6-a3ea-bba790d94636 | textbox | SPECIFICATION AND CLAUSE:
57f1030f-6a09-5393-8158-d5d950b46603 | textbox | HOLD POINT DESCRIPTION:
8a4219f4-597a-54e3-acb3-27741f143a7c | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 6 - Rock Rip Rap
| checkpoint | HOLD POINT
a458ae1e-8c4b-5116-b4ad-c343a14f0c93 | note | REQUIREMENTS / REFERENCE - R11 Cl 3.4
916f73ad-ddea-5bb0-9d1a-5be58e799cc9 | note | ACCEPTANCE CRITERIA - Rock for rip rap scour protection must be dense, hard, durable, resistance to weathering, angular in shape and free from defects and degradation and chemical alteration. | ACCEPTANCE CRITERIA - Rock for rip rap scour protection must be dense, hard, durable, resistance to weathering, angular in shape and free from defects and degradation and chemical alteration.
1ed9ab1c-ba7a-5c6e-9351-18aff8bc27e0 | note | Rock that is laminated, fractured, porous or physically weak must not be used.
26660ca7-441b-5173-bf03-fa5ce19b3793 | note | Rock must be free from overburden, spoil, shale and organic matter.
c455aef3-a645-551a-910f-1d45f22481c7 | note | The rock must be certified by the Geotechnical Engineer to confirm that it is suitable for use in the works
22aa25f0-2bd4-5e3f-b5cc-eeba5660d2bf | note | The rock must also comply with the property requirements of R11 Cl 3.4.2, and the sizing and grading requirements of Cl 3.4.3
8ab07806-df4a-5c8f-b32d-1969fca03517 | note | Provide test results for rip rap rock once for each source of rock material, prior to placement
7b61253d-af67-5945-b01e-8f9065b062c8 | note | HOLD POINT: Provide test results and certification documentation regarding the properties and source of the rock rip rap
25815364-bbd0-5658-9344-ba9222c778ef | textbox | HOLD POINT NUMBER:
727c10ab-2cb4-567e-9485-11dc27b41558 | textbox | DATE SUBMITTED:
9fe594c0-233b-5282-b362-f8bb4160bda3 | textbox | Work Start Date:
7a8b1cf1-dd4c-59b2-8457-27d034e2cb55 | textbox | SUBMITTED BY:
32c6ebc9-8945-553c-a5ff-a5ae12884876 | textbox | SPECIFICATION AND CLAUSE:
5bfb2814-1b6a-5c5e-a889-8dd3c84ab364 | textbox | HOLD POINT DESCRIPTION:
c70ecc82-aa93-510e-be0b-8359e3449e0a | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Setting out
| checkpoint | HOLD POINT
90c085c0-4b8f-5015-9f34-ae28378b02e9 | note | REQUIREMENTS / REFERENCE - R11 Cl 4.1.1 R11 Annexure C
8efd8b02-ea4c-568c-a961-b40e6c7d67de | note | ACCEPTANCE CRITERIA - HOLD POINT: At least 10 working days prior to the date of commencement of the work, provide notification to the Principal that set out of drainage system has been completed and details of any design changes in locations and levels proposed by Abergeldie | ACCEPTANCE CRITERIA - HOLD POINT: At least 10 working days prior to the date of commencement of the work, provide notification to the Principal that set out of drainage system has been completed and details of any design changes in locations and levels proposed by Abergeldie
4b57178c-b0ec-5b0e-8e07-6c9ba4f56891 | textbox | HOLD POINT NUMBER:
001d305e-9fc5-5dde-8308-125eb960e250 | textbox | DATE SUBMITTED:
3d07f688-a471-509f-b537-c69ee56416fe | textbox | Work Start Date:
0de23369-ce0a-5ac4-be5e-8b2abc5fece5 | textbox | SUBMITTED BY:
1be5c596-2f0c-52b6-83f1-50b67b16e6b3 | textbox | SPECIFICATION AND CLAUSE:
a5b6651a-bf8b-53fc-a875-ba954e4fa4bc | textbox | HOLD POINT DESCRIPTION:
c45336c8-f1f5-590e-9cc4-65050f2b0919 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Open Drains
| checkpoint | HOLD POINT
0f7988b6-0f7b-5f31-aece-763328a84106 | note | REQUIREMENTS / REFERENCE - R11 Cl 4.2.1
36066ac7-8996-5b90-8208-3df17cc21add | note | ACCEPTANCE CRITERIA - Excavate open drains (including topsoil) as per Drawings or to a minimum depth of 300 mm, minimum base width of 500mm and a minimum waterway area of 0.2 m2, with side batter slopes not steeper than 2H:1V. | ACCEPTANCE CRITERIA - Excavate open drains (including topsoil) as per Drawings or to a minimum depth of 300 mm, minimum base width of 500mm and a minimum waterway area of 0.2 m2, with side batter slopes not steeper than 2H:1V.
710a56fe-0649-5f58-8909-3d172231da97 | note | Grade to a slope of not less than 0.5% to ensure a free flow of water.
aaf27656-5fbb-5c9c-a63a-a4a2428f47de | note | All linings must be placed to prevent water ponding
b24104bb-2607-5a3d-aefe-1cf8b0e9351e | note | HOLD POINT: Notify the Principal if 0.5% minimum grade cannot be achieved
45a7efef-3ff1-513a-8e84-4576fadf89b6 | textbox | HOLD POINT NUMBER:
e3f6a2f1-b127-51f1-b2a5-bb590f09d393 | textbox | DATE SUBMITTED:
bc78a201-e2f1-5654-bb89-e84dd6a949ce | textbox | Work Start Date:
37591d9a-d313-59c0-8d39-5acd34b34838 | textbox | SUBMITTED BY:
dfaa8044-b13f-50d5-bfcd-953b480225ac | textbox | SPECIFICATION AND CLAUSE:
86c29a41-4a1e-5f00-bff4-7513e0444ecb | textbox | HOLD POINT DESCRIPTION:
857cf449-dee1-56c9-b1d7-939a403887f2 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Excavation for drainage structures
| checkpoint | WITNESS POINT
89386a1d-db47-5591-b5ac-600632302adf | note | REQUIREMENTS / REFERENCE - R11 Cl 4.3.2 Table R11.2
d6d7b89d-8a02-51f8-a497-288bcb064635 | note | ACCEPTANCE CRITERIA - WITNESS POINT: Submit notification to the Principal, not later than 24 hours but not earlier than 5 working days prior to the anticipate date of completion of excavation and preparation of foundations for pipe installation and other drainage structures. | ACCEPTANCE CRITERIA - WITNESS POINT: Submit notification to the Principal, not later than 24 hours but not earlier than 5 working days prior to the anticipate date of completion of excavation and preparation of foundations for pipe installation and other drainage structures.
04537a94-1be8-5427-be79-f90d4904f166 | textbox | WITNESS POINT NUMBER:
67cd60b0-a20d-5f16-94f3-25d6a0e167eb | textbox | DATE SUBMITTED:
b00a4fc6-dff8-528e-916a-c3afc82ca070 | textbox | Work Start Date:
21755e54-6016-5990-a65c-6c3dea6ef6b0 | textbox | SUBMITTED BY:
ccff1f5a-0f13-5e3a-9e25-ab015bb9e72c | textbox | SPECIFICATION AND CLAUSE:
70c625b1-fd28-5f5d-8cc8-c8809e4109b3 | textbox | WITNESS POINT DESCRIPTION:
6e6676ef-5003-5afa-951d-b4eabc83d434 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 10 - Inadequate Foundation Material
| checkpoint | HOLD POINT
31e3ccb9-a301-5106-962d-bf688cd7ad5f | note | REQUIREMENTS / REFERENCE - R11 Cl 4.3.3 Table R11.2
195aface-877e-590c-8335-eecbf825108d | note | ACCEPTANCE CRITERIA - Notify the Principal of any area of the foundation which may contain material that is inadequate to support the drainage structure. Principal may direct method of rectification if they are in agreeance. | ACCEPTANCE CRITERIA - Notify the Principal of any area of the foundation which may contain material that is inadequate to support the drainage structure. Principal may direct method of rectification if they are in agreeance.
d52cb443-be94-5aab-ad63-042196bccab5 | note | Where sides of trenches for drainage structures are composed of material which may require removal and replacement, notify the Principal of the presence of such material | Where sides of trenches for drainage structures are composed of material which may require removal and replacement, notify the Principal of the presence of such material
ebf8819e-a3f4-5da1-af94-11b33199a378 | note | Replace inadequate foundation material with materials from cuttings or with other material acceptable to Principal and compact to (requirement of Table R11.2) 95% compaction | Replace inadequate foundation material with materials from cuttings or with other material acceptable to Principal and compact to (requirement of Table R11.2) 95% compaction
70691957-7226-5cf4-85a9-3d783c2e39f1 | note | Geotechnical engineer to arrange tests and inspect all foundations of all proposed drainage structures following replacement or foundation treatments and provide certification that foundations are acceptable | Geotechnical engineer to arrange tests and inspect all foundations of all proposed drainage structures following replacement or foundation treatments and provide certification that foundations are acceptable
7436b700-5ac3-548b-ab30-0569f2795bb6 | note | HOLD POINT: Details of tests, inspections, assessment and any proposed foundation replacement or treatment by the geotechnical engineer | HOLD POINT: Details of tests, inspections, assessment and any proposed foundation replacement or treatment by the geotechnical engineer
7b5bf6d2-7f1c-510c-8902-4742e35baea9 | textbox | HOLD POINT NUMBER:
f39dae23-0cdf-5347-909b-4686c6d5c5fd | textbox | DATE SUBMITTED:
43130618-f2d0-5a54-a016-a30ae6c52401 | textbox | Work Start Date:
c237e27b-3c03-5069-8d9a-ec9526a84f2c | textbox | SUBMITTED BY:
010aaef0-11a6-5b50-a78c-46489c226e0a | textbox | SPECIFICATION AND CLAUSE:
d3f13a77-980b-5a81-8cdd-4b1e4fc3313f | textbox | HOLD POINT DESCRIPTION:
0dcc263e-d7e5-5b7f-9ff1-8150d9a6b640 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - Construction of Other Drainage Structures
| checkpoint | WITNESS POINT
2e4cb7a3-0b74-55f4-9ca8-485ab70c74b4 | note | REQUIREMENTS / REFERENCE - R11 Cl 4.7
5d1460fb-c22b-5f32-b979-6be33b0b9b0a | note | ACCEPTANCE CRITERIA - References to “other drainage structures” means “drainage structures other than pipes and box culverts” and includes pits, associated ladders / step irons, pit covers, lintels and grates, junction boxes, drop structures, inlet and outlet structures, headwalls, wingwalls, batter chutes and energy dissipators, and modifications to existing drainage structures | ACCEPTANCE CRITERIA - References to “other drainage structures” means “drainage structures other than pipes and box culverts” and includes pits, associated ladders / step irons, pit covers, lintels and grates, junction boxes, drop structures, inlet and outlet structures, headwalls, wingwalls, batter chutes and energy dissipators, and modifications to existing drainage structures
cc8ac97f-d46c-57fd-933b-ea70a8ffe296 | note | WITNESS POINT: Submit notification to the Principal at least 7 days prior to construction of drainage structures other than pipes and box culverts | WITNESS POINT: Submit notification to the Principal at least 7 days prior to construction of drainage structures other than pipes and box culverts
97025f74-0f03-5e82-9c03-fb7f588e9274 | textbox | WITNESS POINT NUMBER:
8f02576b-c35d-5bb8-9d63-842fd3dbb585 | textbox | DATE SUBMITTED:
63aeecb1-4406-5f9a-88c8-333ee5c1b1c4 | textbox | Work Start Date:
d87e5afe-0db2-565c-86c7-ecd3b6fc1691 | textbox | SUBMITTED BY:
3b4a67a8-faa5-5397-99e8-e064f7c01885 | textbox | SPECIFICATION AND CLAUSE:
86cc4e86-fae6-5530-849e-9796e1a3a50a | textbox | WITNESS POINT DESCRIPTION:
d05a2d14-7da7-5cf7-a096-8f24ac5f794a | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 12 - Compaction
| checkpoint | VERIFICATION
8e444f64-d294-52d7-85b4-0d76455f2749 | note | REQUIREMENTS / REFERENCE - R11 cl 4.9.2 Table R11.2
f0399b9a-70fa-5f7e-8936-61c55a750707 | note | ACCEPTANCE CRITERIA - Place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150mm compacted thickness and compact to 95%. For backfill of Select Fill in Side and Overlay zones of box culverts, and for existing twin 1800mm diameter culvers as shown on the Drawings, the minimum relative compaction is 98% | ACCEPTANCE CRITERIA - Place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150mm compacted thickness and compact to 95%. For backfill of Select Fill in Side and Overlay zones of box culverts, and for existing twin 1800mm diameter culvers as shown on the Drawings, the minimum relative compaction is 98%
22d393b4-bc94-55ec-a7a1-f0204a3395d8 | note | For backfill material within the Selected Material Zone of the adjoining earthworks (Refer R44 Spec) the minimum relative compaction is 102% | For backfill material within the Selected Material Zone of the adjoining earthworks (Refer R44 Spec) the minimum relative compaction is 102%
99fdcfbd-e10d-5383-9244-5bed0e9b7b3e | note | Refer to Table R11.2 for compaction requirements
96cb7f7c-e245-5f14-86ed-0c33a8362fc4 | note | Follow procedures for achieving adequate compaction of fill outlined in Abergeldie’s Project Quality Plan
f127d336-ed51-5457-a0bf-02f762535710 | note | Comments / Attachments / Records - Compaction test results
| section | 13 - Construction Traffic
| checkpoint | HOLD POINT
7d1940e6-7dcf-55d0-8912-3033a9065d70 | note | REQUIREMENTS / REFERENCE - R11 Cl 4.10 TfNSW G2 – C2
9d68efc8-f6bf-5b71-83c2-065b6838f422 | note | ACCEPTANCE CRITERIA - Prior to moving heavy construction plant or vehicles over box culvert structure, submit the Principal with a certificate and verification of protective measures in accordance with TfNSW G2-C2 if required. | ACCEPTANCE CRITERIA - Prior to moving heavy construction plant or vehicles over box culvert structure, submit the Principal with a certificate and verification of protective measures in accordance with TfNSW G2-C2 if required.
45229acc-79b4-5147-aa68-d7da37bad0a4 | note | HOLD POINT: Submit certificate of verification of protection measures prior to heavy construction loading
713628dd-b982-5a27-aa60-dcb980b49dd5 | textbox | HOLD POINT NUMBER:
027c0eb9-022f-5208-9d62-65ab1245680a | textbox | DATE SUBMITTED:
97bce385-822d-519e-8fe1-d3f7b3ddc7b1 | textbox | Work Start Date:
2ffe0d26-37fb-54e4-a4c0-88cae40514f6 | textbox | SUBMITTED BY:
eb0ab50c-6697-50ec-be2c-7ae02d82b76a | textbox | SPECIFICATION AND CLAUSE:
16053338-d5c8-506b-9f17-8ad9fbdf8e0e | textbox | HOLD POINT DESCRIPTION:
542d20ad-de3c-5d28-922e-034c26ec4606 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 14 - Construction Tolerances
| checkpoint | VERIFICATION
aa3b4fb6-a33b-543e-8497-b6fe3ef87a9d | note | REQUIREMENTS / REFERENCE - R11 Cl 5.1 Table 11.4 TfNSW R116 TfNSW R119 TfNSW R83
7030ad1f-984d-5a78-940b-7b64f0cbdf9e | note | ACCEPTANCE CRITERIA - Assets installed as per required construction tolerances
f40241f8-0aeb-599c-8f3f-4b140e112d1a | note | Comments / Attachments / Records - Survey report
| section | 15 - Inspection of Stormwater Box Culverts
| checkpoint | VERIFICATION
2991a518-22fb-57ab-813b-8a85d7380fc8 | note | REQUIREMENTS / REFERENCE - R11 cl 5.2
95032ac9-186b-5caa-8790-3963f0c618a3 | note | ACCEPTANCE CRITERIA - Prior to commencing construction work undertake a CCTV inspection of any existing stormwater drainage pipes and box culverts that are to remain and provide a condition report to the Principal. Report any non-conformities including cracks greater than 0.15mm. Nominate a repair method in line with Concrete Pipe Association of Australasia’s publications listed in R11 Cl 5.2. Do not commence repair works until the Principal authorises the repair method(s) | ACCEPTANCE CRITERIA - Prior to commencing construction work undertake a CCTV inspection of any existing stormwater drainage pipes and box culverts that are to remain and provide a condition report to the Principal. Report any non-conformities including cracks greater than 0.15mm. Nominate a repair method in line with Concrete Pipe Association of Australasia’s publications listed in R11 Cl 5.2. Do not commence repair works until the Principal authorises the repair method(s)
fc8530e4-ac27-5225-8f6f-53bcbb27e27d | note | Carry out CCTV inspections of box culverts to verify that the works have been constructed within the specified tolerances, the flow of water is not obstructed by waste construction material left inside, and to check for visible signs of defects, at the following times: | Carry out CCTV inspections of box culverts to verify that the works have been constructed within the specified tolerances, the flow of water is not obstructed by waste construction material left inside, and to check for visible signs of defects, at the following times:
1755b627-3ed7-525d-b9f0-a053bf342046 | note | On completion of the subject drainage structure and prior to commencement of the overlaying pavement,
e7d8ee2e-35e3-54d5-bf5f-b64929f92e47 | note | On completion of overlying pavement but prior to opening to traffic, and
f0704cec-bd94-5415-8ba4-c1e8efa1a7d0 | note | No more than 14 days prior to completion
f90742af-3577-51f1-aec3-ce8e083919b1 | note | On completion of the inspections, submit to the Principal a report of these inspections and any nonconformity detected. The inspection and reporting must be in accordance with WSA05-2008 | On completion of the inspections, submit to the Principal a report of these inspections and any nonconformity detected. The inspection and reporting must be in accordance with WSA05-2008
| section | Identified Records
| checkpoint | Please upload any Identified Records here
| section | Lot Verification
| checkpoint | Lot Verification complete
30231ca9-8a59-5c5f-a07c-782911524c59 | textbox | Lot Verified By:
25af7531-432a-55ca-a307-8d5f2bd3a514 | textbox | Lot Closed Date:
2330344f-ac53-55e5-bf83-74d3fbad1c82 | button | Submitted to Client | Yes, No, N/A
eea841ff-d0fe-5032-ad65-3a6fbe81f518 | button | Reviewed by Client | Yes, No, N/A
fb5de652-3183-5f7f-bf82-4674bb826697 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 03 - B80 Concrete Structures (B80) Rev 1 |  | ITC 03 - B80 Concrete Structures (B80) Rev 1 | ad2f37d3-b5ec-45e6-8666-d30fd8f6bd1b
| section | Lot Information
| checkpoint | Lot Information complete
efe32787-5571-5e06-b2d4-ad73f56dcbb5 | textbox | Lot Opened On
8bb8c69b-c198-5a83-9954-313684a9082a | textbox | Date of Works
747be7c9-15ad-571d-be38-e5148714b02d | textbox | Lot Type
4ff104df-c2bf-5457-9ab7-62b80d276d74 | textbox | Start Chainage
e89555d5-96dc-5c3e-92f8-e8ebef7d60ca | textbox | End Chainage
0fada8b2-c448-5dd1-a99a-a0eabd03e37e | textbox | Offset
c39ecb72-dc8b-532e-8b22-8e4e77c22186 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
673c6cf8-8834-5af3-8315-10bb4ceb8840 | note | REQUIREMENTS / REFERENCE - Project Safety Plan
b03963fa-c406-5053-80e2-16de3476609c | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural).
89117d20-a4ac-516a-8f2b-697bde15ef0a | note | Required Safe Work Method Statements completed and signed.
c00bbcbd-aee0-5a64-8c35-21fe7326964c | note | Comments / Attachments / Records - Subcontractor’s safety plan/procedure approved.
| section | 2 - Environment
| checkpoint | VERIFICATION
d4f31725-c468-5938-bc95-86a1f268c859 | note | REQUIREMENTS / REFERENCE - Project Environment Plan
ccaa00c9-beeb-5966-8f08-3f3606102103 | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
ffb3faa2-babf-53d6-bbad-d1e67619741d | note | Air quality to be visually monitored for dust etc as a direct result of construction activities.
| section | 3 - Concreting Personnel
| checkpoint | HOLD POINT
f4e0f334-ed06-52d9-891e-3df388126ceb | note | REQUIREMENTS / REFERENCE - B80 Cl 7.2.3
fad431ee-56f7-5940-9e78-2eb564fab36d | note | ACCEPTANCE CRITERIA - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
4b28d30c-ef4e-5ea4-a901-dccb1f587d6c | textbox | HOLD POINT NUMBER:
0fe8940b-042f-5142-b283-e948cb88c90b | textbox | DATE SUBMITTED:
6f857733-8855-579f-90f9-7fb30a9058f1 | textbox | Work Start Date:
067103b0-bee3-5ca7-8a58-c45714dae975 | textbox | SUBMITTED BY:
9546e3f6-22f5-5a58-b0e0-998ed835d145 | textbox | SPECIFICATION AND CLAUSE:
14b1b9ff-ec76-5f08-a410-fef89d991fd8 | textbox | HOLD POINT DESCRIPTION:
4aa455ee-5296-5f7e-afe0-66982228b87f | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 4 - Submission of Mix Design
| checkpoint | HOLD POINT
82dce949-cb66-5c38-b290-b8b08a27f5a7 | note | REQUIREMENTS / REFERENCE - B80 Cl 3.9
745dfacc-7e2f-584b-abaa-b40b7a5c51d8 | note | ACCEPTANCE CRITERIA - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
f6110ff1-cbe8-5282-9b21-ae6e20c71464 | textbox | HOLD POINT NUMBER:
61e818f9-0c15-5afa-8e88-3abd3dc62139 | textbox | DATE SUBMITTED:
c94b754a-96da-586c-ba2d-e0a865ff20f0 | textbox | Work Start Date:
31aef8ea-b415-5036-b591-bf6f70fea1dc | textbox | SUBMITTED BY:
303533ba-0dd3-5200-a17a-1102128a2b3e | textbox | SPECIFICATION AND CLAUSE:
fd038f86-cb97-5ca8-9e38-f9bab4973b7d | textbox | HOLD POINT DESCRIPTION:
ee617af1-f7e5-54a8-9f5b-569c6c4121b6 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Test Members
| checkpoint | WITNESS POINT
5228ecc8-8a5d-5d5e-b47c-00d4685f726a | note | REQUIREMENTS / REFERENCE - B80 Cl 5.3
788b5a76-8a6b-5f9f-9f0d-a49ebdc71d50 | note | ACCEPTANCE CRITERIA - Provide notice in writing to the Principal, at least 2 working days, of the upcoming placement of concrete for the test member(s)
c02e6251-d574-5670-91ec-ef7ad2103020 | textbox | WITNESS POINT NUMBER:
11cbcfcf-fb6c-5d86-a258-a197e702c072 | textbox | DATE SUBMITTED:
b60f3bae-7953-5b78-a742-70dad9fc296e | textbox | Work Start Date:
bffd22de-167d-5e0f-8ac2-ca6df149c168 | textbox | SUBMITTED BY:
439dd451-8a89-5f21-809e-24d1c0e14478 | textbox | SPECIFICATION AND CLAUSE:
27ef1a03-7282-58e4-a248-de8f7be0bfe3 | textbox | WITNESS POINT DESCRIPTION:
080a2dd4-71a2-5aaa-96ee-8c681ff12785 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 6 - Formwork Certification
| checkpoint | HOLD POINT
4a569ffc-f9a8-57f9-912e-799593259ebb | note | REQUIREMENTS / REFERENCE - B80 Cl 5.2.3
11173b65-a800-5580-9ebf-d08164bf2087 | note | ACCEPTANCE CRITERIA - Formwork and all temporary supports to be designed and conform to AS 3610.1
303f5297-3baa-52a5-8e2f-54e782f360b9 | note | Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection
4eaf1f25-132f-5a0e-bb6d-5edaa762ea32 | note | Comments / Attachments / Records - Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C.
96cf4908-f927-5dc8-813e-f3ef6e30171e | textbox | HOLD POINT NUMBER:
dc4867d2-3a8c-52c1-bb8c-f80f7df4701d | textbox | DATE SUBMITTED:
4d8cbcb6-3b3e-5b42-82eb-48d472fe26e0 | textbox | Work Start Date:
94ac1c7d-b709-5758-83fa-0f1edc5673fb | textbox | SUBMITTED BY:
401016ad-1ac2-53b2-8ed9-518acc917023 | textbox | SPECIFICATION AND CLAUSE:
ae5c55bb-ea9f-5dd7-8c0f-d428151c3353 | textbox | HOLD POINT DESCRIPTION:
63252f81-cdd3-50cd-9a91-371832019e67 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Prefabricated Cages
| checkpoint | WITNESS POINT
3fd9e637-da36-5d70-8525-d239162d6647 | note | REQUIREMENTS / REFERENCE - B80 Cl 6.6.2
2c715b47-a1b5-51d7-a15d-c9979b6e9d8b | note | ACCEPTANCE CRITERIA - Detail design location of lifting and transport support pins for prefabricated cages
40b80bec-8f1b-5232-9cc6-70568528792e | note | Submit to the principal shop drawings of the prefabricated design with certification, at least 2 working days notice of intention to transport
77049eb5-e986-5999-8895-4ae1ab48114e | textbox | WITNESS POINT NUMBER:
fdf34a70-5997-503c-9456-f3c0f480bb77 | textbox | DATE SUBMITTED:
dcf258b2-c6cd-5458-a672-53725092bdc1 | textbox | Work Start Date:
8771da34-41b5-5ce6-a354-dc042a86b320 | textbox | SUBMITTED BY:
0d6fdd1e-9ed4-52da-b0fb-933437d9e1ae | textbox | SPECIFICATION AND CLAUSE:
8af49849-3515-5226-8b3b-6094f961ab6c | textbox | WITNESS POINT DESCRIPTION:
5de22bb7-c43f-5ed6-8bb8-8d525b9623e2 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 8 - Checklists for Conformity
| checkpoint | HOLD POINT
dd4b66db-2322-5e2c-ae63-e9747744543d | note | REQUIREMENTS / REFERENCE - B80 Cl 7.5.1
3d4bac9f-2eaa-5b09-8c2c-4869e879327e | note | ACCEPTANCE CRITERIA - Submit to the Principal the checklists used for verifying conformity of the nominated concrete mix, formwork, reinforcement and embedments for precast concrete members cast off site at least 2 working days prior to commencement.
a6fbd43e-f016-51c8-90ae-32319e197e21 | textbox | HOLD POINT NUMBER:
efa73acd-1c81-56e8-833b-3aa56702146c | textbox | DATE SUBMITTED:
21b79c67-779b-5b83-a2d3-925e574616fd | textbox | Work Start Date:
70f0a10b-a09e-5ce3-ad5a-a475660f090b | textbox | SUBMITTED BY:
ae85a546-ee17-512c-a009-297d25a255df | textbox | SPECIFICATION AND CLAUSE:
fb799235-01c2-5bdb-9d17-a84df65480a2 | textbox | HOLD POINT DESCRIPTION:
8c5f37d2-9571-598f-8335-f3ab0531a438 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Certificate of Conformity
| checkpoint | HOLD POINT
96000298-60fe-5b4b-bb44-e4e242f99862 | note | REQUIREMENTS / REFERENCE - B80 Cl 7.5.2
63a288a8-69df-5a3f-b0dc-09b977e2d4ea | note | ACCEPTANCE CRITERIA - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working days prior to commencement a Certificate of Conformity of formwork, reinforcement and embedments for the member(s)
11d1676b-b5f6-5254-b3cd-7c688c409c90 | textbox | HOLD POINT NUMBER:
444d1256-d246-5292-8a51-cace821697ad | textbox | DATE SUBMITTED:
b1e6f756-d3b3-5788-813d-f70856819854 | textbox | Work Start Date:
bb846d0f-46c6-5f2e-b0f1-c288106bd857 | textbox | SUBMITTED BY:
89691d97-05b5-5969-9b9a-83e898ee6a32 | textbox | SPECIFICATION AND CLAUSE:
50045255-0773-5eed-8a3d-9e4990564dac | textbox | HOLD POINT DESCRIPTION:
46f4a44f-0fc1-57bc-9a19-47da44f99496 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 10 - Supply and Delivery of Concrete
| checkpoint | VERIFICATION
b417b114-654e-507f-8f8c-94411648b1e4 | note | REQUIREMENTS / REFERENCE - B80 Cl 4.1
6fb0ccc9-f2cb-5c4c-9577-ca17a0f40ab9 | note | ACCEPTANCE CRITERIA - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added
58726abd-4fa0-5347-80f8-a7385d658866 | note | Comments / Attachments / Records - Concrete delivery dockets
| section | 11 - Sampling & Testing
| checkpoint | VERIFICATION
8832669d-d9d0-5cc9-ab01-2c37b1a22542 | note | REQUIREMENTS / REFERENCE - B80 L1
a5ce14c2-577c-5cb7-9ee7-a02735d7c3ee | note | ACCEPTANCE CRITERIA - Slump test to be taken each load
e12ce030-2949-50ac-8674-8cad66bebc71 | note | Compressive strength cylinders to be taken once every 25m3
ef100eb9-13a5-534a-9005-9a51d322f3d3 | note | Comments / Attachments / Records - Concrete test results
| section | 12 - Formwork Removal
| checkpoint | VERIFICATION
7b7dd752-346a-5a9d-a2b7-01d909afc6c3 | note | REQUIREMENTS / REFERENCE - B80 Cl 5.9
dfea85fa-fe73-5950-b7a2-9cdfb81314d7 | note | ACCEPTANCE CRITERIA - Remove formwork in a way and time that achieves specified characteristics and prevents damage
b3882cc3-a815-5db7-9fa5-3b5f2ac7e9fa | note | Adhere to the minimum stripping times as detailed in CL 5.9.2 and table B80.12
2f00c0ee-406a-52c3-b2a9-11ce298abcc2 | note | Comments / Attachments / Records - Survey report for completed works
| section | 13 - Concrete Cracking
| checkpoint | VERIFICATION
66d3dcc3-b2e8-5198-9e4a-e8c5c922a920 | note | REQUIREMENTS / REFERENCE - B80 Cl 9.3
04392d83-010b-551f-b281-7dc24aec2a5a | note | ACCEPTANCE CRITERIA - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days
90af7ca1-3d1b-574a-9f12-83754ac50020 | note | Submit crack map to the principal with proposed remedial actions
| section | 14 - Early Trafficking
| checkpoint | HOLD POINT
6ae6e8e4-35ab-5470-9627-75e713324fca | note | REQUIREMENTS / REFERENCE - B80 Cl 9.9
a85533e0-d464-5bda-b0d6-da9b9582127e | note | ACCEPTANCE CRITERIA - In the event early trafficking of the bridge deck is requested, at least 2 working days prior to commencement of early trafficking, submit the “strength versus age” relationship of concrete, with supporting test results, and evidence of completion of curing.
dd3b4102-2416-5ba3-ae3d-bcf5c3967a01 | note | Make good any damage arising from early trafficking of the bridge deck
4676bd85-68f9-59c4-9116-ab7e76edd8f1 | textbox | HOLD POINT NUMBER:
c44ad129-d27c-57ea-9362-33b6d2a59c32 | textbox | DATE SUBMITTED:
20fc2155-ef7f-55b9-b5fe-e266b8a374fa | textbox | Work Start Date:
038ed12a-ffb7-5b47-8eaf-b864e8a08547 | textbox | SUBMITTED BY:
cc7b73da-4e53-5e8c-8a3f-c8f23e0e5a13 | textbox | SPECIFICATION AND CLAUSE:
21d907af-7473-5e28-b353-9f96762ae98d | textbox | HOLD POINT DESCRIPTION:
b5180de7-aba8-58dd-9b30-44a66263baf9 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | Identified Records
| checkpoint | Please upload any Identified Records here
| section | Lot Verification
| checkpoint | Lot Verification complete
cffee76d-a86e-5bd5-9aba-7332af22ced5 | textbox | Lot Verified By:
3f3462a5-f6b0-5ff6-80e7-30eed1d12891 | textbox | Lot Closed Date:
febbdfc3-8a2c-54e0-bd63-199feac2710b | button | Submitted to Client | Yes, No, N/A
c0342b9e-3d78-5f6a-b68e-f0b2b832cbe3 | button | Reviewed by Client | Yes, No, N/A
1ceea631-81f8-5471-88ac-30bd65f993b3 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 04 - R53 Concrete for Roadworks Rev 1 | itp | ITC 04 - R53 Concrete for Roadworks Rev 1 | 7401c29c-c66a-4c8a-bf14-31cb6824269a
| section | Lot Information
| checkpoint | Lot Information complete
dbbcdd95-5683-5375-8695-bc3412775544 | textbox | Lot Opened On
5e5f42cb-7a73-5781-8012-ef2db5956a93 | textbox | Date of Works
d61d867e-c1b7-536a-8831-b813d646c25b | textbox | Lot Type
afc531d1-df7f-5e11-bc3a-4177a9348540 | textbox | Start Chainage
bb1e68e7-9094-5fc4-a23d-27ebd5223993 | textbox | End Chainage
f887420b-f650-5541-bf72-a0a1c105368f | textbox | Offset
4519d717-6f1e-5429-b909-e4be7d5a5cf9 | textbox | Control Line
| section | 1. Material Compliance
| checkpoint | 1.1 - Submission of Nominated Mixes
4bae2289-1816-589a-a732-0efce741167d | note | Document Reference / Applicable Standard - R53 Cl 2.4.3
40f62462-064c-5d60-b301-36b8dc28009d | note | Acceptance Criteria - Where the nominated mix(es) has had production assessment carried out in accordance with AS 1379 Clause 6.3, submit the production assessment report complying with AS 1379 Clause 6.4.2. Include a statement from each material supplier certifying that the constituent materials meet the requirement of this Specification.
1e49afa4-22cd-5620-9d05-838d8d86084f | note | Frequency/ Process Held - Once / 5 working days prior to commencement of production of mix
23ff142c-8d7f-5b54-bb15-aa584d161c19 | note | Inspection - ACPL - H
0d874c47-64ad-5652-9be2-9daf279ed37b | note | Inspection - Client - H
3152038c-8b21-58d7-af0d-1e4426d08504 | note | Verifying Records - Mix Design Report
| signoff | AUTHORITY HOLDPOINT
| section | 2. Construction
| checkpoint | 2.1 - Notification of Concrete Placing and Finishing
04ed8f66-7a68-5959-9467-0d6683153da5 | note | Document Reference / Applicable Standard - R53 Cl 3.3.1
f490908f-18e3-579b-9fc4-ceaeca93c9dd | note | Acceptance Criteria - At least 2 working days prior to the placing of concrete, provide notice of:
9d029cd9-ad43-5b54-b87c-af89f80a5248 | note | – Expected completion time of fixing of the formwork and reinforcement (if applicable) and;
092a5f99-dcb6-5d91-baed-b236b22d9902 | note | – Expected commencement date and time of placement of concrete
2cd3a92b-1e92-565f-b683-d00002401378 | note | Frequency/ Process Held - Once / At least 2 working days prior to each placement
cb8cf051-ac08-5c37-aebf-3de774d27d95 | note | Inspection - ACPL - H
25613d00-4872-5238-8a5a-727f122ba7c9 | note | Inspection - Client - H
8a8a12b1-cbdf-50e6-bf94-dd69d9405b8d | note | Verifying Records - HP Submission
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete and Air Temperature / Rain
362fdd37-34ea-5c98-856b-adeb63e73cdd | note | Document Reference / Applicable Standard - R53 Cl 3.3.2, R53 Cl 3.3.3
4ba742c0-2dd8-547b-905b-338002035e85 | note | Acceptance Criteria - Do not place concrete in the works if its temperature at the point of discharge is less than 10C and more than 32C.
dc1ca3e9-26f2-5e36-9fd6-ec8c73e00c9f | note | Do not place concrete of the measured air temperature is below 5C or above 35C. Do not place concrete during rain or when rain appears imminent.
a326100e-36af-5627-9cd4-84cc49031c0e | note | Frequency/ Process Held - Once / prior to concrete placement
64c58fad-bdd1-5506-8dfa-5a7d9805e664 | note | Inspection - ACPL - S
3b7bc425-a150-5842-95de-a1baae1cf1dd | note | Inspection - Client - S
132ba64e-d392-593b-8d5b-371e983b9843 | note | Verifying Records - Project Quality Plan Pour Record Sheet
| checkpoint | 2.3 - Placing and Compacting
d178e51c-9ef4-520c-adc7-55199e9bd604 | note | Document Reference / Applicable Standard - R53 Cl 3.3.4
fcf5ef91-1cd3-5e80-9969-e833554a6b6b | note | Acceptance Criteria - Place concrete in such manner that:
92b4d6d6-307f-5569-a624-e24aa507a04c | note | (a) limit segregation or loss of materials;
8d694fb0-6583-507b-9449-88673c9fe93a | note | (b) limit premature stiffening;
eb0f130a-9564-5461-a5b5-fc1e963a12a9 | note | (c) produce a dense homogeneous product which is monolithic between joints and edges;
2c9ee12b-f920-589b-9d89-23394f138266 | note | (d) provide the specified thickness and surface finish.
8c25ec36-fd82-519f-a184-9fcb5a599c13 | note | Carry out vibration in a regular and systematic manner to ensure that all the concrete is thoroughly compacted.
ccbdba57-c53e-5d73-90b1-a33407b0317d | note | Where internal vibrators are used, they must have a minimum diameter of 50 mm with an operating frequency between 130 Hz and 200 Hz.
193ab9b4-75a1-53cd-841c-79b9926002d5 | note | Frequency/ Process Held - During Placement
36277fd8-4780-5b33-8250-b7bb2495fc5a | note | Inspection - ACPL - S
7dc03237-9d46-5c27-bc4e-2e669e3faede | note | Inspection - Client - S
ee9cd104-91e4-5c5a-a2b9-fda9994ca8f0 | note | Verifying Records - Visual Inspection
| checkpoint | 2.4 - Unformed Surface Finish
deac33ea-79a2-54f8-840e-c2c72798d9f3 | note | Document Reference / Applicable Standard - R53 Cl 3.3.6
25455d9d-7d87-5ee0-ab27-fac11541de07 | note | Acceptance Criteria - Finish unformed concrete surfaces in such manner that:
14825a5b-3917-5a97-91ca-89b566c7060d | note | (a) achieve the specified dimensions, grade and surface texture;
bceec45a-5c8b-51f6-ab28-d600beaeea85 | note | (b) avoid plastic or drying shrinkage cracks.
d6aa17df-f2a8-5c5d-85e7-7fb1d13374d1 | note | Frequency/ Process Held - During Construction
bf79fd7d-a829-53e6-9727-a18144ebc2c0 | note | Inspection - ACPL - S
a3172589-9a62-5d6e-ab50-a902d0df891b | note | Inspection - Client - S
252445ba-fbfe-5be6-8097-4b4df392dc3e | note | Verifying Records - Visual Inspection
| checkpoint | 2.5 - Joints
1ebf01c9-132e-51cf-b068-e19ee789f832 | note | Document Reference / Applicable Standard - R53 Cl 3.3.9
795e5cdb-8f07-5655-9abd-4c49b45baaed | note | Acceptance Criteria - Roughen the surface of concrete at construction joints to expose the coarse aggregate. Wash clean the roughened surfaces and projecting reinforcement, and remove all excess water and loose material prior to placing the adjoining concrete.
62968d47-3aaa-5f8d-933d-706851ffbe6f | note | Frequency/ Process Held - During Construction
9f7f06bf-d6f5-5275-b8b4-355db106b6d7 | note | Inspection - ACPL - S
fc9b61e7-fd86-50b0-906d-14cf44acb097 | note | Inspection - Client - S
09a3cf71-bba0-5275-8a8f-d34bd861d986 | note | Verifying Records - Visual Inspection
| checkpoint | 2.6 - Curing
f9e346e4-a952-50fc-a857-408f287a7fd4 | note | Document Reference / Applicable Standard - R53 Cl 3.4
cb45a83d-bf03-528a-9c28-9f2bccd8520a | note | Acceptance Criteria - Apply curing compound to unform surfaces immediately after the surface is firm and free of bleed water
51c0659d-080a-5fc1-8ae6-bbf9a8f2375d | note | Apply curing compound at the rate specified by the manufacturer
0411790b-ea89-509c-ada3-7d0a9cd1f5f9 | note | Apply two coats hen necessary to ensure complete and uniform coverage. The time between the first and second coat must be in accordance with the manufacturer’s recommendation.
e4f8a327-cc09-504a-96cf-d4dfe654a6c9 | note | During application, implement measures to prevent the curing compound drifting away from the target concrete surface and deposited on adjacent surfaces.
708fac71-6058-59f9-b7de-99f56032a9d8 | note | Maintain the curing membrane intact until at least seven days have elapsed after concrete placement
bda25a2c-33bf-50d9-8eb9-e6bcf6bf6b85 | note | Frequency/ Process Held - During Construction
c09a993c-db19-5303-909b-ea2039cc85f2 | note | Inspection - ACPL - S
2dcdeae2-72bd-5220-9926-1ed4912cf718 | note | Inspection - Client - S
9f2037ac-a5ae-58ff-864d-9685e2b5e949 | note | Verifying Records - Project Quality Plan
| checkpoint | 2.7 - Mortar, Grout and Sprayed Concrete
b463ea7a-de67-5640-87d6-5669fa384085 | note | Document Reference / Applicable Standard - R53 Cl 3.6
3b3afb35-5a0d-5e1b-ad63-d010b3eac36e | note | Acceptance Criteria - Notify principal prior to placing of mortar, grout and sprayed concrete.
6c1a08f5-1425-553b-897d-dc9f18d1a688 | note | Frequency/ Process Held - Prior to placing Mortar, grout or sprayed concrete
7fbbcc6a-f48d-5cb0-b8db-6fc4ff2341f3 | note | Inspection - ACPL - W
fd204778-4f04-57d6-9e87-74128d84543d | note | Inspection - Client - W
f328c032-fb2c-5ce2-adbe-a4119853f5e2 | note | Verifying Records - Visual Inspection
| section | 3. Conformity
| checkpoint | 3.1 - Sampling and Testing (Concrete)
9fe8f9d0-f433-54ea-8364-e024dd7a824b | note | Document Reference / Applicable Standard - R53 Cl 4.1.1
3201cf0a-a0f8-5726-8dc9-6a009634cd31 | note | Acceptance Criteria - Slump:
8c85103b-689f-5724-ac64-ff1e2613a850 | note | ○ Perform slump tests on each strength sample
34c0d419-7f22-5bbd-bf7d-9a5f31b9300a | note | Strength:
c4945773-1209-5a70-b933-edb46e75aa97 | note | ○ Each grade at a plant shall be sampled at a frequency of at least one sample per 100 m3 of that grade produced except that, for Grade 20 concrete when 15 or more samples per month are obtained, the frequency may be reduced.
7e810274-d32e-5de5-b2b7-ce8e79e3e8e2 | note | Frequency/ Process Held - Prior to Placement
72b901a8-ab70-58b8-a6c8-e1c10d5235b2 | note | Inspection - ACPL - S
9b4ef3a4-ac53-5d06-889d-df723374b977 | note | Inspection - Client - S
02a071df-4419-59ea-addc-d68ef478272d | note | Verifying Records - Slump Results Strength Results
| checkpoint | 3.2 - Cracking
790079a3-a262-59ed-a474-7d11f9869f3f | note | Document Reference / Applicable Standard - R53 Cl 4.2
672ec15c-07a1-5e05-8c1a-eacb896ed7ee | note | Acceptance Criteria - At the end of the curing period, the concrete surface must have no unplanned cracks of width greater than 0.2 mm, measured at the concrete surface after completion of 21 days drying. Where such cracks exist, identify them as nonconformities.
b06fdabe-f1b6-50bd-a5e0-89c6e7e17e41 | note | Frequency/ Process Held - Once / Prior to Lot Closure
bc89dd44-a147-5c68-8c9f-81df3afb6758 | note | Inspection - ACPL - S
5e25f190-a130-5eca-967b-e685d6076115 | note | Inspection - Client - S
e311b8cb-53ca-5c57-a592-260afbbb5055 | note | Verifying Records - Crack Map
| checkpoint | 3.3 - Dimensions and Levels
f2314fef-250c-5655-b3ee-2b11d870d819 | note | Document Reference / Applicable Standard - R53 Cl 4.3
8f6a3210-22fa-554f-bced-b9efc25aa00b | note | Acceptance Criteria - Dimensions and levels of surfaces constructed using fixed forms must be as shown on the Drawings or in the relevant Specification, and within the tolerances stated in AS 3610.1, unless specified otherwise on the Drawings or in the relevant Specification.
a368a579-e46e-58bb-a613-4e190f915d6f | note | Dimensions and levels of unformed exposed surfaces, and surfaces constructed by slipforming or extrusion, must be as shown on the Drawings, and within the tolerances specified in the relevant Specification.
9ff9cb14-992b-561f-87dc-6b166746f9a3 | note | Frequency/ Process Held - Once / Prior to Lot Closure
643a7a5a-0005-501f-b0aa-764f1fad5112 | note | Inspection - ACPL - S
bbf0be46-fa68-5c43-89f1-a23ae7bf607c | note | Inspection - Client - S
b957eccd-5a30-52a1-8ebd-273a9f497c18 | note | Verifying Records - Survey Report
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
e82f52df-60c7-58ba-8745-f6b5adb667ec | button | Any non-conformances? | YES, NO
b67d9ff3-9042-57ce-9573-b794579d90b7 | textbox | No's:
4bb39173-8a4a-582e-ad9c-5ab2a4b14904 | button | Closed Out | YES, NO
0c039715-cb7e-53c2-982a-2902dd41d40e | button | All work has been satisfactorily completed. | YES, NO
1245fb27-639a-5022-8e0c-8c200c4748e3 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
a1852c9f-4aa3-5d6e-9291-c5f1810aef5b | textbox | Lot Verified By:
a9d5d516-0bfa-583e-a77d-095367d0c7d8 | textbox | Lot Closed Date:
db801382-fb29-5330-86d5-1096008826e2 | button | Submitted to Client | Yes, No, N/A
e72a8413-fce4-50d4-b3c9-bf8050076189 | button | Reviewed by Client | Yes, No, N/A
277dabbe-bce8-5191-8317-304feca3c285 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 05 - R44 Earthworks UZF Rev 0 |  | ITC 05 - R44 Earthworks UZF Rev 0 | 306c1411-8920-4671-b46c-2700ebe7d164
| section | Lot Information
| checkpoint | Lot Information complete
c8c3f261-686e-5bf5-bb55-79dc133f83f1 | textbox | Lot Opened On
59541f67-f34a-5861-b688-1e2c0c9ed39c | textbox | Date of Works
dd006d30-192f-5ce6-91dc-bf6862fa1aa2 | textbox | Lot Type
2a648da5-ae2c-5862-979f-aed3b3d74b7c | textbox | Start Chainage
030d3379-c68c-5a43-9308-a6988d1b4d5c | textbox | End Chainage
e3277697-3a2e-5df9-9f58-81e0d98866ea | textbox | Offset
bf011e06-62e9-5c70-b6f1-e2bdcaa8aed2 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
17936901-6553-5ad4-9392-df0f38b1c459 | note | Requirements / Reference - Project Safety Plan
b8ab80f8-8f3c-5d73-9f5d-16a4c77b09b9 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
eaa80136-04e3-52f9-9c7c-f34ef8e4cae6 | note | Required Safe Work Method Statements completed and signed
ea394f39-fb73-5d4e-a8db-f16b3091c256 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
81c38e0a-8183-54f9-baab-186642edd951 | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
13db5d7d-3e71-5d86-8e2f-005b88b6442a | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38 | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
4c55f7e5-177e-5d42-bbb6-7f4174567f11 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Personnel
| checkpoint | VERIFICATION
424f2fd9-6958-5fa8-8801-332e685a97fe | note | Requirements / Reference - R44 Cl 1.8, 1.9
919f70eb-f0da-5537-953e-09867e85a7fc | note | Acceptance Criteria - Geotechnical Engineer: Engage a Geotechnical Engineer to meet the requirements of TfNSW G1 Clause 19, to undertake or organise for tests, calculations, reports, recommendations etc, where stated in this and other Contract Specifications | Acceptance Criteria - Geotechnical Engineer: Engage a Geotechnical Engineer to meet the requirements of TfNSW G1 Clause 19, to undertake or organise for tests, calculations, reports, recommendations etc, where stated in this and other Contract Specifications
15853d03-12f2-539a-82ad-211ce02d021a | note | Occupational Hygienist: Engage an Occupational Hygienist with an appropriate degree qualification and with a minimum of 5 years’ experience in contaminated land, site assessment and remediation, and also having appropriate accreditation as an occupational hygienist. The Occupational Hygienist must be involved in inspections, tests, reports, assessments and / or recommendations where stated in this Specification. They must be on site: | Occupational Hygienist: Engage an Occupational Hygienist with an appropriate degree qualification and with a minimum of 5 years’ experience in contaminated land, site assessment and remediation, and also having appropriate accreditation as an occupational hygienist. The Occupational Hygienist must be involved in inspections, tests, reports, assessments and / or recommendations where stated in this Specification. They must be on site:
c12a7caa-3912-50cf-adcd-bba74faf2dc0 | note | Whenever topsoil operations are underway (Cl 2.3)
5b98c9cb-6741-5ee2-a958-7f9b013349a0 | note | During advance contamination assessments (Cl 2.3.2), and
65061356-bf65-5260-aed9-40cb4adfcfb8 | note | At other times as required in this Specification
c6b2b97b-9ebb-5ed9-b8ac-e22d65fb3930 | note | Comments / Attachments / Records - Test report
| section | 4 - Existing Site Survey and Setting out
| checkpoint | VERIFICATION
34084fc6-7171-5e48-826c-676b08a4b607 | note | Requirements / Reference - R44 6.1 R44 6.2
85b48dcb-d88a-548e-bc67-5377561e1818 | note | Acceptance Criteria - Survey to determine surface levels at sufficient locations to determine the volume of compacted imported material placed during works | Acceptance Criteria - Survey to determine surface levels at sufficient locations to determine the volume of compacted imported material placed during works
cf4b34fd-ca7c-5301-93ee-0b4f5697e768 | note | Set out embankments and transitions zones using pegs, batter profiles or equivalent. Maintain drainage to work area in a manner that prevents ingress of water into materials and ensures controlled run-off and no ponding. | Set out embankments and transitions zones using pegs, batter profiles or equivalent. Maintain drainage to work area in a manner that prevents ingress of water into materials and ensures controlled run-off and no ponding.
e57349e4-0882-5322-908e-a23689e05ec1 | note | Plant/Equipment is selected such that constant tracking of the underlying ground does not turn the existing ground into unsuitable material | Plant/Equipment is selected such that constant tracking of the underlying ground does not turn the existing ground into unsuitable material
| section | 5 - Spoil and Waste Classification Testing
| checkpoint | VERIFICATION
a6c897fc-a5e5-55a2-ad93-db8d1ff8681c | note | Requirements / Reference - R44 CL2.5 TfNSW G36 R44 CL2.5.2
843a8110-24f6-5d55-a573-258da0086294 | note | Acceptance Criteria - Disposal of Non-contaminated materials:
6e9ff7a9-a916-54f9-97aa-7710eac736de | note | At Flat batter slopes on embankments, uniform widening of embankments and stockpiling within site
db346640-1ea5-53d6-95ba-b7b663b5ae94 | note | Approved offsite location (If all on-site areas are at capacity)
3732f7f2-04b5-52e3-ba3a-fdeaec7abc5b | note | Disposal of Contaminated materials:
ce5af65b-8a53-5a5b-9cc6-a96961cadf85 | note | Stockpile and remove offsite any contaminated materials
d4d4114d-621a-5035-847b-0265e2c0eac9 | note | Notify the principal at least 24 hour prior to disposal, of proposed method and location of disposing contaminating materials from site. | Notify the principal at least 24 hour prior to disposal, of proposed method and location of disposing contaminating materials from site.
| section | 6 - Removal of Topsoil
| checkpoint | HOLD POINT
a7a4b0c8-0e9b-5ddb-a587-9c44b3077e13 | note | Requirements / Reference - R44 CL2.3.1
b0fcfe73-ffa5-5c2e-84b2-48c9d5f87e60 | note | Acceptance Criteria - Remove or leave topsoil in place to suit the requirements for earthworks for roadworks, aiming to create a stable formation suitable for the pavement | Acceptance Criteria - Remove or leave topsoil in place to suit the requirements for earthworks for roadworks, aiming to create a stable formation suitable for the pavement
a400fb03-5de0-579b-809d-f4616bd257fa | note | Geotechnical engineer undertakes inspections of all areas, assessing and recommending the depth of topsoil for each area as a Hold Point | Geotechnical engineer undertakes inspections of all areas, assessing and recommending the depth of topsoil for each area as a Hold Point
a3c842f2-7f6d-5a90-94e0-a5614540ed40 | note | HOLD POINT
5cbbcf14-51c8-50c8-8bab-95aa32a22488 | note | At least three working days before your proposed removal of topsoil, provide a recommendation of the proposed depth of topsoil including details of the inspections and other relevant information used to make that recommendation. The proposal must also detail the proposed sub area of topsoil removal (including a plan of that sub area) and a proposed final location of the topsoil once it is removed (either stockpiled within the site or spoiled outside the site) | At least three working days before your proposed removal of topsoil, provide a recommendation of the proposed depth of topsoil including details of the inspections and other relevant information used to make that recommendation. The proposal must also detail the proposed sub area of topsoil removal (including a plan of that sub area) and a proposed final location of the topsoil once it is removed (either stockpiled within the site or spoiled outside the site)
1112c1b6-1c02-53b8-9192-95247789ac1e | textbox | HOLD POINT NUMBER:
0fb8cb88-f098-5d61-b60c-e709cddc0af7 | textbox | DATE SUBMITTED:
0548c3cd-c09b-59b4-8b6f-ec852fe3bd7b | textbox | Work Start Date:
2995f71c-8583-59e9-94d9-fd385e19599f | textbox | SUBMITTED BY:
62313a7c-3485-5923-892a-8652b6d7ccec | textbox | SPECIFICATION AND CLAUSE:
c6674092-f74d-526a-8e00-5479bbb90b27 | textbox | HOLD POINT DESCRIPTION:
ebb5e8ec-6d07-5ea7-a96a-463dc22a35e5 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Removal of Topsoil
| checkpoint | HOLD POINT
c01ac9bb-77b5-5407-8cdf-aff92cb19adb | note | Requirements / Reference - R44 CL2.3.2
f30778ce-383a-56f7-b251-3c3a63a61f79 | note | Acceptance Criteria - Occupational hygienist inspects the topsoil ground surface and document the presence/absence of visible contamination at the ground surface (including asbestos and asbestos containing material) including documenting the likelihood of contamination being present | Acceptance Criteria - Occupational hygienist inspects the topsoil ground surface and document the presence/absence of visible contamination at the ground surface (including asbestos and asbestos containing material) including documenting the likelihood of contamination being present
3b168a36-d7cf-5f37-a5fd-2044c3ea4970 | note | If asbestos and/or other contamination is identified or considered likely to be present, you are to make proposals for the management/remediation measures for the identified or suspected contamination prior to disturbance or removal of the topsoil | If asbestos and/or other contamination is identified or considered likely to be present, you are to make proposals for the management/remediation measures for the identified or suspected contamination prior to disturbance or removal of the topsoil
d9abb070-ea68-5548-ad7b-48f9d96e5671 | note | HOLD POINT
c8bbf7ca-1baa-5ad0-9947-30e43e53797b | note | At least three working days before your proposed removal of topsoil, provide findings of visible topsoil contamination and/or suspected topsoil contamination including details of the inspections and other relevant information used to make that assessment | At least three working days before your proposed removal of topsoil, provide findings of visible topsoil contamination and/or suspected topsoil contamination including details of the inspections and other relevant information used to make that assessment
649ac5fd-fab0-5e39-945d-9b39403729f4 | textbox | HOLD POINT NUMBER:
cd16f3c0-2562-52d7-958a-508186208232 | textbox | DATE SUBMITTED:
335c026b-e1c4-55cf-8c4e-82a1af05c8a0 | textbox | Work Start Date:
c51aeed0-e4f9-576e-bc59-a40568d60b3b | textbox | SUBMITTED BY:
f7705667-c81f-5e10-9c98-e54175df4421 | textbox | SPECIFICATION AND CLAUSE:
d0a82306-b2c5-52a0-81e8-752c2e2fb6f6 | textbox | HOLD POINT DESCRIPTION:
f0929f36-cd94-54a0-a396-218479b01a07 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Topsoil Stockpiling
| checkpoint | VERIFICATION
3defa3c5-f878-5280-9518-88c8a1fe9a85 | note | Requirements / Reference - R44 CL2.3.4 R44 CL2.6 R44 1.6 R44/A A2.1 G71
78bffb0e-a879-59b0-96c8-00ada6a608bd | note | Acceptance Criteria - Locate stockpiles at areas nominated by the drawings or specifications and in accordance with Roads and Maritime (2015) Stockpile Site Management Guideline. Note that Dubbo Regional Council Waste Facility cannot accept Nickel contaminated materials. | Acceptance Criteria - Locate stockpiles at areas nominated by the drawings or specifications and in accordance with Roads and Maritime (2015) Stockpile Site Management Guideline. Note that Dubbo Regional Council Waste Facility cannot accept Nickel contaminated materials.
f1fad0d7-7f24-534b-85dd-527f083d9ab0 | note | Surface joint survey to be carried out at each topsoil stockpile location before start stockpiling with the client.
ecc20337-384c-5a45-bda5-d7fc446cff86 | note | Topsoil stockpiles must:
47e2b0c1-69d5-5464-a824-60b6d9350de9 | note | Be free from weeds, subsoil, other excavated materials, contaminated materials, refuse, clay lumps and stones, timber or other rubbish. | Be free from weeds, subsoil, other excavated materials, contaminated materials, refuse, clay lumps and stones, timber or other rubbish.
02c709a1-cff2-565d-b534-9e16858044bf | note | Be trimmed to a height not exceeding 2m and batter slope ≥ 2H: 1V.
0df65f10-1e60-5f17-bf39-8cc0e0d920f2 | note | Have batters track rolled or stabilised by other means acceptable to the Principal
f2e52589-b0fc-5952-b8e1-ee9fd919ca7b | note | Be seeded with a sterile cover crop in accordance with R178. Seeding to be carried out progressively within seven days of completion of each 500 m2 of exposed batter face | Be seeded with a sterile cover crop in accordance with R178. Seeding to be carried out progressively within seven days of completion of each 500 m2 of exposed batter face
0cf66542-458e-56c3-93a5-3839b98a74b0 | note | Be less than 1000m3 each
20ea9e91-a7c6-5128-a3a6-c9ca8a6328d5 | note | Comments / Attachments / Records - NOTE: ALL TOPSOIL TO BE SPOILED AND DISPOSED OF AT A LICENCED RECEIVING FACILITY OR AT ANOTHER TFNSW PROJECT | Comments / Attachments / Records - NOTE: ALL TOPSOIL TO BE SPOILED AND DISPOSED OF AT A LICENCED RECEIVING FACILITY OR AT ANOTHER TFNSW PROJECT
| section | 9 - Survey after Removal of Topsoil
| checkpoint | HOLD POINT
64f1ac37-0580-5427-bc3d-5ec08526e2bf | note | Requirements / Reference - R44 CL2.3.5 R44/A A1 G71 CL 2.10.2 G71 Cl 2.10.1
55c5e012-b36f-5042-943c-1815e6731bd7 | note | Acceptance Criteria - Determine surface levels in each cutting and embankment at sufficient locations after removing topsoil to determine volume of excavation for general earthworks and the volume of unsuitable material | Acceptance Criteria - Determine surface levels in each cutting and embankment at sufficient locations after removing topsoil to determine volume of excavation for general earthworks and the volume of unsuitable material
260db45a-b8e5-53c6-9bd8-b37b3e7ba02c | note | HOLD POINT
d40270de-8840-59cc-8d1a-e27eb6acca3d | note | Submit a completed Survey Report of the existing surface levels, and a notification that the position and extent of all cuttings and embankments shown on the Drawings, and any cut/fill transitions, using pegs and batter profiles or equivalent, prior to commencement of construction. | Submit a completed Survey Report of the existing surface levels, and a notification that the position and extent of all cuttings and embankments shown on the Drawings, and any cut/fill transitions, using pegs and batter profiles or equivalent, prior to commencement of construction.
cb5ff824-f6dc-538b-a26a-35fffa28586e | note | Joint survey for surface at each topsoil stockpile location before commencing stockpiling and Surface after stripping of topsoil.
3b1ea499-590f-524e-b562-c82c898275a0 | textbox | HOLD POINT NUMBER:
cf2aac28-b96c-547b-a0f7-4a4e9414b9b0 | textbox | DATE SUBMITTED:
b7822a52-fccb-5ccd-ba82-aa20c28b2529 | textbox | Work Start Date:
bf42557a-3cb2-548c-87d4-402d87acb6ce | textbox | SUBMITTED BY:
68c3a698-660b-5811-8604-7bed4ebbc2cc | textbox | SPECIFICATION AND CLAUSE:
5c12bd8c-43d2-584b-ba87-4428a1928cbb | textbox | HOLD POINT DESCRIPTION:
2be8acd0-b477-5a9e-ac1c-76f1ab45b831 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 10 - Unsuitable Material
| checkpoint | HOLD POINT
baf04654-8c16-5c0c-a97d-8f6e2c5ae8aa | note | Requirements / Reference - R44 CL1.6 R44 CL2.4.1 R44 CL.2.4.5 R44/A A1 TfNSW G71
aa38a976-6249-5f6c-98f6-782577725a5a | note | Acceptance Criteria - After stripping, earthworks processes are held to allow inspection by Geotechnical engineer initially and then by the Principal. Where unsuitable material is found, Geotechnical engineer must assess the extent of unsuitable material and make that assessment report available to the Principal including any supporting information. The Principal will consider the assessment and instruct you regarding the requirement for any removal of unsuitable material. | Acceptance Criteria - After stripping, earthworks processes are held to allow inspection by Geotechnical engineer initially and then by the Principal. Where unsuitable material is found, Geotechnical engineer must assess the extent of unsuitable material and make that assessment report available to the Principal including any supporting information. The Principal will consider the assessment and instruct you regarding the requirement for any removal of unsuitable material.
f151d3ae-a2e0-5d9b-b05e-45e25434cb77 | note | Where unsuitable material is found, such unsuitable material must be excavated to the extent directed by the Principal
5763f10e-c677-58ba-a885-1b941fdb88ed | note | HOLD POINT
4801847d-0481-5daa-8833-d6e1601d7788 | note | Notification that unsuitable material has been removed as directed
1bca2a5e-f33f-5de1-af44-c5ac37d50ab2 | note | Joint survey before and after removal of unsuitable material, survey in accordance with Specification TfNSW G71 to determine the surface levels at sufficient locations to later determine the volume of unsuitable material removed. | Joint survey before and after removal of unsuitable material, survey in accordance with Specification TfNSW G71 to determine the surface levels at sufficient locations to later determine the volume of unsuitable material removed.
ddc32063-1d36-5975-9ce0-685d264a4557 | note | Prior to releasing the Hold Point, the Principal will inspect the excavation and may direct removal of further material as unsuitable material prior to authorising the release of the Hold Point | Prior to releasing the Hold Point, the Principal will inspect the excavation and may direct removal of further material as unsuitable material prior to authorising the release of the Hold Point
a651d861-76be-533c-9c2a-3a16ba31ac79 | note | Comments / Attachments / Records - Only applicable if unsuitable material is found, otherwise not applicable
3c7290f7-29b3-58e9-bd60-2b5d1346b3c3 | textbox | HOLD POINT NUMBER:
010c6878-59a8-5921-aa4f-2a082cc5cea2 | textbox | DATE SUBMITTED:
cb702dc0-004e-505b-afca-7d32d8b6f74b | textbox | Work Start Date:
6f343437-1fe9-514f-a314-634aceae71c4 | textbox | SUBMITTED BY:
b2c8ce19-d57f-5f7d-b658-6bb52724b21d | textbox | SPECIFICATION AND CLAUSE:
3a4cfd86-8f09-5638-ab67-c0ea9c64aa5e | textbox | HOLD POINT DESCRIPTION:
2c9bf528-6850-5bbf-9e28-7bbd5b10b656 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - ACM – On-Site Encapsulation Plan
| checkpoint | HOLD POINT
d8af0ead-edd2-57ff-99f1-99484b633478 | note | Requirements / Reference - R44 Cl 2.5.2.1
46cdffeb-028c-5d5d-8c81-68ae93d30623 | note | Acceptance Criteria - HOLD POINT: On-Site Encapsulation of Asbestos Contaminated Material
af7e3784-4c7a-5ec3-a59e-4a015057588a | note | Submit an Asbestos Management Sub-Plan (AMSP), including the Remediation Action Plan and details of proposed encapsulation and proposed locations at least 4 weeks prior to on-site encapsulation of ACM. | Submit an Asbestos Management Sub-Plan (AMSP), including the Remediation Action Plan and details of proposed encapsulation and proposed locations at least 4 weeks prior to on-site encapsulation of ACM.
1ebe1728-8329-5931-975c-7ee427f2d37c | textbox | HOLD POINT NUMBER:
39dfdcdb-8881-5ae2-8654-8cf8dd32edbe | textbox | DATE SUBMITTED:
9d4f465c-d3e8-51cb-8637-d0c3e59179df | textbox | Work Start Date:
a39666b0-139a-5cbc-835a-12b025859024 | textbox | SUBMITTED BY:
3c608e1e-878b-5570-8d1f-a19e6a0493cc | textbox | SPECIFICATION AND CLAUSE:
8001105d-5aed-52ef-b707-f79598fddb65 | textbox | HOLD POINT DESCRIPTION:
21c4bf14-1619-5e1a-ac8c-4364ece4ceec | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 12 - ACM – Excavation of ACM
| checkpoint | HOLD POINT
ff51fc5b-8ff0-5c32-a169-3766043d8e18 | note | Requirements / Reference - R44 Cl 2.5.2.1
3ac81975-f3db-5ce2-91c5-d512bb5cc90f | note | Acceptance Criteria - HOLD POINT: Excavation of Asbestos Contaminated Material
7e102296-97eb-5887-8eec-1b7492d38829 | note | At least 24 hours prior to excavation, submit details of: each proposed location and method of encapsulation, air monitoring and dust suppression methodology for management and treatment of ACM, if a borrow pit option is proposed, submit a report from the hydrogeologist confirming and certifying the suitability of the locations and the design and drainage system(s) required | At least 24 hours prior to excavation, submit details of: each proposed location and method of encapsulation, air monitoring and dust suppression methodology for management and treatment of ACM, if a borrow pit option is proposed, submit a report from the hydrogeologist confirming and certifying the suitability of the locations and the design and drainage system(s) required
| section | 13 - Contractor Arranged Borrow Areas
| checkpoint | VERIFICATION
82430a81-9168-5ebe-b6bd-e7ffc283bbf7 | note | Requirements / Reference - R44 2.7.3
61f6cc9d-6804-5f4c-b2e7-d8d86656535a | note | Acceptance Criteria - Provide copies of all approvals and consents to Principal at least 5 working days prior to commencing work at these borrow areas. | Acceptance Criteria - Provide copies of all approvals and consents to Principal at least 5 working days prior to commencing work at these borrow areas.
c3b37786-8389-59ab-9a89-fa35bd0952d4 | textbox | HOLD POINT NUMBER:
2fb74959-f70f-5f6c-a091-cd8f315544db | textbox | DATE SUBMITTED:
7657e309-8692-5205-ab4f-1e765a3ebc31 | textbox | Work Start Date:
f25a59ba-dd24-57d6-bdd1-9c19a1be6ded | textbox | SUBMITTED BY:
dad4b0da-1b7b-5f44-bfd9-5bd89e14e360 | textbox | SPECIFICATION AND CLAUSE:
f32f0498-34eb-5f03-a608-9a58ac44351c | textbox | HOLD POINT DESCRIPTION:
aebbe3b8-fbe7-5b8b-9a81-3a7cd9d1f59d | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 14 - Foundation Treatments – Embankment and Cutting
| checkpoint | HOLD POINT
df9569bc-4542-5067-98f3-f1916a1838bc | note | Requirements / Reference - R44 CL3.1 R44 CL3.2 R44 CL3.3 R44 Cl 3.4
01a6c84e-4a9e-5071-b65b-06edc84ac72c | note | Acceptance Criteria - After preparation of the foundation area, present the area for inspection by the principal prior to placing pavement materials | Acceptance Criteria - After preparation of the foundation area, present the area for inspection by the principal prior to placing pavement materials
e6e5564e-2d4b-52f8-8686-589b4fc415e7 | note | Geotechnical engineer to assess the required test method or methods, organise tests and carry out inspections of all foundations and confirm and or/ assess which foundation treatments and their extents are required. Provide the results of all tests and assessments and the proposed foundation treatments to the Principal, issued as a Hold Point. | Geotechnical engineer to assess the required test method or methods, organise tests and carry out inspections of all foundations and confirm and or/ assess which foundation treatments and their extents are required. Provide the results of all tests and assessments and the proposed foundation treatments to the Principal, issued as a Hold Point.
2ace26b0-e30b-5cfa-b25e-a0b175dfe1d5 | note | SUBMIT HOLD POINT FOR EITHER EMBANKMENTS OR CUTTINGS, SUBJECT TO RELATIVE HEIGHT OF EXISTING SURFACE VS DESIGN HEIGHTS | SUBMIT HOLD POINT FOR EITHER EMBANKMENTS OR CUTTINGS, SUBJECT TO RELATIVE HEIGHT OF EXISTING SURFACE VS DESIGN HEIGHTS
f01dd7f3-5ebc-5794-b352-a7d04c723848 | note | HOLD POINT (EMBANKMENTS / CLAUSE 3.2)
0405c9af-de0a-575f-a29e-1434a1d2b59d | note | Submission of:
27b33816-33fb-55e8-9b16-10470b939eed | note | Survey report,
d9c51086-d489-590d-aee3-d7be5d254621 | note | Notification of completion of clearing operations;
c7b9c679-92b8-540e-8f89-3a1fd8e39726 | note | In areas other than beneath Shallow Embankments, notification that:
6e648b08-ee46-51e2-8e0b-59197b8c065b | note | topsoil has been removed in accordance with Cl 2.3; or
bd038549-2c1a-5cd8-b4cf-c0e19d1fd150 | note | grasses have been flattened/mowed if shown on the Drawings or specified;
241aeb9a-48da-5237-a264-8da915739894 | note | In areas beneath Shallow Embankments:
d2d1520a-a022-5ec8-9dd6-dcb65381418a | note | notification that topsoil has been removed and surface excavated in accordance with Cl 3.5.1; and
af2dd615-6ba8-5814-bdd0-ba7768d033f0 | note | CBR (10 days), CBR (swell) and PI test results, required if in accordance with Cl 3.5.1
87a4f4e7-fd48-55ac-95c5-956bd7e9a1d6 | note | Details of tests, inspections, assessment and any recommended foundation treatment(s) and extents proposed by Geotechnical Engineer | Details of tests, inspections, assessment and any recommended foundation treatment(s) and extents proposed by Geotechnical Engineer
84a9e72a-e421-5db9-b1a9-74de551ee733 | note | HOLD POINT (CUTTINGS / CLAUSE 3.4)
faafa69d-4e72-521c-a166-17828352be5a | note | Submission of:
6bc79461-0b69-58b3-b993-d0231bdc3ed5 | note | Notification of completion of excavation to:
9df23386-f63a-5c57-b730-620e4205edc1 | note | Designed Floor Level, or Foundation Level, as appropriate; and
fb880fc8-11f2-56c2-bde4-f40b515b3084 | note | Depth specified for Cut / Fill Transition Zone (refer to Clause 3.5)
01619ca1-2443-5f6c-8c8c-f548b1d1a9ed | note | CBR (10 days), CBR (swell) and PI test results
b698a744-eff2-5f08-8cf5-a931abab6c1b | note | Details of tests, inspections, assessment and any recommended foundation treatment(s) and extents proposed by Geotechnical Engineer | Details of tests, inspections, assessment and any recommended foundation treatment(s) and extents proposed by Geotechnical Engineer
42a29f7a-b6c3-5c54-8ad9-32b417b3123d | note | (The submission must be concurrent with the submission for any adjoining Shallow Embankment foundation required by the Hold Point in Clause 3.2) | (The submission must be concurrent with the submission for any adjoining Shallow Embankment foundation required by the Hold Point in Clause 3.2)
edf7ee46-840b-5af9-a231-bf17fef1bc05 | textbox | HOLD POINT NUMBER:
8c788e6b-7875-54f5-9220-94530260ca62 | textbox | DATE SUBMITTED:
e085e035-dd4d-5412-a534-a454d987605b | textbox | Work Start Date:
1542be27-6a2b-500f-a3ca-60d12f1006f6 | textbox | SUBMITTED BY:
b8659260-3d81-59ac-8d23-bf67a8e7a78c | textbox | SPECIFICATION AND CLAUSE:
188a0154-0353-5bfa-9b04-1cbf67d4ef58 | textbox | HOLD POINT DESCRIPTION:
ebe98114-4410-5697-aa6c-029f6ba7f562 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 15 - Cuttings in Rock
| checkpoint | HOLD POINT
dd9cfa9b-60bb-5346-baf7-49d17450baea | note | Requirements / Reference - R44 CL 4.2.
670f8ce7-d932-59cc-a8d8-1d775b1e77de | note | Acceptance Criteria - Clean cut batters in rock with slopes > 1H:1V with compressed air when excavation to the level of each bench is complete. The Principal is to assess the batter’s stability when all loose, unstable materials are removed and joints are exposed. | Acceptance Criteria - Clean cut batters in rock with slopes > 1H:1V with compressed air when excavation to the level of each bench is complete. The Principal is to assess the batter’s stability when all loose, unstable materials are removed and joints are exposed.
007c3f1b-e737-5a80-ad51-39a8ce8033ee | note | Geotechnical Engineer is to undertake inspections and arrange any required tests of all cleaned batter and bench/floor surfaces, as well as assess their stability and recommend treatments for the Principal’s approval. | Geotechnical Engineer is to undertake inspections and arrange any required tests of all cleaned batter and bench/floor surfaces, as well as assess their stability and recommend treatments for the Principal’s approval.
6521005b-cfd8-5489-91ff-ed4ec4bfc681 | note | HOLD POINT
ac22141c-8845-5302-869e-888c496d4461 | note | Present the clean batter/ bench and associated assessment and any alternate proposals by Geotechnical Engineer for geotechnical inspection and consideration of proposals by the Principal, before excavation below bench level for slopes > 1H: 1V can proceed. | Present the clean batter/ bench and associated assessment and any alternate proposals by Geotechnical Engineer for geotechnical inspection and consideration of proposals by the Principal, before excavation below bench level for slopes > 1H: 1V can proceed.
b473b99c-4a81-5154-920f-2883778ddabc | textbox | HOLD POINT NUMBER:
1c654e20-e1d3-5eeb-a1e0-79aa3cbb57d2 | textbox | DATE SUBMITTED:
a08c301b-ee90-5beb-948d-e1626c49dfcb | textbox | Work Start Date:
a84ac891-9291-520f-ba70-2b12aa543744 | textbox | SUBMITTED BY:
b2ec364c-7858-58ec-b70e-1cf222d4ed1a | textbox | SPECIFICATION AND CLAUSE:
7289e6fd-41d4-5e80-9dcf-9b707fb0d2fc | textbox | HOLD POINT DESCRIPTION:
34bcc471-3c08-55b2-82f9-6959fe270ab3 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 16 - Batter Tolerances in Cuttings
| checkpoint | VERIFICATION
42ff7d0e-8900-5775-9aa0-b752efca5938 | note | Requirements / Reference - R44 CL4.3.
| section | 17 - Embankment Batter Tolerances
| checkpoint | VERIFICATION
5e3fcb55-b7e7-510f-9767-647b74e97a07 | note | Requirements / Reference - R44 CL 5.4 Table R44.8
| section | 18 - Delivery of Site Won and Imported Material for Upper Zone of Formation Material - UZF
| checkpoint | HOLD POINT
32fa1722-b328-5e86-8066-ac5bb5364aa7 | note | Requirements / Reference - R44 6.1.1
9beaa2dd-1778-5abd-80d0-f55dd6b7bc66 | note | Acceptance Criteria - HOLD POINT
a0ed7d11-2dd9-56f8-a0d3-b7956d26a2ca | note | Submission of proposed source locations, quantities and type of material and verification of conformity
1697093b-982b-5aa3-9ee3-4f2b56e0a770 | note | If imported, verification that all possible sources and stockpiles of material have been exhausted.
b29e36e9-1396-5443-bb6b-930a2d40f392 | note | Before placing imported upper zone material in any formation, carry out a survey in accordance with TfNSW G71 to determine the surface levels at sufficient locations to later determine the volume of compacted imported material placed in the works. | Before placing imported upper zone material in any formation, carry out a survey in accordance with TfNSW G71 to determine the surface levels at sufficient locations to later determine the volume of compacted imported material placed in the works.
7b70a387-ec3f-5cb4-9428-7c29b021a32d | textbox | HOLD POINT NUMBER:
dfae49a8-66df-53b5-9ebb-2bd1327e6800 | textbox | DATE SUBMITTED:
1d9e6e97-2f19-54c1-b22f-6a2a8ad6e853 | textbox | Work Start Date:
1c441ce3-ffd1-5e07-9fe1-0602ef7ed327 | textbox | SUBMITTED BY:
74db0681-75f6-5ef6-a10b-f88343b8429d | textbox | SPECIFICATION AND CLAUSE:
e1741388-3dec-5970-9887-449afe21f359 | textbox | HOLD POINT DESCRIPTION:
4163cae0-ba5a-5d33-883a-adbeaef2f99b | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 19 - Delivery of Site Won and Imported Material for verges
| checkpoint | HOLD POINT
5570d449-2160-5dc3-a3cc-3aa8210c93db | note | Requirements / Reference - R44 6.2
58dc4b05-3cfa-509b-adaf-ccccf075a34b | note | Acceptance Criteria - HOLD POINT
cab3acc9-b4e0-5c80-9c77-1ffbcad72743 | note | Submission of proposed source locations, quantities and type of material and verification of conformity
99097e13-f95e-5650-97a1-5e37d1cdad22 | note | If imported, verification that all possible sources and stockpiles of material have been exhausted.
b05add58-be56-5581-b67f-094a8d051a25 | textbox | HOLD POINT NUMBER:
f0161730-f80e-5b82-ba57-e85b08b40db6 | textbox | DATE SUBMITTED:
059d28d1-38b8-5898-9a8b-8e666190118e | textbox | Work Start Date:
20e3103d-3832-597d-a8c0-badcf8da297d | textbox | SUBMITTED BY:
433a1b7c-f47b-5e9b-a844-a7faefae4259 | textbox | SPECIFICATION AND CLAUSE:
c13fa626-6cc9-565f-867b-f6286aa1acf4 | textbox | HOLD POINT DESCRIPTION:
d172d276-3ac4-50b0-b29a-6337e67ac1e4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 20 - Relative Compaction Conformity Criteria
| checkpoint | VERIFICATION
9aa977fc-6ea6-5a86-bc21-7f5e02997a37 | note | Requirements / Reference - Table R44.10 R44 A5 TfNSW Q6 CL L3.1
1a9d2032-f2b1-590d-ae04-c2a5fc19598c | note | Acceptance Criteria - All compaction testing for the aforementioned layers in accordance with TfNSW Q6 Specification.
7d65e25b-31e6-540a-b610-e08b38bdf004 | note | Minimum Testing Frequency CL L3.1
e7884af5-5266-5414-baf6-d2f70bb6617a | note | Rel. Compaction (%)
7389d657-3c12-52d3-a78b-22acd2f1e076 | note | Layers replacing unsuitable material. 95.0
6e183169-9fb8-5de5-9a88-fa2b7d7e96c4 | note | Material layers placed up to underside of SMZ (incl. Shallow Embank., Cut/Fill Transition) Entire area on the floor of cuttings 98.0
8a9b16a4-58b0-56bf-9d25-74d997d85e54 | note | Moisture Content: All Earthworks Materials = 60 - 90 %
351a2011-4164-53de-9b64-a14cd6f430b4 | note | Comments / Attachments / Records - Compaction test results
| section | 21 - Construction of each trial section of rock fill
| checkpoint | WITNESS POINT
ba8d7841-48da-510c-94c0-abfda524c4d8 | note | Requirements / Reference - R44 CL 7.5
796809ac-6648-5052-8642-8539b17f1605 | note | Acceptance Criteria - WITNESS POINT: Construction of each trial section of rock fill
6dd8b43d-e3f4-5475-8f69-49c983efb169 | note | Notification of the place, date and time of construction of the trial section, at least 3 working days prior to commencement, with details i) to vi) | Notification of the place, date and time of construction of the trial section, at least 3 working days prior to commencement, with details i) to vi)
081eb5da-c467-524a-972f-fd2c1406522f | textbox | WITNESS POINT NUMBER:
3c7b4947-7d6a-5853-9487-30d09b2e0cb8 | textbox | DATE SUBMITTED:
f529a6b8-ff10-55b2-a36a-b31a96645382 | textbox | Work Start Date:
746f6074-a7bc-5f7c-a785-ebccb2cba70d | textbox | SUBMITTED BY:
a37ba18a-d7bd-5e50-823f-21b0f18b1f67 | textbox | SPECIFICATION AND CLAUSE:
35d72185-1a25-5b6b-bc7c-3d0e22654b32 | textbox | WITNESS POINT DESCRIPTION:
2b1adc73-b937-5023-85b0-64404808f48a | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 22 - Construction of remaining section of rock fill
| checkpoint | HOLD POINT
1377baca-9955-58df-b1f9-eaef5ea882e7 | note | Requirements / Reference - R44 CL 7.5
d3db964a-2558-53d9-b150-980cdd7c5f2e | note | Acceptance Criteria - HOLD POINT: Construction of remaining sections of rock fill
9847b391-161a-5469-bcd8-ff0f7109c892 | note | Verification, including test results, of conformity of each trial section including details of the proposed compaction procedure, any test results and survey reports. | Verification, including test results, of conformity of each trial section including details of the proposed compaction procedure, any test results and survey reports.
fb73c612-970a-52ee-9f75-912ce27c3d2c | textbox | HOLD POINT NUMBER:
302e8b89-3cec-5614-ba81-06370dc9603a | textbox | DATE SUBMITTED:
6603f39b-0cb8-558e-80ef-16e68ee1d213 | textbox | Work Start Date:
c8aab57a-5a46-54b7-98df-993800b7ba92 | textbox | SUBMITTED BY:
43891e03-f58d-5383-b500-2c064deb5399 | textbox | SPECIFICATION AND CLAUSE:
46a3e157-7835-5ec2-a66f-c4d694ca757c | textbox | HOLD POINT DESCRIPTION:
62f5f9e3-706d-5fd5-ab7c-56d57178e6fb | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 23 - Deflection Testing – Proof Rolling
| checkpoint | WITNESS POINT
41df309f-afeb-5603-95c4-e678014fd858 | note | Requirements / Reference - R44 CL 7.6.1 R44 A4/A4
0024e444-7c8c-58fb-ade4-74ab958d15c3 | note | Acceptance Criteria - WITNESS POINT:
04ebb314-cdf3-5566-b949-c5b5dc148291 | note | All surfaces within 1.5m of underside of SMZ must be capable of withstanding proof rolling
24fa0a7e-0a14-590e-801f-dbc3a287143c | note | Carry out proof rolling in accordance with Test Method TfNSW T198 of embankment lots and other surfaces within 1.5m of the underside of the Selected Material Zone. | Carry out proof rolling in accordance with Test Method TfNSW T198 of embankment lots and other surfaces within 1.5m of the underside of the Selected Material Zone.
e3fd69a6-e679-56d8-a176-116b8d3f1f21 | note | All proof rolling is to be carried out under the supervision of the contractor’s Geotechnical Engineer who must also provide written verification of compliance, or recommendations for other action as required | All proof rolling is to be carried out under the supervision of the contractor’s Geotechnical Engineer who must also provide written verification of compliance, or recommendations for other action as required
2a7daa3d-3a9b-53e2-92fc-6328c1849985 | note | The tests must not exhibit visible deformation, rutting, or yielding and/or show signs of distress of instability
4068aaf6-405c-5d28-85fe-f6edf9f2a9b8 | note | In the event of a failed proof roll, rework or recompact the affected area prior to reinspection. Rework the foundation of the lot if reworking is unsuccessful. | In the event of a failed proof roll, rework or recompact the affected area prior to reinspection. Rework the foundation of the lot if reworking is unsuccessful.
b3047d53-5e92-5958-b1de-9dde48e4f96e | note | Carry out proof rolling of all lots affected by rain or lots which have exceeded 7 days since last proof rolling, including any lots which have previously been proof rolled. | Carry out proof rolling of all lots affected by rain or lots which have exceeded 7 days since last proof rolling, including any lots which have previously been proof rolled.
54dd6aba-0d66-521a-ae42-59cc966c497d | textbox | WITNESS POINT NUMBER:
3e786f90-f03b-5e98-b3ad-50757db8d158 | textbox | DATE SUBMITTED:
a7e6c0ca-718c-592b-9ec8-cab95864c350 | textbox | Work Start Date:
87db6dd2-2b5e-5231-b9d5-244a3bac458f | textbox | SUBMITTED BY:
e54dca61-8265-5055-a2d2-c0e3fb74d9a8 | textbox | SPECIFICATION AND CLAUSE:
512e0909-1fae-5814-9acc-dbc1b98b0d78 | textbox | WITNESS POINT DESCRIPTION:
de6863d2-790a-5031-a9a3-3840ce86575b | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 24 - Benkelman Beam
| checkpoint | WITNESS POINT
a24efb18-5a8e-58b4-9028-6b884319a8a0 | note | Requirements / Reference - R44 CL 7.6.2 R44 A4/A4
335bfea6-bcc4-5d1b-ba4d-5df09b3426ee | note | Acceptance Criteria - Where specified in Annexure R44/A4, conduct deflection testing using the Benkelman Beam in accordance with Test Method TfNSW T199. | Acceptance Criteria - Where specified in Annexure R44/A4, conduct deflection testing using the Benkelman Beam in accordance with Test Method TfNSW T199.
6fe05c35-d190-5930-ba99-eafc4ca044cf | note | Underside of SMZ
7be54bb8-aae8-5e2d-abe9-123974ec7863 | note | Top of SMZ
5d40be21-51c2-5f04-936b-919af850c15b | note | Where no SMZ is specified, conduct Benkelman Beam testing of the formation at the level of the underside of pavement
46c58b40-f1c0-5d51-bb37-11a31d79e90b | note | Carry out deflection testing by Benkelman Beam within 3 days of taking samples for compaction testing and moisture conformity testing of the material, or such longer period as approved by the Principal due to adverse weather conditions | Carry out deflection testing by Benkelman Beam within 3 days of taking samples for compaction testing and moisture conformity testing of the material, or such longer period as approved by the Principal due to adverse weather conditions
6ad9e828-1a9d-5c3a-8d7d-33def6d5fad8 | note | All Benkelman Beam testing is to be carried out under the supervision of the contractor’s Geotechnical Engineer who must also provide written verification of compliance, or recommendations for other action as required | All Benkelman Beam testing is to be carried out under the supervision of the contractor’s Geotechnical Engineer who must also provide written verification of compliance, or recommendations for other action as required
13b8c3f0-eb9e-5b53-a567-739587d1140c | note | In the event of a failed Benkelman Beam, confirm next steps with Geotechnical Engineer prior to making any changes to the lot being tested | In the event of a failed Benkelman Beam, confirm next steps with Geotechnical Engineer prior to making any changes to the lot being tested
49a76b10-9a23-5eb8-b050-0e78fc435f33 | note | WITNESS POINT: Notification to the Principal of the time, date and location of Benkelman Beam testing and results.
ba3daafe-4641-51b5-9156-9c1008e6fdb5 | note | Comments / Attachments / Records - Where specified in Annexure R44/A4
3636939f-37e2-5f0d-8bcc-c98cc09f7175 | textbox | WITNESS POINT NUMBER:
5bba4733-c2f7-50c1-9c81-d2c056212f5d | textbox | DATE SUBMITTED:
32da94b3-c46a-552e-9cb1-98a7d8b1e9c3 | textbox | Work Start Date:
e7596db9-05d3-5749-ae3d-27c7f18a3de9 | textbox | SUBMITTED BY:
5eb8aa49-5eca-50e0-b6a8-682588a79372 | textbox | SPECIFICATION AND CLAUSE:
f7a1cf09-6443-54ad-9e19-96dac5ba926d | textbox | WITNESS POINT DESCRIPTION:
3c150dba-8910-516a-bfa8-2395c4534467 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 25 - Finalising Layer Prior to Placing SMZ
| checkpoint | HOLD POINT
e7582417-52a4-5437-9fc5-973e8bcb9693 | note | Requirements / Reference - R44 7.6.2
6677333d-2417-532b-99de-77894fb87b08 | note | Acceptance Criteria - HOLD POINT: Placing each Lot of SMZ, or each Lot of pavement where there is no Selected Material Zone.
802488bc-3e8b-59df-bede-2ed6c4e94ba4 | note | Submit deflection test results, Survey Report of the finished surface and verification of conformity of each lot of formation.
26192372-a2e5-5682-bf97-037c22c197db | textbox | HOLD POINT NUMBER:
53bbd87b-6b3f-591c-b16a-97da0df1ebfd | textbox | DATE SUBMITTED:
8f7761b2-6a02-5823-8ef6-e8558c453790 | textbox | Work Start Date:
335df508-01b7-5466-a5b7-5765bc5a8294 | textbox | SUBMITTED BY:
c4ed7358-db16-5d55-8000-d895cec3770e | textbox | SPECIFICATION AND CLAUSE:
6af2f0d4-39c5-516b-bd52-68e48b502bfe | textbox | HOLD POINT DESCRIPTION:
68720880-c253-5d2f-b4bb-8996d3ff1c3d | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 26 - Level Control (Subgrade survey conformance)
| checkpoint | VERIFICATION
300a1dba-acd7-5e5e-9a16-f0f41a3f922b | note | Requirements / Reference - R44 CL 7.7 Table R44.11
b5f5567b-2b93-5e18-97ba-395f1d9bc5ea | note | Acceptance Criteria - Where SMZ is be sealed, conform SMZ thickness , surface levels and surface deviation in according with TfNSW R71 clauses 8.5 (b), 8.6 ( b) and 8.7 respectively. | Acceptance Criteria - Where SMZ is be sealed, conform SMZ thickness , surface levels and surface deviation in according with TfNSW R71 clauses 8.5 (b), 8.6 ( b) and 8.7 respectively.
c22b8043-98e4-585d-bd04-110fcb5cd50b | note | Ensure conformance of the finished surface levels of the floors of transitions, earthworks layers and zones, and verges are within the Tolerances specified: | Ensure conformance of the finished surface levels of the floors of transitions, earthworks layers and zones, and verges are within the Tolerances specified:
| section | Lot Verification
| checkpoint | Lot Verification complete
439b9369-105e-59c7-ab41-367161ce9d4a | textbox | Lot Verified By:
beec54d4-db55-59f9-a07b-b7df75f57a90 | textbox | Lot Closed Date:
e3058f13-7004-5859-8cac-b07c2a95ad19 | button | Submitted to Client | Yes, No, N/A
36081959-bd94-5637-b406-4d1df2c3b759 | button | Reviewed by Client | Yes, No, N/A
e4284e42-7852-55bd-86ac-fb6a28608531 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 06 - R44 Earthworks Select Material Zone (SMZ) Rev 0 |  | ITC 06 - R44 Earthworks Select Material Zone (SMZ) Rev 0 | e541a305-ce2d-47ee-837e-6a59e69f429c
| section | Lot Information
| checkpoint | Lot Information complete
aec00fef-f6a7-5be8-87ae-ec1cca60531f | textbox | Lot Opened On
eeedc736-0f9e-52f2-ab72-dab50ab33167 | textbox | Date of Works
36d321dd-fd82-5eb7-a827-091620cc42fc | textbox | Lot Type
c688a72d-71e3-52f2-a012-c87cc399ebd3 | textbox | Start Chainage
f8a79196-9837-5ff2-b245-8533d0086be8 | textbox | End Chainage
53a763ae-ad1c-5a27-a76c-64991726b68f | textbox | Offset
99b518bf-4c36-5bad-afe8-1284b86a84a9 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
897d41b4-f73a-57e8-82ba-637ea71f3b6c | note | Requirements / Reference - Project Safety Plan
c7f01a2e-3da8-5d81-9548-173f3f7010ec | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
8a6f8996-8d05-5ee7-9991-fbef2b12108c | note | Required Safe Work Method Statements completed and signed
4c8bce9a-379b-5b03-af96-1b63b38ed763 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
364564d1-318c-5370-ae60-bc5bf7131e3c | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
a3a99165-1dbf-55b7-a55d-3cc99ef9ebc4 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38 | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
1d0a7f27-ef4d-5c29-b9b0-3ce86c67c4f9 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Site Won Selected Material
| checkpoint | VERIFICATION
c7454dcb-690d-57ab-b409-cdda0170e23c | note | Requirements / Reference - R44 Cl 2.8.5.2 R44 Cl 6.1.2 R44 A2.2 RMS 3051 RMS 3071- Clause 5.1
781da082-af82-52fc-a049-66a9a6d40256 | note | Acceptance Criteria - Material is the same source in both layers
5075000a-65f7-5b99-8cd7-127a6559ca25 | note | Any site won selected material must:
6833a195-fef7-5260-8bd8-4c86c9ab41c6 | note | Have a characteristic CBR (4 day) value of minimum 33 for the upper 150mm layer (T117 test method), for the fraction passing 19mm AS sieve | Have a characteristic CBR (4 day) value of minimum 33 for the upper 150mm layer (T117 test method), for the fraction passing 19mm AS sieve
68056162-d0ee-59ae-ba82-ff0308adf15e | note | Have a characteristic CBR (4 day) value of minimum 19 for the lower 150mm layer (T117 test method), for the fraction passing 19mm AS sieve | Have a characteristic CBR (4 day) value of minimum 19 for the lower 150mm layer (T117 test method), for the fraction passing 19mm AS sieve
56850b78-4046-5449-b513-256afacc01ca | note | Have a Plasticity Index of maximum 15 (T109 test method)
817bb772-9ceb-5e91-bf8c-755d2ec6f975 | note | Be free from stone larger than 53mm maximum particle dimension
4dd92925-d09f-5125-a769-5debe589a231 | note | Have no less than 50% passing the 19mm AS sieve
| section | 4 - Imported Selected Material
| checkpoint | VERIFICATION
4fc54d60-9923-5691-9c77-9794664d7a41 | note | Requirements / Reference - R44
d4baa484-fbf5-5f5e-8701-8739a87d327b | note | Acceptance Criteria - Place and compact each layer of the SMZ with a compacted thickness not exceeding 150mm and not less than 100mm | Acceptance Criteria - Place and compact each layer of the SMZ with a compacted thickness not exceeding 150mm and not less than 100mm
a225a731-699b-5475-9171-5579d8fc1909 | note | Material is from the same source in both layers
386490ad-838f-5a05-aa9d-cfdfe6e2858e | note | Imported material to be used for the selected Material Zone must meet requirements of Specification TfNSW 3071.
de1e577f-c087-5007-b1cf-981b8ef6cbc1 | note | PI = 15 MAX
ed864f26-f78b-522e-8d5b-6a44ae0878f5 | note | CBR (upper 150 mm thick layer) = 33 min
6d057741-f18d-5520-aa83-631af8acc735 | note | CBR (lower layer) = 19 min
4dff7b21-c63d-5a1b-8135-1973066df95e | note | Particle Size Distribution as per table below
339206da-6725-56ca-b2b3-98c0a9462f87 | note | Provide Principal with details of nominated materials, together with a recent certificate verifying the material conforms to RMS 3071 | Provide Principal with details of nominated materials, together with a recent certificate verifying the material conforms to RMS 3071
7c00e040-852f-5cd1-923e-40d1d3dd7057 | note | If source of supply, method of production or type of material changes, submit details of the new nominated material and re-confirm material is suitable for use | If source of supply, method of production or type of material changes, submit details of the new nominated material and re-confirm material is suitable for use
| section | 5 - Underlying layers
| checkpoint | VERIFICATION
9625c864-eb90-5028-9c88-967b1dc309bd | note | Requirements / Reference - R44 Cl 6.1.1 TfNSW 3071 CL 7
8375eae1-384f-5eb8-84b0-176db3c80ff4 | note | Acceptance Criteria - Underlying layers beneath the SMZ layer must comply with either UZF or Construction of Heavily Bound Pavement Course ITP’s & conform to specific test requirements etc. of R44 prior to placement of SMZ Material | Acceptance Criteria - Underlying layers beneath the SMZ layer must comply with either UZF or Construction of Heavily Bound Pavement Course ITP’s & conform to specific test requirements etc. of R44 prior to placement of SMZ Material
| section | 6 - Delivery of Material
| checkpoint | HOLD POINT
c70dae70-72b4-5838-8558-521ed6bc927b | note | Requirements / Reference - R44 CL 6.1.2
3999b9b9-f29e-51fa-8395-3264a73b674a | note | Acceptance Criteria - HOLD POINT: Delivery of Material - Submission of details of location, quantities, type and verification of conformity of Upper Zone Material (including selected Material). If imported, verification that all possible onsite sources of material have been exhausted | Acceptance Criteria - HOLD POINT: Delivery of Material - Submission of details of location, quantities, type and verification of conformity of Upper Zone Material (including selected Material). If imported, verification that all possible onsite sources of material have been exhausted
3bdd9d8b-0cd4-5d95-80c7-678e5237b6ff | note | At least five working days prior delivery of material from a new certified stockpile, provide notification of intended delivery
b2fc1e6c-467f-5e12-a5e4-855e6e978b41 | textbox | HOLD POINT NUMBER:
387e480a-4e01-588e-9d3f-7ed2b0c2c0be | textbox | DATE SUBMITTED:
4e60110b-02a4-51e5-b0d8-a332b927e9ed | textbox | Work Start Date:
b05e9466-b21a-50f3-b9f6-5b4b1d8b78ca | textbox | SUBMITTED BY:
4ef8051f-47b9-5477-8fca-348294d2d109 | textbox | SPECIFICATION AND CLAUSE:
3bf40e50-b63b-52a3-9e85-62eff4b80f99 | textbox | HOLD POINT DESCRIPTION:
a8447ef6-2b9e-5790-982f-2f8a55972413 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Prior to Placement
| checkpoint | HOLD POINT
ce6fdc62-8d8e-56c5-8074-fb6241f626ef | note | Requirements / Reference - R44 Cl 6.2
18b4db33-26f0-5ee7-ab3e-1bfe8069de94 | note | Acceptance Criteria - HOLD POINT: Placement of SMZ - Prior to placement of material in SMZ, submit to Principal test reports verifying conformity of each lot of stockpiled material for use in Selected Material Zone | Acceptance Criteria - HOLD POINT: Placement of SMZ - Prior to placement of material in SMZ, submit to Principal test reports verifying conformity of each lot of stockpiled material for use in Selected Material Zone
890e2896-ae5c-5831-bbfa-d3cb7fb85906 | textbox | HOLD POINT NUMBER:
5a651b40-8a62-5b3e-976f-26c956904123 | textbox | DATE SUBMITTED:
f6faf960-c6a4-5ac1-81f5-65c4e4dd7c6d | textbox | Work Start Date:
d1f4627b-fb19-5d36-a762-ec1711501180 | textbox | SUBMITTED BY:
5d05e720-dd72-5920-a1db-c34292cefeac | textbox | SPECIFICATION AND CLAUSE:
11ba79ec-b6ec-5d0b-9b99-ab79248661b8 | textbox | HOLD POINT DESCRIPTION:
57ebe812-355d-58d0-93ce-8ff3efe599e4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Material for Verges
| checkpoint | HOLD POINT
c11e6e40-cdd2-5e62-9215-2b9af0c25a1f | note | Requirements / Reference - R44 CL 6.1.2 R44 CL 7.7.1
437b2d0c-8918-59f4-be18-a330f0ddbe74 | note | Acceptance Criteria - HOLD POINT: Delivery of site won and imported material for the verges – Submit proposed location, quantities and type of material, and verification of conformity. If imported, provide verification that all possible sources of the material within the site have been exhausted | Acceptance Criteria - HOLD POINT: Delivery of site won and imported material for the verges – Submit proposed location, quantities and type of material, and verification of conformity. If imported, provide verification that all possible sources of the material within the site have been exhausted
c4801008-1d6d-5a95-8de3-c6cee58bce45 | textbox | HOLD POINT NUMBER:
4ceb16e9-afaa-555f-bf44-2a5661501823 | textbox | DATE SUBMITTED:
d57e578a-b787-5836-a458-9eff999a2c00 | textbox | Work Start Date:
19d2fb87-0e29-5b59-964a-86df151834e9 | textbox | SUBMITTED BY:
54a838dd-6295-5ec1-8a7c-3b2b883d4bd6 | textbox | SPECIFICATION AND CLAUSE:
9ea04740-5839-561f-82c3-13e01d903d1b | textbox | HOLD POINT DESCRIPTION:
f5c876be-38bc-5be4-b8d1-41ce2e282781 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Trimming
| checkpoint | VERIFICATION
4c3c8501-64d9-5645-9c40-78a74b23a605 | note | Requirements / Reference - R44 CL 7.3 R44 CL 7.4
49cd8319-529b-59b8-b943-ee9516329a53 | note | Acceptance Criteria - Trim the selected material zone to meet tolerances shown in clause 7.7.1
a303305f-c84f-571f-a95c-ed1f95c087ca | note | Top of lower layer of SMZ - +10 mm / -40 mm
c827c35d-0533-5af3-924e-f67cbbfd6ed4 | note | Top of upper 150mm layer of SMZ, where overlaying layer is not part of contract - +0 mm / -20 mm
401700bc-7875-5c2c-88f1-d0b4521fddfa | note | Top of upper 150mm layer of SMZ, where overlaying layer is part of the contract - +0mm / -20mm
| section | 10 - Lot Conformity
| checkpoint | VERIFICATION
55ff7ccb-6aa4-5033-9228-9ba7ee4e7ce8 | note | Requirements / Reference - R44 CL 7.6.1
63eff72a-fa43-507f-9226-e8ddaf712ba9 | note | Acceptance Criteria - Determine the relative compaction in accordance with TfNSW R44 Cl7.4.
5eddb935-c3b9-563b-bfda-5414a8b0ffc8 | note | Each layer of Selected Material Zone = 102.0%
| section | 11 - Proof Rolling
| checkpoint | WITNESS POINT
f3e8ecd8-2c4e-5b0e-8087-5dc172c5631f | note | Requirements / Reference - R44 CL 7.6 R44 CL 7.6.2 R44 Annex A4
1f2a6c05-426b-5964-9542-d062d127272f | note | Acceptance Criteria - WITNESS POINT: Proof rolling of any embankment fill layer, or any other surface within 1.5m of the underside of the Selected Material Zone | Acceptance Criteria - WITNESS POINT: Proof rolling of any embankment fill layer, or any other surface within 1.5m of the underside of the Selected Material Zone
3cad8e8c-9643-5548-ba01-4914d58f104a | note | At least 1 working day prior to the proof rolling, notify the Principal and provide verification by the Geotechnical Engineer that the subject layer or surface conforms in all respects except for proof rolling | At least 1 working day prior to the proof rolling, notify the Principal and provide verification by the Geotechnical Engineer that the subject layer or surface conforms in all respects except for proof rolling
096073ee-3279-5de5-ae9a-3a9ef83cd5db | note | All proof rolling is to be carried out under the supervision of the Geotechnical Engineer, who must also provide written sign off or recommendations for further actions | All proof rolling is to be carried out under the supervision of the Geotechnical Engineer, who must also provide written sign off or recommendations for further actions
48fa912b-1ac6-52a1-8b40-82c1bce6c50d | textbox | WITNESS POINT NUMBER:
cc292fca-bfa3-5e8a-a26b-d66f109221c9 | textbox | DATE SUBMITTED:
2de5d814-d261-57d4-a9a5-72fc64828c92 | textbox | Work Start Date:
8f14fa00-a550-5f91-af87-7e52d4a8efdb | textbox | SUBMITTED BY:
a908bbb7-fff4-588e-b33b-70389f2b4689 | textbox | SPECIFICATION AND CLAUSE:
b93ea382-1869-50df-bc62-4bcbe3839d30 | textbox | WITNESS POINT DESCRIPTION:
c1b574f6-ed7b-510b-a18e-32953b3875cd | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 12 - Deflection Testing
| checkpoint | WITNESS POINT
cac6c0b7-0873-50d5-ba6f-475a1ac59524 | note | Requirements / Reference - R44 CL 6.1.2 Table R44.10
65e02d23-ac9f-5a72-ac9b-bb27d793bbd9 | note | Acceptance Criteria - Conduct deflection testing using Benkelman Beam in accordance with Test Method TfNSW T199 of the following surfaces: | Acceptance Criteria - Conduct deflection testing using Benkelman Beam in accordance with Test Method TfNSW T199 of the following surfaces:
7eedc2a8-6ef0-53fb-afd3-2dc6b2d0a95a | note | Underside of the Select Material Zone
a13b8bc7-455c-5545-80cf-58dcff9e1341 | note | Top of the Selected Material Zone
a91bcd1c-1bec-5498-bcc7-de1c9051c939 | note | Carry out testing within 3 days of taking samples for compaction testing and moisture conformity testing of the material.
1a4ef3d9-c5a1-5bc0-bc40-58ad2a9767f1 | note | Where Benkelman Beam test cannot be conducted due to insufficient space or short run length (<100m) notify Client and request approval for Proof Roll in lieu of Beam test | Where Benkelman Beam test cannot be conducted due to insufficient space or short run length (<100m) notify Client and request approval for Proof Roll in lieu of Beam test
ff234c14-0384-521c-bc38-a877d25e9072 | note | WITNESS POINT: Provide notification at least 1 day prior to proof rolling / Beam test
94b92f18-581a-562b-a75f-645a534f8227 | note | All Benkelman Beam testing is to be carried out under the supervision of the Geotechnical Engineer who must also provide written sign off of compliance or recommendations for further actions | All Benkelman Beam testing is to be carried out under the supervision of the Geotechnical Engineer who must also provide written sign off of compliance or recommendations for further actions
76a30248-1d64-5714-a894-77f5fbfe071e | note | Where characteristic deflection does not exceed 1.2mm, the standard deviation of the Lot must not exceed 0.2mm. If the required characteristic deflection exceeds 1.2mm, the coefficient of variation of the Lot must not exceed 25%. | Where characteristic deflection does not exceed 1.2mm, the standard deviation of the Lot must not exceed 0.2mm. If the required characteristic deflection exceeds 1.2mm, the coefficient of variation of the Lot must not exceed 25%.
46934f8d-243e-5e29-af53-0e810f8ca281 | note | Where these values are exceeded, re-examine the Lot boundaries, re-check the Lot for homogeneity, and subsequently re-nominate the Lot (or parts thereof) for further testing following reworking. | Where these values are exceeded, re-examine the Lot boundaries, re-check the Lot for homogeneity, and subsequently re-nominate the Lot (or parts thereof) for further testing following reworking.
25d9a11d-9569-5016-ba5c-6e5f999186ef | note | Maximum characteristic deflection
458f3094-04e0-50d9-a3b0-8b87d3f4863d | note | 1.0 mm (Top of Selected Material Zone), 1.2mm (Underside of Selected Material Zone)
5c5dbc88-df50-5a20-959c-14a4a03f5233 | textbox | WITNESS POINT NUMBER:
f48e6419-e08e-56ae-a191-bd7eb78fe786 | textbox | DATE SUBMITTED:
fcf18e06-3b7b-5837-bb95-fbd5df787830 | textbox | Work Start Date:
708a9af8-643b-579e-994d-f2aae3d79681 | textbox | SUBMITTED BY:
8035d85a-303f-519f-92e8-9a40396481fe | textbox | SPECIFICATION AND CLAUSE:
80a6940e-5d9a-5d6d-a228-252758689f52 | textbox | WITNESS POINT DESCRIPTION:
7c13c92d-4e90-547a-8072-f5925f5838c0 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 13 - Covering Each Lot
| checkpoint | HOLD POINT
af010b25-69d3-573d-88fc-31ff07a2c492 | note | Requirements / Reference - R44 CL 6.1.2 Table R44.10
f4b43ed7-23e1-5f30-aefe-defe5fce8665 | note | Acceptance Criteria - HOLD POINT: Prior to covering each lot of SMZ, submit to principal verification of conformity of each lot of SMZ placed with relevant test and survey reports. | Acceptance Criteria - HOLD POINT: Prior to covering each lot of SMZ, submit to principal verification of conformity of each lot of SMZ placed with relevant test and survey reports.
584c46de-a779-53c5-b252-a0227bb13455 | note | Test Reports include Relative Compaction, Moisture Content and Deflection Monitoring (Beam Test) Results.
506a38b4-8adf-5204-990a-60ced321d454 | textbox | HOLD POINT NUMBER:
50667949-1b98-5506-8d6c-7179ac2ab8e6 | textbox | DATE SUBMITTED:
90e18675-0f15-5b3d-9c98-d912d893d928 | textbox | Work Start Date:
e1da95dc-0d24-5630-bb26-bb87419648ba | textbox | SUBMITTED BY:
30087441-b4cb-526f-bff5-40bf1829cd32 | textbox | SPECIFICATION AND CLAUSE:
5031e042-e48b-5cf7-83b6-066a9ed7484e | textbox | HOLD POINT DESCRIPTION:
9a9371e1-5808-5440-893c-3663d627d27f | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 14 - Placing SMZ, or pavement where there is no SMZ Zone
| checkpoint | HOLD POINT
2cb7146f-d43d-5753-9019-96d521635eb1 | note | Requirements / Reference - R44 CL 7.6.2
ed87bb3f-78bd-5b82-9c6f-f96529cf5e6b | note | Acceptance Criteria - HOLD POINT: Submit deflection test results, Survey Report of the finished surface and verification of conformity of each Lot of formation | Acceptance Criteria - HOLD POINT: Submit deflection test results, Survey Report of the finished surface and verification of conformity of each Lot of formation
ad7ac779-5cf7-526b-92e2-d1d927f5e87b | textbox | HOLD POINT NUMBER:
1b6886d8-935f-5da8-9102-846783bd88e7 | textbox | DATE SUBMITTED:
4d721364-afb1-5d39-ac1d-517b83df683e | textbox | Work Start Date:
0be782db-41fa-55cb-877d-35663d228d93 | textbox | SUBMITTED BY:
14b3b780-7e55-5f49-b8fb-adcafa842460 | textbox | SPECIFICATION AND CLAUSE:
edfac406-3d00-5e49-88c0-6a52edd760e0 | textbox | HOLD POINT DESCRIPTION:
17ae5052-f116-5991-a04d-3687724fb675 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | Lot Verification
| checkpoint | Lot Verification complete
4c7d4189-a9e3-55c7-ba2d-e21114bf438f | textbox | Lot Verified By:
e3318554-eaab-57de-b3d2-b7b62f18a1f2 | textbox | Lot Closed Date:
a6859924-4557-5f65-88f4-ef29910272ca | button | Submitted to Client | Yes, No, N/A
5bb1d02d-e070-59ce-8658-9ae97f9e17b0 | button | Reviewed by Client | Yes, No, N/A
2d6e3ca4-0d4b-525d-99b9-ab43d6ce4434 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 07 - R15 Kerb and Gutters Rev 1 | itp | ITC 07 - R15 Kerb and Gutters Rev 1 | c9461529-4844-4043-b2b6-6e3734d33f85
| section | Lot Information
| checkpoint | Lot Information complete
dfd64e0a-4aeb-522b-8d46-e8abe3db0bf2 | textbox | Lot Opened On
30c725a1-6904-5691-b2d6-f89b1c51b97f | textbox | Date of Works
b563ba21-f8e0-5ab4-8c34-3ee5c388af49 | textbox | Lot Type
8ef1b341-0c95-58f6-b165-ae68c79663fb | textbox | Start Chainage
74161b4e-d2c9-5552-8859-12124a6d7894 | textbox | End Chainage
258e17b3-e16d-5420-90e6-49c3d9a1f843 | textbox | Offset
a202e987-0275-529c-8b71-a0298a0f550b | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - IFC Drawings are Current
4a6c234e-09ed-5967-bc81-51bcebcc84b4 | note | Document Reference / Applicable Standard - Pavement IFC Drawings
50a567a2-bc60-5e91-bcaa-e37539552fc6 | note | Acceptance Criteria - Use of latest revision of approved Issued for Construction (IFC) Drawings. Any changes in design, RFI was raised and approved:
f4556580-9e3c-5c15-a198-83bdbb757f45 | textbox | RFI
c553bcf2-d49c-51b6-ae06-56f00f197d3a | note | Frequency/ Process Held - Once / Prior to Construction
f8c3c712-5ad4-54b9-960d-7eb38312f586 | note | Inspection - ACPL - S
7056747e-541d-5446-a2b0-f0c68038462a | note | Inspection - Client - S
7e080222-1448-5e27-9ac1-00448a7d1ad2 | note | Verifying Records - Pavements IFC Drawing
| checkpoint | 1.2 - Underlying lot conforming
fe0e47f9-a652-58b2-91c1-541a6c4521c5 | note | Document Reference / Applicable Standard - Survey Report
afe89d81-4042-57a8-8189-692800a4c97b | note | Acceptance Criteria - Underlying/Preceding lot is conforming prior to commencement including survey levels of underlying lot and K&C Subgrade
613ec8a3-781d-5216-aae6-181b132b8d02 | note | Frequency/ Process Held - Once / Prior to Construction
8f40f743-c396-5166-8758-3f33854c2876 | note | Inspection - ACPL - S
0c2ef9df-1e23-5625-a34a-cf5e85139b5f | note | Inspection - Client - S
8eb7aeff-d504-57f3-90f8-f1d0f066e034 | note | Verifying Records - Test Results / Survey Report
| checkpoint | 1.3 - Concrete Mix Design
c29b13fe-b038-5df5-aecc-a4bd79dc7e62 | note | Document Reference / Applicable Standard - R53 Cl 2.4.1, R53 Annexure, R53/E, R15 Cl 2.2
35c531e2-97c1-5692-ae61-61175501a431 | note | Acceptance Criteria - Concrete Mix Design approved by client
07195412-93d3-5840-9c57-733d6ed47d40 | note | 25mpa – 15 – 25mm slump – max. nom aggregate 10mm
479504f0-bbac-5101-95fe-6c5f61a87c82 | note | Frequency/ Process Held - Once / prior to construction
6cd37821-1649-59e7-b7d7-40cb0e49bdfd | note | Inspection - ACPL - H
bf4fccb9-bf19-5502-a8b8-92dbcec0453c | note | Inspection - Client - H
354a453c-f023-5868-ba7d-afc003797fd0 | note | Verifying Records - Concrete Mix Design
| signoff | AUTHORITY HOLDPOINT
| section | 2. Construction
| checkpoint | 2.1 - Survey Set out
274805de-01ee-520c-89a7-cc7cdae0cd4d | note | Document Reference / Applicable Standard - QMP
ebc32581-0cce-5cf1-a107-62fd67decf4e | note | Acceptance Criteria - Survey set out as per design drawings
e2c17161-6a78-57cf-8fc5-33c7b78962dc | note | Frequency/ Process Held - Once / Prior to Placement
06ca5209-c246-564d-8e08-18dd0b938a7f | note | Inspection - ACPL - S
caa627b0-526a-579b-b107-07d94244f93e | note | Inspection - Client - S
d56e7a50-9454-52be-a516-51baef7a771f | note | Verifying Records - Set out Report
| checkpoint | 2.2 - Placement of Concrete
29c1ef7c-f552-5725-9ae8-19e4a24e5b32 | note | Document Reference / Applicable Standard - R53 Cl 3.3.1
e0e06adb-7922-530f-b43a-a331fad813f5 | note | Acceptance Criteria - Provide 2 working days’ notice to client of expected completion of preparation and expected commencement date and time of concrete placement
0e936203-e9ea-520f-8131-3332f6dbf639 | note | Frequency/ Process Held - Once / Prior to Placement
21d7eaac-4a86-585e-be89-a95a5c7a3eb1 | note | Inspection - ACPL - H
54e39d9c-683c-5d36-a440-9f591623d905 | note | Inspection - Client - H
af504707-a7d4-593b-bead-22ef09bdca12 | note | Verifying Records - HP Submission
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Concrete Sampling
c254e55e-3459-51a1-bd5c-7e27d3577b59 | note | Document Reference / Applicable Standard - R53 Cl 4.1 AS1379
0860afb4-ec95-5b8f-a364-8e55b37ab436 | note | Acceptance Criteria - Slump:
222f0212-4bf9-529e-826c-f5c05a5389a1 | note | ○ Perform slump tests on each strength sample
bbcf5878-b60d-57fd-a2d7-6095387a5548 | note | Strength:
39508643-f57d-56bf-b2d9-dacc7de3ceac | note | ○ Each grade at a plant shall be sampled at a frequency of at least one sample per 100 m3 of that grade produced except that, for Grade 20 concrete when 15 or more samples per month are obtained, the frequency may be reduced.
506fd688-56b0-5629-94ea-be1c48b1c889 | note | Frequency/ Process Held - Prior to Placement
d88662fc-0e1c-5ffc-a51c-face379abc4d | note | Inspection - ACPL - S
0dc543fb-7f38-5fea-be67-c712652cbf95 | note | Inspection - Client - S
57279ba6-03c6-528a-933d-c75b55e6e02c | note | Verifying Records - Slump Results Strength Results
| checkpoint | 2.4 - Concrete and Air Temp
b70098bb-0ef1-5d7d-a90b-f49afe322eca | note | Document Reference / Applicable Standard - R53 Cl 3.3.2
5f9eb58e-42d0-58b0-877d-2acdb765cb50 | note | Acceptance Criteria - Do not place concrete during rain or when air temperature in the shade is below 5oC or above 35oC
d5a67c36-4966-5785-a38f-5ea95413544e | note | Frequency/ Process Held - Prior to pouring each load
fea54f42-6a37-525b-8825-55142d4db072 | note | Inspection - ACPL - S
32ac706a-5e36-547f-9718-e82d06c5bfad | note | Inspection - Client - S
6ef6de0f-f69f-52b1-8353-0892215c6ff4 | note | Verifying Records - Pour Record
| checkpoint | 2.5 - Joints
34bc3f7a-8267-5999-86b9-dec4ff49dcae | note | Document Reference / Applicable Standard - R15 Cl 2.6, R15 cl 3.8
93e61b91-1672-5d73-8635-dbe7fcfe7470 | note | Acceptance Criteria - Joint sealant must be silicone sealant conforming to Specification TfNSW R83. Form and prepare joints in conformity to AS 2876.
d8351fcc-56d3-541d-abee-3cb0f075c80f | note | Shrinkage Control Joints: Spaced every 2.3 to 3m. Constructed by guillotining extruded work. Min 50% of the area of the section shall be cut. Resultant slot to be tooled to a depth of not less than 20mm to provide a groove of not less than 5mm in width.
75796663-a5f3-5c55-99c8-9d2a8d7818ae | note | Construction Joints: For Machine placed concrete, the last section of poorly formed or compacted concrete is to be removed while still plastic. Approx. 300mm. Leave suitable square face. Immediately prior to placing further concrete, the contact face shall be covered by a thin coat of cement water paste of creamy consistency. A Construction joint shall not be used to replace a shrinkage control joint.
1fe0c95b-6387-5ef0-a26f-11c757e5f87e | note | Frequency/ Process Held - Once / prior to placement of concrete
976aa66f-1eca-5e22-8a08-2538caeb41d2 | note | Inspection - ACPL - S
68bc4fc5-2edb-51cd-a5fa-c4552f60adc3 | note | Inspection - Client - S
370e3070-6dd9-5af9-967c-b977b6fcab99 | note | Verifying Records - Checklist
| checkpoint | 2.6 - Curing
b5987455-32fa-5ff6-83dc-55f820695823 | note | Document Reference / Applicable Standard - R53 Cl 3.4.3
1b61aad3-5754-5f45-b34a-e5939aaf691f | note | Acceptance Criteria - Apply curing compound to unform surfaces immediately after the surface is firm and free of bleed water
20822334-856a-5edc-8dc0-4ea94ea3ed4d | note | Apply curing compound at the rate specified by the manufacturer
6fc786eb-0944-525b-a780-826425b8fccd | note | Apply two coats when necessary to ensure complete and uniform coverage. The time between the first and second coat must be in accordance with the manufacturer’s recommendation.
e5957196-29dd-5a09-95ab-9109e9de2f7a | note | During application, implement measures to prevent the curing compound drifting away from the target concrete surface and deposited on adjacent surfaces.
13fbb02e-a938-56de-8715-37b0847d2cee | note | Maintain the curing membrane intact until at least seven days have elapsed after concrete placement
960f565b-ec94-5f93-9a71-221f2e035c02 | note | Frequency/ Process Held - Once / prior to placement of concrete
409f2938-2952-5dac-b35f-4597791451f2 | note | Inspection - ACPL - H
affdabf1-69d7-5c95-8bab-42753357f8aa | note | Inspection - Client - H
61296dfa-bf5b-580b-a4b5-16c3f1845858 | note | Verifying Records - Checklist
| checkpoint | 2.7 - Concrete Finish
e26a1ad9-d714-59de-a465-4c150fb8de30 | note | Document Reference / Applicable Standard - R15 Cl 3.9
346c8949-34a8-5b5f-8bc7-bc2666197a97 | note | Acceptance Criteria - Unless otherwise shown in the drawings, provide a steel float finish to channel inverts and faces of kerb and broomed finish to vehicular crossing and ramps. Brooming must be transverse to the direction of travel.
54afeddc-c243-5cbc-b4ac-f656a06fcae9 | note | Protect the concrete surface from rain during and after surface finishing and until final set.
1ee40a28-e66b-53d8-ad21-d88e1993503c | note | Frequency/ Process Held - Once / Prior to Survey
d31e8e53-7c39-5e5a-a0a0-78f89f2ddf0c | note | Inspection - ACPL - S
56aaf9e3-dbe3-55a8-8b99-2107991a22d2 | note | Inspection - Client - S
b61fd801-ad11-56db-a1f8-0ee0e4bc7cd6 | note | Verifying Records - Visual Inspection Project Quality Plan
| section | 3. Conformity
| checkpoint | 3.1 - Conformity
74917ff9-90a7-5d8a-aacc-d1a7deb50ad0 | note | Document Reference / Applicable Standard - R15 Cl 4
7bd26f0b-caaf-56b2-bc90-f5b841ccccd0 | note | Acceptance Criteria - All finished surfaces must conform to the lines, levels, grades, thicknesses and cross sections shown on the Drawings within the specified tolerances.
d9a456d6-3935-5a36-84dc-958edb8483bd | note | The tolerances stated in AS 2876 for irregularities in the bedding layer, level of the bedding layer, horizontal alignment, level, deviation from a 3 m straightedge, deviation on vertical curves, and profile dimensions also apply, except that the level of the constructed channel lip must not vary by more than 0 mm above or 10 mm below the adjoining pavement surface at any point.
bebe405c-4652-5baf-b552-50f65080fd6a | note | Frequency of conformity testing as per Annexure R15/L:
8a750f55-48eb-504a-9ab8-f7dd4a92dc5b | note | Frequency/ Process Held - During concrete delivery
cedcc87c-1a84-5ea8-85f1-51edb7589cc9 | note | Inspection - ACPL - S
9b3dbd3f-4d74-55d6-8242-feaf41a6ed7e | note | Inspection - Client - S
be97b71b-4ee2-5828-889e-f1c9a041de80 | note | Verifying Records - Concrete Docket Survey Report, Concrete Pour Record
| section | Review by Quality Manager / Project Engineer
| checkpoint-no-value | Review by Quality Manager / Project Engineer
9c47b30a-8b92-5460-9896-96603fb463a0 | button | Any non-conformances? | YES, NO
dd9185a1-6cfd-531f-82fe-864ab52a2604 | textbox | No's:
8d9def4f-1878-5b31-b9bb-03ea5dad4aa1 | button | Closed Out | YES, NO
6c98138e-80d0-55a6-8d9d-fe6909733ea9 | button | All work has been satisfactorily completed. | YES, NO
570674ec-2d5f-510e-83fe-123f9ad2e7bd | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
f5698ff0-b0d2-59a0-a4de-2be79d2bd0a4 | textbox | Lot Verified By:
7abdc1a6-c793-5602-8642-8508e6d8e440 | textbox | Lot Closed Date:
ef3360df-d190-5bad-b281-d56945a85c9c | button | Submitted to Client | Yes, No, N/A
9c06d55f-659f-5803-82cf-b8e0365cf79a | button | Reviewed by Client | Yes, No, N/A
5a32483d-f093-5e79-8fbe-b881ea2568f8 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 08 - R16 Precast Box Culverts Rev 0 |  | ITC 08 - R16 Precast Box Culverts Rev 0 | d1fadcb0-6230-40d5-883f-a43cdf04bf44
| section | Lot Information
| checkpoint | Lot Information complete
52b26d70-f434-5482-be3f-0108a644cb41 | textbox | Lot Opened On
80f394d5-76e5-5a44-a604-bf18406381a7 | textbox | Date of Works
a874729b-73f9-5f33-892b-646ead7dde31 | textbox | Lot Type
18e4b832-23c6-5483-bd72-4b08bdeb34d8 | textbox | Start Chainage
c2a70cb3-aaf9-5d3f-8b27-0f379f4ff7f2 | textbox | End Chainage
6fa7c35a-9135-50e9-897a-10ac55962186 | textbox | Offset
00389dce-d5cf-5a79-a2bc-16a3c563a060 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
998e4b74-b0d5-5802-b49c-868bf2bb3985 | note | Requirements / Reference - Project Safety Plan
3848bfe1-0346-5ac2-bd1f-d8937584f954 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
1349b640-3f19-5328-8229-ea187aa55907 | note | Required Safe Work Method Statements completed and signed
c2944c77-43ff-570e-9004-2123a291f5a5 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
d03304f6-a772-52eb-a0f5-e692786d3abe | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
943bd586-e4a0-5d5f-a58d-c62ef5acb36a | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
91ec2595-cad7-5589-a602-bb2fe8346fda | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Basic Requirement
| checkpoint | VERIFICATION
dd32f07c-cbcc-526b-82bf-955b400b0e7f | note | Requirements / Reference - R16 Cl 1.4
a2a5e9d0-eb04-5c10-ae06-3bc8ffe86df4 | note | Acceptance Criteria - Design, test, manufacture and deliver all culverts and link slabs in accordance with AS 1597.2 and the additional requirements of this Specification
| section | 4 - Concrete Work
| checkpoint | VERIFICATION
0cf83e7d-a716-5624-9a09-a537bbf3070d | note | Requirements / Reference - R16 Cl 4
c179eb45-40aa-5cae-a35e-c99fa8c795c1 | note | Acceptance Criteria - Concrete, reinforcement and embedments must comply with TfNSW B80
d2d5971d-de89-582e-b805-41775e400475 | note | At 28 days after concrete placement, measure and classify any defects in accordance with AS 1597.2. Mark defects and cracks larger than 0.1mm as nonconforming. Map nonconforming cracks and defects
c554dcc0-84af-5104-be63-881496508570 | note | Unless directed otherwise, defects Type 1 and 4 may be accepted without repair, defects Type 2 and 5 may be accepted after repair, and reject units with defects Type 3 and 6. Repair defects in accordance with TfNSW B80
93b565e2-8975-5f7e-bdc9-f08009cb4fe1 | note | Comments / Attachments / Records - Map of nonconforming cracks and defects (if applicable)
| section | 5 - Design Requirements and Procedures
| checkpoint | HOLD POINT
2f242844-0b81-502e-9e8e-3196998028a5 | note | Requirements / Reference - R16 Cl 2
3b94ffb0-eabb-558c-91c8-305dd30f18ff | note | Acceptance Criteria - Design requirements and procedures of AS 1597.2 and where required, AS 5100 also applies
a57a5ae3-3bdf-5c58-91ff-0e782be7534a | note | Include in the design records the calculations produced during both the design and verification processes. Include construction plant loadings in the calculations.
e25fea2b-bbd8-56c7-9712-ca74aa88075e | note | Provide certificate demonstrating compliance with these requirements
82fbdcad-d146-565d-8735-1274f9065931 | note | HOLD POINT: Delivery to site of culverts. Submit to the Principal design output and certification of compliance at least 5 working days prior to commencement of delivery to site
a3c9ad12-8c15-5c25-b46b-0d167d74de2d | textbox | HOLD POINT NUMBER:
e674e8b0-5f02-5c34-a54e-3958aac0f002 | textbox | DATE SUBMITTED:
fbbdf14c-5e03-5427-a452-5786101714a2 | textbox | Work Start Date:
c8d62ffe-c541-561e-afc5-d6c3ca63c452 | textbox | SUBMITTED BY:
728f869c-5ed2-5da6-87d7-8abb96bc7778 | textbox | SPECIFICATION AND CLAUSE:
f379d9c3-43b8-5e9d-bcae-87df1bb85a37 | textbox | HOLD POINT DESCRIPTION:
567ec5b5-b818-5d9b-8def-17a22043a59e | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 6 - Design Based on Load Testing
| checkpoint | HOLD POINT
ead55cf3-c9e4-5aa0-9f98-8820a8576d89 | note | Requirements / Reference - R16 Cl 3
ae2d0ee3-8400-5394-8c0c-25c6bc89b296 | note | Acceptance Criteria - Where the culvert design is based on load testing, provide certification, supported by testing and calculation records, demonstrating that the design complies with AS 1597.2 and AS 5100 as necessary for each different culvert / load combination.
b93a1275-a85f-58ef-9d8c-8a41d2a66a5d | note | Refer to Annexure R16/E for a table of basic test loads for standard small culvert units and link slabs
419b7cd2-5ed8-5593-beff-66238ea669a5 | note | HOLD POINT: Delivery to site of culverts. Submit to the Principal testing and calculation records and certification of compliance at least 5 working days prior to commencement of delivery to site
f1000a67-8eed-581e-9e97-046e6ed41217 | textbox | HOLD POINT NUMBER:
94e0decc-b9f2-51ad-a547-36a840f34bce | textbox | DATE SUBMITTED:
16a65505-e2ba-5986-aafb-7a1aab51fd0a | textbox | Work Start Date:
e6838da4-7de2-5a75-85e5-0d7b0110a8e1 | textbox | SUBMITTED BY:
7d5d2b4e-d7bc-5622-802e-b95d5d7aadb4 | textbox | SPECIFICATION AND CLAUSE:
0e079258-9b80-5565-a93f-1896b27ad0ce | textbox | HOLD POINT DESCRIPTION:
31484a80-633c-55fe-80fd-28b8174f38a2 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Delivery to Site and Storage
| checkpoint | VERIFICATION
88f15ead-ff5b-5cb1-9d22-9e35712919b4 | note | Requirements / Reference - R16 Cl 7
ac167f8d-f755-5366-b962-d0f2c9a08233 | note | Acceptance Criteria - Do not transport any unit until at least seven days after casting and until the concrete has reached the specified 28 day strength
82c98baa-a123-572e-b1bd-69145a546057 | note | Design (and provide any necessary certification by a qualified engineer) and make suitable storage areas for delivery of box culvert units, link slabs and associated components, taking into account any double stacking being proposed
| section | 8 - Sampling and Testing
| checkpoint | WITNESS POINT
10a41c3a-ab26-552d-b316-a5c4420b672d | note | Requirements / Reference - R16 Cl 5
8e58948b-274e-50d2-90b0-139a80269e99 | note | Acceptance Criteria - Routinely sample and test for each quality parameter (except concrete strength) in accordance with AS 1597.2. Sample and test for concrete strength in accordance with TfNSW B80
e7f9f4f9-3849-5619-bc89-52585d5afc87 | note | WITNESS POINT: Crack serviceability test. Provide at least two working days’ notice of intention prior to carrying out the test. Before starting testing, submit a certificate of compliance of test loads, and other relevant details supported by verification checklists
b6df1d8c-42fe-594a-8c0d-a43472b0423e | note | Comments / Attachments / Records - Design certification (if required)
9bad1dd9-33e8-5156-b1e8-dd26358cb6aa | textbox | WITNESS POINT NUMBER:
9fec8814-c0b3-5289-98a1-f9a3b1a094b7 | textbox | DATE SUBMITTED:
fb297ce9-d108-5c8a-b2fd-00ea358ac345 | textbox | Work Start Date:
c32c1be7-9178-52a2-b66a-7acdb60b276f | textbox | SUBMITTED BY:
8e206fb1-6811-5d95-8ae3-e66551c6a2b4 | textbox | SPECIFICATION AND CLAUSE:
51f8979f-94ea-5879-b668-910e0d0db14a | textbox | WITNESS POINT DESCRIPTION:
743fe10c-331e-5ed1-8f2d-ade89e7097f9 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 9 - Contractor Certification
| checkpoint | VERIFICATION
038b7f03-e573-5153-a5d1-02a884960fe2 | note | Requirements / Reference - R16 Cl 6
7e02efa8-8305-5dc4-97f4-120e7a04836e | note | Acceptance Criteria - Do not supply any damaged and subsequently repaired units, link slabs or associated components without the prior approval of the Principal. Submit details of any nonconformities and the proposed repair methods to the Principal for their approval prior to undertaking repairs
8c275a84-5cc5-5b37-970b-7785fbe3b1b8 | note | Proposed repair methods include repair of Type 2 and 5 defects as per TfNSW B80. In the case of cracks and patching, clean the affected area with a wire bristle brush, apply a suitable primer / bonding, and then patch with a B80-suitable product such as Renderoc HB40 Plus, HB70 Plus or similar. Take care with the finished surface and apply a suitable finish to match the surrounding concrete, curing where necessary. These repair methods must be submitted to the Principal for their approval prior to being used.
7dc6c0be-f013-59ed-a7eb-67065511bd30 | note | Prior to incorporating the units into the works, provide the Principal with a certificate for each item, stating that the units conform to the Specification and that all nonconformities have been rectified in accordance with the Principal’s approved extent and method
3f47371c-b6b2-5c1c-9962-326fdbc10e79 | note | Comments / Attachments / Records - Certificate(s) of compliance
| section | 10 - WAE Records
| checkpoint | VERIFICATION
50d870a6-227c-51b5-90d8-be286e3e9799 | note | Requirements / Reference - R16 Cl 8
9320b14f-2819-598f-a08c-8e4c06cd1dd3 | note | Acceptance Criteria - Provide works-as executed records for the precast crown units manufactured for the box culverts, showing all dimensions, reinforcement and date of manufacture
fd146b02-fa46-5277-9efe-bd766b6242f3 | note | Include concrete target compressive strength, strength at 28 days, and strengths when forms are stripped in your records
0b8cf14e-8c98-5dbb-9e0f-088156e262b2 | note | Include details of approved repairs in accordance with Clause 6, if any
76cfcfb8-11ec-5f67-a91b-df8bbc09b7f0 | note | Comments / Attachments / Records - WAE records
| section-nested-checklists | NCR
| checklist | ITC 09 - R33 Trench Drains Rev 1 | itp | ITC 09 - R33 Trench Drains Rev 1 | 4f846bfc-a0ff-447a-bc01-fbce28393591
| section | Lot Information
| checkpoint | Lot Information complete
d5d36809-b0b1-5ad0-a95e-38f2bcb030c2 | textbox | Lot Opened On
f881ee71-56a4-5c15-8d15-4e38a756c42f | textbox | Date of Works
2a6f8176-fde7-57fc-9823-51ed7a46b3a9 | textbox | Lot Type
d91a0c47-a1d9-5e12-bfc2-996573906b18 | textbox | Start Chainage
6376fdce-8dd1-55a0-a508-55b614311704 | textbox | End Chainage
9de6016f-a65c-5435-9595-354509c75f5c | textbox | Offset
a20c8703-5ab6-57af-8de7-ee3cf139081c | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - IFC Drawings are Current
1841cc5b-5d7b-5262-b6b8-4a3b7b68179e | note | Document Reference / Applicable Standard - Pavement IFC Drawings
9ea162e7-480b-504d-a203-f6a2419ded4b | note | Acceptance Criteria - Use of latest revision of approved Issued for Construction (IFC) Drawings. Any changes in design, RFI was raised and approved:
2c53a4cd-1f38-5582-a8b0-7fb1cab0f98e | textbox | RFI
bfda08d9-8e94-55d4-aa36-6e74473c9624 | note | Frequency/ Process Held - Once / Prior to Construction
2204a0d9-90d3-52fb-ab68-73be53bc6075 | note | Inspection - ACPL - S
dc32b83c-7848-59ed-a01a-7c1609e401ec | note | Inspection - Client - S
c207e62e-a097-5b58-99c8-ebfb89390d7d | note | Verifying Records - Pavements IFC Drawing
| checkpoint | 1.2 - Underlying lot conforming
2f9076b5-992a-5645-9f39-49c2a9ce4a97 | note | Document Reference / Applicable Standard - Survey Report
8ecbfda1-b6c0-51c8-a5d5-c5428a605bfa | note | Acceptance Criteria - Underlying/Preceding lot is conforming prior to commencement including survey levels of underlying lot
40439ccd-b56f-5e0a-b9ed-d07d5743f67a | note | Frequency/ Process Held - Once / Prior to Construction
f5b3c875-93ba-528b-894d-f00251c121b8 | note | Inspection - ACPL - S
dc8bcdb9-a285-5259-a640-6cd413b9fd22 | note | Inspection - Client - S
0d48dc3a-73ea-5e68-bae4-a3dd288717a3 | note | Verifying Records - Test Results / Survey Report
| section | 2. Material Compliance
| checkpoint | 2.1 - Corrugated Drainage Pipe and Rigid Strip Filter Drain
d199a50e-d2c6-55c9-981d-21a220b50e37 | note | Document Reference / Applicable Standard - R33 Cl 2.1
42426303-318c-58e9-92b5-f92e040723f1 | note | Acceptance Criteria - Corrugated plastic drainage pipe (both perforated and non-perforated) must comply with Specification TfNSW 3552. Caps and other fittings must be in accordance with the manufacturer’s recommendations.
60b74caa-9661-5547-80be-1c7ed98e48d2 | note | Seamless tubular filter fabric for use with corrugated perforated plastic drainage pipe must comply with Specification TfNSW 3553.
1381294f-227d-5a00-aa73-a1bab26a2d33 | note | Rigid strip filter drain must comply with Specification TfNSW 3556.
e2ff0bd3-02e5-5da5-8b9d-561bb38bfe39 | note | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
a346f880-4c19-5443-93c3-a4dc35bc38a4 | note | Inspection - ACPL - S
2f98542a-dbd8-5067-a45f-6cb48ce55694 | note | Inspection - Client - S
845bdf09-2cdd-585c-873e-bd0f49500c79 | note | Verifying Records - Compliance Records
| checkpoint | 2.2 - Geotextile
97b73f0c-4987-5120-8141-dd87827df5b0 | note | Document Reference / Applicable Standard - R33 Cl 2.2
3d970bbe-dd5c-5c59-8b71-39ee248d6f52 | note | Acceptance Criteria - Geotextile must comply with specification TfNSW R63.
d1debd23-cc5e-58ab-9fc7-f7325a1e89bb | note | Geotextile for wrapping around rigid strip filter drain must be non-woven geotextile of Strength Class A
0af5d1c3-3120-531a-a74f-be0924d8dca7 | note | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
ddcf78b7-5cd4-5950-b630-28518d9b7fe0 | note | Inspection - ACPL - S
1889c71c-a3a0-5aa3-9e6a-dde70e57a591 | note | Inspection - Client - S
1b0aadb7-4ec0-5cfe-af3c-fec89b419a1f | note | Verifying Records - Compliance Records
| checkpoint | 2.3 - No Fines Concrete and Aggregate Filter Material
3714ae11-a6ca-5994-bdbc-f2c2cc780c6b | note | Document Reference / Applicable Standard - R33 Cl 2.3, TfNSW 3580, D&C 3222 Cl 6
8cbf7150-caa0-5470-9737-3b92b43a217f | note | Acceptance Criteria - No fines concrete must be Grade NFC SD complying with Specification TfNSW 3222
76b748eb-5dd8-5d55-b4a0-4e23072ac69c | note | Aggregate filter material must comply with Specification TfNSW 3580 and the Drawings for the aggregate type.
7c75c0a7-627b-5fd8-bccb-5fdf63924c99 | note | Detail the mixing plant and delivery vehicles
6df0a60b-b8eb-5a26-8ea7-9cca50650a22 | note | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
49c9a9c6-0a34-594d-9723-0ccb79b1f42e | note | Inspection - ACPL - H
e928a078-df87-5f81-9034-902f00703c0a | note | Inspection - Client - H
e81b298b-011b-5eae-bc67-518d6a2c332a | note | Verifying Records - Mix Design & delivery methodology / Compliance Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Selected Material
cecc9616-4a19-56e8-a7a3-c024d70829cd | note | Document Reference / Applicable Standard - R33 Cl2.4
d5afb239-136a-5cb7-911e-dbb6d5d8e3b6 | note | Acceptance Criteria - Select Material must meet the requirements of Specification TfNSW R44. Select material at batter outlet and at the transverse outlets of pavements interface drains must, in addition, have a maximum particle size not exceeding 50mm.
3eb242ed-bed4-50c6-9619-e3b8033dc79e | note | Selected fill material for the plug used in staged construction must have a maximum particle size not exceeding 20mm and PI not exceeding 12.
ab7a4007-7214-5cbc-a616-83e7a70e89bb | note | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
d0fa5c74-4a4a-56d2-afe1-0394fd94d31e | note | Inspection - ACPL - S
b24ea202-75a3-5f82-953f-2a4a51ad0095 | note | Inspection - Client - S
ec2e9260-be96-504a-9bf6-85b21b0ad49c | note | Verifying Records - Compliance Records
| section | 3. Construction
| checkpoint | 3.1 - Order of Construction
7f281d7d-fbd4-5823-ad5a-df6b365a65de | note | Document Reference / Applicable Standard - R33 Cl 3.1
01532184-56db-5014-8b7b-b1f2349c2d34 | note | Acceptance Criteria - Where trench drains are to be installed in embankment foundations, construct the trench drains after completion of clearing, stripping and general excavation operations, but preceding the commencement of embankment construction adjacent to the trench drain.
5c214626-3e13-58d9-85f7-7b5fe2d5a53e | note | If trench drains are required in cuttings, construct the trench drains as soon as practicable following completion of earthworks.
1f420afc-403e-5a42-8e6c-06f3484a5227 | note | Where the top of earthworks is to be stabilised, construct the trench drains after completion of stabilisation.
fea73bff-47eb-5c74-b17d-2dc13c53a35c | note | Where excessive ground water is encountered, trench drains may be installed prior to stabilisation if approved by the principal.
67d7ad41-fc4e-51b4-b210-7e8ca4381212 | note | Frequency/ Process Held - During construction
79a93bf4-d73c-5874-8da3-4683fbe6f6c1 | note | Inspection - ACPL - S
83f20b79-5db9-5081-8c54-555be4fb09ce | note | Inspection - Client - S
2a43e487-9c9c-5bfe-a28c-fa01dde1206a | note | Verifying Records - N/A
| checkpoint | 3.2 - Excavation
16beffad-85a9-5b2b-8a57-fa182e152dd2 | note | Document Reference / Applicable Standard - R33 Cl 3.2
ab514999-8f2d-5a72-b6a5-13dfeacd1868 | note | Acceptance Criteria - Unless otherwise specified, the bottom of the trench must be at the same grade as the roadway. Where the grade of the roadway is less than 0.5%, provide minimum grade of 0.5% by increasing the depth of the trench.
e37104ad-f95c-53c0-aec8-670542b497a7 | note | Excavated material must either be stockpile or incorporated in the works or disposed of in accordance with R44.
ca4d18ec-f829-5f36-b0cd-a84569033039 | note | Frequency/ Process Held - During construction
7a224caf-f8ff-58d2-af95-46f9ed059692 | note | Inspection - ACPL - S
2a970ad0-e2e0-58b5-a8e8-835c3e5a8563 | note | Inspection - Client - S
c473cbc7-c67e-5a1a-a643-ada922132af8 | note | Verifying Records - Survey Report
| checkpoint | 3.3 - Geotextile Installation
01d022df-a919-517e-b8f9-b2a152740b54 | note | Document Reference / Applicable Standard - R33 Cl 3.3
6c7f655d-3b14-5ab9-b908-daeda97b752a | note | Acceptance Criteria - When installing geotextile, do not allow loose material from the trench walls or outside the trench to enter the excavation.
3d101f8f-d829-5467-a4f6-9241df622dbc | note | Keep all geotextiles clean and secure the geotextile to ensure that they are located as shown on the drawings on completion of backfill.
26b9a6a0-9fbf-507e-b7e8-bef8f609c995 | note | Frequency/ Process Held - During construction
520239ec-47ab-55b2-8449-fbfaf9fc9375 | note | Inspection - ACPL - S
09e089aa-1440-56db-83f8-6671eda160c0 | note | Inspection - Client - S
64d61b82-da48-5709-aaa9-e7357d2c7971 | note | Verifying Records - Visual Inspection
| checkpoint | 3.4 - Laying of Pipe
a7e56234-6460-588b-95a5-5c557a2b3342 | note | Document Reference / Applicable Standard - R33 Cl 3.4
0ca11a30-c54d-50b9-9ea0-04c7738f2bad | note | Acceptance Criteria - Lay the pipe in the centre of the trench on a bed of filter material 100mm thick to the required line and grade as shown on the drawing.
0be047c1-91ff-5afb-bfc2-c7f876eb9d75 | note | Keep the number of joints in the pipeline to the minimum and connect the pipes using coupling complying with the manufacturers recommendations.
e2e03c65-e1cb-51ab-90d5-79103d5f7c0f | note | Where an inlet into the trench drain is provided at a stormwater pit, the invert level of the inlet must be above the hydraulic grade line of the pit and as close to the underside of the pavement layer as possible.
dc26f797-dec4-531a-83ef-2d344d2b73d9 | note | Cap the upstream end of buried pipes where the upstream end of the pipe is enclosed within filter material and is not connected to a stormwater pit.
663290d3-83dc-5e17-8122-37038558b919 | note | Where the filter material around the pipe is Grade F5 or F7 aggregate filter material (refer TfNSW 3580),
c6a35144-5d86-5040-b97a-c0b4b29cfeaf | note | (a) for corrugated perforated plastic drainage pipe, install a seamless tubular filter fabric around the pipe;
d59093da-a1e4-5f48-96ca-f8f6004d63ee | note | (b) for rigid strip filter drain, wrap the strip filter drain with non-woven geotextile of Strength Class A. The geotextile must encapsulate the rigid strip filter and be joined by heat or an electrically generated welding process.
0c3f574f-baed-5a53-a152-a2b91d3cc8a0 | note | Frequency/ Process Held - During Construction
0db7af39-601a-5a49-9e69-4c7d9536a8e5 | note | Inspection - ACPL - S
37573eb5-cfe8-50b8-ad03-924cb3e579cb | note | Inspection - Client - S
7ea1a638-afeb-5213-93ee-a824b9ef46db | note | Verifying Records - Visual Inspection
| checkpoint | 3.5 - Backfilling
5c886e52-c83c-54e1-a367-1120685d0359 | note | Document Reference / Applicable Standard - R33 Cl 3.5, TfNSW 3222 Cl 7.1
e72ca65f-2173-5d83-9d3e-c69fc87d8595 | note | Acceptance Criteria - Compact the filter material to its full depth to avoid post-construction consolidation and to provide an even surface at the same level as the adjacent material.
fccec615-f668-5541-b5f1-a32bb4ec0316 | note | Verification that pipe laying, jointing and bedding are complete and conforming.
331280f7-5dfa-5b16-8346-0b6d94158220 | note | At the end of each days production, total up the individual masses of cement and aggregates using in the days production of no fines concrete, and provide these details to the principal
cc80e097-505b-596e-b254-dd4773bb9fe6 | note | Frequency/ Process Held - Backfilling
6bbaf42c-fcda-5acf-9414-f08d436acabf | note | Inspection - ACPL - H
b71d0462-0628-5e63-89ca-ee3f657ea24e | note | Inspection - Client - H
a41a2c00-34a7-5910-b730-5b1ce03a99c2 | note | Verifying Records - Visual Inspection
| signoff | AUTHORITY HOLDPOINT
| section | 4. Outlets and Marking
| checkpoint | 4.1 - Outlets at Stormwater Drainage Structures
017a3a7a-1b9a-5505-8808-753b8ba9ee65 | note | Document Reference / Applicable Standard - R33 Cl 4.2
6e7e1236-0362-5b3e-9b95-9ab21018fd12 | note | Acceptance Criteria - Where the outlet of the trench drain is at a stormwater pit or other stormwater drainage structure, the height of the pipe invert above the base of the trench drain must taper from 100 mm to zero within the end 5 metres from the outlet.
3e227974-6084-50a8-80aa-1a8f3fb3895d | note | Where a trench drain is one without a pipe, provide 10 m of corrugated perforated plastic pipe immediately upstream of the outlet and taper the height of the pipe invert as described above to facilitate discharge of water. Fit the upstream end of the pipe with a suitable cap to prevent entry of material.
5b33c872-8691-5df3-9ef8-e387a6aa8772 | note | Frequency/ Process Held - Installation of Outlets at Stormwater Drainage Structures
1bc61889-8a36-5bd7-ad93-343d374d6f4c | note | Inspection - ACPL - S
17f8707a-8365-555c-87f0-78ef40bed3f9 | note | Inspection - Client - S
e66f1c4c-7a0a-5929-9f9c-f55719bab12a | note | Verifying Records - Visual Inspection
| checkpoint | 4.2 - Outlets at Batters
1ff66702-ee31-5798-9dd0-eb52314d27f1 | note | Document Reference / Applicable Standard - R33 Cl 4.3
9ba0a5bb-ca94-56d5-9ff7-69791d7f823d | note | Acceptance Criteria - Where it is not possible to connect the trench drain to a stormwater pit or other stormwater drainage structure, construct an outlet at the batter to discharge water beyond the edge of the road shoulder.
f02a0cd0-0183-5420-947e-e2b1f2897293 | note | The outlet pipe must be of the same type and size as those in the trench drain but must be non- perforated for the length extending beyond the edge of the pavement.
ca47f10b-aee3-5481-9d05-f2f68795f7c3 | note | Lay the non-perforated section of pipe at the base of the trench. Taper the height above the base of the trench of the connecting section of perforated pipe, from zero to 100 mm, over a 2 m length.
4f156822-026c-5566-bf7a-003d1e5cab21 | note | Backfill the trench along this section of pipe with Selected Material of maximum particle size of 50 mm, and compacted to a relative compaction of 95% as determined by Test Method TfNSW T166.
539ca95f-b6b5-5a94-ba3d-e4237928071f | note | Construct a batter outlet structure at the discharge end in accordance with the Drawings. Locate the outlet so that erosion of the adjacent area does not occur or protect the outlet by placing selected stone in the splash zone.
9fe0f16e-c9af-5063-9c35-6f4acc028906 | note | Frequency/ Process Held - Installation of Outlets at Batters
2bb15690-c8db-51ac-a86f-4f2d78a4241c | note | Inspection - ACPL - S
467d5e44-d907-52d3-b409-a6d08a469cfc | note | Inspection - Client - S
37dcb58e-953f-5a6e-ac7c-158557c659da | note | Verifying Records - Visual Inspection
| checkpoint | 4.3 - Marking
29f7dfb8-2904-5533-9c7f-7c39b6abf42f | note | Document Reference / Applicable Standard - R33 Cl 6
379c3317-ffa8-5c81-b93c-d447b7862637 | note | Acceptance Criteria - During construction, physically mark out on site the inlets and outlets of the subsurface drains, to avoid damage to them during construction.
06dfea1e-718e-5771-bee6-97041c96d618 | note | Frequency/ Process Held - Marking of Outlets and Inlets
be83167a-31b4-57f4-9a23-e9a04ea43a60 | note | Inspection - ACPL - S
62b1651b-5ead-5269-93e7-306d75c135b7 | note | Inspection - Client - S
70f16d2b-7f72-5213-b707-485638761d63 | note | Verifying Records - Project Quality Plan
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
4bb530e6-24fb-5460-b9a3-e6056e05ab2e | button | Any non-conformances? | YES, NO
07a73052-6696-5fc5-89ff-1ca6943624d2 | textbox | No's:
d159c22c-0aa6-57d8-a70d-a4fe2a5475b9 | button | Closed Out | YES, NO
06402b39-e436-50e9-9771-7f5607a9f8f9 | button | All work has been satisfactorily completed. | YES, NO
fdc551f8-aaac-539e-9393-3ea12800493f | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
5345ca76-e4f8-50ea-a50a-a91f020eab9a | textbox | Lot Verified By:
46705dea-a78f-56c2-be91-d26c81dece15 | textbox | Lot Closed Date:
153ed819-f3d2-5ff5-9429-0843c3c9a4ff | button | Submitted to Client | Yes, No, N/A
c2a51f2b-2d2f-58ee-8a31-f1a00770ffcc | button | Reviewed by Client | Yes, No, N/A
9e82baf5-3668-5416-9856-a626b4d53ed1 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 10 - R50 Earthworks Stabilisation Rev 0 |  | ITC 10 - R50 Earthworks Stabilisation Rev 0 | 742be5df-8a03-43fc-aaab-8277d0815a33
| section | Lot Information
| checkpoint | Lot Information complete
950ca26c-e6dc-5f3b-a119-27cf818e8fbc | textbox | Lot Opened On
73433329-7adc-5af6-b18f-39d035c704d1 | textbox | Date of Works
b0927a57-308e-5475-b33d-89af76a3cada | textbox | Lot Type
6f4f5da2-4370-547f-bd6c-af539349e82e | textbox | Start Chainage
2719b034-5c10-5a56-915e-a5d5671dbfbc | textbox | End Chainage
ba7c8047-72b9-51d3-842a-a9f8a1a603db | textbox | Offset
84099604-2d49-5aa6-af0a-6bf8346985c4 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
75bc7fb6-a8e9-59c1-810b-2886a0801908 | note | Requirements / Reference - Project Safety Plan
685f0e91-a4be-5946-91e5-12108cd9d4b3 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
0e4391ef-c879-5159-8635-5a5cfa8a4497 | note | Required Safe Work Method Statements completed and signed
71d6b757-742e-56d3-9432-91b82bb4d993 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
f2239582-132a-57d1-950f-f96ad054bff5 | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
2f3fe1be-57ff-56ff-b71b-332414f070e3 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38 | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
df3f3e4b-4060-5183-9fb4-6d3be4a00b7b | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - General Notes
| checkpoint | VERIFICATION
2991ef14-91ae-5836-9668-2a6ecf02ab7e | note | Requirements / Reference - R50 Cl 3
7d17714e-1082-5fbf-b45a-62065880e800 | note | Acceptance Criteria - Where the Principal has not nominated a mix design, prepare one to meet the material properties specified in Clause 3.2.2. Submit the proposed mix design (if applicable) to the Principal for approval at least 10 working days before commencing stabilisation works | Acceptance Criteria - Where the Principal has not nominated a mix design, prepare one to meet the material properties specified in Clause 3.2.2. Submit the proposed mix design (if applicable) to the Principal for approval at least 10 working days before commencing stabilisation works
ee73f486-8750-5f41-b8b1-8861effdb930 | note | Unless specified otherwise, the proposed mix design must not result in a post-stabilisation UCS value (after 7 days accelerated curing) greater than 1.5 MPa (TfNSW Test Method T131). When used for R44 Specification works, the CBR and PI values must meet the requirements of TfNSW R44, following stabilisation | Unless specified otherwise, the proposed mix design must not result in a post-stabilisation UCS value (after 7 days accelerated curing) greater than 1.5 MPa (TfNSW Test Method T131). When used for R44 Specification works, the CBR and PI values must meet the requirements of TfNSW R44, following stabilisation
4c91b69d-13b4-5a91-abe4-6b45d85092ed | note | Do not carry out stabilisation works during wet weather or if rain is likely to fall during the process. Do not stabilise during periods of high wind which could cause loss of stabilising agent or cause a nuisance or danger to people, the environment or property (See also TfNSW G36). ACI Environmental Site Representative must confirm in writing that weather conditions are suitable for stabilising | Do not carry out stabilisation works during wet weather or if rain is likely to fall during the process. Do not stabilise during periods of high wind which could cause loss of stabilising agent or cause a nuisance or danger to people, the environment or property (See also TfNSW G36). ACI Environmental Site Representative must confirm in writing that weather conditions are suitable for stabilising
4895b25c-091f-503d-a8c8-878ec79f7560 | note | Where subsoil drains are required for pavement drainage, carry out any stabilisation of the SMZ prior to construction of the subsoil drains | Where subsoil drains are required for pavement drainage, carry out any stabilisation of the SMZ prior to construction of the subsoil drains
7886a369-5366-5c00-9021-1864a997c58e | note | Comments / Attachments / Records - Proposed mix design (if applicable)
| section | 4 - Trial Section
| checkpoint | HOLD POINT
6545d525-3255-5b18-9428-8f49d8fb5984 | note | Requirements / Reference - R50 Cl 7
e45a3ab5-2411-5805-bcd8-dad030696384 | note | Acceptance Criteria - Prior to completing stabilising works, construct a trial section of stabilising at a location agreed with the Principal, using the same materials, equipment and methods as will be used for the other works. | Acceptance Criteria - Prior to completing stabilising works, construct a trial section of stabilising at a location agreed with the Principal, using the same materials, equipment and methods as will be used for the other works.
5a2a8f91-90f7-5fe9-9124-c8cf188f6bfc | note | The trial section, if conforming, will become part of the project works
2a25cc29-20f5-51cc-a5e0-f8a573668c8c | note | The trial section must be between 100-200m long for the proposed Lot width
4e780678-e634-54b7-9a95-b8a506acabe4 | note | In the event of nonconformities refer Cl 7.2
c1bd1d10-d3cd-5957-ab96-db51077199db | note | A new trial may be required if stabilisation materials, plant or methods change
9c4ace05-50f8-571b-a100-e2b5d368ffed | note | HOLD POINT: Stabilisation of earthworks using a particular combination of materials, equipment and methods not previously trialed. Submit to the Principal, documentation, including test results, verifying that the trial section conforms to the specified requirements | HOLD POINT: Stabilisation of earthworks using a particular combination of materials, equipment and methods not previously trialed. Submit to the Principal, documentation, including test results, verifying that the trial section conforms to the specified requirements
70223ec4-2c86-5f16-a12d-a562084a023b | textbox | HOLD POINT NUMBER:
5706ef86-b943-53df-90da-963d55b2905a | textbox | DATE SUBMITTED:
5c3ef7f4-b073-5177-8b98-849f2a2b1f46 | textbox | Work Start Date:
251ce1d9-bc99-5fc4-acf6-472d3a6b0896 | textbox | SUBMITTED BY:
1a24f29c-73e2-5283-aef1-a0d230f561e2 | textbox | SPECIFICATION AND CLAUSE:
6baf7b67-af9f-5576-b62a-f1276c1131e1 | textbox | HOLD POINT DESCRIPTION:
11afe750-512f-5f22-bc0d-87063ca139b0 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Stabilisation – Insitu Mixing
| checkpoint | VERIFICATION
59068751-f78a-597e-8bfe-fea135df56fd | note | Requirements / Reference - R50 Cl 4
73e2613e-4b54-5ece-b521-e11540556c4f | note | Acceptance Criteria - Prior to mixing, compact the layer to a minimum of 95% relative compaction (Test Method T166) and trim the surface parallel to the Designed Finished Surface Level | Acceptance Criteria - Prior to mixing, compact the layer to a minimum of 95% relative compaction (Test Method T166) and trim the surface parallel to the Designed Finished Surface Level
84d55851-31fe-5582-866c-6f255d906c35 | note | Prior to spreading the binder, tyne and/or rip the insitu material to facilitate insitu mixing, taking care not to disturb any lower layers | Prior to spreading the binder, tyne and/or rip the insitu material to facilitate insitu mixing, taking care not to disturb any lower layers
d04f7e5a-f282-5370-839a-508b8b46604f | note | Provide binder type, spread rate and stabilisation depth at least 5 working days before commencing any stabilisation work.
269d7e48-098a-5c99-9a7d-55a260ab864f | note | Determine the spread rate of the binder as per the specified or proposed mix design. When using lime, adjust the spread rate to accommodate any variation in lime index between the source of lime used in the mix design testing, and the lime delivered to site | Determine the spread rate of the binder as per the specified or proposed mix design. When using lime, adjust the spread rate to accommodate any variation in lime index between the source of lime used in the mix design testing, and the lime delivered to site
4f8059b5-f564-59fd-be83-4d23f01374e7 | note | Determine the actual spread rate achieved for each spreader run using Test Method T136
88555f26-eac1-527a-aaee-07f889743806 | note | Where quicklime is used as a binder, commence slaking of the quicklime within 30 minutes after spreading by spraying water on the spread quicklime. Repeat until slaking is complete. | Where quicklime is used as a binder, commence slaking of the quicklime within 30 minutes after spreading by spraying water on the spread quicklime. Repeat until slaking is complete.
0ce9f27e-0efa-57ae-9a0b-79c597b941d1 | note | Apply water uniformly and avoid allowing water to concentrate in ruts or hollows. Use town water where suitable and where approved for use in the works. Water to be free from oils, acids, organic matter and any other matter which could affect the stabilisation reaction | Apply water uniformly and avoid allowing water to concentrate in ruts or hollows. Use town water where suitable and where approved for use in the works. Water to be free from oils, acids, organic matter and any other matter which could affect the stabilisation reaction
cce66148-8dc1-52a4-9f2f-29241e6010d6 | note | Provide sufficient water storage capacity at the plant and ensure a continuous water supply throughout the stabilisation operation
844ce1cb-8fe8-5634-a9c8-d17a489e7e8c | note | Develop a work method with a target moisture content envelope for the work. Moisture must be uniformly distributed throughout the depth immediately prior to compaction | Develop a work method with a target moisture content envelope for the work. Moisture must be uniformly distributed throughout the depth immediately prior to compaction
1d7d2251-8a28-5d41-8c9e-e651dd9c81eb | note | For insitu stabilisation, use purpose built mixing equipment which is suitable for the depth and area to be stabilised, such as a stabiliser | For insitu stabilisation, use purpose built mixing equipment which is suitable for the depth and area to be stabilised, such as a stabiliser
40383efc-173f-5c85-bf69-eed89e0d3f20 | note | Replace worn or damaged mixing blades or tynes to maintain mixing efficiency
d15ee1e8-9144-5ebc-a09e-df353f7a0ed1 | note | Comments / Attachments / Records - Relevant Lot Records
| section | 6 - Stabilisation – Plant Mixed Material
| checkpoint | VERIFICATION
35ef2ae2-74ab-5c15-893a-2bd6700576bc | note | Requirements / Reference - R50 Cl 5
97bdf598-2d0c-5b73-ab45-9313e3c4ee31 | note | Acceptance Criteria - Carry out premixing of the material in a stationary ‘driven pugmill’ mixing plant. Before commencing the mixing, calibrate the mixing plant to determine the rate of addition of the binder at various plant speeds. Method of calibration of mixing plant to be determined by Subcontractor and reviewed by Abergeldie. Typically this will be done with calibration certificates. Additionally, prior to commencement of main works a trial section will be completed as per R50 Clause 7.1. A new trial will be required if there are any changes in equipment, materials, mix, plant or rate of work | Acceptance Criteria - Carry out premixing of the material in a stationary ‘driven pugmill’ mixing plant. Before commencing the mixing, calibrate the mixing plant to determine the rate of addition of the binder at various plant speeds. Method of calibration of mixing plant to be determined by Subcontractor and reviewed by Abergeldie. Typically this will be done with calibration certificates. Additionally, prior to commencement of main works a trial section will be completed as per R50 Clause 7.1. A new trial will be required if there are any changes in equipment, materials, mix, plant or rate of work
7425484b-84d1-5381-96f2-f400307ed77b | note | Continuously feed the component materials of the mix (including water where necessary) into the pugmill. Mix together for at least 30 seconds once all materials have entered the pugmill | Continuously feed the component materials of the mix (including water where necessary) into the pugmill. Mix together for at least 30 seconds once all materials have entered the pugmill
8f009b2a-fafe-58e9-ad82-09d2c9c96f1f | note | The mixing operation must avoid segregation occurring in the mix. Do not use quicklime as the binder when mixing by stationary plant. Remove any split binder within 4 hours | The mixing operation must avoid segregation occurring in the mix. Do not use quicklime as the binder when mixing by stationary plant. Remove any split binder within 4 hours
9c64a2eb-ea8e-5760-b945-818449d697ef | note | Maintain the actual rate of incorporation of binder to within 10% of the specified rate.
2b1f554b-27ee-51fb-9ecc-b161cccf37de | note | If the mix is delivered in open bodied vehicles, cover the load to minimise moisture loss during transportation to site. Control the moisture of the delivered mix to 60-90% of optimum moisture content (OMC) using Test Method T162 | If the mix is delivered in open bodied vehicles, cover the load to minimise moisture loss during transportation to site. Control the moisture of the delivered mix to 60-90% of optimum moisture content (OMC) using Test Method T162
eff4e2c6-580e-5b95-afa2-779a5941238c | note | Take samples of the mixed material before placing to determine the field moisture content. Complete testing as per T162 as soon as practicable after mixing but no later than 8 hours after mixing | Take samples of the mixed material before placing to determine the field moisture content. Complete testing as per T162 as soon as practicable after mixing but no later than 8 hours after mixing
7a02b97b-0b0e-5c00-b7b7-139144e8444f | note | Immediately prior to placement, lightly scarify or tyne the target surface to a depth not more than 25mm. Do not incorporate segregated or non-uniformly mixed material into the works. Place and spread the plant mixed material such that it can be compacted and trimmed to achieve the requirements of TfNSW R44 Spec. | Immediately prior to placement, lightly scarify or tyne the target surface to a depth not more than 25mm. Do not incorporate segregated or non-uniformly mixed material into the works. Place and spread the plant mixed material such that it can be compacted and trimmed to achieve the requirements of TfNSW R44 Spec.
0d1a8b06-daf5-589d-8ade-516ea4d63187 | note | Comments / Attachments / Records - Relevant Lot Records
| section | 7 - Completion of Works
| checkpoint | VERIFICATION
7c4dfb73-b5fc-58a2-b75e-116746b9d971 | note | Requirements / Reference - R50 Cl 6
9e6ed917-d6e1-5fcf-80bb-76174da8b4fe | note | Acceptance Criteria - Ensure the entire process of mixing the material, placement, and the final compaction and trimming are a continuous operation | Acceptance Criteria - Ensure the entire process of mixing the material, placement, and the final compaction and trimming are a continuous operation
5db88f87-46e2-55fb-830f-db41991c045a | note | After spreading the plant mixed material or mixing the binder into the insitu material, commence compaction immediately. Compact material to achieve the requirements of R44 and Table R44.10 | After spreading the plant mixed material or mixing the binder into the insitu material, commence compaction immediately. Compact material to achieve the requirements of R44 and Table R44.10
5edc3f5e-2d93-5873-be54-aa711cf96754 | note | Following compaction, trim the surface to the required heights shown on the drawings and within the tolerances of R44 and Table R44.11. Do not reuse any cut material taken during the trimming, re-use it as earth fill or dispose of it | Following compaction, trim the surface to the required heights shown on the drawings and within the tolerances of R44 and Table R44.11. Do not reuse any cut material taken during the trimming, re-use it as earth fill or dispose of it
96de3d4b-304f-5928-8b6d-5904b8cd8f0f | note | For quicklime, hydrated lime, or slag/lime blend binders, complete compaction and trimming within 24 hours after commencing the mixing. Reworks may be carried out up to 24 hours after mixing following the Principal’s approval | For quicklime, hydrated lime, or slag/lime blend binders, complete compaction and trimming within 24 hours after commencing the mixing. Reworks may be carried out up to 24 hours after mixing following the Principal’s approval
b77948ea-6da2-5989-904a-5f5b4116baa9 | note | For cement binders, complete the compaction and trimming within 2 hours after commencing the mixing. Reworking is not permitted | For cement binders, complete the compaction and trimming within 2 hours after commencing the mixing. Reworking is not permitted
b05ab343-b496-5554-91f0-68329db04792 | note | Compact construction joints such that all material complies with this Specification and the material on either side of the joint is not damaged | Compact construction joints such that all material complies with this Specification and the material on either side of the joint is not damaged
7ab6acfd-8c59-5250-b356-eb3d534ffcb9 | note | Take note of any Construction Joints- Longitudinal and Traverse Joint for both Insitu and Plant Mixing and Placing.
6eb1e88b-fd20-581c-8e81-7c2c1f1f5d0b | note | Protect stabilised layers against rapid drying by keeping the surface continuously damp until a covering layer is placed
bb43bab6-6c05-5658-b099-ce516dc1923d | note | If stabilised layer lies immediately beneath the pavement, and a pavement layer will not be placed within 5 days of the completion of stabilisation, apply a layer of rapid setting bitumen emulsion at the rate of at least 0.5L/m2, within 2 days of the completion of compaction and trimming. | If stabilised layer lies immediately beneath the pavement, and a pavement layer will not be placed within 5 days of the completion of stabilisation, apply a layer of rapid setting bitumen emulsion at the rate of at least 0.5L/m2, within 2 days of the completion of compaction and trimming.
f0f8b76c-7a5c-5f71-8c84-57e3e69af89e | note | Do not allow any trafficking from unrelated plant or equipment until compaction of the stabilised surface is complete
671fd490-d049-56cb-bb31-5f0962b2bd99 | note | Comments / Attachments / Records - Relevant test and survey records (where applicable)
| section | 8 - Conformity
| checkpoint | VERIFICATION
a6731791-6a10-5a53-9c0b-4a22e6ac5427 | note | Requirements / Reference - R50 Cl 8
51602b21-2e69-5fbe-baa5-073d885c8753 | note | Acceptance Criteria - For insitu mixing, determine the uniformity of mixing across the vertical direction by comparing the added binder content of the top and bottom halves of a test hole as per AS 5101.3.2. | Acceptance Criteria - For insitu mixing, determine the uniformity of mixing across the vertical direction by comparing the added binder content of the top and bottom halves of a test hole as per AS 5101.3.2.
98d83f0d-1f03-5376-907d-a11d383498bd | note | Determine the characteristic relative compaction as per TfNSW R44 Clause 7.3, noting that the sample for determination of the maximum density of the stabilised material in the layer must be taken as soon as practicable after mixing (insitu mixing) or placement (plant mixed), and before compaction. Compact the sample within 3 hours of sampling. The compaction results must conform to the requirements of TfNSW R44 | Determine the characteristic relative compaction as per TfNSW R44 Clause 7.3, noting that the sample for determination of the maximum density of the stabilised material in the layer must be taken as soon as practicable after mixing (insitu mixing) or placement (plant mixed), and before compaction. Compact the sample within 3 hours of sampling. The compaction results must conform to the requirements of TfNSW R44
6a24f50b-2255-54d2-8cda-4d3cb77aff77 | note | Where stabilisation is undertaken to meet the CBR and/or PI requirements of TfNSW R44, the stabilised material must conform to these requirements, following completion of stabilisation | Where stabilisation is undertaken to meet the CBR and/or PI requirements of TfNSW R44, the stabilised material must conform to these requirements, following completion of stabilisation
| section | Lot Verification
| checkpoint | Lot Verification complete
42aa8fe5-459e-581b-b919-d5f316a8e244 | textbox | Lot Verified By:
6f55e709-34d6-5a1d-b2ca-dc2b4bc99cfc | textbox | Lot Closed Date:
1b4eab8a-51df-59d5-a37f-979d418f2c10 | button | Submitted to Client | Yes, No, N/A
883cd6f0-123a-5a4d-9c9e-c2ebbb978978 | button | Reviewed by Client | Yes, No, N/A
12df8abb-139f-5527-a5d7-a384901b386a | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 11 - B54 Driven Tubular Steel Piles Rev 0 |  | ITC 11 - B54 Driven Tubular Steel Piles Rev 0 | e0bc39c6-b7cd-4e08-be1d-14a116c5f2bd
| section | Lot Information
| checkpoint | Lot Information complete
ca6a3a5c-5606-5d63-b262-15c7fc84820c | textbox | Lot Opened On
8d4b10c3-8fe5-502a-9376-81fce28d7a5a | textbox | Date of Works
03205c77-5ae5-5ef5-896c-318fbc011b68 | textbox | Lot Type
98ef5d2d-7a57-5f3e-ba6d-e0264fa2196b | textbox | Start Chainage
1cdd33fa-5da1-5d70-8fdd-889a418db2ae | textbox | End Chainage
750b4d43-f303-5a2b-8e10-e7d7567711cc | textbox | Offset
953cd0ee-8d04-5392-ad68-6bf4490dba9a | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
290a61a5-e1ab-5baa-99d3-64cdcaecf4d0 | note | Requirements / Reference - Project Safety Plan
de56971f-9ee0-5589-aac5-9859b1a87bde | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
1236fae6-d572-5f0b-8969-0cae53ac7be9 | note | Required Safe Work Method Statements completed and signed
caa5c22b-9f74-5b17-b9dc-09fce957f2b3 | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
28a57e2a-69be-5d7f-898c-2530ad019cb8 | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
841a4205-0f0c-54b0-b698-857d32f50e8c | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
ccaf0111-8bde-5dd8-8cc2-9b526cb82405 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Materials
| checkpoint | VERIFICATION
961b297b-6896-5c25-8209-ccd5670d676e | note | Requirements / Reference - B54 Cl 2
b7249b86-2b3a-581d-88cb-82ab2ec9066d | note | Acceptance Criteria - Materials must be in accordance with the Drawings and this Specification. Where shown on the Drawings, supply and fix steel end plates or driving shoes to the pile toes prior to driving
1c49c287-a2f8-52b3-a11f-2795aeaeba4a | note | The following steels may be used: AS 3678 (Grades 250 or 350), AS 1548 (Any grades) or AS 1594 (Grade HU 240)
09d75523-ca48-5604-9daa-f53598641a92 | note | Provide evidence that materials comply with the relevant Australian Standards and TfNSW specifications. Provide material test reports as per Annexure B54/C2
ff5e49ea-ac8b-5fab-8dfd-62e8b2108377 | note | Comments / Attachments / Records - Material test reports
| section | 4 - Construction of Temporary Works
| checkpoint | HOLD POINT
4b3d98a6-a79c-52ea-9aeb-4fb605b9bf70 | note | Requirements / Reference - G1 Cl 26
1486670b-a07a-5b87-b69f-2db0b2ed34ee | note | Acceptance Criteria - As per Item 5 above, design lifting points and the like and submit details for piles as a temporary works design in accordance with TfNSW G1 Clause 26
672a381c-9915-572b-8819-b43b77f603e1 | note | HOLD POINT: Construction of temporary works
95dcd452-3b5a-5594-9502-7432fe6cf1fb | note | At least 15 working days prior to construction of temporary works, submit the Design Report (including drawings and methodology, if applicable) for proposed temporary works, including design certification
7ac6232e-f183-5eef-94f3-a2150b9fed2e | textbox | HOLD POINT NUMBER:
bb6d850a-0b46-586a-9b11-192affac2989 | textbox | DATE SUBMITTED:
1553be68-25ce-5203-a1b7-4b4b2bdb68f1 | textbox | Work Start Date:
ff9f1228-b5cb-5c2e-b461-20eeaade603a | textbox | SUBMITTED BY:
2bfe4307-5ba6-5ef2-ada3-5288a7986809 | textbox | SPECIFICATION AND CLAUSE:
f0c520bc-cb80-55fc-8284-b847ee7db3bc | textbox | HOLD POINT DESCRIPTION:
25b703ee-f070-5096-b8fe-a5bb01902a82 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Use of Temporary Works
| checkpoint | HOLD POINT
8e4a937e-53aa-5d50-b6f1-b4caec91705c | note | Requirements / Reference - G1 Cl 26
e37b09ea-6bcb-5759-b667-a05530927b0b | note | Acceptance Criteria - HOLD POINT: Use of temporary works
96eca1f2-950e-50d7-971d-3536aa4d42fc | note | At least 5 working days prior to use of temporary works submit the construction certification to the Client
ecd4aab3-9868-5e8d-b5b9-57f01bc0b0f1 | textbox | HOLD POINT NUMBER:
c07aa321-0b55-5174-b399-e9d8db81fc86 | textbox | DATE SUBMITTED:
a4f382ee-1031-525c-9810-aad41f09a825 | textbox | Work Start Date:
6309f6a0-4811-58ef-af63-8ffeb5fe7d86 | textbox | SUBMITTED BY:
2f77aefa-2a01-5f5b-910c-ed1a71a3a9e7 | textbox | SPECIFICATION AND CLAUSE:
231bc3e5-e520-51d9-8733-690414e6da25 | textbox | HOLD POINT DESCRIPTION:
758ae7f2-e0ea-5048-a928-b4d922343100 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 6 - Site Preparation
| checkpoint | HOLD POINT
f7761e0f-9af0-5a87-b7e8-f4a7f886a855 | note | Requirements / Reference - B54 Cl 4
71437ffe-6de3-5b07-8f3c-0ff1ed8eea06 | note | Acceptance Criteria - Undertake temporary works to access the required “new borehole” at pier one and carry out the required geotechnical investigation as a priority (refer to TfNSW G1 Cl 9.2)
e6a87d87-aceb-552a-a05b-56677368d517 | note | Prior to commencing pile hole excavation, drill an additional borehole and take 50mm diameter cores and other appropriate tests / investigations to confirm the geotechnical assumptions for piles at Pier 1. The Geotechnical Engineer must also be in attendance during any borehole / coring and other tests / investigations. The Geotechnical Engineer is to log these activities and make their interpretations available for the Principal’s review
146c75b9-1d1b-56fd-a4d3-a48bf964f446 | note | Commence taking of the core samples and other appropriate tests/ investigations at a level that is at one metre above the level of the top of the rock socket shown on the Drawings, for that pile, to a depth that is at least 3 m or 3 pile diameters, whichever is the greater, below the pile Contract Level
9569e3a9-4587-5262-8040-9fc61fc25721 | note | Log the cores in accordance with AS 1726, place the cores in suitable core boxes and make them available for inspection by the Principal as required
2a263f92-0e75-5e23-acbf-ac87ac36449e | note | Carry out any excavation or backfilling in the vicinity of the piles in accordance with Specification TfNSW B30.Stage the driving of the piling as per the requirements of B54 Cl4 .2
de473b93-c000-5d87-863c-81e7a84fcd6d | note | Clause 4.2 - Where the level of the bottom of the pile cap is more than two metres below the existing natural surface level, prior to the driving of the piles, carry out excavation for the pile cap to a level which is not more than two metres higher than the level of the bottom of the pile cap, to reduce any temporary contribution of the ground above the bottom level to the pile resistance measured during driving
f691f49c-9123-5057-9115-bd5b8e6c1bee | note | HOLD POINT: Commencement of construction of any piles for Pier 1. At least 20 working days prior to commencing construction of any piles for Pier 1, submit the logged boreholes / cores and other appropriate tests / investigations, as well as the Geotechnical Engineer’s interpretations
040a617b-0ccd-5346-aa91-cc579c5f7831 | textbox | HOLD POINT NUMBER:
c0f1cf34-d92f-51af-ad6c-57f4e50dcfe6 | textbox | DATE SUBMITTED:
6e57fceb-5523-5003-bf79-20a0ffb5defc | textbox | Work Start Date:
dece3266-04dd-5daa-891f-3e30e991f0de | textbox | SUBMITTED BY:
e4327a1a-41d8-5b82-aeb5-17c36aadced1 | textbox | SPECIFICATION AND CLAUSE:
192d3bab-b4d2-5076-9acc-175d886bef90 | textbox | HOLD POINT DESCRIPTION:
3652714c-5b54-5e0f-9648-1db930b03635 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Piling Plant and Piling Method
| checkpoint | HOLD POINT
a9120d00-9702-5aa3-9ca0-7e3c1777045c | note | Requirements / Reference - B54 Cl 5 B54 Cl 5.3
ad6ad8d8-21cd-54b7-9b7d-9451006bd8b6 | note | Acceptance Criteria - Without limiting the requirements of TfNSW G22, prior to bringing any piling plant to site, provide drawings and calculations with certification from a suitable Chartered Professional Engineer of any working platforms or supports required to keep the piling rig stable and safe during piling operations. This also applies to any barges used to keep the piling stable and safe during piling operations
37128178-cd63-5c95-ba9a-b8948d445a0e | note | Drive piles using diesel, compressed air, drop or vibration hammers or a combination of these. Do not use clutch operated drop hammers
b97d7789-9852-585a-b3a9-0f46549f2615 | note | Maintain the equipment and its packing, replace packing regularly to maintain efficient cushioning
c3c9f93e-0d64-50bb-8a39-472b678b13ce | note | Pre-boring may be used to assist in achieving the Minimum Penetration Depth specified. Where pre-boring is used, submit details of the proposed pre-boring equipment and methods including pre-boring diameter and certification by a suitably qualified engineer that the proposal will not be detrimental to the pile performance. The depth of pre-boring must not exceed the Minimum Penetration Depth specified
cec00736-de7f-5902-8b1a-a1c6f6e07c59 | note | HOLD POINT: Setting up of piling frame and driving of all piles, including Test Piles and Representative Piles. Submit details of the proposed driving equipment and method, together with certification, including calculations by a Chartered Professional Engineer with membership of Engineers Australia practicing in the field of Civil or Structural Engineering or equivalent, and verifying that under the proposed site configuration and site conditions, the equipment nominated will be used within its safe working capacities
bd20bf34-d602-5377-8c5f-cf6cf3b79396 | textbox | HOLD POINT NUMBER:
d8e9b1c0-61d4-5f6f-b54d-88e0383104e1 | textbox | DATE SUBMITTED:
4ca768c5-941c-57bb-b54f-23b51bccbd58 | textbox | Work Start Date:
c222887c-d921-5935-81f2-0c9cb37d94d9 | textbox | SUBMITTED BY:
31511a25-2882-5580-8936-28d48a73d7ee | textbox | SPECIFICATION AND CLAUSE:
8eb9e47c-b3c0-5fbf-a99d-806198f4ecbd | textbox | HOLD POINT DESCRIPTION:
95cc2390-7e14-5abd-9f77-41b025dc11e5 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Test Pile Notification
| checkpoint | HOLD POINT
2c43c71a-ecb0-5890-9cfb-261745171e98 | note | Requirements / Reference - B54 Cl 7.1
80246ba8-36b0-581d-acc7-17cda9a07e38 | note | Acceptance Criteria - Drive Test Piles at the locations nominated on the Drawings. Drive all Test Piles prior to driving the remaining piles.
8bd1f7e5-b035-56be-a514-074da529dfc0 | note | HOLD POINT: Driving of each Test Pile. Submit notification of the time and location of the driving of each Test Pile at least one working day prior to commencing
c7172e26-324a-5b66-9b50-d07daeef1e64 | note | NOTE: Test Piles will be completed as part of the Test Piling package of works for this project, hence this Hold Point is not required
9ed6a35b-40ff-5d13-9255-bd5bd42879bf | textbox | HOLD POINT NUMBER:
7b8f41ab-6067-58bc-8853-49c996581e98 | textbox | DATE SUBMITTED:
bbe7e201-581c-51f9-86fb-f6d414d35f7b | textbox | Work Start Date:
865622ee-4a20-55d0-86f6-126896e4de60 | textbox | SUBMITTED BY:
00284192-8543-5431-9478-3a0cbea895ce | textbox | SPECIFICATION AND CLAUSE:
b5c22c29-04da-5d43-b93d-657914fe6c1c | textbox | HOLD POINT DESCRIPTION:
c569d1f6-1b31-587f-93de-9cd83f4738fa | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Test Pile Results
| checkpoint | HOLD POINT
1982b1ae-5d8e-5206-9fe7-eb3480ee43a2 | note | Requirements / Reference - B54 Cl 7.2
c5abee62-c6c3-5e29-a5df-c46b91978709 | note | Acceptance Criteria - Record the number of blows per metre for Test Piles over the whole driven length. For the last ten blows, record the final Set in mm and the average Temporary Compression per blow
0d490a56-5b0d-5838-b8f3-3f8ee5b70438 | note | Unless shown otherwise on the Drawings, perform Dynamic Testing over the whole driven length, and record data for analysis from the start to the end of driving on the steel tube alone. Verify the resistance of the Test Pile before or after filling the tube with concrete, as specified on the Drawings
4e20ecbf-7597-5317-9938-1e95eee843cc | note | Unless specified otherwise, carry out a restrike test in accordance with Clause 13.3 after a minimum period of 24 hours
22174823-4f86-5b1a-9cff-522faa471053 | note | On completion of driving the Test Piles, submit to the Principal the driving records and Dynamic Testing reports of the Test Piles. Allow three working days for the Principal to consider the submission and instruct the lengths of the remaining piles
5017da66-bdea-5b62-8810-af48ded90d13 | note | HOLD POINT: Making up the pile lengths, and driving of piles represented by the Test Piles. Driving of all piles, other than Test Piles. Submit driving records and Dynamic Testing reports of all Test Piles, including restrike test results
debb5d0e-a49c-5d19-8fdc-98880ce99289 | note | NOTE: Test Piles will be completed as part of the Test Piling package of works for this project, hence this Hold Point is not required
aaca21d7-c2b6-5177-aff6-29b72327d6f2 | textbox | HOLD POINT NUMBER:
7102cfd5-8246-5add-a91c-951029d3e0b5 | textbox | DATE SUBMITTED:
65c35be1-076b-586d-8fbd-73ce54b1b258 | textbox | Work Start Date:
b2d51462-df13-5357-aca6-e0fae225eaf1 | textbox | SUBMITTED BY:
8f2922e8-3e56-5fce-bcc1-5c0c2a09beec | textbox | SPECIFICATION AND CLAUSE:
eb752c57-bfca-56de-9f0f-cc479d1cbdfd | textbox | HOLD POINT DESCRIPTION:
042f8642-2da6-580f-9ae3-c4a67204448f | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 10 - Representative Piles
| checkpoint | HOLD POINT
c13760bf-7f8c-5a0a-a295-ec5fe77b2a73 | note | Requirements / Reference - B54 Cl 8
2f26bf8c-312d-51c6-9bc4-f6b3557e7846 | note | Acceptance Criteria - Drive Representative Piles at locations nominated on the Drawings
e51aef72-ef6b-5406-98ea-e94971133642 | note | Record the number of blows per metre for Representative Piles over the whole driven length. For the last ten blows, record the final Set in mm and the average Temporary Compression per blow
aad1b898-7a6f-50e8-9eb6-427426eea919 | note | Perform Dynamic Testing over the whole driven length and record data for analysis from the start to the end of driving on the steel tube alone. Verify the resistance of the Representative Pile before or after filling the tube with concrete, as specified on the Drawings
cf2b72e9-3f83-561d-850b-228b77ff1422 | note | Unless specified otherwise, carry out a restrike test in accordance with Clause 13.3 after a minimum period of 24 hours
1d1f5472-0d76-58d7-8012-8cb148ce75c7 | note | If there is any reason to believe the geotechnical conditions are not essentially uniform, the Principal may nominate additional piles to be Representative Piles
1f91b422-0477-5a5a-8fea-c9635b17e807 | note | HOLD POINT: Driving of each Representative Pile. Submit notification of the time and location of the driving of each Representative Pile at least one working day prior to commencing
345de2a9-0372-588d-ba14-99074e46858d | textbox | HOLD POINT NUMBER:
913cd22e-7237-57bb-87e1-87842b0664dc | textbox | DATE SUBMITTED:
b4f018fd-7996-59aa-a6b3-4fa53b1d4d0c | textbox | Work Start Date:
4f35af16-ea56-5245-bf12-46f03c120450 | textbox | SUBMITTED BY:
712d59f7-5df1-536a-8ae9-a0a0224b2219 | textbox | SPECIFICATION AND CLAUSE:
c1819626-96fa-5846-afaa-c2e6b9f601d7 | textbox | HOLD POINT DESCRIPTION:
040032da-2f34-5591-baf9-f6f12d52cf03 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - Driving Operations
| checkpoint | VERIFICATION
db71bee2-88d3-5d9f-a4a1-bb299c016c76 | note | Requirements / Reference - B54 Cl 9
dc319db9-1d80-56b4-bcc0-5db7feb579f5 | note | Acceptance Criteria - Scare fish prior to driving, including undertaking some initial “warning strikes”
348e956f-dbf5-5793-a6ba-a0a6dbd24edf | note | The Piling Supervisor must supervise and control the driving at all times
b6fa56af-fc3f-536f-ae42-125f48b8991e | note | During all driving operations, the driving equipment, procedures and parameters must be in accordance with the procedures established during driving of the Test Pile / Representative Pile. Confirm during driving, using the records of the Test Pile / Representative Pile, that the pile is being driven in the same manner, using records of number of blows per metre, Penetration and Temporary Compressions
d7ed9099-80ae-508f-9d40-4d80a3728425 | note | At all times during the driving operation, adjust the driving equipment such that the blow of the hammer is directed centrally and axially on the pile head
54349f81-23f5-547c-9069-6816e783fb92 | note | Submit to the Principal each week a day-by-day program showing the scheduled work for pile hole excavation and / or reinforcement cage and concrete placement
59b9e9ad-74ab-537d-9bcc-1d7d90def911 | note | During driving and excavation of each pile, the Geotechnical Engineer must also be in attendance. They are to verify that driving operations conform to the requirements of the Specification and that the requirements of each pile are satisfied (or better) as per the Drawings
4d148872-e544-5465-92f1-8bfc72ae03e3 | note | Submit to the Principal for acceptance, details of relevant qualifications and experience of the Geotechnical Engineer
e6c51db8-f5f9-53f4-be82-cb95b7ff6d2f | note | Tolerances on pile installation must conform to Section 7 of AS 2159, except that the inclination tolerance for vertical piles is 1%, measured on the internal side of the casings
a84b0780-6156-5b3f-8974-afdd101272da | note | Remove all excavated material from the site, unless specified otherwise. Collect and treat water, as well as any waste concrete, as per Specification G36
cab94c71-6106-5585-a8bc-32cf6fd351a8 | note | Protect each pile hole to prevent personnel, site run-off and loose material from falling in during excavation. Make each pile hole safe with appropriate measures, including covering it with a secure lid whenever the pile is not under construction. Leave the finished top of the casing at least one meter above ground level to prevent personnel and loose material from falling into the pile hole.
8f246ce9-2803-535c-9cbc-74586883b57d | note | Comments / Attachments / Records - Details of relevant qualifications and experience of geotechnical engineer
| section | 12 - Driving of Each Piles
| checkpoint | WITNESS POINT
76ce7dcf-dbab-54cd-ba4b-35d6a1424426 | note | Requirements / Reference - B54 Cl 9.3
dd8e38c6-c2c0-5041-b2c5-1cf4fb926d9b | note | Acceptance Criteria - WITNESS POINT: Driving of each pile. Submit notification of the time and location of the driving of each pile at least one working day prior to commencing
c038d793-9e7e-57e5-b36c-af962185b863 | textbox | WITNESS POINT NUMBER:
8d278f5f-14fc-5acc-8191-6b8107c5fce2 | textbox | DATE SUBMITTED:
05d5573c-6dcf-54f2-821a-f7f938308779 | textbox | Work Start Date:
5316e812-318a-59b1-91d9-9b1803d14c55 | textbox | SUBMITTED BY:
e4b0e929-d9ae-5083-8052-f536a4241ef1 | textbox | SPECIFICATION AND CLAUSE:
42f7e641-9032-5181-bda1-6be277fb128f | textbox | WITNESS POINT DESCRIPTION:
a47fb270-cd42-5c29-9e08-9c5cf177df72 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 13 - Driving of Any Further Piles
| checkpoint | HOLD POINT
9e0a217b-649a-5560-b0a9-c7bd8d76002b | note | Requirements / Reference - B54 Cl 9.3
abaa6fa4-7eec-5fef-bd1b-8007ed8a2b06 | note | Acceptance Criteria - During pitching, lift and support piles at the positions shown on the Drawings
e4424cdb-22ec-5398-8090-6ca64ce88e3e | note | During the initial stages of driving, do not bend or spring piles into position. At all stages of driving, the pile frame must not exert any undue lateral force on the pile. At all times, do not restrain the pile against rotation about its longitudinal axis
b8b27cc4-7577-559f-8ef0-4a60deb44ea6 | note | If damage occurs to the head of the pile or the rest of the pile, consult B54 Cl 9.3 for next steps
858f3152-a343-58c8-8b30-acdf6fe5147e | note | Where the pile driving equipment is altered, test the equipment to determine the relationship between the operation of the equipment and the Net Driving Energy at the head of the pile
894d2a91-7007-58d3-88f3-a53e17ea0946 | note | HOLD POINT: Driving of any further piles (For piles not founded in rock and if Minimum Penetration Depth is not achieved). Submit details of the amended driving method, together with certification that the amended driving method is likely to result in achieving the Minimum Penetration Depth before the required pile resistance is obtained
521cbd52-6249-5397-8946-83746ac3127d | textbox | HOLD POINT NUMBER:
ab05b333-98c1-509a-99e0-49bd167079bc | textbox | DATE SUBMITTED:
5e31cea6-2234-5320-ba67-df05cba8c0f2 | textbox | Work Start Date:
432fd829-2f7f-5e8b-9b7c-ea0f008992e9 | textbox | SUBMITTED BY:
daaa631d-061b-5f3a-abe8-1320c90a84f1 | textbox | SPECIFICATION AND CLAUSE:
e8ab14de-322e-52c8-bf43-e2a2a1af0712 | textbox | HOLD POINT DESCRIPTION:
c84535c6-8568-5cd6-a6a9-2ec2ff0619b4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 14 - Backfilling and Concreting
| checkpoint | HOLD POINT
f8e1ae92-9d69-5e40-805f-811408fbbf1f | note | Requirements / Reference - B54 Cl 11
fdac7b6b-5d4b-5d27-a7a7-a708962778d4 | note | Acceptance Criteria - Prior to concreting a pile, bring the bottom of the hole to a clean and stable condition and maintain in that condition without contamination or softening until concrete is placed. If this cannot be achieved, place a concrete plug and allow the concrete to set before the reinforcement is placed in position
fa4e3ecb-f73f-52c1-a3ce-f82056393e18 | note | Supply and place reinforcement in accordance with Specification TfNSW B80. Thoroughly clean the pile shaft of all loose material, including any material adhering to the inside of the tube, before the reinforcement is placed
9fb0a22c-44dc-5ad0-b84a-30a093441467 | note | Supply and place concrete in accordance with Specification TfNSW B80. Use only high workability concrete or self-compacting concrete conforming to Annexure B80/G. Use a rigid tremie pipe and a hopper to place concrete in piles. Where a concrete pump is used, a flexible rubber hose may be used to transport the concrete between the discharge hopper of the pump and the hopper of the tremie. The tremie pipe must be watertight throughout
1026462a-20b3-5ac7-83b3-131fdcff428a | note | Insert the tremie pipe inside the pile hole until the bottom end of the tremie is at the base of the pile, before charging the tremie with concrete. In wet pile holes, do not commence concreting until the pile hole is filled with sufficient head of water as to equalise the external water pressure from the surrounding ground. When placing concrete in water, a larger over-pour may be required.
6c40f37d-8873-52d1-9792-6a7cdb3b54ba | note | Discharge any slurry used to prime the concrete pump and tremie pipe away from the pile hole
513eaac3-9c20-5bc0-8ad7-f5ee8b76fee8 | note | Place concrete in such a manner and with such consistency that pockets of air, water, or ground materials are not entrapped in the concrete, and the space between the reinforcement and the side walls of the hole are completely filled with compacted concrete
d9b53bb7-d6e5-5e62-86ef-9b1871eb226b | note | Provide a continuous supply of concrete such that each pile hole is concreted in one uninterrupted operation
e79ac326-4e77-5d80-97be-5fe27f265b31 | note | Continue pouring concrete until the excessive water, mud or other non-conforming materials included in the concrete, are discharged from a point in the pile tube, and managed in accordance with environmental requirements
f98c9cae-18c7-54c4-a71a-a45bc0fbe8b9 | note | HOLD POINT: Backfilling the pile shaft (if applicable) and cutting off of a pile after completion of driving (upon completion of driving of each pile). Submit driving records and survey report showing the alignment and plan position of the pile. Also include certification by the Piling Supervisor that the pile has been driven in accordance with this Specification
5626250f-e02f-5a7b-84b6-4382bce348d7 | textbox | HOLD POINT NUMBER:
5777ee07-b1cb-50cd-bdd8-bff981626357 | textbox | DATE SUBMITTED:
55e2cb37-0bc0-5697-bbb1-7f4718c28f5c | textbox | Work Start Date:
c4ba344f-0058-51ae-9632-d7c7be5e4665 | textbox | SUBMITTED BY:
f2a34fea-f457-5009-92a1-67eb3b2b73f5 | textbox | SPECIFICATION AND CLAUSE:
39826644-536a-5a39-9ee5-33c83c52d5a9 | textbox | HOLD POINT DESCRIPTION:
97e0eae3-bd28-56bc-b20d-8c963032576d | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 15 - Dynamic Testing
| checkpoint | VERIFICATION
f4057a31-f52d-532f-b0bd-b8b7891da7c7 | note | Requirements / Reference - B54 Cl 13
d978bed1-0486-58ef-9f61-9ed8f8bbbd5f | note | Acceptance Criteria - Carry out Dynamic Testing in accordance with this Clause and AS 2159, using an approved organisation with approved equipment and dynamic testing system and analysis, as listed in the “Lists of TfNSW Approved Bridge Components and Systems”
2216b373-a783-5b76-a478-f00f3f662fa8 | note | Use the following testing procedure: Attach four bolt-on transducers to the pile at a min. of 1.5 times the maximum pile width below the head of the pile in accordance with the requirements of the system supplier. Following the connection of the transducers to the analyser, strike the pile with sufficient energy to verify the required pile resistance. Allow for any required re-set of relaxed pile to complete the dynamic testing
937e25c1-2367-589b-b837-e3e12cb07150 | note | Avoid pile damage due to overstressing, and record the driving stresses, measured pile resistance, Nominal Driving Energy, measured Net Driving Energy and Set
70de8b69-36ac-57d7-84b8-4347e68348bc | note | When a restrike test is required, consider only the first 20 blows at the beginning of the driving to be part of the restrike test. Measure the driving parameters at the required Net Driving Energy on blow numbers 6 to 15 inclusive
c951ad18-e5bf-5c76-9794-f83a6e4edac8 | note | Analyse the dynamic test results for each pile tested. Analyses must include full Dynamic Analysis using measured field parameters of the test data and resistance versus Set curves, when requested by the Principal, showing a minimum of six different resistances and the corresponding blowcounts
8b6bd991-ee5a-57e8-8100-09d54200dc92 | note | Provide the Principal with two copies of a report for each pile tested, including details such as complete PDA output (or approved equivalent) for all blows and CAPWAP analyses (or approved equivalent) for selected blows
e39173a1-7b57-5165-8249-11c879d7ef78 | note | Comments / Attachments / Records - Dynamic test results
| section | Lot Verification
| checkpoint | Lot Verification complete
45d39f34-5dec-576a-989c-7888df18f124 | textbox | Lot Verified By:
651839d6-77f8-5034-ab24-4da71511d702 | textbox | Lot Closed Date:
56e01d03-5563-51cb-a30c-989086072a3e | button | Submitted to Client | Yes, No, N/A
0823ec7d-648a-5049-94a3-5e34f9fb942c | button | Reviewed by Client | Yes, No, N/A
069d2fcf-15b3-513d-9ae5-ccb208012f19 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 12 - B59 Cast In Place Reinforcement Concrete Piles Rev 1 |  | ITC 12 - B59 Cast In Place Reinforcement Concrete Piles Rev 1 | fa7595d9-9e36-416f-b03e-9ec53c3220c0
| section | Lot Information
| checkpoint | Lot Information complete
8ab7dda2-acba-5a8c-ba9a-0759b8fdf557 | textbox | Lot Opened On
8dbed823-e335-58b7-8962-31f9503dc8c7 | textbox | Date of Works
bfb0148d-e15d-54cc-bbde-30d77486e60f | textbox | Lot Type
a374e765-47c0-539b-bd84-65d3b0d59c89 | textbox | Start Chainage
0f42c652-e0d7-458e-b7bb-e4f191e27eb2 | textbox | End Chainage
3c2a5e5d-a951-4363-8525-f0fb39550965 | textbox | Offset
71c1ad2d-6ea0-5a5f-b1eb-9571221718cf | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
478d12a7-7444-56b0-a644-b0dc696cd6f5 | note | Requirements / Reference - Project Safety Plan
64acc267-d71c-5a28-8e84-43665f55352b | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
6f5c808d-2d84-54a4-9bb6-5efb43f4165c | note | Required Safe Work Method Statements completed and signed
ccb6cb89-7f8b-51c6-856f-7cb527290654 | note | Subcontractor’s safety plan/procedure approved
c8d4b232-4243-5e81-8c20-8ce05c284823 | note | Frequency - Prior to commencing works
58e411cb-3e32-501e-9a79-227e4a566f89 | note | Comments / Attachments / Records - SWMS
| section | 2 - Environment
| checkpoint | VERIFICATION
ccd5e651-f6f9-50a8-bbbc-f5894b73de54 | note | Requirements / Reference - Project Environment Plan
527afef8-d9c8-5478-b0eb-13be8eca5d17 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
0b325e12-fb53-5cb4-8e96-0c0bb08d62ab | note | Frequency - Prior to commencing works
b4e41da5-b423-59ca-bef0-b7faa842f2f9 | note | Comments / Attachments / Records - CEMP; EWMS
| section | 3 - Concrete Mix Design
| checkpoint | HOLD POINT
48a5924f-a766-5af3-8e12-29b5a25eeeca | note | Requirements / Reference - B80 Cl 3.9.1
1f43c907-44ef-5320-b7ed-9f06e8962f69 | note | Acceptance Criteria - HOLD POINT: Use of each nominated mix
1940d4dc-c2e0-56ca-8573-695296b457ed | note | At least 4 weeks prior to the proposed date for use of the concrete mix, submit to the Principal the following:
f80ba855-a04c-5762-b19b-94209c704def | note | (a) (i) all details in Clause 3.9.3; or
2f3f1965-29f8-570f-89b0-558bff652d46 | note | (ii) mix ID and concrete mix design of a nominated mix from the Register of TfNSW Concrete Mixes
4703bf4d-58ba-5805-8007-5af72ed97d70 | note | and
2956faef-7672-52bc-90d3-89755bbacb8d | note | (b) a statement stating that the mix conforms to the B80 Specification and is suitable for its intended use
0dbd655d-62a6-5690-a505-e69e744858df | note | Frequency - Prior to ordering concrete to site
849b2e4e-5d9d-5b33-a852-df07a7c4fdc1 | note | Comments / Attachments / Records - HOLD POINT; Mix Design
4d136183-5314-5abd-a4a5-18036b4cc557 | textbox | HOLD POINT NUMBER:
7c8740c4-f2e9-5068-acb6-e8f778111614 | textbox | DATE SUBMITTED:
2c4d91f1-78d7-59ac-99fb-4a110a5fde7f | textbox | Work Start Date:
84096c9a-857a-50f6-87b4-c6f48f8cea8e | textbox | SUBMITTED BY:
419369c9-ce43-54e0-9f93-fbe9ab809c02 | textbox | SPECIFICATION AND CLAUSE:
c22366e2-6762-5f84-9ee9-02a93c8ae4bc | textbox | HOLD POINT DESCRIPTION:
711b0686-b5fb-569b-9a8e-e5a7bd5e5313 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 4 - Pour method
| checkpoint | HOLD POINT
babb6bbb-0cb8-5021-aeed-ab7c9e663acf | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing at least 2 working days prior to pour
dbc4e590-c375-524a-b908-d3c4bbedf804 | note | (a) delivery rate;
4bb58f89-d17f-570f-a96d-0764685e9c9f | note | (b) placement method and rate;
97b8ab25-03aa-5a8b-8157-c922546ef7e5 | note | (c) equipment on standby wherever required
cbb6f016-c66f-5bb1-9fca-2d800fcf15a1 | note | At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
ad4db2cf-89a1-53fc-9bc9-6f67c6af01bb | note | Frequency - Prior to concrete placement
18faf00e-fbea-584a-8927-14ab600bc149 | note | Comments / Attachments / Records - HOLD POINT; Pour Method Statement / Methodology
788c6611-6fa7-544d-b67a-f90932ca0f3c | textbox | HOLD POINT NUMBER:
dca3531a-2c14-5fce-aacf-3b9a50c2015c | textbox | DATE SUBMITTED:
f76079d7-7e6f-5c20-bfde-a916c706ba8f | textbox | Work Start Date:
ab917704-d32e-5b4e-b66d-8a3c3fb8826d | textbox | SUBMITTED BY:
9c3f6a8a-a831-5bfd-99df-f78a94115efb | textbox | SPECIFICATION AND CLAUSE:
3b56182b-c9fc-54e0-8c50-407755222840 | textbox | HOLD POINT DESCRIPTION:
09a106bb-06ca-5821-8cbb-ea6530b06927 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Delivery of Prefab. Reinforcement Cages
| checkpoint | WITNESS POINT
9fb1e760-8c5b-5323-9d2e-7e3807830833 | note | Requirements / Reference - B80 Cl 6.6.2
0a518ee1-9df0-5301-ab38-b70a88dac9f5 | note | Acceptance Criteria - Show on the shop drawings the design location(s) of lifting and transport support points for prefabricated support cages, and mark these locations indelibly on the cage during fabrication. Show the lifting requirements on a drawing on durable material, attached to the cage prior to lifting. Conform to B80 Cl 6.5 for welding of load bearing welds
ae879469-a70a-5db7-b00d-87038c398e22 | note | WITNESS POINT: Assembly, lifting and transport of cages
da192625-e69a-5837-90e9-f81980d6113c | note | At least 2 working days prior to expected date of delivery, submit to the Principal a Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
21823470-d139-5cfd-9d4c-6ea891b465c6 | note | Provide marked up shop drawings for the reinforcement as per B80 Cl 6.6.2
2a5bfc19-d2f1-534c-bfe2-e68d1edfa6bd | note | Frequency - During manufacture of the cages
f18560fb-82b0-5964-9a2d-15c66ad5b7d2 | note | Comments / Attachments / Records - WITNESS POINT; Lifting certification
c23cf578-6069-58b3-ac38-f768b1c208de | textbox | WITNESS POINT NUMBER:
1abf305a-1db6-503a-8499-17cbcf3698b6 | textbox | DATE SUBMITTED:
a9757e23-2697-52e5-a11b-5f71ea7b0c41 | textbox | Work Start Date:
60cb912b-8863-5f0c-b029-2e2adc15fc70 | textbox | SUBMITTED BY:
8a2a0834-93f9-50ac-8292-2633b21e0ab6 | textbox | SPECIFICATION AND CLAUSE:
9c2bfd0a-3156-5e1f-9656-0d17e5c36a6b | textbox | WITNESS POINT DESCRIPTION:
3b90d3ca-2614-5648-975d-c18d8a249f1b | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 7 - Program and Personnel
| checkpoint | VERIFICATION
9fac18a2-3dd1-5030-8082-23baa8fe429d | note | Requirements / Reference - B59 Cl 3
481de0d2-7d0b-58ad-890b-9da38364987a | note | Acceptance Criteria - Weekly program to be agreed with principal
c496fe1b-7263-5c24-a588-445d0b95238b | note | Geotech Engineer to determine Pile termination, if greater than 1.0 meter from the indicative levels shown on the Drawings, must advise the Principal who will review and consider the adjustments.
bf10e430-96f8-52d5-967e-8e4d41acc5c9 | note | Geotechnical Engineer attending the piling works
8d15f629-c2c2-51c5-99c6-849e9a64ec5e | note | Frequency - Prior to commencing piling works on site
34884ab1-7c39-5f9f-8c12-a360c0350ae1 | note | Comments / Attachments / Records - Geotechnical Engineer qualifications; Weekly Program
| section | 8 - Concrete Grey Cards
| checkpoint | HOLD POINT
58dce6c9-10ae-5496-b06c-637e9f3704f4 | note | Requirements / Reference - B80 Cl 7.2.2 B80 Cl 7.2.3
629a73d8-85b0-5fe2-99a3-8c7cc1e2101f | note | Acceptance Criteria - The Concrete Supervisor must hold a TfNSW Bridgeworks Concreting Grey Card and have suitable and acceptable TAFE (or equivalent) qualifications for the concrete works taking place, and must be present during all stages of the pour until implementation of the curing regime
bf7cec9c-4fe0-509d-8244-f46768d603d1 | note | Pour Crew to have TfNSW Bridgeworks Concreting Grey Card
29eee239-92f2-55d3-ae0b-69b8520ba8d3 | note | HOLD POINT: First concrete pour in the Works
59092b2b-c1eb-5f33-b16a-f68e374e4542 | note | At least two weeks prior to the first concrete pour, submit to the Principal the names of the personnel who will be involved in the relevant concreting works, which of these personnel hold a Grey Card, as well as corresponding evidence of this.
25a7f3f4-99c0-5546-8981-117549eebbba | note | At least four working hours prior to pouring concrete, provide the Principal with a statement stating that at least half of the personnel who will be involved in the pour hold a Grey Card
c1a0bcc6-7f17-5ab0-81cd-61508067cbd2 | note | Frequency - Prior to pouring concrete
def8f425-a8c0-5011-b490-21307580cb0e | note | Comments / Attachments / Records - HOLD POINT; Nominate and submit Supervisor and their qualifications; B80 Grey Cards
a9b57205-3718-5a76-9400-14d3666198d1 | textbox | HOLD POINT NUMBER:
26d224b6-e385-56df-bafb-f286fe66cd4f | textbox | DATE SUBMITTED:
32cc16cc-3b81-5f44-8ce1-99e1499a882a | textbox | Work Start Date:
4cc40020-97cf-5b92-a30d-dd651ff0d19a | textbox | SUBMITTED BY:
bbbfa199-e514-5fc4-9e29-bae584d39b0a | textbox | SPECIFICATION AND CLAUSE:
825b3b7a-bf2b-5ab6-8648-4ec46f586924 | textbox | HOLD POINT DESCRIPTION:
ad42440b-43b5-58d4-a9dc-a4a63f32ae4e | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Proposed Plant and Method
| checkpoint | HOLD POINT
2280709d-dc89-5388-b170-2acd8722eaf4 | note | Requirements / Reference - B59 Cl 3.3 B59 Cl 3.4.1
2980402f-9303-59b0-9703-2a51b0b63753 | note | Acceptance Criteria - HOLD POINT: Delivery of piling plant and equipment to the Site
a1cff189-ebe2-5c14-b192-56e0fc5e8a9d | note | Submit to the Principal details of the proposed piling equipment and method together with certification, including calculations, by a Chartered Professional Engineer, that proposed piling equipment and working platforms or supports.
aed4eaae-1b58-57f4-a90b-0ab74052fb0a | note | The piling equipment must have the capacity to excavate the pile shaft and socket in the founding material to the specified depth and diameter to achieve the design pile resistance, including the capability to excavate an additional pile depth (if required) of either 3 m or 3 pile diameters, whichever is the greater.
532a2435-5804-5fee-9521-973227678a39 | note | Without limiting the requirements of Specification TfNSW G22, prior to bringing any piling equipment or plant to the site, provide drawings and calculations certified by a Chartered Professional Engineer with membership of Engineers Australia practising in the field of geotechnical engineering (or equivalent), verifying that under the proposed set up and site conditions, the proposed piling equipment and working platforms or supports will operate safely.
677b13f9-0813-5476-845e-179db1e30b3b | note | Frequency - Prior to commencing piling works on site
1faa3a6e-fd5c-5435-801a-37a612b34cf2 | note | Comments / Attachments / Records - HOLD POINT; Piling equipment specs including piling platform signoff
621e70ad-ef9f-53ef-b46a-9f9a3f541864 | textbox | HOLD POINT NUMBER:
b6f74589-f86b-5bc3-8939-7dfe509b84e6 | textbox | DATE SUBMITTED:
c89f3d3e-b79d-5298-8bd8-29892f287f1c | textbox | Work Start Date:
54017e11-4ae3-58cb-890f-c2112aa96354 | textbox | SUBMITTED BY:
9cc23743-1acd-5212-8ceb-6b705a1d2f83 | textbox | SPECIFICATION AND CLAUSE:
fae2a4ad-d817-5f40-ace0-c468cc5bdb54 | textbox | HOLD POINT DESCRIPTION:
dd5bc0d7-ca9f-5501-aae1-549deea47b6e | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 10 - Pile Set Out and Additional Boreholes
| checkpoint | HOLD POINT
b8957a30-0e87-5458-af93-a9ecca82d62c | note | Requirements / Reference - B59 Cl 3.7 B59 Cl 4.1 B59 Cl 3.6
a5bc187b-f4b6-5db4-b15c-e54288386201 | note | Acceptance Criteria - Set out locations for piles as per the Drawings with adequate recovery pegs and survey markers so that the drilling and/or piling rig can be set up accurately at the specified location and aligned correctly for each pile.
c9696a7f-38c3-5d86-81f0-500979dd8d51 | note | HOLD POINT: Commencement of excavation of pile hole
60d8cd9a-6d91-54c9-9573-0dd428d27045 | note | Provide the following documents to the Principal:
9c27b58f-baed-5e0c-8bea-7ba6e225d4d4 | note | (a) Certification that pile hole set out (refer Cl 3.6), and additional boreholes (refer Cl 3.7) where required, have been completed
29b906db-28ef-5df0-9aba-eb9f13ecf72d | note | (c) If not previously submitted, details of the following: (i) Extent of sacrificial casing for each pile hole. (ii) Method of placing concrete in the pile hole including size and number of any proposed tremie pipes (refer to Cl 6.5)
6930103d-e3f3-542d-9112-484e6c63b797 | note | Frequency - Prior to excavation of any pile holes
d40127de-0679-5cfb-891c-68ff42776260 | note | Comments / Attachments / Records - HOLD POINT; Pile set out report; Extent of Temporary Casing; Concrete placing statement
877dec9e-4a7e-5c2b-b137-724c550d2d4f | textbox | HOLD POINT NUMBER:
a078e19d-d3c3-5f85-8779-b033c4542402 | textbox | DATE SUBMITTED:
cf9d83ca-0dbd-522e-915b-a9ec1986c58d | textbox | Work Start Date:
9fc21d72-aa1b-5c1c-8324-cf7c4864d43c | textbox | SUBMITTED BY:
a837804a-7ef4-58e4-a317-e45b6c13aade | textbox | SPECIFICATION AND CLAUSE:
faa53a47-7f23-50ec-82e3-dcd500064978 | textbox | HOLD POINT DESCRIPTION:
12ed858b-3fdc-56d2-8279-1822d0386ff4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - Pile Hole Excavation
| checkpoint | HOLD POINT
097c56ec-90be-5174-8f54-8b8d8d329434 | note | Requirements / Reference - B59 Cl 4.2 B59 Cl 4.3.1 B59 Cl 4.4 B59 Cl 4.5 B59 Cl 4.6 B59 Cl 7
f41c29e4-17de-5938-9d01-80da8576a705 | note | Acceptance Criteria - If a temporary casing is used, drive or sink the temporary casing through any inferior materials, without damaging it, to seal its toe in the founding layer. Ensure that the casing toe is fully embedded in founding layers on a slope or in ground that is comprised of variable materials.
d2942f61-9c0d-5ed4-9fff-c78f55197fc6 | note | Excavate into the founding material to obtain a rock socket of the specified depth in rock, of the class of rock or founding material specified in the Drawings. Record and measure the operating parameters of the drilling rig when excavating the first pile hole, and excavate subsequent pile holes with the same parameters and work methods
888a9e0f-c006-5087-bda2-f5ed90f47645 | note | Where excavation of the pile hole to a level lower than that shown in the Drawings is recommended by the Geotechnical Engineer, the Principal will either accept the level reached or direct that excavation be continued to a lower level
7531cc5c-91c4-5122-84e1-490a785c46e4 | note | clean the pile hole prior to completion of excavation
40eb6c0c-0e69-59e8-a0a4-d294d66f841f | note | To verify conformity with Clause 4.5.2, provide equipment to allow the Principal to indirectly examine the pile hole from top to bottom, including the socket base and side.
20b192c3-fbe6-569e-86fc-d2e466ab4ef0 | note | Tolerances on pile installation must conform to Section 7 of AS 2159, except that the inclination tolerance for vertical piles must not exceed 1%. Demonstrate to the Principal that the inclination tolerances have been achieved.
39846461-0178-5b67-a8e8-e2c9df20d481 | note | HOLD POINT: Acceptance of pile hole
f9819dca-e2c9-581c-a24e-03e807936ef4 | note | Notification, including associated report(s) by your Geotechnical Engineer, that the pile hole excavation is complete, and documentation verifying that the plan position, size and alignment of the casing, and the pile hole, will result in a pile that conforms to the specified tolerances and other requirements of the Drawings and this Specification
c1d9b61d-82ee-508f-a27a-88bbdaae0b9e | note | Following acceptance of the pile hole, keep the side and base in a clean and stable condition until such time as the concrete is placed
e36a8499-38dd-56f4-b90d-3c51ffb497a0 | note | Frequency - Prior to placing the cage
69e928ad-96a2-527e-9310-43ca8eaaa614 | note | Comments / Attachments / Records - Methodology; Joint Inspection after completion of Pile drilling; HOLD POINT; Geotech Piling Report; Drilling Records
c5bbcf66-da4e-5904-b69c-282198b41f27 | textbox | HOLD POINT NUMBER:
74a9b87c-25ba-514c-8a49-5eefae888622 | textbox | DATE SUBMITTED:
7b48ec54-9e36-54cd-836b-0cfc7bb1c2c1 | textbox | Work Start Date:
4ee9af1d-40ec-5410-b0ed-c9f614c793f6 | textbox | SUBMITTED BY:
4d9362af-c021-5f78-9f84-63b893467e06 | textbox | SPECIFICATION AND CLAUSE:
dbb71e33-6363-5739-9025-917a01b69091 | textbox | HOLD POINT DESCRIPTION:
c8d133b7-f4b1-59c2-8953-9420244a7230 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 12 - Inspection of Reinforcement Cage
| checkpoint | WITNESS POINT
464a1535-9423-53e1-b9a4-31d570ff073c | note | Requirements / Reference - B59 Cl 5.1
8b2f620d-113b-579f-b990-bff96cb50ad7 | note | Acceptance Criteria - Clean the pile hole and reinforcement cage of all loose and adhering material before and after the reinforcement cage is placed
29a216c5-c60c-5030-84e9-0b2ee9454e09 | note | Place the reinforcement for the piles as per B80 and B59 Specifications. Ensure the reinforcement cage is centralised and that minimum concrete cover is not less than the specified value
b4702f71-901a-52cf-94c1-6188af0a67ae | note | WITNESS POINT: Inspection of reinforcement cage prior to placing into pile hole
3f00fc36-14b7-5d33-96e1-2673e8bf2f56 | note | Notify the Principal at least 2 hours prior to proposed time of placement of the reinforcement cage into pile hole.
bc72e9e1-7514-59f9-bc80-66d427a674f5 | note | Frequency - Prior to pouring concrete
cd47e10f-d9cd-55d9-b05c-6dc707c79270 | note | Comments / Attachments / Records - WITNESS POINT; Pile Cage inspection prior to installation
d433cae0-2b4e-51c5-9b19-948fd6061609 | textbox | WITNESS POINT NUMBER:
1a3540fc-19f4-5702-bd95-9feaa2eaef9f | textbox | DATE SUBMITTED:
17bf4602-0fe4-59ef-92ad-d280c6f44e89 | textbox | Work Start Date:
8d65e3d0-82f6-55b8-8da0-e308eab12e45 | textbox | SUBMITTED BY:
3a42f8f8-a104-5eba-a657-ba022986641c | textbox | SPECIFICATION AND CLAUSE:
8552f658-4829-5c21-95a9-8ebed5b8c5ad | textbox | WITNESS POINT DESCRIPTION:
fe80be01-262a-51bb-993d-7fc7dd017ea2 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 13 - Cleaning of Pile Hole and Reinf. Cage
| checkpoint | HOLD POINT
729b23d5-767f-55f1-b488-437e1e0d7f5c | note | Requirements / Reference - B59 Cl 5.2 B59 Cl 6.1
4acde0d4-0169-510e-9d41-c3738aab58b5 | note | Acceptance Criteria - Place the steel reinforcement and concrete as soon as practicable following final socket cleaning, and within 24 hours of the excavation of the pile hole. Where this is delayed, do not place the steel reinforcement if further cleaning of the pile hole or rock socket is required
99d5a527-d00f-5fdf-85d1-dd9ac380be2d | note | HOLD POINT: Placing steel reinforcement cage in the pile hole
49444cc0-a63b-56ca-bf3f-f3fd0d8f6bcc | note | Submit to the Principal Certification that the pile hole is clean, and that all loose and adhering materials have been cleaned from the reinforcement cage
e996c555-baa4-5910-b852-cb71d1958165 | note | At the time of concreting, the pile hole side and base must be clean and conform to the parameters specified on the Drawings.
519895b8-60e2-5ba9-aea4-2ee447f20d79 | note | Frequency - Prior to pouring concrete
d84c4b1f-8ae1-541e-bd4c-e06430751394 | note | Comments / Attachments / Records - HOLD POINT; Pre Pour Checklist
dd67613d-62f8-51d5-93e6-aca9ab0988c9 | textbox | HOLD POINT NUMBER:
e7346297-56f1-5490-9831-f6da73655fbf | textbox | DATE SUBMITTED:
7c786b2e-42ad-5a71-b9d0-a9d94b237146 | textbox | Work Start Date:
04c50595-cec4-5f4f-8837-387f4c21fdf6 | textbox | SUBMITTED BY:
99f3e9fc-6f87-5d92-aad7-5d49365dbeeb | textbox | SPECIFICATION AND CLAUSE:
769dcf7d-c472-50d4-8c00-2de5980b7be9 | textbox | HOLD POINT DESCRIPTION:
4a720771-96e3-51ff-a9c4-ec5885de951a | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 15 - Test Member
| checkpoint | WITNESS POINT
e7a511c6-49b4-544c-9cd8-6ce8f3d47461 | note | Requirements / Reference - B80 Cl 5.3 B59 Cl 6.2
4a1d90b4-64c2-51e1-b51d-6d74f5494f14 | note | Acceptance Criteria - Produce test members if directed by the Principal, to demonstrate the suitability of the concrete mix for the Works, and the suitability of the work methods.
7872aadd-24b0-5398-adaf-6f94a3991f33 | note | Where test members are required, design and construct them in accordance with AS 3610.1 for test panels. The method of construction must effectively simulate the formwork, reinforcement layout and concreting operations to be applied in the works themselves
725206f8-0083-5856-ae8d-04ed003e10d8 | note | If the test member does not meet the design requirements, discuss further actions with the Client prior to making any changes to the work methods, or casting any additional test members
eadfaf7b-b016-58ac-b841-689b6eaa5505 | note | WITNESS POINT: Placement of concrete for the test member (if required)
c4a127e5-7d81-557b-b79e-194a06b5f200 | note | Provide at least two working days’ notice, in writing, of the proposed placement of concrete for the test member. Thereafter, give the Principal the opportunity to inspect the constructed test member
1d26f992-559f-5a11-b8b3-43a8ec37b01d | note | Frequency - Prior to pouring subsequent piles
b369d194-ecaf-5d32-8152-2103cf2bccbd | note | Comments / Attachments / Records - WITNESS POINT; Proposed Time and location to inspect test member (Prior/Post)
aece936c-1c5a-591f-8f40-ed4f81c52ffb | textbox | WITNESS POINT NUMBER:
d59f89e1-4fb4-5491-99a1-fab7992325ab | textbox | DATE SUBMITTED:
d0da1282-8313-54b1-8d38-d1dcde703a2b | textbox | Work Start Date:
bc1fdc5b-f470-554e-87b2-895c9861d581 | textbox | SUBMITTED BY:
23af3ec4-3e4d-5efc-a662-db22975f9bcd | textbox | SPECIFICATION AND CLAUSE:
116502ab-bee7-562a-a7b1-bbb2485d2759 | textbox | WITNESS POINT DESCRIPTION:
2845d782-a382-59b5-ae73-44a995e66591 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 16 - Pouring of Concrete
| checkpoint | VERIFICATION
636bdaa9-af4e-55e1-ae1c-ba901930230a | note | Requirements / Reference - B59 Cl 6.3 B59 Cl 6.4 B59 Cl 6.5 B59 Cl 6.6 B59 Cl 6.7
89d58385-a8fc-5ac0-97d0-4200005f0de7 | note | Acceptance Criteria - The pile hole may only be dewatered where practical and subject to the Principal’s approval
d3c5d674-6ad5-5b9c-be28-b591b43a6661 | note | Provide a continuous supply of concrete, such that each pile hole is concrete in one uninterrupted operation. All concrete placed must have the nominated workability of the approved concrete mix, at the time of placement in the pile hole
069df959-95f4-5f50-a9f5-a07edb1909d3 | note | Unless specified otherwise, place the concrete as per TfNSW Specification B80
d6727b09-c3cd-5396-86f7-3870cfef858f | note | In the event of nonconforming B80 concrete, pursue the avenues provided in the B80 ITP
d704df8f-1e0e-5081-8596-02efa7d548c3 | note | Use a tremie pipe and hopper to place the concrete. The tremie pipe must be rigid and watertight throughout. Tape a steel plate to the bottom end of the tremie pipe or similar, prior to placing concrete, and select a suitable tremie size and concrete pump (if needed)
f0814004-d4e1-5a7f-af77-f23b23dc68d5 | note | Place the concrete in a continuous process from the base to above the top of the pile, in a manner and consistency such that pockets of air, water or ground materials are not entrapped in the concrete, and the concrete cover completely consists of sound concrete
07157f25-d0a0-5856-b44b-5fc1a3d29893 | note | During concreting, maintain a record of the depth of the tremie pipe outlet against the level of the concrete in the pile hole, and the corresponding volume of concrete placed.
4b041d1d-fa7b-5d86-9a69-842b6cae113f | note | During concreting, lift the tremie pipe progressively as the concrete level rises, but at all times keeping the bottom end of the tremie pipe a minimum of 2 m below the top surface of the concrete until sound concrete appears at a minimum of 400 mm above the pile cut-off level, to avoid defective concrete at or below cut-off level.
511ea9b0-e50d-5020-9e17-6d9720c9eb91 | note | Retain other relevant records, such as concrete pour dockets and records
4014e0df-ae45-5da2-ad5b-977a716432c0 | note | Frequency - During the pours
803f9150-6ab3-59f7-b730-a5fd71d232aa | note | Comments / Attachments / Records - Concrete pour dockets and records; Concrete test results
| section | 18 - Cut Off and Clean Up
| checkpoint | VERIFICATION
86791cc6-8d68-5dca-9b15-0f81db66bf19 | note | Requirements / Reference - B59 Cl 6.10
42ef4041-ded4-5d38-9fb2-252ba583e8a1 | note | Acceptance Criteria - Carefully remove any concrete and/or casing above the cut-off level without damaging the permanent work, no earlier than 24 hours after completion of placement of concrete
6da29e3a-65d0-5ec5-b0bc-b46d963ef1ce | note | The top of the pile must be undamaged, sound, free of any laitance and loose material, and have a surface roughness profile not less than 3mm. Where the concrete below cut-off level is cracked or defective, cut away and repair the pile in consultation with the Principal
35e1ce7f-ab05-5685-966a-35eebb645c33 | note | Keep the reinforcement protruding from the top of the pile clean and protected from damage
41598535-f999-5a4e-bb52-60b06647f745 | note | Frequency - Following completion of pouring
d265e1eb-36a0-551b-a933-4348da8e93c8 | note | Comments / Attachments / Records - As builts
| section | 19 - Installation Tolerances
| checkpoint | VERIFICATION
488e2a77-6fe5-54a8-b9cb-a2e67bc4e54b | note | Requirements / Reference - B59 Cl 7
ae7f22a2-8f15-57a1-b0f9-523abe8e4a03 | note | Acceptance Criteria - Tolerances on pile installation must conform to Section 7 of AS 2159, with the exception that the inclination tolerance for vertical piles must not exceed 1%.
2db0d61e-0db0-5df9-ae37-98dcac6e193d | note | Demonstrate to the Principal that the inclination tolerances have been achieved
1a4aec3e-6ffc-5739-8a6d-e503398bab12 | note | Frequency - Upon completion of works
42985770-7977-5d6a-b12f-40a76cbb14de | note | Comments / Attachments / Records - Survey reports or Drilling Records
| section | 20 - Identified Records - Cores
| checkpoint | VERIFICATION
57409e7a-16f7-5ea7-abb6-eb66116988b0 | note | Requirements / Reference - B59 3.7
4ff5115f-44a2-5255-a7a7-7ccdce4a8f62 | note | Acceptance Criteria - Cores and your Geotechnical Engineer’s interpretive findings
| section | 21 - Identified Records – Piling Records
| checkpoint | VERIFICATION
1e6aff3f-6626-51b2-b36e-76a15f708d66 | note | Requirements / Reference - B59 4.5.3
79d32a22-af5d-54fc-b328-3ed3df51014f | note | Acceptance Criteria - Piling records, signed by Piling Supervisor, verifying conformity of the pile hole upon completion of its excavation
| section | 22 - Identified Records – Pile Hole Examination
| checkpoint | VERIFICATION
22cd8831-a62f-5bf5-8bc5-131810815f83 | note | Requirements / Reference - B59 4.6
62e6dbd2-4714-5ba6-8e6f-666c803b43b2 | note | Acceptance Criteria - Results of pile hole examination
| section | 23 - Identified Records – Pour Details
| checkpoint | VERIFICATION
d8361f8b-00ee-5c47-9e63-ccc8dd002e1c | note | Requirements / Reference - B59 6.7
42a1f63b-b33e-5d6e-809b-507da0f9d416 | note | Acceptance Criteria - Records of tremie outlet depth, concrete level in the pile hole and volume of concrete placed during concreting
| section | 24 - Identified Records – Pile Integrity Testing
| checkpoint | VERIFICATION
a147dfa8-3883-5b15-9d5f-be595f97a44d | note | Requirements / Reference - B59 8.1, 8.2
72f1f0df-4dec-56cd-88bd-2defcc2f60ae | note | Acceptance Criteria - Pile integrity testing results
| section | 25 - Identified Records – Pile Load Testing
| checkpoint | VERIFICATION
4389b4ea-fbc8-5dba-901e-2b248504763e | note | Requirements / Reference - B59 8.3, 8.4
5db09d55-637f-5ce2-826d-601134d5ae0d | note | Acceptance Criteria - Pile load testing results
| section | 26 - Identified Records – Nominated Mixes
| checkpoint | VERIFICATION
5f9933fb-ae32-5899-bc14-d6b7d0a13e74 | note | Requirements / Reference - B80 3.9
30658818-8782-53a8-9ecb-6babc041c0ee | note | Acceptance Criteria - Submission of nominated mixes
| section | 27 - Identified Records – Variation from Mixes
| checkpoint | VERIFICATION
e9331092-a632-57b9-b200-ad79e5015841 | note | Requirements / Reference - B80 3.9.4
84fe8a9c-86cb-57cd-9116-74742ba4f207 | note | Acceptance Criteria - Variations from nominated mixes
| section | 28 - Identified Records – CoC (Formwork + Reinforcement)
| checkpoint | VERIFICATION
b4e2c1f5-95e1-5718-8e8a-fb984ef4e1da | note | Requirements / Reference - B80 7.5.1
92432df4-6b41-52cd-a49e-b1a20da76b73 | note | Acceptance Criteria - Certificate of Conformity in respect of formwork, reinforcement, embedments and other relevant details or precast concrete members cast at off site locations
| section | 29 - Identified Records – CoC (Curing Compound)
| checkpoint | VERIFICATION
6b0e98cf-a8b3-5598-a2e9-27d912151ac2 | note | Requirements / Reference - B80 8.2.3
d97d3de4-dd1d-5135-a074-8f2f81dc246f | note | Acceptance Criteria - Certificate of Conformity of curing compound
| section | Lot Verification
| checkpoint | Lot Verification complete
a3b4a46c-f8cd-5ab9-a6d1-4ff5dd4cc442 | textbox | Lot Verified By:
ebab0b3c-181d-50bb-8a02-9b1d0297a851 | textbox | Lot Closed Date:
6ec9cd5a-39e3-5f5e-ba02-53bd153f45d5 | button | Submitted to Client | Yes, No, N/A
438ed311-f8a8-5e0c-b055-ed045a95d5b0 | button | Reviewed by Client | Yes, No, N/A
dd3263fe-d9bf-5de3-b3ab-90b0b849ebe3 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 13 - B201 Steelwork for Bridges Rev 0 |  | ITC 13 - B201 Steelwork for Bridges Rev 0 | c468bc5e-d1aa-447c-bde0-c13f81016300
| section | Lot Information
| checkpoint | Lot Information complete
94d60385-5006-5a1d-8e74-779d79b7ffb2 | textbox | Lot Opened On
938821c6-8af1-5ea6-8d58-56cd744fdcd1 | textbox | Date of Works
a89ade90-2efb-5bfc-80be-c9c1ca6e7626 | textbox | Lot Type
72b5f639-9420-5b29-a765-21ec1c697215 | textbox | Start Chainage
434c0f7e-dba9-5f14-b37e-cec8bdc814ea | textbox | End Chainage
b32283a2-43a9-51af-ba3f-89ccc55cf033 | textbox | Offset
f9f1cdd4-ddee-5a24-ad9f-fb4afc279be4 | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
ba0c43ad-e601-55fd-9e18-fdb69bd56b21 | note | Requirements / Reference - Project Safety Plan
c41aff62-e227-5b79-8287-79433e281eab | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
daeebcfb-d22f-500f-998a-81ad2459d0cc | note | Required Safe Work Method Statements completed and signed
2525adff-23d8-5ddd-865b-9aa7624067cd | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
272fca30-8f7c-5998-b89d-78c4e63b48dd | note | Requirements / Reference - Project Environment Plan G36 CL 3.1 G38, G40
6cbf5800-4b0c-557d-9369-9f0026fa0712 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
0c6a0722-7159-5065-b161-2c9586e339a8 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Product Conformity Assessment
| checkpoint | HOLD POINT
47869d4b-8fbc-528b-ae7e-970fd6cc9a81 | note | Requirements / Reference - B201 Cl 5.2
407b3da3-4982-56f6-9b89-aa1f8938b9df | note | Acceptance Criteria - All steel must be produced by steel manufacturers certified by a product conformity assessment scheme acceptable to the Principal, such as ATIC Scheme 10. Third-party conformity assessment bodies must be accredited to AS/NZS ISO/IEC 17065 either by JAS-ANZ, or by the IAF
68943630-1b37-5836-9d67-8b74a2819448 | note | Any alternative product conformity assessment scheme to ATIC Scheme 10 must be submitted for review and accepted by the Principal prior to commencement of procurement of the steel
fd1fc638-fef5-5235-a52c-a3866e874c57 | note | HOLD POINT: Steel procurement
bc7e82ff-ffa7-562f-aae8-bd863067ce11 | note | Provide valid certification of the steel manufacturer for the production of steel conforming to the applicable standard issues by either a JAS-ANZ or IAF accredited body, submitted no later than 10 working days before the steel is ordered
feb56450-e1f5-5f72-90f9-26d51b87f707 | textbox | HOLD POINT NUMBER:
88cdd654-121b-5054-99d8-58f534ce9ed1 | textbox | DATE SUBMITTED:
5bab4d74-dd08-58c6-828a-07372b607236 | textbox | Work Start Date:
36d5da2c-084c-58a0-8a98-2d61384d1cd6 | textbox | SUBMITTED BY:
8bf7d220-8c09-5b48-b59a-9e7706c96374 | textbox | SPECIFICATION AND CLAUSE:
b07e9570-532c-5547-9f24-ddb8aac903d0 | textbox | HOLD POINT DESCRIPTION:
e7b317b7-8d0d-51a3-baca-f35eb36af3c8 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 4 - Structural Steels
| checkpoint | WITNESS POINT
d91be803-2514-57d2-9962-eadb05d01035 | note | Requirements / Reference - B201 Cl 5.3
5fb9627a-d6a0-5e4b-92e3-cbd180076ae8 | note | Acceptance Criteria - Prior to steel fabrication and when specified in Annexure B201/A6, carry out testing in conformity to the applicable product standard on at least two samples
21e8cecc-c68a-567d-8f92-2aaba3208365 | note | Thickness tolerances and surface condition to conform to AS/NZS 5131. Any additional repair to surface condition imperfections will be deemed to be nonconforming
d384b548-88c8-5611-9d4c-1448dc76b088 | note | Any cutting or shaping of steel plates and sections after the steel has left the mill are regarded as fabrication work and must be done in conformity to this Specification
67b952af-f09c-56c4-aa4c-09b908dd968a | note | In addition to the requirements of AS/NZS 5131, carry out ultrasonic examination of structural steel in the vicinity of critical welded details and at other locations shown on the Design Drawings. The method of test to be used upon the parent metal must conform to AS 2207 and AS/NZS 1554.1
f3418d44-527e-515c-8030-079f993db442 | note | Do not use any steel which is bent, damaged or excessively rusted in the Works. Steelwork will be deemed to be nonconforming where def22222NZS 3679.1 or AS/NZS 3679.2, as applicable, and where permitted by the Principal
6c17607a-127c-5267-adcf-2bf31a00949b | note | WITNESS POINT: Steel verification testing
c55e0784-8747-57b7-9f30-27a34391bc60 | note | Provide at least 5 working days’ notice to the Principal of the commencement of steel verification testing
7288ad11-0c12-5dd5-8c37-fee27d500833 | textbox | WITNESS POINT NUMBER:
0e31ac65-e131-54b5-940c-4c9c7692543c | textbox | DATE SUBMITTED:
72bce8b5-dc5c-5f75-94e8-c0e5755b03ed | textbox | Work Start Date:
59c798f9-b156-5e75-831b-20306b8a5c9e | textbox | SUBMITTED BY:
c90f7613-5596-5d4f-b126-2e3333fcb42b | textbox | SPECIFICATION AND CLAUSE:
109ab2c9-e004-5558-a988-bfb2db778449 | textbox | WITNESS POINT DESCRIPTION:
bfe282b4-aeda-53e3-8052-b18aa36b27dd | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 5 - Shop Drawings
| checkpoint | HOLD POINT
17943376-a8be-5e83-bc14-1f452ac6271f | note | Requirements / Reference - B201 Cl 6.1
523aa8cc-fd99-5fab-b3c5-e33f0178f438 | note | Acceptance Criteria - HOLD POINT: Fabrication work
9dd86219-78f1-5fbf-9b5b-233c89e0e7db | note | Submit shop drawings conforming to the Design Drawings for approval and certification by the Designer in accordance with Clause 4.6.2, and procedures as detailed in Clause D1 of Annexure B201/D, items (b) to (v), at least 20 working days prior to commencement of fabrication work
c3d14801-3029-51be-a798-a374fcb2dd91 | textbox | HOLD POINT NUMBER:
753a1b0d-63c7-5db5-8b04-a39b1a398f79 | textbox | DATE SUBMITTED:
5e533467-500e-5a0c-9c8a-bbf3df2e1155 | textbox | Work Start Date:
bf53002c-4ece-5d1f-a5bc-97de6ec128f1 | textbox | SUBMITTED BY:
c725baed-5f12-54d2-b665-bd06fd432638 | textbox | SPECIFICATION AND CLAUSE:
c5f4e0ac-b6b3-5f21-aee3-a8be90c0050d | textbox | HOLD POINT DESCRIPTION:
519b9f7e-98e6-5170-ad46-3f27111a8c85 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 6 - Fabrication Work
| checkpoint | WITNESS POINT
8ac9eeaa-697e-51fd-80ef-1da8658234e3 | note | Requirements / Reference - B201 Cl 6.1
cf59f44b-5a0f-5f3b-971a-f99aa3ebfd5c | note | Acceptance Criteria - WITNESS POINT: Commencement of fabrication work
f0509ff3-5595-59b3-9541-99f418a8e14f | note | Notify the Principal at least 10 working days ahead of when fabrication work will commence
ad8c901e-65fe-593c-91bc-223c62759180 | textbox | WITNESS POINT NUMBER:
eaf3f442-c1c8-57eb-ba8f-625d7525345f | textbox | DATE SUBMITTED:
4139296c-09de-551d-a01b-752a8c2db0c1 | textbox | Work Start Date:
afa043a5-26d8-5766-8335-ac22ef9497df | textbox | SUBMITTED BY:
1d555571-f846-5978-84e1-f0dc966b91a1 | textbox | SPECIFICATION AND CLAUSE:
c0788eb9-5805-5ca9-9431-fa144f090448 | textbox | WITNESS POINT DESCRIPTION:
1f16dd6f-190b-5719-bbae-bd07b73f3d0c | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 7 - Cutting
| checkpoint | HOLD POINT
26309965-e547-535f-a7fe-35d0391d329a | note | Requirements / Reference - B201 Cl 6.5
f3ce7b95-a66e-5991-82d5-7327e0b321e3 | note | Acceptance Criteria - Where possible, carry out all cutting using machines that are mechanically guided and moved at uniform speeds. Use hand cutting only for secondary cuts, repairs and other work where machine cutting is no possible (as approved by the Principal)
53078f5a-cdd3-5856-8dcb-24b0fcfa58d0 | note | Remove rough edges after cutting and dress off uneven outer edges to a true line. Unless shown otherwise on the Drawings, round all corners on exposed edges to a radius of approx. 2mm by hand or power tools, except where these edges will later be welded
376db881-9db3-5ec5-8bca-8d020972f74a | note | Where flame cutting is necessary, use machines that are mechanically guided and moved at uniform speeds. Carry out flame cutting of plates, sections and other components with surfaces which will be used in the ”as-cut” condition using procedures that minimse the reduction in properties at the cut surface
598322be-e14c-5286-96a6-2909c4beef0a | note | Do not cut steel under stress or loading
8473c721-f9e3-5884-ad0b-f44891b872ae | note | HOLD POINT: Further work on the steel item following flame cutting
98c60645-d129-5ba2-8d21-0d35f191512b | note | Provide test reports verifying that the specified Vickers hardness number has not been exceeded on flame cut surfaces prior to further work on that steel item
e6c55510-fd4f-5ea8-b31d-c76e3bb8fe7b | textbox | HOLD POINT NUMBER:
b9010734-1be9-5371-8ff6-cf73fe5ead95 | textbox | DATE SUBMITTED:
07b651c0-c0ee-5d28-b8aa-1cd123f78ca4 | textbox | Work Start Date:
83185849-6d1a-58b0-ab8e-e5ef31930850 | textbox | SUBMITTED BY:
b5310eb4-4f80-5aff-93a0-3b5200bba20b | textbox | SPECIFICATION AND CLAUSE:
b4ccc95e-546f-5909-89e5-b21fadcc10e4 | textbox | HOLD POINT DESCRIPTION:
a8285ab2-3871-5779-8cad-59091ff10cc4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Shop Assembly
| checkpoint | VERIFICATION
95de2f24-1d22-508c-a316-084ad145b36f | note | Requirements / Reference - B201 Cl 6.9, B201 Cl 6.10
1d580d1e-4d84-50a9-85d1-a0b35672ad4c | note | Acceptance Criteria - Carry out shop assembly of structural steelwork to confirm the alignment, level and fit of the components and to verify the suitability of the templates, if any, used during fabrication to prove or obtain conformity to the Design Drawings, as follows:
1105ce97-c99d-5ffb-992e-2dd9c08205dd | note | (a) for all splices in main girders; or
5a7134da-bbfd-5463-8a6a-88a08e8d43e0 | note | (b) when required by the design
676263dd-2a0e-5421-8778-474d1a82c1c2 | note | Shop assembly will not be required for girders for simply supported spans less than 25m in length unless specified otherwise
7c4181f1-5e9b-5654-b753-128944fcb1fd | note | For spans 25m or greater with steel cross girders or cross frames, the first two lines of girders (ie Abutment A to Abutment B) fabricated must be shop assembled to check the fabrication, the fit and the suitability of the templates used
294028e5-cbf6-507a-af8c-cfdfa8cceffb | note | Submit certification of satisfactory shop assembly to the Principal, and match mark all shop assembled joints before dismantling
611a89ef-b196-5a0d-82aa-95099938ac1e | note | Assembly check must conform to AS/NZS 5131
e60a2fac-2648-508f-bfb7-09474d1d828a | note | Comments / Attachments / Records - Certification of satisfactory shop assembly
| section | 9 - Transport to Site
| checkpoint | HOLD POINT
bd0feb93-6d80-5258-b9e1-6e440f797b6d | note | Requirements / Reference - B201 Cl 6.11
f6014528-3548-530c-95e8-1823ff1e1ca9 | note | Acceptance Criteria - The Fabricator must complete inspection of the steelwork not less than three working days prior to any products being dispatched for protective coating or delivery to site. They must provide the Principal at least 2 days’ notice prior to transport that the steelwork is available for inspection
71961529-53d6-52d7-8e19-d434eff72646 | note | HOLD POINT: Transport of fabricated steelwork to other workshops or to site
828f48d1-d439-592b-917b-8122e6b344f1 | note | Submit the relevant documents from the Fabricator's Data Report (refer Clause 15) for the fabricated steelwork and procedures required for its transport as specified in the PROJECT QUALITY PLAN, at least 10 working days prior to transport
bdc6385f-f553-5a44-a51e-6a4da493df4b | textbox | HOLD POINT NUMBER:
5042a6c1-625f-58b4-8cd9-daef6710cbbd | textbox | DATE SUBMITTED:
b046f9cf-b341-5f38-96da-5968450015be | textbox | Work Start Date:
1ed210b1-1b72-57bf-b962-8fea66e29284 | textbox | SUBMITTED BY:
4b35944f-c76e-556d-b475-0ac73a4669d3 | textbox | SPECIFICATION AND CLAUSE:
fa6b3d42-ffe9-5352-9b07-c735193bf4b9 | textbox | HOLD POINT DESCRIPTION:
d8e96382-85c2-5491-8ef8-ad09756cbec4 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 10 - Splices
| checkpoint | HOLD POINT
2978f732-cfd8-540c-86cc-590842a75007 | note | Requirements / Reference - B201 Cl 6.19
d5c5e293-5468-513c-a7e8-b2e26c76aa46 | note | Acceptance Criteria - All splice welds must be full strength butt welds
04f0a730-4707-5934-8d67-ac64ed89fe04 | note | All splices in main girders must be shop assembled to check the alignment, level and fit of the components and to verify the suitability of the templates (if any) and must be match marked before being dismantled
7e6576f6-37a8-5c66-a2c9-0f89b1b20107 | note | Where field splices are required, finish the ends of all girder segments true, as shown on the Design Drawings, to a tolerance of ± 1mm over the depth and width of the girder
d32461dd-dd1e-57a0-b320-cb5ed2453c00 | note | Butt welded or fillet welded web-to-flange splices must be non-destructively examined using ultrasonics when the following apply:
eeecbe85-bbce-5884-915d-c56a7b16020e | note | flange plates are Grade 350 or higher;
672366b8-8926-5070-b62c-34b543024886 | note | flange plates are 25mm thick or greater
bce4c41d-4fe1-5bb8-8a9c-c31f5be24f66 | note | but the above does not apply to welded beams conforming to AS/NZS 3679.2
2699416e-3e81-5902-9244-d3428a36e4c1 | note | HOLD POINT: Commencement of fabrication of members with splice locations nominated by the Contractor
c49b26fc-c7c3-58e6-8fc3-a64fc9823b2a | note | Submit details of design and locations of proposed splices to be used in the steelwork, at least 10 working days prior to the proposed commencement of fabrication
696c9b78-eef5-583a-b0b9-2a59f2bb63ae | textbox | HOLD POINT NUMBER:
6fa4ece3-5019-5119-9e8b-4f848d501638 | textbox | DATE SUBMITTED:
1921d7a8-d035-5321-a842-98997940a228 | textbox | Work Start Date:
7e344bbc-34dc-5e70-9abb-1074bf198952 | textbox | SUBMITTED BY:
718b36a4-623a-5f2a-8337-54ccbe975cd7 | textbox | SPECIFICATION AND CLAUSE:
c9599938-e2e7-513a-a3dd-9be8e9f56f18 | textbox | HOLD POINT DESCRIPTION:
0dc66fe4-a60b-57a3-b1d0-e9e76ff329e7 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - Ancillary Steel Items (Railings)
| checkpoint | WITNESS POINT
0f35398f-a140-5e88-8002-4461d17bc98c | note | Requirements / Reference - B201 Cl 6.22
5e4d279d-7893-59d2-8a05-7d922e446aa5 | note | Acceptance Criteria - Fabricators of ancillary steel items specified in this Clause must have a quality management system in place, certified by the WTIA as conforming to at least AS/NZS 3834.3.
8b384f91-fb49-5c40-93d2-663f5fbb6798 | note | Except where shown on Design Drawings, splices are not permitted for ancillary steel items
ffc83c23-b292-5c34-91b5-aec591fce31b | note | Where items are to be hot-dip galvanised, take adequate measures during fabrication to ensure items are not distorted or otherwise damaged during the galvanizing process
8ea576c3-4089-5f67-a6ac-07dae0476213 | note | Straight barrier railings, prepare suitable templates to check the grade of completed panels
9ae41397-b428-5679-a347-78130b792405 | note | Curved barrier railings, include full details of the proposed procedure for carving, including measures to ensure uniformity of curvature and minimum distortion of the cross-section, when submitting the fabrication procedures
dc4e19a6-2d0b-5515-ab63-9f929cad4cc0 | note | Curved pedestrian railings, carry out a trial erection before applying the protective treatment
c5eb81a7-c3cf-5ac5-9927-9c0617a49682 | note | WITNESS POINT: Trial erection of curved railings for pedestrian bridges
aa9cb92f-480a-5748-a1c0-a14b75e75981 | note | Provide at least 3 working days notice of the trial erection together with evidence that the alignment and location of the railings will conform to the Design Drawings and the Specification
9451189b-ee85-5892-8fb1-db661cef17ce | textbox | WITNESS POINT NUMBER:
16982966-4d08-5668-9072-c305a5a676c6 | textbox | DATE SUBMITTED:
8366d07f-6422-5ac8-960f-101bb62acd26 | textbox | Work Start Date:
dd77cfa7-71db-5d7a-bf54-0aab74ff724d | textbox | SUBMITTED BY:
cc8f392d-7fe1-54ff-8e07-29f61d65e1ca | textbox | SPECIFICATION AND CLAUSE:
3fbb7464-da5e-5e66-9d75-b657a2cfa7b3 | textbox | WITNESS POINT DESCRIPTION:
97b9530e-2258-5ad0-9f3c-c5ffc0e54de6 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 12 - Weld Procedure Qualification Test Piece
| checkpoint | WITNESS POINT
3b3c0a1d-1714-53c5-8e09-57c720973fe5 | note | Requirements / Reference - B201 Cl 7.4.1.1
67b06d68-0c71-5e06-881b-a3b8c0d3e2bd | note | Acceptance Criteria - The Welding Procedure Specification for each welded joint must be qualified and approved by the Responsible Welding Coordinator.
f2c4aa36-dd75-5a9b-82b3-c23a6afdb1d0 | note | The welding of all test pieces must be done under the direct supervision of the Responsible Welding Coordinator
93bf19a6-30d5-5f4f-94d7-1705b1010320 | note | WITNESS POINT: Manufacture of weld procedure qualification test piece
633cbfee-f574-5ed5-8ada-6749495d2c7b | note | Provide at least 3 working days’ notice of the time and place where the welding and testing of test pieces and/or assemblies will be carrier out
ce5d55ad-c515-5d55-8870-c66b8c4f7b8c | textbox | WITNESS POINT NUMBER:
526c6fd7-82e0-52ab-93c5-0baf79a7c51b | textbox | DATE SUBMITTED:
6ed4a61d-7289-5d09-9846-92fa848b8625 | textbox | Work Start Date:
c2a78e1c-19f2-52df-b8f6-a6c90f4c9e84 | textbox | SUBMITTED BY:
c37726af-67bc-5303-8c86-2dac1f35a29d | textbox | SPECIFICATION AND CLAUSE:
b4cba725-c700-5811-97e9-1d3ce3df2f10 | textbox | WITNESS POINT DESCRIPTION:
18da9f55-3da0-59ee-bf94-62a0d0955b79 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 13 - Welding Procedure Specifications
| checkpoint | VERIFICATION
5f76d9e8-f147-51e1-87a3-5f36bc50e12a | note | Requirements / Reference - B201 Cl 7.4.1.1
9b82854f-1519-5dd6-ac9c-bee7fb942fad | note | Acceptance Criteria - Weld procedures for repair work must be qualified and approved
4a4e0958-35dd-508e-ab80-c1659a2996c3 | note | The qualification and approval of the weld procedure must be documented in a Welding Procedure Qualification Record (PQR or WPQR), including the applicable test certificates and documents listed below, and a Welding Procedure Specification (WPS) as follows:
f1719f33-0556-51dd-bd68-eb6d15019b92 | note | (a) WPS showing all welding parameters for the applicable ranges;
1bcc46f3-6151-568a-9cb9-85efb0b17320 | note | (b) PQR running sheet showing the welding parameters for each pass obtained during the welding of the test plate;
6d3defb5-de29-5fc1-8d92-a8897569f15c | note | (c) applicable material certificates;
ad7bff7d-2c36-5a53-8535-81e25e8e7d0c | note | (d) macro test report, in conformity to AS 2205.5.1, including macro photograph at x1 or greater;
36191e63-d06d-5ebc-abbf-37a13207f53d | note | (e) if applicable:
e2fc6cdf-5427-5d27-83de-6dd7a963a627 | note | (i) non-destructive test report conforming to AS 2177 and/or AS 2207;
f295000c-754c-548c-b00a-f75b50f448e0 | note | (ii) mechanical test report – transverse butt tensile test conforming to AS 2205.2.1, and transverse guided bend test conforming to AS 2205.3.1;
da7b5531-6b8d-550d-b185-453e5b932e8a | note | (iii) HAZ hardness surveys conforming to AS 2205.6.1;
f6337f27-72ac-5501-ac37-14dd8a74acb1 | note | (iv) impact tests, at appropriate test temperatures in conformity to AS 2205.7.1;
bdeb7008-518e-5165-b0a2-683f7f48db01 | note | (v) post-weld heat treatment charts and certificates conforming to Section 14 of AS 4458
6a9fec78-b3d1-5333-a93c-95d2270ab235 | note | HOLD POINT: Commencement of welding
17a7d0d3-c24d-5d86-96e4-a7f2aabb44c1 | note | Submit Welding Procedure Specification(s) at least 5 days prior to commencement of welding
| section | 14 - Welding Qualifications
| checkpoint | WITNESS POINT
292626e3-bac2-527f-b10d-035ac9074660 | note | Requirements / Reference - B201 Cl 7.4.2
a5c3df8a-50e8-53d7-9cab-3f18ffb90524 | note | Acceptance Criteria - Identification and traceability of welders and welding procedure specifications are required irrespective of the designated Construction Category
7bd407f8-1451-5b63-9156-ba57f65890f1 | note | All welders must be qualified to AS/NZS ISO 9606.1 or alternatively to AS/NZS 2980 subject to acceptance by the Principal
d125ae15-0987-56c8-87c4-4632ea48f573 | note | WITNESS POINT: Welder qualification test, including manufacture of a welder qualification test piece
ef5c2169-a22b-561b-b202-b7568a23272f | note | Provide at least 3 working days’ notice of the time and place where the welding and testing of test pieces and/or assemblies will be carried out
65255112-9fb1-59b4-8a68-7ac2e58acb95 | textbox | WITNESS POINT NUMBER:
8192505d-b249-5fca-b599-d4908d8c574f | textbox | DATE SUBMITTED:
0a3c1a5b-4e9d-5105-b71c-74cbb05ed678 | textbox | Work Start Date:
a0db3e32-c453-5dff-88dc-8d5cc093d784 | textbox | SUBMITTED BY:
5d4f7ac4-b7e8-5208-8341-85655c295639 | textbox | SPECIFICATION AND CLAUSE:
116a6856-809d-50a3-98fe-f4f5c4ca2b81 | textbox | WITNESS POINT DESCRIPTION:
a3a38a31-e294-5c03-874e-45d713b9cd2e | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 15 - Butt Welds
| checkpoint | WITNESS POINT
1c66c4f5-73ca-54fd-a794-22965c31a90d | note | Requirements / Reference - B201 Cl 7.5.9
886b6ad1-5b01-5f38-9a2d-02df9752f5e6 | note | Acceptance Criteria - Hydrogen controlled welding processes must be used for all butt welds for flange and web splices in main girders and columns, for extending members, for splices in bridge barrier railing, and for T butt welds
aae755fd-9feb-582e-bf06-860ecbd5854c | note | Hydrogen controlled electrodes must be used for all manual metal arc butt welds
8f1aa4ab-b10c-5970-be3d-fbce190a8dc8 | note | WITNESS POINT: Butt weld preparation
2dc81372-ba67-5ff6-9661-c4321312d016 | note | Provide at least 3 working days’ notice of commencement of fabrication of butt welded joints
84c1bb5f-a6d9-5891-a089-546c67430587 | textbox | WITNESS POINT NUMBER:
b8a7fc61-e9be-5ef9-a793-1e57872b397c | textbox | DATE SUBMITTED:
c47386dc-3922-5b6e-a7e7-b6200e9d36c5 | textbox | Work Start Date:
67775b67-5deb-5b52-b598-c90638bdb111 | textbox | SUBMITTED BY:
0a2ac4d1-bcc5-5bb7-bb94-eb704ebcec7c | textbox | SPECIFICATION AND CLAUSE:
45a3cbc8-32c9-5bcc-8b21-24e2a8f6a3d8 | textbox | WITNESS POINT DESCRIPTION:
c226757d-cc0b-5c0c-ac18-7a574e1996c6 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 16 - Stud Welding Certification
| checkpoint | HOLD POINT
73840efd-31a9-53a9-8f37-2b2c50ca0487 | note | Requirements / Reference - B201 Cl 7.5.11
34696c86-2bc6-5a2c-80d3-39a9c9189d6a | note | Acceptance Criteria - Fillet welding of stud shear connectors is not permitted, except for repair work
1f8a6de1-664e-5801-b14a-a758297deea5 | note | Documentation for stud material properties and certification of the stud base welding must be submitted prior to the commencement of welding of studs
930d5821-e000-5cfb-8475-d5c309f2e484 | note | HOLD POINT: Commencement of stud welding
05398116-3379-559c-9851-f9821449d212 | note | Submit all details required for stud certification and the qualification of the stud welding procedure and the stud welding operator, at least 5 working days prior to commencement of any stud welding of members
b698613f-5776-5efe-b5ed-57d6acaf9d2a | textbox | HOLD POINT NUMBER:
66eb8f62-1d56-5a0c-907e-deac161e8675 | textbox | DATE SUBMITTED:
f85dcb48-42ec-5e9d-9e72-965cb5338c71 | textbox | Work Start Date:
5a2fdf0b-0c79-54cb-8aa8-07a6fd48b364 | textbox | SUBMITTED BY:
f1879880-9dc8-5f80-aa6a-0cf7264ccd75 | textbox | SPECIFICATION AND CLAUSE:
a3ff9b7d-f1fe-56f9-925f-96236bf91225 | textbox | HOLD POINT DESCRIPTION:
756a0941-79ca-57d4-9140-a4609598fc31 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 17 - Stud Welding Testing
| checkpoint | WITNESS POINT
b4eef4c1-a8bc-54b6-b346-d1e9443cbc66 | note | Requirements / Reference - B201 Cl 7.5.11
069f3f20-a680-56fb-86e1-b6e0839525e3 | note | Acceptance Criteria - Carry out testing of welded stud shear connectors as specified in Table 201.L2 of Annexure B201/L2
156417bc-bd75-537d-a4ff-0705b980a287 | note | WITNESS POINT: Testing of welded studs using ring and bend tests
b66cddeb-aa59-5fc4-8092-9aadf1b5b46a | note | Provide at least 3 working days’ notice ahead of testing taking place
5334172d-6b61-5257-8b38-400fd5a26931 | textbox | WITNESS POINT NUMBER:
37216c63-6129-56fb-acc0-67ae78f35f91 | textbox | DATE SUBMITTED:
f3ee64cc-ad84-52a6-a13f-b693520aeba4 | textbox | Work Start Date:
dffc26c8-1b57-59ee-9336-02caee53693a | textbox | SUBMITTED BY:
687ab96a-227b-5017-94fd-407a5909b2c2 | textbox | SPECIFICATION AND CLAUSE:
2df72cfb-a0ba-5f1d-83cb-4626ffac02ac | textbox | WITNESS POINT DESCRIPTION:
2da754a5-fa2d-5dec-bbd6-b1530284d118 | textbox | BRIEF NOTES:
| signoff | WITNESS POINT SIGN OFF
| section | 18 - Welding Subsequent Similar Items
| checkpoint | HOLD POINT
8492d70c-f74a-5e31-be63-fc55471c2f09 | note | Requirements / Reference - B201 Cl 7.5.15.1
f4961472-57db-5f25-86ae-c7a731f48954 | note | Acceptance Criteria - Where the work includes the fabrication of similar items, inspect the first one welded (the prototype) and submit the required documents to the Principal prior to any welding of subsequent items
b4c76721-7a18-55dd-a3a7-f305cd8b7be8 | note | The prototype must be inspected by the Welding Inspector
643007bb-542f-53cd-961a-a1b7388d1193 | note | In addition to the non-destructive examinations specified in B201 Clause 13, the extent of inspection on the prototype must comprise 100% testing of all butt welds using either ultrasonic or radiographic test methods, with 100% magnetic particle testing of all crucifix fillet welds and 33% of all other filler welds
c74768b5-8388-5259-8e2f-f15193f2d8a3 | note | Carry out these tests of the prototype welds at least 48 hours after the weld to be tested and its adjacent welds have cooled to ambient temperature
ee4b087d-ea8b-5915-a2a9-4eeec4d14c0c | note | Carry out weld inspections after all heat treatment is completed
d25ee1c5-46f4-5df1-be6a-c9cc2ee0cc8c | note | HOLD POINT: Commencement of welding of subsequent similar items
0e4e9157-878f-56a8-a971-9e554b4c516b | note | Submit documents demonstrating conformity of the prototype at least 5 days prior to the continuation of the welding
e9e987c5-21c5-54bd-b4e1-68ff13fbbc8f | textbox | HOLD POINT NUMBER:
2c3a6691-f89c-52a1-87e2-15fd62f6c523 | textbox | DATE SUBMITTED:
29bdc3ff-32e4-54c3-9d3f-85dfa4822545 | textbox | Work Start Date:
4019bb5a-88ba-5e81-a7d4-6afacecdadf9 | textbox | SUBMITTED BY:
b12a2fe6-4502-5bab-b21b-5a9a7b2cf4cc | textbox | SPECIFICATION AND CLAUSE:
9fcc690f-7fb9-58c1-b9d1-ea9731025b5c | textbox | HOLD POINT DESCRIPTION:
466e142f-0a77-5e98-a491-811e1af5f22b | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 19 - Acceptance and Correction of Welds
| checkpoint | HOLD POINT
be3a87a9-adf4-527e-bf7f-840c4a875788 | note | Requirements / Reference - B201 Cl 7.6, B201 Cl 7.7
65319d79-9e2c-5210-b7c4-18d24270dd59 | note | Acceptance Criteria - Routine and seismic requirements must conform to AS/NZS 5131
f0428770-963c-595a-8e7a-6ed9a874ec88 | note | The relevant requirements of this Specification, including the Hold Points, apply to the welding of steel structures subject to high levels of fatigue loading. Where reference is made to AS/NZS 1554 or AS/NZS 1554.1, the corresponding clauses of AS/NZS 1554.5 also apply
9b12d27d-f784-5bcf-9fe6-d07e7ba17dfc | note | In the case of welding dissimilar steels, the process must be reviewed and documented by the Welding Coordinator
d69b301f-bac5-5a81-9c22-3b4d902a33ec | note | Correction of welds – Welds not carried out in conformity to this Specification will be deemed as nonconforming
867d630d-fe3c-5776-83dc-d78adc938540 | note | If a nonconforming weld is detected, inspect the remainder of the weld (if not already required to do so) and repeat the same cycle of inspection until no more nonconforming welds are found
261fbcdb-fc25-5b5a-85e9-7ed7df2ce45e | note | Notify the Principal of any nonconformity of welds, together with the extent of the nonconformity, the proposed repair procedure, the results of re-inspection after repair and the outcome of the welding procedure review
7014b9cd-c00d-57ef-ac76-a921cbc0d1f4 | note | Repair lengths of weld containing imperfections exceeding the limits in Table 6.2.1 and Table 6.2.2 of AS/NZS 1554.1. Repair the defects using a welding procedure qualified in conformity to B201 or requalified in conformity to Clause 4.11 of AS/NZS 1554
d3745e62-d674-5f6c-be13-86abf4318b17 | note | Submit the repair procedure to the Principal for review at least 3 working days prior to commencement of repair work. Reinspect the full length of the repaired weld together with 100% visual inspection and 100% NDE of 300mm of weld on each side of the repaired weld
619a310f-a861-5200-b726-98c26ba329a4 | note | HOLD POINT: Further welding or repairs to welds
2046db24-a135-5e68-b53d-43a2a1a07e8f | note | Submit results of the inspection and examination of all completed welds, including any nonconforming welds, together with the extent of the nonconformity, the proposed repair procedure and the outcome of the welding procedure review
8f28e0c1-5b77-5428-bed0-9549818f12d8 | textbox | HOLD POINT NUMBER:
16401888-dce7-592e-b014-616024035903 | textbox | DATE SUBMITTED:
773988f0-400c-5244-808b-4c9fe29e69ee | textbox | Work Start Date:
3d3a5e36-157e-5578-ad78-1f71d9520624 | textbox | SUBMITTED BY:
b9c29f61-045d-59c1-8439-15906357f8c7 | textbox | SPECIFICATION AND CLAUSE:
db74e4da-a889-5f10-847a-c89922887b45 | textbox | HOLD POINT DESCRIPTION:
b052564f-8af1-53c1-bf4e-0328c5891da5 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 20 - Starting Bolting Operations
| checkpoint | HOLD POINT
da9ea935-f5d3-54a4-a999-3351873bcdb8 | note | Requirements / Reference - B201 Cl 8
c8602e65-5deb-5982-ac32-327ad78c2927 | note | Acceptance Criteria - Unless specified otherwise in the Contract Documents or this Specification, all bolting must conform to AS/NZS 5131
54a40ac9-41bd-5ba7-a9b5-51bd307334a4 | note | Identify and keep traceability records of the specific bolts used at each bolted connection
98265ff8-50b7-5154-83f3-d1470643bb01 | note | Bolts must not be welded
06edd1d7-86c2-557a-9f83-86394f979b6e | note | HOLD POINT: Commencement of bolting operations
3c5d6911-cc94-569e-ba67-f2d586a2a3d2 | note | Submit documents covering procedures, personnel qualifications and experience, equipment details and other evidence of conformity of bolting operations to AS/NZS 5131, at least 10 working days prior to starting
775fe99e-d557-5628-ab35-29ef89af57bc | textbox | HOLD POINT NUMBER:
0230803b-44b4-51a1-9311-1eb3cea1d3f4 | textbox | DATE SUBMITTED:
2b962249-a4d4-5f80-9ef8-d2cc729ade20 | textbox | Work Start Date:
e08a1d00-9c69-5fe2-9389-d32fb4f9329d | textbox | SUBMITTED BY:
1cd3f730-5971-5c5e-92dd-a24a107247c4 | textbox | SPECIFICATION AND CLAUSE:
572adf78-065b-5d34-8dcc-a422b355ad32 | textbox | HOLD POINT DESCRIPTION:
951b4ebd-e42c-5d15-80cb-9225162d736e | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 21 - Finishing Bolting Operations
| checkpoint | HOLD POINT
995dcc61-764c-5469-9737-983782b54f74 | note | Requirements / Reference - B201 Cl 8
134ee2a9-f59e-5c0e-bc4a-ca055715d5fc | note | Acceptance Criteria - HOLD POINT: Completion of bolting operations
a4c2f319-17b1-5d9e-8d44-81c848ea85a5 | note | Submit test reports, bolting records and other evidence of conformity of bolting operations to AS/NZS 5131
ff14dc8d-912f-5bf5-80ac-10e5593cc80a | textbox | HOLD POINT NUMBER:
03d094f8-a005-53fc-b46e-7d75c27291f8 | textbox | DATE SUBMITTED:
c2eea1fc-4f58-5aa5-9e87-f1a696e1d873 | textbox | Work Start Date:
6c0aacdb-23b1-5f61-ab05-740100629a33 | textbox | SUBMITTED BY:
cd31bc69-b800-5cc1-b3a9-030095b8c5a1 | textbox | SPECIFICATION AND CLAUSE:
c2f65539-10a8-55b8-8cf7-432ef84f4595 | textbox | HOLD POINT DESCRIPTION:
d62c548c-e002-56bd-a253-d9d13f81f66f | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 22 - Erection of Steelwork
| checkpoint | HOLD POINT
62cd4d3e-3278-53f3-b49e-7ada71ecd427 | note | Requirements / Reference - B201 Cl 11
a0f95e79-8eb1-5db8-928a-53ba04473209 | note | Acceptance Criteria - Erection of steelwork must conform to AS/NZS 5131 and the Contract Documents, as well as Specification B201
181e14b4-c8ea-5a8e-a8b3-9b72c1db399c | note | Risk assessment must conform to TfNSW G22
919d3ffe-7a7e-5a14-b734-5c6dd81a4ecf | note | Site survey and stability checking must conform to AS/NZS 5131
831d4af6-6c55-5939-b891-74f6035430ed | note | Arrange the supports for members with provision for fine adjustment to achieve the required profile in the Design Drawings
2a2f5eb2-9cb0-54f5-82fb-bb581904a2ce | note | Submit a certificate by a suitably qualified surveyor verifying that the profile of the falsework is in conformity to the profile shown on the Design Drawings. Show details for the allowances for settlement and joint take-up
d0dc28ff-2e70-5863-8de7-c0cca9140df5 | note | HOLD POINT: Erection of structural steelwork
2b5f4e00-081d-5e0d-8bf2-0a3788b093fc | note | Provide certification as per Clause 11.5 above
b33aaf8a-9de6-5b94-bb1d-aa595b163d7e | textbox | HOLD POINT NUMBER:
d80293f9-4851-5e4b-bf1a-53fc2b0e5d2d | textbox | DATE SUBMITTED:
6455ba29-dd95-576d-95a7-89f6219a1757 | textbox | Work Start Date:
41729f08-4cba-55a8-bd94-2ca73800eb3d | textbox | SUBMITTED BY:
8488850e-50a1-53fe-b296-dd53846f0442 | textbox | SPECIFICATION AND CLAUSE:
ade7d9ad-0d2a-54d0-a4f3-c8df44cb307d | textbox | HOLD POINT DESCRIPTION:
95f67926-05b9-55fe-88cc-ac83abc22255 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 23 - Bolts, Joints, Surveyor’s Certificate, Expansion Joints
| checkpoint | VERIFICATION
b692ca24-423d-52e4-af6a-1856b0d477d6 | note | Requirements / Reference - B201 Cl 11.9 – B201 Cl 11.12
aefb6d6b-cc03-5db6-b9fe-c278f31563fa | note | Acceptance Criteria - For field welded joints, hold the ends of the members and/or segments in place during welding using temporary devices. Upon completion, carefully remove the devices and restore the steel surfaces by grinding smooth and flush. Examine 100% of all field welds both visually and by ultrasonic or radiographic methods
727adb1a-056b-57a5-be4d-475475af2d54 | note | Carry out the assembly of field bolted connections in conformity to Clause 8. The joints must be friction-type connections. Tighten the bolts using the part-turn method. For joints containing more than eight bolts, check the “snug-tight” condition by a second run over the bolts. Once fully tightened, do not release and re-tighten bolts to either the original position or otherwise. Submit a certificate by an NER-registered engineer verifying that bolting has been carried out in conformity to this Specification
74740358-b424-55a6-ae38-58166c603487 | note | Submit a diagram certified by a suitably qualified Surveyor that shows the profile of the completed member(s) in relation to the profile shown on the Design Drawings
72f3f162-1cfc-5728-9cc1-73082809f918 | note | Expansion joints have been dimensioned for the mean temperature shown on the Design Drawings. Allow for changes in the length of the superstructure caused by temperature variations by placing the expansion joints such that the clear distance across the joint will be as shown on the Design Drawings at the specified temperature. Install the proprietary joint strictly in accordance with the supplier’s TfNSW approved joint installation procedure and other requirements in TfNSW B201. Following installation, the joint must be watertight. Installation of the joint must result in a smooth ride for passengers in vehicles traversing the joint.
dc9d324d-185a-5bd9-823d-1834a94f6a92 | note | Conform to the following tolerances:
5f6f7bd8-76c0-5397-8504-5d529d304efe | note | (i) Vertical – within ±3mm of the design level over all top surfaces of the joint;
15eda21c-9c1a-5932-aa55-c4c16d46499d | note | (ii) Horizontal – within ±5mm of the design location of the joint;
55ddc8bd-b165-58ef-ae52-38c5a46c3659 | note | (iii) Joint gap – within ±5mm of the specified width
6a052ec5-2c6a-531d-a154-56dfb69ff06c | note | Comments / Attachments / Records - Submit diagram from surveyor
| section | 24 - Steel Bridge Girders Supplied by Principal
| checkpoint | VERIFICATION
7251189f-821f-5eff-b151-4b897a527bb4 | note | Requirements / Reference - B201 Cl 11.15
84802ad4-5ee2-5779-b33f-c1cea369f988 | note | Acceptance Criteria - Where steel bridge girders are supplied by the Principal, these will be supplied, delivered and stacked on site at no cost
54309454-c0a0-5702-b5f1-2995a28faebb | note | They will be supplied prefabricated and with the protective treatment(s) applied
cbf345d9-da5c-5562-ada0-d184abcfaa9b | note | Prior to delivery, provide the Principal with details of a suitable location for dropoff of girders
2efdace8-41d7-53ad-bf09-dbde635a438e | note | Issue the Principal with a signed receipt for each girder at the time of delivery and stacking. The receipts must include the identification marking of each girder and report on any damage or defects. Where damage or defects are found, obtain certification from the Principal that they were there upon delivery
7c2c7d32-b1d8-5100-be34-4bcc4d9c323c | note | Any damage or defects listed on the receipts and verified by the Principal as existing at the time of delivery will be rectified by them. Any that are not recorded or certified will be rectified by Abergeldie
ac83769c-5fec-5a49-b454-f3ae0414c19b | note | Following any rectification work by the Principal, certify in writing to the Principal that each defective steel bridge girder has been rectified to the specified condition
47bb408e-7737-5ed6-9b39-3c4d204a015a | note | Comments / Attachments / Records - Test results; Inspection certificate
| section | 25 - Inspection, Testing and Correction
| checkpoint | VERIFICATION
21041fd3-9e5f-5641-947f-c7bd095ae576 | note | Requirements / Reference - B201 Cl 13
5ffc97b5-a2a9-5ed5-932f-912f81a1dd6e | note | Acceptance Criteria - Conform to AS/NZS 5131 and Annexure B201/L
f7459861-24c9-5e7e-b542-4a21762b841d | note | All testing, including material testing, testing of welding procedure test coupons and non-destructive inspections, must be performed by labs with third-party accreditation to AS ISO/IEC 17025 by a signatory to the International Laboratories Accreditation Cooperation (ILAC) through their Mutual Recognition Agreement (MRA) in the specific field and class of testing, for the purpose of establishing conformity to the requirements
75eaa5f1-b3e2-51d6-af8f-2722abfbf8f7 | note | The appropriate logo or further details of the signatory must be noted on the document or test report
083a71d5-5d17-5f48-9653-5879bbfdf62c | note | Note that NATA is a ILAC (MRA) accredited body
7ac793b1-9cd5-5fb3-9446-2b81fb6679b5 | note | Mill certificates and other test and inspection certificates must be in English and include the specific content required by a particular materials standard or test method
4727fac1-296b-5c2b-9416-31fed2e08c7e | note | All non-destructive examination reports must be prepared as required by AINDT qualified and certified non-destructive testing technicians. The report must identify both the technician carrying out the test and the technician responsible for the test report
| section | 26 - Modifications to Fabricated Steelwork, Existing Structures
| checkpoint | VERIFICATION
7d5137a5-4207-5a56-955c-a0c33e7ff242 | note | Requirements / Reference - B201 Cl 14
59ec5369-b949-5583-9276-4c8acd132eee | note | Acceptance Criteria - Site modifications to fabricated steelwork or existing structures must conform to the applicable TfNSW Maintenance Specification(s) or to AS/NZS 5131, as appropriate
591ef4f4-ea7d-57c1-a832-ad496f1c5153 | note | Submit the proposal in writing for any site modifications to the Principal for approval prior to carrying out any such modification
c3263267-d94d-5279-ac9b-c258e69f56a7 | note | HOLD POINT: Modification of fabricated steelwork or existing structures
ab13675e-fa53-5b9a-8c6f-6af362ba653a | note | Submit full details of any proposed site modification on fabricated steelwork or existing structures, including design calculations and detailed drawings, at least 30 working days prior to commencing any such work
| section | 27 - Certification of Completion of Fabrication
| checkpoint | VERIFICATION
c9625c4a-cd0d-5648-8e00-ed9df95e9684 | note | Requirements / Reference - B201 Cl 15
148c124b-4c06-5430-b7d8-bb86e34626be | note | Acceptance Criteria - During the construction of the Works, the Fabricator must:
1675dadf-f07c-536b-b6a3-aeaa7d07fc3d | note | (a) compile all technical details and records of activities into the Fabricator’s Data Report (FDR);
a517f109-96cd-5a03-bf63-3690584d432f | note | (b) keep the FDR up to date so that its submission on completion of the Works is not delayed;
211276e5-fdef-5ff2-b20c-04c4bf4a16ce | note | (c) prepare the FDR in either of the following formats;
42c8bbf7-8ef4-585c-af66-d9e90daf26b0 | note | (i) hard copy, using A4-size binders with file separators clearing separating each section, with a detailed table of contents at the front of each binder;
f630b0fb-eafa-50e2-b3a3-e7fddd35a4a2 | note | (ii) soft copy, as a set of electronic files.
b6b3153a-dde8-58ea-88c0-b8e90a7f375b | note | (d) ensure that all documents in the FDR are in English, use SI units and are complete originals or clearly legible copies
4d5283af-6899-52ac-be3d-1b299bf81cbb | note | (e) include in the FDR all information under the following headings as a minimum:
02c0ef48-6867-53b8-b1bb-89c1d8147635 | note | (i) fabrication specific procedures included in the PROJECT QUALITY PLAN;
c31f4c16-7d54-54c3-b3ba-38481ae39084 | note | (ii) qualification of relevant fabrication personnel (Responsible Welding Coordinator, Welding Supervisor, Welding Inspector, NDT operator and welders);
f5ae3f50-b086-519b-b9fd-b993d3d8a493 | note | (iii) inspection and test plans (ITPs) and documents detailed within the ITP;
18ba881c-0f02-5a7c-adfb-73efb91609d8 | note | (iv) deviations from the Contract Documents;
38c40a43-69e9-5295-8010-8440470d4c11 | note | (v) material test certificates, including for steel supplied to the Works, and for bolts, nuts and washers;
1c7394ce-3ac6-5182-ab5b-f2786928b74b | note | (vi) welding records, including weld maps, welding procedure specifications, welding procedure qualification records and relevant test certificates, welder qualification records, and welding consumable certificates
f0228b44-9355-5a04-bca3-2b27ff655cb6 | note | (vii) Non-Destructive Examination reports;
c24d1e1e-797f-5cca-a55f-cfe00151610a | note | (viii) work-as-executed drawings of the fabricated members;
b99d75f9-0bf1-52e8-87a5-510467dbbb71 | note | (ix) nonconformity reports and outcomes of corrective actions;
e21f45b2-7796-508a-b1e6-b736189402e4 | note | (x) shop assembly records;
8422f7b0-d7df-571e-8dae-de205cb8ceed | note | (xi) instrument calibration certificates
16f0aad1-7094-5a61-adf7-c9906c1dc90f | note | (xii) inspection and testing records, including measurements of dimensions compared with relevant tolerances
a6fb7ceb-e8f0-58de-b782-7c2451faf076 | note | (xiii) delivery / dispatch records
2aff0888-475b-565b-97ae-7fa47db86a4e | note | HOLD POINT: Completion of fabrication
b55fa52c-b78c-54e8-8b30-cb1633e7ecf7 | note | Provide the Fabricator’s Data Report (FDR) to the Principal within four weeks of completion of fabrication
| section | 28 - Project Specific Requirements
| checkpoint | VERIFICATION
d3e05abd-d9e2-5800-8754-13968adc6c30 | note | Requirements / Reference - Annexure B201/A
8fc6d3d7-812f-53e5-92ec-456f86a6fb0a | note | Acceptance Criteria - Construction Category for Specific Components (refer Cl 4.2) – Not applicable
fc96b16f-9541-5ff9-8f11-c907b3bd6ef8 | note | Treatment Grades for Specific Components (refer Cl 4.3) – Only as specified within this Specification
9914eb7b-5ae6-54e8-9717-559b9ce6711b | note | Essential Tolerances for Specific Components (refer Cl 4.4.1) – Only as specified within this Specification
fe995903-4216-5123-845d-56e62bb323d2 | note | Function Tolerances for Specific Components (refer Cl 4.4.2) – Only as specified within this Specification
b7352e48-5257-5911-88b6-a2e095f5e1aa | note | Details of Building Information Models (refer Cl 4.5) – Not applicable
b8bcebe4-0fe1-5aad-a3d2-8c487e0401d7 | note | Verification Testing of Steel Samples (refer Cl 5.3.1) – Only as specified within this Specification
9999ff35-065b-55dc-b5d0-c6786464f244 | note | Special Test Pieces – The Works covered by this Specification require the preparation and testing of special test piece(s) as detailed in Clause 7.4.2 of this Specification and as specified in the PROJECT QUALITY PLAN
| section | Lot Verification
| checkpoint | Lot Verification complete
5a15dfec-409b-569b-816d-e116daf1f027 | textbox | Lot Verified By:
c816b27f-cbcc-544b-91e8-49f12fbfd1a1 | textbox | Lot Closed Date:
12f7c472-291d-50c0-b133-1483a874d908 | button | Submitted to Client | Yes, No, N/A
4782aa9b-3a00-5890-9c93-57dcb5fb0ad6 | button | Reviewed by Client | Yes, No, N/A
8f1f79f4-32f6-5fde-9783-eb63a7e2ccad | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 14 - R54 Concrete Paving Rev 0 |  | ITC 14 - R54 Concrete Paving Rev 0 | 5603fe5e-0136-4970-9a86-095a3c3d5887
| section | Lot Information
| checkpoint | Lot Information complete
9113560e-1e3b-5b83-8a2e-d9bde736a228 | textbox | Lot Opened On
aadb29e8-bab3-5200-bb30-70e93439eadf | textbox | Date of Works
114f9e6a-720e-5eed-8a5b-680a16df9935 | textbox | Lot Type
762de5b9-0d40-5c06-a99d-258eb21187da | textbox | Start Chainage
4add8f7b-cf75-5e2b-88d0-e680e58f80f0 | textbox | End Chainage
5deefd5d-8586-54a3-915e-03bb85d3d168 | textbox | Offset
11b47e28-8c33-5610-88e7-71302edd154f | textbox | Control Line
| section | 1 - Safety Review
| checkpoint | VERIFICATION
03670640-c50b-5661-8d06-1d7dfb225df5 | note | Requirements / Reference - Project Safety Plan
4984b7b9-f2f0-52a9-a5f6-015e138cb426 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
630d2c9b-0c0e-5b8b-b50b-8d6810e9e0be | note | Required Safe Work Method Statements completed and signed
6a1bebd0-ca43-5229-8984-641e5e96dc5c | note | Subcontractor’s safety plan/procedure approved
| section | 2 - Environment
| checkpoint | VERIFICATION
37ea3cb7-fee7-5d1f-a9a5-c36cfb622f1a | note | Requirements / Reference - Project Environment Plan G36 Cl 3.1 G38, G40
ba1e49db-8a42-5e3c-a003-7794b4c316ad | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
f46616bc-080b-5b2a-bdb1-8e632272dd46 | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
| section | 3 - Material
| checkpoint | VERIFICATION
5c2b2971-d136-549f-9a74-6672ee2f0500 | note | Requirements / Reference - R54 Cl 2 Test Method TfNSW T109, TfNSW 3051, R53
935fcdff-f73f-5656-a999-cc8b0fc62434 | note | Acceptance Criteria - Select Fill Type U must consist of a granular material with a particle size grading of 100% passing the 26.5 mm sieve and a Plasticity Index, determined by Test Method TfNSW of between 2 and 12
64e45224-8715-573a-b1d5-42892cac4ca1 | note | Class 2 DGB must comply with Specification TfNSW 3051
8dc04e25-e5d0-529b-8388-5368e3de5ab1 | note | Supply of concrete and steel reinforcement must comply with Specification TfNSW R53
| section | 4 - Unsuitable Material
| checkpoint | HOLD POINT
7b142dce-4308-5622-99aa-f637d10f86fe | note | Requirements / Reference - R54 Cl3.2 R44 Cl3.1 TfNSW R44
f286118d-25ab-5687-a379-e65257cdcfd3 | note | Acceptance Criteria - Have the Geotechnical Engineer undertake tests and inspections of all foundations and verify that they are suitable for General Concrete Paving, or otherwise recommend a foundation treatment in accordance with TfNSW R44 Cl 3.1
33a3423b-ed31-50d6-ae0d-b8b3df865266 | note | Notify the Principal of any area of the foundation which may contain material that is unsuitable to support the proposed pavement.
723fd931-0a9e-5d17-9aa9-5f0086dd49ee | note | If the Principal agrees that the material is unsuitable, or deem any areas of the foundation to contain unsuitable material, the Principal may direct that removal and replacement of this unsuitable material or some other foundation treatment in accordance within TfNSW R44.
41ed8297-9ef1-5c8a-993e-626f88a8969a | note | The Hold Point in TfNSW R44 regarding unsuitable material applies.
a3f4db42-e188-5e26-8f31-ad2db65b3497 | note | HOLD POINT: Removal of unsuitable material (if applicable)
2223f217-0144-5871-8aa2-eb37f8060984 | textbox | HOLD POINT NUMBER:
976b287a-7f7d-5f2a-9308-c1bda2bbbc4a | textbox | DATE SUBMITTED:
51702d23-61ea-5dfb-9104-d5ee69ee3ed5 | textbox | Work Start Date:
92c8df67-4497-5c46-bcf9-d4445227658a | textbox | SUBMITTED BY:
7ae3d21a-16e3-592c-b0b8-4144407aea01 | textbox | SPECIFICATION AND CLAUSE:
23df9171-b677-57a9-b315-3f2d1ef0b39b | textbox | HOLD POINT DESCRIPTION:
e4189d63-ac80-5671-aacf-5f1176be5f2e | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 5 - Foundation Levels
| checkpoint | VERIFICATION
41cb305c-7116-5402-a1fd-6c1cc8dd533c | note | Requirements / Reference - R54 Cl3.5
6a632989-d361-5735-896a-290d847f110a | note | Acceptance Criteria - Construct the top of foundation to the design surface levels, with a tolerance of +5 mm and -10 mm
3c4de9e8-0469-53cb-a81a-b803776ab488 | note | The finish surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 10 mm, except at grade changes
a45848f9-4d4d-5120-9d85-675cac16db57 | note | Comments / Attachments / Records - Survey report(s)
| section | 6 - Concrete Mix Design
| checkpoint | HOLD POINT
50abe4aa-bdb7-5727-8b6d-a5eb6b145cd0 | note | Requirements / Reference - R53 Cl 2.4.3
b605c558-9de1-5b61-aae7-246895b36f38 | note | Acceptance Criteria - Concrete manufactured and supplied in accordance to R53 and AS 1379
909bfaae-0c42-5d36-b13a-ab4449cd764b | note | HOLD POINT
cb1f0bbe-1255-5e0f-8234-5e7a8f19ff93 | note | Provide either:
d359b86b-bb3e-5af1-bdaf-551933f066ea | note | The documents specified in R53 Cl 2.4.3 items (a) and (b) OR
50ed38c3-d3f9-53af-8e51-60eec7dc72da | note | Details of mix(es) selected from the TfNSW Register of Concrete Mixes, together with a statement certifying that the mix conforms to this Specification and is suitable for its intended use.
430192bc-2dd4-53f5-99a2-7acf6ae87f1b | textbox | HOLD POINT NUMBER:
7d023868-027d-5ccf-9bf1-6899dfa3dfc2 | textbox | DATE SUBMITTED:
cd315a6f-2c0a-5eb3-8f53-f92e42260579 | textbox | Work Start Date:
d5f995c8-7c25-58a6-9ad8-12c4d12805c1 | textbox | SUBMITTED BY:
0fc31a4a-defd-5e8f-845b-b7869b2eeec7 | textbox | SPECIFICATION AND CLAUSE:
ae92213c-42e6-57ef-8f1d-38cf7061c4f1 | textbox | HOLD POINT DESCRIPTION:
e99df2fe-118b-5d9d-86bb-9b64250b1754 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 7 - Placing of Concrete
| checkpoint | HOLD POINT
1500ba48-f0dc-5319-9549-076de601a2b2 | note | Requirements / Reference - R54 Cl 4.3 R53 Cl 3.3.1
a4b00c3e-7cb4-5412-a8ef-307b9bcfbe90 | note | Acceptance Criteria - Comply with Clause 3.3.1 of TfNSW R53
75e61270-e6e2-5230-a776-7a9ec33cc08b | note | The Hold Point in TfNSW R53 for placing of concrete applies.
f66d7e07-2b68-5a4d-bd7e-46c3a0c66166 | note | The Principal may inspect the completed reinforcement and formwork prior to authorising the release of the Hold Point.
ef224f72-562c-5391-a2ca-5c2bdb9a3857 | note | Before commencing placement of concrete, remove all dirt, and other foreign matter from the forms
0aee9ca0-e172-52aa-b576-a9523bc18ba9 | note | HOLD POINT: Pre-pour inspection of concrete.
5aa26ce7-302c-5b1c-aa25-f61c79362bb9 | note | Notify the Principal of:
1bb52be2-4de9-5570-9c2d-e76adbdf8b68 | note | expected completion time of fixing of the formwork and reinforcement (if applicable) AND
482cdecc-c65f-56e3-8aa4-8c31ee102b5c | note | expected commencement date and time of placement of concrete
05c47fd5-7f6e-5356-b969-0e0299583f66 | textbox | HOLD POINT NUMBER:
d9478ca1-5c47-5d6f-b890-a436ede8554d | textbox | DATE SUBMITTED:
2768446c-d474-5962-bccc-79f4d25b0a24 | textbox | Work Start Date:
60194602-8e0e-597b-bd9b-d6834265baab | textbox | SUBMITTED BY:
0fb66917-0a7f-5fac-ace3-1ccd6d122614 | textbox | SPECIFICATION AND CLAUSE:
11d5cb57-2454-5c03-9316-96f04e04e2fc | textbox | HOLD POINT DESCRIPTION:
fb1b1839-7a3d-50a0-8c9a-ddbbde1e9a19 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 8 - Proposed joint layout and reinforcement details
| checkpoint | HOLD POINT
943ad890-d6de-5ead-ae25-c8a2e8f30280 | note | Requirements / Reference - R54 Cl 4.4 R54 Cl 4.4.2
f4f4170e-f598-5531-ae8c-5df1036fc7f3 | note | Acceptance Criteria - Construct transverse joints at right angles ±6° to the longitudinal edge of the paving slab, otherwise the slab will be treated as odd shaped. Where possible, avoid creating odd shaped and mismatched slabs.
f3d1661d-b9f5-5234-8f9c-5802cd16fd6b | note | HOLD POINT: Steel reinforcement fixing and concrete placing
01124ed2-c82b-5572-80d2-6714ef325359 | note | If joint layout is not shown on the Drawings, submit a drawing showing the proposed joint layout and reinforcement details.
bb85fc56-b4c3-56a6-a425-2ba890240b37 | textbox | HOLD POINT NUMBER:
31ba3426-69a7-5de2-9f6a-8599c3d1fc70 | textbox | DATE SUBMITTED:
332f97bd-74ea-5db5-b828-377277c1b7c7 | textbox | Work Start Date:
fd9ee08e-d641-52a3-960b-6e7bb449d1a1 | textbox | SUBMITTED BY:
97264e71-2b96-54b7-83df-3fe5bd05e570 | textbox | SPECIFICATION AND CLAUSE:
3a779a09-13cd-53d9-9ade-ef2501981021 | textbox | HOLD POINT DESCRIPTION:
898fabd2-690a-55f7-889a-42ae1958d5cf | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 9 - Surface Finish
| checkpoint | VERIFICATION
32164b82-0f43-52dd-8c02-dff28accd32a | note | Requirements / Reference - R54 CL 5.1 R54 Table R54.3 R54 Cl 5.3
2865a467-3d07-564d-8f28-f4908c043bc3 | note | Acceptance Criteria - Unless shown otherwise on the Drawings provide on the top surface of concrete paving (except patterned concrete paving) the surface finish specified in Table R54.3. The finished paving surface must be uniform in colour and appearance.
a57dd524-9123-58fb-9b68-a2a7535521f1 | note | The finished paving surface must be uniform in colour and appearance.
97a5e453-34f3-5ed5-b784-e816eee2ccfd | note | All edges, except for those abutting other paving or structures, must be neatly rounded to a radius of 10 mm. Edges abutting other paving or structures must be neatly rounded to 5 mm radius.
58f6c4d5-ed89-5d1e-984f-224229a975d2 | note | Construct the finished surface of the concrete paving to the design surface levels, with a tolerance of +10mm and -5mm
0f8fcb4f-4151-5ba6-b402-38e7f97979f4 | note | The finished surface must not deviate from the bottom of a 3m straight edge laid in any direction, by not more than 5mm, except at grade changes. Where the concrete paving abuts an adjacent structure, any vertical step across the joint must not exceed 5mm unless shown otherwise on the Drawings
9319e938-01d9-537e-8ea5-e54afc5b2ae8 | note | Comments / Attachments / Records - Survey report(s)
| section | 10 - Patterned Concrete Paving Details
| checkpoint | HOLD POINT
328deb27-696b-5947-81c3-702cf77433e9 | note | Requirements / Reference - R54 Cl 5.2.1
b854509b-57b5-5f10-b17e-c1423223b3c4 | note | Acceptance Criteria - HOLD POINT: Placing of patterned concrete paving
630d1854-c758-5cdc-ad8c-e814a440650f | note | Provide details of pattern, colour, class of finish and experience of personnel in producing patterns on concrete paving, at least 5 working days prior. The Principal may require a sample panel to be prepared and submitted
68168c5b-ff07-5042-b1f2-c7bebfdcae07 | textbox | HOLD POINT NUMBER:
008da835-0340-5b58-abda-e6b4e409e8fb | textbox | DATE SUBMITTED:
abbbcddf-0b05-5d46-b842-71e58796a3cd | textbox | Work Start Date:
bcff390e-83a7-552e-9ca8-2c3fa29d6a92 | textbox | SUBMITTED BY:
784a8d62-a1b6-5b6e-881a-da65d735130f | textbox | SPECIFICATION AND CLAUSE:
28e510fb-125f-5dea-93f7-ca02e7ad0e6a | textbox | HOLD POINT DESCRIPTION:
c38dae9c-440f-5e2d-beb1-9650b27c625b | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 11 - Tactile Indicators
| checkpoint | HOLD POINT
5d394f60-2842-5627-82b1-ec290aa76c6e | note | Requirements / Reference - R54 Cl 6.1
1a587765-c373-50f1-819a-d570611c38db | note | Acceptance Criteria - Tactile indicators must conform to AS/NZS 1428.4.1 and must be stain, slip, impact and UV resistant
acf22357-fbd4-575b-8f50-fb17c9887e91 | note | Performance levels (refer AS 3958.1 for definition) is specified as “Commercial”. Comply with the installation guidelines in AS 3958.1 Clause 3.3.1.2 (Exterior floors – General applications, using cement-based adhesive or modified mortar) where applicable.
0c0a156f-ea44-5c76-882e-99ecdbb32dff | note | HOLD POINT: Construction of paving with tactile indicators
d447a6c4-5860-5c43-882f-7dddb3f4a9be | note | Submit details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method.
7be093d5-f15b-5f69-aebe-bdc8ea3b9129 | textbox | HOLD POINT NUMBER:
9ebda262-0e77-553d-9d5a-afa402ae1132 | textbox | DATE SUBMITTED:
957e7ccb-dea5-56c3-bfb1-0c79d8a3c43c | textbox | Work Start Date:
66e66250-0fd2-56b9-93b6-db7356dee575 | textbox | SUBMITTED BY:
f3dfaafe-89b8-5fe2-a2b6-576d2e7c7341 | textbox | SPECIFICATION AND CLAUSE:
662d554b-bb75-5350-bb6c-97277beb5684 | textbox | HOLD POINT DESCRIPTION:
ab09421c-8c0e-5050-995f-7ae9b76c0dc0 | textbox | BRIEF NOTES:
| signoff | HOLD POINT SIGN OFF
| section | 12 - Close out of Lot
| checkpoint | VERIFICATION
2d8b8bfa-0181-5a05-a18a-1c68ee83a13d | note | Requirements / Reference - R54 R53
0f76eaaa-730b-5a66-9a41-445dfc6b72ba | note | Acceptance Criteria - Provide all required documentation for close out of the Lot
b7111247-8f35-5fc1-92a6-53d2c0eb87c5 | note | Comments / Attachments / Records - Concrete delivery docket(s); Concrete test report(s)
| section | Lot Verification
| checkpoint | Lot Verification complete
7394472c-b0bc-5918-b0d3-6aad34cde980 | textbox | Lot Verified By:
d793f4d1-489d-5b88-80d2-dece386f2fb4 | textbox | Lot Closed Date:
bcdec2ab-cdc1-5c10-a2e3-8d306c877875 | button | Submitted to Client | Yes, No, N/A
aefe8cbb-c2d6-5830-95c4-eef31c8e714c | button | Reviewed by Client | Yes, No, N/A
65e114c9-bcb2-5279-bbed-ab7bb1e9407f | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 15 - R63 Geotextiles Rev 1 | itp | ITC 15 - R63 Geotextiles Rev 1 | 398a4d13-0bee-4e8c-a6d6-f24aa894f639
| section | Lot Information
| checkpoint | Lot Information complete
062e9393-4ae5-5190-ab1e-01a88aa31b1c | textbox | Lot Opened On
064a9927-10ea-5004-a090-15e203e76064 | textbox | Date of Works
d69cf80c-4d5f-5cf6-ace6-c0f2dc5caba0 | textbox | Lot Type
5796b077-61a5-5e42-bd1f-76078a83df82 | textbox | Start Chainage
dd1d5a39-daf8-5099-9165-fe3ff855fd39 | textbox | End Chainage
006a7568-b085-570d-a4aa-781ab8e0327e | textbox | Offset
c3f8f15f-1cc9-5af3-bc14-55ec56938b9d | textbox | Control Line
| section | 1. Material Requirements
| checkpoint | 1.1 - General Material Requirements
aed3ba9d-4082-5e7f-a3f7-57507bb195a2 | note | Document Reference / Applicable Standard - R63 Cl 2.1
d51a5ad1-f7c7-5c55-813e-2c7c3e9982e2 | note | Acceptance Criteria - The fibres of the geotextile and thread used in joining lengths must consist of long chain synthetic polymers composed of at least 95% by mass of polyolefins or polyesters.
43ac87aa-b11e-5897-8e4a-3306f6a17d35 | note | Geotextiles must be free of any flaws which may have an adverse effect on the physical and mechanical properties of the geotextile.
3efa77fd-8a74-59cb-a21f-43d62c968aea | note | Geotextiles may be manufactured under controlled conditions from recycled materials. Geotextiles manufactured from recycled materials must conform to the requirements of this Specification, be identified as such on the Certificate of Compliance
812aa34a-053c-56f0-9d7f-00942511fee1 | note | Frequency/ Process Held - Once / Prior to procurement
a4fcab62-408d-565a-9aba-50ced7b57021 | note | Inspection - ACPL - S
c0610dad-ec7f-57e8-a689-0456fbe0f156 | note | Inspection - Client - S
65836d21-1b4f-5f1e-be89-2b238dd4db8e | note | Verifying Records - Material Data Sheet
| checkpoint | 1.2 - Strength and Filtration Class Requirements
8bc2a4e9-360a-5b5b-8335-20f459aabbe2 | note | Document Reference / Applicable Standard - R63 Cl 2.2
08a971f1-4f0f-541a-a095-f86cce64b9d5 | note | Acceptance Criteria - Geotextiles for the applications of separation and/or filtration must meet the relevant Strength Class requirements of Table R63/E.2 to ensure survivability.
113914ba-1f80-5a63-be3e-c6a873a7fda6 | note | Geotextiles must meet the relevant filtration requirements of Table R63/E.1 for each application.
dced4195-d444-5021-b261-6c1a8aa4ffef | note | Frequency/ Process Held - Once / Prior to procurement
5774a414-76db-5610-925a-41083b359fcf | note | Inspection - ACPL - S
8868e2f6-ea54-5466-ba07-75e12cce540a | note | Inspection - Client - S
45c96770-100e-5a71-9e96-6d5c6428bc0e | note | Verifying Records - Material Data Sheet
| section | 2. Site Sampling and Testing
| checkpoint | 2.1 - Certificate of Compliance
9fad6303-3eb2-5482-9989-0062759ea5f2 | note | Document Reference / Applicable Standard - R63 Cl 2.5
b80a5fc3-efd5-5931-9dcb-8c3500240193 | note | Acceptance Criteria - Provide a Certificate of Compliance that the geotextile complies with all the requirements of this specification for its specified usage together with tests results reported on NATA endorsed test documents. The certificate must not be more than twelve months old.
e76a814d-405e-5c3c-96fd-71e84bd81a38 | note | Frequency/ Process Held - Once / Prior to delivery of geotextiles
52d5c4c0-013a-522a-abd4-490cbd71829f | note | Inspection - ACPL - H
92c38ed4-2fc4-5e5a-9e40-cf5548f1d436 | note | Inspection - Client - H
5db3b3df-9aa7-55d1-8a73-42aa70b6ed3f | note | Verifying Records - Certificate of Compliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Site Sampling and Testing
a8489db4-8988-53f5-afa3-f750c32a1f0f | note | Document Reference / Applicable Standard - R63 Cl 2.4
a7909e80-884a-595b-b06b-184d5bfe16d6 | note | Acceptance Criteria - Location, date and time of sampling and person sampling to be witnessed by the client. Frequency of sampling and testing must be in accordance with Table R63.1.
78d26f35-c1be-5fec-9cb4-54298b4d8a16 | note | A representative sample, covering approximately 15 m2 of geotextile (e.g. 3 m by 5 m), is cut from each sampled roll but not within 2 m of the start or end of the roll. Where directed, provide samples to the principal.
e016ddec-4cac-56d9-a942-ae044831ab23 | note | Clearly mark, for example by means of a large arrow, the longitudinal direction of the geotextile on each sample.
75824401-751d-5b7a-899b-8470b1ca72be | note | Test the geotextile samples at an approved NATA registered laboratory accredited for the range of tests given in Table R63/E.1 and Table R63/E.2.
4702a74e-1f7c-56a9-af47-e624ce5f88ee | note | Frequency/ Process Held - As specified / Prior to Lot Closure
38dfa8f6-27bb-5f3c-9528-946b18af1bbe | note | Inspection - ACPL - W
53c845c9-6822-54b4-a13d-b6e3aed7bc5f | note | Inspection - Client - W
b65141d6-3a1c-5cfb-97f5-2d04fed05953 | note | Verifying Records - Test Results
| checkpoint | 2.3 - Sampling Test Results Submission
7ef5696d-d13a-56bd-b251-328b25fd085d | note | Document Reference / Applicable Standard - R63 Cl 4.1
06e55181-ee3d-515b-aa82-e6682a36d857 | note | Acceptance Criteria - Site sampling test results referred to in Clause 2.4 at least 14 days prior to placement of geotextile.
cec76f2c-51f7-5888-8197-a92dd1c75b6f | note | Frequency/ Process Held - Once / 14 days prior to placement of geotextile
f03a046a-1492-5837-a078-f3a4e24d4bf3 | note | Inspection - ACPL - H
5d14c177-cc1a-5203-af44-d7960b74f48b | note | Inspection - Client - H
0a47b250-74f2-52c1-b0c4-2a0a86b66dc0 | note | Verifying Records - Test Results
| signoff | AUTHORITY HOLDPOINT
| section | 3. Storage, Identification and Delivery
| checkpoint | 3.1 - Storage, Packing, Identification and Delivery
b721bb4a-83b6-5324-99b3-17d6dc14b807 | note | Document Reference / Applicable Standard - R63 Cl 3
471bc1c2-d6e9-5648-b1c3-3ba7b8f4f88f | note | Acceptance Criteria - Geotextiles must be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
78db1515-4e80-5c64-a1da-9728f682c142 | note | Geotextiles must not be stored directly on the ground or in any way they may be affected adversely by heat, dirt or damage.
f6b632e0-16ac-59b2-a6a0-92604a183750 | note | The protected geotextile rolls must be clearly labelled showing manufacturer, type of geotextile and batch number identification number.
1cbeb448-29f5-5fa2-83a6-10408a15be8e | note | Geotextile must be delivered to the site at least 14 days prior to commencement of installation.
8198f3bb-01f7-5fe1-b837-45603e33928d | note | Frequency/ Process Held - Delivery to site
04bbbc0a-4e8f-577c-bea2-c65d895cb2e4 | note | Inspection - ACPL - S
949d91cb-a803-5e82-b2a5-d4896d461bab | note | Inspection - Client - S
467aef50-7f2c-5c20-ab18-6e2f08cfdf6c | note | Verifying Records - Visual Inspection
| section | 4. Construction
| checkpoint | 4.1 - Placement
6fad7cc8-c9c9-58c8-bd6f-6add5fea0c26 | note | Document Reference / Applicable Standard - R63 Cl 4.3, R63 Cl 4.5, R63 Cl 4.6.3
d083e734-2608-5b42-84ba-46a7de08875c | note | Acceptance Criteria - Cover the placed geotextile with either the fill material or a suitable protective sheeting within 48 hours of being placed.
36cb7578-6345-5eec-aad6-4d1509ead62d | note | Unless specified otherwise on the Drawings, the overlap must be 500 mm or greater where large ground deformations are expected.
56dd4538-ec26-5ca4-b4fe-048dd5227931 | note | Provide in your PROJECT QUALITY PLAN how you would ensure that your construction process and compaction method does not damage the geotextile.
d44961bf-bf6b-5b76-8b68-c367d2a4ddb3 | note | The principal may require a site trial to evaluate your construction process and compaction method.
acf16edf-bcde-5d25-a3bf-1466b4c28247 | note | Frequency/ Process Held - Once / Prior to Placement
c669aa01-da42-5a50-9545-5342872e9e9b | note | Inspection - ACPL - S
59c0b88c-df6f-533e-8dff-5111ee00db65 | note | Inspection - Client - S
1af71fcd-160d-5660-8462-91b0456a88fe | note | Verifying Records - Project Quality Plan
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
14906b84-32fa-56f6-b714-3f7011973656 | button | Any non-conformances? | YES, NO
0a9cde31-7e9b-5f37-8f30-eef43369c93f | textbox | No's:
04ad7a39-a3b9-5eb4-8dad-b31d3bcb61ee | button | Closed Out | YES, NO
67988256-8575-534f-ae13-b53b6e140ec7 | button | All work has been satisfactorily completed. | YES, NO
66a6d6b4-758b-54b4-87ef-25dac6d64071 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
2d450207-cf9b-5571-a8f1-defe5efaf9e5 | textbox | Lot Verified By:
eedfd606-35ee-5a69-ab8f-75da02a7dfe2 | textbox | Lot Closed Date:
cc14d160-5851-56ae-8544-ea3c386f52a5 | button | Submitted to Client | Yes, No, N/A
b645ed1c-bd5a-50af-b794-e73faeec83b7 | button | Reviewed by Client | Yes, No, N/A
739107a6-94e3-5bf0-b4de-c49302becce0 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 16 - R116 Heavy Duty Dense Graded Asphalt Rev 1 | itp | ITC 16 - R116 Heavy Duty Dense Graded Asphalt Rev 1 | 8d98456c-b58f-4818-bb66-e744110e34d8
| section | Lot Information
| checkpoint | Lot Information complete
58151fbd-7fb5-5aa7-b0ed-765b82010a91 | textbox | Lot Opened On
05feed24-9147-5627-8d00-ae47593fce21 | textbox | Date of Works
618b7e15-71fc-5d4b-b436-532b0e29b6e4 | textbox | Lot Type
dd1fce17-0c94-5157-bec1-aed3dcbe4e9d | textbox | Start Chainage
bfe38dd1-e30c-5e08-9c14-cdaa4d6f12ce | textbox | End Chainage
3686da31-5141-5c23-ba2a-e118378756f7 | textbox | Offset
ab028a5a-bffd-5070-9105-35fcba104807 | textbox | Control Line
| section | 1. Material Requirements
| checkpoint | 1.1 - Production Trial
7bebe83a-982d-509e-aff8-a17e75506cdb | note | Document Reference / Applicable Standard - R116 Cl 2.3.2
b26d1c53-01b7-5a40-aaf0-3c4e7fa93f51 | note | Acceptance Criteria - As part of your nominated mix design submission process, conduct a production trial to demonstrate conformity of the nominated mix.
86d4987f-54ca-5362-9ad5-44c2f51da0e9 | note | All production trial tests on each nominated mix must be from one trial batch. The tests on the constituent materials must represent the materials used in this trial batch.
15ed9732-b250-56e9-96ce-a3991c3c3dca | note | Frequency/ Process Held - Once / Prior to placement
34e1d85b-d4bf-5201-82a1-c439639d2a93 | note | Inspection - ACPL - S
6d85bcca-63cf-5125-8920-cb60ae23a5d8 | note | Inspection - Client - S
6149ac60-13b9-57ea-b302-12a6ea9c69fa | note | Verifying Records - Conformity Statement
| checkpoint | 1.2 - Nominated Mix Designs
f94fbab6-e34d-55dc-ac9b-92f02bc47faa | note | Document Reference / Applicable Standard - R116 Cl 2.3.5
86257bbd-3add-5c5c-be30-e841b3c8af6a | note | Acceptance Criteria - Submit to the principal documents referenced in Clause 2.3.3 (Nominated Mix Design Submission Details) at least 7 working days before the nominated mixes are proposed to be placed.
a0336f65-2029-5ce6-a7ad-9af1cb174b1f | note | Frequency/ Process Held - Once / Prior to placement
1822f369-97fa-590d-8cd0-3d9c61fb22f7 | note | Inspection - ACPL - H
9b8844f2-aba7-58ab-beed-af0f71b83bcf | note | Inspection - Client - H
7a6ade38-74ff-5d5f-81a5-a5cca8d15acb | note | Verifying Records - Mix Design Submission
| signoff | AUTHORITY HOLDPOINT
| section | 2. Placing Asphalt
| checkpoint | 2.1 - General Placement
fadb8234-8e57-579c-ad96-07d8bcc41b61 | note | Document Reference / Applicable Standard - R116 Cl 3.1
c4884740-814e-5032-9fb8-13fd8c7b09c0 | note | Acceptance Criteria - Provide for traffic in accordance with the requirements of Specification TfNSW G10 when carrying out asphalt paving.
6c65e320-f873-5efa-a20e-3700f91eb11d | note | Prepare the surface to be paved in accordance with AS 2150, including removal of raised extruded thermoplastic road markings and raised pavement markers.
bdd4ab7d-5ced-5afd-87b4-3568c90968a5 | note | Frequency/ Process Held - Once / Prior to placing Asphalt
458af404-ec2a-5bde-a65b-97a96447a3a1 | note | Inspection - ACPL - S
4621fa7b-a914-58e7-8002-e6d5d9698588 | note | Inspection - Client - S
ff4033e3-79c6-525e-bba9-7fab09c3b6be | note | Verifying Records - Visual Inspection
| checkpoint | 2.2 - Application of Tackcoat
5d3ab38d-0df2-5b11-aec6-f2dbc2c0c5d7 | note | Document Reference / Applicable Standard - R116 Cl 3.2
216dff4a-58fc-56e8-84a4-cd52d18faec1 | note | Acceptance Criteria - The existing surface must be clean, dry and free from loose material, prior to application of the tackcoat.
4e50b00d-9b9f-5ed8-adde-18ba8cca6c06 | note | Apply the tackcoat evenly at a rate of between 0.15 and 0.30 litres of residual bitumen per square metre, ensuring that it is effectively bonded to the surface. For joints and chases, double the application rate.
534cfe20-f2a1-5e3b-bbef-2f9558d87bfa | note | Nominate in writing to the principal your proposed tackcoat application rate prior to applying the tackcoat.
7f55dd58-2ebe-5e1a-8daf-ba1d62b21217 | note | Provide to the Principal a signed daily record of the average tackcoat application rate applied to each Lot.
94fb29d9-32bc-530d-b342-1d77413dcdba | note | Report the tackcoat application rate in terms of residual bitumen and state the percentage dilution of the tackcoat used during spraying.
47cbf928-9f3f-5bd2-8cb2-9135773ffde8 | note | Frequency/ Process Held - Once / Prior to applying tackcoat
73dd7bb5-ea83-5d15-80f3-2dd8e8cea98f | note | Inspection - ACPL - S
34bb4549-1496-5587-b824-ee7c62f5c72e | note | Inspection - Client - S
64482e52-b99d-5143-a697-d744db4a65f9 | note | Verifying Records - Application Rate Statement, Daily Records
| checkpoint | 2.3 - Temperature and Weather Conditions for Asphalt Placement
9f3edcb8-c373-5926-83bb-8a71c9bb2f3b | note | Document Reference / Applicable Standard - R116 Cl 3.3
6c21a91a-c57b-5ee1-9671-e660b6918d6f | note | Acceptance Criteria - Measure and record the temperature of the surface to be paved, and wind velocity at the point of asphalt placing.
104181be-fc43-5b76-a454-53a2e8a60baf | note | Do not commence or continue placing asphalt containing binder complying with TfNSW 3253 if the temperature of the surface to be paved over, measured at existing surface level, is less than 8°C where the nominal size of asphalt is less than 20 mm, or less than 5°C where the nominal size of asphalt is 20 mm or greater, for a zero-wind speed.
4ab03781-ede5-5acf-bb59-3d9e958f5868 | note | These minimum temperatures are increased by 5°C for asphalt containing binder complying with TfNSW 3252.
4d0e601f-9b72-5174-8076-913eb95af2f3 | note | These minimum temperatures are increased by a further 5°C for each 5 kph of wind speed above zero; however the minimum temperatures must not exceed 30°C.
3a72c1ba-3f80-5260-b88c-88e23cb9546b | note | Do not place tackcoat and/or asphalt when the surface is wet, and/or when wet weather appears imminent.
7023c452-3cf8-58b8-bb3e-b6046aa9abc8 | note | Frequency/ Process Held - Once / Prior to each asphalt placement
be1a2969-0051-5935-9820-bdcffcff8ac0 | note | Inspection - ACPL - S
c02dbbd0-ceb3-519c-994d-0ab94237d884 | note | Inspection - Client - S
421a0806-f580-5ee6-a15a-4466ce413fba | note | Verifying Records - Visual Inspection
| checkpoint | 2.4 - Paving and Compaction Temperatures
337fedb6-37c4-5bc6-8849-e25f0673b00f | note | Document Reference / Applicable Standard - R116 Cl 3.5
4356e8b3-2cc6-56aa-9037-febdcc836740 | note | Acceptance Criteria - Submit the following details prior to commencement of paving using nominated mixes:
7598b4bd-522e-575a-b267-8d80f3cbf859 | note | (a) minimum temperature at which asphalt will be delivered to the paver;
01b50332-4510-5770-b6c6-8316eadc1018 | note | (b) minimum temperature at which initial compaction of the asphalt can still commence;
b41ff7ee-25c3-5e79-9b36-21f8d34d4240 | note | (c) method of temperature measurement.
bd1880e2-729c-5c7e-bd79-20d08c4d54f2 | note | Frequency/ Process Held - Once / Prior to commencement of paving
fcd69694-9dea-5e27-aa5b-7379da3524b0 | note | Inspection - ACPL - H
8f42e54e-ce1e-566b-b0c1-625f551293c2 | note | Inspection - Client - H
465f5d8b-a510-55f9-b8d2-4b0bfb9dff0b | note | Verifying Records - Paving Temperatures Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Course and Layer Thickness
493d4f42-1aa4-5708-9aca-1d9b6989b14d | note | Document Reference / Applicable Standard - R116 Cl 3.6
9b13f6a7-1f47-524c-b702-267acb07cda4 | note | Acceptance Criteria - Control the course thickness by maintaining the design levels during placing and the surface shape requirements specified in Clause 5.6.
5fd31f59-75e3-5dcb-9fc3-389a0056f878 | note | Where a course comprises more than one layer, and the layer thicknesses have not been specified on the Drawings, nominate the thickness of each layer in your PROJECT QUALITY PLAN.
cbe1f76e-ba0f-5264-be66-8c43062456ad | note | The nominated thickness of a layer of asphalt must be between 3.0 to 5.0 times the nominal mix size.
4a05a308-7d31-5303-9610-f04e03f96e0c | note | Frequency/ Process Held - Once / Prior to commencement of Paving
6134a066-8349-5029-aed4-63da92b62e18 | note | Inspection - ACPL - S
fe280dec-b23a-5397-a981-f81e40cabcc7 | note | Inspection - Client - S
acdc3a95-c515-5868-ae4c-7c93ad413362 | note | Verifying Records - Project Quality Plan
| checkpoint | 2.6 - Nonconforming Layer Thicknesses
c0a57262-75e2-57a9-8288-79953bbdf3ab | note | Document Reference / Applicable Standard - R116 Cl 3.6.3
839853a9-175b-59ba-b9d4-0379a2a7a9f7 | note | Acceptance Criteria - For corrective courses and tie-ins to an existing pavement, you may propose for approval by the Principal to place layers in thicknesses that does not conform to the specified thickness requirements.
08120272-c00e-575a-8695-f2fed732b4f8 | note | Prior to placing asphalt in layer thickness not conforming to specifried layer thicknesses, submit o the principal the following:
4f25d723-1971-5956-92b8-136aa2cd1707 | note | (a) nominated layer thicknesses which does not conform to specified thicknesses;
4f0f5fa2-f10b-50d9-b42c-a2a04f415d56 | note | (b) work methods capable of producing a dense homogeneous layer at these thicknesses;
1616c3bf-d473-5dec-a451-3244de6e5e76 | note | (c) areas affected, and evidence that these areas are the absolute minimum necessary.
7af4a82e-1f77-524c-bd56-d7e531dd35cb | note | Frequency/ Process Held - Once / Continuation of works in Lot
006a5c58-8f00-5e3f-8c0e-abcc81096846 | note | Inspection - ACPL - H
2aa7336a-3623-534c-9c8b-71e88de44d3a | note | Inspection - Client - H
beb18aa7-dc56-5ab9-9632-69da00d4d0a3 | note | Verifying Records - Non-Conformance Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Joints
8582acba-8221-5eb9-827a-878fbb509e42 | note | Document Reference / Applicable Standard - R116 Cl 3.7
e1e46e91-d47b-5581-bbd5-73a0d0ffe468 | note | Acceptance Criteria - Longitudinal joints must be:
d9bfef49-4f69-5908-b506-34772814dd65 | note | (a) offset by 150 mm from the joint in the underlying layers;
0b5b6352-dc7c-504c-abb2-f8732ad11070 | note | (b) located within 150 mm of the line of change in crossfall;
b92b82e5-2c41-58f9-95df-c725aa2de5fb | note | (c) coincident with final traffic markings, unless otherwise approved by the Principal.
f9b43bc4-061e-56b5-abcf-7ca612640564 | note | Transverse joints must be:
8a4ff6ea-5719-5f0b-a790-e7ce7fb6b26c | note | (i) located at a minimum of 25 m apart;
65741bb5-3647-5d3e-a107-b2309c997c97 | note | (ii) offset by a minimum of 1 m from the joint in the underlying layer;
12e88950-ee3a-5888-92d9-6ea459b15f63 | note | (iii) formed at the commencement of each paving run;
ad9183b3-3227-5bd0-837f-902052208ff6 | note | (iv) formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.5.
78a0f6f7-e898-536c-9090-a63ae9597d64 | note | Include in your PROJECT QUALITY PLAN the procedure for the construction of joints including a jointing plan showing widths and include temporary and final lane line configurations.
2b4256ad-6cad-516f-9280-2e453519f8c2 | note | Frequency/ Process Held - Once / Prior to Paving
a0a2a60a-62bc-55ad-9ef9-d71ca5c63343 | note | Inspection - ACPL - S
d429f1ba-2e75-5d1a-9d97-f7650e16524f | note | Inspection - Client - S
89978d78-90b2-50ec-9375-f0f548dc2a3c | note | Verifying Records - Project Quality Plan
| checkpoint | 2.8 - Trial Section
26e014fd-28eb-55f2-8076-bcbc91a92582 | note | Document Reference / Applicable Standard - R116 Cl 3.8
ac2ddbbe-ee12-5ada-90fb-41a393cfe99f | note | Acceptance Criteria - Prior to commencement of paving of the Works, construct a separate trial section using the plant and personnel proposed for the work for each nominated mix.
90eb0e02-fccc-5d72-b499-f98aa80e38bb | note | Each trial section must be located remote from the Works, unless otherwise approved by the Principal. Demonstrate conformity with the Specification in respect of:
f8897990-989d-5ac9-9af7-a52833aa478b | note | (a) homogeneity;
4f06ce7a-13dc-5492-ab87-afe51130831c | note | (b) insitu air voids;
8e8b27f6-a3a4-5e43-9dd7-320d79302c8d | note | (c) course thickness;
6c2e9f16-a017-50c4-b373-551dfe02b49d | note | (d) course position;
58695cb6-27ba-5720-acba-f18012b1cf2b | note | (e) surface shape;
31eab2cf-76eb-5649-a254-8fc7a46c55c0 | note | (f) joint quality, widths and layout;
a3a69d7c-443b-56ad-9880-21f8b0d72eb2 | note | (g) ride quality, where specified.
ff6b36e6-df72-5dd6-9f9f-3437036eec64 | note | Submit to the principal details of:
46fb244f-ce15-5cf7-a1d4-388ba14cbdb4 | note | Verification checklist and all relevant test results from the trial section demonstrating conformity to the specified requirements, at least 3 working days prior to commencing of paving at locations other than trial sections.
c0fcf57c-a095-5245-a53b-925d46e452b9 | note | Frequency/ Process Held - Once / at least 3 working days prior to Commencement of paving at locations other than trial section
c1e6431d-7219-5812-b6bc-1569a103d941 | note | Inspection - ACPL - H
3ea284fc-7046-5067-94ab-06496c39d129 | note | Inspection - Client - H
983bd03f-20b2-5c64-aead-deb8c5854827 | note | Verifying Records - Verification Checklist
| signoff | AUTHORITY HOLDPOINT
| section | 3. Sampling and Testing of Placed Asphalt
| checkpoint | 3.1 - Frequency of sampling and Testing
48834d52-fc45-5af8-ad90-a2d96b2bb7b1 | note | Document Reference / Applicable Standard - R116 Cl 4.1.1
576717fe-9486-5a2a-8f89-0e605160eae0 | note | Acceptance Criteria - Frequency of sampling and testing of placed asphalt must be in accordance with Annexure R116/L.
e6af8c52-9324-5110-a14f-7cb4e76f9998 | note | Frequency/ Process Held - Once / At least 14 working days prior to each placement
c42dec54-f6ad-5a2b-9c1b-e1be13600f80 | note | Inspection - ACPL - H
adbfc418-da7e-56a7-a67b-4b3b78268819 | note | Inspection - Client - H
0139e1ec-8c61-52e3-970d-cce1fcfc8a71 | note | Verifying Records - Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Determination of Bulk Density
5cc5fc77-c483-5e87-96f8-524086164e7b | note | Document Reference / Applicable Standard - R116 Cl 4.2.2
1c5e01fe-1819-56b3-9aa4-7f3fc19dca6d | note | Acceptance Criteria - Do not test asphalt layers less than or equal to 30 mm thickness for insitu air voids. Calculate the characteristic values of insitu air voids in accordance with Annexure R116/K1. Determine Bulk Density by either of the below methods
e612b69f-4faf-5108-8a2f-ef6b916029e6 | note | Cores:
083f85c3-d67d-5769-a7c5-e450d1259519 | note | ○ Take cores in accordance with AS 2891.1.2.
7bad1fea-eed5-5339-b714-ff15759a9c10 | note | ○ When trimming, do not reduce the core layer thickness by more than 5 mm. Determine the bulk density of cores taken in accordance with AS/NZS 2891.9.2.
a445d0b3-d983-5f2c-9d79-a33d532e31e7 | note | Nuclear density gauge:
234d5a3e-fc04-5dc9-b685-66bd4e6e2a57 | note | ○ Take measurements in accordance with AS/NZS 2891.14.2 and AS/NZS 2891.14.3.
9141f8b0-146a-54d9-9256-2bf839d8ddbb | note | ○ Determine the bulk density of cores taken for density offset calculations in accordance with AS/NZS 2891.9.2.
a1e0ff60-0b8d-5f2b-b3b0-c73d3c09c0b8 | note | ○ Determine the density offset separately for every change in nominated mix and specified layer thickness. Verify that the applied density offset is still valid wherever there is a change in site characteristics, such as underlying surface roughness, composition of underlying layer and density of underlying layer.
03d1feb3-4a00-5013-a014-c2cd20f9fb37 | note | ○ Report the density offset on all test reports.
1135d233-d295-50ce-ae37-c1b81610fc79 | note | Frequency/ Process Held - Once / Prior to Lot Closure
0f682214-28f4-57a3-a892-ca67a75c20ab | note | Inspection - ACPL - S
d1e9a010-8150-5492-bfe6-c6d90e71ad4e | note | Inspection - Client - S
7019ff87-72b5-5899-998e-20f6a957b512 | note | Verifying Records - Test Results
| checkpoint | 3.3 - Determination of Course Thickness
8357ada0-3ecd-5d0b-947f-38d7d40b19c6 | note | Document Reference / Applicable Standard - R116 Cl 4.3
97095e93-b9bf-581e-8bd2-b7d934e3724e | note | Acceptance Criteria - From Cores:
04fc6683-46f6-5d51-98c2-ee09cf8b55b0 | note | ○ Determine the characteristic values and average value of thickness of the Lot using statistical techniques as specified in TfNSW Q from cores taken in accordance with AS 2891.1.2.The cores may be the same as those taken for determination of air voids (refer Clause 4.2), but the core layer thickness is determined prior to trimming of the core.
7a58d74a-ff22-5250-b88c-7cfa3a0cfb3f | note | ○ Where the asphalt is placed in one or more layers to form a single course, determine the course thickness by adding the average thickness from cores of the lower and upper layers.
2fe6bc55-996e-5cda-aab1-cc20ba5ad759 | note | ○ For the purpose of determining the course thickness from cores, the core diameter can be less than 95 mm and the test specimen may comprise more than one layer.
d835470a-b22c-5962-b801-2f03d8937e53 | note | ○ Calculate the maximum and minimum characteristic values of thickness for the Lot in accordance with Annexure R116/K2.
64ecd2bf-dd82-5e56-b7d2-8e531b2eac78 | note | By Survey:
43b13434-b9fa-56bb-b30b-cfd55c494121 | note | ○ Carry out surveys for product conformity in accordance with Specification TfNSW G71 Clause 5.3.3.
f0966464-bf4b-5722-a3a6-7410216def0a | note | ○ The average compacted course thickness of each Lot calculated from surveys must be consistent with the average compacted course thickness of the respective Lot determined from cores.
1c86a49a-cb1f-583d-8fc0-09a890a86f25 | note | Frequency/ Process Held - Once / Prior to Lot Closure
0681ed41-637a-54d0-ac5c-e5282c38d601 | note | Inspection - ACPL - S
a6b907d1-67f6-50ff-a6bd-c9c9e8de2b5b | note | Inspection - Client - S
df14c7d9-1b6f-5796-8acb-272200187b03 | note | Verifying Records - Test Results
| checkpoint | 3.4 - Determination of Course Position
0bf215d1-454f-55d2-a9f9-6aa3c90ac831 | note | Document Reference / Applicable Standard - R116 Cl 4.4
a184cb04-0934-5005-916e-feba09cb2aae | note | Acceptance Criteria - Where finished surface levels are not specified, determine the course position of each Lot by reference to existing pavement surface and road fixtures.
700a39fc-fa33-5938-b126-c1047f52cf0b | note | Where finished surface levels are specified, measure the course position of each Lot by survey in accordance with TfNSW Q and TfNSW G71 Clause 5.3.3.
8f679a64-9d05-5a6d-bc2a-098cf5584fde | note | The survey location of any point on the surface of a course for level determination must be located within 25mm from the corresponding point determined from the Drawings.
17f6eb5b-aeef-57ba-9c6d-5f5e994e474d | note | Frequency/ Process Held - Once / Prior to lot closure
49960b71-52be-5eec-8dc1-e623b42284dd | note | Inspection - ACPL - S
873255d1-047d-5682-8497-e6eebcc88d8d | note | Inspection - Client - S
9653810b-0e1c-5228-ad0c-144cfd824433 | note | Verifying Records - Survey Report
| checkpoint | 3.5 - Determination of Surface Shape
95ce8d97-0fb1-518c-9320-4056001997ea | note | Document Reference / Applicable Standard - R116 Cl 4.5
c97a5649-ea78-5692-a30e-108a1a3db1a4 | note | Acceptance Criteria - Determine and report the surface shape in accordance with Test Method TfNSW T183.
644b701a-d288-5751-b0f0-a8c8ccb31cc1 | note | The maximum Lot size must be in accordance with TfNSW Q but extended to include the adjacent longitudinal joints, transverse joints and tie-ins.
1e9c5cee-ad78-58c5-b2d5-a50a851b2439 | note | Prior to placing the next overlying course, determine the surface shape in accordance with Clause 4.5.1. Deal with any conformities in accordance with Clause 5.8.1.
47f64cf6-d855-56dc-ba3f-5502fd777509 | note | Frequency/ Process Held - Once / Prior to lot closure
43f52ec9-90cd-5438-803a-eabf4c6734b5 | note | Inspection - ACPL - S
05914868-8107-57d5-8975-aa54d5ecf8a8 | note | Inspection - Client - S
cb1cdc54-3413-5d26-8333-5c52ae47911a | note | Verifying Records - Shape Report
| checkpoint | 3.6 - Determination of Ride Quality
7937ffff-7ef0-5c47-88bc-c29bc0081a9b | note | Document Reference / Applicable Standard - R116 Cl 4.6
bece53e2-53d7-5e5a-bdca-e6b7a365c6f0 | note | Acceptance Criteria - See subcontractor ITP
550d361e-1703-5293-bbdc-44847cfcd1aa | note | Frequency/ Process Held - Once / Prior to lot Closure
50fd7afa-8ed6-58d1-9cc3-7cd9691f7808 | note | Inspection - ACPL - S
5ec589e7-2ad9-5bf2-833c-8010798007d0 | note | Inspection - Client - S
49dac942-58b5-596d-88bf-0bf5df507765 | note | Verifying Records - ITP
| section | 4. Conformity
| checkpoint | 4.1 - Rectification of Non-Conforming Lots
5af67ffb-4117-5427-804f-9e9af7256c04 | note | Document Reference / Applicable Standard - R116 Cl 5.8.5
d579f85f-e2f0-5172-85ee-b1706623fe35 | note | Acceptance Criteria - Submit to the principle the non-conformity report and details of your proposal to rectify or replace the lot prior to undertaking rectification works or replacement of a non-conforming lot.
a446a072-09d2-5915-b42c-f289c780e77b | note | Frequency/ Process Held - Once / Prior to lot Closure
dad8fdf4-ba98-5a18-81b3-400a17526004 | note | Inspection - ACPL - H
a37d5bb6-63dc-58bf-b0b9-d752ecae5e1a | note | Inspection - Client - H
53d3df70-46f8-53be-a409-f710d8afbaa8 | note | Verifying Records - NCR
| signoff | AUTHORITY HOLDPOINT
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
dd523f95-9aa1-5f05-89cb-0650194a2bab | button | Any non-conformances? | YES, NO
10d0317f-435a-5576-8b67-ad8733af319a | textbox | No's:
65f2f53d-dc45-59d6-b1f4-81bdd9b955f4 | button | Closed Out | YES, NO
c6a9f272-f1cf-5f41-98ca-9dab6d70c7ed | button | All work has been satisfactorily completed. | YES, NO
61d372d9-20f2-50c7-a069-bf8411fa7e28 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
12fb1b85-0bac-50a0-969c-483f673497e2 | textbox | Lot Verified By:
8998076f-bb1e-5214-9372-27a449240af1 | textbox | Lot Closed Date:
92c46646-20e6-592b-8d5f-cf16fcc11312 | button | Submitted to Client | Yes, No, N/A
c5e71ea6-0095-5414-bb31-21184fce5bcf | button | Reviewed by Client | Yes, No, N/A
a4d80a8c-3d60-50a6-992e-9a631303bf84 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITC 18 - R107 Sprayed Bituminous Surfacing (with Polymer Modified Binder) Rev 1 | itp | ITC 18 - R107 Sprayed Bituminous Surfacing (with Polymer Modified Binder) Rev 1 | d6dee04a-6f0c-4f98-ae7f-dd68dc7b078a
| section | Lot Information
| checkpoint | Lot Information complete
f45a146c-b619-5dae-bd4b-d9fb04e9bc91 | textbox | Lot Opened On
7a630fa7-1a09-59bf-b10d-54f66ae89efe | textbox | Date of Works
39949d32-7d4a-5c38-a9ce-fcc55a94c6e4 | textbox | Lot Type
52c00ee7-9388-5d71-9b51-4bce26bb1a7c | textbox | Start Chainage
dee17820-3092-55dc-a219-8a8b9723c566 | textbox | End Chainage
7d1c374d-1375-5882-9abb-1a3cbc8eb25e | textbox | Offset
52c149cd-af95-5059-8428-d1a3512dffc7 | textbox | Control Line
| section | 1. Material Requirements
| checkpoint | 1.1 - Bituminous Materials and Polymer Modified Binder
37775aac-7f47-5f76-94c0-0ac6a24c40d4 | note | Document Reference / Applicable Standard - R107 Cl 2.1
60dd60b3-1771-57b8-b096-e2736f50c12c | note | Acceptance Criteria - Provide documentary evidence of the binder conformity for each delivery used in the work. Also sample at the point of delivery and provide a representative sample of the delivered binder to the Principal.
49ef3ed1-c6d6-514d-89ed-875ba4e35198 | note | The binder for seals and reseals must be in accordance with Annexure R107/A1 and must conform to Specification TfNSW 3252.
b0b3beec-b678-5aa2-93c1-9a5062f4513c | note | Torsional recovery and softening point must also conform to the requirements of Annexure R107/A1.2 at the point of delivery.
fa569575-7b54-5412-999b-fd451a21471f | note | Do not heat binder above 190oC or the manufacturer’s written recommendations, whichever is the lesser.
7bb034ed-6c85-5dd8-9465-b2627d983383 | note | Implement procedures for storage and handling of binder that ensure prevention of segregation and contamination of the binder by flushing liquids or other materials.
8447f3e4-88f9-56d4-ba68-5441b1dd811b | note | Frequency/ Process Held - Once / Prior to supply of Bituminous Materials
7949eaf2-d132-5d4a-b4b1-ec8e2dc7671c | note | Inspection - ACPL - S
efec5b9d-d5e2-5aad-828d-a954c40f6497 | note | Inspection - Client - S
f3e99d1e-57ce-5fa3-809a-e0d40f53776d | note | Verifying Records - Evidence of Conformity
| checkpoint | 1.2 - Aggregate Precoating Agent and Bitumen Adhesion Agent
ed4a6fc3-98d1-5717-8a7b-f2f65633add9 | note | Document Reference / Applicable Standard - R107 Cl 2.2, TfNSW 3268, TfNSW 3269
7f910ae1-d436-5b45-af62-42ea68987e2c | note | Acceptance Criteria - Aggregate precoating agents must conform to Specification TfNSW 3268 for the grade of polymer modified binder specified in Annexure R107/A.
b8eb96f9-52c5-52a9-9697-664d9a2380a1 | note | Bitumen adhesion agents must conform to Specification TfNSW 3269 for the grade of polymer modified binder specified in Annexure R107/A.
342b6ba7-843f-51b3-8ce0-a36e446121c2 | note | Frequency/ Process Held - Once / Prior to supply of aggregate precoating agent and bitumen adhesion agent
d3c6d479-365e-5f09-bca0-7f6f555c0f90 | note | Inspection - ACPL - S
424e91ee-4445-5938-b1a1-d693d8bc546a | note | Inspection - Client - S
afd58037-8098-5352-811f-fcf7160125a6 | note | Verifying Records - Certificate of Conformity
| checkpoint | 1.3 - Aggregate
c918600c-273d-504c-b70c-a584136da3c3 | note | Document Reference / Applicable Standard - R107 Cl 2.4, TfNSW 3151
e09be458-28d0-59e4-a96c-b728732f3c42 | note | Acceptance Criteria - Obtain test results for each Lot of aggregate, in accordance with TfNSW 3151, before aggregate from the Lot is incorporated in the Works.
ceb9d0cd-985d-5baa-aee6-241fb2b2341a | note | When requested, provide a sample to the Principal from the same Lot by riffling or quartering your own samples. The amount of material obtained for each sample must be in accordance with the nominal size of the aggregate as per AS 1141.3.
ccb8e255-0490-5350-9915-f51c9a8a9c67 | note | Frequency/ Process Held - Once / Prior to supply of aggregates
8ab59756-4b03-5cf0-a2f4-36201e5e959a | note | Inspection - ACPL - S
708040ce-81d1-5574-9383-4b5c5456a2fb | note | Inspection - Client - S
5528ea8b-2cd2-5855-977b-1e2faba63df8 | note | Verifying Records - Test Results
| checkpoint | 1.4 - General Materials and Design of Bituminous Surfacing
6259ac39-ec33-5877-9e8c-3282710b3632 | note | Document Reference / Applicable Standard - R107 Cl 3
1f5b41ca-b537-53da-b1b7-e8fde3fb82b3 | note | Acceptance Criteria - Carry out the design of bituminous surfacing in accordance with TfNSW Form 395K as appropriate and submit the design details including all results from texture testing for reseals and ball embedment tests for seals. Design application rates are the "nominated application rates" and materials used for the design are the "nominated materials".
1c804d0a-ce64-5b9a-a8a7-e9a0d65752db | note | Frequency/ Process Held - Once / Prior to placement
8d468bed-9810-57c5-a744-1a6f75d6125e | note | Inspection - ACPL - S
11d2cac4-f23a-5346-8b2c-730a390e798b | note | Inspection - Client - S
312678b1-0c60-5b95-96af-cde96e5e9993 | note | Verifying Records - TfNSW Form 395K
| checkpoint | 1.5 - Submission of Nominated Design
494b78f9-ad5b-58a5-addd-a294c90344bb | note | Document Reference / Applicable Standard - R107 Cl 3.3
15872819-673a-594d-891e-16e721b294fd | note | Acceptance Criteria - Submit to the Principal the nominated design together with certification for the nominated materials at least seven days prior to the commencement of sprayed bituminous surfacing works.
d5eae320-376e-51f6-9449-3a9231664220 | note | Include the following details in the submission:
3697c829-7cfe-57cd-8a43-83df0b72aca9 | note | (a) Each constituent material;
8fec579d-42e3-54c2-bb1a-cdc458c8b30b | note | (b) Verification of conformity of the nominated materials;
56bf2103-aa25-598d-b39d-92780db100e9 | note | (c) Endorsement.
54a6a8c8-e69c-527b-84bb-371b69e3b88f | note | Frequency/ Process Held - Once / Prior to placement
8b089a25-c176-5ff4-a524-dcdaa04d5d26 | note | Inspection - ACPL - S
46c03456-3c28-52c5-8896-fd6ab727c75c | note | Inspection - Client - S
438cb18b-d3dd-527a-8382-e65d52471deb | note | Verifying Records - Design Certificate
| checkpoint | 1.6 - Sealing Operations using Proposed Design
8f2b3761-4877-5baf-abe7-b5713c8b35ea | note | Document Reference / Applicable Standard - R107 cl 3.2.3
e0f5381b-f26c-50ac-b14f-e71516f057e2 | note | Acceptance Criteria - Submit to the principal Documents referred to in Clause 1.2.4 (Project Quality Plan) and the proposed bituminous surfacing design together with certification for the nominated materials and design verification documentation at least seven days prior to the commencement of sprayed bituminous surfacing work.
b024e1c2-f17e-5f3f-8bc0-b7f7c27f7ddc | note | Frequency/ Process Held - Once / 7 working days prior to commencement of sprayed bitumous surfacing work
99f3a063-3b2b-5732-bfd3-905075dbbe90 | note | Inspection - ACPL - H
cd2e3694-b3e8-5a06-bbd9-1266e637e0d8 | note | Inspection - Client - H
6902da02-e8e7-528b-82eb-c961ea7179e3 | note | Verifying Records - Project Quality Plan, Design Verification Documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.7 - Review of Nominated Application Rates
43c068f6-9200-5d0a-940c-cd2a51c676b1 | note | Document Reference / Applicable Standard - R107 Cl 3.3
e8df2ed6-46c8-5108-84b6-46398d546c4d | note | Acceptance Criteria - Submit to the principal the below prior to spray sealing works for each work location: Select the locations where each Lot of aggregate is to be incorporated in the Works.
b27228a6-8d26-5f6c-b032-b963a5400c76 | note | Review the bituminous surfacing design at each location based on the actual ALD test result for the actual aggregate to be used instead of the ALD value of the nominated aggregate and using the appropriate TfNSW 395 design form. The revised application rates are “target application rates”.
8319bbc3-4862-52f5-a1f9-71c7a05632e4 | note | Frequency/ Process Held - Once / Prior to spray sealing works
ecb4b644-e6f3-5412-97de-77f41e63a170 | note | Inspection - ACPL - H
8534523c-cb34-5eec-973e-2248516ee1b6 | note | Inspection - Client - H
4b5b73c7-5752-5522-bfe5-b4a7cc3163a4 | note | Verifying Records - Aggregate Lot Details, Target Application Rates
| signoff | AUTHORITY HOLDPOINT
| section | 2. Process Control
| checkpoint | 2.1 - Application of Sprayed Bituminous Surfacing
40f57940-1109-5a38-8be2-0c80e08948e9 | note | Document Reference / Applicable Standard - R107 Cl 4.2
7237fdcd-2b92-5063-aa91-865f086a2c97 | note | Acceptance Criteria - Carry out sprayed bituminous surfacing so as to:
99a08002-292e-582d-9659-db8695d70327 | note | (a) provide a uniform application of binder with adequate adhesion to the underlying surface;
4aa78b98-3b7b-579c-a407-8ae6f7fea56e | note | (b) provide a uniform cover of aggregate particles (except for primes); and
60c31f84-2266-5bc8-a652-a54e7c7b63f7 | note | (c) achieve effective bond between binder and aggregate (except for primes).
2fefb7bd-2965-5974-8eb6-5dcd1fb96f04 | note | Frequency/ Process Held - Once / Prior to Application
947c7e7c-f336-573a-8205-df183b52c64b | note | Inspection - ACPL - S
8df897c1-dfbc-5d22-95d7-aa1fc4a3f0be | note | Inspection - Client - S
ea9d776b-0f0f-5870-b6b8-362d6da26045 | note | Verifying Records - Project Quality Plan
| checkpoint | 2.2 - Work Records
68569bc8-3dba-54fb-a63b-326aff41a6e3 | note | Document Reference / Applicable Standard - R107 Cl 4.4
311f6776-bbe0-5ab7-a58d-e514275106c3 | note | Acceptance Criteria - Record the particulars of the work performed on TfNSW Form 500E.
cc442be8-cc07-5bae-857b-193cae45bc57 | note | Record details of primer, primerbinder, binder and aggregate applied immediately after every sprayer run. Each form must be signed by your representative as a true record of the work performed. Supply the principal with a copy of each completed form.
f610e9d0-464b-5052-beea-ca5315b0c190 | note | Frequency/ Process Held - Once / Prior to Lot Closure
e01ba982-50b5-5532-8ec1-f31a2eb55f88 | note | Inspection - ACPL - S
4ec99881-c7c3-5146-bdc6-000841abd267 | note | Inspection - Client - S
6ff316a6-f136-5c44-b2f4-eb1781cd68a4 | note | Verifying Records - TfNSW Form 500E
| section | 3. Conditions for Commencement
| checkpoint | 3.1 - Preparation of Pavement Surface
0b7d6272-803a-5b57-8257-08328e8d8d5b | note | Document Reference / Applicable Standard - R107 Cl 5.2
52499ea2-ce6c-54cb-a4f9-8592f300561e | note | Acceptance Criteria - Before the application of primer, primerbinder or binder, sweep the pavement surface using a rotary road broom or suction broom to provide a uniformly clean surface. If necessary, carry out additional sweeping by hand, using stiff bass or similar brooms. Sweeping must extend at least 300 mm beyond each edge of the area to be sprayed.
347ffe79-ed12-5f53-986c-45cb4d9f6d87 | note | Where sealing work is carried out on localised areas and/or half pavement widths, remove any remaining loose material from the pavement surface immediately adjacent to the swept areas.
4641a219-6369-5343-abf2-b489c9886609 | note | Remove adherent patches of foreign material from the surface of the pavement. Mask or remove raised pavement markers.
14f926f2-47d6-5f93-b858-c603f8671527 | note | Measure and record pavement temperatures at regular intervals during work.
65be1219-3534-52ee-bb51-cb9eb152fa5d | note | Place a spirit or mercury-in-glass thermometer or other suitable type of thermometer in direct contact with the pavement.
5c1a3c42-aaaf-53ef-9e88-f73fb253cd0e | note | Undertake spraying of polymer modified binders only if the pavement temperature has been at or above 20oC for at least one hour before commencement of spraying and does not fall below the specified minimum pavement temperature for spraying during the period of spraying.
5a36eeb9-79bc-55ba-aa74-f443e590b182 | note | Do not spray wet pavement or while rain appears imminent or during strong winds or dust storms.
42857df6-182f-59f8-8b53-db02ff9a8a94 | note | Frequency/ Process Held - Once / Prior to application
3054b8e2-d573-5883-a12a-f95c6a087bc9 | note | Inspection - ACPL - S
237a0011-d702-5ae5-9487-19e5042d5343 | note | Inspection - Client - S
95263eaf-8732-5c06-9b4a-2f3fe7268777 | note | Verifying Records - Visual Inspection
| section | 4. Application of Spray Sealing, Binder and Aggregates
| checkpoint | 4.1 - Application of Sprayed Bituminous Surfacing
0633bb0e-7a45-5ff4-9854-4dcd7c0c01cc | note | Document Reference / Applicable Standard - R107 Cl 6
6e1f0dde-f277-5362-993b-c29ab2fedd5e | note | Acceptance Criteria - Apply the binder by using a sprayer. The sprayer must have a current Sprayer Certificate (TfNSW Form 354) issued or accepted by Transport for NSW.
41281ee1-c681-5118-bbf2-d97c1075d079 | note | Measure and record the temperature of the polymer modified binder using a thermometer or other suitable means, accurate to within 2.5% over the range 100-240C. If the temperature of the binder is below the minimum temperature recommended by the manufacturer of the polymer modified binder, the binder may be heated providing safe heating practices are adopted. Do not use burners unless the level of the material in the heating tank is at least 250 mm above the tops of the heating tubes.
a93983a6-4f9c-56f1-915b-59685d79e7e1 | note | Where bitumen adhesion agent, cutter oil or flux oil is to be included, add it to the polymer modified binder in the sprayer and circulate the mixture at a rate of at least 700 litres per minute for fifteen minutes before spraying.
81cbd651-0fef-5e01-9b81-1b3312b330e5 | note | Frequency/ Process Held - Once / Prior to Application of Spray Seal
15020425-4fc8-55fd-b834-0a17d45aedf2 | note | Inspection - ACPL - S
4e72733e-a438-5007-86d2-208e6eaa1729 | note | Inspection - Client - S
efd5c344-d347-59bd-923b-e10a2563d287 | note | Verifying Records - TfNSW Form 354
| checkpoint | 4.2 - Application of Polymer Modified Binder
be251dd0-3a6c-557c-abfa-a4b93bff3cb5 | note | Document Reference / Applicable Standard - R107 Cl 7
52c33928-0319-5768-b6b6-ca105455e251 | note | Acceptance Criteria - Limit the area to be sprayed to the area that can be covered with aggregate at the target application rate and rolled initially within five minutes of spraying polymer modified binder.
fdecc71c-67a5-5cdc-bcf7-16b43eb17f94 | note | Do not spray polymer modified binder over a prime until at least 48 hours after spraying the primer or such longer period as required for the primer to become completely dry.
3af204d8-bd82-5515-b0d5-6967d9828963 | note | Do not spray polymer modified binder over a primerseal until at least twelve months after spraying the primerbinder unless the hardness of the primerseal measured using Test Method TfNSW T271 is less than 2.5 mm.
0381bb85-50db-5410-bca9-2e24bdc23508 | note | The type of polymer modified binder must be as specified in Annexure R107/A1.
8b2004ee-37cb-5bde-a2f2-b122116a7734 | note | Base nominated and target application rates and quantities of polymer modified binder on the volumes of polymer modified binder measured at a temperature of 15C and do not include any bitumen adhesion agent or added oils.
fd1d8e5c-cfe2-58a9-80a9-8e73a8bbc981 | note | Where bitumen adhesion agent and/or cutter oil has been added to the polymer modified binder, adjust the application rate of the total binder at 15C to allow for the quantity of additives in the mixture.
db492b30-fea8-5caa-8467-9eb4a3f46f6d | note | Determine the hot application rate of total polymer modified binder, including bitumen adhesion agent and cutter oil, using the appropriate multiplier from TfNSW Form 500E.
57205603-190c-5252-a9bf-e67b055b8147 | note | Frequency/ Process Held - Once / Prior to application of Polymer Modified Binder
466a692a-fd12-517f-932b-66dd8e5b20fc | note | Inspection - ACPL - S
a2c8fe4e-3aee-5c34-a0f0-843f79baa132 | note | Inspection - Client - S
82ec39e7-6524-51ac-9ccd-b508fb2fd0bd | note | Verifying Records - TfNSW Form 500E
| checkpoint | 4.3 - Application and Incorporation of Aggregate
2ec25a97-80d7-563e-9f2d-fc77e3612c93 | note | Document Reference / Applicable Standard - R107 Cl 8
f77971b4-ff11-5aa4-b01b-f7967ae34722 | note | Acceptance Criteria - Use only precoated aggregate.
6f729013-83a2-5f6f-8bc3-475c0b8b28e1 | note | The application of aggregate must proceed after spraying is commenced and must be completed and rolled initially within five minutes of spraying the binder.
61b9031c-0789-5ed0-a75a-6afd81c1cafd | note | Apply the aggregate of the specified nominal size and at the target aggregate application rate.
ebf8828e-7d59-5a15-a451-cd4b69ba2011 | note | The method to determine the actual aggregate spread rate must conform to Test Method TfNSW T274 or a method approved by the principal and detailed in the PROJECT QUALITY PLAN.
c6385585-52c7-569c-96ae-23e5a5bda5ce | note | Report the aggregate spread rate as actual rate using TfNSW Form 500E.
84ec1e58-ef5b-5bcc-a023-1f1b1926c72b | note | After the aggregate has been applied to each section of the work, carry out initial rolling with two or more dual axle smooth pneumatic tyred multi-wheel rollers of mass greater than 7 tonnes without ballast and minimum tyre pressure of 550 kPa. Continue initial rolling until the aggregate is firmly embedded in the binder
aab49355-c39b-5aba-ba37-3e48675323b9 | note | Roll the cover aggregate with pneumatic tyred multi-wheel rollers at not less than eight passes within one hour of spraying at every point on the surface.
d63a0684-552c-5845-8ddc-afe9bc819406 | note | Frequency/ Process Held - Once / Prior to incorporation of aggregate
1fad886a-a17d-5cbc-a11a-d2e889141aac | note | Inspection - ACPL - S
34376474-e188-5401-b60c-47750c031765 | note | Inspection - Client - S
02cb0cc8-86b9-5e6c-861e-dfc0c5e0740a | note | Verifying Records - TfNSW Form 500E Project Quality Plan
| checkpoint | 4.4 - Sweeping and Loose Aggregate Removal (10mm and 14mm Seals / Reseals Only)
198fbe12-a3a4-5883-b98e-61fda483926e | note | Document Reference / Applicable Standard - R107 Cl 9
329f2bcd-db0f-5e3a-8b0b-82d246dc3ba9 | note | Acceptance Criteria - After final sweeping and prior to the work being opened to traffic at the pre-existing signposted speed, the number of loose aggregate particles (per m2) not including aggregate particles from any scatter coat, determined in accordance with Test Method TfNSW T277 must not exceed the values shown in Table R107.1:
0ae6b531-767d-58c2-9252-c327bc71dc24 | note | Areas where speed limits exceed 60 km/h and that are opened to traffic prior to final sweeping must have temporary speed zone ‘loose stones’ and ‘slippery’ warning signs and temporary 60 km/h speed zoning in place until the maximum allowable loose aggregate requirement is met.
bdf098f7-4c2f-5565-a513-4cb7f472065d | note | Notify the principle of the time and location prior to commencement of final sweeping and loose aggregate measurements prior to opening to traffic.
bf824dbe-fe66-5e3c-a277-26f93ae6c8f7 | note | Frequency/ Process Held - Once / Prior to Lot Closure
ba52da50-8339-52d7-bbfc-8cf0a8c3a829 | note | Inspection - ACPL - W
4a0bdc69-ee23-50cd-8258-54acf0a31779 | note | Inspection - Client - W
813ab4ef-966f-5ab2-b12a-f6a310b385e4 | note | Verifying Records - Visual Inspection
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
caa845d9-bed6-51ad-88d6-c77c8f54d5b1 | button | Any non-conformances? | YES, NO
84fdd74b-0cea-5034-bb9e-5d79417ad645 | textbox | No's:
37ec7590-8f4f-5d3f-bea4-9326151905b9 | button | Closed Out | YES, NO
2361b927-7676-5c88-867d-45121adad22e | button | All work has been satisfactorily completed. | YES, NO
59639929-e56b-58fc-b6b9-dc5d3d9ed98f | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
5d105fc2-05fc-5a97-9893-44394b4d7049 | textbox | Lot Verified By:
c39ff767-1f25-59c5-8160-2ed4fb7f086a | textbox | Lot Closed Date:
848ace3f-7ec1-5026-8dfc-7fe0360e7881 | button | Submitted to Client | Yes, No, N/A
7ab6c00a-2158-51a0-9f73-632baa60ef42 | button | Reviewed by Client | Yes, No, N/A
01381e3d-704d-53b7-a576-9c8fb3b4845a | textbox | Submission Comments:
| section-nested-checklists | NCR
581354bf-84ad-40cf-b958-fa449b3bd346 | checklist | ITC 19 - R54 General Concrete Paving Rev 1 | itp | ITC 19 - R54 General Concrete Paving Rev 1 | 5faff2d5-9c14-4e8f-a0a8-7e4b76e96d3e
6df0b33c-6cc5-437e-b2ff-762b701f2bb2 | section | Lot Information
eb9b12d5-9fc6-412c-9371-d2be8bd72641 | checkpoint | Lot Information complete
0fac6174-312b-5021-a09c-1adf4e766611 | textbox | Lot Opened On
d4d4b93c-cf60-51fb-a8a5-151746e942db | textbox | Date of Works
cbb91b60-066c-5776-96de-a521a510f51e | textbox | Lot Type
acf861ff-a5fc-5bc2-a905-a85a2545175f | textbox | Start Chainage
935f7c99-88b7-5348-8daa-44bb015d7a7a | textbox | End Chainage
bbde4778-05c8-5870-bcef-003a65a3bb03 | textbox | Offset
7ff66574-d812-5f71-b502-b3b8fb2ea299 | textbox | Control Line
c9f2c3c1-73bd-4b1e-9eeb-bc10668838a8 | section | 1. Material Compliance
ea3a9559-9d4b-460e-814e-044dbb33e680 | checkpoint | 1.1 - Select Fill Type U
fed8e70c-5a8f-5ece-bd3c-3e2a045be8cd | note | Document Reference / Applicable Standard - R54 Cl 2.1.1
69655b7f-9331-5d3f-9004-540b06f05d4b | note | Acceptance Criteria - Select Fill Type U must consist of a granular material with a particle size grading of 100% passing the 26.5 mm sieve and a Plasticity Index, determined by Test Method TfNSW T109, of between 2 and 12.
60d0c586-6c96-52fd-80fd-307c67b88fe1 | note | Frequency/ Process Held - Once / prior to placement
e9a8b5dc-4067-5e3d-a546-0c75cd44be54 | note | Inspection - ACPL - S
e1b22449-8cee-5d45-99e6-e09037128f43 | note | Inspection - Client - S
8d635c9c-c5fa-53d6-8d68-b7afd1601c2d | note | Verifying Records - Material Test Report
834a9db2-ad5d-48bd-958d-c91a6e466d84 | checkpoint | 1.2 - Class 2 DGB
ed1fb451-9115-5225-a0f4-9c62e247243f | note | Document Reference / Applicable Standard - R54 Cl 2.1.2
658e8a1e-bb66-52f0-9a3e-b7df5204699c | note | Acceptance Criteria - Class 2 DGB must comply with Specification TfNSW 3051
55051fee-b431-5b42-89c4-59471a36f5f3 | note | Frequency/ Process Held - Once / prior to placement
df999c55-4096-50fc-b90c-7df45525d8db | note | Inspection - ACPL - S
bd468711-b826-592c-9516-d7565544b0cb | note | Inspection - Client - S
2e819b98-639b-5e9d-a413-35bfb26e4c4e | note | Verifying Records - Conformance Certificate
c29dee13-c2da-4740-b8c4-23f98c90ee32 | checkpoint | 1.3 - Concrete and Steel Reinforcement
28912708-29e9-5087-b602-e8431385dc98 | note | Document Reference / Applicable Standard - R54 Cl 2.2
2e76ad53-8004-5868-8a76-5f5b924eaa80 | note | Acceptance Criteria - Supply of concrete and steel reinforcement to comply with TfNSW R53
e88ed518-3650-558e-b040-24348ab45147 | note | Frequency/ Process Held - Once / prior to placement
d39635a3-2800-5374-85d0-96eacf4ea59c | note | Inspection - ACPL - S
131393ad-999a-5dc6-b467-5dd1504f6624 | note | Inspection - Client - S
60fc4216-ac4d-5e1b-8fbf-23847ab22d29 | note | Verifying Records - ITP-04
232ef374-d6f2-40d5-bb3e-5f312c396fca | section | 2. Earthworks and Subbase
602e746e-d34c-413f-b54a-2d6441dfc289 | checkpoint | 2.1 - Excavation and Filling
88cb3bf4-d228-50d1-b0d2-7da19d9e2f28 | note | Document Reference / Applicable Standard - R54 Cl 3.1
33578d90-f508-55d1-8f35-079942774481 | note | Acceptance Criteria - Excavate or fill in accordance with TfNSW R44
a7cf0294-e8c8-5004-a061-2b56d5544748 | note | Top up low areas to required levels using Select Fill Type U
de2dc3a9-0830-5e46-9013-f57ec275e9b4 | note | Unless shown otherwise on the drawings, fill the space at the sides of paving or behind kerbs with Select Fill Type U
34ed6f99-a1f5-5c19-8f42-55a48d4329d7 | note | Frequency/ Process Held - Once / At least 2 working days prior to each placement
21de4881-ffe3-59d4-8701-cdff41cc530d | note | Inspection - ACPL - S
c44e37d0-ef9f-5056-9c54-ef0116972b95 | note | Inspection - Client - S
8d9f2f11-91f7-57dc-b74c-ff01bc653397 | note | Verifying Records - ITP06
c9754217-93b1-469a-8de4-ffb06ee62811 | checkpoint | 2.2 - Granular Subbase
d0e919ee-6575-51db-a666-4f9cdc74170e | note | Document Reference / Applicable Standard - R54 Cl 3.3
e4175885-30db-54eb-898a-c50afd94a33a | note | Acceptance Criteria - Unless shown otherwise on the Drawings, construct a subbase layer comprising Class 2 DGB beneath the concrete paving as follows:
594d94ed-deb9-5892-a8d0-538e0eecba01 | note | (a) Footpath: 75mm thick;
52f569d0-cd20-5182-b46c-8179cb5ee5fd | note | (b) Bicycle path/shared path: 150 mm thick.
23cf0d30-3d71-57cb-ac7e-f4a0509c22de | note | Frequency/ Process Held - Once / prior to compaction
68694c2d-426f-5d76-ac0e-2e0fadb9c6de | note | Inspection - ACPL - S
e24c8f30-8bef-590a-8cde-1fcb02fa98f6 | note | Inspection - Client - S
98d7a61a-dd2c-535c-b297-9b1b1f67346f | note | Verifying Records - Survey Report
098cd653-aad3-452e-98f7-6d6c3ee166fb | checkpoint | 2.3 - Compaction
b6e5dd2d-ed17-5ed8-ba34-461f84828ed5 | note | Document Reference / Applicable Standard - R54 Cl 3.4
3bc8725a-7d8e-54e7-a796-62f81946651d | note | Acceptance Criteria - Compact the subbase, foundation, etc to achieve the minimum characteristic value of relative compaction specified in Table R54.1.
93e4fb7c-ca22-5e62-b29b-73dfe04f250a | note | For driveways, comply with the relevant Council’s requirements, unless specified otherwise in the contract documents.
760a0958-56ef-54ee-967c-3bbfd9b33246 | note | Frequency/ Process Held - Once / prior to conformance survey
9f641852-d9e7-5423-9bc8-894632c1899b | note | Inspection - ACPL - S
d4e8c77d-b25b-545a-a30e-b4dc6db6c4f1 | note | Inspection - Client - S
d2be5283-d21a-59dc-bd74-fd02de61511d | note | Verifying Records - Compaction Results
6a6172d9-52d0-42c4-b639-74a477342070 | checkpoint | 2.4 - Levels
a2c19085-ade1-51e7-a388-12c620a87dff | note | Document Reference / Applicable Standard - R54 Cl 3.5
ef32081d-54fe-5d88-bb0c-3ce846775ddd | note | Acceptance Criteria - Construct the top of foundation to the design surface levels, with a tolerance of +5 mm and -10 mm.
a9b341a9-5c1b-522b-9135-e07069995283 | note | The finish surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 10 mm, except at grade changes.
8a632c83-6355-50ea-995a-2cd3034390cf | note | Frequency/ Process Held - Once / prior to paving
9fd2d1c1-1411-5a52-b073-2252eac2b0a7 | note | Inspection - ACPL - S
81b10f56-96fc-5716-b512-4dd9eb4287d8 | note | Inspection - Client - S
2bdaeeee-4a52-538e-a128-7581e9a02210 | note | Verifying Records - Survey Report
5a91bc90-4615-4018-8594-9cfaf17fc56e | section | 3. Concrete Paving
ed8e945f-874f-4835-ba96-4a4460ac2675 | checkpoint | 3.1 - Joints
32c45b2c-3359-5c36-bd3c-89cec76cb5c9 | note | Document Reference / Applicable Standard - R54 Cl 4.4.2
3164c82d-70e3-5950-988e-e0fd805b8040 | note | Acceptance Criteria - If not shown on the Drawings, submit a drawing showing the proposed joint layout, and including reinforcement details, particularly for odd shaped and mismatched slabs.
1a679850-b856-576b-ba7a-490922dbeeda | note | Transverse joints must be constructed at right angles 6 to the longitudinal edge of the paving slab, otherwise the slab will be treated as odd shaped slabs.
54ed8154-1302-5fad-8a2a-8bd9a240307f | note | For details on joint requirements, see clause 4.4.3.
d4ad1013-e65e-56e6-a6de-b130ba0cdcb7 | note | Frequency/ Process Held - Once / Prior to steel fixing
7c2dfb30-9ce0-5a2c-8cb6-75e484b9b5d8 | note | Inspection - ACPL - H
3d8ff476-e8db-5ff0-a7e4-4d986b346b61 | note | Inspection - Client - H
eb6963b7-b8f2-519b-af28-9c7dcf8a4063 | note | Verifying Records - Proposed joint location and reinforcement drawing
a29a1b0b-cf8c-44b6-991b-8792da2af8bd | signoff | AUTHORITY HOLDPOINT
b293eaac-67a7-4920-972c-07a5c162cc96 | checkpoint | 3.2 - Patterned Concrete Paving
97a85608-b4e8-56bb-885d-045c80fed744 | note | Document Reference / Applicable Standard - R54 Cl 5.2.1
f87ebd9d-132e-5d44-9390-8d16af8d47d9 | note | Acceptance Criteria - Submit to the principal details of pattern, colour, class of finish and experience of personnel in producing patterns on concrete paving.
f3ffaccc-aa4b-5ddc-880a-ac4523897d58 | note | Unless shown otherwise on the drawings, provide surface finish as per Table R54.3. The finished paving surface must be uniform in colour and appearance.
d63e728a-6b97-5260-8490-6ba88d8b2ab3 | note | All edges, except for those abutting other paving or structures, must be neatly rounded to a radius of 10 mm. Edges abutting other paving or structures must be neatly rounded to 5 mm radius.
2d1ebe6b-ab06-5e80-9414-ed933d856c04 | note | Frequency/ Process Held - Once / Prior to concrete placement
ab09cadf-8c76-52be-9106-71b1156bf00f | note | Inspection - ACPL - H
dd564b6d-20d5-5aca-8846-4542f0aeffa4 | note | Inspection - Client - H
3c1d55ef-9a89-57cd-910e-68b0826ef71b | note | Verifying Records - Patterned Paving Plan
4df4ef58-ee18-4038-aff2-fe88d91573cb | signoff | AUTHORITY HOLDPOINT
c4f5d68d-41aa-48e2-92cf-d2a63928d649 | checkpoint | 3.3 - Steel Reinforcement
5655c338-c661-5dfa-a13b-90feeac6a687 | note | Document Reference / Applicable Standard - R54 Cl 4.2
27718867-1de9-51b2-b6ad-6736aa84b0e2 | note | Acceptance Criteria - Provide steel reinforcement for concrete paving slabs as shown on the drawings
76879e95-bdb5-5033-be41-a20b596e68bd | note | Provide a minimum cover for the steel reinforcement in accordance with TfNSW R53, unless shown otherwise in the Drawings.
2a874c66-6534-5740-99e5-079179aaaa64 | note | For slab of thickness 120 mm and greater, fix the steel mesh within the top half of the slab.
3c8d5cd4-a0bf-56d1-8257-15e245776262 | note | For slabs of thickness less than 120 mm, fix the steel mesh at the mid-depth of the slab. In this case, the minimum cover specified in TfNSW R53 does not apply.
b2d5d2aa-4409-5146-bc0f-f2377bce7feb | note | Frequency/ Process Held - Prior to Placement
a706afbf-38f9-53a6-8723-99245b71b73b | note | Inspection - ACPL - S
11cfa6ec-3d00-5c7e-a8c9-66b0bfab0f83 | note | Inspection - Client - S
6f9e068f-75a3-5743-aec8-4545547637c9 | note | Verifying Records - Pre-Pour Inspection
ea217f81-e086-4599-833f-244f1e3571a9 | checkpoint | 3.4 - Concrete Placing
1b93b144-eba0-5f63-9728-b8b43722bec5 | note | Document Reference / Applicable Standard - R54 Cl 4.3
eed5ac71-5d9c-5243-a1d5-0d05e887f064 | note | Acceptance Criteria - Comply with Clause 3.3 of TfNSW R53
4d772af4-7b09-55aa-9048-56002981a84d | note | Hold Point in TfNSW R53 for placing of concrete applies
f3f220d8-6ff4-5098-814b-2fa589070f9f | note | Frequency/ Process Held - Once / Prior to Lot Closure
a9452888-b6b2-5028-9490-e6d1bb4519d2 | note | Inspection - ACPL - S
66369a5e-7fbb-53d2-a25c-0669a3942113 | note | Inspection - Client - S
b57a7902-3673-5de3-acb2-ced144ad2086 | note | Verifying Records - ITP04
c76d42c2-e33f-4f84-aea1-2325e2a886e8 | section | 4. Finished Paving Surface
cdcefd72-d3d6-47cb-98df-029a4b1525c1 | checkpoint | 4.1 - Patterned Concrete Paving Procedure
87b1f88f-740d-50aa-a35a-849973d130b5 | note | Document Reference / Applicable Standard - R54 Cl 5.2.2
e28c0869-5d35-5852-a62a-67e5789f5781 | note | Acceptance Criteria - When constructing patterned concrete paving, apply the stencil only after the bleed water has evaporated from the concrete surface.
aef14f70-d2b5-58a9-89e9-e0b32c60069c | note | Apply each coat of colour hardener at a consistent rate achieve a total thickness of between 3 mm and 4 mm.
4f0dfd57-506d-5731-821e-5532c77e6377 | note | On removal of the stencil, the surface must exhibit a well-defined pattern with no edge ravelling.
0d36a425-b1d6-558e-8bb8-ccc4641e466c | note | Apply a suitable sealer to the finished surface within 24 hours of forming the pattern, followed by a second coat of sealer 3 days later
efcc04bd-1c53-5ac0-8eee-753f06c28574 | note | Frequency/ Process Held - Once / Prior to Survey
eb5ec723-421a-5cc1-b3d0-cfc347434f2a | note | Inspection - ACPL - S
6d3c5c37-27a6-564c-88be-91b98a083318 | note | Inspection - Client - S
5a4875c9-e3fa-5819-8288-d241e84f5e99 | note | Verifying Records - This ITP
5dbd8a61-6bfb-4cce-8fe4-0ab4cf558413 | checkpoint | 4.2 - Finished Surface Level
a48a0262-8307-5177-930c-ae5b3801f7d9 | note | Document Reference / Applicable Standard - R54 Cl 5.3
62fdeef7-ffa6-5cdb-a660-50297d4969b5 | note | Acceptance Criteria - Construct the finished surface of the concrete paving to the design surface levels, with a tolerance of +10 mm and – 5 mm.
18c528ab-9f75-580c-9f1c-39b71aa667da | note | The finish surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 5 mm, except at grade changes.
c460df1f-1970-5302-b45a-da1c38cd79fc | note | Where the concrete paving abuts an adjacent structure, any vertical step across the joint must not exceed 5 mm unless shown otherwise on the Drawings.
5dfeb015-e929-50dc-9cc2-fe8f83127867 | note | Frequency/ Process Held - Once / Prior to placement tactile indicators or lot closure
b8a04675-a205-5e9d-95b6-44265f95e202 | note | Inspection - ACPL - S
0c3129f6-4f54-5ef4-a5c2-233ee64d4bc7 | note | Inspection - Client - S
bd925c9d-178d-5ad7-a431-0f4c0dc6bee2 | note | Verifying Records - Survey Report
e2e51b66-9de3-4bc6-9965-e528dbd794bd | checkpoint | 4.3 - Tactile Indicators
9db09263-c377-5df2-81a5-7f520f38265a | note | Document Reference / Applicable Standard - R54 Cl 6
d25c80ac-9aa8-560d-b2aa-1e9459cb3a3f | note | Acceptance Criteria - Submit to the principal details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method prior to placement.
9ccc2e9d-4013-515b-a0aa-5f4d046c57d6 | note | Install tactile indicators at the locations shown on the Drawings.
950f9f14-72de-576a-b6a1-18e792c2cc36 | note | Prior to installing the tiles, allow the concrete to cure for the duration specified in TfNSW R53, or a duration recommended by the tile adhesive manufacturer to suit the adhesive used.
34663e07-58fb-5388-9e95-eabac673bc60 | note | Prior to placing tiles, clean the concrete slab of dust using water jets, and any contamination using where necessary high pressure hydro-blasting, sand/grit blasting or mechanical scabbling.
48b649d6-6717-5d7f-a4b8-d78a6fb49e4b | note | Install the tiles such that they are fully bedded, without any voids beneath the tiles.
afea8552-dacc-503c-a06a-bc6e09a8a708 | note | Install the tiles at the tile manufacturer’s recommended spacing. Pack the spaces between tiles with grout, and free of all voids and pits. Remove any excess grout, grout film or haze.
0739504a-b4d9-5e66-991d-87c8ec0c1318 | note | Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer
69867709-8967-5beb-b5b7-229f788867d7 | note | Frequency/ Process Held - Once / prior to placement of tactile indicators
72fd6114-5fb9-5dce-98f8-58113e4719c4 | note | Inspection - ACPL - H
83b4fd88-2f6d-57a1-9a58-b42be9b7774f | note | Inspection - Client - H
24488a78-54ad-5c66-8834-142dfdbaca1e | note | Verifying Records - Tactile Indicators Proposal
eef0f049-97c3-455a-81db-a1d73ea4bb3d | signoff | AUTHORITY HOLDPOINT
7687b972-67df-4b31-8c43-85047e3f847c | section | Review by Project Manager
c858ef95-de9b-43a6-87d8-ad3526230356 | checkpoint-no-value | Review by Project Manager
f4b99177-6247-5dba-9a0d-888a6b9e530b | button | Any non-conformances? | YES, NO
6f79aa1c-250b-546d-b0c5-543c67f4fa19 | textbox | No's:
d42c0cd0-f3c3-59d8-95c3-34560ca13a94 | button | Closed Out | YES, NO
79dcab6a-29f5-5c05-819a-f7433be068ee | button | All work has been satisfactorily completed. | YES, NO
11df10d5-6d90-53d0-b0a8-a547d46a7fd5 | textbox | Name:
c26221ae-f5a9-406c-bfad-8191f28d6310 | signoff | Add signature
7284cd28-8fce-4c18-8900-97be3c4eb4e2 | section | Lot Verification
d377e3ce-f877-465a-8bf4-4db98e37eefa | checkpoint | Lot Verification complete
4eadd0c4-7c8b-5f06-a3bd-2d71a0bf517a | textbox | Lot Verified By:
cf89bbea-60c3-58ba-a2b1-4bb2b341e5ae | textbox | Lot Closed Date:
81800459-a315-539b-bce5-5c4fd45e904c | button | Submitted to Client | Yes, No, N/A
32928bac-b760-5d5f-abec-0e61ff206516 | button | Reviewed by Client | Yes, No, N/A
6a395734-9350-5db6-97f9-6c4de169d9f8 | textbox | Submission Comments:
71eb48c4-dda3-44e1-8f8f-6419fb853061 | section-nested-checklists | NCR
3d50c609-cb42-424d-affc-d6bd563a9b32 | checklist | ITC 20 - R106 Sprayed bituminous surfacing (with cutback bitumen) Rev 0 | itp | ITC 20 - R106 Sprayed bituminous surfacing (with cutback bitumen) Rev 0 | 35312472-5c26-4534-be09-26e7fbde53b7
f3b018c2-c082-4cad-9809-d4bcecb6d6eb | section | Lot Information
63cf54eb-8317-48d9-ba76-58388c9c4011 | checkpoint | Lot Information complete
9b4ecb32-0cc1-5750-8956-81b9764688b8 | textbox | Lot Opened On
52a0521a-dfe1-5d0a-a627-4554c10436e6 | textbox | Date of Works
0c88a51d-7b4e-563c-b713-5a68b86e4f4e | textbox | Lot Type
2e0c7d75-723a-5e07-8ec6-69a6000409c5 | textbox | Start Chainage
b48e6e8e-8365-591c-be7c-047d91958c05 | textbox | End Chainage
ef7f646a-2255-5467-9ce2-673a2edae88c | textbox | Offset
0985e413-7366-5154-98da-8c6753039cff | textbox | Control Line
a721e10d-13d0-4b82-b0c1-aa019748704c | section | 1 - Safety Review
6a64b374-75de-4997-aa7f-1e0dcba3d148 | checkpoint | VERIFICATION
7f65335b-bb21-56f5-8f07-e16d33a07a4d | note | REQUIREMENTS / REFERENCE - Project Safety Plan
e22446c7-239e-5562-9619-7b123ab40fc2 | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural)
acc3d7a7-b7a4-521c-bdc6-775bc6f4ad24 | note | Required Safe Work Method Statements completed and signed
cd51b183-7b4c-50a4-af57-3623d73909dc | note | Subcontractor’s safety plan/procedure approved
fe8017d6-08c0-56ed-98f7-ebdb8e610ecc | note | FREQUENCY - Prior to commencing works
eddb810f-c9f5-43fc-a12f-35bdff26c4d7 | section | 2 - Environment
f1947156-6726-43ac-854a-c34eb1dfbd60 | checkpoint | VERIFICATION
ce26dae8-1efb-5a8b-b506-82bc0254c27e | note | REQUIREMENTS / REFERENCE - Project Environment Plan G36 G38 R44 cl 1.7
c55ba4b8-ac54-5836-9728-e6353dc6bc71 | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
f2b6167b-6a9d-5fe3-98f6-e1432917731b | note | Air quality to be visually monitored for dust etc. as a direct result of construction activities.
a61de296-a070-55b4-98be-aa7f046c557d | note | FREQUENCY - Prior to commencing works
97df96ee-e797-44a5-a91e-2d334d6fb334 | section | 3 - Submission of nominated design
aadec942-c557-4a6b-ba8d-211cd6e9a4ca | checkpoint | VERIFICATION
7ed60961-2b8f-592e-b4d7-c09a8a614034 | note | REQUIREMENTS / REFERENCE - R106 Cl 3.3
b7482550-575f-56fc-bcce-81373d872cc8 | note | ACCEPTANCE CRITERIA - Submit to the Principal the nominated design together with certification for the nominated materials at least seven days prior to the commencement of sprayed bituminous surfacing works.
6b0adf2c-0172-5034-ba41-0f1650beffc4 | note | Include the following details in the submission:
29dc9ef8-3e84-557e-bf17-1a6138a326bf | note | (a) Each constituent material;
d997fed0-c6bc-5bac-84e4-02426315aa4d | note | (b) Verification of conformity of the nominated materials;
1cc17d2b-bfb7-53f5-b664-309818f5652d | note | (c) Endorsement.
6090f174-cc27-5da7-8f22-7fc5d281619b | note | FREQUENCY - 7 days prior to the commencement of sprayed bituminous surfacing works
6f1c10bc-fd4b-5cd4-984c-7c5db5b88e93 | note | Comments / Attachments / Records - Submit nominated design for materials
4ec8d85f-363a-45bf-b941-676660645fa5 | section | 4 - Endorsement
6457c7f5-201d-4527-b78d-1c8ef764c48b | checkpoint | HOLD POINT
a80715ca-2902-5e7b-abb5-a6669cf0aa52 | note | REQUIREMENTS / REFERENCE - R106 Cl 3.3.3
f44b6b66-1172-5efb-a362-6abac6be6537 | note | ACCEPTANCE CRITERIA -  Submit a statement signed by you stating that each design and its constituent materials meet the requirements of Clauses 2 and 3. The statement must include NATA endorsed test results for all specified tests. Attach a copy of your completed verification checklist.
8a6d25a6-f150-5242-9a8d-81c2bcb3df6a | note | Submit documents referred to in clause 1.2.4 and the proposed bituminous surfacing design together with the certification for the nominated materials and design verification documentation at least seven days prior to the commencement of sprayed bituminous surfacing work.
ee2049f6-971c-561e-ac7e-1889cad99682 | note | FREQUENCY - 7 days prior to the commencement of sprayed bituminous surfacing work
50bc79fa-2998-519d-95fa-366ce44c7083 | note | Comments / Attachments / Records - Hold Point
b705605c-f1a9-5fe0-9365-4d6693f107b4 | textbox | HOLD POINT NUMBER:
925d8f7e-79cf-5c10-ae99-7aecad14fa94 | textbox | DATE SUBMITTED:
3cb7b989-0105-5b9c-a8d8-a72eaeb5c505 | textbox | Work Start Date:
e97afd29-8713-50bf-b8ce-c033b6647482 | textbox | SUBMITTED BY:
8cda4b3f-0a81-5a90-ba84-cdc2e768329e | textbox | SPECIFICATION AND CLAUSE:
8eb3dae7-a442-5f80-a93e-fc1ca36b76a7 | textbox | HOLD POINT DESCRIPTION:
8416036c-5e14-5632-ada3-11a18dcb9637 | textbox | BRIEF NOTES:
fbdfde9f-961b-4f60-a9b0-5617fbc7e36b | signoff | HOLD POINT SIGN OFF
185fdc31-be02-4737-81be-382085c8d195 | section | 5 - Review of nominated application rates
a075173c-a3d1-4729-a32d-c7ab4921cc6c | checkpoint | HOLD POINT
ed1b408e-6a34-5570-8a69-f167a56cf563 | note | REQUIREMENTS / REFERENCE - R106 Cl 3.4
d558c857-5038-5169-b1b7-4c6597561eec | note | ACCEPTANCE CRITERIA - Select the locations where each Lot of aggregate is to be incorporated in the Works.
81c078e2-09cb-5ab8-b728-c50afa8db106 | note | Review the bituminous surfacing design at each location based on the actual ALD test result for the actual aggregate to be used instead of the ALD value of the nominated aggregate and using the appropriate RMS 395 design form. The revised application rates are “target application rates”.
3caefe1e-87c8-56c6-bde9-89261701b4cf | note | Prior to sprayed sealing work for each work location, submit aggregate lot details and target application rates.
3670d490-99b2-57fe-a4c1-ec178afad365 | note | FREQUENCY - Prior to sprayed sealing work for each work location
29161781-0307-5b26-907b-41f4b59ebc74 | note | Comments / Attachments / Records - Hold Point
22581063-614c-5047-892f-4a8f86d68446 | textbox | HOLD POINT NUMBER:
9515c3fe-23ec-5d1a-87f9-fdbcd000c083 | textbox | DATE SUBMITTED:
66b93c35-06c6-54f8-8540-92d62ebbbf11 | textbox | Work Start Date:
15d68227-f75a-5176-a35e-3545f7e886ef | textbox | SUBMITTED BY:
9b25d496-e388-5725-8a3a-8d5baef79601 | textbox | SPECIFICATION AND CLAUSE:
4501840a-1f3f-53f2-a824-53a6882e04df | textbox | HOLD POINT DESCRIPTION:
ca766f4f-2f34-51ec-be93-80f14d9e3be7 | textbox | BRIEF NOTES:
08bb47f7-1e73-44dc-a733-5788b915ecdc | signoff | HOLD POINT SIGN OFF
acbd9679-b78c-4059-94a5-16a83042b672 | section | 6 - Work records
1f0dd7a5-623a-4b0a-a5ea-e0905237793d | checkpoint | VERIFICATION
0a90f6b6-8db9-5eae-8c6a-ff23d8343841 | note | REQUIREMENTS / REFERENCE - R106 Cl 4.4
a138fedc-a346-55e7-9fd1-f8605455f157 | note | ACCEPTANCE CRITERIA - Record the particulars of the work performed on RMS Form 500A or 500C (as appropriate). Record details of primer, primer binder, binder and aggregate applied immediately after every sprayer run. Each form must be signed by your representative as a true record of the work performed. Supply the Principal with a copy of each completed form.
9c1dcff1-e554-50da-b5cf-018d788b9b47 | note | FREQUENCY - During undertaking of works
fb7da6e6-27e2-46a1-8724-29b892a6946e | section | 7 - Sweeping and loose aggregate removal
aa615220-f365-4f6d-b83c-f6290d617ab8 | checkpoint | WITNESS POINT
da1084ee-fe0c-539b-9333-3c9e8fb5eb1a | note | REQUIREMENTS / REFERENCE - R106 Cl 9
3c397e16-e1aa-5bda-885a-9cfac9c5f60a | note | ACCEPTANCE CRITERIA -  After final sweeping and prior to the work being opened to traffic at the pre-existing signposted speed, the number of loose aggregate particles (per m 2) not including aggregate particles from any scatter coat, determined in accordance with Test Method RMS T277 must not exceed the values shown in Annexure R106/A. The test location must be representative of the section and as agreed by the Principal. Include the reporting system to be used to record test results of loose aggregate after final brooming in the PROJECT QUALITY PLAN. If values are not specified in Annexure R106/A, the values shown in Table R106.5 apply.
44545b4c-f5b9-5df1-b60b-88fce9e26bb7 | note | Areas where speed limits exceed 60 km/h and that are opened to traffic prior to final sweeping must have temporary speed zone ‘loose stones’ and ‘slippery’ warning signs and temporary 60 km/h speed zoning in place until the maximum allowable loose aggregate requirement is met.
a2298644-3742-5035-99f6-45b5563371e9 | note | The following witness point will apply:
0a1b7518-9288-589c-a22f-026f8e1163e4 | note | ○ Prior to final sweeping and loose aggregate measurement prior to opening traffic, submit notification of the time and location prior to commencement
17b69a71-d155-55ef-a28d-e46f623ff5e1 | note | FREQUENCY - Prior to commencement of final sweeping and loose aggregate measurement
459de217-26a1-530b-a801-2eb3a71ef452 | note | Comments / Attachments / Records - Witness Point
31e94180-01a0-501c-a7e4-e651a8520415 | textbox | WITNESS POINT NUMBER:
6d119892-b421-537b-b5fd-910988914e89 | textbox | DATE SUBMITTED:
6f8d9f34-a01c-5c2c-909a-95b6d6028bac | textbox | Work Start Date:
82293fbe-c855-5616-99f6-c88789c53f30 | textbox | SUBMITTED BY:
e020e930-0fb4-56fb-9103-7f8f28b5ea99 | textbox | SPECIFICATION AND CLAUSE:
f4932be2-0645-566a-bfa1-c95e55811bfd | textbox | WITNESS POINT DESCRIPTION:
88783ddd-9d05-5695-a301-d61d7e89c846 | textbox | BRIEF NOTES:
421373d3-c828-40bc-bd6f-2aa96609a23f | signoff | WITNESS POINT SIGN OFF
a85f8291-6ef5-4d07-b00a-93c129a3e57d | section | Review by Project Manager
efb52b94-67fa-4651-88f3-8a8cdb776890 | checkpoint-no-value | Review by Project Manager
97d862b2-0817-55d9-ad6b-00b14fe1f73d | button | Any non-conformances? | YES, NO
11ecebd2-639b-5a4f-b6fd-f715d71a4a04 | textbox | No's:
dc57278d-c8cd-5a87-9576-54dca3104930 | button | Closed Out | YES, NO
53d5393f-eac9-5a03-91ed-49676e3c9038 | button | All work has been satisfactorily completed. | YES, NO
d1e5a41a-fe95-5cb2-ae0b-610ab9265247 | textbox | Name:
753a2b77-a8cd-430f-9168-38aada2d6dab | signoff | Add signature
8d55514c-ea61-4601-a8fd-a17e6a370a90 | section | Lot Verification
51353e50-7621-4ae0-b05d-02251c3b1704 | checkpoint | Lot Verification complete
85cbb62e-2aac-5c9c-97fb-ee946edd7622 | textbox | Lot Verified By:
502d3880-2ee3-5209-8315-0fe36d516f40 | textbox | Lot Closed Date:
3ce43e96-6a98-5608-a6f6-99f066408be8 | button | Submitted to Client | Yes, No, N/A
eb2af5a6-39fc-5f67-b696-eb9f80dfc7e5 | button | Reviewed by Client | Yes, No, N/A
fd3d0649-8500-5908-9843-283d87b0c58f | textbox | Submission Comments:
0d06a8ee-2a8c-43ad-a2e2-1b2d07b921dd | section-nested-checklists | NCR
| checklist | ITC-B5.7 - Checklist - Parapet Installation Span 7 |  | ITC-B5.7 - Checklist - Parapet Installation Span 7 | 4e3e7182-94fa-4b04-bbfe-9065bf050aa8
| section | Lot Information
| checkpoint | Lot Information complete
d80a4a9f-9311-4511-ad5c-0fdbc3d2f1d2 | textbox | Lot Opened On
0ad3dd18-e959-49b2-a7c7-2d8d2b21b21e | textbox | Date of Works
375e3ba5-4497-424d-9ba7-38b2f690c2c1 | textbox | Lot Type
4b0984d7-bf5d-4f9d-979e-487488188eee | textbox | Start Chainage
a35eae1d-37dd-5ad8-89a8-773b84770d32 | textbox | End Chainage
e26700a6-0ef1-575e-906f-79a6bd76205a | textbox | Offset
dbe31814-b1ed-59e3-825f-f974e6eeadca | textbox | Control Line
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | 1 - Installation of Cover Plate
12575728-2a69-54ff-a50f-283da99b0b6e | note | Requirements / Reference - BR-DRG-1078 RFI258
53c64eaf-65f6-52d4-a796-6485b8aeed84 | note | Acceptance Criteria - Verify correct cover plate type at correct location Place cover plate as per details on BR-DRG-1078 – 1080 Concrete inserts and countersunk screws placed as per RFI258
f698d47e-5b49-560e-97c5-1c0d00816c09 | note | Inspection - S
dca344c1-5040-552d-91dc-e1d2a2f821c8 | note | Comments / Attachments / Records - Checklist
| checkpoint | 2 - Installation of Cover Plate Ferrules
a548758d-da19-5bc9-adb6-efedf94906a5 | note | Requirements / Reference - RFI258
84a8cc49-107a-5264-8d36-d992f8b87172 | note | Acceptance Criteria - Cover plate ferrules to be installed at nominated locations as per the approved methodology (see RFI258).
70affa0e-bc1b-513f-a25e-d94d5cd6983a | note | Inspection - S
e15a5fee-1898-537a-a8af-87480f69949b | note | Comments / Attachments / Records - Checklist / Redline Markup
| checkpoint | 3 - Grouting of Lifting Points
d0c260ec-94d9-570a-a988-f7a3279f0140 | note | Requirements / Reference - N/A
d5a185f8-90da-56bf-8104-c9acbfc7ec3a | note | Acceptance Criteria - Visible lifting points at top of parapets to be grouted using Sika 212-HP grout
9a46ab30-2db8-5059-9646-18d8f0cd9ac7 | note | Inspection - S
efa5dd46-cd00-5855-98d3-5f8d76a2690c | note | Comments / Attachments / Records - Checklist / Grout Cube Results
| checkpoint | 4 - Installation of Junction Box Cover Plate
178a7e78-3e12-59d1-a9cd-1dd62765671d | note | Requirements / Reference - BR-DRG-1112 RFI-258
096075c6-4958-5736-b5c7-023468611d5e | note | Acceptance Criteria - Junction box cover plate to be installed as per BR-DRG-1112 and RFI258
45cecade-abc8-5778-939d-1b938aa1f82f | note | Inspection - S
2aee1482-fc12-58e7-83c3-66b0e0ebf844 | note | Comments / Attachments / Records - Checklist
| checkpoint | 5 - Installation of Expansion Joint Conduit Connection
305c0149-a524-5108-a0fa-b2e258666938 | note | Requirements / Reference - BR-DRG-1076
3770a80e-4a00-57bb-bc19-c3a377f13751 | note | Acceptance Criteria - Install as per details on BR-DRG-1076
1d61c9fb-043e-53e9-bb9a-743fa0f72fab | note | Inspection - S
0149345f-622c-506e-a398-9c4bc2dd7a68 | note | Comments / Attachments / Records - Checklist
| checkpoint | 6 - Installation of Signpost Brackets
1de43f42-8e27-5ec8-bfd3-e9a462910939 | note | Requirements / Reference - BR-DRG-1128
a1457572-a1e3-5c4a-a232-e1e57562bcf7 | note | Acceptance Criteria - Install signpost barrier where required as per BR-DRG-1128
9f398c10-c435-52eb-9aa8-86d93c4008c5 | note | Inspection - S
eb16dfd1-b7aa-5325-a747-1440962b0723 | note | Comments / Attachments / Records - Checklist
| checkpoint | 7 - Installation of Name Plate
9757e931-a827-5d69-b983-27d9aa332d96 | note | Requirements / Reference - BR-DRG-1128 B345
db77e43f-30ae-5d79-b7e8-b93a4f38e931 | note | Acceptance Criteria - Install name plate at location nominated on BR-DRG-1128 Name plate designed and installed as per DRG B0701 and B345
f1ad184c-d03e-58c8-8310-f9f7b3add984 | note | Inspection - S
0602da59-424b-5709-986a-48abe2b2f77c | note | Comments / Attachments / Records - Checklist
| checkpoint | 8 - Installation of Details at Joints
f8f06e26-5bf6-5b6d-b569-fe807d209d6e | note | Requirements / Reference - BR-DRG-1075
c06c1326-2e03-5c24-b029-e16e1ef6e8b2 | note | Acceptance Criteria - Install joint details as per below images taken from BR-DRG-1075.
f2090d95-584b-5420-9c98-4818dee133ce | note | Inspection - S
9cc47929-b0c4-55a4-9bda-2c8c769c4e8a | note | Comments / Attachments / Records - Checklist
| checkpoint | 9 - Cathodic Protection Steel Conduit (Pier 9 only)
ba6d1ad0-56fc-5772-9a19-8f3ddb6d8ce9 | note | Requirements / Reference - BR-DRG-1073
e4e79abb-895d-5c2c-a34b-214afbf65447 | note | Acceptance Criteria - Cathodic protection steel conduit placed on tail of parapets as per BR-DRG-1073
ea378209-b45d-5321-be5e-7f21a3962711 | note | Inspection - S
96fcb456-2096-5ee9-b607-d36e2a490fcc | note | Comments / Attachments / Records - Checklist
| section | Review
| checkpoint-no-value | Review
8fbf105f-e83a-52be-91b2-c8b20f829d72 | button | Any non-conformances? | YES, NO
614ac924-2f49-5874-810f-589428c0efa2 | textbox | No's:
e24edeff-0fd2-5af6-a06e-5746dbe12862 | button | Closed Out | YES, NO
cf400029-12c5-5539-90cc-7e673a6ad4ce | button | All work has been satisfactorily completed. | YES, NO
ce4e9967-0166-5270-a93a-7aa433e42f5d | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
508489d7-642a-56ae-a271-4f80f40499fb | textbox | Lot Verified By:
db952155-e98f-5f17-94ee-a8ef284f92e2 | textbox | Lot Closed Date:
2084db1e-6f73-52c5-a4e6-bdb5ccb008df | button | Submitted to Client | Yes, No, N/A
a00696b7-18af-59e4-baf4-1bafa1eff4cb | button | Reviewed by Client | Yes, No, N/A
b59fee4b-071c-5413-a5ef-52c93a583a08 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP - B2.P - FRP Preliminary Works |  | ITP-B2.P - FRP Preliminary Works | 06bbe528-cb60-472a-95d1-04cf93846520
| section | Lot Information
| checkpoint | Lot Information complete
6a2ea530-be68-5d4a-be6a-fa0445ce5988 | textbox | Lot Opened On
5dea5668-1532-5548-8c3a-1b016fd09800 | textbox | Date of Works
8be95151-1d30-5008-8ccb-15aa946e1f84 | textbox | Lot Type
e411d844-b56e-5f7e-870f-a4e0624a726e | textbox | Start Chainage
ecb4a0a2-049e-5277-92e7-88eabfd30703 | textbox | End Chainage
1aba0ee3-64e7-5349-9c71-5e3446f1c35f | textbox | Offset
4979f1b2-5a2b-55fb-84fa-8e05de1fb51c | textbox | Control Line
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | 1.1 - Safety Review
3536eff4-3ec1-5998-98d6-4d81e456c43f | note | Requirements / Reference - Project Safety Plan
12c3e88a-201b-5c82-855f-4dd5be5821a0 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved.
082e63c4-682d-5c64-a4e7-82c6a43c6b7f | note | Frequency / Process Held - Before Commencement of Works
cb80168a-2815-5942-8444-2e4007323442 | note | Inspection - ACPL - W
3a5e4639-ba1a-5adb-af73-a8336e46d17c | note | Inspection - Client - S
70801ef0-44c9-5c62-8a31-283f1bbf4883 | note | Comments / Attachments / Records - Signed SWMS
| checkpoint | 1.2 - Environment
693559c7-d308-51ff-9af3-903cb933bf65 | note | Requirements / Reference - Project Environment Plan
c1afbc19-ee71-50d7-81df-6e219326a623 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc as a direct result of construction activities.
90baa8a0-2efe-5117-b7a9-125b8d20215a | note | Frequency / Process Held - Before Commencement of Works
35db1184-add6-52a6-9c22-564ff14e2133 | note | Inspection - ACPL - W
328a41cc-2d55-571f-9629-89a25a0fca0e | note | Inspection - Client - S
d902bdca-2620-5be8-a143-2c789158d900 | note | Comments / Attachments / Records - SECP AQMP
| checkpoint | 1.3 - Submission of Nominated Mix Design
bd0327b6-3089-5685-9c4f-27a60e14449e | note | Requirements / Reference - B80 Cl 3.9.1
c83ae007-63b9-5895-8cca-ff22fe8bc320 | note | Acceptance Criteria - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
0e9c0651-f414-5246-b536-9d11729faeb2 | note | Frequency / Process Held - Prior to ordering concrete to site
bb7a1a0b-3a1e-54b9-aeb8-1183ead726db | note | Inspection - ACPL - H
82e31620-6583-5a26-997f-51e44a61ebcf | note | Inspection - Client - H
081e46b5-0847-5b87-93e5-7126b896a6a2 | note | Comments / Attachments / Records - Mix Design Submissions - HP107 - HP109 - HP128 - HP132 - HP134
| checkpoint | 1.4 - Concreting Personnel
00cbdf54-2db6-5d33-80db-402f67aa7fcb | note | Requirements / Reference - B80 Cl 7.2.3
2b88e2cb-b174-565d-8f9d-8ce6ce77be71 | note | Acceptance Criteria - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
06ee9ac7-8f74-5283-9b75-ac6b50d4816e | note | Frequency / Process Held - Prior to first concrete pour
422b8325-1fc8-5c59-bb04-c0994ad5a86b | note | Inspection - ACPL - H
20d634b2-a500-514d-8ee1-bf539b26c876 | note | Inspection - Client - H
1b6fcdc6-c22c-5aa6-b3a3-b88759941282 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards - HP135 - HP136 - HP137 - HP199 - HP243
| checkpoint | 1.5 - Test Members
5308b72f-c8cf-56de-8085-85ece879f284 | note | Requirements / Reference - B80 Cl 5.3
e3d819d7-2f86-519f-ba05-f5254ac5c3f2 | note | Acceptance Criteria - Provide notice in writing to the Principal, at least 2 working days, of the upcoming placement of concrete for the test member(s) In the event the test member does not meet the design, reassess the process with the Client and pursue alternatives if necessary
d85f1f1f-62f3-5ff6-906f-0bf5027fd1cb | note | Frequency / Process Held - Prior to commencing concreting for permanent works
646db002-6a6e-5e17-bb93-4a41563a5701 | note | Inspection - ACPL - W
191f2772-9345-5852-b47b-28b1d3035322 | note | Inspection - Client - W
39567e9a-a075-55f0-867c-ae5109807f39 | note | Comments / Attachments / Records - WP009
| checkpoint | 1.6 - Fabrication of Reinforcement
23f16b2e-e9b2-5587-8801-2da8278cdf65 | note | Requirements / Reference - B80 Cl 6
5a723a49-2141-52d0-8495-8fee95852133 | note | Acceptance Criteria - Steel reinforcement must be certified by the ACRS for conformity of the reinforcement production and processing to the requirements of AS/NZS 4671 Chairs and Spacers must comply with AS/NZS 2425. The smallest chair or spacer dimensions must not be less than the specified cover, and the largest dimension must not exceed 1.8 times the cover. Fabrication tolerances must be as shown in Table B80.14
b66ee103-400a-5ed3-b161-3d23b99436ae | note | Frequency / Process Held - Once / Prior to FRP
4c6bf45d-0ae5-5c2d-8716-98956d136003 | note | Inspection - ACPL - S
04adc8f7-c291-5df6-ab1f-ee3a5e4890ae | note | Inspection - Client - S
13901ed5-ac26-57a0-b9be-4c14e5eb341b | note | Comments / Attachments / Records - Product Certificates
| checkpoint | 1.7 - Welding Operations
98de0567-bf26-50b5-8c78-ef6d4e2cb15c | note | Requirements / Reference - B203 Cl 4
fec5ae76-6437-5436-bcef-43041f0eda03 | note | Acceptance Criteria - Prior to the commencement of welding of steel reinforcement for the Works, submit the following: (a)welding personnel names, roles, qualifications and experience; (b)welding procedure specifications (WPS) for the required welding; (c)welding procedure qualification records (PQR or WPQR) for the applicable WPS; (d)proof of conformity of proposed welding consumables to this Specification.
15e981af-1170-54a7-a492-e0d85b1bf8a5 | note | Frequency / Process Held - Once / 5 days prior to welding operations
64c02ee5-e4be-56d3-8924-ad7b6aaaddf2 | note | Inspection - ACPL - H
10df8a7d-e135-5f3e-9bbf-8762d7a1fd4f | note | Inspection - Client - H
6328c448-2be2-5d86-8747-a15f68949a54 | note | Comments / Attachments / Records - Welding Qualifications WPS/WPQR - HP047 - HP173 - HP180 - HP181 Welding Consumables
| section | Lot Verification
| checkpoint | Lot Verification complete
bf6d635f-f77a-589d-a86a-c568ed05fc2c | textbox | Lot Verified By:
59f99640-91a1-51bd-ba7c-547ad306f6cf | textbox | Lot Closed Date:
bd7a630d-0985-577c-b284-5808b42e6036 | button | Submitted to Client | Yes, No, N/A
4ce3dbf0-1c1d-5d95-bee1-b0e8dd89890a | button | Reviewed by Client | Yes, No, N/A
d14f8c2d-8dae-5301-9e05-eed154087bef | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP - FRP |  | ITP-FRP | dbec5ba6-9445-48a4-91f0-cebd35234b63
| section | Lot Information
| checkpoint | Lot Information complete
a4bedfa9-8150-5f2c-91b4-60b88eb5e878 | textbox | Lot Opened On
d0369a30-821b-5bd7-bc74-ee8483d871e2 | textbox | Date of Works
40dd6f18-5d67-5106-9e61-3aa8f7a30e1b | textbox | Lot Type
016dfaf0-3c23-513b-9387-a9dbc6daa18b | textbox | Start Chainage
82644ca4-26d2-5d1c-b17f-77877be570e7 | textbox | End Chainage
de161d57-376b-512f-8d9f-e69f0d9110c4 | textbox | Offset
bae088c4-96ce-5847-855d-4700666e7008 | textbox | Control Line
| section | Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
1c15e89b-48b7-505f-8bc0-c224fdd360b1 | note | Requirements / Reference - Preliminary Works (FRP) ITP
8037473c-ed68-5b07-a89b-5e1a332b79a8 | note | Acceptance Criteria - Sign-off of ITP-B2.P FRP Preliminary Works ITP
752865ee-1589-52d5-926a-2c483beac188 | note | Frequency / Process Held - Once / Prior to Construction
c2e1a22b-2b93-5ed8-8c02-54d20e9e52d7 | note | Inspection - ACPL - H
2c9690d2-7aee-5262-97d5-dc7555385321 | note | Inspection - Client - H
75678bf1-90b9-51ea-b746-578851625007 | note | Comments / Attachments / Records - ITP-B2.P
| section | Construction - 2.1 Pile Cap
| checkpoint | 2.1.1 - Survey Set out
cafb6966-a225-50e9-a02c-05143c3ba44a | note | Requirements / Reference - B80 Cl 5.8
f86f137e-eb15-511c-b2da-43acfdcf7baf | note | Acceptance Criteria - Survey set out as per design drawings
3d4b5b72-ed15-5291-8624-7e3e843671e7 | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
51483bbd-1ec8-583b-a9e2-91a975176aba | note | Inspection - ACPL - S
87ebe4bc-9efe-5ab3-8aab-da8b8c7fad07 | note | Inspection - Client - S
d95e3222-5421-5ce5-b2a7-d654b04b8358 | note | Comments / Attachments / Records - Set out Report
| checkpoint | 2.1.2 - Formwork Certification
9a0f38f3-addd-5af9-9f9a-5b5861d6c65e | note | Requirements / Reference - B80 Cl 5.2.3
5ddb8e56-0b86-52e8-a860-9cd5ec93eee5 | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member. Locate construction joints at the base of piers at least 100mm above the top of the pilecap.
85fa0b93-a3c2-5b9c-a496-1fe221704bcb | note | Frequency / Process Held - Prior to constructing formwork
52ccb853-13c0-5dcc-b380-e3ba6125739b | note | Inspection - ACPL - H
76184d63-b794-51bf-b1e2-63aefa76594c | note | Inspection - Client - H
5f36b57e-4797-5f73-8fbd-0b7cd6e343ec | note | Comments / Attachments / Records - Formwork Documentation/Design Certification - HP115
| checkpoint | 2.1.3 - Installation of Thermocouples
8ce1bc5f-1bfb-5d73-bd08-b5f25ca4647e | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1023
64a68daa-9d39-5d6e-b616-75f637bdaddb | note | Acceptance Criteria - Thermocouples must be located within the pile-cap to monitor the maximum temperature and differential temperature across the concrete. The location, frequency of testing, methodology and precautions must be submitted to the principle prior to the concrete pour. Thermocouples to be installed at: - Mid Length at Centre - -50mm from the outer surface
79794d98-7fa0-5cc2-8e62-88ad721a5fbd | note | Frequency / Process Held - Once / Prior to concreting
7d322f8f-e9f9-5586-abd0-c8acf2a81495 | note | Inspection - ACPL - S
dfe60ce6-2e14-5bae-b334-b008913c9f38 | note | Inspection - Client - S
407278bd-509e-598b-b9b6-d280bc626fe7 | note | Comments / Attachments / Records - Thermocouple Data Sheet
| checkpoint | 2.1.4 - Certificate of Conformity
d764b624-2fa1-5de4-8fc2-df0278aa6648 | note | Requirements / Reference - B80 Cl 7.5.2
744391b6-e3ef-5636-8e47-8e51152e3265 | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working hours prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s)
23ee732e-0ffe-5254-bccd-e5ecc77e5b9c | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
a218d8bf-fa44-5648-8d40-7273902c1a19 | note | Inspection - ACPL - H
b5f324f3-1611-5daa-8b47-5969a83fc9f4 | note | Inspection - Client - H
f3b277a4-c2b3-5e89-8fba-2874fcc3d023 | note | Comments / Attachments / Records - Method Statement - HP186
| checkpoint | 2.1.5 - Certification of Steel Fixing Prior to Concreting
b7ae53fa-e618-5bd8-9884-2f78d1469eb4 | note | Requirements / Reference - B80 Cl 7.5.2
4e1b8c3e-0cb8-5236-8f25-8edcf9750703 | note | Acceptance Criteria - Splice reinforcement only at locations shown on the drawings. All welding must conform to specification TfNSW B203 and the bar manufacturers recommendations. Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: 45mm unless otherwise specified Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
6188b179-69f1-5fbf-92e5-fc9760de5acb | note | Frequency / Process Held - Once / prior to placement of concrete
aa9fd712-98d9-5fd7-bec5-585a59d2fca3 | note | Inspection - ACPL - H
5215965e-9c7d-5af3-bb67-d699d30f8751 | note | Inspection - Client - H
f37a668c-929e-53c8-8660-e2630d2ceb10 | note | Comments / Attachments / Records - Pre Pour Checklist
| checkpoint | 2.1.6 - Certification of Formwork prior to Concreting
c29d02f7-d613-5e19-9d1c-42aa688554e5 | note | Requirements / Reference - B80 Cl 5
8c1ffad7-5b86-52ee-b118-a9aeeac1bf5b | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
7ebfd21e-96ac-5d09-b1fc-fcf60ce18db0 | note | Frequency / Process Held - Once / prior to placement of concrete
f3c206ae-2f82-5cc8-8a17-6272c48372ab | note | Inspection - ACPL - H
2ee5a4b5-db7b-551e-bc01-71cab5889acc | note | Inspection - Client - H
fc07c007-f5af-503d-9405-b6eab7402a74 | note | Comments / Attachments / Records - Pre Pour Checklist
| checkpoint | 2.1.7 - Electrical Continuity Testing
7e43ac3d-9c0a-57e8-9e37-e8239b73508e | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1017
8237cf56-24d2-5253-ac46-a372528468b2 | note | Acceptance Criteria - Electrical continuity must be established for all reinforcement. Following the electrical continuity methodology, <2Ω must be achieved.
e489de1c-fcdc-5152-afe3-f8f4d7eb77db | note | Frequency / Process Held - Once / prior to placement of concrete
8d3d3029-a649-551e-abd7-57943f4ec061 | note | Inspection - ACPL - S
fc0321cc-8532-5c53-a4a0-a08563f90bb2 | note | Inspection - Client - S
a5c7c2ec-c8e8-59c7-89ee-428b4001dcc9 | note | Comments / Attachments / Records - Continuity Report
| checkpoint | 2.1.8 - Concreting Personnel
89b351d5-59c3-5a97-8033-c55e1fc5941b | note | Requirements / Reference - B80 Cl 7.2.3
5abfdecd-41ba-5936-909c-4e44b45d8198 | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
0939dea8-5e18-5717-914e-9d9101fd90ff | note | Frequency / Process Held - Once / four hours prior to concrete pour
a93fc626-ab44-5149-b6d9-58939b57ce75 | note | Inspection - ACPL - H
772524d1-c730-5371-8ada-03151f08d7b3 | note | Inspection - Client - H
b093a429-0301-5df4-a6c0-3f780f25082b | note | Comments / Attachments / Records - Concreting Personnel Grey Cards - HP137 RFI-031 - Email to TfNSW
| checkpoint | 2.1.9 - Supply and Delivery of Concrete
9c593b21-4c78-5855-a9ad-ab5507b04b3a | note | Requirements / Reference - B80 Cl 4.1
795a9c88-14df-5a01-ba3a-952c5ccdb45f | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
5459776b-9fe9-51ae-adf0-5f58bbbff6fe | note | Frequency / Process Held - During concrete delivery
7e07117a-5d2f-5643-a446-a5db3483f57c | note | Inspection - ACPL - S
4a6856fe-494e-5eb6-99b6-0d7c3c38923d | note | Inspection - Client - S
88fafc48-0dda-55a7-bcbb-a3170ce1c787 | note | Comments / Attachments / Records - Concrete Docket Concrete Pour Record
| checkpoint | 2.1.10 - Concrete Sampling
ce6e5a92-4d6d-5f7c-a07c-507ed0b5ff46 | note | Requirements / Reference - B80 Annexure B80/L
55ee957d-3dbb-5307-aff6-3a8b109e7550 | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
c9830605-1b4d-53f3-b3a9-734d8adf46db | note | Frequency / Process Held - Each element / prior to placement
06c9dde3-a68e-586a-a687-43be4a74391d | note | Inspection - ACPL - S
231763b6-4b37-51d6-a0cd-f196141618c1 | note | Inspection - Client - S
91e6d8ca-2741-5b07-8991-d847a57a5102 | note | Comments / Attachments / Records - Concrete Sample Report Test Results - 7 days - 28 days
| checkpoint | 2.1.11 - Concrete Placement
ce392d0e-38ee-51dd-9d0b-473f926f1547 | note | Requirements / Reference - B80 Cl 7
46c80710-51cd-5627-ad2d-2ac7c1c737fd | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32CAmbient temperature 5-35C 40MPa Concrete Concrete placed in pile cap to be carried out in once continuous operation Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
25b8b7a4-c528-5fab-8a6f-50a82b9d45b7 | note | Frequency / Process Held - Once / prior to Curing
8c952f36-87c5-5e5a-90c9-968534eafdf0 | note | Inspection - ACPL - S
accd893b-3103-513c-8b4d-22ade1c7e859 | note | Inspection - Client - S
97f2dff8-ab27-5ed8-adc5-06bab07a43de | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.1.12 - Concrete Curing / Stripping of Formwork
7fef63f1-59ea-5225-95a9-9919ae51cebd | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
f80651cf-74b4-5944-9934-609801e7bff3 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting B2 exposure classification requires 14 days wet curing Formwork to be stripped after no less than 12 days Remove formwork in a way and time that achieves specified characteristics and prevents damage
093a7fff-e98e-54fc-9897-27e6d78618ec | note | Frequency / Process Held - Once / prior to Concrete Sign off
0bae88a6-eacd-5ce4-8920-ce923ce70b6d | note | Inspection - ACPL - S
ff74584d-6df0-5c4c-8a06-c7ee313ea862 | note | Inspection - Client - S
d925ff04-59c9-517c-a583-2f0055ad0f98 | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.1.13 - Concrete Cracking
b25e4c59-6951-5357-9952-d6e33e2e9c85 | note | Requirements / Reference - B80 Cl 9.3
a91a207d-062b-5c3f-94c0-1e685f22837c | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
6ddf29c5-385a-5e4b-896f-5a92870c183e | note | Frequency / Process Held - Inspection following removal of formwork
b0e3f9f0-041c-526b-a3c8-5bfb83705a89 | note | Inspection - ACPL - S
73c9bb68-ad03-59c3-b44a-835052c0b72d | note | Inspection - Client - S
da3443eb-9939-53e4-bb78-41d4d2e75088 | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.1.14 - Concrete Sign off
e5baaced-5121-5570-aaca-b753ec2ea0cc | note | Requirements / Reference - B80 Cl 8
a488da5e-c832-5994-aa87-98855d1e649b | note | Acceptance Criteria - Min 40mPa at 28 days
bcd7a5e5-493f-5ef3-ac0e-20af125b5cb8 | note | Frequency / Process Held - Once / Pier Concrete Pour
1fb260ec-292c-55eb-8bca-8af599a53707 | note | Inspection - ACPL - H
96bc4bee-86a6-55d9-987e-9de20994b515 | note | Inspection - Client - H
e31f5591-b155-5a59-8799-7124beaacad6 | note | Comments / Attachments / Records - Concrete Test Results - 28 days
| checkpoint | 2.1.15 - As-Built Survey
ba068a4e-1fe3-5e92-b55d-1fa524a27819 | note | Requirements / Reference - B80 Cl 9
c506fc84-3422-5180-9bb7-a53a20634310 | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Plan Dimensions: -10mm / +50mm Deviation in Plan Position in any direction: 50mm Deviation in Thickness -5mm / +25mm Deviation in Top Surface Level (RL): -25mm / +25mm
94fbd905-99ea-58c5-ad85-1fdbe30617d9 | note | Frequency / Process Held - Once / Pier FRP
3a0fd44b-4c46-5163-b2d0-9ad06742e681 | note | Inspection - ACPL - S
7d2a8693-0dc8-58fb-a842-25eb241f5c74 | note | Inspection - Client - S
c0f1e16a-7397-5d64-8995-4943a14644a0 | note | Comments / Attachments / Records - As-Built Survey Report
| section | Construction - 2.2 Pier
| checkpoint | 2.2.1 - Survey Set out
a6fd74d2-9374-56d2-9139-6703ad1ebc65 | note | Requirements / Reference - B80 Cl 5.8
b45ea45d-68e9-59b0-8ecd-ef23fe6352e3 | note | Acceptance Criteria - Survey set out as per design drawings
4ccaf865-75e5-570e-81fa-27811dd78dc8 | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
8e35aa6b-97bb-55c5-aec2-7b1052ffae2a | note | Inspection - ACPL - S
e092fdd1-3fd1-5e33-9e53-fdf8fd4f20a6 | note | Inspection - Client - S
89121c96-8826-5439-bd78-3b2de5a831ad | note | Comments / Attachments / Records - Set Out Report
| checkpoint | 2.2.2 - Formwork Certification
75b74b9a-9cfa-52f6-b5d1-bab6d78cdbf4 | note | Requirements / Reference - B80 Cl 5.2.3
f2146591-d81a-5aad-9afa-53943093fa1c | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member. Locate construction joints at the base of Headstock at least 100mm above the top of the pier.
de39fec7-1385-5ff2-b8c5-db0f8c10f8a2 | note | Frequency / Process Held - Prior to constructing formwork
75b98e99-c879-5bf7-b882-0b8cba4a922c | note | Inspection - ACPL - H
cf7e4847-16ae-5018-a2d3-c6ade3e78170 | note | Inspection - Client - H
2020e903-3cb7-52e7-a493-ff5569fc3bab | note | Comments / Attachments / Records - Formwork Documentation/Design Certification - HP115
| checkpoint | 2.2.3 - Installation of Thermocouples
022b05a6-0903-528c-ad2d-45f6b8d617f6 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1023
4b0ed184-344b-53ba-8e3a-503c6e3790e2 | note | Acceptance Criteria - Thermocouples must be located within the pile-cap to monitor the maximum temperature and differential temperature across the concrete. The location, frequency of testing, methodology and precautions must be submitted to the principle prior to the concrete pour. Thermocouples to be installed at: - Mid Height at Centre - -50mm from the outer surface
9c4bf3cc-0a02-57a5-9c6e-e9315269374d | note | Frequency / Process Held - Once / Prior to concreting
b35e9539-91e1-5718-b408-e78434ef5c24 | note | Inspection - ACPL - S
04cf82b8-3c3e-5174-904c-1f393d2148c2 | note | Inspection - Client - S
85c00210-d7f0-5094-808a-6abd7bc9b535 | note | Comments / Attachments / Records - Thermocouple Data Sheet
| checkpoint | 2.2.4 - Certificate of Conformity
9ccbaa5a-e62e-5648-8872-fb03cc47ccfa | note | Requirements / Reference - B80 Cl 7.5.2
92ceaa85-0bfd-5fad-bc3b-4f0f6555d967 | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working days prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s)
794d9388-3fa0-5bbf-a4b5-2f0139ec7ec7 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
2c4291fd-6499-5616-94bc-2129baf0e8fd | note | Inspection - ACPL - H
fe2762f0-e7b6-542b-9402-3f0ed77ffb9b | note | Inspection - Client - H
75503fda-ddc1-55a5-beff-d33bbdb2dc9f | note | Comments / Attachments / Records - Method Statement - HP186
| checkpoint | 2.2.5 - Certification of Steel Fixing Prior to Concreting
cb4d7d86-e262-5b2f-9d64-e160b4976027 | note | Requirements / Reference - B80 Cl 7.5.2
5dbabfd4-f72e-5e12-87cc-384e3f8c362e | note | Acceptance Criteria - Splice reinforcement only at locations shown on the drawings. All welding must conform to specification TfNSW B203 and the bar manufacturers recommendations. Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: +-45mm Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
c0cae366-760a-5edf-afc0-c299e92dc7b0 | note | Frequency / Process Held - Once / prior to placement of concrete
e8cf3136-0033-5bd7-9e4a-0f0323429574 | note | Inspection - ACPL - H
32bf022f-dfab-557a-80d3-f3924d2482f7 | note | Inspection - Client - H
73b7745a-4f0f-5fbd-8832-157ea7a2ee99 | note | Comments / Attachments / Records - Pre-Pour Checklist
| checkpoint | 2.2.6 - Certification of Formwork prior to Concreting
0ca10436-19a4-5825-bc96-300b771e6b05 | note | Requirements / Reference - B80 Cl 5
0c26979d-f419-5d0b-bbab-a450d08f257b | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
bcf84c33-32a8-53f4-ae26-027ff2baaa97 | note | Frequency / Process Held - Once / prior to placement of concrete
7c091884-7118-577d-b13f-3cfd3739a482 | note | Inspection - ACPL - H
6d85c9ea-4421-58c6-8a7d-9a8766f87ab4 | note | Inspection - Client - H
3b221f50-29c2-50fe-831c-4fa0a9201e51 | note | Comments / Attachments / Records - Pre-Pour Checklist
| checkpoint | 2.2.7 - Electrical Continuity Testing
65178f54-a531-5e3d-9127-25ce647f801a | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1017
a53adf5f-66a4-5161-9e35-b84ca6105b16 | note | Acceptance Criteria - Electrical continuity must be established for all reinforcement. Following the electrical continuity methodology, <2Ω must be achieved.
ec4695df-3cbe-5b70-a1c1-dc2029cff97f | note | Frequency / Process Held - Once / prior to placement of concrete
40b1aed4-4af1-58e1-91c9-07b5bc92de31 | note | Inspection - ACPL - S
defb29ac-f9d6-5dea-8df4-218f99fb1e23 | note | Inspection - Client - S
6b313991-e3d0-535c-9f00-b0b7f6fd866d | note | Comments / Attachments / Records - Continuity Report
| checkpoint | 2.2.8 - Concreting Personnel
61fc378d-277f-544a-8ed3-eddc59aeca84 | note | Requirements / Reference - B80 Cl 7.2.3
eeeb4d9b-8c4b-59f4-b8ec-7f557dd8bb6e | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
f7cb1f29-9fc0-55ae-a7d7-384c927a9c18 | note | Frequency / Process Held - Once / four hours prior to concrete pour
bc261e69-9e40-559f-a801-250e8593d208 | note | Inspection - ACPL - H
67973de7-c73f-51f3-b18b-bbfab8f099db | note | Inspection - Client - H
59880c1f-0799-5106-849a-196d4f3eddc7 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards - HP137 RFI-031 - Email to TfNSW
| checkpoint | 2.2.9 - Supply and Delivery of Concrete
19b5e2d5-44fa-5b8c-8b85-35ee8429d572 | note | Requirements / Reference - B80 Cl 4.1
bc1c9b64-aeea-51c6-8404-4923535a46fc | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
0728204e-ae84-529e-b00c-adb581a6ab16 | note | Frequency / Process Held - During concrete delivery
86cdafed-f716-55f5-a4d2-ec13c8a132ee | note | Inspection - ACPL - S
d9f10f83-d8da-597b-ac9c-333c098a59cd | note | Inspection - Client - S
1f531ee9-6263-5e05-aa30-102856135488 | note | Comments / Attachments / Records - Delivery Docket Concrete Pour Sheet
| checkpoint | 2.2.10 - Concrete Sampling
0c8b256b-6a77-5fdf-bb1d-056e692fb692 | note | Requirements / Reference - B80 Annexure B80/L
194fe8ff-6dc5-5a23-a37b-8a1d8d4acb05 | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
0d449e18-4e72-5cca-992a-b910386aff58 | note | Frequency / Process Held - Each element / prior to placement
88b21c1c-6aec-5c38-b37f-aefc1d4dc205 | note | Inspection - ACPL - S
c16d7271-3097-54cf-97e1-e680a0302416 | note | Inspection - Client - S
07ad6bf9-9e00-57b4-8c83-b55aa456bb30 | note | Comments / Attachments / Records - Concrete Sample Report Test Results - 7 days - 28 days
| checkpoint | 2.2.11 - Concrete Placement
64c4fcf7-9b93-5406-b16e-a041711178ae | note | Requirements / Reference - B80 Cl 7
6211df56-6451-596f-aaff-77b59c1fc66f | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32CAmbient temperature 5-35C 40MPa Concrete Concrete placed in column to be carried out in once continuous operation Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
31576b4a-6e53-5773-8770-2a5b64c655a6 | note | Frequency / Process Held - Once / prior to Curing
bc2a1657-1d7c-5ef4-8bc3-92e7389cb51d | note | Inspection - ACPL - S
42e35f8d-f3ee-58bf-ac8a-2e3d13a6d3dc | note | Inspection - Client - S
36ca3ba4-b1b3-5e8d-994f-0b6612eac1e0 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.2.12 - Concrete Curing / Stripping of Formwork
bf935678-845e-567c-8bf5-765e28352f89 | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
fcd82f55-65df-5bb8-97b6-1f99f8185fd1 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting B2 exposure classification requires 14 days wet curing Formwork to be stripped after no less than 5 days Remove formwork in a way and time that achieves specified characteristics and prevents damage
fbc8b97b-a3ba-5725-93e3-b607ca1277b7 | note | Frequency / Process Held - Once / prior to Concrete Sign off
5d772d4b-6a1d-551f-9291-de422890e130 | note | Inspection - ACPL - S
adb9012f-3a58-5756-acb9-b7d71c216897 | note | Inspection - Client - S
2b21798f-1563-5664-8bff-16aa6bd2ad3a | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.2.13 - Concrete Cracking
893f9155-31e3-5b4a-8b9a-2e0eec6ad0a1 | note | Requirements / Reference - B80 Cl 9.3
357af230-4a94-5b8c-b7f0-5fc0b2513a2c | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
84d88f6d-cf9f-5a03-8077-6145af5558a6 | note | Frequency / Process Held - Inspection following removal of formwork
191ea2a5-308f-5f02-a3f8-49940e8d68e3 | note | Inspection - ACPL - S
b4ee1cfa-d7ba-5ed6-906b-3654c0de53bb | note | Inspection - Client - S
6aa6a399-9b39-5dca-b469-e1384b250eb0 | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.2.14 - Concrete Sign off
0be035c1-8832-5eec-8735-e1136ac4bcd6 | note | Requirements / Reference - B80 Cl 8
28b33189-ea36-56b9-bfa3-0b3824e243d9 | note | Acceptance Criteria - Min 40mPa at 28 days
6e2bb030-b333-594f-8025-e0ed0280c2c9 | note | Frequency / Process Held - Once / Pier FRP
ba32c538-a46d-5ced-919c-6b342549e133 | note | Inspection - ACPL - H
2d48e79b-2419-5164-9371-acc04adebf07 | note | Inspection - Client - H
9b283995-54b2-5e65-a969-4a565dcbf4da | note | Comments / Attachments / Records - Concrete Test Results - 28 days
| checkpoint | 2.2.15 - As-Built Survey
1b721cc9-78e0-534a-8136-dc8cef77a54b | note | Requirements / Reference - B80 Cl 9
760ff909-eb2b-5984-ad2b-3c43a7b30c8c | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Plan Dimensions: -10mm / +25mm Deviation in Plan Position (at any level) in any direction: 25mm Deviation from alignment of row of members: 10mm Deviation from vertical or specified batter: 6mm in 3m (1/500) Deviation in Top Surface Level across width of member: +/-5mm
3c5a663f-1607-594e-9df0-49833bf40161 | note | Frequency / Process Held - Once / Headstock FRP
7d374906-f87e-56b3-b2e6-6c8b4b3768a5 | note | Inspection - ACPL - S
1c8c28eb-bad9-5023-880d-801113d97ad4 | note | Inspection - Client - S
b95b9939-4d71-511b-8a38-c4a60a9fb8a8 | note | Comments / Attachments / Records - As-Built Survey Report
| section | Construction - 2.3 Headstock
| checkpoint | 2.3.1 - Survey Set out
5017bb02-ee29-5e3a-b70d-577140d2158c | note | Requirements / Reference - B80 Cl 5.8
15adb4e8-9484-5b6c-8998-af3da8704972 | note | Acceptance Criteria - Survey set out as per design drawings
fd5f633a-6c47-5e14-91e5-abeedc97e99b | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
7335217f-d32d-53bc-aeba-abf01391e5ea | note | Inspection - ACPL - S
a4810974-7977-5ae6-b0d7-1545d794812d | note | Inspection - Client - S
dfb2b1c0-1513-5479-9e4b-be785f44a3d5 | note | Comments / Attachments / Records - Set Out Report
| checkpoint | 2.3.2 - Formwork Certification
ee89c419-ec67-5477-a743-ea9039030f0f | note | Requirements / Reference - B80 Cl 5.2.3
31276485-f6fa-5ffb-936d-374b5a27f979 | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member.
ed717b74-f1ff-5683-80ce-e3a8090de43a | note | Frequency / Process Held - Prior to constructing formwork
5a3381bf-97a9-5786-a279-1730fd1a9d80 | note | Inspection - ACPL - H
18c35001-976c-563f-9c0e-f8ab8ba31ec9 | note | Inspection - Client - H
04e5c846-551b-565a-9dc3-f4617b2f307f | note | Comments / Attachments / Records - Formwork Documentation/Design Certification - HP115
| checkpoint | 2.3.3 - Installation of Thermocouples
b29434df-90c6-5d56-a103-01913a8d6b48 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1023
41652c8c-a1bf-5257-8d05-3945bf074d9a | note | Acceptance Criteria - Thermocouples must be located within the headstock to monitor the maximum temperature and differential temperature across the concrete. The location, frequency of testing, methodology and precautions must be submitted to the principle prior to the concrete pour. Thermocouples to be installed at: - Mid Length at Centre - -50mm from the outer surface
8910f012-61f1-5cb1-a983-aed1eefbd868 | note | Frequency / Process Held - Once / Prior to concreting
c2b65ed2-3ec4-5c79-b520-a208333fa54b | note | Inspection - ACPL - S
82c7fd2e-7f1a-51d2-95ef-cc3a67b78472 | note | Inspection - Client - S
f2b2315a-56ae-5b5e-8548-e3abdc268922 | note | Comments / Attachments / Records - Thermocouple Data Sheet
| checkpoint | 2.3.4 - Certificate of Conformity
2f414089-6fb8-544c-a729-11897294a496 | note | Requirements / Reference - B80 Cl 7.5.2
3961c428-68e1-57da-aab6-a1d82fa1499e | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working days prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s)
db1bc27f-6b03-584b-a827-f5ac39c84983 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
a92cf170-5187-5776-9a6b-266e6531f494 | note | Inspection - ACPL - H
150ca17d-1f02-5b56-99cb-bef212a47ab2 | note | Inspection - Client - H
8b8ea5f1-642b-5c60-b11b-11872b0441c5 | note | Comments / Attachments / Records - Method Statement - HP186
| checkpoint | 2.3.5 - Certification of Steel Fixing Prior to Concreting
e353c810-48ff-57fd-846a-c513d84d7698 | note | Requirements / Reference - B80 Cl 7.5.2
3019470e-9bc9-5363-b09c-2fcc5b3768dc | note | Acceptance Criteria - Splice reinforcement only at locations shown on the drawings. All welding must conform to specification TfNSW B203 and the bar manufacturers recommendations. Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: +-50mm Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
514c817a-4d6e-526a-b60b-317290e591a7 | note | Frequency / Process Held - Once / prior to placement of concrete
4f41fd39-0460-512c-98c0-f42948fc92d8 | note | Inspection - ACPL - H
9596debd-2334-5a27-9d77-2916293bdc4e | note | Inspection - Client - H
85b51d0d-fb78-55ec-b7ac-8d0f8f763364 | note | Comments / Attachments / Records - Pre-Pour Checklist
| checkpoint | 2.3.6 - Certification of Formwork prior to Concreting
2ac9d76b-d6a0-53c1-8842-e219e67e1bf7 | note | Requirements / Reference - B80 Cl 5
9df697e2-4769-502f-9834-5f86840b0cbe | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
6bbc0a59-2388-5730-b931-dfa2fd3d4c1f | note | Frequency / Process Held - Once / prior to placement of concrete
7ab614f2-d5bd-5754-b78f-b5d2294b4cf3 | note | Inspection - ACPL - H
43c5a1dc-878c-50cf-bbb8-741210aef52c | note | Inspection - Client - H
b3344305-248d-542f-9f42-66aca3f2a934 | note | Comments / Attachments / Records - Pre-Pour Checklist
| checkpoint | 2.3.7 - Electrical Continuity Testing
232a2497-8133-541e-8d2e-bcf457bd235a | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1017
7227a0eb-3938-5929-a4b7-ea8a0de3bcde | note | Acceptance Criteria - Electrical continuity must be established for all reinforcement. Following the electrical continuity methodology, <2Ω must be achieved.
9dab8ee5-e2ca-5bab-84c3-fda1cde973c4 | note | Frequency / Process Held - Once / prior to placement of concrete
b109e21d-d7d0-57b0-b8da-e43e4c145f6f | note | Inspection - ACPL - S
afc71f63-ea7a-5b44-b550-c05dfaf66634 | note | Inspection - Client - S
3b20e851-8422-509d-bcd0-9a36a64cce15 | note | Comments / Attachments / Records - Continuity Report
| checkpoint | 2.3.8 - Concreting Personnel
a6108b77-35db-5643-b4ee-c53c38fb5ace | note | Requirements / Reference - B80 Cl 7.2.3
af5ec5ab-d7b4-555d-ad63-6e9f2e887931 | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
a9f814ab-2590-56b1-8997-7342cd367019 | note | Frequency / Process Held - Once / four hours prior to concrete pour
1043285a-b148-508c-acc8-9b916940bb4e | note | Inspection - ACPL - H
5c118cc0-456d-50bd-a15e-3f83d99facf7 | note | Inspection - Client - H
480c2baf-f50d-5b44-b775-f09e061ba4f1 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards - HP137 RFI-031 - Email to TfNSW
| checkpoint | 2.3.9 - Supply and Delivery of Concrete
80909b99-b481-5e09-be2c-e683296e3d09 | note | Requirements / Reference - B80 Cl 4.1
9acb73ad-ba0c-5097-9034-ace613689e1b | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
eb489895-8a8d-5107-a744-78cdb44b8d75 | note | Frequency / Process Held - During concrete delivery
a2ded95c-1bea-5c06-9381-1096b1df0701 | note | Inspection - ACPL - S
32aad623-76db-51d4-bfd1-91205bd40f50 | note | Inspection - Client - S
941db05f-de4f-5866-8392-b0fb917b2f12 | note | Comments / Attachments / Records - Delivery Docket Concrete Pour Sheet
| checkpoint | 2.3.10 - Concrete Sampling
a347b2fb-b11d-5a54-bae7-4784393d52e1 | note | Requirements / Reference - B80 Annexure B80/L
b1c98591-558c-502b-8159-f0e8b2cb33c8 | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
2840cafd-969b-525c-ad08-1943e64c0936 | note | Frequency / Process Held - Each element / prior to placement
28df5955-0375-564f-9fcd-d076d84c3f45 | note | Inspection - ACPL - S
b812937a-e60e-574a-8b8e-b32d18d95b0c | note | Inspection - Client - S
d5a3a145-2b2e-50ab-b188-f816bdd79584 | note | Comments / Attachments / Records - Concrete Sample Report Test Results - 7 days - 28 days
| checkpoint | 2.3.11 - Concrete Placement
6adacee9-908a-50d7-9912-4d52d2e2d4eb | note | Requirements / Reference - B80 Cl 7
298e2efe-6d61-599c-a196-b13f33d551c3 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32CAmbient temperature 5-35C 40MPa Concrete Concrete placed in headstock to be carried out in once continuous operation Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
6ca2989d-5f22-5245-8bd6-1f5470e8681d | note | Frequency / Process Held - Once / prior to Curing
df63dbff-f393-5adf-84e0-22bd32949b04 | note | Inspection - ACPL - S
438e56d6-4c48-594a-9483-b53cc20e0f89 | note | Inspection - Client - S
66ac0326-4aa3-55ff-be5f-b3ff97d8b208 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.3.12 - Concrete Curing / Stripping of Formwork
93209082-ce28-582d-8d42-8d95bce292d2 | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
ee0fe55e-6e47-5821-aff2-1b814884e7bf | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting B2 exposure classification requires 14 days wet curing Formwork to be stripped after no less than 12 days Remove formwork in a way and time that achieves specified characteristics and prevents damage
20f92aea-1d28-5b05-91aa-6cdc7dab1516 | note | Frequency / Process Held - Once / prior to Concrete Sign off
5296da0d-67d1-5fd7-8ef7-e36c83979a56 | note | Inspection - ACPL - S
e8a10cbf-49b7-5d15-a0bc-df0c12681903 | note | Inspection - Client - S
9b756842-4f62-531b-8362-457030e5a067 | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.3.13 - Concrete Cracking
98d69ab7-b202-5375-b11b-9e0c171d81bb | note | Requirements / Reference - B80 Cl 9.3
0493bdb3-ba05-5c6f-a176-c9ab70a8de49 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions. Non-conforming surface imperfections and defects also to be recorded and assessed.
4915dc4c-3086-519b-b8a2-e64346a41ecc | note | Frequency / Process Held - Inspection following removal of formwork
99ce469a-55da-5395-82c7-e0f23922949c | note | Inspection - ACPL - S
b53658c5-0640-5842-953c-8144a97f5067 | note | Inspection - Client - S
58596bc8-0e3f-577e-9ce2-83b870b012d8 | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.3.14 - Concrete Sign off
dd6c827a-881d-59f2-ab8a-d8398196122d | note | Requirements / Reference - B80 Cl 8
826f2f0d-af6d-5ccf-9c54-8816c0b0e157 | note | Acceptance Criteria - Min 40mPa at 28 days
a497ba05-b5fc-5e75-a3cc-f2750e6263bf | note | Frequency / Process Held - Once / Lot Closure
4ef7fb04-d0d7-58c4-b123-c5ef3062f96e | note | Inspection - ACPL - H
ca9b7e1f-0862-56f5-af3a-aa5ff81ec7eb | note | Inspection - Client - H
2d62ce53-85fd-5ec3-abdd-9d280687fd98 | note | Comments / Attachments / Records - Concrete Test Results - 28 days
| checkpoint | 2.3.15 - As-Built Survey
8d589297-15d5-54e9-bf32-2b57b6b1c58f | note | Requirements / Reference - B80 Cl 9
136446cd-89a4-5921-b46b-28d2c97b2901 | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Plan Dimensions: -10mm / +25mm Deviation in Plan Position (at any level) in any direction: 25mm Deviation from alignment of row of members: 10mm Deviation from vertical or specified batter: 6mm in 3m (1/500) Deviation in Top Surface Level across width of member: +/-5mm
874d15e5-36a4-50bb-bf0f-44d2c19fe6fd | note | Frequency / Process Held - Once / Lot Closure
6a023c6d-c2e0-586a-83b5-6fb069e965a3 | note | Inspection - ACPL - S
f9a3ed90-1597-578c-a85b-69f202bc7807 | note | Inspection - Client - S
e24d5f2e-9c79-5aa4-89bb-5f526243c843 | note | Comments / Attachments / Records - As-Built Survey Report
| section | Lot Verification
| checkpoint | Lot Verification complete
303517ec-6c97-586b-89a3-7b59b3553078 | textbox | Lot Verified By:
11d2d985-8afa-55ea-bc64-b2ee3ab79fa9 | textbox | Lot Closed Date:
4c0b7388-3342-584a-9796-e53a2f6f0b05 | button | Submitted to Client | Yes, No, N/A
dc057049-ce26-5a1b-b6e3-02c48b113d2d | button | Reviewed by Client | Yes, No, N/A
d3ea8704-6df0-55cd-8fd0-bd3a2754fd08 | textbox | Submission Comments:
| section-nested-checklists | NCR
23959678-a856-4bd0-9193-765409f5b5bc | checklist | ITP 15 - R55 Rocks Gabions & Mattresses Rev 0 | itp | ITP 15 - R55 Rocks Gabions & Mattresses Rev 0 | 45dc36a4-e66d-4400-a846-bbcc9da5360f
670f5f61-46a3-4e7b-bbc5-d7600b4942fa | section | Lot Information
902ac3e9-100f-428a-98ba-900374745a19 | checkpoint | Lot Information complete
8d9f12aa-74a9-52d0-814d-a4f716e4a7cb | textbox | Lot Opened On
2e969cbc-1bf8-56ba-b25d-7c20a142126f | textbox | Date of Works
73414c00-b68c-529f-a8ef-19c0bb2c10c8 | textbox | Lot Type
9c5cf20b-2723-5898-8874-4a8c0d189226 | textbox | Start Chainage
148dba0e-eecc-53fe-9792-306cc896c210 | textbox | End Chainage
052b2179-7a5b-57d8-8694-03ba0fc4c478 | textbox | Offset
192acde4-50aa-506b-8499-3ce0eb1064fc | textbox | Control Line
3bf56b7b-48ff-4a25-873b-c12f7f36e67a | section | Details
56d441a3-7148-4381-87fe-402a0ef198fc | checkpoint | 1 - Safety Review
f3e4d1bb-7468-52a3-a9bc-91a7230ddbca | note | Requirements / Reference - Project Safety Plan
f0731883-9441-564f-af8a-337aeb979ada | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
30845f41-dee4-56eb-9269-65cc65ab7b21 | note | ○ Required Safe Work Method Statements completed and signed
b903db90-85c1-5247-9dc2-c2453cab3135 | note | ○ Subcontractor’s safety plan / procedure approved
ba1f645e-493c-5197-bf2e-6b456174282b | note | Frequency - Prior to commencing works
05c9ee1a-66e2-5905-89bc-5a6d02fa588f | note | Inspection: ACPL - W
b8e3d695-1467-5586-8766-d20497d1fc18 | note | Inspection: Client - S
8e99cb1d-88b2-411a-8786-0d6062fc7e23 | checkpoint | 2 - Environment
009dd739-39f5-5b75-97e1-bfffac394e2b | note | Requirements / Reference - Project Environment Plan
15f5f556-1240-558e-bf3d-68f25a0f97e3 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
f6b53460-a195-5f9f-ba51-8942a7e87728 | note | ○ Air quality to be visually monitored for dust etc as a direct result of construction activities
889e35dd-d3c7-57f7-b3c4-ed05cd3c670d | note | Frequency - Prior to commencing works
7dac9f64-6e5b-525b-8a92-f939f02cb3f8 | note | Inspection: ACPL - W
e4fa614d-0755-5099-841f-5f6f71a4d5e8 | note | Inspection: Client - S
9e1c032c-2dab-4750-a668-d51bd9ca149e | checkpoint | 4 - Gabions
3bec5c54-9486-5051-8644-7d113736c641 | note | Requirements / Reference - R55 Cl 2.1
c9565722-72a0-5ee0-ae4f-1e1b44bbd7b5 | note | Acceptance Criteria - Gabions must be flexible, woven, galvanized wire mesh boxes of dimensions as shown on the Drawings conforming to ASTM A975-97. Where specified on the Drawings, the galvanized wire mesh must be coated with PVC.
4cc5bd50-771b-5b3f-bb0d-f6b2cb7f2630 | note | ○ The galvanizing coating must be a 95% Zinc, 5% Aluminium Mischmetal alloy conforming to the requirements of ASTM A975-97. The physical properties of the steel wire and PVC coating must conform to the requirements of ASTM A975- 97.
e438a550-d4f2-5abf-9487-fff0bae345fc | note | Frequency - During Installation
772fa920-e48d-5918-b0fd-9b210cfbc0bb | note | Inspection: ACPL - S
23cd9651-0e50-5625-8c60-a3d90806f2d5 | note | Inspection: Client - S
9b27bc22-1dc0-4bb8-8c88-7207940de513 | checkpoint | 5 - Mattresses
3a313065-d3a6-52da-b3cd-6f49a028988a | note | Requirements / Reference - R55 Cl 2.2
8d89ede6-c9ac-583c-a3ba-19e9908efe45 | note | Acceptance Criteria - Mattresses must be flexible, woven, galvanized wire mesh boxes of dimensions as shown on the Drawings conforming to ASTM A975-97. Where specified on the Drawings, the galvanized wire mesh must be coated with PVC.
82cf282e-dd68-59ba-aef7-69f5c7151576 | note | ○ The galvanizing coating must be a 95% Zinc, 5% Aluminium Mischmetal alloy conforming to the requirements of ASTM A975-97. The physical properties of the steel wire and PVC coating must conform to the requirements of ASTM A975- 97.
e02facd8-50e6-5f6b-b323-9549c921e6f3 | note | Frequency - During Installation
bd0092c1-2f35-544d-9023-78368d1e8767 | note | Inspection: ACPL - S
d9fcd001-a487-51bd-bade-323e8024a278 | note | Inspection: Client - S
781ea829-1d72-4a1a-96e1-56bc822816df | checkpoint | 6 - Selvedges
9aeeb3bc-512c-5ce0-8af4-fbf09fd38810 | note | Requirements / Reference - R55 Cl 2.3
ef754458-6e5d-585c-b6f6-d32181208c52 | note | Acceptance Criteria - All edges of the gabions, mattresses, diaphragms and end panels must be selvedged with a continuous wire in accordance with ASTM A975-97.
6d476a3e-02ad-5662-9443-028b9109106f | note | Frequency - During Installation
d499a566-c283-5ded-b3d7-4719beaa33f0 | note | Inspection: ACPL - S
55caa10d-5ee3-5b9f-b263-de4d046e9fe3 | note | Inspection: Client - S
3fb493bb-29a7-441a-9320-248d846e4186 | checkpoint | 8 - Lacing And Connecting Wire
6cee6761-68e9-5a48-975e-3e4dd1395385 | note | Requirements / Reference - R55 Cl 2.5
ebf718eb-9d24-535c-9a47-e86cb79bccb7 | note | Acceptance Criteria - Lacing and connecting wire must be supplied with the gabions, mattresses and mesh panels to perform all the wiring operations to be carried out in construction of the gabions or mattresses. Materials must conform to ASTM A975-97. The minimum diameter of the wire (or wire core in the case of PVC coated wires) must be 2.2 mm.
d7bbff91-f9c8-5858-8bfa-f91a05cfffd6 | note | ○ Alternative fastener systems such as “C” clips in place of lacing and connecting wire are permitted but must conform to the requirements of ASTM A975-97.
6a915436-2a83-56d1-a91c-d1f69ee91478 | note | Frequency - During Installation
45a33fbd-e4a1-5ac7-a514-2be95e12d750 | note | Inspection: ACPL - S
cc0ec31d-93a7-53e8-84a2-9795a1aaa369 | note | Inspection: Client - S
57dc0f66-4ccf-453d-8915-c06a4d24fe92 | checkpoint | 9 - Rockfill
1eaa030c-a354-5c2f-bad1-6cbe9e763664 | note | Requirements / Reference - R55 Cl 2.6
26f8d7a9-a3d5-584f-993d-d38e0f269a56 | note | Acceptance Criteria - Rockfill must be dense, hard, durable and clean rock.
94bd62c7-e130-5abf-9d49-6cc2d2440d72 | note | Frequency - During Installation
bf4a2bee-9087-58e2-934c-3fa886d8e481 | note | Inspection: ACPL - S
0fca4cc3-1dde-5b48-bdab-710221ca7865 | note | Inspection: Client - S
6d1d287e-1402-443d-8eee-cbe3d2e6002e | checkpoint | 10 - Aggregate Wet/Dry Strength
556edb83-e482-5d86-bdcd-9453e5a2c6c1 | note | Requirements / Reference - R55 Cl 2.6.1
ff1973a3-21ed-59ab-9e99-b31e30a05662 | note | Acceptance Criteria - Rock from all sources must have a wet strength of at least 100 kN and a maximum wet/dry strength variation of 35% when tested in accordance with Test Method TfNSW T215. The rock may be crushed by the testing authority so as to produce material that is suitable for testing by Test Method TfNSW T215.
116e5b07-338c-5d3d-8047-7539bfbabad4 | note | Frequency - During Installation
758e36fc-2f65-541c-bbd0-4e2acdf51bcf | note | Inspection: ACPL - S
e4cc2cbc-9857-5b61-be30-190d06a66949 | note | Inspection: Client - S
8c08b604-17f1-5274-a547-2304ab643b51 | note | Comments / Attachments / Records - If practical, recycle any unwanted guide posts.
3cda7ecb-3cf4-59bd-a79d-9e7c5a37822c | note | — Test results
55e5d1af-21c4-4f56-97fe-7fb14060e37d | checkpoint | 11 - Size
3d6fb550-7ce5-576b-a44e-6a016ce1ba7f | note | Requirements / Reference - R55 Cl 2.6.2
8b90fe50-64ad-56c3-98c3-15bf9b623e4a | note | Acceptance Criteria - For gabions, the minimum and maximum rock size must be 100 mm and 250 mm respectively.
71191a6e-a075-5b12-bb00-b972c2b7d617 | note | ○ For mattresses, the minimum rock size must be 75 mm, and the maximum rock size must be two thirds of the thickness of the mattress or 250 mm, whichever is the lesser.
201102cf-0ad9-5f55-92bb-d0ad1138362c | note | ○ HOLD POINT: Use of rockfill.
4a220067-132d-5d73-8f01-7a8527b35fef | note | ○ Submit details regarding the properties and source of the rockfill.
e8de381c-c06c-5d14-bd5d-03b44f0a1a5a | note | Frequency - During installation
3809ec02-0d9b-55e7-af80-524f448fa382 | note | Inspection: ACPL - H
7a865804-9d09-5da5-b487-e1b13d7b180a | note | Inspection: Client - H
604cd1d4-bd6d-5129-8428-672c3be15595 | note | Comments / Attachments / Records - HOLD POINT
e23002e0-2fb7-43d6-a4c4-d38aed7c8cb1 | signoff | AUTHORITY HOLDPOINT
9ce3624c-09ba-46c4-9f42-d42acc036379 | checkpoint | 12 - Installation - General
bc719f04-5876-5ef0-a509-2055fbfa9a2e | note | Requirements / Reference - R55 Cl 3
ca00cf29-171b-589b-b537-fbc00b9b47d5 | note | Acceptance Criteria - Assemble and install all gabions and mattresses in accordance with the requirements of this specification and the manufacturer’s recommendations.
4c935de1-6887-53d2-ba95-bb505adb8517 | note | ○ Carry out the excavation shown on the Drawings prior to the installation of the gabions, mattresses and/or Terramesh panels.
bd858fa7-7654-5137-bbdf-b21a502f333f | note | ○ Use the excavated material for the construction of embankments, or dispose of it to spoil in accordance with Specification TfNSW R44.
551b0702-9717-5a7d-a7e2-ade451a04113 | note | Frequency - During installation
8d42380b-71b7-5be4-8a3e-600633c84e60 | note | Inspection: ACPL - S
f1e97ec1-f84e-54d8-a414-1713a262debf | note | Inspection: Client - S
6104991f-ec74-4fc5-a23f-febe206216fc | checkpoint | 13 - Stretching
73c4ec0e-309b-5dd1-a524-22dc649d7f96 | note | Requirements / Reference - R55 Cl 4.3
2801678e-b52e-58bb-a685-517b57ad2a77 | note | Acceptance Criteria - HOLD POINT: Filling of gabions.
7650f6b9-f246-58d9-9d43-02e9e4b90541 | note | ○ Provide verification that the gabion units have been supplied and assembled in accordance with specification requirements.
05007520-30c7-5d70-b3f3-7be606611eaf | note | Frequency - During Installation
3f5be2d3-3133-59dd-8a76-2f00fe278124 | note | Inspection: ACPL - H
c93b8080-c40f-5c9b-8f50-c658c2516526 | note | Inspection: Client - H
aed2d05b-4740-535b-a637-64f292e2df33 | note | Comments / Attachments / Records - HOLD POINT
c5004ce6-40c5-4dcc-bc3b-f058e3d9f256 | signoff | AUTHORITY HOLDPOINT
611735b8-aea2-41ad-9dcb-990969cf06c7 | checkpoint | 14 - Filling
85497a1b-8ef8-5879-983d-980150256fc3 | note | Requirements / Reference - R55 Cl 4.4
824776f6-b55f-5b6f-a4a9-0f111da24583 | note | Acceptance Criteria - Carry out filling of the gabion boxes only while the gabion boxes are under tension.
0f21bc4f-dcd0-501a-8d23-88fadf7bd373 | note | ○ Place the rocks at the front face, and all other faces which will be exposed in the completed structure, by hand packing so as to produce a neat face free from excessive bulges, depressions and voids.
447324e6-b075-535a-9473-ad7efa0d0284 | note | ○ Provide internal bracing wires prevent distortion of the gabion units during filling and in the completed structure.
8f7c8c99-50fc-58f7-bcae-f12380fab7af | note | ○ Mechanical filling equipment may be used provided that adequate precautions are taken to protect any PVC coating from abrasion during filling operations.
06d51b8a-61c5-539d-a123-39363217c139 | note | ○ Release the tension on the gabion boxes only when fully laced and sufficiently full to prevent the mesh from slackening.
02ff1838-a391-5ce0-a38c-245090d66612 | note | Frequency - During Installation
a0034c5e-2064-5bae-95ff-34869aeef713 | note | Inspection: ACPL - S
0bb8278b-ffd7-5e34-95e5-2b97e0466576 | note | Inspection: Client - S
9cc97b57-9f02-48bd-80f1-95d20f01b9e5 | checkpoint | 15 - Final Lacing
6f9f98b3-4031-5970-9c58-453a23441cd4 | note | Requirements / Reference - R55 Cl 4.5
e5e84855-8141-5e4d-8c25-2ddf4e17219e | note | Acceptance Criteria - Closing and lacing down of lids must proceed as soon as practicable after the filling operations particularly where there is a likelihood of storm or flood during construction.
ace1b71d-1d30-563f-a0f0-53c824c4c116 | note | ○ Stretch the lids tightly over the filling with suitably designed closing tools and lace down securely through each mesh along all edges, ends and diaphragms before commencing work on the next layer of gabion.
f281e5b5-6969-586f-9a9c-9a182b6e6bbb | note | Frequency - During Installation
c2b92ea9-33f6-5898-a717-e0392ecb76c8 | note | Inspection: ACPL - S
f1331184-5669-586d-b695-0f0e98a851a3 | note | Inspection: Client - S
a3a59f8e-df15-440a-89ea-3cf055b6be6e | checkpoint | 16 - Installation Of Mattresses
0a6aa874-e3d3-5dff-a8b8-e4ed6fdc47c9 | note | Requirements / Reference - R55 Cl 5.1
ff60601f-92e1-59bd-87d8-cce5fbfcfa01 | note | Acceptance Criteria - Prior to assembly, open the wire mesh out flat on the ground and stretch it to remove all kinks and bends.
73c4d639-f030-58d0-997f-d28f7f77ee80 | note | ○ Assemble the mattresses individually, by raising the sides, ends and diaphragms, ensuring that all creases are in the correct position and that the tops of all four sides and the diaphragms are even.
c51ec792-98f2-5f1a-9d4f-234df840ae24 | note | ○ Maintain tightness of the mesh and wiring at all times.
dd056d31-cc80-5bfa-9672-eddd83503549 | note | Frequency - During Installation
68ed7e75-f64f-590e-a822-3e2baba807fd | note | Inspection: ACPL - S
3d210af7-055a-583c-9e85-933a6b9894de | note | Inspection: Client - S
2f19ca01-efe5-4c8d-9909-6e4d429518c2 | checkpoint | 17 - Erection
6560e4c7-f9f7-580d-b9fb-4d89f5cc3480 | note | Requirements / Reference - R55 Cl 5.2
2c3e6c95-f514-5fae-a127-863779fc10c8 | note | Acceptance Criteria - Only assembled mattress or groups of mattresses may be positioned in the structure, with each mattress being securely laced to the surrounding ones along the perimeter.
f4fafd25-45d7-5bb7-97c5-db017dd4164d | note | ○ When the mattress is laid on a slope steeper than 1(V) in 1.5(H), secure the upper edge by galvanized star pickets driven at 1 m centres a minimum of 900 mm into the ground, or as shown on the Drawings.
9cfa5a86-a4ad-5f73-a8c3-a1ec554f7a44 | note | ○ HOLD POINT: Filling of mattresses
83453810-bb99-59ba-80d3-83dcf76e0d70 | note | ○ Provide verification that the mattress units have been supplied and assembled in accordance with specification requirements. The Principal will inspect the installed mattresses prior to authorising the release of the Hold Point.
775c3678-1b8a-5976-aba6-5129ecf7682f | note | Frequency - During Installation
76326bee-6cf1-5cb4-b2b4-5b718a6dcab9 | note | Inspection: ACPL - H
85684360-eb34-5b7a-ae47-7408b21ae8fb | note | Inspection: Client - H
b4185420-afb8-5161-90da-fea3dccb09c4 | note | Comments / Attachments / Records - HOLD POINT
7ee7b954-e601-43f5-a2b0-698c115d0818 | signoff | AUTHORITY HOLDPOINT
c7df1cb5-10b2-4b02-8523-48000bb784be | checkpoint | 18 - Filling
eddb6710-fe1a-53f8-9bc7-3d6f29f4af2a | note | Requirements / Reference - R55 Cl 5.3
0d24c7da-a587-59a0-ace0-d95f5ba0e02b | note | Acceptance Criteria - Mechanical filling equipment may be used provided that adequate precautions are taken to protect any PVC coating from abrasion during filling operations.
8733ebcb-a24d-5118-8b0a-e80afd578460 | note | ○ Redistribute the filling materials by hand to ensure that all diaphragm compartments are fully filled and to produce a neat and level top surface.
8eec5236-0357-59a0-9391-7692c0da25bc | note | ○ Mattress units must be overfilled by 25 mm to 50 mm to allow for subsequent settlement.
07694232-4393-5090-932d-ac109f119eac | note | Frequency - During Installation
3bad4859-6d83-5534-b3b4-ea172bd25e4c | note | Inspection: ACPL - S
b425de68-536d-53b0-bba9-cd0d483d5546 | note | Inspection: Client - S
af24ed2f-cf99-45d6-975e-a176ee71abf1 | checkpoint | 19 - Final Lacing
bbbb629d-d604-5938-a7cd-6c9784bcbd3a | note | Requirements / Reference - R55 Cl 5.4
ec173eac-6b59-5e45-a80d-3fd85058ee4c | note | Acceptance Criteria - Closing and lacing down of lids must proceed as soon as practicable after the filling operations have been completed.
053b4b64-9172-51d1-a0ae-2b5760c42737 | note | ○ Stretch the lids tightly over the filling with suitably designed closing tools and lace down securely through each mesh along all edges, ends and diaphragms. The ends of all lacing wires must be turned into the mattress on completion of all lacing operations.
f658d7de-fc1c-5c04-9206-13689682980b | note | Frequency - During Installation
526e3d00-87b8-50ae-b2af-27358b7565e4 | note | Inspection: ACPL - S
7c300e54-0dd8-5a74-af03-cc41f231ac6f | note | Inspection: Client - S
be7017af-d5af-4cc0-af63-9d99c6105ad6 | checkpoint | 20 - Geotextile For Gabions And Mattresses
6da1b703-ea54-5b3c-8d38-ff2e47687998 | note | Requirements / Reference - R55 Cl 6
c2774f41-48ac-58f5-a2be-b0906bf5d7a1 | note | Acceptance Criteria - Before laying out gabions or mattresses, place the geotextile between the wire cage and the material being protected or retained. The geotextile must be a non-woven type meeting the requirements of Geotextile Strength Class C and Filtration Class 2 in accordance with Specification TfNSW R63.
4e8381d5-c580-5951-89c4-9a587fd6940e | note | Frequency - During Installation
2af9bb90-7e44-53bf-8cc0-42598e6833f9 | note | Inspection: ACPL - S
020c085c-95a4-5cf1-8147-b52ddc839362 | note | Inspection: Client - S
03937bdb-ef82-4740-84fb-4c09b2dbdf8f | section | Review by Project Engineer
d2cf6282-98e4-421d-b8a5-84967b1b2556 | checkpoint-no-value | Review by Project Engineer
91d0b40d-3cbf-5c04-8bea-fcf95f962da3 | button | Any non-conformances? | YES, NO
1d1c54b1-39eb-59ee-bd01-dca64a4db713 | textbox | No's:
bc7cfc4e-8480-5f9f-a307-2c54eec718b5 | button | Closed Out | YES, NO
00539504-4bd4-5ec0-83ae-7ec509342783 | button | All work has been satisfactorily completed. | YES, NO
4217215d-ae1c-5f2b-b924-b2a3b4c1bbba | textbox | Name:
8a25afed-e367-4e1b-828d-7a3bcda64301 | signoff | Add signature
b9a13b63-8005-4561-8f46-8cd0a8b49222 | section | Lot Verification
8a78f580-9959-4080-ab3f-6171abba4d3e | checkpoint | Lot Verification complete
3cafdbf3-ab66-5d2c-8b8e-5d6f7a4bc749 | textbox | Lot Verified By:
400a9c99-0328-55dc-9ef3-d218a44eede1 | textbox | Lot Closed Date:
39d21535-0637-531d-a8f0-b243e36952ed | button | Submitted to Client | Yes, No, N/A
a1564c25-86e1-5ed5-88d2-97150e2e76e6 | button | Reviewed by Client | Yes, No, N/A
a1761233-dd42-592b-93ef-94afad076d6a | textbox | Submission Comments:
f10f5985-28b8-4f42-94d3-487729b93f30 | section-nested-checklists | NCR
07e70956-c845-4285-a6e0-c6d3c9b782f4 | checklist | ITP 19 - R101 Cold Milling | itp | ITP 19 - R101 Cold Milling | ac045a35-675c-4a3d-a871-18aebff0071f
93ee2f23-86b7-43e7-a208-c4689e1b1b82 | section | Lot Information
59efe9c8-2c5a-4683-bf2a-523bdbf12029 | checkpoint | Lot Information complete
d02b3d2e-802a-5390-9142-be4e0bb3a596 | textbox | Lot Opened On
208600ec-6ab6-5416-8107-e545e50be7c1 | textbox | Date of Works
36be2038-a08b-5f93-a576-780ff420d019 | textbox | Lot Type
63bb7564-3313-5946-8bfb-66d8bb493d5d | textbox | Start Chainage
f896d273-b7c5-5a36-aaf8-54829a69122b | textbox | End Chainage
43d52029-1262-568e-adc4-a2912a959cfa | textbox | Offset
7bec1f10-548f-5f3c-8989-3d3e838d06e9 | textbox | Control Line
b62f88d3-00a2-4035-8d1c-8f9b4f7d0e0a | section | Details
0083ee64-96b7-49f6-b116-dcb5ec5bb414 | checkpoint | 1 - Safety Review
7c428c49-cf3d-5a7f-b747-964c54f32777 | note | Requirements / Reference - Project Safety Plan
a98ff76b-ea82-5c71-b46f-86c3491d837a | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural)
a67f5076-96b5-5510-bd1d-78daa823c145 | note | ○ Required Safe Work Method Statements completed and signed
836d2453-ca38-5f26-b9c0-444f2fb1020c | note | ○ Subcontractor’s safety plan/procedure approved
fa25e97c-97bc-54d2-8104-0634551e2437 | note | Frequency - Prior to commencing works
5e6c9665-5fae-5479-9447-84c6345e1593 | note | Inspection – Engineer Sign & Date: ACPL - W
a0ed4151-f504-5c7a-bf58-6e2750326cb1 | note | Inspection – Engineer Sign & Date: Client - S
54a7d2a1-1a5c-4a5e-8b5e-7fc3ae73d0de | checkpoint | 2 - Environment
c85a2c25-8b26-54d4-a01b-ad348d15436b | note | Requirements / Reference - Project Environment Plan
0b768b1d-8030-56e1-a865-9a70768ba7ab | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
7e5ae78f-2f95-5a49-b67a-39c628a83428 | note | ○ Air quality to be visually monitored for dust etc. as a direct result of construction activities.
3692d27a-f694-534b-85cf-5070e1e111de | note | Frequency - Prior to commencing works
db05bf31-d8d6-5e51-94ed-354c3feb5f05 | note | Inspection – Engineer Sign & Date: ACPL - W
2e8a4fea-ee9d-58ec-9edc-3b4de0e25911 | note | Inspection – Engineer Sign & Date: Client - S
85f238c9-66dd-4483-9023-5adbecdf2419 | checkpoint | 3 - Scope
aa03dda5-64ec-5a00-96e0-25678e529570 | note | Requirements / Reference - R101 Cl1.1
bc3e54c4-07d8-57be-81c8-83dd5862e8d2 | note | Acceptance Criteria - ○ This Specification sets out the requirements for the removal of pavement materials from road pavements and Concrete Structures by cold milling, including the treatment of the milled vertical faces and the cleaning up and removal and disposal of the milled materials.
66f9da5b-368f-55d8-98c3-39b09d6c410f | note | Frequency - Prior to commencing works
cbc7d1a2-3e5a-5d44-8631-1bfe3c5f3a98 | note | Inspection – Engineer Sign & Date: ACPL - S
b17b3227-95ce-5581-a060-2493fcefd5d2 | note | Inspection – Engineer Sign & Date: Client - S
91f1b28e-76a0-4223-ba36-d2f932c83b3d | checkpoint | 4 - Survey of Hidden Objects
247bed36-64e9-51ec-8b59-7e3ab9f4e703 | note | Requirements / Reference - R101 Cl3
00633d2d-cb49-57e3-bd25-fb663ec53838 | note | Acceptance Criteria - ○ HOLD POINT: Submission of verification documentation, the marking of milling depths and locations of all Hidden Objects on site, records
8fb21b54-dfe6-52e9-8fac-33e1706924a8 | note | Frequency - During works
fcb66e18-fa80-5af4-af1a-4381870441c9 | note | Inspection – Engineer Sign & Date: ACPL - H
4a2424db-bdd3-5868-a522-296e2bb2aad4 | note | Inspection – Engineer Sign & Date: Client - H
7b2b4f2b-e590-547b-a35e-eeae35174cd5 | note | Comments / Attachments / Records - Hold Point
ecf4e6c4-f64c-4ee9-b966-2f3becac4df6 | signoff | AUTHORITY HOLDPOINT
4c781261-0fd9-4cce-b829-790276d6b7e4 | checkpoint | 5 - Working Tolerances
bd0d2ac1-60d5-5458-8293-8a3568582460 | note | Requirements / Reference - R101 Cl4.1
c12d262f-edb7-5faa-a39a-64df38f8ad4f | note | Acceptance Criteria - ○ Depth of cut and other dimensions must comply with the tolerances specified in Table R101.1.
dbfc8527-fc89-5f87-a1ea-08310a7da9ce | note | Inspection – Engineer Sign & Date: ACPL - S
2e2cd531-f9d6-574c-98cd-bdec996c69ac | note | Inspection – Engineer Sign & Date: Client - S
bd5087a4-2af9-48bc-9125-7e97c40a52d6 | checkpoint | 6 - Milling to Achieve Specified Depth of Cut
07d49ad9-20ed-5f81-90f1-d2584103d312 | note | Requirements / Reference - R101 Cl4.2
abcd2609-7549-5232-8f26-7df2887b5797 | note | Acceptance Criteria - ○ HOLD POINT: Written notice to the Principal at least 24 hours in advance of the time when the floor of the milled area will be available for inspection.
05942350-2596-5853-9fa5-7a319082bc08 | note | Frequency - At least 24 hours prior to
025afdd8-e501-527a-8be6-ccd91e0d0546 | note | Inspection – Engineer Sign & Date: ACPL - H
5aa160fe-c3e2-5046-b466-8a7afdf2a158 | note | Inspection – Engineer Sign & Date: Client - H
e4590f39-a77c-576b-8054-029b050e714a | note | Comments / Attachments / Records - Hold Point
0c2899b5-9f21-4524-a0cb-6de1a735e2e4 | signoff | AUTHORITY HOLDPOINT
47f94bee-d198-46e1-b901-2b9a141e4529 | checkpoint | 7 - Milling to Achieve Specified Level
83199ce1-c7fa-56f6-b310-203ef0ab5590 | note | Requirements / Reference - R101 Cl4.3
021feea8-b516-5dd5-9e12-43ed3e931405 | note | Acceptance Criteria - ○ HOLD POINT: Survey Report of the milled floor (if specified in Annexure R101/A) and written notice to the Principal of the time that the floor of the milled surface will be available for inspection.
912b7ad1-7772-5977-b97e-5749d48bd31a | note | Frequency - As required
0b3a6023-efdd-5d3f-a0df-59fe36bf3e36 | note | Inspection – Engineer Sign & Date: ACPL - H
e5c59d30-cf89-5032-b89c-a90a7eb583de | note | Inspection – Engineer Sign & Date: Client - H
7c5436ff-ede3-592a-b36d-8946cba2383b | note | Comments / Attachments / Records - Hold Point
b39ff597-aac0-4a93-9ef6-13955b8aabbf | signoff | AUTHORITY HOLDPOINT
fa3ab0d8-cccf-4776-a4c4-4fde23d7796b | checkpoint | 8 - Milling to Optimise Final Ride Quality
49b7e9a5-c624-5751-814f-20af51967951 | note | Requirements / Reference - R101 Cl4.5
4f2f7e12-1556-5087-aebb-d8e7d70de227 | note | Acceptance Criteria - When milling is required to optimise final ride quality, the outcome must be achieved by cutting to an average depth predetermined by survey. The nominal cutting width must be 2 m.
bf610593-6265-54eb-97cc-e91e0bb62a4f | note | ○ The milling machine must be equipped and operated using a minimum 6 m averaging beam or an equivalent non-contact system. Set milling operations to a constant speed and the cutting sequence must start from the crown towards the kerb.
d3c0b333-82c8-50ca-8e24-be46b8b5c2c6 | note | ○ You may propose, and implement subject to the Principal’s prior approval, an alternative method for achieving effective averaging control on the profiler
f9c9a626-e9c5-5e66-9c28-ce66a0185f28 | note | ○ Verify the shape and profile of the milled surface by the use of a 3 m straightedge after each cut. Carry out testing transversely and longitudinally at intervals not exceeding 10 m using Test Method TfNSW T183. The milled surface must not deviate from any point on the bottom of the straightedge by more than 5 mm.
70f9bf7a-acd2-5f37-a9d0-58061093a3e6 | note | Frequency - As required
df23f495-224c-55e2-83fa-54ffc37d203e | note | Inspection – Engineer Sign & Date: ACPL - S
3c425baa-9eb0-5f12-8350-14de6e8730a6 | note | Inspection – Engineer Sign & Date: Client - S
a9c45eae-aca1-408e-8602-066497b721f4 | checkpoint | 9 - Investigation of Thickness of Existing Asphalt over Concrete Structures
e86b84b3-5e29-5e53-abea-9b440bebada5 | note | Requirements / Reference - R101 Cl4.6.1
ae510f2d-0193-52ec-a5ee-5a89cf46b64a | note | Acceptance Criteria - Where the Principal is responsible for the investigation of thickness of existing asphalt over Concrete Structures, the information on thickness of existing asphalt will be clearly marked on existing pavement prior to the commencement of the Contract
50a82a34-6e66-5687-a837-8c0a99e94b3c | note | ○ Where specified in Annexure R101/A, carry out a comprehensive investigation to determine the thickness of the existing asphalt over each Concrete Structure. The Principal will provide you with any available preliminary information, including relevant work-as- executed drawings.
a76b2221-4bbb-55ff-8014-3e7a2f23c207 | note | ○ Carry out the investigation as follows:
86fcbb5b-3c65-5689-9fa3-aca893c61f5f | note | a) Determine the proposed pattern of milling works and mark on the pavement the lines of movement of the depth sensing foot on each side of the milling machine
3e7aad22-63f3-56bd-b939-e0685aba951c | note | b) Investigate the thickness of asphalt by taking small diameter cores (e.g. 25 mm), at 3 m intervals (over concrete bridge elements) or 20 m intervals (over other concrete structures) along each line of movement of a depth sensing foot, at least 24 hours prior to the commencement of milling.
0e41af7d-60f5-5eb4-af3f-d7e2d38c34e5 | note | ○ Submit the findings of the investigation to the Principal at least 24 hours before commencement of milling.
1a488a00-a1de-565d-a1d8-844c3b9491b6 | note | Frequency - 24 hours before commencement of milling
b3e40eb8-1e2c-5a29-adca-9578695f56b5 | note | Inspection – Engineer Sign & Date: ACPL - S
897bee86-ea6a-5b3f-95cd-46e89dbc9f40 | note | Inspection – Engineer Sign & Date: Client - S
25fd1c9b-9328-4d07-9ed8-072df8747dfd | checkpoint | 10 - Revised Scope of Works Based on Investigation
7fdd7372-4c37-50be-8c43-dc25df80499c | note | Requirements / Reference - R101 Cl4.6.2
1f1b8514-9bfa-5ace-b8cd-c22857ae60a5 | note | Acceptance Criteria - ○ WITNESS POINT: Notify the Principal not less than 24 hours prior to milling of the time and date of commencement of milling and the time and date the proposed depths of cut will be marked on the surface the surface
73b3bbc9-2864-5a38-8e90-b48e20b000d7 | note | Frequency - 24 hours prior to milling
0f9d67e1-7bf9-5f4d-b626-a7bf56b0b66d | note | Inspection – Engineer Sign & Date: ACPL - W
14dd42bc-f8f4-589b-aa9e-04cc4256c04f | note | Inspection – Engineer Sign & Date: Client - S
715e7d81-32eb-5a07-a320-1f63bd89d748 | note | Comments / Attachments / Records - Witness Point
5c9ec369-8f49-45a3-bec8-03effdcca628 | checkpoint | 11 - Milling Operations
f3d5a154-e7f5-5124-89ed-c6031243f9f6 | note | Requirements / Reference - R101 Cl4.6.2
0fd02735-649d-5e48-96f4-e39469294391 | note | Acceptance Criteria - Milling operators must have adequate training and experience in the operation of the cold milling machine (including automatic sensing equipment).
f24b1b14-7d3a-5b8b-a688-7ef93f285f5c | note | ○ Submit to the Principal the experience and training records of each operator prior to the commencement of work on site.
5b39e9b9-7cd0-5e9d-b503-02dbb0ed2abf | note | ○ During milling operations over Concrete Structures, provide three suitably trained and skilled milling machine operators at the cold milling machine at all times as follows:
9707a9d1-1237-5c51-90ec-a656ab70ae9d | note | i) One on the driving platform
24e0c1de-f20e-5f14-84bd-fe9fc7d843cd | note | ii) One on each side of the machine generally in the vicinity of the sensor/cutting mandrel
c6cb8870-8eaf-58d1-aa74-73bc18912163 | note | Frequency - Prior to the commencement of works
67e3a150-a200-554a-ad50-a77691121b9c | note | Inspection – Engineer Sign & Date: ACPL - S
24743873-3beb-5d44-b220-284d44474ac5 | note | Inspection – Engineer Sign & Date: Client - S
2b582237-c9b3-44b4-8b69-16167c691d06 | checkpoint | 12 - Milling Procedures
32931791-1118-5530-b04f-8c20051c47f2 | note | Requirements / Reference - R101 Cl4.6.5
e09659be-cf3c-5b38-8b86-8742f30d8282 | note | Acceptance Criteria - ○ HOLD POINT: Written notice to the Principal together with proposed procedures for the work at least 7 days (except for Clause 4.6.2 where it is 24 hours) prior to the commencement of milling work
e7806e73-a513-563b-85d6-e6bee9bd515a | note | Frequency - 7 days prior
76a63d6f-6f19-5ece-967d-e1a11f6ab328 | note | Inspection – Engineer Sign & Date: ACPL - H
b9360d9e-35d4-598f-941c-859c7e224950 | note | Inspection – Engineer Sign & Date: Client - H
715ebd03-b67e-54f7-9f8d-def383bd1539 | note | Comments / Attachments / Records - Hold Point
b1d67f79-8545-4c6d-a09c-44fe66be49c4 | signoff | AUTHORITY HOLDPOINT
b3c2a183-1612-4bd5-b104-04da7e1e0685 | checkpoint | 13 - Operation of Cold Milling Machine
0d3ab246-727e-554b-937f-1872026d6207 | note | Requirements / Reference - R101 Cl4.6.6
f960fc74-11af-5147-a154-cd0f3e3be492 | note | Acceptance Criteria - Do not use cold milling machines to correct the shape, level or ride quality of the surface of Concrete Structures unless specified or specifically directed by the Principal.
7ae87a34-36bb-556e-957d-46b677cc9575 | note | ○ During the operation of cold milling over Concrete Structures, take all necessary precautions to prevent the cutting teeth from contacting the concrete. Measure the actual depth of cut on both sides of the cold milling machine at intervals not exceeding 3 m (over concrete bridge elements) or 10 m (over other Concrete Structures).
1216b2cf-9d36-5abe-accb-00feca1c63d4 | note | ○ HOLD POINT: After the cutting teeth have contacted the concrete, notify the Principal immediately of the incident and submit details of the cause and the proposed course of action
2689fb09-a740-5f0d-b099-28d54686b2e4 | note | Frequency - As required
141bae7a-eb3a-5313-bc8e-88e089a1240b | note | Inspection – Engineer Sign & Date: ACPL - H
6903bfba-096c-50cb-80ca-31602a1f04fb | note | Inspection – Engineer Sign & Date: Client - H
e75fed4a-1edf-525a-9293-35f2952084a2 | note | Comments / Attachments / Records - Hold Point
d7e89e5c-9ed5-4131-a477-c3b55e073cda | signoff | AUTHORITY HOLDPOINT
ea1a06f3-d8cc-49e9-a595-aa8572e22e33 | checkpoint | 14 - Operation of Cold Milling Machine
5df4eb5d-8fb8-5059-8609-3dd897b8bb56 | note | Requirements / Reference - R101 Cl4.6.6
779948c6-abe8-5f11-bd90-94256d1eb893 | note | Acceptance Criteria - ○ Hold Point: After any change to the pattern of the cut surface due to broken or worn cutting teeth, notify the Principal immediately of the incident and submit details of the cause and the proposed course of action
7075a5d3-1c0b-51b9-89cf-6f4bcc9f8795 | note | Frequency - As required
d1b81405-1e45-5279-8618-6913bf9c3140 | note | Inspection – Engineer Sign & Date: ACPL - H
9c6c1125-a3d3-5d87-8291-f7d798ea066e | note | Inspection – Engineer Sign & Date: Client - H
47139028-6b6b-5201-819d-b93b3f0ba423 | note | Comments / Attachments / Records - Hold Point
0d8ad7c9-e6cf-4b3b-83e4-b11bfdf804da | signoff | AUTHORITY HOLDPOINT
ab1f1255-1bdf-44c0-8da1-47405b54f534 | checkpoint | 15 - Work in Vicinity of Object within Milling Area
7e5a6946-8d1a-5080-835d-557c985246be | note | Requirements / Reference - R101 Cl4.7
48b4af8c-9497-52ec-a4ab-b03fee576730 | note | Acceptance Criteria - ○ Where objects are located within the proposed milled area, remove the surrounding material for at least 0.5 m from the extremities of the object by means other than cold milling.
9e92702a-ca47-547d-8659-4e8fd6861a8e | note | Frequency - Prior/During Works
1e7369cd-22c5-5f52-be3b-a05618f6171d | note | Inspection – Engineer Sign & Date: ACPL - S
49d28a72-f6a4-51e7-a61a-75850ab47201 | note | Inspection – Engineer Sign & Date: Client - S
cc44e025-f054-4d8e-ab45-1a424b332a90 | checkpoint | 16 - Unsuitable Material
62ccd8d9-9f2e-5d1d-9d9f-007583fa167f | note | Requirements / Reference - R101 Cl4.8
acfbfaff-e97d-5a43-8452-d1dc9896746f | note | Acceptance Criteria - Remove any planes of weakness within the asphalt, cement concrete and/or pavement materials, or any unsuitable material existing at the base of the cut, which is not removed by the milling operation to the extent directed by the Principal.
66986f8a-a5e2-5e2a-a1aa-c5e54b8fa6d1 | note | ○ HOLD POINT: Written notice to the Principal of the time that the removal of the unsuitable material will be completed and be available for inspection.
fcb02b9e-01c1-51d6-8b7a-6648a35a8b3b | note | Frequency - If applicable
a740156e-edb1-57ea-88d3-964b5e4e2be5 | note | Inspection – Engineer Sign & Date: ACPL - H
553ff5a3-5781-52b4-a701-aaf8f100132c | note | Inspection – Engineer Sign & Date: Client - H
846da83e-be55-5c70-b77b-739e7cbd86eb | note | Comments / Attachments / Records - Hold Point
3c327376-0084-42aa-a1bd-8ee654d1fcaf | signoff | AUTHORITY HOLDPOINT
c2610cff-fe0d-49ad-9e8c-223a13fc12dc | checkpoint | 17 - Temporary Treatment at Edges of Milling
306d280d-d7cd-580b-9927-e0367b1b43ed | note | Requirements / Reference - R101 Cl4.9
a4bc3e9e-3fdb-56ed-943e-6c782b0f810f | note | Acceptance Criteria - Prior to opening of the work to traffic, ramp the edges of the milled surface to tie into the existing road levels. The dimensions of ramps must be as follows:
330cb07b-4f17-599e-9157-fa42a2b8e0aa | note | i) Transverse joints
6472f7d2-1d13-5c77-880b-b6c8163d0381 | note | ii) Longitudinal joints
2bb477db-eff6-51ae-b85d-97a2de8892b1 | note | iii) Interface with structures
a0215ec1-3589-5238-a7b7-ba76141b44da | note | ○ Form the ramp by either bevelling with the cold milling machine or by placing asphalt.
5dd40ddd-5028-543f-a669-39adcf8e6127 | note | Inspection – Engineer Sign & Date: ACPL - S
5f18d9a1-6181-5d79-a15c-6846b431a917 | note | Inspection – Engineer Sign & Date: Client - S
4df3f816-c65f-434b-9011-e13cf622c426 | checkpoint | 18 - Clean up & Disposal of Milled Materials & Temporary Ramp Materials
e2111149-6a00-51a1-9ef8-0363458da75d | note | Requirements / Reference - R101 Cl4.10
a61f5de8-dc13-5dd1-a8db-9d3f11d839b3 | note | Acceptance Criteria - After final sweeping and prior to the work being opened to the traffic at the signposted speed, the number of loose aggregate particles determined in accordance with TfNSW T277 must not exceed 20 particles per square metre. The test location must be representative of the section and as agreed by you and the Principal.
d54277e9-1499-55b9-91bb-7e636eb1d8f2 | note | ○ HOLD POINT: Notification of the time and location prior to commencement at least 24 hours prior.
9558e676-e61b-5ef3-8ed3-2071629ec286 | note | Frequency - At least 24 hours prior
6052516e-e180-5fff-b698-8f92d8ae57a9 | note | Inspection – Engineer Sign & Date: ACPL - H
47ff038b-c08f-532c-b1cc-95fccc402558 | note | Inspection – Engineer Sign & Date: Client - H
391d3316-a01b-5d31-8c45-3d689e9c37ed | note | Comments / Attachments / Records - Hold Point
dcc32306-d1d7-4f06-8c26-f03008e4589a | signoff | AUTHORITY HOLDPOINT
81ae6b29-d669-46ae-b050-67faf474097f | section | Review by Project Engineer
9892f718-e40c-484d-b62a-1a66324c4c6b | checkpoint-no-value | Review by Project Engineer
bcf80f03-c699-5872-a91d-d6bddb7d1aa3 | button | Any non-conformances? | YES, NO
6cbb3477-5053-5707-889e-58a939b181ca | textbox | No's:
1ac4fcbd-1fad-5ef6-9a43-86cecafe5684 | button | Closed Out | YES, NO
f28d2791-0a62-5cf8-8515-2c5f57212083 | button | All work has been satisfactorily completed. | YES, NO
96c09adc-7aa8-5f52-ba8f-00dbb9525f58 | textbox | Name:
4200a24c-2796-4c22-9eab-81ba78726c0b | signoff | Add signature
b82a33b7-91ec-4700-9746-db97dba39c03 | section | Lot Verification
87fce023-4821-4a8f-93cc-7a64eba75bb5 | checkpoint | Lot Verification complete
a5f68dc8-110c-5446-bc2c-87918447ab84 | textbox | Lot Verified By:
289f3fc5-96e4-569b-a8e4-544c1aaf38b3 | textbox | Lot Closed Date:
4e1be15a-305d-5a56-9a42-08e7d1e86ce1 | button | Submitted to Client | Yes, No, N/A
d4b5f242-707f-5350-8531-f931cba32ec6 | button | Reviewed by Client | Yes, No, N/A
4c97fce0-3aac-5652-a8e1-f02161c3977a | textbox | Submission Comments:
cc91fa82-110f-4b2c-b879-7d016a0d784b | section-nested-checklists | NCR
45ed03f2-5a90-443c-be17-1d80df3aa8fa | checklist | ITP 34 - B30 Backfill of Structures | itp | ITP 34 - B30 Backfill of Structures | cdf20955-e75a-42df-8305-a6b0a11e8b53
de456f72-fb8f-4d9b-bbb8-cc9326fb74fc | section | Lot Information
25181b97-f746-4a81-83c4-207e147840bc | checkpoint | Lot Information complete
b73396df-20f7-5acf-80ce-9f8f56c240f1 | textbox | Lot Opened On
64c00a0a-629c-5a18-8351-09189793df99 | textbox | Date of Works
34b1a2d5-3cff-5329-a0bd-35572e08be2b | textbox | Lot Type
838a4de7-df04-5c64-9ce6-13f1ec062753 | textbox | Start Chainage
35ba25d6-ebf1-5f71-af0d-7af30b3124f5 | textbox | End Chainage
71c08d27-1ed1-5d6f-aa42-2bdd8462bff7 | textbox | Offset
402836d9-c76a-5d8b-8a9a-327c7d5669f4 | textbox | Control Line
5ea0136b-5983-4ab3-b5b1-e0e4ab488ac6 | section | 1. Preliminary
e8252c27-dc37-4493-b7df-d986f52dda96 | checkpoint | 1.1 - B30 Material Approval
9684de98-065d-5e89-b52f-f711d092b75f | note | Requirements / Reference - B30: cl 6.2.1
4d3366cc-097b-5c40-ba88-bced730fe5c7 | note | Acceptance Criteria - Select Backfill for Structures
b558a7f5-9173-5129-8dd4-511b1946d8cc | note | Chemical testing -
7ec503ff-bda3-53bc-ae8d-af5ff4ac8a62 | note | ○ pH >=5.5
2f84e80a-9b97-5360-99a7-e662c5394479 | note | ○ S04<=1000mg/L
18686ef4-df92-51fb-86fa-02ec225a6238 | note | ○ Chlorides<= 200mg/l
1d1629cc-7033-5b98-a0c2-33c210d01cd0 | note | Particle Size Distribution -
8ad0b994-1f1b-5ee5-94f8-3e6f3cbac9f5 | note | ○ As per B30 table B30.2
21fc3b26-55cb-5c27-9f54-5e795df06d0a | note | ○ Coeff uniformity >=5
7b99e2ed-b375-503d-b0a0-0201ecbf8704 | note | ○ PI<=15
455c8c30-317e-5a89-80aa-81737a5fb379 | note | Notification / Frequency - Per stockpile. 1 test per 500m3
9bd7840f-7562-5376-8a2b-e7a13158bcfd | note | Inspection - ACPL - H
fbd533e0-89ee-5f95-bb85-232f89fe3f37 | note | Inspection - Client - H
3ffc6595-f4a6-4d18-9460-eafe3f9d13e7 | signoff | AUTHORITY HOLDPOINT
6ef90d38-bdd2-406f-a61d-0cdf0333b91f | checkpoint | 1.2 - Age of Structure and B30 Extents
ef0fea7b-6c18-591e-9dfd-1d60e86dd432 | note | Requirements / Reference - B30: cl 6.3
712f034e-39a2-5950-ad84-26b7b8b47bb7 | note | Acceptance Criteria - Age of structure
39476e53-2b36-55a7-bfa8-a9de329e8619 | note | ○ Wait at least 7 days or 75% of the specified minimum 28-day compressive strength of the member is achieved before commencing backfilling of structure.
8ca5d8f9-fd13-58d9-b955-dfd7d6eff64a | note | NOTE -
439b1308-b33a-5ace-85ce-d79d2668dd09 | note | ○ Date last pour on RW1/Abutment B: 22/10/24
2c44d1a3-8a77-5c79-b444-8bc74f9fa6ed | note | ○ Date start backfill RW1 Abutmnt B:27/11/24
2bf2faf6-28a7-573b-9dd1-3b25400af698 | note | ○ Waiting period: 5 weeks
09a3aeb6-e391-551f-bd8b-e0956534dea4 | note | ○ Date of last pour on RW2: 19/11/2024
5ff79230-9646-5e15-b177-0e82b417c5ff | note | ○ Date start backfill RW2: 16/12/2024
8f673f73-0ea8-53c1-8771-b6fa8fc4b667 | note | ○ Waiting Period: 4 weeks
22c11de2-42e6-5bb9-aac6-e601febba03b | note | B30 Extents
7568ad90-376d-5c57-adc9-e931f22b53a7 | note | ○ Ensure excavation will allow backfilling of B30 within a distance of H/2 from edge of base slab, where H is the distance between the base of the footing and the top of the wall as indicated in B30/E
3e0f48ac-e400-5473-ba3e-9cafecc6d62f | note | Notification / Frequency - Once per Structure
be2117fb-6e59-5bea-8f2f-bfd99249e198 | note | Inspection - ACPL - S
52d0a13f-20f0-4bea-b429-bd1593dd75f5 | section | 2. Construction
954e07a7-b267-4058-ab41-3cb2c4d4cb15 | checkpoint | 2.1 - Backfill against several sides of a structure
da25e411-7615-59da-bd88-5c47a3edd3ef | note | Requirements / Reference - B30: 6.4.5
dc0524a5-d6e4-5ec5-99cf-49ce9544bf1b | note | Acceptance Criteria - Real time monitoring of the Abutment during the B30 placement
0c9b350a-139c-5f37-b66a-15ab9d22ea5f | note | Notification / Frequency - Per Lot
1cc1819f-453c-5940-8fef-68ef955a13d0 | note | Inspection - ACPL - S
ac4195c7-30a6-4e0c-a978-dd13458b039f | checkpoint | 2.2 - Placing and Compaction - B30 Select Backfill
c7a8d11d-03bb-53cc-b2fd-03a12c871a41 | note | Requirements / Reference - B30: cl 6.4
02089f92-544c-5e43-ac5e-aef47b26d4cf | note | Acceptance Criteria - Moisture requirements:
84344920-5aa9-5240-8be3-20e8b07f2ef8 | note | ○ Moisture between 60-90% of OMC
26d33e13-546f-524d-b7f2-620ffd2cb472 | note | Compaction Requirements:
2453cfd4-cea1-5e62-8426-3a880c0c056f | note | ○ 98% relative compaction using T173 and T166 and determine characteristic relative value of compaction per Q6.
1cfcfc22-325d-5410-82dc-0216bd1edcdf | note | Notification / Frequency - Per Lot
4fe5b154-a325-51a2-8e72-f073d260eeba | note | Inspection - ACPL - H
9eacc520-8b6d-5618-8f6f-3fa193bcfdfa | note | Comments / Attachments / Records - The greater of one test per layer, or one per 50m2 or one per day
ae144896-3ec7-4021-8fae-e07aed426185 | signoff | AUTHORITY HOLDPOINT
b1c07b46-5fd6-40b5-9704-870052cba6a7 | checkpoint | 2.3 - Maximum layer thickness- B30 select backfill
877fc018-001d-56b3-8481-72e07be0c9c9 | note | Requirements / Reference - B30: table B30.5
844cea2d-5c14-531a-abba-16d5649072ee | note | Acceptance Criteria - Maximum layer thickness:
01e7905d-24d6-5ef6-a429-c3a54c887a2b | note | ○ 150mm
ee7f3d2e-0276-5fc5-b80d-e7898ad1b8be | note | Notification / Frequency - Per lot
205ffa7b-1c19-5b40-8e14-9c60876a11ae | note | Inspection - ACPL - S
bbdb8f68-3a3c-48c0-839b-cf472678f7a7 | checkpoint | 2.4 - Drainage Zone behind the retaining structures
9a82ab71-0a15-551c-939b-9de2c88a0931 | note | Requirements / Reference - Cl. 6.5
4f00ec3f-6a28-5ff8-80bb-75b1a89b91c6 | note | Acceptance Criteria - Installation of Drainage Material (Strip Drains)
e288a1c3-a1b0-5d26-aa0b-68f4e2a01ee8 | note | Notification / Frequency - Per Structure
1e965e8d-8ae7-5a8b-920a-55a8b94ead7b | note | Inspection - ACPL - S
8302a312-ced3-4486-ac93-1c3fa20621ab | section | Review by Project Engineer
84735865-4ccc-42d1-a1ec-4ecdc7bc2c61 | checkpoint-no-value | Review by Project Engineer
930918bc-d6ff-5be5-81ce-dd67c4f42ace | button | Any non-conformances? | YES, NO
e440d9ee-b9a0-5aec-a8a5-0acba49abc79 | textbox | No's:
f3cac2ac-bff0-523e-905a-df4114ea89bc | button | Closed Out | YES, NO
ef5d810f-9bbc-57e4-82e2-1800d8a29462 | button | All work has been satisfactorily completed. | YES, NO
4bf28fd2-8475-5f89-9244-1ef28125444e | textbox | Name:
5cf7bc27-eb58-4395-a5da-13969a7a4227 | signoff | Add signature
40406bab-5dfa-48bd-af74-fb0f13b7000a | section | Lot Verification
1ec44e53-e58d-4ea6-ae15-8b71c1147b60 | checkpoint | Lot Verification complete
0a12e718-4aa1-594e-b330-17295af8437d | textbox | Lot Verified By:
bce00240-a263-5908-9f61-ed48431c2ff2 | textbox | Lot Closed Date:
6f9d5020-1dbb-5545-b9ee-c43980833606 | button | Submitted to Client | Yes, No, N/A
4afd4d3a-07ac-5b45-94e6-62d3959d94bf | button | Reviewed by Client | Yes, No, N/A
5de0548f-552c-5f2a-a65e-3e397f9a60ae | textbox | Submission Comments:
2d7214b2-ddee-4cd1-b449-818f53030eb9 | section-nested-checklists | NCR
| checklist | ITP-B1.4 - Piling Pier | itp | ITP-B1.4 - Piling Pier | 4678568f-fa8a-431f-8a37-a5620a226673
| section | Lot Information
| checkpoint | Lot Information complete
1940faf2-285a-428e-b088-d736b15ebd0f | textbox | Lot Opened On
e99a9414-3dde-4db4-8a88-4a43cf02d547 | textbox | Date of Works
6248a533-8e87-4b37-b68a-5046cd610de2 | textbox | Lot Type
4fd1fbf0-972c-4274-87a0-ddff07b39d22 | textbox | Start Chainage
3d781f14-4c66-4329-8420-6f3b7d45e1d5 | textbox | End Chainage
a6765a7b-4067-402a-be31-45f47d0e4281 | textbox | Offset
601c5021-4da2-50a4-a3a9-77fc7d55003f | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
f78c4683-5d8e-50d6-a90c-1955d6c95f96 | note | Requirements / Reference - Preliminary Works (Piling) ITP
76c99725-fe68-5f8d-8b31-41098624cbf1 | note | Acceptance Criteria - Sign-off of ITP-B1.P Piling Preliminary Works ITP
ce8399b5-d584-5937-9d95-07cd89cbac0e | note | Frequency / Process Held - Once / prior to construction
37c234f3-505e-5112-b291-5832ccb842ca | note | Inspection – ACPL - H
d3a5b390-0ab4-5b84-88d2-5d391c0948ee | note | Inspection – Client - H
bb922e6f-fadc-505a-bcc0-23184eb77fc5 | note | Comments / Attachments / Records - Preliminary Works (Piling) ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Check Drawings are IFC and current
47bc4ead-fd75-5afd-92fb-01e776ad7c34 | note | Requirements / Reference - A182600-JAC-DD-BR-DRG-1001 - 1013 AS5100
cb3132a4-517a-5caa-94ab-31e9536d6efb | note | Acceptance Criteria - Drawings IFC, Current and Correct
e9060146-016c-5750-9437-4b5fd7b253f9 | note | Frequency / Process Held - Once / prior to work commence
b7862825-9f8c-5af5-a552-79f459691727 | note | Inspection – ACPL - W
dd8642a0-d8f7-5871-8225-fd5fd013b462 | note | Inspection – Client - S
192a950a-5533-5529-b3de-ba6238ad99a2 | note | Comments / Attachments / Records - This ITP Drawing register
| checkpoint | 1.3 - Transport of Fabricated Steel Items to Site
cb9c3b61-ab80-56a5-b146-35e6f7797b44 | note | Requirements / Reference - B201 Cl 6.11
20482190-f80e-5d3f-950b-8104758d0fda | note | Acceptance Criteria - As agreed, QA checksheets can be submitted to release transport of casings, with FDRs submitted afterwards. See below table for sign-offs of all casing sections.
c026799c-5ac4-5d52-a371-1b39e6ab7f71 | note | Frequency / Process Held - Per Delivery / 1 day prior to deliver
92c92fcf-80e0-579a-8d4b-a21533682771 | note | Inspection – ACPL - W
ef9643db-4e87-5380-96a2-c1437e09d99c | note | Inspection – Client - W
9ee3b48a-83ec-51e9-8623-d3649e404509 | note | Comments / Attachments / Records - QA Checksheet
| checkpoint | 1.4 - Certification of Completion of Fabrication
c63e8855-dd4e-5e9e-bfff-61142d554c81 | note | Requirements / Reference - B201 Cl 15
989418e1-fe6a-5c60-ba4b-31054ba7301b | note | Acceptance Criteria - Fabricators Data Report submitted for relevant casings prior to work commencing. Refer to table below for sign-offs of each casing section.
d6a5024b-2c44-5562-a303-daf4483ee82d | note | Frequency / Process Held - Per Casing / prior to driving
3e298626-77af-52cf-9af3-2a637921cfc8 | note | Inspection – ACPL - H
c1f29f8e-d429-5e97-8fd1-93bd31a4532d | note | Inspection – Client - H
ccd56823-17e7-5627-90ad-c66b6fbd6648 | note | Comments / Attachments / Records - Fabricators Data Report
| signoff | AUTHORITY HOLDPOINT
| section | 2. Construction - 2.1 - Pile 22
| checkpoint | 2.1.1 - Marking of Piles
cb9d5830-a6db-5421-b1be-54cd5410fc4d | note | Requirements / Reference - B54 Cl 2.9
749063a9-bac8-568d-a715-b06f7aa52250 | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
9deac658-bf75-5523-b60f-668f1e065693 | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
daba1aab-cb1e-59f5-8f11-dac6604ae0c2 | note | Inspection – ACPL - S
69fa1d12-82f3-5c2a-b889-8da4a7ae7481 | note | Inspection – Client - S
27bd00d9-75ef-516f-b3c9-b41729a154fc | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.1.2 - Survey set out
11e98987-31aa-53f8-b80e-36706e44d352 | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
ebf92df6-ab6b-581e-9bb7-9d144c4ffff8 | note | Acceptance Criteria - Survey set out as per design drawings
37d2d2c0-e958-57ba-b1f2-dc15387c2a8e | note | Frequency / Process Held - Each Pile / prior to driving operations
e2d3178e-06e0-5966-a983-0d088f74e4e0 | note | Inspection – ACPL - S
fc2c9969-3441-5e18-9b44-1b1a97669ede | note | Inspection – Client - S
9b8dfb07-a197-534e-b46e-cc8a47259ae0 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.1.3 - Verify Correct Casings prior to Driving
b60738df-4c0c-507c-af71-510a43625d63 | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
4b91bcda-001f-5bdd-b24f-4207931c05d1 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
99dfda23-6d16-5c12-b8fc-b21fb44a473c | note | Frequency / Process Held - Each Casing / prior to lifting of casing
8f389e5b-06dc-5948-970b-bd23560aac00 | note | Inspection – ACPL - S
80492fbc-de86-5af8-ae0c-8244b288c6b5 | note | Inspection – Client - S
d4cf6c3b-dfbd-51f4-9427-2e1fa7a5e922 | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.1.4 - Pile Driving
df04d83c-201e-5190-931c-de8e03ce39fd | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
7cc2467e-81d3-5d4e-9019-d7fae60baae2 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile. Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 23) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
80902ad9-1117-52a5-b27b-ff61ed0f5c5f | note | Frequency / Process Held - Driving of each pile / one day prior to driving each pile
aecc35c9-426c-5ab0-9fea-4f30ce6a5bc5 | note | Inspection – ACPL - W
2a78edd3-2971-5021-9939-4f66c3731672 | note | Inspection – Client - W
df511629-6657-51ed-bd02-c2f2bf75af6b | note | Comments / Attachments / Records - Driving Record Sheet
| checkpoint | 2.1.5 - Splicing of Piles
aaf7ace2-ccde-5e8d-b438-32d7060701e7 | note | Requirements / Reference - B54 Cl 2.6 B201 Cl 13.2
a37abeb8-707a-5e37-a70f-77a69555dc9e | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
20580d45-bb4c-55fd-8793-23f78dcc3818 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
6c27d9d9-fa0b-5bfb-a35a-75cce6607a79 | note | Inspection – ACPL - S
663ec995-39b8-5c08-b61e-fd0bf825e554 | note | Inspection – Client - S
e2ffa993-e3dc-5221-a874-b1c32a293dff | note | Comments / Attachments / Records - Weld Test Results
| checkpoint | 2.1.6 - Backfilling of Pile shaft
d7ec2a65-5fb0-55ec-ae88-d6d52df20871 | note | Requirements / Reference - B54 Cl 11.1
52d149a1-f08c-5632-8139-2a622b1d116d | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
5815cfa9-9473-588d-a0ce-82970595d2c7 | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
df978160-57e2-567d-af20-65ce87214a49 | note | Inspection – ACPL - H
b8ca664f-8833-58f3-8636-35d65470bf81 | note | Inspection – Client - H
17952472-efaa-5075-a6ae-ac01db92f4b9 | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.7 - Placement of Mass Concrete Plug
48a73cf6-dde3-5af6-b37b-75cbf432ca5b | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
88419c85-2f73-563e-a417-1c04f298b419 | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
e3768562-757d-5650-a89e-adda0f2b4e34 | note | Frequency / Process Held - Each Pile / prior to lifting of reinforcement cages
796812d6-c39d-545f-9dc2-679b3def7052 | note | Inspection – ACPL - S
80b9eb64-ae54-5593-a7ec-21f75e7c5961 | note | Inspection – Client - S
78a8f883-acec-5a6b-96eb-611e94251686 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.1.8 - Assembly, lifting and transport of reinforcement cages
7d33277f-4fa9-5a20-ade6-c02530429e05 | note | Requirements / Reference - B201 Cl 6.6.2
8ac90c7b-bdf5-5f35-aa73-3833570ffd48 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
76fce460-275a-5dca-a0de-abc3a1cec972 | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
fbe762bd-2e3d-5fda-a5b0-77d408426bb7 | note | Inspection – ACPL - W
512b356c-c9a6-5845-a443-bdb1602aa081 | note | Inspection – Client - W
328bb9b6-4a6a-5e7c-a577-fd571de5e21d | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.1.9 - Placement of reinforcement
0ebf17a4-669c-5dde-9591-d2ae24acce38 | note | Requirements / Reference - B54 Cl 11.2
20b249b3-3549-56c1-ae1e-502a85eb549e | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
94384b89-cc5c-549d-838b-804c48472683 | note | Frequency / Process Held - Each Pile / prior to concrete placement
cea93578-66f1-50a6-a8c4-9d88a9ffffc9 | note | Inspection – ACPL - S
d37b5e90-0397-52a5-8301-ae23452dc619 | note | Inspection – Client - S
49223381-086d-54c1-8f59-6ab1ef4acb8c | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.1.11 - Certification Prior to Concreting
7377921b-8fe9-5614-a2a3-38e104b1396a | note | Requirements / Reference - B80 Cl 7.5.1
4235328d-8b6f-514b-a134-d6ec88591c3d | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
67190c95-fd6c-54c2-8458-ccded06618dc | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
4b564831-7667-5334-919a-788c05d8da10 | note | Inspection – ACPL - H
17b37f8c-ad9c-5618-8286-2a36e59c849f | note | Inspection – Client - H
a6af3389-05dc-55a5-a858-7bc5c3c99ab6 | note | Comments / Attachments / Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.10 - Concrete Sampling
5ffa3411-1205-5f9d-bd51-dc40adeb45e2 | note | Requirements / Reference - B80 Annexure B80/L
e76103cd-4fc0-534c-9289-1d38e368040f | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
9b02a593-a474-54ca-8462-f82d2e9676bb | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
2311b33b-9e3e-59e3-ad42-49e257187f8a | note | 1no. slump test per batch of concrete 550+/- 50mm
010432b8-5301-5351-9752-d9b65f09a748 | note | Frequency / Process Held - Each Pile / prior to concrete placement
ef407ee7-8e73-5b14-aa52-bd13c6fba8fd | note | Inspection – ACPL - S
a974b99f-3736-532a-a59a-e988886148e4 | note | Inspection – Client - S
969bad13-78c6-5e0b-848b-eef998629b99 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.1.12 - Concrete placement
49dade46-57f0-5b79-9fa9-ddaa187e1130 | note | Requirements / Reference - B80 Cl 7
90cfd99c-1ae7-5bfa-80aa-11e16f2619c1 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
6fba2086-4f45-5306-8efb-5cc8e473eff1 | note | Frequency / Process Held - Once / prior to cutting of concrete casing
76735e02-038b-5780-b7d0-649a7cb45c36 | note | Inspection – ACPL - S
c16ee6c3-4231-5c1e-a56a-f8cc415e206c | note | Inspection – Client - S
dc4be827-6253-561c-88ec-7e61a11fc435 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.1.13 - Cutting of casings
21b02d7b-83af-5285-b356-519014f47695 | note | Requirements / Reference - B54 Cl 12
30ac2a18-4c6c-5f83-8781-75b64cef3eae | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
4f425c4e-319c-5dd3-9842-28c1df688119 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
60960b1b-066c-5ecb-bdaa-92d79d8571f4 | note | Inspection – ACPL - S
378db71c-d870-5ebb-a803-2f81d1523b44 | note | Inspection – Client - S
891ef15a-d251-502c-b284-25dc5a01a409 | note | Comments / Attachments / Records - Photos
| checkpoint | 2.1.14 - Concrete curing/Sign off
ab97c16a-840a-5de0-bbf0-f1e67cc606e7 | note | Requirements / Reference - B80 Cl 8
60d7be05-f69b-5efa-92f5-f203fc31b82e | note | Acceptance Criteria - Min 40mPa at 28 days
a45a9bdc-f335-5294-8919-ada4719f0282 | note | Frequency / Process Held - Once / Pile Cap FRP
83caf156-3976-50f9-8cf7-30e0712567fb | note | Inspection – ACPL - H
9b00e1f2-df26-59ec-9193-440dfd00489f | note | Inspection – Client - H
9e3cd0ab-48d2-59cc-a736-099ec268550c | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 2.2 - Pile 23: Representative Pile
| checkpoint | 2.2.1 - Marking of Piles
72b9de1f-a811-5fc8-bf1c-faf0c56dba28 | note | Requirements / Reference - B54 Cl 2.9
975a95d5-7e73-52d7-b148-9759d449188d | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
60e860f3-724f-5e49-abde-0878fa123326 | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
bb761d4d-bab9-538d-917a-a910853beb27 | note | Inspection – ACPL - S
731e92ef-46c8-5584-ac82-17def430185c | note | Inspection – Client - S
c45847ad-eb14-5402-85ce-b17e4fc58a81 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.2.2 - Survey set out
078dfb09-9772-59e4-84f6-d50681433aa1 | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
5a2a11eb-04c3-5052-8bd3-2304a4e8e805 | note | Acceptance Criteria - Survey set out as per design drawings
0dcef4fc-8633-5155-8c84-24128440bd5e | note | Frequency / Process Held - Each Pile / prior to driving operations
3a81bd26-27ba-5ee0-817e-d5194f8d2033 | note | Inspection – ACPL - S
589d648b-c7fd-58f1-a5fb-ca4cff9b5960 | note | Inspection – Client - S
254957a4-f3ff-5a2f-93f3-f95ca75b2f41 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.2.3 - Verify Correct Casings prior to Driving
302d1ee9-35ac-5e9f-908e-cc90b7e8f45c | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
3abb07b6-7e6f-5f26-b6ae-972fcdd0515a | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
f1995ac2-4366-5528-b16e-c047ddfc083b | note | Frequency / Process Held - Each Casing / prior to lifting of casing
6fe51da6-1598-5662-a92b-40963b412338 | note | Inspection – ACPL - S
47208913-b1bc-5e8e-934e-c2c95a80f1eb | note | Inspection – Client - S
3456fcd9-3e16-555b-a928-3a5e9063b64b | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.2.4 - Driving of Representative Pile
9e4c40fa-a9d3-5b7c-b14c-320c42d72524 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 8
f08ef386-e4f4-5c4e-b466-7c4e12a6dc87 | note | Acceptance Criteria - Notification of the time and location of the driving of each representative Pile. Representative pile driven to nominal refusal in rock Record number of blows per meter over the whole driven length. For the last 10 blows, record the final set in mm and the average Temporary Compression per blow. Perform Dynamic Testing over whole length of driven length of Pile
e7832cc0-b969-5455-b2d2-f11d1dc0fc74 | note | Frequency / Process Held - Each representative pile / prior to restrike
3f871da5-aed5-5569-bfc9-38bc8e9f66d1 | note | Inspection – ACPL - H
798cf151-d2b8-523c-aa70-be31d5cbbe81 | note | Inspection – Client - H
bc482ef7-184f-5d06-a248-0cb8f14c9a9c | note | Comments / Attachments / Records - Prior Notification of Driving Driving record Sheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.5 - Restrike
4c2f5b1b-d660-5b9e-b196-4fdf1b7131fa | note | Requirements / Reference - B54 Cl 13.3
817a22ec-ecab-5607-a642-f7f5f7dafb22 | note | Acceptance Criteria - Restrike required on all test and representative piles. If restrike fails, perform additional restrike no sooner than 7 days after completion of piling and prior to any concrete infill
a805296a-4810-5ba5-bd9e-3476449fe3a0 | note | Frequency / Process Held - Each representative pile after 24 hours / prior to splicing of piles
d9084e31-9aa1-59e2-9279-e07b69c2d2af | note | Inspection – ACPL - S
38adab70-0358-51df-8b66-6058b646463c | note | Inspection – Client - S
a1c4403d-e7df-555b-9751-10e97ad76e4c | note | Comments / Attachments / Records - Driving record sheet
| checkpoint | 2.2.6 - Splicing of Piles
61c858f1-d531-5680-a570-4813d89690d6 | note | Requirements / Reference - B54 Cl 2.6
c7f6a154-adca-54ef-9043-f030a311790e | note | Acceptance Criteria - Where pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
03018ca7-0c75-59e2-a186-30a68576d320 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
6e14dbca-a637-59f0-8d5b-6f29b146bf55 | note | Inspection – ACPL - S
48819737-bcc4-508a-82f8-2c8a8ce3ea5f | note | Inspection – Client - S
76a44468-05a8-52fb-ae43-8d66e82a6308 | note | Comments / Attachments / Records - Driving record sheet
| checkpoint | 2.2.7 - Backfilling of Pile shaft
c5e611ae-c313-53b7-8251-1197dd28e446 | note | Requirements / Reference - B54 Cl 11.1
dd245cd0-2f51-5d47-87f9-da8d31265485 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
1c84c303-3347-59f7-ac6c-e6ac35187d07 | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
7650b059-8311-5327-8a61-fd0abbbb420c | note | Inspection – ACPL - H
2dc7e97a-5136-55f2-a77e-80e333bdd0f3 | note | Inspection – Client - H
6661ab60-8cef-5fec-aba7-a840beefda4f | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.8 - Placement of Mass Concrete Plug
f56c111c-2161-59aa-affc-8227e424a06f | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
a48f108b-52ea-5047-8beb-e2c92569f6f3 | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
354bfa7a-83e7-55f3-ad2d-57e24da52558 | note | Frequency / Process Held - Each Pile / Prior to lifting of reinforcement cages
e48c22df-9e52-5c20-8485-bef01a275077 | note | Inspection – ACPL - S
471a40d6-d424-5ec2-9f56-71c189ae8878 | note | Inspection – Client - S
89971e43-8724-5c9a-b71d-cc19c8bedb3e | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.2.9 - Assembly, lifting and transport of reinforcement cages
ee214d62-383c-5b1e-b423-b38e338d40c1 | note | Requirements / Reference - B201 Cl 6.6.2
d585525a-11e5-5f5c-aa38-4df850e1506c | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
5e099d54-0a2a-5d57-bd21-a266435a4ce7 | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
4a9a7024-f281-5773-a481-a1b08d5b54fc | note | Inspection – ACPL - W
f931788d-881c-56ce-a8d0-d5c43e656318 | note | Inspection – Client - W
57f6a0b1-cc03-5f57-a2e2-520a9ec76ce5 | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.2.10 - Placement of reinforcement
c138ee58-962a-526c-aad9-041f4e94edf1 | note | Requirements / Reference - B54 Cl 11.2
2912728e-40d5-5ad9-b26f-f23942064f1e | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
2d973008-cfc9-5dfd-9721-718d02ee03f9 | note | Frequency / Process Held - Each Pile / prior to concrete placement
85404f72-d54e-50a7-9f6b-faec364dc1a0 | note | Inspection – ACPL - S
4d8c0969-4e4e-5ad0-866f-90b1968c3174 | note | Inspection – Client - S
c3de9fe4-4edf-553d-bc3a-76a1810a0522 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.2.11 - Certification Prior to Concreting
56bfaa3c-749a-51bf-8f03-65336a7026bd | note | Requirements / Reference - B80 Cl 7.5.1
8b6ee9a3-322d-500f-ac55-6922d5ee62eb | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
b11602b0-0abd-59b6-be82-d749cc3b0c2d | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
4b08067a-df99-58a5-b7dd-6cd49102e5af | note | Inspection – ACPL - H
04653add-4896-5cc2-ba90-70e9752140e0 | note | Inspection – Client - H
af0f8af7-0908-53c7-b3ed-be602462bd40 | note | Comments / Attachments / Records - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.12 - Concrete Sampling
9df58e60-02c0-5dd0-b009-b332892763be | note | Requirements / Reference - B80 Annexure B80/L
a3e9f850-bfb4-5c85-a6d6-21862f239cc7 | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
37edede7-9ff8-5d61-b642-957782f788da | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if >25m3)
43838635-279c-5592-a2fc-76af8b08b816 | note | 1no. slump test per batch of concrete
101922ce-9aed-54ec-a737-bfee5aa52284 | note | Frequency / Process Held - Each Pile / prior to concrete placement
2ba02cef-6909-5fb9-bfdc-9580f518e424 | note | Inspection – ACPL - S
2fdf25f6-f3cb-5729-baf6-f610b92f3b25 | note | Inspection – Client - S
2b7abac3-3f64-586d-9bef-8e0a4fda72a8 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.2.13 - Concrete placement
1917b6c0-0b00-592c-8b69-a3106c8896da | note | Requirements / Reference - B80 Cl 7
41f287ab-4406-5084-970f-859bd37be075 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
8db554b2-69cd-56b1-b4cc-ff8b0e3250d7 | note | Frequency / Process Held - Once / prior to cutting of concrete casing
dc3073dc-d313-5c52-978e-d05c3ce0e70f | note | Inspection – ACPL - S
a9f8c8d4-837a-54e3-a229-8f38cb140261 | note | Inspection – Client - S
6da57cf1-cd6c-572a-b1c0-904c8c49a1b6 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.2.14 - Cutting of casings
a28535a1-0895-5957-aa63-1ffe286b5292 | note | Requirements / Reference - B54 Cl 12
d522d953-439a-5dce-97e0-3af3bcf7b730 | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
3a5b445d-62b6-54b4-b495-3afb0e1f9ae1 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
813feaea-0242-5f8b-8f82-450a6eca0a6e | note | Inspection – ACPL - S
fdabeff2-57a0-5301-997c-de5e1092936d | note | Inspection – Client - S
| checkpoint | 2.2.15 - Concrete curing
db365ac1-b16a-515a-b97a-03d918502e1f | note | Requirements / Reference - B80 Cl 8
21023979-93f5-55e9-88c1-aeaf08e0d55f | note | Acceptance Criteria - Min 40mPa at 28 days
86c73bae-5b87-5586-aaa4-58772bc4131a | note | Frequency / Process Held - Once / Pile Cap FRP
b9fcf3db-772c-530b-8dfe-92683f1187c2 | note | Inspection – ACPL - H
70a03966-407f-5091-af76-534d2a86f276 | note | Inspection – Client - H
23d7ce09-1113-5bee-a0b6-cd6feb37d7b8 | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 2.3 - Pile 24
| checkpoint | 2.3.1 - Marking of Piles
0a51ca78-e301-5c99-9236-13abbcfc9f45 | note | Requirements / Reference - B54 Cl 2.9
778ba824-bf94-5eb7-aa14-1d400f006fdb | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
8f43625a-d1e7-5a32-83ba-e3d17fc5b669 | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
f2afda6a-4a2a-5a7b-bcca-c8efe71965f6 | note | Inspection – ACPL - S
840950ee-ec57-5392-9013-7c790f87cce7 | note | Inspection – Client - S
a4f2291c-3ba4-5e19-9d95-0ee9b532907f | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.3.1 - Survey set out
61b18145-fa59-5a33-b874-7ffbe091f5db | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
ef85e41e-d2d7-51a4-80fc-447a62cb74b1 | note | Acceptance Criteria - Survey set out as per design drawings
fc243f2c-b914-5067-a64f-071d84cc6c69 | note | Frequency / Process Held - Each Pile / prior to driving operations
8432cd55-22a0-5ac1-b4a7-f1bb2c9a9ab1 | note | Inspection – ACPL - S
f0762b57-f619-599b-887b-e57caed75e44 | note | Inspection – Client - S
c059789b-fc97-55e5-a556-171d0aa57c7d | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.3.2 - Verify Correct Casings prior to Driving
666deac0-4329-5732-b036-e73876302a72 | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
fee5d75a-17db-54ef-a213-2f8d39b68888 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
684b7a1d-a4ae-5a34-9830-4d7a09947e82 | note | Frequency / Process Held - Each Casing / prior to lifting of casing
61123b48-b1f7-5177-8ae0-84abd2380be2 | note | Inspection – ACPL - S
0073efcf-374e-5ed1-ae9d-395466f4b2c1 | note | Inspection – Client - S
ebbe9eaa-77e0-5fd3-bd26-2fdf8fd62b17 | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.3.4 - Pile Driving
d3727d8c-5a71-5ed7-9fd1-c2d1dcf9f9f6 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
ab72fc8a-015e-5fff-b60c-fb800b395067 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile. Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 23) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
4ccf795c-2181-57e5-825c-2e0e722f1375 | note | Frequency / Process Held - Driving of each pile / one day prior to driving each pile
c587a08f-dd72-5ab7-9d4a-71fb115cbfae | note | Inspection – ACPL - W
5759fa6a-5adf-5448-84c2-faa77161c953 | note | Inspection – Client - W
58e06485-983a-56a5-8e61-207e2f9a2c8f | note | Comments / Attachments / Records - Driving Record Sheet
| checkpoint | 2.3.5 - Splicing of Piles
d4310fa7-1f80-53b1-9a72-1c2bf9093e44 | note | Requirements / Reference - B54 Cl 2.6 B201 Cl 13.2
7faca2c7-3512-56e7-88be-abe9c5170203 | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
d5734abb-dc2b-58aa-9436-d59b583fdac6 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
df694a95-52a1-5a43-82a0-00518e48ad8e | note | Inspection – ACPL - S
ce6eb64e-4566-5702-8ee9-2d381fa52ff1 | note | Inspection – Client - S
be67228e-3b9d-5398-9541-13d7cac602b0 | note | Comments / Attachments / Records - Weld Test Results
| checkpoint | 2.3.6 - Backfilling of Pile shaft
b57ae200-e9fa-5aa3-b0a1-f82cfdb9aca6 | note | Requirements / Reference - B54 Cl 11.1
e5535e40-67bb-503f-82ba-eb590f43d86c | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
015ea538-b27b-5db6-9015-54da3e5ff3df | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
2da515af-0f39-5f90-978f-765c71056552 | note | Inspection – ACPL - H
c4576bdd-6c43-57b7-905e-0aea03de0379 | note | Inspection – Client - H
22534a96-a815-55fd-b009-7c3b14c3e81d | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3.7 - Placement of Mass Concrete Plug
7c675d46-ab4c-52fb-9e86-9234b28001d5 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
8957d808-ad1a-5f40-815a-73fed1bd60cd | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
cda9d7fc-43fd-5934-8cf9-a018bc8b9fbb | note | Frequency / Process Held - Each Pile / prior to lifting of reinforcement cages
eeeb024a-c240-5d42-a767-b3d17772e12b | note | Inspection – ACPL - S
2ad5e67f-1e87-556e-9aa5-241d4f576ad9 | note | Inspection – Client - S
a88f2e40-8983-5ff4-8922-6cefe7899089 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.3.8 - Assembly, lifting and transport of reinforcement cages
8c4d4a1c-ee2f-5449-aca5-864be95595f8 | note | Requirements / Reference - B201 Cl 6.6.2
2041a65f-8aa6-5bcf-8864-82260acd9fd0 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
c03ea0ba-e09a-5297-9268-9ebd3862a1ef | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
482f6765-03fb-5bad-81d4-6875fa3df651 | note | Inspection – ACPL - W
d8e84a16-063f-5c70-b54a-9fa452f9cb54 | note | Inspection – Client - W
337625f4-a1f3-57c9-8c16-85005ab34be2 | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.3.9 - Placement of reinforcement
ba327478-7639-5461-99ab-bd508bdcec46 | note | Requirements / Reference - B54 Cl 11.2
ae7c04b3-eaac-5577-9385-bc4ff1a424d4 | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
ca351f94-fd41-5c93-87b9-11eff0b2c135 | note | Frequency / Process Held - Each Pile / prior to concrete placement
57d7a4fd-94de-5651-9a26-990b175f15d1 | note | Inspection – ACPL - S
dcd3914b-755c-5a34-b1b0-27fa0555c895 | note | Inspection – Client - S
7680f8c2-16cd-5141-a194-12eaba42e7a4 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.3.10 - Certification Prior to Concreting
ce407a14-f709-535a-b873-da96af04be40 | note | Requirements / Reference - B80 Cl 7.5.1
ad066a85-d3bf-56fe-95a6-2044c9a27d57 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
53dc05af-75e2-5fec-be68-585fcee8ca31 | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
460cf55b-972b-5883-9b8b-a36983ecfcf4 | note | Inspection – ACPL - H
2a33b8de-d11d-538f-bf2e-b611656d2f3c | note | Inspection – Client - H
4ffab225-a6d4-5349-b35b-a4b2becf5861 | note | Comments / Attachments / Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3.11 - Concrete Sampling
bc58e870-5810-52b0-af71-c22aa68f4ec6 | note | Requirements / Reference - B80 Annexure B80/L
4cb146c4-0f00-52b6-99c5-e8f2bf4f54cb | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
09ae7ab5-c6e5-5b42-8500-15deea9b6439 | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
13853454-f2ed-52b7-82b5-982fbd28cc39 | note | 1no. slump test per batch of concrete 550+/- 50mm
1800cd10-bffa-54e3-a10d-95fb1bcc78f7 | note | Frequency / Process Held - Each Pile / prior to concrete placement
bc0ef859-b2f9-542c-93ff-3776bdc05ac6 | note | Inspection – ACPL - S
6a945e31-a580-5d34-ae57-9d3a5cae7cab | note | Inspection – Client - S
472f56d7-1b6f-5c99-98f0-f203135d20e8 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.3.12 - Concrete placement
7a710a2e-fcf7-5590-8308-7c658fc08756 | note | Requirements / Reference - B80 Cl 7
f9146c95-0b58-58d9-b0f1-ce4f10361132 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
c9b36577-5525-5905-9406-b597ac84261f | note | Frequency / Process Held - Once / prior to cutting of concrete casing
c0ad0f43-4032-5543-b2b3-4e159b1db71a | note | Inspection – ACPL - S
9d7f8802-83e0-5cce-8121-f8511c00e675 | note | Inspection – Client - S
17d93091-a33d-5386-96ef-846c9f2313ac | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.3.13 - Cutting of casings
e8f09e58-8e1b-562a-9398-0a9791029df0 | note | Requirements / Reference - B54 Cl 12
f1eaa3ff-e342-57f5-ba10-e434136bd31d | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
7f167131-bf4b-5e77-ae50-c1bb41ce61b0 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
9f48acf2-9cb2-5bf3-afd8-663bfd7e1d15 | note | Inspection – ACPL - S
5b559901-3118-5539-9703-7d9d659b0146 | note | Inspection – Client - S
bf1aec17-48d1-505d-b064-8fdcb6e67150 | note | Comments / Attachments / Records - Photos
| checkpoint | 2.3.14 - Concrete curing/Sign off
773c5e4f-fea5-5938-9f32-57818c806075 | note | Requirements / Reference - B80 Cl 8
4318fce9-dc64-506e-a163-d76633f81eb4 | note | Acceptance Criteria - Min 40mPa at 28 days
a9cefbe5-3293-562e-96b0-3f0556f66efc | note | Frequency / Process Held - Once / Pile Cap FRP
25b6c635-0d06-5e9f-a5b6-a85d65062373 | note | Inspection – ACPL - H
9cf9d1df-8cee-5408-a95c-8cad31c558f1 | note | Inspection – Client - H
4edb625d-312f-535f-88b3-771c487e5af3 | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 2.4. - Pile 25
| checkpoint | 2.4.1 - Marking of Piles
d60230d7-3148-5cd4-8b05-3bc74a12f62c | note | Requirements / Reference - B54 Cl 2.9
dcb5af79-e34e-5568-bd0d-ac255ed1b05c | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
681d99c7-24e0-54f2-9d36-0ade245d4e1d | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
b53e77d9-5bc8-5054-b619-85aac212a8a9 | note | Inspection – ACPL - S
a2fc2268-8680-575d-9b16-6af143bf8eb3 | note | Inspection – Client - S
236cec42-5db4-544b-959f-7a587be6554d | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.4.2 - Survey set out
801f8090-7aeb-51d2-8058-23954d0dd789 | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
fba19d68-128c-5a2c-b74d-5a2947959a0e | note | Acceptance Criteria - Survey set out as per design drawings
f13b232a-d65f-5636-ac9a-f93252b1e328 | note | Frequency / Process Held - Each Pile / prior to driving operations
796a60b2-f330-5d89-8545-a19d8305baf6 | note | Inspection – ACPL - S
43f46307-6b0c-599b-8f6e-101845e9cf58 | note | Inspection – Client - S
d4536108-98fc-5a4d-809c-c15e6c51b6c4 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.4.3 - Verify Correct Casings prior to Driving
ca81dcc8-404f-5e48-8d66-ef054d9a910d | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
34bb2886-2ba4-5394-b0ae-0e5fb3f39f4a | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
d0b01cb7-6219-5d15-8313-ec40a8fb0e02 | note | Frequency / Process Held - Each Casing / prior to lifting of casing
124ed0b8-9c49-5641-94d4-6ad5f606a3b0 | note | Inspection – ACPL - S
a4851abd-4751-59b0-a16f-cc1bcd81aa90 | note | Inspection – Client - S
dfd2657f-8b2d-5a25-9977-d9fcdf1d6c8a | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.4.4 - Pile Driving
0960c1cb-4fca-54b9-b707-6c0f0dbe4921 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
177e44d1-69f8-572f-bb57-0730b9229f40 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile. Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 23) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
17e5b0a6-e404-59c7-8d7a-6edf16c78e81 | note | Frequency / Process Held - Driving of each pile / one day prior to driving each pile
dda37177-c357-556f-86cf-87b210a0cd35 | note | Inspection – ACPL - W
d850682e-1078-5d57-94cc-6720533cca54 | note | Inspection – Client - W
8c068743-d3ee-5350-868b-7c5fb4106edf | note | Comments / Attachments / Records - Driving Record Sheet
| checkpoint | 2.4.5 - Splicing of Piles
0f895152-11a4-5751-aab0-aeb4ade2a75d | note | Requirements / Reference - B54 Cl 2.6 B201 Cl 13.2
384e1ff0-eb51-565c-bf8e-c9109e64cd2f | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
4ca76e2f-c9fd-50a0-9e71-ca5ef3400d74 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
bde97f26-c023-5b73-8d72-87e5e37209a4 | note | Inspection – ACPL - S
5e0fd28f-aaed-5546-b8d2-dd9ffc647084 | note | Inspection – Client - S
b49c96bb-833f-5ebe-8cee-81b75936feed | note | Comments / Attachments / Records - Weld Test Results
| checkpoint | 2.4.6 - Backfilling of Pile shaft
842b7d76-2aa7-52b7-a93a-0e050e99cc7c | note | Requirements / Reference - B54 Cl 11.1
6c08c806-62aa-58a5-9da6-f623bc786201 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
1b9cb04a-ca6d-51a9-9533-ea900bebc510 | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
bdc1e6bd-417b-517e-b2fb-35bd866d3fd9 | note | Inspection – ACPL - H
d092f85b-8304-53a1-bbdb-2ad146e292c9 | note | Inspection – Client - H
d1d36b29-6856-51b7-af40-459d65f29e4d | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.7 - Placement of Mass Concrete Plug
cc0f3fd6-60b2-5490-8f6b-e01be62915a7 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
0e420f67-4b31-5d5f-a2b7-649654890f2d | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
ea9e85d3-bba0-5265-b351-80fdc65e189e | note | Frequency / Process Held - Each Pile / prior to lifting of reinforcement cages
47790d1a-eb31-539e-9679-4d62ba483225 | note | Inspection – ACPL - S
129e9ca8-b91a-57d7-8444-c7a453ac5a8c | note | Inspection – Client - S
dbeae46d-83c5-5f3b-84f2-e630d3d21448 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.4.8 - Assembly, lifting and transport of reinforcement cages
a4272cd4-a25c-5a7f-8ff6-6b6722d0e169 | note | Requirements / Reference - B201 Cl 6.6.2
a1ec5ab0-c8a9-5723-9479-63590f11d809 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
0cb829b4-bbc4-5056-b8f0-5e6851ed09ac | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
0b258fe4-2b33-5474-87a1-62eb9a6f9aff | note | Inspection – ACPL - W
91664883-f975-51ac-8d58-1e2d5d8609b9 | note | Inspection – Client - W
47d707ca-80fc-5f2f-aea2-e8586e0003be | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.4.9 - Placement of reinforcement
aa2d4a5f-be02-5be9-a9d0-0f4ada79cf16 | note | Requirements / Reference - B54 Cl 11.2
6774e0ef-4c3d-54ab-998f-2d7302ae3a89 | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
2d012b38-3463-5edf-b393-c6f5773d0b19 | note | Frequency / Process Held - Each Pile / prior to concrete placement
9f4ffe5e-7b8c-5468-8eda-8d089d3e228c | note | Inspection – ACPL - S
0e8b8071-7bd4-5d53-b8fa-66e653507a1f | note | Inspection – Client - S
b7eefb1e-ec21-52b5-84e2-615ef3e0c632 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.4.10 - Certification Prior to Concreting
7912c03b-57f6-584d-866f-513810c4d8f4 | note | Requirements / Reference - B80 Cl 7.5.1
73ab3e6b-e92d-5266-b6a0-17f411478bb8 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
268444cd-cb5c-568a-91f7-e7e0476563d0 | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
f5e84821-70c3-5543-bc57-d23399e8102a | note | Inspection – ACPL - H
88718a5a-541f-5232-af92-fbe26848a1e2 | note | Inspection – Client - H
2185d59b-1cfc-57ad-9b37-121b3b46e86d | note | Comments / Attachments / Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.11 - Concrete Sampling
9f27821d-d10c-50d0-94f7-89fc6b350bd5 | note | Requirements / Reference - B80 Annexure B80/L
46a50da9-280c-54a6-81ee-26c1150ae6dd | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
690bc88f-6da7-560f-bcc6-6cbdcf2a3b25 | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
de34ff83-1aa6-5d12-87dd-ac55e0768229 | note | 1no. slump test per batch of concrete 550+/- 50mm
7c440190-40cb-572b-9082-9e82a4693095 | note | Frequency / Process Held - Each Pile / prior to concrete placement
f676bad4-ea2c-566c-9684-3ff065b54453 | note | Inspection – ACPL - S
aeaf286e-e749-5f0e-87f6-f9023444e91f | note | Inspection – Client - S
e8270370-4e69-59fc-bb15-75f6e98661e2 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.4.12 - Concrete placement
4de69ec2-7021-53c0-b0c6-9eb041e86b01 | note | Requirements / Reference - B80 Cl 7
4d28537a-076c-53e2-8e12-2167408119ac | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
83ec9ced-dee9-546d-9ce5-d354c085e24e | note | Frequency / Process Held - Once / prior to cutting of concrete casing
47dc0106-a72e-5bd3-9384-2a02a89cd081 | note | Inspection – ACPL - S
84b24b8a-ee85-5074-8bf3-ec5892690520 | note | Inspection – Client - S
92704229-3891-55f7-be04-81811743dc98 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.4.13 - Cutting of casings
71898fdf-8132-5f0f-884a-2fbeefa0ef86 | note | Requirements / Reference - B54 Cl 12
3649bc2d-d2d4-5d36-95e4-129464e5b1af | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
fde2a7c8-8891-5fd8-bd03-27a8e0ee1658 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
46249175-c5e0-528c-9b10-25740443d523 | note | Inspection – ACPL - S
40b32b40-a749-5dd5-92b0-3b273c2a6ef3 | note | Inspection – Client - S
546bd028-96a7-55f5-825b-6b6ce06b1204 | note | Comments / Attachments / Records - Photos
| checkpoint | 2.4.14 - Concrete curing/Sign off
158d5a58-7ee2-5dfe-a285-4d344a8a0260 | note | Requirements / Reference - B80 Cl 8
de2ff245-c700-533f-a9a8-c6cf230c63d4 | note | Acceptance Criteria - Min 40mPa at 28 days
ce98e132-579b-5b60-9aad-49d45fbab998 | note | Frequency / Process Held - Once / Pile Cap FRP
e02c3934-443e-57ea-bf34-b9ad23819931 | note | Inspection – ACPL - H
f0c836a4-ad0f-5b48-8e5c-3ca480edc851 | note | Inspection – Client - H
b0940d78-089a-54a3-9c23-dde78950a2c9 | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 2.5 - Pile 26
| checkpoint | 2.5.1 - Marking of Piles
61663773-fbc7-58b8-a53b-9c8243f226d0 | note | Requirements / Reference - B54 Cl 2.9
c58f851b-b841-5235-bf53-1178c2e3c303 | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
7c05c642-37bd-5b54-b0b7-a139a7107803 | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
467d8240-a7f6-5071-bb4d-edaf6a7fc124 | note | Inspection – ACPL - S
c771e02d-1bf0-5589-b08f-ff14ad197b09 | note | Inspection – Client - S
52aea37b-6995-53fe-b34e-1d160f4e2667 | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.5.2 - Survey set out
729d5f2c-7197-5eeb-8a47-1008ed50bc7c | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
c9c33bd7-4a8d-504f-85dd-09a3e4db07b2 | note | Acceptance Criteria - Survey set out as per design drawings
58321522-b232-5802-9ba0-e8ddd57e0549 | note | Frequency / Process Held - Each Pile / prior to driving operations
88d3eaf8-884e-5275-aed3-9707ab29c1ca | note | Inspection – ACPL - S
a4e5ce64-a0e4-5650-8e48-76a5b096ebb0 | note | Inspection – Client - S
8c2cd2f1-919b-59af-9381-c04982d63033 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.5.3 - Verify Correct Casings prior to Driving
eb13e3a5-47f0-5ae0-88db-8c59d88c2430 | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
3bfa59b9-288a-5911-a910-2433420f84c2 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
0b98efc2-baa3-5725-b587-5066b4808dd3 | note | Frequency / Process Held - Each Casing / prior to lifting of casing
0de457fa-5d73-5bbd-80e9-f8a4e44971e5 | note | Inspection – ACPL - S
b32614a8-0e61-509c-8a88-6ba11210235e | note | Inspection – Client - S
bce99ade-9224-554d-9a8e-48abf75486cc | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.5.4 - Pile Driving
19d4aaf4-2618-570f-b2e4-c238e52c42fe | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
21650d58-d3a6-5ae9-8fc5-f20e67f9ae76 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile. Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 23) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
809d117e-5ad8-59b6-87e3-dd6b77dd3b5e | note | Frequency / Process Held - Driving of each pile / one day prior to driving each pile
344a9325-4439-5aed-8d84-ed3604a6da6e | note | Inspection – ACPL - W
570b05d0-3952-5eaa-b4a8-5b9213177c1e | note | Inspection – Client - W
ff31821a-b088-538d-a03e-f794e385135d | note | Comments / Attachments / Records - Driving Record Sheet
| checkpoint | 2.5.5 - Splicing of Piles
899559d2-e5d9-54ca-8e3b-141af089868b | note | Requirements / Reference - B54 Cl 2.6 B201 Cl 13.2
85f0dea9-e8d9-5bf4-9fe0-fbb0c10d7f5a | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
45b006d5-212a-588a-bfaf-4af4a222d4e4 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
0eb5335e-79da-5ed7-818d-b863d0a300aa | note | Inspection – ACPL - S
e1597834-3934-5a64-a700-d874ebc78176 | note | Inspection – Client - S
8c269580-1002-58a9-b683-b0f89fc44193 | note | Comments / Attachments / Records - Weld Test Results
| checkpoint | 2.5.6 - Backfilling of Pile shaft
74a5f79f-71e7-52e8-aacb-69a48b348972 | note | Requirements / Reference - B54 Cl 11.1
82bdda87-3210-55e7-b792-27824e240102 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
5e9431cb-3d2a-525b-ab9c-134841e27eb9 | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
3d5c55c8-ec70-5b2e-95c2-66a5b93c7101 | note | Inspection – ACPL - H
d1e369a2-35c7-51a6-97e8-a5f19c6ebf7c | note | Inspection – Client - H
aee3ee46-6b3a-56ef-977f-a56130afb5ac | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5.7 - Placement of Mass Concrete Plug
a18332d8-4df3-5083-8c94-1f0343f4d214 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
9eecb4a6-ff87-5448-b763-719ecadfe817 | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
934985be-6f50-549f-8892-0c1cee611e1e | note | Frequency / Process Held - Each Pile / prior to lifting of reinforcement cages
d8730315-b3f0-50f5-8a33-792091c2cfad | note | Inspection – ACPL - S
83a19630-5ad5-5626-813b-6de6da14f6cd | note | Inspection – Client - S
67db7135-135e-5b1c-bc9b-f3658f2462fc | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.5.8 - Assembly, lifting and transport of reinforcement cages
92ec3d7b-ab50-5d30-9a81-ebd0876c8938 | note | Requirements / Reference - B201 Cl 6.6.2
2a25b4c7-7e57-5a1b-9c4f-987ef9602ff1 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
170a1c68-49a6-598a-8f02-4ab44193e369 | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
3ce40269-127d-5548-af84-58bee3510991 | note | Inspection – ACPL - W
e5eb08ae-e591-5f46-8e16-c546a98d1c28 | note | Inspection – Client - W
1decb1a4-5d22-5ee4-9a82-648e21f9c27d | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.5.9 - Placement of reinforcement
8745962a-52f2-5800-8bdb-7dae44d8eab4 | note | Requirements / Reference - B54 Cl 11.2
a3bebc50-7850-535b-b3c4-dfc83f8cd41a | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
d5f7e966-81f6-5a69-9796-c3587f391b09 | note | Frequency / Process Held - Each Pile / prior to concrete placement
3a5432cb-6f8b-5d86-b1c1-118f87f68689 | note | Inspection – ACPL - S
6d635beb-8d8b-51b0-bf68-fb78c82bd88b | note | Inspection – Client - S
9f015855-647f-5397-84df-3c42868b5937 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.5.10 - Certification Prior to Concreting
2c6e1784-f483-58c6-bdb5-d85a45fc64fa | note | Requirements / Reference - B80 Cl 7.5.1
a371bcaa-7123-55ec-a9cd-ddba678139f6 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
a80982c7-e4f3-52a5-ab2e-efdf0afba31b | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
37b533e2-a7c2-5ec8-8f80-4ec105c4b99f | note | Inspection – ACPL - H
db84f923-8556-5502-b89f-34497b14b7e6 | note | Inspection – Client - H
c61ce67d-644f-5051-9ddf-164aab22e145 | note | Comments / Attachments / Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5.11 - Concrete Sampling
9f9f95c4-fd83-513b-9cc6-c6ac2debf225 | note | Requirements / Reference - B80 Annexure B80/L
b3748aba-d9fa-5fd8-bea1-112bf5e79a37 | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
83f8ef96-879b-5d47-882d-ecd45ec36bcd | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
ebdd1f2f-7b3f-53f8-8829-24b5aa040a27 | note | 1no. slump test per batch of concrete 550+/- 50mm
11bc8312-2a92-521e-91ae-b640c47c3385 | note | Frequency / Process Held - Each Pile / prior to concrete placement
09ab3112-94a0-51ed-97b4-ba4268733ac1 | note | Inspection – ACPL - S
afb17aad-c952-56b0-9d4c-685683cc790b | note | Inspection – Client - S
8142c72f-3cb8-5a35-9ec9-973ae39d6396 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.5.12 - Concrete placement
07c73f48-308e-528d-90b5-5a61d08ca8f3 | note | Requirements / Reference - B80 Cl 7
268ed9bb-647e-5dc6-8174-c9e17a15973d | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
8e45ed1c-3625-56f6-a6c7-eeab556bb4f8 | note | Frequency / Process Held - Once / prior to cutting of concrete casing
42b4188e-d4b5-5ef0-8525-be11091360c2 | note | Inspection – ACPL - S
2b7f5852-f8cc-5989-8b88-62559857e4ac | note | Inspection – Client - S
399e275a-a281-547f-9cf0-78402a0a8fa9 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.5.13 - Cutting of casings
f78ee702-b78e-58c4-a785-dbfeb26a3376 | note | Requirements / Reference - B54 Cl 12
abf14787-2574-5d37-9b6b-548561f86183 | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
24a4a21e-b57a-5237-ab47-a0237ef52a76 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
5a2b61e9-920e-5d8b-855b-5040a07ea701 | note | Inspection – ACPL - S
1322f070-6259-5a28-9741-2b2bf87c5b09 | note | Inspection – Client - S
9d8b7f4e-1924-5599-86bb-fafed6b9af29 | note | Comments / Attachments / Records - Photos
| checkpoint | 2.5.14 - Concrete curing/Sign off
96b79fe7-4140-538e-a6b7-5b4e7f917350 | note | Requirements / Reference - B80 Cl 8
9ffab98f-56fa-589f-aa68-8b95e842a484 | note | Acceptance Criteria - Min 40mPa at 28 days
34d50869-4ccd-5f63-bcee-02b22f8b4b54 | note | Frequency / Process Held - Once / Pile Cap FRP
2efa3357-1089-5f68-93e4-7965d27fdaa3 | note | Inspection – ACPL - H
ae005321-3cc3-5ed1-9d42-973dab448c2c | note | Inspection – Client - H
8034c37d-c0b0-5e43-8c4a-62e2bc49b4de | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 2.6 - Pile 27
| checkpoint | 2.6.1 - Marking of Piles
3cfe0ef1-f2bc-5356-b904-432bae7d8ba9 | note | Requirements / Reference - B54 Cl 2.9
525fbdb3-aca9-5cab-bb57-6e1c08c2c96e | note | Acceptance Criteria - Mark all Test Piles at 1m intervals commencing from to show penetration depths attained during driving. Mark all other piles for traceability purposes
cfca11c3-53cf-51d4-9129-8f7f6614df41 | note | Frequency / Process Held - Each Casing (1m intervals) at point of delivery / prior to lifting
25a38127-c09d-5496-b407-ed4f2e635844 | note | Inspection – ACPL - S
f499e857-93b0-5cc7-8d0d-e27a032ea15c | note | Inspection – Client - S
73e30598-6f69-598f-bfc2-90cd59bc1bce | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.6.2 - Survey set out
2e982c9d-c77e-54ba-8567-4d99edad2cbf | note | Requirements / Reference - G7 Cl 5 IA182600-JAC-DD-BR-DRG-1009 - 1011
8b983d53-0dd2-5b74-8a4a-87019a9cde8c | note | Acceptance Criteria - Survey set out as per design drawings
e546d6ff-69b7-545f-9e3c-d7aa390acea3 | note | Frequency / Process Held - Each Pile / prior to driving operations
dfdbba75-04e8-566d-abf6-9beccc3f2324 | note | Inspection – ACPL - S
0d40f633-4d4a-54a5-af1c-decc5f767958 | note | Inspection – Client - S
56a2498c-8f0f-5b34-8aa4-90bcacf6b935 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.6.3 - Verify Correct Casings prior to Driving
1a661adf-558d-5ea2-bc84-4ed548d31a12 | note | Requirements / Reference - IA 82600-JAC-DD-BR-DRG-1012-1013
43d0dbf0-637e-5162-844f-2744be185b07 | note | Acceptance Criteria - Visual inspection verifying correct casings are being installed
d1cd76e9-b032-56e5-b142-6878d1a45904 | note | Frequency / Process Held - Each Casing / prior to lifting of casing
62367056-ddf0-57d7-9a76-9776934f8ff3 | note | Inspection – ACPL - S
b4c2d407-8e6f-555f-81b6-c2fd04c7793c | note | Inspection – Client - S
af8e5cf2-b12c-57c0-ad4c-c4f9315b5a60 | note | Comments / Attachments / Records - This ITP Photos
| checkpoint | 2.6.4 - Pile Driving
2a870a2e-6dbc-5125-ad60-755a92f2d14d | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 B54 Cl 9.3
f064d35b-b008-5979-901a-ed2e75768389 | note | Acceptance Criteria - Notification of the time and location of the driving of each pile. Piles driven to nominal refusal in rock or to the required pile resistance, as demonstrated by dynamic testing of the representative pile (Pile 23) Once minimum penetration depth has been achieved, drive the piles further to the same resistance as the representative pile but with the same driving parameters established during the driving of the representative pile. At the end of driving, the Net driving energy delivered to the pile must be within 10% of that used at the end of driving and restriking of the appropriate test/representative pile.
e8723c71-9ea4-5864-acac-1d8fa9544678 | note | Frequency / Process Held - Driving of each pile / one day prior to driving each pile
f54aff8c-80ff-52e7-af92-3bcdbc91247d | note | Inspection – ACPL - W
93f5fe1b-ebad-5a6f-b85e-d8b1ad9e7475 | note | Inspection – Client - W
34752182-db9b-5a3b-af05-2150a4b52529 | note | Comments / Attachments / Records - Driving Record Sheet
| checkpoint | 2.6.5 - Splicing of Piles
6cdbd6e9-7c23-51d3-acc9-34e7f15e129c | note | Requirements / Reference - B54 Cl 2.6 B201 Cl 13.2
cecc06bd-1875-5aca-b1eb-86e8ded9a728 | note | Acceptance Criteria - When a pile needs to be lengthened on site, splice on additional length of pile using Full Penetration Butt Welds
f0b70f9f-0ec6-511f-88eb-6c971ff597a8 | note | Frequency / Process Held - Each length of Pile for each Pile / prior to driving Following section
92bffe21-aaf6-5a9b-9db7-df336387763d | note | Inspection – ACPL - S
5cd78a2a-94af-5af5-acd9-2b84acb85e25 | note | Inspection – Client - S
0fbade79-024c-5d14-872a-6c15f4636eb7 | note | Comments / Attachments / Records - Weld Test Results
| checkpoint | 2.6.6 - Backfilling of Pile shaft
54d356a6-4125-598c-956e-0c49e65dece6 | note | Requirements / Reference - B54 Cl 11.1
614918ca-4afe-58e0-b2d5-0f1f46e7b758 | note | Acceptance Criteria - If the level of material inside the tube is higher than the level shown on the Drawings, excavate the pile to the level shown on the Drawings without disturbing the soil plug at the bottom of the hole. If the level of material inside the tube is below the bottom level of the reinforced concrete section shown on the Drawings, backfill the pile shaft to this level with sand or other approved granular material. Compact the granular material by flooding with it with water.
71435b7e-6836-55ff-870d-abd6df44c98e | note | Frequency / Process Held - Each Pile / prior to placement of concrete plug
8cbd108d-3e17-57c3-b396-dfbd47022d40 | note | Inspection – ACPL - H
74908563-d5f4-569a-aaa1-62129fef7179 | note | Inspection – Client - H
df989518-075b-5b06-8204-1b3267d4aeb4 | note | Comments / Attachments / Records - Driving records Survey Report Certification by Piling Supervisor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6.7 - Placement of Mass Concrete Plug
9725e31d-b29d-53d7-af06-2ba4de6b7738 | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1012 B54 Cl 11.3
d3bd9145-f76d-50dc-ac0d-6dc0e372d588 | note | Acceptance Criteria - 20MPa Mass Concrete Plug poured using rigid tremie pipe, as per design drawing.
64c473b5-bb42-5fd0-a471-c4a1fc2877e2 | note | Frequency / Process Held - Each Pile / prior to lifting of reinforcement cages
4fe7e0d5-5477-56f6-95a1-fbb770010e13 | note | Inspection – ACPL - S
89d3fea6-7b61-509a-b24e-92d5dc72550f | note | Inspection – Client - S
8513caef-59fa-533b-be66-6f850ce83908 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 2.6.8 - Assembly, lifting and transport of reinforcement cages
b5733bdf-9518-5952-95f5-a480d98420a3 | note | Requirements / Reference - B201 Cl 6.6.2
7ffa78ba-8d1a-59cd-ae3d-ca7a1ba04226 | note | Acceptance Criteria - Submit to Principal Certificate of Conformity in respect of load bearing weld sizes and locations, and conformity of finished welds, together with drawings and checklists
8198419e-4305-5cea-abf4-cdc5c1deb022 | note | Frequency / Process Held - Once / At least 2 working days prior to transport to site
c5bd5419-b8d6-5310-95d1-796c15e65c92 | note | Inspection – ACPL - W
87a442f7-2827-58a2-ae04-35e0c945411a | note | Inspection – Client - W
a317a152-d79c-5db2-881d-587e93e47092 | note | Comments / Attachments / Records - Certificate of Conformity
| checkpoint | 2.6.9 - Placement of reinforcement
2640ae06-d293-549c-96bf-b55aa4b8e22e | note | Requirements / Reference - B54 Cl 11.2
64a6f6d2-0dee-5f5f-ae3c-cf11820aa694 | note | Acceptance Criteria - Prior to placement of reinforcement, thoroughly clean pile shaft of all loose material Fabricate and place the reinforcement cage so that the projecting bars from the pile will pass through the pile cap bars. Use spacers attached to the cage to maintain the cage in position after placement. Cover to reinforcement nearest to the concrete surface to be 50mm Reinforcing bars to be grade D500N Clear distance between lapped bars must not exceed 3x bar diameter
6453fb3e-1dab-5df4-af91-7e592f7e5a56 | note | Frequency / Process Held - Each Pile / prior to concrete placement
46cf16c2-1306-5b18-9301-d19ef63906e9 | note | Inspection – ACPL - S
4b517742-987e-5d4f-a509-0b023e9d8737 | note | Inspection – Client - S
ad27b4ad-697c-57a3-bd9e-beb47393d691 | note | Comments / Attachments / Records - This ITP
| checkpoint | 2.6.10 - Certification Prior to Concreting
48388aec-c69b-5735-82a6-b95e29e71c55 | note | Requirements / Reference - B80 Cl 7.5.1
4ea73aea-cf05-57a9-b46a-dcef960e4555 | note | Acceptance Criteria - Submit to the Principal a pour specific method statement detailing: (a) delivery rate; (b) placement method and rate; (c) equipment on standby. At least 4 working hours prior to commencement of placing concrete (unless otherwise permitted by the Principal), submit to the Principal a Certificate of Conformity, endorsed by the Concrete Supervisor, in respect of formwork, reinforcement, embedments and screeding guide rails or height pins. This certificate must be accompanied by verification checklists and other details showing conformity to this Specification.
d469de9f-4f44-528d-85ed-eabf955d1619 | note | Frequency / Process Held - Once / 2 days prior to each concrete placement
3ea67569-9b51-53b4-81ac-82903d5358e2 | note | Inspection – ACPL - H
1bf56360-5b61-5423-882f-a1612a2427cd | note | Inspection – Client - H
5f1aaced-0132-5f86-b344-cae3c6eef15e | note | Comments / Attachments / Records - Pre-Concrete Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6.11 - Concrete Sampling
7b43ef90-c314-5dfd-b6bd-f6a1dd913a7c | note | Requirements / Reference - B80 Annexure B80/L
abde99c1-f213-5634-99db-59f5796e83e2 | note | Acceptance Criteria - The nominal rate of sampling shall be taken:
871252a7-b6f7-597e-ab80-293f4d74e6a6 | note | Compressive Strength: 1no. 7-day & 2no. 28-day samples per 25m3 (or per pour if <25m3)
4cdfd2f6-ea8a-5b33-b0ee-d74ccdbfeccc | note | 1no. slump test per batch of concrete 550+/- 50mm
9bf24a7f-cc45-54a7-a672-e8239817dfbe | note | Frequency / Process Held - Each Pile / prior to concrete placement
57e5c9d7-4295-5bda-9ccc-a714e5e82b6c | note | Inspection – ACPL - S
488db7f8-5c59-55de-a4c7-02509a28cfc6 | note | Inspection – Client - S
f50b1cf8-4913-5bd9-bd08-ac7c8bcca7d8 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.6.12 - Concrete placement
fe1caad1-5fd2-5505-a5f1-12b1fa97cc13 | note | Requirements / Reference - B80 Cl 7
7ccffd15-a9af-5251-8a67-4fcdb0f280cb | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature must be 5-35C 40MPa Concrete Concrete placed in piles to be carried out in one continuous operation.
2a8d3cd3-447b-5e74-9bf3-0cefe1259f70 | note | Frequency / Process Held - Once / prior to cutting of concrete casing
79843c33-1fda-5960-bc24-8bbdd10111ed | note | Inspection – ACPL - S
56eb0aa8-7ff0-55e7-ac46-78df3506e8f8 | note | Inspection – Client - S
a1b338d0-b9a2-5321-a19d-714c20714a1e | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record
| checkpoint | 3.6.13 - Cutting of casings
25ef6af9-b0ba-5ef4-8d86-466bd37234d7 | note | Requirements / Reference - B54 Cl 12
c0015fd7-bffd-5d12-9a1e-6f2d7959d7fa | note | Acceptance Criteria - Carefully remove any concrete / casing above the cut off level shown on the drawings no earlier than 24 hours after completion of placement of concrete
94823121-d385-530a-987d-4ab264cbfbd0 | note | Frequency / Process Held - Each Pile / No less than 24hrs after concrete pour
b1a3b0e9-103c-52d4-952d-f85e65caf647 | note | Inspection – ACPL - S
58822a32-eeae-5a9d-a83f-4e35c0435b8d | note | Inspection – Client - S
aef717a1-2efa-58fd-8fbd-085da5d23d73 | note | Comments / Attachments / Records - Photos
| checkpoint | 3.6.14 - Concrete curing/Sign off
63d22704-454c-54a6-88d6-8c692133c3f4 | note | Requirements / Reference - B80 Cl 8
7acf9ba9-fdc2-55c0-ab7a-668b8513f2f5 | note | Acceptance Criteria - Min 40mPa at 28 days
da0db3c8-ee28-5c6b-9123-0bd129cea009 | note | Frequency / Process Held - Once / Pile Cap FRP
28ba124e-8bf1-5ff5-9bac-3054393b1485 | note | Inspection – ACPL - H
31849cc6-3626-5148-be7a-e48c3d8eb92f | note | Inspection – Client - H
dd0a6010-e321-5a84-93b8-b0989ce288a5 | note | Comments / Attachments / Records - Test results Concrete Register
| signoff | AUTHORITY HOLDPOINT
| section | 3. Submission
| checkpoint | 3.3.1 - As-Built Survey
1c5011bd-e0d6-5134-b809-5155f22a851a | note | Requirements / Reference - IA182600-JAC-DD-BR-DRG-1009 Rev_5
aa4f0618-cbd4-5675-8490-5fa75c4d2289 | note | Acceptance Criteria - Within positional tolerance of +/- 50mm plan positional tolerance Top of pile level must be constructed with +10/-0mm Vertical Level Tolerance
3a174d46-9d8a-51d4-aadc-018eb7a91ab7 | note | Frequency / Process Held - Once per Pier / Prior to lot submission
fd6bada1-eb2c-5fa4-9271-98b9e32e561d | note | Inspection – ACPL - H
22707231-5c58-5f58-b093-3e9552e82f96 | note | Inspection – Client - W
54a6951e-fe5d-5893-887b-b388c8abe57e | note | Comments / Attachments / Records - Survey Record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - Driving Records
9ed64618-cde1-5f04-9fd6-ed2c74cb42da | note | Requirements / Reference - B54 Cl 6.6
a39161d7-8fdc-5699-b5c7-d90b34af49b7 | note | Acceptance Criteria - Prepare driving record for each pile including:
6174d519-f5a0-5e16-b336-37ddfd9636a0 | note | Date of Pile Driving
cab5d4d7-ccd9-5979-8064-a2c17b7bf808 | note | Design location, inclination and dimensions
aa8c1eca-f67b-58d0-a531-0a88f6adafb5 | note | Ground Surface level at the time of driving and toe level at end of driving
083b95f6-b9c3-55ee-b22e-f6eba4566675 | note | Reports of Dynamic Testing, including restrike tests, when carried out and any other relevant information.
4f7c5c17-e9b5-5d69-a529-c8a690cd0f9d | note | Frequency / Process Held - Once per Pier / Prior to lot submission
8f30d632-329a-5830-8411-0efdd909bef2 | note | Inspection – ACPL - S
0ae3bdc4-9c45-58ed-921b-0d7060d2f0c0 | note | Inspection – Client - S
5cfe5e4f-74da-59d7-9945-c0e65d320f1e | note | Comments / Attachments / Records - Driving Records
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
575d14f9-09ac-5786-9637-4989c4414eea | button | Any non-conformances? | YES, NO
c182adcd-2eab-574b-a80e-759f0b9f3a88 | textbox | No's:
840e719c-a801-521f-a2df-ab803f36f258 | button | Closed Out | YES, NO
05fcf004-441d-5895-92ca-5091e8b8553e | button | All work has been satisfactorily completed. | YES, NO
b097d45c-4e3a-558f-b71a-b20b18378515 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
b1ae7d34-3a5b-562e-afdc-a4b54bb9e363 | textbox | Lot Verified By:
1173bfd3-cd5e-5ea2-8a87-e34b2adc4c5d | textbox | Lot Closed Date:
6664c5eb-583d-5b26-b4d0-5fd3858c7c85 | button | Submitted to Client | Yes, No, N/A
67a58d82-9c5f-5268-8107-40afd0de0008 | button | Reviewed by Client | Yes, No, N/A
5dde422a-68b3-56b3-9e93-c9bfb4dbbb73 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B1.P - Piling Preliminary Works ITP |  | ITP-B1.P - Piling Preliminary Works ITP | 27c30622-3a59-4d39-a297-27f17e696dfe
| section | Lot Information
| checkpoint | Lot Information complete
433037a3-9927-46aa-b09e-19d3981260d9 | textbox | Lot Opened On
5dc7796f-6146-4e37-9ee6-b2a510113594 | textbox | Date of Works
5d6d3feb-1230-4af3-8fb7-d18398ff8eef | textbox | Lot Type
5c5b88b3-d28d-4848-97cc-fde8da0a2c9b | textbox | Start Chainage
75ecee13-a4c0-411a-be71-dde1491a13b5 | textbox | End Chainage
a6aa4c6d-9b19-44c0-8e8e-aebb5c9ce14b | textbox | Offset
40f1c186-72a9-49c5-b8ba-f81ad3739250 | textbox | Control Line
| section | 1. Prelims
| checkpoint | 1.1 - Safety and Environmental Review Check CEMP, EWMS, AQM-SP TGS and VMP signed off by personnel
215e339f-270d-576a-b5b7-e3fbc89acd1d | note | Requirements / Reference - Project Safety Plan G22 Project environment Plan, G36 Cl 3.1, G38, G40 CEMP EWMS TGS VMP AQM Sub-Plan
430ed47f-20ac-5461-bc79-f9d145db23bd | note | Acceptance Criteria - Site Inductions undertaken for all working personnel
261ce1b9-809c-5214-94d0-753d6a2933c3 | note | SWMS approved for works
22943f3d-30e1-594d-834b-94fa057e448f | note | ESC Plan approved.
b761c685-8dd4-5a17-ad6c-175d3c14e3b5 | note | EMP approved.
28e8b66c-6d6d-59df-9957-f7b84172619b | note | Air Quality Management Sub-Plan Approved
02dbffef-5149-551b-aac1-7624507ac5f3 | note | All work undertaken must be approved by Environmental Site Representative and comply with CEMS and CEMP
56b8ba00-caea-574f-b524-ce4102a76531 | note | Frequency / Process Held - Once / prior to work commence
0b0dd410-8328-5b34-a212-bbafc22b870b | note | Inspection – ACPL - H
21ec9dde-22b0-5995-9fb8-eaa730c57df9 | note | Inspection – Client - S
4d785bf0-6d26-5192-b6f6-989e4af3082b | note | Comments / Attachments / Records - This ITP CEMO EWMS AQM-SP TGS VMP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Acceptance of prior works (Test Piles)
7a6dd623-03c2-5ee7-9b66-fe2ceb4557e9 | note | Requirements / Reference - G1 Cl 29.2
d81b6cb7-b8ee-5893-a566-01656afec1e4 | note | Acceptance Criteria - Prior Work Acceptance Report, including:
bc8d1a8e-215e-51d2-9cf1-67d734d7499b | note | Detailed Survey Reports
921c331e-8e39-55d5-a576-03aef8b7af7b | note | Geotechnical testing
09f281d9-1268-51a9-afa8-a438b6a556a7 | note | Proposals for resolving any non-compliances
a3f3279a-e350-504b-abe4-3b7cd944ea9e | note | Variation proposal (if required)
45c60e28-5e41-5fa0-83bd-468c7b764cd7 | note | Of the work undertaken by others
c288faa1-e4f5-5570-bacd-320aec0604f1 | note | Frequency / Process Held - Once / (at least 5 working days) Prior to commencement of construction
0285a6b7-3af0-5657-808e-d4fa57ab5bcc | note | Inspection – ACPL - H
2961b5f7-39ca-51f6-bb71-594bc0bab170 | note | Inspection – Client - H
7d287f3b-e6e2-5f66-8ea6-b88f1fdec13b | note | Comments / Attachments / Records - Prior Works Acceptance Report
| signoff | AUTHORITY HOLDPOINT
| section | 2. Design of Temporary Works
| checkpoint | 2.1 - Design of Piling Platform
ad4825f5-61e3-5a80-b1a9-98c9d13679f6 | note | Requirements / Reference - G1 Cl 26
86d3302d-b451-5af6-942c-efd8f6ae0bf5 | note | Acceptance Criteria - Acceptance of Temporary Works Piling Platform
7cc71081-807b-52e2-b696-722effbd3105 | note | Frequency / Process Held - Once / 15 days prior to construction of Piling platform
96e1649a-b488-5661-8881-9518fa860a08 | note | Inspection – ACPL - H
9c187531-9c51-5317-b886-e9dc3223fa20 | note | Inspection – Client - H
bd0f74bd-d5ce-542b-98d2-7fe193254346 | note | Comments / Attachments / Records - Temporary Works Design HSID Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Design of Lifting Points (Casings)
7edf4cbd-ce2b-5fe4-a363-1810ede1ea0e | note | Requirements / Reference - Report FE-180535-01-R-01 Rev 1 G1 Cl 26 B54 Cl 3
e55bf11e-6699-5f18-8436-230b9f3945ac | note | Acceptance Criteria - Verify, by engineering calculations, that proposed method of lifting and stacking of piles will not cause any damage to the piles,
f744f3c8-3407-5a50-9609-43a6dfbf7668 | note | Frequency / Process Held - Once / 15 days prior to welding of lifting points on casings
3b8ac1c9-6293-5f37-9ec6-d22a4c334ec9 | note | Inspection – ACPL - H
2f2aa46f-b683-56a8-86ac-404fdeee226c | note | Inspection – Client - H
059dbbef-67da-5d85-93aa-419b8282bc46 | note | Comments / Attachments / Records - Temporary Works Design Test Records HSID Register
| signoff | AUTHORITY HOLDPOINT
| section | 3. Construction of Temporary Works
| checkpoint | 3.1 - Construction of Piling Platform
5325d56c-84b0-589a-ae73-5f5d2a84c50e | note | Requirements / Reference - G1 Cl 26
0262da39-c892-570e-890a-506e1fe0646a | note | Acceptance Criteria - Construction certification
55abeba5-9fd2-5813-9c0f-1809d5c7087b | note | Frequency / Process Held - Once / 5 Days prior setup of piling rig
3b6f964a-9bd8-5e86-b07d-5bbe86a6445a | note | Inspection – ACPL - H
a4941626-486f-5b4a-8213-27de65ec5924 | note | Inspection – Client - H
13a96189-cba2-5e20-a7b2-77b46dda74d5 | note | Comments / Attachments / Records - Temporary Works Design, HSID Register, Construction Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Construction of Lifting Points (Casings)
7a0e82cf-5a91-50a1-8ef5-8a424d1bd638 | note | Requirements / Reference - Report FE-180535-01-R-01 Rev 1 G1 Cl26 B54 Cl 3
5285b1a2-4120-5035-9602-9289e99b10d0 | note | Acceptance Criteria - Construction Certification
38c00f6a-2396-5928-ab9a-e5deadf4162d | note | Frequency / Process Held - Once / 5 days prior to first delivery of casings
e2dcbfef-1449-58f5-8ac6-28e046aa7b6f | note | Inspection – ACPL - H
1c2b838a-b924-524a-8b73-37a24d3c4673 | note | Inspection – Client - H
fb309d96-54da-55bc-94d8-2984a5cf506c | note | Comments / Attachments / Records - Temporary Works Design, HSID Register, Construction Certification
| signoff | AUTHORITY HOLDPOINT
| section | 4. Use of Temporary Works
| checkpoint | 4.1 - Verification of driving method
45721884-bc5c-5ad2-bfe0-b162cb5fd889 | note | Requirements / Reference - B54 Cl 5.3
2f686497-f586-5b25-802d-bab08a51ed97 | note | Acceptance Criteria - Details of proposed driving equipment and method together with certification, including calculations by CPE, EA verifying that under proposed setup and site conditions, nominated equipment will be used within its safe working capacities.
592e85a2-e3ce-5ced-872d-d935775e3395 | note | Frequency / Process Held - Once / Prior to setup of piling rig
52909127-3b7d-5352-a3cd-f46f133bd297 | note | Inspection – ACPL - H
2cf636b3-7ecb-5b53-a10a-77352f76f773 | note | Inspection – Client - H
b119bce3-6042-575d-a5af-92e127ace64c | note | Comments / Attachments / Records - HSID Register, Engineering Certification
| signoff | AUTHORITY HOLDPOINT
| section | 5. Welding Procedures
| checkpoint | 5.1 - Welding Procedure Specifications
3849f071-8aa0-5f08-8ad5-0e12bfcfab49 | note | Requirements / Reference - B54 Cl 2.6, B201 Cl 7.1.2,
24d968f0-15ca-519e-bd01-b15b752452fd | note | Acceptance Criteria - All welding procedures, welder qualifications and welding to confirm to TFNSW B201 for AS1554.1 Category SP
9ea83ce2-ccc3-517b-a6a7-d8e26d9a68ee | note | Frequency / Process Held - Once / prior to work commence
a5bad9ea-b8fb-5169-ae56-ced94c6738bd | note | Inspection – ACPL - S
4289dd37-97c1-5b6a-af1f-797a633f0ed7 | note | Inspection – Client - S
cea1af87-3a95-59f9-b53b-7fde76fd8b27 | note | Comments / Attachments / Records - Wagstaff Welding Quality Plan Wagstaff Method Statement
| checkpoint | 5.2 - Qualification of Welding Procedures
19902228-fff9-50d3-aea1-2bf49cf77477 | note | Requirements / Reference - B201 Cl 7.4.2
b1ff9127-1a0a-5cdb-aeb2-14bcea1d895f | note | Acceptance Criteria - Manufacture of weld procedure qualification test piece
ff3e98ad-da6c-5f78-945f-8aa9a40e1c0a | note | Frequency / Process Held - Once / At least 3 working days notice of time and location of welding and testing
b329b761-7e7e-5925-a4fb-6e144fe91737 | note | Inspection – ACPL - W
df5a75ba-8a3e-54c7-8d59-93dc4b8a054c | note | Inspection – Client - W
7fe6d5d3-e84a-561b-9030-5aedec2a1a14 | note | Comments / Attachments / Records - Welding Procedure Qualification Record Welding Procedure Specification
| checkpoint | 5.3 - Execution of Welding
b4f4b6d5-7447-55fd-98b4-ed8df66a9053 | note | Requirements / Reference - B201 Cl 7.5.15
f33a376a-addc-5d7e-a6a9-f0f83facd088 | note | Acceptance Criteria - Where the work includes the fabrication of similar items (900mm diameter, 1050mm diameter and 1200 diameter), inspect the first one welded (referred to as the prototype) and submit the required documents to the Principal prior to any welding of subsequent items. The prototype must be inspected by the Welding Inspector to check that the welding processes used are satisfactory, dimensional tolerances are not exceeded and that welding of further items will result in completed components which are within tolerance.
44f2b4dd-8bc0-508b-bbb1-07affefe1c2a | note | Frequency / Process Held - Once for each size pile casing / prior to commencement of welding
d3515311-b49b-5a20-b38e-034e0084d313 | note | Inspection – ACPL - H
d52415bc-7675-5321-8350-c5d5facbd35f | note | Inspection – Client - H
7c6996e4-19b2-5b8d-8634-ae5e4786c4af | note | Comments / Attachments / Records - Prototype FDR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Commencement of Welding
621eb897-c996-5d32-8fab-b2ee6daa4865 | note | Requirements / Reference - B201 CL 7.4.1.1
90a8833b-1f77-55f1-8c17-f3da6c2ff93e | note | Acceptance Criteria - Submission of Welding Procedure Specification A weld procedure can be used in production only after the Responsible Welding Coordinator and the Welding Inspector has reviewed and approved the PQR and WPS.
9178796a-ea92-537c-800b-3dc6bf06dab6 | note | Frequency / Process Held - Once / 5 days prior to commencement of welding
6e788e97-2bc5-5ed2-af8a-4647476a7566 | note | Inspection – ACPL - H
2bfc0d33-6e0f-545b-a0a7-de9fea800ed1 | note | Inspection – Client - H
bbc44c3b-09db-5525-b8f2-4749d3a844d2 | note | Comments / Attachments / Records - Welding Procedure Specification Welding Procedure Qualification Record
| signoff | AUTHORITY HOLDPOINT
| section | 6. Material Approvals
| checkpoint | 6.1 - Steel Procurement (ABFI Steel Casings)
4b1a6f1d-e3e5-5dcc-bf45-fa123afcbe8d | note | Requirements / Reference - B54 Cl 2.2 AS3678 Grades 250 or 350; or AS1548 (any grades); or AS1594 Grade HU 240 B201 Cl 5.2
1db0110e-69dc-5533-af53-c4fa00075193 | note | Acceptance Criteria - Casings as per Shop Drawings and Design Requirements Supplier Certification sent to Principal Valid certification of the steel manufacturer for the production of steel conforming to applicable standards issued by either JAS-ANZ or IAF
e743f114-1e5e-56a4-9926-9642b35c564e | note | Frequency / Process Held - Once / no later than 10 days prior to ordering steel
a37013a2-284c-535d-8b3f-065bf68fefb3 | note | Inspection – ACPL - H
22085d42-c437-531d-bf13-e9444ac4ef56 | note | Inspection – Client - H
af95ea16-86cd-57ed-bcfe-4bbfef0546fd | note | Comments / Attachments / Records - Mill Certificates Shop Drawings Suppliers Declaration of Conformity (SDOC)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Steel Verification Testing
d2b5be35-5e63-57c3-9c24-9e71961faac4 | note | Requirements / Reference - B201 Cl 5.3.1
3ed73d51-8647-5b33-bb80-98c890311afe | note | Acceptance Criteria - Steel verification testing in conformity to the applicable product standard on at least two samples.
93a3625f-937d-5b3b-9186-d2f311224d51 | note | Frequency / Process Held - Twice / prior to delivery
10e1451b-b99a-57b8-94d5-dbffb60d9c78 | note | Inspection – ACPL - W
d37b0873-5b90-57b7-bdea-250061e755f2 | note | Inspection – Client - W
8053216b-bf47-518c-b378-4a9d77d123f7 | note | Comments / Attachments / Records - Test Results
| checkpoint | 6.3 - Fabrication of Members with Splice Locations
605e3ab4-1537-5059-8d48-4d1ee1a5713e | note | Requirements / Reference - B201 Cl 6.9.1
ccb13818-baec-5c21-bbde-fbd542629d72 | note | Acceptance Criteria - Submit details of the design and position of the proposed splices for the approval of the Principal.
a03e6e5b-affb-5f3f-9525-72518ffd948a | note | Frequency / Process Held - Once / 10 days prior to fabrication
8535b1f4-5a4c-5117-ae96-4ef13b8caaa9 | note | Inspection – ACPL - H
820011f0-5044-50a9-9089-45f9a3246871 | note | Inspection – Client - H
79765558-a65f-503d-9320-d55944b8a159 | note | Comments / Attachments / Records - Design Drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Concrete Mix Design Approval
3c2da5f0-bd45-5872-8ecd-7a993ea0d3b3 | note | Requirements / Reference - B80 Cl 3.9.1, B80/A.1.2, A.2: Project Trial Mix preparation - AS102.2 Trial Mix Batch - AS1379
b91d9158-9919-592c-b665-9541184a4c39 | note | Acceptance Criteria - Concrete mix design as per design drawings and approved by Principle.
3eca4427-a943-5071-a9fa-0e0d15a29821 | note | Concrete Exposure Classification: B1
32c864a3-790a-55ba-84c8-9aac3168ed27 | note | Minimum 28 Day Compressive Concrete Strength: 40MPa
24cf104d-d344-52e6-a50a-4812ad3d2ad5 | note | Slump Flow Spread: 550mm +/- 50
d2ede887-7f23-57a5-8813-6dfe325c50a6 | note | VSI Rating (max): 0
81553869-cdcd-5852-9b38-30ecdb35545a | note | Sieved Portion: ≤ 15%
c8ce6682-24ac-5c3d-888c-93c1936b5e40 | note | Penetration: ≤ 10mm
997553ff-d551-5059-af1d-3d87cef6beb9 | note | Spread: <50mm
6b1dc6c2-c3d8-5d0b-bafd-6b1d1dadabe5 | note | Height: ≤10mm
7f993307-12d9-51db-ba1b-85acc4667515 | note | Frequency / Process Held - Once / At least 4 weeks prior to use of concrete mix
f5260a29-b79b-576a-9163-11cf0ba8621c | note | Inspection – ACPL - H
1946a882-5f19-5159-ad32-36249a1d776c | note | Inspection – Client - H
28bd8cef-8a6b-56f0-8d1e-6fda21844343 | note | Comments / Attachments / Records - Concrete Mix Design Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.5 - Certification of Concrete Crew
bb9e217a-d3fc-54b1-ae7e-2fb96d1e68f8 | note | Requirements / Reference - B201 Cl 7.2.3
36bef88f-c49c-527f-9087-63008dcdcd07 | note | Acceptance Criteria - Submission of concreting crew Grey Cards. In addition to the Concrete Supervisor, at least half of the remaining crew must hold a TfNSW Bridgeworks Concreting Grey Card.
a53bd7ae-84e6-58f2-9aeb-b12212f1d8ee | note | Frequency / Process Held - Once / at least two weeks prior to first concrete pour
1f15c03a-b040-5814-b0b5-9e0591068229 | note | Inspection – ACPL - H
43f213fe-11e9-59de-9d37-d405ca5941ad | note | Inspection – Client - H
81668df7-404c-5a3a-a491-7401f6617bac | note | Comments / Attachments / Records - Concreting Grey Cards
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.6 - Supply of Casings
f7c6a7ab-8942-5c38-afe2-e7e1c2c1ca8b | note | Requirements / Reference - B201 Cl 6.1 Supply AS/NZS4671 Fabrication AS5100.5
4cb6c440-47d7-54aa-9f22-654faf8fae4e | note | Acceptance Criteria - Casings as per Shop Drawings and Design Requirements Supplier Certification for materials and consumables sent to Principle.
6dc15518-ed09-5e08-af1b-b83da7d0eaee | note | Frequency / Process Held - Once / prior to fabrication of casings
60c87d58-ea8a-5e67-9f88-573383a1f692 | note | Inspection – ACPL - H
898d0b85-08c9-52da-bd13-cda41ad4bbcb | note | Inspection – Client - H
6d68794c-90ce-52d8-a299-29fe787716a9 | note | Comments / Attachments / Records - Shop Drawings Mill Certificate Suppliers Declaration of Conformity (SDoC)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.7 - Supply of Reinforcement Cages
0f1da4ec-0c1c-5eca-bbac-0c266f273337 | note | Requirements / Reference - B201 Cl 6.1 Supply AS/NZS4671 Fabrication AS5100.5
a6dfae6b-32a7-55d7-9dc7-35779404c639 | note | Acceptance Criteria - Cages as per Shop Drawings and Design Requirements Supplier Certification for materials and consumables sent to Principle.
27c95a25-9edb-503a-bec9-deb760294ac5 | note | Frequency / Process Held - Once / prior to fabrication of cages
485e0172-5ed5-53be-b0c3-d80a1e19bb93 | note | Inspection – ACPL - H
02d82259-9bb7-549c-83b6-9b673c3f4d0a | note | Inspection – Client - H
0cc33185-8ac9-590f-a2a1-ec3210afd21c | note | Comments / Attachments / Records - Shop Drawings Mill Certificate Suppliers Declaration of Conformity (SDoC)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.8 - Lifting and Transport of Prefabricated Cages
32de4da6-4dc5-5fe8-8d64-26d2347a89e1 | note | Requirements / Reference - B80 Cl 6.6.2
207eeed9-5d5e-5d33-888b-fdc84c591fd1 | note | Acceptance Criteria - Show on the shop drawings the design location of lifting and transport support points for prefabricated reinforcement cages, and mark these locations indelibly on the cage during fabrication. Show the lifting requirements on a drawing on durable material, attached to the cage prior to lifting. Submit to the Principal one copy of all prefabricated reinforcement cage shop drawings showing the size, type and location of load bearing welds, lifting and support points and lifting requirements. The person who designed the load bearing welds must certify the shop drawings.
712389e6-2215-5557-8ae5-6485f29debce | note | Frequency / Process Held - Once / two days prior of intention to transport cages to works
41ad57ea-9432-5546-853f-65133d7e885c | note | Inspection – ACPL - W
53f5e59b-c41c-5d32-9c30-5bbc7a7e1535 | note | Inspection – Client - W
9cf3b7a5-2dd5-5afd-a7e8-71049eeb9811 | note | Comments / Attachments / Records - Shop Drawings
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
4ed46f25-61eb-51bc-ba6e-7499b77b80f8 | button | Any non-conformances? | YES, NO
9ff1e652-03b0-5c9b-8f50-fad469abb374 | textbox | No's:
8c72bf20-2949-5ac4-92c9-8b9f57c5d5b0 | button | Closed Out | YES, NO
f9783ba7-cdf9-5551-b915-2b92a38565a3 | button | All work has been satisfactorily completed. | YES, NO
17fe3abe-e914-5f35-9ab5-2bc319828efe | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
50153252-2dc0-5193-8a8f-0f7c39cecb22 | textbox | Lot Verified By:
4902f62a-7cf3-519a-846c-ad42ac7bf026 | textbox | Lot Closed Date:
7469d834-c7c7-5255-a7b7-2a655d9315b5 | button | Submitted to Client | Yes, No, N/A
a8040bda-ca91-530d-a6fa-bcc6c7f486be | button | Reviewed by Client | Yes, No, N/A
3990b4ed-9e74-5dfb-8690-7e6fce0e1055 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B2.1 - FRP Abutment B | itp | ITP-B2.1 - FRP Abutment B | e54674b0-cf64-40ac-a835-fa363b0b504a
| section | Lot Information
| checkpoint | Lot Information complete
34572547-a7e8-467e-9773-83e1fee42fea | textbox | Lot Opened On
400f42f0-7f22-4354-b561-a8b82a9d2486 | textbox | Date of Works
434ae863-3753-4ce8-a817-5d5ea66d887f | textbox | Lot Type
c729df31-c1e9-4a7d-8ee0-3f438aad59c6 | textbox | Start Chainage
4fcd078f-6e96-4ed8-9d87-ca2bdaed8616 | textbox | End Chainage
6449ef26-918f-4266-a38e-c1702238ed62 | textbox | Offset
5ef29240-0120-50d7-a1cd-27d47622feb6 | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Concreting Personnel
4127542c-4395-5009-adab-1829dea96711 | note | Requirements / Reference - B80 Cl 7.2.3
f7c6034f-f563-52dc-b603-5525a77b4666 | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
e614ea38-6620-5151-b002-9d4b755d61c4 | note | Frequency / Process Held - Each concrete pour
3c59382a-4c1e-54a2-a394-40b1d5484992 | note | Inspection – ACPL - H
7455e3b6-e129-57be-9593-65d1b8c5dba1 | note | Inspection – Client - H
e5322ba1-1382-54d3-9f6b-2a34cf91a471 | note | Comments / Attachments / Records - Hold Point
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Formwork Certification
f3e48cb2-9469-5b52-a197-8494177249ab | note | Requirements / Reference - B80 Cl 5.2.3
e2286b87-fcda-5e63-95e2-3ef9ab5519cc | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C.
0ef47e37-f43c-53aa-9d46-96161ad8bae4 | note | Frequency / Process Held - Prior to constructing formwork
7263dcfb-34c7-52ce-a433-33962c58d0e1 | note | Inspection – ACPL - H
1bef3a36-8865-510b-a83a-29aeaf0a67fd | note | Inspection – Client - H
479aa5fa-4487-56e3-b2ed-cf48f7e85530 | note | Comments / Attachments / Records - Hold Point
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Reinforcement
cfce111e-29b3-5bf1-aa1d-f2b37c37db53 | note | Requirements / Reference - B80 Cl 6
224daf01-2028-51b7-8588-ae4b6513a0c7 | note | Acceptance Criteria - Steel reinforcement to be certified by ACRS and to AS/NZS 4671 Reinforcement to conform to the type and grade specified in drawings Store and protect the reinforcement to prevent damage, corrosion or contamination Chairs and spacers to comply to AS/NZS 2425 Lap and splice lengths to conform to the below tables or as specified on the drawings and Cl 6.4 Lap lengths for piers: Lap lengths for bridge deck: Reinforcement is to be tied, and if required to be welded, must conform to Cl 6.5. Where cathodic protection, or provision for future cathodic protection, is required as shown on the drawings, all longitudinal reinforcement must be tack welded to a N12 bar to maintain electrical continuity in accordance with AS 2832.5. The electricity connectivity of reinforcement is to be tested in accordance with AS2832.5 Support reinforcement from the formwork or blinding with concrete chairs or spacers Supply and install cast-in items as per drawings[KC1] [IY2] [KC3]
53807ae0-efe4-5bb4-8871-0f5cdbd020af | note | Frequency / Process Held - During forming up works
9681116a-f3b0-5c12-8cad-021e14b3f35d | note | Inspection – ACPL - S
b2a6c8d0-2f11-5f8c-ab39-8abdf4355879 | note | Inspection – Client - S
| section | 2. Construction
| checkpoint | 2.1 - Survey
1b3185ca-a78b-5bc8-a474-8640432fbd19 | note | Requirements / Reference - B80 Cl 5.8
3bd2a7ee-9357-540c-a475-02d991f0d56c | note | Acceptance Criteria - Control all survey activities in accordance with TfNSW G71 Maintain records for checking and verification of items as planned and as measured Fabricate and erect structures to achieve specified dimensions, levels and alignment
a7ea7ae6-b933-57c8-a22d-f1e1cedb15f9 | note | Frequency / Process Held - During construction works
1a669058-914f-586a-a502-aaf6dc5d0267 | note | Inspection – ACPL - S
bac34535-a8ac-5748-86cd-99516fd9ec0c | note | Inspection – Client - S
| checkpoint | 2.2 - Prefabricated Cages
40bb82b3-e3de-5278-a4e2-42724b9e85b7 | note | Requirements / Reference - B80 Cl 6.6.2
31943a7e-0770-5ec3-a57f-0eec02592c97 | note | Acceptance Criteria - Detail design location of lifting and transport support pins for prefabricated cages Submit to the principal shop drawings of the prefabricated design with certification, at least 2 working days’ notice of intention to transport
ff36fa7c-d755-5ee0-bc8e-2b947a7bbcf7 | note | Frequency / Process Held - Prior to delivery to site
b6d8f2f9-e695-5552-a8b0-de9d0e9ac70e | note | Inspection – ACPL - W
1403c0db-b400-563f-9a0d-b40d3e28d126 | note | Inspection – Client - W
1519e15a-954a-5c62-b6d8-61a388d0b7b4 | note | Comments / Attachments / Records - Witness Point
| checkpoint | 2.3 - Formwork Erection
8e5f1d06-28b1-5c99-96f8-a073f1a74a01 | note | Requirements / Reference - B50 Cl 5.6
6d476f89-b183-5404-9656-a6190a74c5a2 | note | Acceptance Criteria - Erect formwork in accordance with certification and drawings Erect panels to be neat and symmetrical, mortar tight and to follow the grain. Treat the interior surface of the formwork and removable items.
52ca1600-e271-5c42-bea7-524ca0356f43 | note | Frequency / Process Held - Following formwork certification
3d0ef54f-19a3-5ab2-9d4d-123e20f52ce5 | note | Inspection – ACPL - S
18c28ebd-dbe0-5532-9c15-67c1f1e2dbc6 | note | Inspection – Client - S
| checkpoint | 2.4 - Construction Joints
9dc334be-f117-5998-bf5c-2fd8415fd708 | note | Requirements / Reference - B80 Cl 5.4 & 7.4
b853d5e5-52c4-536e-ba88-e23f5b7be09f | note | Acceptance Criteria - Locate construction joints as shown on drawings, submit details of any other proposed joints Do not locate joints in salt water from 1.0m below min. low water level to 1.0m above max high tide, unless detailed Locate joints at the base of columns or walls at least 100mm above tops of footings or pile caps Roughen surface to 3mm Remove loose material and clean surface
fd346ca0-638a-5a0a-8c65-06e373f894c0 | note | Frequency / Process Held - During forming up works
2bb34203-218f-50e0-8288-609439251dfe | note | Inspection – ACPL - S
1431c108-4606-5e97-8df3-3177e1208cd0 | note | Inspection – Client - S
| checkpoint | 2.5 - Tolerances
1e68a72f-ba14-5dda-8d23-c6dc17620ae5 | note | Requirements / Reference - B80 Cl 6.7 and 9.4 Bonacci Structural Concrete Cl 4
8f1d7665-9a26-57e6-b33f-8de4c4985b70 | note | Acceptance Criteria - Concrete cover to be 50mm unless specified otherwise in the Drawings, and with cover tolerances as per Table B80.16 Tolerances for ends of reinforcement ± 50mm Spacing or bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15 Final concrete surfaces must conform to table B80.18
5bf77987-9102-5bd8-9b8f-45bc8864f33a | note | Frequency / Process Held - While forming up, and following pouring of concrete
6ce1d3a6-2755-59aa-a84e-b5110f1f275b | note | Inspection – ACPL - S
17715585-ce1d-55f6-b910-d9b1cd6d9708 | note | Inspection – Client - S
| checkpoint | 2.6 - Supply and Delivery of Concrete
161e1c15-6dda-5682-a2d1-94de8bf639c9 | note | Requirements / Reference - B80 Cl 4.1
dd080a1f-ff34-58b3-87bd-3f9f8c5f8e29 | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
436b78f4-fea9-5719-8094-0d68701ab9ce | note | Frequency / Process Held - During concrete delivery
be534831-4536-5840-ae06-b111bf6c8c07 | note | Inspection – ACPL - S
fe1cb9f5-2368-5e5f-b779-27d24e0386f4 | note | Inspection – Client - S
| checkpoint | 2.7 - Certificate of Conformity
2c9920d4-7d63-5dac-9cb6-653b74cfc236 | note | Requirements / Reference - B80 Cl 7.5.2
013194a3-31e3-5387-abeb-6c6d0a103d1a | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working days prior to commencement a Certificate of Conformity of formwork, reinforcement and embedments for the member(s)
83b39ade-c736-5042-a059-16ae1a3aeed4 | note | Frequency / Process Held - Prior to pouring these member(s)// each placement of concrete in the works
bfc3e55c-e901-5999-a62c-fc5cbca358d1 | note | Inspection – ACPL - H
e79fc32d-3d78-5e3b-906d-ec6610282e82 | note | Inspection – Client - H
8ed4678a-8a3d-53cf-a79d-f74a44a6a3b8 | note | Comments / Attachments / Records - Hold Point
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Placing, Compacting and Finishing Concrete
22cb5347-9fe4-5d35-a682-e92a1e8d8de9 | note | Requirements / Reference - B80 Cl 7
5a5e8ecb-7a1a-5e76-81c8-26400ff38c6e | note | Acceptance Criteria - Place, compact, finish and cure concrete as to: Prevent segregation or loss Prevent premature stiffening Prevent non-conforming displacement Produce homogenous and monolithic product Fill formwork to intended level, expel trapped air and surround all reinforcement Provide specified finishes Control cracking Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Do not place against concrete that has already set or will create cold joints Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
268a5db3-2036-5ce9-a758-a3a494e3e9e9 | note | Frequency / Process Held - During concrete delivery and finishing
8ce76d5e-34c4-526f-9303-79b12024fa99 | note | Inspection – ACPL - S
9b66f330-07b0-5382-a9aa-082882574d03 | note | Inspection – Client - S
ba7f4f46-7e94-515c-b899-5f2e6539268d | note | Comments / Attachments / Records - - Concrete delivery dockets - Concrete test results Survey report
| checkpoint | 2.9 - Placing, Compacting and Finishing Concrete
0377dc53-ed35-50be-9d5d-d90737187c33 | note | Requirements / Reference - B80 Cl 7
58eadd4e-fd7b-5acf-9bde-794b110ad0f9 | note | Acceptance Criteria - Place, compact, finish and cure concrete as to: Prevent segregation or loss Prevent premature stiffening Prevent non-conforming displacement Produce homogenous and monolithic product Fill formwork to intended level, expel trapped air and surround all reinforcement Provide specified finishes Control cracking Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Do not place against concrete that has already set or will create cold joints Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
6afaa811-e056-565c-b9c8-28692b8e71c3 | note | Frequency / Process Held - During concrete delivery and finishing
87994b89-9ff1-5008-8d69-d194e82d696b | note | Inspection – ACPL - S
f1d22f74-4c04-54f6-a22c-f0a4914a8877 | note | Inspection – Client - S
f1eb0e7b-6d62-5986-9ffa-e350f9ea873b | note | Comments / Attachments / Records - - Concrete delivery dockets - Concrete test results - Survey report
| checkpoint | 3 - Weather
5f562796-1c56-50da-bb09-a2035dbf74fe | note | Requirements / Reference - B80 Cl 7.3
0dc9c187-2988-575a-86b9-2cb576aea06b | note | Acceptance Criteria - Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent
af7c393a-4fda-5038-a660-c0863b99abcc | note | Frequency / Process Held - During concrete delivery
afcef985-370d-52fc-8211-4d4393fed74b | note | Inspection – ACPL - S
33b5572a-35ad-5b93-940e-9f959439c4fc | note | Inspection – Client - S
| checkpoint | 3.1 - Curing
eacc689b-1c5e-5c1d-93f3-b417d6402447 | note | Requirements / Reference - B80 Cl 8 B80/E
9e808362-1f81-5c97-96fb-e7677ec24e79 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime Ensure wet curing surfaces are completely covered in hessian with plastic sheeting Curing compounds to conform to table B80.17 Provide certificate of conformity from curing suppliers, sampling and testing. Sample and test at a rate of not less than one test per 3000 litres, or part thereof, supplied to site Do not use wax emulsion compounds on deck surfaces Apply curing at specified rate in two coats to form a continuous membrane B2 exposure classification requires 14 days wet curing Ensure that curing and insulation is carried out to the specified methodology to ensure thermal loss does not occur
6519a34e-929a-50e4-b3c0-b02780e0e91e | note | Frequency / Process Held - Following finishing of concrete
2d97b376-4b79-5851-9e3a-8f86acbaed3c | note | Inspection – ACPL - S
aba68c20-6176-5b66-9f32-56f2cf7cf966 | note | Inspection – Client - S
| checkpoint | 3.2 - Formwork Removal
cbf18ca6-de7c-5a13-aade-e5010ba3af32 | note | Requirements / Reference - B80 Cl 5.9
33dbd293-c267-53c6-aab6-79351f7b05c9 | note | Acceptance Criteria - Remove formwork in a way and time that achieves specified characteristics and prevents damage Adhere to the minimum stripping times as detailed in CL 5.9.2 and table B80.12
a6b310d5-2bf6-5faa-a5b9-230ad98f05a5 | note | Frequency / Process Held - Following completion of curing
ebd9729a-cb4b-5382-9b49-3c4bff076d90 | note | Inspection – ACPL - S
607a5a61-5386-5de0-bf5f-1efd19cec668 | note | Inspection – Client - S
| checkpoint | 3.3 - Concrete Cracking
d95a25ac-4bc1-5e1c-b6ee-5a3ff42c787b | note | Requirements / Reference - B80 Cl 9.3
e677a5f1-058d-5c89-b2d4-c947ecbbf225 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions
29f88f77-e3d9-5dd8-8e7d-3d31369c0307 | note | Frequency / Process Held - Inspection following removal of formwork
70d6effe-594f-5b5c-9175-e32076911ee0 | note | Inspection – ACPL - S
37f07859-19ac-58c2-98b3-5d3fc7e55c72 | note | Inspection – Client - S
| checkpoint | 3.4 - Early Trafficking
8aac6b08-181d-544a-aad9-c0f2484e18fa | note | Requirements / Reference - B80 Cl 9.9
4dadb0d9-bc26-5eea-b4b8-d7a9bf31f5ce | note | Acceptance Criteria - In the event early trafficking of the bridge deck is requested, at least 2 working days prior to commencement of early trafficking, submit the “strength versus age” relationship of concrete, with supporting test results, and evidence of completion of curing Hold Point cannot be released in the event of insufficient concrete strength test results, or if curing has not been completed. Make good any damage arising from early trafficking of the bridge deck.
f7632be3-b07e-5c33-9e68-13a0ea4010f7 | note | Frequency / Process Held - Prior to any early trafficking of the concrete bridge deck
cfbe2988-3e88-5d46-a0b1-6a67fe9ca988 | note | Inspection – ACPL - H
4492660c-eec7-5983-9113-a540a6063ec2 | note | Inspection – Client - H
4a1612bf-a398-5247-ace7-5f21fd9ad17e | note | Comments / Attachments / Records - Hold Point
| signoff | AUTHORITY HOLDPOINT
| section | Submission
| checkpoint | 3.3.1 - As-Built Survey
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
376c485b-6a34-52e2-9d2d-919e8f8c6cd9 | button | Any non-conformances? | YES, NO
af181577-a480-576a-8433-b184c9ae3792 | textbox | No's:
ffd7232e-b092-5e96-92c5-85192d3b8e1d | button | Closed Out | YES, NO
67bd6e5c-fc55-54cb-881c-b265e9dd98fc | button | All work has been satisfactorily completed. | YES, NO
78361859-8ffe-5dd0-9aa9-854dd13b3281 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
69846e84-d74b-5bf0-a7ac-b486b307437d | textbox | Lot Verified By:
5e477578-6811-5d27-bd52-42622253a512 | textbox | Lot Closed Date:
33026d2b-20bd-54f1-9cd9-4bd9990b4d19 | button | Submitted to Client | Yes, No, N/A
f5352c4a-ce2f-538b-8ed8-c88b78998621 | button | Reviewed by Client | Yes, No, N/A
c5e23947-9e52-53a7-b408-80e4995870a6 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B2.P - FRP Preliminary Works | itp | ITP-B2.P - FRP Preliminary Works | ebdd4591-db03-411c-beb2-3081f3e95472
| section | Lot Information
| checkpoint | Lot Information complete
abd11236-8c10-4ded-9de6-e2de0c6ce02e | textbox | Lot Opened On
38493668-0fba-4499-b833-d8db56526618 | textbox | Date of Works
4ffe40a6-041f-4a4c-802a-54233429090a | textbox | Lot Type
75b1a434-e3ac-475a-9ff8-6f2a646b91b3 | textbox | Start Chainage
e54f8582-bba8-4523-96ae-3d6d0f511081 | textbox | End Chainage
95996600-672b-4930-ae8f-0d0785758724 | textbox | Offset
cfd2c9d5-a69e-5d78-8959-452303895ce6 | textbox | Control Line
| section | 1. Prelims
| checkpoint | 1.1 - Safety Review
8d2ccd26-dcc6-5b98-a7a1-e1c6a733b928 | note | Requirements / Reference - Project Safety Plan
95deaa49-bed3-57dc-a09e-ef75a11c8e51 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved.
a22d7a49-34de-5fc6-9cfa-d8538f5710e4 | note | Frequency / Process Held - Before Commencement of Works
372a5746-36d2-5f88-b05d-62d75f8cb092 | note | Inspection – ACPL - W
671af131-9a53-560a-855a-564c68bb526d | note | Inspection – Client - S
aa3abf95-b83a-5dca-924e-40ad4bccc507 | note | Comments / Attachments / Records - Signed SWMS
| checkpoint | 1.2 - Environment
e7732465-b943-5bff-8d2c-0213e70811e0 | note | Requirements / Reference - Project Environment Plan
51d40024-a018-5121-9a42-f1a14ec70c8f | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc as a direct result of construction activities.
2bfd773b-e363-58a9-8b2a-ac7d21389288 | note | Frequency / Process Held - Before Commencement of Works
2e7edc97-cbe8-5401-b15d-49c9f4370d33 | note | Inspection – ACPL - W
7ed7498d-ce80-5b7b-b83d-e543e2476c63 | note | Inspection – Client - S
ddde0f92-efd3-5c85-b34b-59a497571c49 | note | Comments / Attachments / Records - SECP AQMP
| checkpoint | 1.3 - Submission of Nominated Mix Design
65d4501d-3167-50fb-9c5e-9e49ce0a505a | note | Requirements / Reference - B80 Cl 3.9.1
6e35dd24-3b17-5f0c-8fcd-c1233007ad0a | note | Acceptance Criteria - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
5980d9a4-647e-5fd1-9d2a-4a8d0f99fbfa | note | Frequency / Process Held - Prior to ordering concrete to site
bd82c19c-c32d-5cf4-989c-0dbb41a22510 | note | Inspection – ACPL - H
2789b779-9138-56a2-bcd9-a9a0f14d0970 | note | Inspection – Client - H
51386e60-8ea4-5afe-a9f8-2ffe1c354f6f | note | Comments / Attachments / Records - Mix Design Submissions - HP107 - HP109 - HP128 - HP132 - HP134
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Concreting Personnel
3b9c468f-db83-57db-acae-a0b5f3bf505c | note | Requirements / Reference - B80 Cl 7.2.3
fd0a5f32-47b9-53c1-b1b8-756fecf83152 | note | Acceptance Criteria - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
8f627e50-6f78-5e88-8083-667e719f25f0 | note | Frequency / Process Held - Prior to first concrete pour
d0888982-faf2-5995-a8bd-fdcda03623a1 | note | Inspection – ACPL - H
cf2f5847-adae-5341-a7d4-b7342c5f5676 | note | Inspection – Client - H
98687b5c-70bc-5c6b-abd7-5ea02abb59d7 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards - HP135 - HP136 - HP137 - HP199 - HP243
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Test Members
03101db3-b4ae-527f-ab53-e208e9b912c9 | note | Requirements / Reference - B80 Cl 5.3
ed6ec487-aba6-5756-aee6-7bb96756eac7 | note | Acceptance Criteria - Provide notice in writing to the Principal, at least 2 working days, of the upcoming placement of concrete for the test member(s) In the event the test member does not meet the design, reassess the process with the Client and pursue alternatives if necessary
f95c10e2-f4a3-5815-abd1-a7df10bdd14b | note | Frequency / Process Held - Prior to commencing concreting for permanent works
d9393138-8dd4-57c0-9098-c0c9d6951726 | note | Inspection – ACPL - W
35fc6284-da09-5617-a07d-21c8a2e6ebf3 | note | Inspection – Client - W
156a5d22-c299-5ea5-aac2-61c2044d0854 | note | Comments / Attachments / Records - WP009
| checkpoint | 6 - Fabrication of Reinforcement
4a79564b-e034-575a-a956-718b07660c66 | note | Requirements / Reference - B80 Cl 6
84fa87ae-dfa3-5fa1-9adb-b82826e61761 | note | Acceptance Criteria - Steel reinforcement must be certified by the ACRS for conformity of the reinforcement production and processing to the requirements of AS/NZS 4671 Chairs and Spacers must comply with AS/NZS 2425. The smallest chair or spacer dimensions must not be less than the specified cover, and the largest dimension must not exceed 1.8 times the cover. Fabrication tolerances must be as shown in Table B80.14
7bdb4e4d-31f3-5ee7-be6d-ebfed4589cfc | note | Frequency / Process Held - Once / Prior to FRP
83c6e7b2-f0f0-563f-85ac-122cf2a66cf1 | note | Inspection – ACPL - S
41759b26-f855-5476-8626-711f02bfa6b5 | note | Inspection – Client - S
558fe19a-8c08-5f7d-8b74-c48553b1885b | note | Comments / Attachments / Records - Product Certificates
| checkpoint | 7 - Welding Operations
d8d9a626-fa5d-5400-9698-a2957128d854 | note | Requirements / Reference - B203 Cl 4
34971ff7-98d6-5e84-9f78-b7a366ced744 | note | Acceptance Criteria - Prior to the commencement of welding of steel reinforcement for the Works, submit the following: (a)welding personnel names, roles, qualifications and experience; (b)welding procedure specifications (WPS) for the required welding; (c)welding procedure qualification records (PQR or WPQR) for the applicable WPS; (d)proof of conformity of proposed welding consumables to this Specification.
bcc7d476-48f5-5fc1-955f-7bc54a710fa0 | note | Frequency / Process Held - Once / 5 days prior to welding operations
9e243e6f-f97f-52f6-86c5-c9af4fd19499 | note | Inspection – ACPL - H
1b90d145-e6bf-548d-b8e5-ff2c75d561d0 | note | Inspection – Client - H
07609bd4-f50c-5d26-8319-7a3395f844f8 | note | Comments / Attachments / Records - Welding Qualifications WPS/WPQR - HP047 - HP173 - HP180 - HP181 Welding Consumables
| signoff | AUTHORITY HOLDPOINT
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
a36c7a03-c324-56f7-a8bb-7753e7a0672a | button | Any non-conformances? | YES, NO
eab65956-96d2-5e8e-87ab-bf28180d18d6 | textbox | No's:
ddd501c4-b620-56d7-86a2-2699d19f0164 | button | Closed Out | YES, NO
2b584c93-80d2-57bf-84dd-407f7b07588f | button | All work has been satisfactorily completed. | YES, NO
3222e54b-31b5-55e6-9b2c-bc7f5f02f382 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
eae562fa-2531-54cb-abc4-b1650d4f6f4a | textbox | Lot Verified By:
98540860-7ec3-50dd-a50e-3da2c1382130 | textbox | Lot Closed Date:
e425bc3a-c7d7-5730-88ea-7788662c053d | button | Submitted to Client | Yes, No, N/A
2dcb21be-d891-52c5-aec2-09a0f7b9a8cf | button | Reviewed by Client | Yes, No, N/A
cca1501e-4c40-58e8-9e35-929135f6a568 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B3.6 - Girder and Bearing Installation Span 6 | itp | ITP-B3.6 - Girder and Bearing Installation Span 6 | f42fc1f9-f9d0-423a-8549-284c04b78846
| section | Lot Information
| checkpoint | Lot Information complete
c805a72a-1584-4f7a-9fb3-a9c6a576b43d | textbox | Lot Opened On
7042fdc0-0f34-4c22-a070-aa31d227ca73 | textbox | Date of Works
c6a0e993-477e-4759-b2e3-4e72587df808 | textbox | Lot Type
166909a6-bf61-4c2f-9176-e938c7781d0f | textbox | Start Chainage
47d36972-2cc7-43f9-b700-96934a4a4764 | textbox | End Chainage
a309a232-123d-4265-abb2-93d61589a1f3 | textbox | Offset
cd7d5895-b476-532b-9ca5-37b76c435cf4 | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
9d9f6420-2143-5cbf-bc44-e22be8c8da38 | note | Requirements / Reference - Preliminary Works (FRP) ITP
14d92d5f-c8a6-5474-a794-362cabafd929 | note | Acceptance Criteria - Sign-off of ITP-B3.P FRP Preliminary Works ITP
38df1ed4-a9cf-512c-a8ae-83034027041d | note | Frequency / Process Held - Once / Prior to Construction
54ed2047-7a3d-53bb-8a17-417e269e3e67 | note | Inspection – ACPL - H
4dd2bb74-c60f-5397-b779-2a89a5b4351e | note | Inspection – Client - H
e5418bcf-6d44-5a3e-a3c1-f21f2564494c | note | Comments / Attachments / Records - ITP-B3.P
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Use of Temporary Works (Girder Walkways)
13c3ab0d-e3a7-5429-96b6-30e7bce8061c | note | Requirements / Reference - G1 Cl 26
c51525b3-3bb3-595e-9e72-e28430aa2b62 | note | Acceptance Criteria - Submit construction certification of girder walkways from a chartered professional engineer with membership of engineers Australia.
b30d47fb-35bc-5605-a086-62ef7a015cf9 | note | Frequency / Process Held - Once / Use of Temporary Works
f681411d-4622-582a-ae32-7bd2a7a566f4 | note | Inspection – ACPL - H
770b150c-f061-568f-805f-344a2e0bd1bb | note | Inspection – Client - H
70d7ae6d-0e36-50a4-aca7-38d35fc1e8e9 | note | Comments / Attachments / Records - Construction Certificate
| signoff | AUTHORITY HOLDPOINT
| section | 2. Girder Assembly and Bearing Installation
| checkpoint | 2.1 - Joint Survey Details Submission
0e1e53e0-8ecd-57d6-a5fb-9943bab80959 | note | Requirements / Reference - G71 Cl 2.10.1
19627258-6622-5c7e-8a3a-ec950b3a610e | note | Acceptance Criteria - Survey date and location, surveyors name, description of methods and equipment to be used to be submitted to principle.
a7fb31e9-3262-558f-941d-a258cc6156ca | note | Frequency / Process Held - Once / at least 3 working days prior to commencement.
af124aab-a54b-5c33-91c8-5610b37e823b | note | Inspection – ACPL - H
5b9853e2-6bfd-51c2-9239-0891fad6f83e | note | Inspection – Client - H
cb88ce89-9ce2-5167-a905-339f8a15bf47 | note | Comments / Attachments / Records - Method Statement
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Survey Set out and Installation Methodology
03aca195-5c02-5068-b5dc-cf9248b107a3 | note | Requirements / Reference - B284 Cl 5.3
f450ab88-d5be-57ee-b877-256d3e1e0355 | note | Acceptance Criteria - Submit a certificate confirming that the proposed installation complies with specification and drawings. Certificate to include Survey Report verifying that the position and level of all temporary supports are in accordance with the Drawings or Work Method Statement Survey Set out as per design drawings
70739ad6-b376-5b4e-b051-97e06e24bd5d | note | Frequency / Process Held - Once / 2 days Prior Fixing of Bridge Bearings
046635f7-2e44-54b4-acc2-d18f1dfc27f5 | note | Inspection – ACPL - H
6d75c7cf-3d64-53e2-96ff-5f8f43a6ea3e | note | Inspection – Client - H
eeffd3f3-32c2-5274-85dc-3ef5b9b3072c | note | Comments / Attachments / Records - Method Statement Survey Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Submission of Joint Survey Results Pre-alignment Survey
84606f53-30a7-53dd-8313-c41759449b10 | note | Requirements / Reference - B150 Cl 4.3 G71 Cl 2.10.2
19dd58d6-cca4-5be5-8782-f2614e7b91dc | note | Acceptance Criteria - Set all bearings to achieve the correct final levels and inclinations, making allowance for and taking into account for variations in hog from design, as specified in the Design Documentation. All falsework and temporary supports must have adequate provision for adjustment to achieve the required profile detailed in the Design Documentation. Survey Report, including any calculations made to determine quantities, at least one working day before disturbing or covering up area of joint survey.
8da6bfd5-6d5c-59ce-9d72-c9fccb5ed3c1 | note | Frequency / Process Held - Once / at least 1 day prior to covering area of joint survey
dbb2ea0b-cc90-5774-99ff-2fa44a35084a | note | Inspection – ACPL - H
00a25258-0f74-5401-a1b1-ddeba7187737 | note | Inspection – Client - H
9b0cf0f0-6726-507d-8e67-b6d12012c8da | note | Comments / Attachments / Records - Survey Report Pre-erection certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Abrasive Blast Cleaning
69ae87a6-7a81-58e9-8816-9889629dcd06 | note | Requirements / Reference - B220 Cl 4.2.3
ac25024f-043e-5e2a-ac6b-f530b70ac6b2 | note | Acceptance Criteria - Notification of commencement of abrasive blast cleaning, at least 2 days prior, including confirmation of completion of rounding of sharp edges and corners.
64ce3c1e-8762-5127-805b-e416d5e8fa41 | note | Frequency / Process Held - Once / 2 days prior
acda43e8-1e13-59e0-9705-0ba8478f9989 | note | Inspection – ACPL - W
0586d007-bb13-5802-95d7-e8602eb00726 | note | Inspection – Client - W
16058bc3-29a2-57a5-808e-6172b90165cf | note | Comments / Attachments / Records - Notification
| checkpoint | 2.5 - Flatness of Bearing Attachment Plates
e418b9e1-a280-504d-8d41-f786e79019e7 | note | Requirements / Reference - B201 Cl 6.22.5
c9fb5376-2fd5-59a5-8d60-beed1b1394d9 | note | Acceptance Criteria - The flatness tolerance ∆ of the attachment plate, measured in conformity to Figure B201.1, must not exceed the lesser of 1 mm and b/1000, where “b” is the plate dimension measured in any direction.
b095852c-d0e2-515a-8c20-e425c28f72e4 | note | Frequency / Process Held - Once per plate / Prior to installation
4f1ed1c4-82e1-5d63-9c39-38e282cda0b8 | note | Inspection – ACPL - S
be396889-573c-56ec-9180-e74d474b2486 | note | Inspection – Client - S
fa5923cf-b538-5f2a-89e0-dac1bb295864 | note | Comments / Attachments / Records - Shop Drawings
| checkpoint | 2.6 - Install Bottom Steel Attachment Plate and Grout Sampling
234855d6-e1b7-53a3-86e0-2f40dc0713e3 | note | Requirements / Reference - DRG-1036 Sheet 36 B284 Cl 2
050d8856-a676-5f9d-bc8b-6f60ee9b00b2 | note | Acceptance Criteria - 1. Drill and tap hole in steel bottom attachment plate to suit M10 levelling bolts.
0b40e97d-7b7d-5c21-8e5c-3138f32317a1 | note | Frequency / Process Held - Once / Prior to installation of Bearings
16149019-efc6-5055-a7b2-c5d231ba3a5a | note | Inspection – ACPL - S
2fa2d0be-e9d1-58b7-986d-aa01c6e130a3 | note | Inspection – Client - S
e15c07c8-7ec8-5cc1-9212-9b7cabfe4e75 | note | Comments / Attachments / Records - Checklist Grout Pour Record Sheet
| checkpoint | 2.7 - Secure Epoxy Blocks and Top Steel Attachment Plates to Underside of Girder
072ea6d6-4f62-535f-879f-768b4cfe4d16 | note | Requirements / Reference - DRG-1036 Sheet 36 & 37
1a115037-1b04-59ed-8a2a-a2e2f0618e97 | note | Acceptance Criteria - 1. Secure pre-moulded epoxy blocks and steel attachment plates to underside of girders with hexagon screws (Grade C) and epoxy resin. Note, ensure correct attachment plate reference is installed.
fdcf6803-2666-5459-81c1-288df45ba10c | note | Frequency / Process Held - Once / Prior to securing bearing top plate to top attachment plate
8a8b7489-d1a7-51da-bc59-beb1f8cd59a2 | note | Inspection – ACPL - S
f68e3fcd-30ba-5a94-922d-2a686156cc19 | note | Inspection – Client - S
c69e180b-9aef-5cde-a9da-ce099e2ba2b1 | note | Comments / Attachments / Records - Checklist
| checkpoint | 2.8 - Install Bearing
5366adaa-d9de-5132-8a0f-6a4b7eadc0a0 | note | Requirements / Reference - DRG-1036 Sheet 36
66656474-f397-509a-ae4c-516ffdf3d4eb | note | Acceptance Criteria - Install Elastomeric Bearing on bottom steel attachment plate.
d4075f04-ba29-593f-b1ed-97d22dc8f367 | note | Frequency / Process Held - Once / Prior to landing girder
b1ba9aac-af9b-5afe-84aa-e95a65c7933b | note | Inspection – ACPL - S
89105656-4971-5b8b-9ac6-073a87f6bc9f | note | Inspection – Client - S
e8d2559b-b058-5d18-813c-e10e6c10d868 | note | Comments / Attachments / Records - Image
| checkpoint | 2.9 - Survey of Bearings
b2619b34-a030-5726-b1df-8a5223fcbcf8 | note | Requirements / Reference - B284 Cl 5.3
fbb380a5-cc3c-5910-9ba6-9bc646c9dfee | note | Acceptance Criteria - Carry out verification of positions and levels of all permanent bearings and temporary supports as a joint survey in accordance with TfNSW G71. Position Bearings must be located such that the bearing centreline in each direction is within 3 mm of the location shown on the Drawings. Level For bridges comprising simply supported girders, bearings must be set to the levels shown on the Drawings within a tolerance of +/- 5 mm. For bearings supporting continuous superstructures, bearings must be set to the level shown on the Drawings with a tolerance of +/- 0.0001 times the sum of the length of the adjacent spans, but not exceeding +/- 5 mm. The bearing inclination including any attachment plates which form part of the bearing must be within 1 in 200 of that shown on the Drawings.
8ec0896f-b721-5b30-b9aa-e961bc5adf8b | note | Frequency / Process Held - For Each Bearing / Prior to landing girder
9ed1c2e5-e389-555e-b1b6-ff3768219f8c | note | Inspection – ACPL - H
97667349-3df7-5dae-af30-6e91387e7a00 | note | Inspection – Client - H
17215fa7-3b93-50fa-806b-c1b601cda756 | note | Comments / Attachments / Records - Product Conformity Survey
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 - Certification of Bearings
e2c4e343-f181-50e4-8c03-a446bd9cb54e | note | Requirements / Reference - B284 Cl 6.3
37967150-2745-579e-865d-e3f75ddc134e | note | Acceptance Criteria - After installation of the bearings and removal of temporary supports, submit a certificate from an Engineer stating that the bearing installation, including their final positions and levels, complies with this Specification and the Drawings.
db7d367d-1002-5423-991b-fbdf4fe65212 | note | Frequency / Process Held - Once per bearing / prior to Girder erection
0f1dd2be-0562-569a-a840-8903b87cfa66 | note | Inspection – ACPL - S
9a2458f5-3522-55d7-bc49-fc00c7217536 | note | Inspection – Client - S
709093cb-1a70-573f-8da6-d9f523a85688 | note | Comments / Attachments / Records - Certificate of Conformity
| section | 3. Girder Erection and Keeper Plate Installation
| checkpoint | 3.1 - Grout Strength Results
47c9bff5-a954-5e40-9868-4ece3d3ea326 | note | Requirements / Reference - B284 Cl 2 DRG-1036 Sheet 36
098db3ee-b9c5-5c06-8386-4df4020dbb64 | note | Acceptance Criteria - Prior to erection of girders, grout strength results to prove grout has reached 32 Mpa .
c2daa2b9-6742-5064-a4e0-c10ceb39dc87 | note | Frequency / Process Held - Once per girder / prior to girder erection
6e925b06-e7dc-536f-9a77-347cabf55d95 | note | Inspection – ACPL - S
96ad398b-ff13-5039-9916-c9502ddc4187 | note | Inspection – Client - S
cfe8eadf-c4d2-5097-8885-6f848bf8203d | note | Comments / Attachments / Records - Grout Strength Results
| checkpoint | 3.2 - Epoxy Strength Results
0552d47d-6fe4-5a9d-bd77-e0d97d78ec66 | note | Requirements / Reference - B284 Cl 2 DRG-1036 Sheet 36
5dcc413c-e75f-5dfd-95f0-23bd101c7ff4 | note | Acceptance Criteria - Prior to erection of girders, grout cube results to prove grout has reached 32 Mpa.
f8d0cc4e-b77e-5fdb-8497-f762ae60e409 | note | Frequency / Process Held - Once per girder / prior to girder erection
25ec9e60-a033-50f4-95f9-832002ec3fc4 | note | Inspection – ACPL - S
d80a7ef1-1bb2-5d96-88ef-c5dd5524ab1c | note | Inspection – Client - S
6c28f500-32aa-57e8-bee6-0bc2effcdb5a | note | Comments / Attachments / Records - Epoxy Strength Results
| checkpoint | 3.3 - Girder Erection
a1f789e3-a58f-52a9-ab8e-e687103ab937 | note | Requirements / Reference - DRG-1036 Sheet 36
99583e8e-1c64-5d7a-8990-3d5c90d7136e | note | Acceptance Criteria - Erect girder on elastomeric bearings and brace as necessary.
99782bcf-ddb9-5648-b507-efad57bf851c | note | Erection operation must be supervised by an Engineer. Ensure that:
083e4d86-bb1b-5c68-93c2-04cdbf98f640 | note | (a) each member is placed in position safely, without damage to the member or the structure; and
ae231bd6-2010-5fc5-86ee-46f63a3ba98c | note | (b) the intended permanent structural action of the member is not:
089e82bf-cd67-539f-95ac-5233fa41aa2e | note | (i) restrained; or otherwise
e43bdb25-ea33-54be-88bd-6ae24f272f5a | note | (ii) adversely affected by the process of erection or by movements which occur due to environmental or construction-related forces
02c92ce6-7b45-50f7-aec5-16d47d738dbe | note | Frequency / Process Held - Once / Prior to installation of Keeper Plates
0b2bb38b-2e92-5024-b44a-e37b597d8473 | note | Inspection – ACPL - S
222d0613-d098-54d0-8fc7-354aed153fdd | note | Inspection – Client - S
877bcf54-c1ae-52d2-8a8f-acd9bd6baba7 | note | Comments / Attachments / Records - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Installation of Keeper Plates D and E
11073070-e59c-5ab6-9827-2188bd4270d3 | note | Requirements / Reference - DRG-1036 Sheet 36
caefe8a5-8d05-56dd-9999-08c76183ff5f | note | Acceptance Criteria - Install Keeper plates Type D and E onto bottom steel attachment plate to achieve 10mm nominal gap. Keeper plates can be swapped and lipped as required. Each keeper plate to have 6 fixings, remaining 6 unused holes to be filled with silicon sealant.
c0518094-fd28-56d2-8993-09815eb8d8fd | note | Frequency / Process Held - Once / Prior to Girder Bracing
bd63cc41-c767-50f5-8a70-c11e97a45fe5 | note | Inspection – ACPL - S
d8737777-c06f-52b4-9cc6-ef42a879a9d8 | note | Inspection – Client - S
dae7c2d4-c08f-58d3-a7c1-3c02dd9a24b6 | note | Comments / Attachments / Records - This ITP
| checkpoint | 3.5 - Girder Bracing
f603a108-0072-59b6-adb6-bed807ba714f | note | Requirements / Reference - Temp Works Design
419847ba-c18e-51b0-911e-b84704fc1759 | note | Acceptance Criteria - Brace Girders as per temporary works design. Effectively support and brace the girders to prevent overturning, unintended sliding, and any other unintended movement, when subjected to any loads, including loads induced by handling and environmental factors. When being placed in position, effectively support, and brace the girders before being released by the crane or other lifting device. Maintain effective support and bracing at all times during subsequent deck forming and concreting operations, and until the deck concrete has hardened.
b88b63d2-4892-570c-882d-c7baea62d4bc | note | Frequency / Process Held - Once / Prior to landing next girder
04777b89-0e42-554a-a69a-f7529d218ab9 | note | Inspection – ACPL - S
39d3b00d-e8f1-5b62-a42a-5512f96f90e2 | note | Inspection – Client - S
c4209370-58da-54f1-a50f-72aae835a320 | note | Comments / Attachments / Records - Temporary works design
| checkpoint | 3.6 - Repeat for Remaining Girders
f1c2ed96-d735-51c4-b836-7c6bb8a03fdf | note | Requirements / Reference - DRG-1036 DRG-1045
d9c04a49-7d82-58ae-81ab-bed40b4c519e | note | Acceptance Criteria - Repeat the above process for all girders in span.
b9c1b095-dcb3-508c-b091-fc3b43cf4208 | note | Frequency / Process Held - Once / Final Survey
702566f8-13f3-51c3-a849-d01b8214483d | note | Inspection – ACPL - S
da1924e5-8849-575f-bbdb-fc36ce7fbccb | note | Inspection – Client - S
9d196051-80fd-5505-96a7-8f9252db8a66 | note | Comments / Attachments / Records - This ITP
| section | 4. Position Verification
| checkpoint | 4.1 - Position and Alignment Verification
ad604efa-4e2d-5ce8-95d6-8fb9023a6777 | note | Requirements / Reference - B150 Cl 6.4 B150 Cl 8
ca0d8c5b-a246-5a79-8415-beb4cfab8925 | note | Acceptance Criteria - Profile Diagram before placing cast-in-situ concrete supported by precast members. D&C G71 joint survey and conformity survey for girders.
5b266a0f-8cfe-5d32-998d-c386835608c3 | note | Verify that members have been placed in their correct position as shown on the Drawings. Verify that members are aligned and placed in series adjacent to one another within specified tolerances.
f4ffc8d9-3359-530d-8555-814842565814 | note | The following tolerances must not be exceeded:
61992579-9e89-5f16-89d7-2ace0a7efd9a | note | (a) Deviation from the correct position must not exceed 20 mm in any direction;
1486bf72-f871-5814-9f76-30935228a61f | note | (b) The deviation from plumb or design inclination between any two points must not exceed 1/200 times the distance between the points or 10 mm, whichever is less.
e4c1342a-c067-57cb-ace1-8e2fc557009d | note | Check all alignment dimensions before final fixing in position
d8d93a50-4363-523a-9728-6ca7bace70cb | note | Frequency / Process Held - Once / Prior to landing next span
22c303e4-cad8-5182-99af-0e35b334d9c1 | note | Inspection – ACPL - S
bf4cddef-e8b9-5b79-aa57-f46ecadd661b | note | Inspection – Client - S
7aa1f8af-db11-540f-b59c-3af10d57a617 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 4.2 - Grout Strength Verification
31e1641f-0c3f-535d-b0d9-806388e6f466 | note | Requirements / Reference - B284 Cl 2
1376450e-c16d-5693-8782-7b8aea8da627 | note | Acceptance Criteria - Verify grout has reached 40 Mpa
5cdacf40-702a-50fb-8411-ddfe1a974f4c | note | Frequency / Process Held - Once per girder / prior to Deck FRP
dcd41a3d-11d5-5a3c-93f4-de13a29f4709 | note | Inspection – ACPL - S
e75939ec-cb80-500f-99e1-cfe22ae740f0 | note | Inspection – Client - S
77f90226-2f89-5a63-b8ac-12cfafabf9ac | note | Comments / Attachments / Records - Grout Strength Test Results
| checkpoint | 4.2 - Epoxy Strength Verification
2f8e26ac-f94e-5326-aabf-b527bd73f6a3 | note | Requirements / Reference - B284 Cl 2
0d57d0fe-28a1-5411-8603-bd8c1ce1e183 | note | Acceptance Criteria - Verify grout has reached 40 Mpa
6252d365-0226-5e0c-a4fc-ef6cd1f46c36 | note | Frequency / Process Held - Once per girder / prior to Deck FRP
e5056e92-a0ae-5642-88a2-45487487ef81 | note | Inspection – ACPL - S
0c3b343d-4ef4-53ab-bcb0-e898a1192387 | note | Inspection – Client - S
cec67394-81b3-5229-a5cb-86544342a41e | note | Comments / Attachments / Records - Grout Strength Test Results
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
5bf2ad87-4320-56ff-9f1d-1b580d3dcf2b | button | Any non-conformances? | YES, NO
f72f5f88-ddc0-5b1d-8328-33ed5b291862 | textbox | No's:
14756ec9-2e87-570a-baf4-ddb76ec41eb4 | button | Closed Out | YES, NO
c52c2324-2325-5e02-93e9-ccdfb418d6d5 | button | All work has been satisfactorily completed. | YES, NO
045fd891-c054-5112-9773-5014a0ba7ead | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
63ce5250-d6b5-565a-b5e1-e83cdb216621 | textbox | Lot Verified By:
77b126ce-d56d-5849-8b93-1d8080a293dd | textbox | Lot Closed Date:
e644c96a-f406-5a91-88f8-8cc8f1addd5b | button | Submitted to Client | Yes, No, N/A
9de883e7-3fd0-5880-bfde-a9228083b2b2 | button | Reviewed by Client | Yes, No, N/A
3d886fab-b73d-5923-9ee1-cb8e06685c59 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B3.CG5 - Cross Girder FRP Pier 5 Rev 3 |  | ITP-B3.CG5 - Cross Girder FRP Pier 5 Rev 3 | 9bd654ed-553a-486d-8f4e-c5318c0a4551
| section | Lot Information
| checkpoint | Lot Information complete
9b94c1ca-23dd-4e58-b7a8-5508a656166c | textbox | Lot Opened On
edbfb422-d354-41b8-81ed-239824fc0224 | textbox | Date of Works
a63e2550-e388-490a-9bca-315238447791 | textbox | Lot Type
1acd684b-5889-4b87-879d-9591a3a70088 | textbox | Start Chainage
0b45c586-dddd-40c6-8014-4151851429ba | textbox | End Chainage
2e62e182-33e9-4dde-b5ad-89509b0c348c | textbox | Offset
03dfaa39-7a72-537d-8206-15cef37e5448 | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
70c700d9-426c-55b5-9b9b-57e0fad28130 | note | Requirements / Reference - Preliminary Works (FRP) ITP
b8f2707c-d6d3-5a6b-ab67-1cee09d01a3b | note | Acceptance Criteria - Sign-off of ITP-B3.CGP FRP Preliminary Works ITP
1af3dfc5-60de-52af-9e53-65ba86c92736 | note | Frequency / Process Held - Once / Prior to Construction
80df6acd-21f3-5c91-a3b7-911f0813989f | note | Inspection – ACPL - H
8571647d-099a-5b75-865c-ea6823517147 | note | Inspection – Client - H
8bdfc728-6910-532b-a51d-8a435f7a91a5 | note | Comments / Attachments / Records - ITP-B3.CGP
| signoff | AUTHORITY HOLDPOINT
| section | 2. Construction
| checkpoint | 2.1.1 - Survey Set out
1a0ed07b-1711-5a69-b139-7e614528273d | note | Requirements / Reference - B80 Cl 5.8
c86fe5a4-69ee-5f66-a1f8-7238f3f1228b | note | Acceptance Criteria - Survey set out as per design drawings
e1e95c74-6634-550b-8a7a-5b66c42d683c | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
2921045a-aae2-5ec1-8bca-91c8dbd686d0 | note | Inspection – ACPL - S
62da7461-856a-5bac-9193-53c930b065d5 | note | Inspection – Client - S
78bb3a17-6a28-53b7-a71b-137c1b407a46 | note | Comments / Attachments / Records - Set out Report
| checkpoint | 2.1.2 - Formwork Certification
003a78be-729f-51be-b93d-2fcc3ff02dbe | note | Requirements / Reference - B80 Cl 5.2.3
173a8313-c8b8-504f-9c42-59dca3e25d47 | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member.
23c46c9f-f006-5dd8-8f68-37afd02acd23 | note | Frequency / Process Held - Prior to constructing formwork
5020be3f-8583-5239-9dd5-9b204b0764a3 | note | Inspection – ACPL - H
a334c29e-70cd-5837-b9c1-ae0ebd693365 | note | Inspection – Client - H
0e33571b-7393-5a4b-b5b6-f930dcca1e34 | note | Comments / Attachments / Records - Formwork Documentation Design Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.4 - Certificate of Conformity
1d6e7ac2-5c53-5bcd-9914-e61c0b5a13c6 | note | Requirements / Reference - B80 Cl 7.5.2
92380c6f-e618-538e-b844-bb553161847b | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working hours prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s)
a718f6f7-8f00-5f80-ba3c-09fd36a86d56 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
4331e20b-fa5a-583f-8b11-39180fa1ae18 | note | Inspection – ACPL - H
7ffe6780-a5c9-501d-b259-33661eb56259 | note | Inspection – Client - H
c080ff14-267b-53cd-8f07-6ee0265cdb6c | note | Comments / Attachments / Records - Method Statement Certificate of Conformity
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.5 - Certification of Steel Fixing Prior to Concreting
596c95f4-2184-566e-9cb9-ef58205f583c | note | Requirements / Reference - B80 Cl 7.5.2
92591226-1d75-5937-9752-eeba38ceb547 | note | Acceptance Criteria - Splice reinforcement only at locations shown on the drawings. All welding must conform to specification TfNSW B203 and the bar manufacturers recommendations. Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: 40mm unless otherwise specified Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
0034899c-0708-5c3b-af58-71ca75961420 | note | Frequency / Process Held - Once / prior to placement of concrete
cd9ded54-28c8-5fa5-a1fa-e3a2fa0c6cba | note | Inspection – ACPL - H
d70bb897-c9ce-586b-9ea2-e44b0fcb478c | note | Inspection – Client - H
d0e148e2-72d0-5a04-b4d1-461e8c08ff67 | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.6 - Certification of Formwork prior to Concreting
0d123dbb-beac-5052-b2d4-389ecee7af1b | note | Requirements / Reference - B80 Cl 5
8a080f58-13c0-5a39-96ea-331a5e07e9d4 | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
a8b3d157-f6ac-5d52-84a3-f6168e3b1536 | note | Frequency / Process Held - Once / prior to placement of concrete
cd1a537d-42df-599c-a19d-8b78eb1b1e57 | note | Inspection – ACPL - H
04f28357-27ce-5234-8aad-e9a67c7264f6 | note | Inspection – Client - H
b66548a4-dd20-56ab-9b39-f7f569425b01 | note | Comments / Attachments / Records - Checklist Certificate of Conformity
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.8 - Concreting Personnel
044c0d56-695e-550b-9d48-95d76576116d | note | Requirements / Reference - B80 Cl 7.2.3
2f2bfc7b-2e4a-5abd-8c74-48f114c0dedd | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
e9c7333e-6569-523e-b002-7e2517d3e87c | note | Frequency / Process Held - Once / four hours prior to concrete pour
01a3bfa7-67ba-5684-981f-1c0adfa1a7c3 | note | Inspection – ACPL - H
a8802c09-b263-5288-be4b-69036833cfce | note | Inspection – Client - H
918fc959-08a0-5ca7-b08f-d2cf7e3ae34f | note | Comments / Attachments / Records - Concreting Personnel Grey Cards RFI-031
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1,9 - Girder Penetrations (pre-pour)
bbc14cd4-efcd-5d82-a32e-8e33a5d8bd7b | note | Acceptance Criteria - All girder penetrations to be sealed prior to pouring concrete.
4fcc97ca-dacc-5064-8ff6-612f61a2085c | note | Frequency / Process Held - Once / prior to pouring concrete
00e48aed-5fcf-5eea-8f8f-2fc60ab2122c | note | Inspection – ACPL - S
7eb2c3a4-c75b-5a09-9c69-c25fc00c6ae8 | note | Inspection – Client - S
12c3f899-e07c-59fb-9b83-18344528da36 | note | Comments / Attachments / Records - Visual Inspection
| checkpoint | 2.1.10 - Supply and Delivery of Concrete
c43dcb3f-7b0e-5152-bf6c-51f8a1038b9b | note | Requirements / Reference - B80 Cl 4.1
524af817-b704-51fe-af28-ed10bbf29048 | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
48f9eb44-7208-5c45-b1bd-6bf2f35afd10 | note | Frequency / Process Held - During concrete delivery
e8cdcd43-8bff-5573-910a-00fb0c1d985b | note | Inspection – ACPL - S
729913c7-6f3b-572e-b155-24fce066540b | note | Inspection – Client - S
52866bc5-007f-5204-8a21-fbf07c6bc923 | note | Comments / Attachments / Records - Concrete Docket Concrete Pour Record
| checkpoint | 2.1.11 - Concrete Sampling
1225680e-21b2-533a-b5c1-a7f7be398c1c | note | Requirements / Reference - B80 Annexure B80/L
2067af19-904e-5877-bc1d-5b0f17f24f6f | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
ee4bf300-31a2-5155-8eb8-c38e89875a2d | note | Frequency / Process Held - Each element / prior to placement
f7b6bb76-a48e-5c73-bbbe-bea97cb4dcc2 | note | Inspection – ACPL - S
5ebb6e63-daeb-56f8-ad12-aa23f9e074a1 | note | Inspection – Client - S
f8e093b9-7dde-5a47-b253-04346150450e | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.1.12 - Concrete Placement
5677da02-18f9-5505-9064-87f4d92fbc8e | note | Requirements / Reference - B80 Cl 7
e324fccc-fd06-5180-85e0-4f8f77048be4 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature 5-35C 40MPa Concrete Concrete placed in cross girder to be carried out in once continuous operation Ensure uplift restraint cast ins are positioned correctly Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D Construction Joint to be prepared on top surface of cross girders where required as per B80 Cl 7.
32ba8585-60d7-5d94-a377-cd2a272a6d9a | note | Frequency / Process Held - Once / prior to Curing
5e48fb97-2417-56f5-95b1-c73176615ddc | note | Inspection – ACPL - S
71427930-bd9d-585e-9b47-0faac61bb685 | note | Inspection – Client - S
3ddfa90e-7385-5bbe-b30e-9266565093ac | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record Photos
| checkpoint | 2.1.13 - Concrete Curing / Stripping of Formwork
01852db0-fd2c-5e80-84a7-1d7aea95416b | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
1821171b-4f36-59dc-b556-1487e1375104 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting A exposure classification requires 7 days wet curing Formwork to be stripped after no less than 7 days Remove formwork in a way and time that achieves specified characteristics and prevents damage
2c42cfbb-5278-5784-a27a-0cde73ad6826 | note | Frequency / Process Held - Once / prior to Concrete Sign off
9f737ebc-48f6-54f0-b42f-a778ee545147 | note | Inspection – ACPL - S
193dafef-33e8-5e6e-8842-ac4970f60537 | note | Inspection – Client - S
c70f298f-04ed-59c1-9ed3-262827b7beda | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.1.14 - Assessment of Defects
d948ba13-a0a9-5e42-823c-359e32f08ad2 | note | Requirements / Reference - B80 Cl 9.3
a5c1966f-e33f-591b-90c7-e2d559266174 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
1f4e8bb1-1d89-56eb-85f5-c1402f870f21 | note | Frequency / Process Held - Inspection following removal of formwork
ff7bb444-2114-5dce-864f-873625babacb | note | Inspection – ACPL - S
fc42ade6-36f4-5e93-bbde-7029a3b1a345 | note | Inspection – Client - S
1771fae9-7979-56da-ae6c-c259ff7fb727 | note | Comments / Attachments / Records - Crack and Defects Map
| checkpoint | 2.1.15 - Concrete Sign off
fa70ff82-5bff-5472-8ffa-3df194ba22ce | note | Requirements / Reference - B80 Cl 8
24699164-05dd-5d5c-8fe9-e41f66f878d6 | note | Acceptance Criteria - Min 40mPa at 28 days
3fcdb94d-e144-5926-a6b6-84c1f08715a4 | note | Frequency / Process Held - Once / Cross Girder Concrete Pour
b0a06771-83f9-50a9-9cc1-30b903bae7b1 | note | Inspection – ACPL - H
85f7ad2f-6af4-5597-a254-8752f0d27aa2 | note | Inspection – Client - H
93704da0-de13-52be-857f-0007197621f7 | note | Comments / Attachments / Records - Concrete Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.16 - As-Built Survey
adae7717-fe53-5032-85c3-cdfe1a6fb150 | note | Requirements / Reference - B80 Cl 9
57aa11a7-fcd7-56b7-a985-80e526e58ccb | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Plan Dimensions: -5mm / +15mm Deviation in Plan Position in any direction: 25mm Deviation from vertical: 1/500 Relative displacement between adjoining members: 10mm Irregularities in exposed concrete surfaces: - Any side dimension <1m: 2.5mm - Any side dimension >1m: 5mm Cover survey to also be completed as per RFI-040
22f70c95-ffa4-5159-adcb-dac64e5bace3 | note | Frequency / Process Held - Once / following removal of formwork
dc599ca5-6579-5892-a56e-e162c737b37f | note | Inspection – ACPL - S
be7b281c-1513-5ea4-83de-e39bbdaadd4a | note | Inspection – Client - S
3d9cec26-cf02-5472-8fd3-428b9fe9df85 | note | Comments / Attachments / Records - As-Built Survey Report Cover Survey Report
| checkpoint | 2.1.17 - Girder Penetrations Inspection (post-pour)
b2947a1e-1f5c-5871-b08e-496d31d4da9a | note | Acceptance Criteria - Inspection of girder penetrations following pour.
43e918b5-5e54-57c9-954a-ebf2636f222f | note | Frequency / Process Held - Once / prior to commencing parapet installation
fbeac315-c8c4-558b-96ca-5dfab2bf43a2 | note | Inspection – ACPL - S
e8183eb4-b816-5d0b-b213-f99022c2792a | note | Inspection – Client - S
b1a87888-adc3-5bb7-8ca4-5eeca40618f6 | note | Comments / Attachments / Records - Visual Inspection
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
9a5536d0-59a9-5330-8c2d-899a1c2ad1fc | button | Any non-conformances? | YES, NO
0fd3ef00-a9ff-55c3-bb9c-f4b99b4ff559 | textbox | No's:
1a2c6ad6-ffb8-5bc1-a43b-c5dfb79879c3 | button | Closed Out | YES, NO
d3ebc7c6-7a4b-56a6-8825-2893f69bf856 | button | All work has been satisfactorily completed. | YES, NO
118a57af-15ac-578c-88c6-64535409b1f6 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
0759fe78-5c3d-5345-88b2-16e3cab1c439 | textbox | Lot Verified By:
a8858edb-d429-5f1b-a317-0cbc85104994 | textbox | Lot Closed Date:
23a38031-ee63-57f2-a4ee-777a54d252fd | button | Submitted to Client | Yes, No, N/A
1a5b40b7-663e-5c30-94c1-2c4256c9cfc3 | button | Reviewed by Client | Yes, No, N/A
54602353-aa82-5f77-be3a-d54bd1c61807 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B3.CGP - Cross Girder FRP Preliminary Works Rev 2 | itp | ITP-B3.CGP - Cross Girder FRP Preliminary Works Rev 2 | 04efc708-8eb1-4c42-aca3-a179a9cdeb99
| section | Lot Information
| checkpoint | Lot Information complete
e5eefb31-a288-4f1c-95e6-a9fc57d46d7c | textbox | Lot Opened On
58cddc37-bef5-4f1e-bf09-964cf715f196 | textbox | Date of Works
e77e144a-acce-4458-99f9-1d7cfd694027 | textbox | Lot Type
541819af-b560-49fa-8584-cf784b61f127 | textbox | Start Chainage
6af1fb97-43a1-42b0-9d9a-618d767d6d74 | textbox | End Chainage
d74523f6-f351-4d6e-9543-18c6c2547883 | textbox | Offset
5293d381-8140-5ad1-937e-231204b1e881 | textbox | Control Line
| section | 1. Prelims
| checkpoint | 1.1 - Safety Review
fc18a4f7-babe-5e15-855a-cd81be8d0943 | note | Requirements / Reference - Project Safety Plan
b5b465d2-f63d-534a-9578-c412846d1e78 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved.
1bfebf20-5a76-5d98-a941-685bbdeb8f49 | note | Frequency / Process Held - Before Commencement of Works
e9b84c89-fe6a-5d48-b983-6d6820479c76 | note | Inspection – ACPL - W
d0cc2d6a-6c8b-5d6e-8921-e1613d04168a | note | Inspection – Client - S
fe5ff6f1-d35a-5b8f-ba8f-afbe591df736 | note | Comments / Attachments / Records - Signed SWMS
| checkpoint | 1.2 - Environment
266a0965-832f-547f-bac5-8137df83f1ca | note | Requirements / Reference - Project Environment Plan
ab7eacab-e2c8-5154-9801-7d34b78d4933 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc as a direct result of construction activities.
7c6cb539-0cc2-5d7c-b2cb-4208770a6e6a | note | Frequency / Process Held - Before Commencement of Works
6d56bcb8-bb3e-5b0c-9122-d9cec8999d5d | note | Inspection – ACPL - W
4c08b15e-770e-508f-a62c-1b338da2126b | note | Inspection – Client - S
33f52fde-501c-5eae-89a3-97826e3eac4f | note | Comments / Attachments / Records - SECP AQMP
| checkpoint | 1.3 - Submission of Nominated Mix Design
1436a337-b1a7-5603-a9f9-b6aa5d7e79b6 | note | Requirements / Reference - B80 Cl 3.9.1
52587b13-fd55-5fce-ab1d-effdfb2edb6b | note | Acceptance Criteria - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
418db127-6f2c-5807-b7fa-fc91074611e5 | note | Frequency / Process Held - Prior to ordering concrete to site
50706a90-59af-5d04-ad23-4ab8857dbdf2 | note | Inspection – ACPL - H
cb032a48-0012-5343-9ed6-59ed47f0683f | note | Inspection – Client - H
5fd80d63-9e93-557f-9898-61828e4843a6 | note | Comments / Attachments / Records - Mix Design Submission
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Concreting Personnel
5a632708-2693-5be7-be34-a8a38b6ffc17 | note | Requirements / Reference - B80 Cl 7.2.3
3fa51f18-3478-5df9-bb89-278f432a62bb | note | Acceptance Criteria - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
0696ee7d-6ee8-5ba5-ae86-f5e0ecdf0014 | note | Frequency / Process Held - Prior to first concrete pour
d3ce6b6d-80d6-5f92-889c-cdd5b4893784 | note | Inspection – ACPL - H
814e96f2-9ba0-5181-8ca8-c54354c94bf9 | note | Inspection – Client - H
f7a87f12-aafa-5ecc-a25b-f16f51688aff | note | Comments / Attachments / Records - Concreting Personnel Grey Cards
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Test Members
705c9235-0580-5cf7-a250-6fe66387745d | note | Requirements / Reference - B80 Cl 5.3
2029a56d-89a0-548c-85e9-1df58db513d9 | note | Acceptance Criteria - Provide notice in writing to the Principal, at least 2 working days, of the upcoming placement of concrete for the test member(s) In the event the test member does not meet the design, reassess the process with the Client and pursue alternatives if necessary
ffba2b7b-da7b-5971-9d18-4ad294af0abb | note | Frequency / Process Held - Prior to commencing concreting for permanent works
6d811fa3-a483-5d8a-86a6-910fb4e5199e | note | Inspection – ACPL - W
87e27827-02ba-52d3-b089-a93f74b5c1e3 | note | Inspection – Client - W
cf136b40-625f-5801-81e9-ea05006b8651 | note | Comments / Attachments / Records - Witness Point
| checkpoint | 1.6 - Fabrication of Reinforcement
3fe16141-2be7-5976-bed3-94f0613cc050 | note | Requirements / Reference - B80 Cl 6
2fd38e8b-e93a-5d82-ba2f-ce20d58d58ba | note | Acceptance Criteria - Steel reinforcement must be certified by the ACRS for conformity of the reinforcement production and processing to the requirements of AS/NZS 4671 Chairs and Spacers must comply with AS/NZS 2425. The smallest chair or spacer dimensions must not be less than the specified cover, and the largest dimension must not exceed 1.8 times the cover. Fabrication tolerances must be as shown in Table B80.14
4ac63207-744f-51f3-8bdf-97bfba8e84af | note | Frequency / Process Held - Once / Prior to FRP
a1ec1af5-e200-5bb3-94b8-87f60d9f76c0 | note | Inspection – ACPL - S
dcc9bc0d-6efe-5292-ba93-aae278319c52 | note | Inspection – Client - S
d0f79227-a58c-53b3-9223-459851f3e458 | note | Comments / Attachments / Records - Checklist ACRS Certificate
| checkpoint | 1.7 - Welding Operations
d9bc4273-7c48-591a-a9ed-d715272b2d93 | note | Requirements / Reference - B203 Cl 4 B203 Cl 5
d224fa93-99a5-5e03-8b42-13863a9c437e | note | Acceptance Criteria - Prior to the commencement of welding of steel reinforcement for the Works, submit the following: (a)welding personnel names, roles, qualifications and experience; (b)welding procedure specifications (WPS) for the required welding; (c)welding procedure qualification records (PQR or WPQR) for the applicable WPS; (d)proof of conformity of proposed welding consumables to this Specification. Welding of steel reinforcement to be carried out in presence of a welding supervisor, and be witnessed and inspected by the Welding Inspector. Test welded splices to confirm that the parent metal strength has not be reduced. Such testing must be carried out by a laboratory with appropriate NATA Registration.
df9627e2-b1b3-5538-9714-503b4d7d131d | note | Frequency / Process Held - Once / 5 days prior to welding operations
1138580f-a27a-51ab-9faf-a30411225d49 | note | Inspection – ACPL - H
1b9f8956-e24c-54d6-8d88-4df81adcb46d | note | Inspection – Client - H
edca476f-8e1d-5fee-8f86-7d633d7c6dfa | note | Comments / Attachments / Records - Welding Qualifications WPS WPQR Welding Consumables Welding Inspection NATA Registration
| signoff | AUTHORITY HOLDPOINT
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
4d995c1f-1db8-5723-b493-2c7752437c00 | button | Any non-conformances? | YES, NO
bac6310f-6e3b-5775-9de1-7fa178efc105 | textbox | No's:
c3a59c2d-bd7b-56fd-aaad-9f59343cfcb2 | button | Closed Out | YES, NO
db17c3ac-b4ee-52b1-9719-89b05b6b7db7 | button | All work has been satisfactorily completed. | YES, NO
6758258c-bb59-5251-b5e0-a9cebef4fe09 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
632c3af2-fb2d-5029-9646-d0b253f3ca94 | textbox | Lot Verified By:
ed0146b1-cde0-578a-b452-ab70b0f82250 | textbox | Lot Closed Date:
57521a1e-1ab9-59ad-852d-793a9124333f | button | Submitted to Client | Yes, No, N/A
510c78ec-445f-5b76-9a59-9b3bbf854960 | button | Reviewed by Client | Yes, No, N/A
a7f51e58-34d8-56cd-86e3-f71565dc5353 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B3.P - Girder and Bearing Installation Preliminary Works | itp | ITP-B3.P - Girder and Bearing Installation Preliminary Works | ae9edabe-d9ad-42aa-a24a-77e56036e0e8
| section | Lot Information
| checkpoint | Lot Information complete
26eeae45-27e7-4529-b3db-ec0464dbbb70 | textbox | Lot Opened On
c6735afb-e735-4e06-96bd-01546e117a3a | textbox | Date of Works
6f59416f-f06d-422f-b6ba-94bb390cd4b2 | textbox | Lot Type
84c816df-3f44-47bb-b3be-3c6bc29aa346 | textbox | Start Chainage
ed6e2f4b-66c9-4b27-b7ef-ae775e2ab634 | textbox | End Chainage
ed49f03c-b98a-447d-9612-d6600a813ee9 | textbox | Offset
1fe6de28-f748-5693-b922-00ca5320aea6 | textbox | Control Line
| section | 1. Prelims
| checkpoint | 1.1 - Safety Review
392839fc-d765-5f85-80d7-adf10151ad48 | note | Requirements / Reference - Project Safety Plan
e7eb8ee4-3198-5b51-98d4-1ff47c76d53e | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed.
1f2d3cbf-5dee-5275-8f74-2963cd26f689 | note | Frequency / Process Held - Before Commencement of Works
27ab8d8a-65bb-50a6-97ac-f3a2dd620b73 | note | Inspection – ACPL - W
d5429bbf-981f-553e-8ff8-d554eab7523f | note | Inspection – Client - S
56767d44-118c-59db-9c3f-5912cdda312f | note | Comments / Attachments / Records - Signed SWMS
| checkpoint | 1.2 - Environment
197bbe24-7b34-58e2-a584-cf1752200a34 | note | Requirements / Reference - Project Environment Plan
4c04d1d1-d034-5c89-a050-80bcea56dfb8 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
fc3f5648-4f26-5ee3-9af2-7aee64d46e80 | note | Frequency / Process Held - Before Commencement of Works
d273e889-4729-5b60-9888-bea6311762b1 | note | Inspection – ACPL - W
0c5bde8b-e431-5084-be83-bdc6df66655a | note | Inspection – Client - S
744d3c09-7718-5072-9cf4-2595e8ba94c7 | note | Comments / Attachments / Records - SECP AQMP
| section | 2. Certification of Temporary Works
| checkpoint | 2.1 - Certification of Lifting Equipment and Methodology (Platform Certification)
f3297921-c7a1-5d48-b75e-59e755302484 | note | Requirements / Reference - B150 Cl 4.1 G1 Cl 26
07445724-267f-55e5-bacf-c0e11757054a | note | Acceptance Criteria - Details of the proposed lifting equipment and method together with certification including calculations, by a Chartered Professional Engineer with membership of Engineers Australia practising in the field of geotechnical engineering that under the proposed set up and site conditions, the equipment nominated will be used within its safe working capacities.
17eae7fd-6885-5559-b547-3babc832b24b | note | Frequency / Process Held - Once / Before setting up of Crane(s)
0fb72d3a-acc7-500d-91cc-cd0ba79054fe | note | Inspection – ACPL - H
d04b3138-03dc-5964-b5b6-14ad61724645 | note | Inspection – Client - H
40aef13b-c106-5925-a27a-7b1df38e29e6 | note | Comments / Attachments / Records - Third Party Geotechnical Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Certification of Lifting Equipment and Methodology (Lifting Equipment Certification)
c283d431-44b6-5215-9c77-8e67a6775273 | note | Requirements / Reference - B150 Cl 4.1 G1 Cl 26
f748461d-cba8-53c6-9e50-ee7e8b016974 | note | Acceptance Criteria - Prior to commencement of any erection, submit a certificate from an engineer, certifying the structural adequacy and compliance of the proposed method of erection (including all supporting and bracing measures) and the falsework with any applicable regulations, Australian Standards, this Specification and relevant design requirements. The certificate shall be accompanied by any drawings necessary to clearly describe the proposed method of erection including detailed drawings of any supporting and bracing measures.
0f19cfa2-9cb1-58d2-9048-8ff710c9a3e0 | note | Frequency / Process Held - Once / Prior to erection of pretensioned precast concrete members.
7d5cf191-f48c-565d-972a-d25c55a60eff | note | Inspection – ACPL - H
d18abf14-8e3a-5c11-a408-3558267cec09 | note | Inspection – Client - H
7c5de24a-79ce-5651-864e-20e0613ce55b | note | Comments / Attachments / Records - Structural Engineer Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Construction of Temporary Works (Girder Walkways)
52179a7e-b23c-5fce-af87-486da3ef6824 | note | Requirements / Reference - G1 Cl 26
f65abfd2-eb9f-5e4c-a60d-7433ffa33b25 | note | Acceptance Criteria - Submission of Girder Walkways Design Report for proposed temporary works including design certification
30af29e4-1e12-5d4f-965c-eb0c3eb42ebd | note | Frequency / Process Held - Once / Prior to construction of Temporary Works
822e78c6-3c56-55b7-b072-a8200869bc53 | note | Inspection – ACPL - H
83d6958e-3523-594c-b299-d4644e48eccf | note | Inspection – Client - H
c83fd850-df04-5335-aea6-68047e347ebb | note | Comments / Attachments / Records - Design Drawings and Design Certification.
| signoff | AUTHORITY HOLDPOINT
| section | 3. Materials AND Approvals
| checkpoint | 3.1 - Fabrication of Bearing Pads
bf700260-ea0f-5342-89c5-24c091d98a0a | note | Requirements / Reference - B280 Cl 5.2
64c0560c-7952-5655-b25c-88507e0bcb4b | note | Acceptance Criteria - Elastomer Conformity Evidence (certificates of compliance) and bearing report submitted to the principle at least five working days before the proposed delivery of pads to site.
dc9ae695-e79c-5f19-b65d-361882ef89b3 | note | Frequency / Process Held - Once / 5 days prior to delivery to site
d4d24efa-87d6-57e3-90ca-f36a2f3f8e9f | note | Inspection – ACPL - H
988dfa12-df6b-5683-8581-3b09b194ba3c | note | Inspection – Client - H
0c438b0f-ee65-546d-b068-669f2b13f738 | note | Comments / Attachments / Records - Witness Point
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Construction of Mortar Pads
4466776d-dc7c-5cd6-9727-cbc7684281ce | note | Requirements / Reference - B284 Cl 4.1
f467102e-042e-52c2-a3ad-d87d9316ef91 | note | Acceptance Criteria - Details of materials and procedures for construction of mortar pads to be approved by the principle. Construct mortar pads to the size shown on the Drawings Where a mortar pad supports a bearing with steel attachment plates, extend the pad at least over the whole plan area of the attachment plate plus a minimum of 25 mm outside the edge of the plate. The maximum thickness at the centre of the mortar pad may be 65 mm, provided that the thickness at any corner of the mortar pad is not more than 70 mm or less than 20 mm, unless approved otherwise by the principal.
5422decc-f942-5266-97de-d706bf9dd909 | note | Frequency / Process Held - Once / Prior to construction of Mortar Pads
f3353281-176e-57d0-9fbf-449bddd10a19 | note | Inspection – ACPL - H
2643286f-e327-55a1-a3a1-229c80be29f3 | note | Inspection – Client - H
04c58e81-fd09-5b36-b87f-223238bbbf39 | note | Comments / Attachments / Records - Epoxy Mortar TDS Construction Methodology
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Initial Assessment of Fasteners
48579642-d221-5cb9-814c-b1d4172155ab | note | Requirements / Reference - B240 Cl 1.4.2
e3510656-2f53-500e-95cd-590e582fc864 | note | Acceptance Criteria - At least 6 weeks prior to commencement of supply of fasteners, submit to the principle the following: (a) name and address of proposed Supplier(s); (b) evidence of conformity to the requirements of Clause 2; (c) product designation, description and proposed purchase lot size; (d) list of required tests in accordance with Clauses 3 and 4; (e) number of specimens to be tested in accordance with Annexure B240/L; (f) initial evidence of conformity to the requirements of Clause 5; (g) sample test certificates of similar type(s) of fasteners, showing conformity to Clause 3 and Annexure B240/L.
01cf208b-5cd4-5e33-9418-9e6057227e7a | note | Frequency / Process Held - Once / 6 weeks prior to commencement of supply of fasteners
df4ac56b-9bfc-5159-9f04-1b0a7126bc56 | note | Inspection – ACPL - H
2c7aea18-9ce7-55b4-8367-335876223053 | note | Inspection – Client - H
84e82c58-a830-5636-928e-404a60b2c3e3 | note | Comments / Attachments / Records - Fastener documentation as specified
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Delivery and Storage of Fasteners
c5fe6f1f-eed4-55e6-996d-ea08818d87be | note | Requirements / Reference - B240 Cl 6.1.1
d56c9502-7450-5d0f-998a-20a77b7739cf | note | Acceptance Criteria - At least 10 working days prior to delivery, submit the following: (a) The manufacturer(s) and the supplier(s) of the fasteners under this Specification must have in place quality management systems independently certified as fully complying with AS/NZS ISO 9001 by an organisation accredited by JAS-ANZ or an affiliated international certification organisation. Provide evidence of the certification with each consignment of fasteners supplied (refer to Clause 6). (b) Details of supplier(s), the relevant lot identification number and trace lot number if any, and the fastener description/designation. (c) Test certificates for the purchase lot(s) in accordance with Clause 4.6. (d) Statement of conformity of the purchase lot(s) to the standards specified in this Specification.
18196250-45e7-5251-8758-20a81af343fe | note | Frequency / Process Held - Once / 10 working days prior to delivery
9eb07e6b-332f-5404-809a-876d01021049 | note | Inspection – ACPL - H
d597eed7-dd59-53cc-91ef-564e5764821b | note | Inspection – Client - H
6b00f440-a47d-5631-bb01-874f83623c08 | note | Comments / Attachments / Records - Fastener Documentation as Specified
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Steel Procurement
4eb35b96-28dd-5d49-a4d0-132a3d584af8 | note | Requirements / Reference - B201 Cl 5.2
9c3bfdf8-1ba7-5305-86b1-b6aec1b587f2 | note | Acceptance Criteria - Valid certification of the steel manufacturer for the production of steel conforming to the applicable standard issued by either a JAS-ANZ or IAF accredited body, submitted no later than 10 working days before the steel is ordered.
340dbc83-838a-53e3-a9fc-de47575364b8 | note | Frequency / Process Held - Once / 10 working days prior to ordering of steel
4a085405-5817-59b2-b079-8066fb80f6da | note | Inspection – ACPL - H
491a9fe6-8cdb-5781-bbe4-54a1d0cf432d | note | Inspection – Client - H
c9736dff-2d6b-5f12-b073-75222e6e0b36 | note | Comments / Attachments / Records - Steel Certificates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Fabrication Work
0a59f312-a046-59e4-9af0-c193908d812c | note | Requirements / Reference - B201 Cl 6.1
7f613d3e-c686-5a07-a8d4-289d8859e135 | note | Acceptance Criteria - Shop drawings conforming to the Design Drawings approved and certified by the Designer in accordance with Clause 4.6.2, and procedures as detailed in Clause D1 of Annexure B201/D, items (b) to (v),
ab0958f2-a6b4-51d1-bb9f-24e4961bf051 | note | Frequency / Process Held - Once / 10 working days prior to ordering of steel
4621d214-02ab-5a04-a3e6-e051048866f0 | note | Inspection – ACPL - H
7d473532-fd34-590e-84c7-d95a197f2bf5 | note | Inspection – Client - H
4a220b31-c608-59a6-ace8-0bb30b88842d | note | Comments / Attachments / Records - Certified Shop Drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Commencement of Fabrication
77e522f1-5b64-5e51-9c73-0b52a961eeee | note | Requirements / Reference - B201 Cl 6.1
28cab398-12b2-526d-98f6-d1dcb7f37afe | note | Acceptance Criteria - Notification to client of commencement of fabrication
577e7748-f0a4-5845-88a1-a31700e68a64 | note | Frequency / Process Held - Once / 10 working days
0cce6efe-0ca6-5a1e-b902-891ac6f01e52 | note | Inspection – ACPL - W
11c27a6c-38da-5020-af4b-541cea9e2297 | note | Inspection – Client - W
21c68304-6287-5c50-bdbe-b8b32ac5c358 | note | Comments / Attachments / Records - WP Submission
| checkpoint | 3.8 - Completion of fabrication
43ba41c1-93a2-562a-89cb-f6189c252234 | note | Requirements / Reference - B201 Cl 15
1c6854e2-66eb-5139-acf4-4edca773d3db | note | Acceptance Criteria - The Fabricator’s Data Report must be submitted within four weeks of completion of fabrication.
80893f61-e884-5c8b-a523-561f6ab28cec | note | Frequency / Process Held - Once / 4 weeks from the completion of the fabrication.
490b4f4a-b952-53fa-b676-17dc19a521ea | note | Inspection – ACPL - H
a2bddc0e-7380-5767-8c56-16ab100f57ef | note | Inspection – Client - H
67ad0f3b-797c-5890-b728-f75ed2bcc5d9 | note | Comments / Attachments / Records - Fabricator’s Data Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Delivery of Elastomeric Bearings
1f61208a-56eb-58e9-8633-d5949cb11a02 | note | Requirements / Reference - B281 Cl 5.2
a26f6100-e307-5d0a-ad11-ea06345f0530 | note | Acceptance Criteria - Elastomer conformity evidence, bearing report and traceability documentation to be submitted .
01a26a78-21cf-5e32-8000-d1edf9edcec4 | note | Frequency / Process Held - 5 days prior to each delivery
5fa7734c-ba29-50cf-9a1c-814930de2566 | note | Inspection – ACPL - H
24ffa2e0-78b0-574d-8512-daac21fa7150 | note | Inspection – Client - H
f88e8fb6-d537-5066-a4f6-89d2e2187665 | note | Comments / Attachments / Records - Bearing QA Documents.
| signoff | AUTHORITY HOLDPOINT
| section | 4. Welding Procedures
| checkpoint | 4.1 - Commencement of Welding
cea27b6c-c000-597c-8b78-6a90a7a079cd | note | Requirements / Reference - B201 Cl 7.4.1.1
949af467-7bd6-563a-a33b-97fd077a0b9d | note | Acceptance Criteria - Weld procedure specification submitted to the principle
a263bd06-e828-5808-8ebe-d8aa3f45508d | note | Frequency / Process Held - Once / At least 5 days prior to commencement of welding
90fe8cd5-966a-5d00-bc23-bfadcf78c086 | note | Inspection – ACPL - H
fff742fc-ae28-512c-8e63-9c16fc7d08c0 | note | Inspection – Client - H
35c30b70-a816-52a9-8928-0960f3c19419 | note | Comments / Attachments / Records - Welding Procedure Specification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Weld Test Piece
c7c6ae45-b668-56ee-af06-52c87bbe5412 | note | Requirements / Reference - B201 Cl 7.4.1.1
bab25003-c5b2-5307-adb2-291ad8b9d2d6 | note | Acceptance Criteria - Manufacture of weld procedure qualification test piece
18ae56c1-6c52-54c1-b60e-905a5dff440d | note | Frequency / Process Held - Once / At least 3 working days notice prior to welding and testing of test piece
35677e3e-82d2-52a7-a531-ca8678b543dc | note | Inspection – ACPL - W
b59602ed-7db0-5c22-8910-cdaafb0bc207 | note | Inspection – Client - W
3ac09f53-90ee-5d0a-a454-c3a08572f697 | note | Comments / Attachments / Records - Welding Procedure Qualification Record
| section | 5. Installation of Bridge Bearings
| checkpoint | 5.1 - Installation of Bridge Bearings
917927d2-4c48-5771-911e-e41fe8a7e21e | note | Requirements / Reference - B284 Cl 5.3
22b8323c-05a2-5622-86a9-0b6748298f12 | note | Acceptance Criteria - Submit a certificate from an engineer confirming that the proposed method of installation complies with the specification and the drawings.
c181d36a-7226-5e3c-a580-a098c99cba4f | note | Frequency / Process Held - Once / At least 2 working days prior to installation of bridge bearings
247adad7-7fcc-5a1f-a8e2-349e00d2a005 | note | Inspection – ACPL - H
7cab3f9d-5828-5539-8667-7a360c932b0a | note | Inspection – Client - H
14e450fa-a501-5ae6-8322-c8e7065d6f40 | note | Comments / Attachments / Records - Method Statement
| signoff | AUTHORITY HOLDPOINT
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
30ff56a1-8051-5278-9da6-4f8ab74da2bb | button | Any non-conformances? | YES, NO
52a924db-18b7-5ce5-ba33-6991614ce0a0 | textbox | No's:
0a1d7a46-10a2-55d1-87fb-decc86d9a874 | button | Closed Out | YES, NO
7217ee1e-4154-58f1-9cef-767ae8f2f65d | button | All work has been satisfactorily completed. | YES, NO
cdf7555b-1b35-559a-97ac-a6348a8b9ba7 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
f2de3c66-0a6d-562e-aec9-1db60ab9b4b6 | textbox | Lot Verified By:
7a82b684-fefc-5a9f-929a-acd7a9a760f7 | textbox | Lot Closed Date:
a9a12cf0-4b1c-5a1e-a84d-67fc5456d36f | button | Submitted to Client | Yes, No, N/A
b3da1067-a7ad-5f33-822a-d2a3b10ec637 | button | Reviewed by Client | Yes, No, N/A
e32951d4-ccd5-5cb2-bdab-5ee621cf455b | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B4.7 - Deck FRP Span 7 Rev 3 | itp | ITP-B4.7 - Deck FRP Span 7 Rev 3 | 393edc4a-a05e-4f06-a485-d5642be29803
| section | Lot Information
| checkpoint | Lot Information complete
e74264fb-98ec-4342-b091-7672ffafe771 | textbox | Lot Opened On
f93b0f92-92f0-499c-860e-465b0569ab93 | textbox | Date of Works
1a70fed3-625c-48c4-98ce-3a2f85d27baa | textbox | Lot Type
c753355a-ec24-46d5-af95-5adec5737f79 | textbox | Start Chainage
cf553271-a955-46cc-ab29-b24608820371 | textbox | End Chainage
b5e083ae-b00b-4997-a34b-f16028cd7565 | textbox | Offset
cbec8eb5-8107-5f97-b0c5-b5dbe121a0bf | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
b4e03324-739c-5063-b627-83e5408c4323 | note | Requirements / Reference - Preliminary Works (FRP) ITP
c83592c6-237e-5ff3-8a38-63fad1708154 | note | Acceptance Criteria - Sign-off of ITP-B4.P FRP Preliminary Works ITP
a2e64417-ce5b-5e21-b438-0e34fe716e6a | note | Frequency / Process Held - Once / Prior to Construction
5b28688a-7489-590f-8d06-3a82bc3e2a87 | note | Inspection – ACPL - H
154675cf-2497-57df-abf0-3fc674aef1b1 | note | Inspection – Client - H
a1359d7a-4059-54be-82cd-78d46f8d7abf | note | Comments / Attachments / Records - ITP-B4.P
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Girder Profile Diagram
9aaef2f7-5c63-54c0-8e88-d44a076515e5 | note | Requirements / Reference - B150 Cl 8 G71
232e612a-de15-50a9-93b5-77a3340f4094 | note | Acceptance Criteria - Before placement of cast-in-place deck concrete, submit a diagram that sets out the profile of the completed member in relation to the profile specified on the drawings. The above shall be performed as a joint survey with TfNSW as per G71.
52155383-eb1a-5aee-a6df-93242f0d8b74 | note | Frequency / Process Held - Once / Prior to placement of deck concrete
bb9a458e-38f3-5834-b4ac-da8ea9b35b12 | note | Inspection – ACPL - H
19321779-f97f-52dd-a244-c34ac05482c3 | note | Inspection – Client - H
f06258d5-708a-5b9e-a121-d0c22f8a1bab | note | Comments / Attachments / Records - Profile Diagram / Survey Report
| signoff | AUTHORITY HOLDPOINT
| section | 2.1 Construction – Pour 1
| checkpoint | 2.1.1 - Survey Set out
e2c36674-74f4-520f-b592-5dda3054fc1b | note | Requirements / Reference - B80 Cl 5.8
d379dc76-2c09-56e9-95ed-4162db9fdb21 | note | Acceptance Criteria - Survey set out as per design drawings
55d7eb22-0253-5c8c-9a27-8d02e0b82ccb | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
739d39db-4bdf-510d-81e8-26fe4a8eea1c | note | Inspection – ACPL - S
5421247d-6fe3-57c0-991f-9f7ab9b6becc | note | Inspection – Client - S
0d39463f-4ba6-57a6-8ba6-7757d05d7c26 | note | Comments / Attachments / Records - Set out Report
| checkpoint | 2.1.2 - Formwork Certification
56938075-09e9-54ae-852d-6e0887c7abbc | note | Requirements / Reference - B80 Cl 5.2.3
95f84212-7c6a-592c-a6ed-91f69553cc0b | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member.
d6caa2a5-79aa-531e-9882-b1c895cec4fc | note | Frequency / Process Held - Prior to constructing formwork
cf84dd85-95c1-5403-b13c-9c59ce6ae407 | note | Inspection – ACPL - H
876b6cb8-583e-5d1c-89cb-7b9a712093e0 | note | Inspection – Client - H
4fcf5a41-2c6e-5bcb-823f-c6cde48f0515 | note | Comments / Attachments / Records - Formwork Documentation Design Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.3 - Certificate of Conformity
a5f90934-aacc-57f3-96b9-be17369bbdc0 | note | Requirements / Reference - B80 Cl 7.5.2
370991af-f9b0-54b0-a45b-48b0717f9eef | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working hours prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s)
7fa9ad51-3646-5f88-9681-5e057266a524 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
1dbbdc23-948f-5ba7-9786-d0ca15a01dc7 | note | Inspection – ACPL - H
541ad84d-9dcb-5404-b791-531c2c10944c | note | Inspection – Client - H
f73936d1-5f77-539a-a54d-b32b2617864e | note | Comments / Attachments / Records - Method Statement Certificate of Conformity
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.5 - Certification of Steel Fixing Prior to Concreting
3b71748d-61d9-55cb-8824-1b2820644f40 | note | Requirements / Reference - B80 Cl 7.5.2
4c2bd158-0abd-558b-bce6-98b7f3d91e60 | note | Acceptance Criteria - Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: 40mm unless otherwise specified Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
eefa1766-5abe-55a2-9fca-93299b9eaf30 | note | Frequency / Process Held - Once / prior to placement of concrete
6e737386-8555-52c2-83d6-5e67004265f2 | note | Inspection – ACPL - H
ab807925-f28a-5e15-8eb3-1ab21ec12e6d | note | Inspection – Client - H
6adbf60f-09e3-5ad2-9cb8-1931b81bce6a | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.6 - Certification of Formwork prior to Concreting
45ca71af-6eef-50c8-94c7-c579e6a915a8 | note | Requirements / Reference - B80 Cl 5
c2a2e7c3-66e4-5b7f-8809-8b2ecbb9c21a | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
ae5ee286-e66f-5615-9642-89f8fb14699d | note | Frequency / Process Held - Once / prior to placement of concrete
66eadf99-2b4d-5f3c-b7dd-d647c0a70474 | note | Inspection – ACPL - H
e81e0f4d-0d80-510d-b9b2-c3e3a2ee36b5 | note | Inspection – Client - H
ef934e6b-e1a1-5960-aca2-a0e65355472f | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.8 - Concreting Personnel
47f5cce1-77be-58c7-a39a-8b7b31c561a4 | note | Requirements / Reference - B80 Cl 7.2.3
06b943e3-5241-5714-9a37-d5b77388a1b0 | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
be06b5d0-a2f3-5c4b-ac7f-73bf870442d8 | note | Frequency / Process Held - Once / four hours prior to concrete pour
a7373c4e-35aa-5563-9b83-ed31ee6eb10b | note | Inspection – ACPL - H
ae931e85-9cd4-5144-81cd-ef83157fa72b | note | Inspection – Client - H
3a1d3443-2aba-5d97-89de-0b2dabf157c4 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards RFI-031
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.9 - Supply and Delivery of Concrete
48fe3d7d-5c8a-507d-951e-06a680ee7111 | note | Requirements / Reference - B80 Cl 4.1
f5404c77-7ba5-58fc-9c9b-bc52cdf677ec | note | Acceptance Criteria - Deck slab must not be poured earlier than 28 days after girder fabrication. All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
bfd428c8-4550-50f5-ba6d-0e88a52ed13a | note | Frequency / Process Held - During concrete delivery
5bcac565-d271-526a-9f81-a847843354ab | note | Inspection – ACPL - S
39f98d34-d027-5971-a307-edbbb67f6b21 | note | Inspection – Client - S
4445ebd9-cfbd-5843-9821-ca606435c22e | note | Comments / Attachments / Records - Concrete Docket Concrete Pour Record
| checkpoint | 2.1.10 - Concrete Sampling
13977ada-2d42-51eb-913b-733c399d3450 | note | Requirements / Reference - B80 Annexure B80/L
27314d0d-e417-5d11-81e8-02f3291b0f2b | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
269ec4db-6420-54f2-9d6c-e3006d48a341 | note | Frequency / Process Held - Each element / prior to placement
efbd4ee5-d678-50e9-a9f2-2004d9c7ea80 | note | Inspection – ACPL - S
4936b28e-e074-53c5-a4fd-79c27f07e35f | note | Inspection – Client - S
9ff8d364-c2bb-59c3-b031-028194c14c62 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.1.11 - Concrete Placement
53113329-dec1-567e-a518-c93afaf047d3 | note | Requirements / Reference - B80 Cl 7
04cd52fa-10e8-5d56-a6fd-fdd556d3b745 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature 5-35C 40MPa Concrete Concrete placed in deck sections to be carried out in once continuous operation as per design drawings Ensure barrier levelling bolts are positioned correctly Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
7c15e4f1-139b-5249-a196-c0e31fad392d | note | Frequency / Process Held - Once / prior to Curing
7052f34c-f034-59c7-85cd-d6af6d986ae9 | note | Inspection – ACPL - S
fb3ee537-9bfd-51b4-8377-12c373fd3a84 | note | Inspection – Client - S
4773a0a0-d8e8-5cda-bb72-b48933258bcc | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record Photos
| checkpoint | 2.1.12 - Concrete Curing / Stripping of Formwork
7121ce6f-65ef-55f2-8676-0eac2c090d16 | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
4c298da9-6e66-596a-aca8-73fc9fdeb160 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting A exposure classification requires 7 days wet curing Formwork to be stripped after no less than 7 days Remove formwork in a way and time that achieves specified characteristics and prevents damage
e98f946f-e0c0-51c0-83a7-35d144619f9d | note | Frequency / Process Held - Once / prior to Concrete Sign off
550aff86-f48e-5654-91c9-7e68c96177f9 | note | Inspection – ACPL - S
5c4ac052-05a5-5426-b04e-a42e0dd4f61d | note | Inspection – Client - S
0cff6589-e416-512d-8211-609f3c562a7b | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.1.13 - Assessment of Defects
a14532e1-fd92-5dcb-a10f-12f2bf8ccecd | note | Requirements / Reference - B80 Cl 9.3
d489c3e0-8ffc-5674-b446-30730ae9bc65 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
f5878c0c-4687-5e16-b555-7e73925a9309 | note | Frequency / Process Held - Inspection following removal of formwork
b5fbe825-c9c4-5dff-98f3-6e95ecb1e17b | note | Inspection – ACPL - S
1e4fc73f-75ae-55f9-9d5f-17045adb2bca | note | Inspection – Client - S
de1af58b-bfdb-5b6b-abef-62b11f36deff | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.1.14 - Concrete Sign off
a14a1eea-1074-5d1c-9518-0fc9ad153dc4 | note | Requirements / Reference - B80 Cl 8
21fd1126-5c18-5eac-95a8-129bf00f97e7 | note | Acceptance Criteria - Min 40mPa at 28 days
f53b0638-e203-5db8-bfb2-148cfc840daa | note | Frequency / Process Held - Once / Stitch Pour
5c56e10e-2e98-59c0-a1c7-07f81c8a8b93 | note | Inspection – ACPL - H
c868bf61-8dcd-5182-9340-ba9007de408a | note | Inspection – Client - H
6329508c-0ea8-545e-91b5-f7e2b5fffc50 | note | Comments / Attachments / Records - Concrete Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.15 - As-Built Survey
626564a1-5490-5e2a-bb95-39889cc45a10 | note | Requirements / Reference - B80 Cl 9
a8237903-5c5b-5ccc-81c6-e2281584e0ae | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Thickness: -5mm / +15mm Deviation in Deck Surface Level (Reduced Level): -10,+5mm Deviation in surface flatness in any direction: 3mm in 3m (1/1000) Deviation in deck joint slot width: -3,3mm Cover survey to also be completed as per RFI-040
0d30e4d3-22cc-5b3d-9eb6-479d24ff90be | note | Frequency / Process Held - Once / Installation of Parapets
2dbe81ee-5bc0-5a79-863e-8c64b3bfd489 | note | Inspection – ACPL - S
35a17828-2c55-5e77-87ef-b47c2a6439c8 | note | Inspection – Client - S
81223125-ffe1-5f49-a072-47d1452e305e | note | Comments / Attachments / Records - As-Built Survey Report Cover Survey Report
| section | 2.2 Construction – Pour 2 (Pier 7 Link Slab)
| checkpoint | 2.2.1 - Survey Set out
e7c08f78-7861-5b1e-976d-865328b7b9fc | note | Requirements / Reference - B80 Cl 5.8
309190f1-a380-5401-9261-89fe38051a95 | note | Acceptance Criteria - Survey set out as per design drawings
2dbf9354-e016-59b5-b63c-8605d8efc6bb | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
f33aadff-9372-5de7-aaf6-f014553ca54e | note | Inspection – ACPL - S
f4e5c708-7c9b-524e-bccf-37998cfeb11e | note | Inspection – Client - S
94933efb-a8ec-594a-b152-e482747c43b8 | note | Comments / Attachments / Records - Set out Report
| checkpoint | 2.2.2 - Formwork Certification
fe2e07bf-1b04-50b7-b05c-348de94d6467 | note | Requirements / Reference - B80 Cl 5.2.3
8c088214-2a95-5830-8a46-d8f19d2a47ba | note | Acceptance Criteria - Formwork and all temporary supports to be designed and conform to AS 3610.1 Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection. Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C. Submit details of proposed construction joint locations together with formwork documentation, which must be perpendicular to the longitudinal axis of the member.
c3c9b5ee-e179-5763-9980-4e7cc2652849 | note | Frequency / Process Held - Prior to constructing formwork
a8f193ec-5f64-50df-9b7d-66281ed35e2f | note | Inspection – ACPL - H
a223beaa-9794-5389-aa76-e82827b7b351 | note | Inspection – Client - H
de8cdb62-cd5f-581d-9dc2-5573c1ce0696 | note | Comments / Attachments / Records - Formwork Documentation Design Certification
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.3 - Certificate of Conformity
8e8b2154-0435-5f39-99a6-e4b9af08ba5e | note | Requirements / Reference - B80 Cl 7.5.2
86ca8315-2680-5e8d-b18f-55bfb25a8fd2 | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working hours prior to commencement a Certificate of Conformity of formwork, reinforcement, placement of 10 thick bitumen impregnated fibre board and embedment’s for the member(s)
3f6d424b-e3dc-557b-a159-ac2add044530 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
e22bf94d-5e1a-5e9d-9048-9d0c2b0ad570 | note | Inspection – ACPL - H
273e805e-4216-52d2-89db-35964314e4d7 | note | Inspection – Client - H
1b7a7799-3197-58c8-9136-963db9501d95 | note | Comments / Attachments / Records - Method Statement Certificate of Conformity
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.4 - Certification of Steel Fixing Prior to Concreting
8a3bfe99-6991-53b7-bade-268942d05100 | note | Requirements / Reference - B80 Cl 7.5.2
870c9552-fda1-5aba-b6c7-0fe22ae97af7 | note | Acceptance Criteria - Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: 40mm unless otherwise specified Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
cf492287-8b92-55d2-b394-2dc217f89e2a | note | Frequency / Process Held - Once / prior to placement of concrete
9a38936e-b53d-5af8-8013-bcc96b2f6ea3 | note | Inspection – ACPL - H
3868c9eb-d838-5ba3-806c-ab6a4309a94c | note | Inspection – Client - H
42972d72-8d81-5fd6-8573-7319821978de | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.5 - Certification of Formwork prior to Concreting
5a49d5a9-dfff-51f7-8704-a214887490cb | note | Requirements / Reference - B80 Cl 5
b0c27f63-4bfd-5f8a-b6e2-0c7665e927f0 | note | Acceptance Criteria - All formwork to achieve concrete with Class 2X finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
dc6869a2-a1d5-573f-bb3b-9f35e3365f82 | note | Frequency / Process Held - Once / prior to placement of concrete
fc6ac5eb-c0b6-5537-bd8d-fc0108e7388a | note | Inspection – ACPL - H
54b64679-be2d-5140-8aff-9361bceb22f2 | note | Inspection – Client - H
fc57e756-6148-5c4d-ba6c-7f12a9c6ccf5 | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.6 - Concreting Personnel
b8f10b3d-0b12-569e-b9e5-1ce716d3a15a | note | Requirements / Reference - B80 Cl 7.2.3
5ed6bcfb-9d53-5b95-9b03-3cdecd4d5bf3 | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
e208aa87-0c52-51f2-9955-15574b86d452 | note | Frequency / Process Held - Once / four hours prior to concrete pour
8b7e4724-80d9-5e30-aef1-0b04b1312456 | note | Inspection – ACPL - H
c1ede5ef-2e2a-53c5-a573-5ff659b3d446 | note | Inspection – Client - H
98c633e6-7a09-5534-86ae-9149b4d5e913 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards RFI-031
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.7 - Supply and Delivery of Concrete
91b5e786-b19a-5019-9fd6-d147a4432f16 | note | Requirements / Reference - B80 Cl 4.1
18bb624e-4129-5f39-a6e0-b7daf63ba6e8 | note | Acceptance Criteria - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
4a7c15ec-f1fa-5942-8631-c4eefadfdef5 | note | Frequency / Process Held - During concrete delivery
488a3632-4f64-57b0-b348-86cf3c7f51ee | note | Inspection – ACPL - S
3e71d361-79c9-5134-98e4-df2045a8b7d5 | note | Inspection – Client - S
f4a69e2b-22e7-5183-90fd-3dd30f45b844 | note | Comments / Attachments / Records - Concrete Docket Concrete Pour Record
| checkpoint | 2.2.8 - Concrete Sampling
f60316a2-1056-5cc3-8c9d-ed1d48f369f1 | note | Requirements / Reference - B80 Annexure B80/L
b90d4ce8-1e05-533a-aae4-f2e09d812deb | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 100 +/- 20mm
0597baa1-a845-5a55-899f-1a7516f2bf3b | note | Frequency / Process Held - Each element / prior to placement
a50ba832-f20c-56a1-bcc4-1b32f151e77d | note | Inspection – ACPL - S
0383809c-64b7-5ccd-a230-1893df5e67bf | note | Inspection – Client - S
8e8a3f83-3ba4-5cac-bf8e-d0833b4e3d32 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.2.9 - Concrete Placement
f6c77370-a4e5-5f55-8933-d0cf8fc36e83 | note | Requirements / Reference - B80 Cl 7
8e85f15b-23ac-5ccf-bf4f-d7cc17d569e7 | note | Acceptance Criteria - Prior to placement deck segments must have reached 32mPa Concrete temperature at discharge >10C and <32C Ambient temperature 5-35C 40MPa Concrete Concrete placed in deck sections to be carried out in once continuous operation as per design drawings. Link slab to only be poured once the average age of girders within that deck segment is 70 days Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
ccb975c2-a58f-5276-bf0f-09c28a933d6d | note | Frequency / Process Held - Once / prior to Curing
f6ae8220-93cb-5989-9918-b05e5ae32a0c | note | Inspection – ACPL - S
7d49caf4-963b-5a62-b7e6-b2bf21f0e47b | note | Inspection – Client - S
a6d003ad-9e93-55d0-bf29-26101050fdd0 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record Photos
| checkpoint | 2.2.10 - Concrete Curing / Stripping of Formwork
37ffe517-5d6d-5dba-a8af-70524cb4c4ba | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
f71e0b3b-eed5-52cf-97fa-d4048824ea99 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Curing agent Fosroc A99 to be applied once formwork is stripped A exposure classification requires 7 days wet curing Formwork to be stripped after no less than 1 day Remove formwork in a way and time that achieves specified characteristics and prevents damage
bc6ba102-be7c-5919-afc4-d0352f7403ee | note | Frequency / Process Held - Once / prior to Concrete Sign off
2b2640b8-6072-5e06-b4ef-ebf5fcf7e4d9 | note | Inspection – ACPL - S
99a25446-ae80-589f-8391-66d9acc13164 | note | Inspection – Client - S
00a17670-7b07-5cf6-b4a0-f0d5e70fee72 | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.2.11 - Assessment of Defects
d6fa2215-0225-5e51-a26f-8a7c37926e18 | note | Requirements / Reference - B80 Cl 9.3
8732cf9d-59a2-5d09-911c-93ca487bbec0 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
d440d590-de3a-5132-a2f2-945c5939d693 | note | Frequency / Process Held - Inspection following removal of formwork
d5851a96-2e8c-5880-9512-34b7b5762146 | note | Inspection – ACPL - S
ee3f1dff-333c-567d-ae52-b7da677b5fb4 | note | Inspection – Client - S
81f5ab64-6c1c-5573-84f4-b1fbfaf9acad | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.2.12 - Concrete Sign off
dd7a2d95-41b7-574b-a5a4-166d6d6d7cfb | note | Requirements / Reference - B80 Cl 8
13dd9fb2-6fb2-5f52-88be-5de0c3ff3374 | note | Acceptance Criteria - Min 40mPa at 28 days
5dbaa61e-9e7f-5142-aed7-f40366a7c60f | note | Frequency / Process Held - Once / Stitch Pour
149d669d-c326-5441-ba5e-1a2559f3b5cc | note | Inspection – ACPL - H
67244695-974b-58ad-a0cb-ffee0cbaf143 | note | Inspection – Client - H
4fa68c23-36ca-540d-96f3-09aa52847116 | note | Comments / Attachments / Records - Concrete Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.13 - As-Built Survey
9604d947-3d29-5e66-b725-487718891b59 | note | Requirements / Reference - B80 Cl 9
e1975d56-3ad4-58ae-a1b3-06adcbc64617 | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in Thickness: -5mm / +15mm Deviation in Deck Surface Level (Reduced Level): -10,+5mm Deviation in surface flatness in any direction: 3mm in 3m (1/1000) Deviation in deck joint slot width: -3,3mm Cover survey to also be completed as per RFI-040
31aee372-6835-5963-8a5d-53eadf4d73dc | note | Frequency / Process Held - Once / Installation of Parapets
2adc9207-f88f-5919-a027-9454b3d7d484 | note | Inspection – ACPL - S
e2744422-6e3e-59b0-a2a3-e9aef2498b29 | note | Inspection – Client - S
98e5f804-9ab8-54ef-8b64-dcfd25c6837b | note | Comments / Attachments / Records - As-Built Survey Report Cover Survey Report
| section | 2.4 Construction – Pour 4 (Span 7 Stitch Pour)
| checkpoint | 2.4.1 - Mix Design Approval
413d7ba2-5565-511c-a8f0-64de47592d66 | note | Requirements / Reference - B80 Cl 3.9
7c378672-490c-5ea8-bf81-c82f8e1628c0 | note | Acceptance Criteria - At least 4 weeks prior to the proposed date for use of the concrete mix, submit to the Principal the following: (a) (i) all details in Clause 3.9.3; or (ii) mix ID and concrete mix design of a nominated mix from the Register of TfNSW Concrete Mixes; and (b) a statement stating that the mix conforms to this Specification and is suitable for its intended use.
89d6d4e2-1003-502c-9654-2cb780ad789a | note | Frequency / Process Held - Once / at least 4 weeks prior to using mix
690a6106-cd72-58ca-9917-62cc583c00be | note | Inspection – ACPL - H
dcae7b12-2bb9-53c2-bf3a-5232aab0f126 | note | Inspection – Client - H
93d64923-0d43-50fc-a56f-ccfaeaab2e44 | note | Comments / Attachments / Records - Mix Design Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.1 - Survey Set out
d88deb09-e947-597e-b65f-606976a024c3 | note | Requirements / Reference - B80 Cl 5.8
ce4a2370-e026-55b8-a03c-c9f3647a5d11 | note | Acceptance Criteria - Survey set out as per design drawings
3a788a9e-974c-569c-86b9-f73b37e9d7c8 | note | Frequency / Process Held - Once / Prior to Fixing of Steel Reinforcement
1b03e8ab-02ec-5c19-8421-5deb010e914a | note | Inspection – ACPL - S
f383e396-7f40-5f9d-9003-cb003f3a171f | note | Inspection – Client - S
a53667ae-c135-5edd-b41e-df2fe731c58b | note | Comments / Attachments / Records - Set out Report
| checkpoint | 2.4.3 - Certificate of Conformity
ad7c2565-8030-56b0-9db8-e8e25a3e115b | note | Requirements / Reference - B80 Cl 7.5.2 BR-DRG-1075
0e3e0c86-de13-5575-8a16-aaa358127de7 | note | Acceptance Criteria - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working hours prior to commencement a Certificate of Conformity of formwork, reinforcement and embedment’s for the member(s) At pier centrelines, note requirement for 30mm backing rod, corkboard and 20mm deep sealant.
150bf429-e71d-57f7-8d9a-72ee94505b13 | note | Frequency / Process Held - Prior to pouring these member(s)// Each placement of concrete in the works
e144bb8e-db12-5caa-9445-4f3331d7d7e3 | note | Inspection – ACPL - H
f3d27c7d-b067-52c8-8516-8d09546b58de | note | Inspection – Client - H
4a3a1d70-d329-5efb-b8d4-7c1920f8a8e9 | note | Comments / Attachments / Records - Method Statement Certificate of Conformity
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.4 - Certification of Steel Fixing Prior to Concreting
b1c9fa8b-1c03-50b4-b82b-8e8173dde0d8 | note | Requirements / Reference - B80 Cl 7.5.2
9553b677-00f2-565f-b76e-f6fa9e4016f2 | note | Acceptance Criteria - Tie wire must be annealed steel wire having a diameter of not less than 1.2mm, where required, tack weld in accordance with Cl 6.5 Wire ties must have a clear cover equal to that shown on the drawings. Required Cover: 40mm unless otherwise specified Spacing of bars ± 15mm, or ±0.1s, whichever is greater as per Table B80.15
72cf876b-ecf8-5cb6-a1d0-5fdf4e137ba8 | note | Frequency / Process Held - Once / prior to placement of concrete
34d06c97-8592-53b8-afd7-0de0e62575b8 | note | Inspection – ACPL - H
6df27bf5-25bb-5d6a-8e41-2a7c516b07c0 | note | Inspection – Client - H
d678ab2d-ee46-5a5a-ae2a-698137996d3d | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.5 - Certification of Formwork prior to Concreting
97ecfe71-066f-5fb1-be6b-e2146af5bc07 | note | Requirements / Reference - B80 Cl 5
9409bc66-13f1-5a5e-b123-f9f5d10f6b1a | note | Acceptance Criteria - All formwork to achieve concrete with Class 2 finish. Formwork strictly in accordance with the certified formwork documentation and drawings. Timber forms to be used. Plywood panels with the grain of the outer plies perpendicular to the studding or joists. Formwork to be mortar-tight.
4ac5e395-b74f-5cdf-8401-06ff9d6aae40 | note | Frequency / Process Held - Once / prior to placement of concrete
9f3a7d68-da8e-53f1-80eb-f7a3a2dd6bc6 | note | Inspection – ACPL - H
ff0b6e65-8154-5ee2-93e2-a01d114f2e09 | note | Inspection – Client - H
5489da6e-fadb-521c-b84f-7b7e110afcf7 | note | Comments / Attachments / Records - Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.6 - Concreting Personnel
e7e87024-7c8e-55b8-9f14-fdb799069169 | note | Requirements / Reference - B80 Cl 7.2.3
9fcee4b3-58dd-5ba4-9744-c3dc3a6b6cae | note | Acceptance Criteria - At least four working hours prior to pouring concrete, submit to the Principal a statement stating that at least half of the personnel who will be involved in bridgeworks concreting operations hold a TfNSW Bridgeworks Concreting Grey Card – via email
111f5392-0f79-53f7-a404-a7d0ed90e0ad | note | Frequency / Process Held - Once / four hours prior to concrete pour
53ebbc87-e5b7-5913-b1a7-fb7d72e86034 | note | Inspection – ACPL - H
f00749e4-7e7e-5720-bbd7-8c76582a61f3 | note | Inspection – Client - H
f6f42a9c-585f-57f3-941b-6db4069cbbbe | note | Comments / Attachments / Records - Concreting Personnel Grey Cards RFI-031
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.7 - Supply and Delivery of Concrete
67ce6852-914e-511e-ba2b-a0fd68e16a5b | note | Requirements / Reference - B80 Cl 4.1
a0956996-1359-5887-9933-a3882624830a | note | Acceptance Criteria - Parapet stitch pour only to be complete once adjacent expansion joints and link slabs are complete. All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching. Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added Reject nonconforming batches of mix, or seek dispensation from the Client on site and prior to pouring
544f402b-f50c-5a1d-a3c7-719be4f7e03b | note | Frequency / Process Held - During concrete delivery
1986bb4f-20b6-53b9-bd79-3b3ad77df2bf | note | Inspection – ACPL - S
a2a1a07f-4658-5a3e-a622-5f83e5763e06 | note | Inspection – Client - S
33e17fa7-3d6c-5bbe-8189-d30917e7cf1c | note | Comments / Attachments / Records - Concrete Docket Concrete Pour Record
| checkpoint | 2.4.8 - Concrete Sampling
cc5482b9-459c-5a02-a67b-2f76db6ace17 | note | Requirements / Reference - B80 Annexure B80/L
40a9f706-c2cc-5202-a469-1381399a633c | note | Acceptance Criteria - The nominal rate of sampling shall be taken: - Compressive Strength: 1no. 7-day and 2no. 28-day samples per 25m3 (or per pour if <25m3) - 1no. slump test per batch of concrete 110 +/- 20mm
fba33bc6-7aa5-5fe3-bff5-8e8024582b67 | note | Frequency / Process Held - Each element / prior to placement
6c8cd647-42c4-57ea-b653-1c1fd710347d | note | Inspection – ACPL - S
d75bbd6a-3cba-5eec-86e7-04362575ff65 | note | Inspection – Client - S
1e9932c0-b04e-50f4-92a9-4c184a213d17 | note | Comments / Attachments / Records - Test Results
| checkpoint | 2.4.9 - Concrete Placement
afe729af-1876-5775-b542-51c0bbc84d09 | note | Requirements / Reference - B80 Cl 7
520331a7-a5ea-5c5d-910d-19b31cc69441 | note | Acceptance Criteria - Concrete temperature at discharge >10C and <32C Ambient temperature 5-35C 40MPa Concrete Concrete placed in stitch pour sections to be carried out in once continuous operation as per design drawings Continuously measure concrete and air temperature during placement Do not place concrete is temperature is below 5 degrees or above 38 degrees, or the temperature requirements stated on the drawings Do not place concrete during rain or when appears imminent Remove all loose material, tire wire, timber, concrete, dirt or water prior to placement Continuously monitor placement and compaction Vibrators must have a min dia. of 50mm operating between 130-200Hz with 1 vibrator per 10m3 placed per hour, min. 1 stand-by Compact and vibrate on a regular, systematic manner, to the full depth or each layer and 100mm into the underlying layer Submit procedure for the restrictions of the evaporation rates to less than 1kg/m2/hour as part of the requirements of Annexure B80/D
de102aea-3092-5c4a-84ec-f3ae74ef1e5b | note | Frequency / Process Held - Once / prior to Curing
b30e4897-251e-55b7-a4b3-e925a1375644 | note | Inspection – ACPL - S
757cb48f-1354-58f5-8d98-54dbd02b0fe8 | note | Inspection – Client - S
25441556-d754-5992-ab3a-316ba90fa362 | note | Comments / Attachments / Records - Concrete Dockets Concrete Pour Record Photos
| checkpoint | 2.4.10 - Concrete Curing / Stripping of Formwork
064fb53c-3746-5b22-a045-ec8d1a8b4cdd | note | Requirements / Reference - B80 Cl 8 B80/E IA182600-JAC-DD-BR-DRG-1023
3ed9aa6d-de34-5bef-92af-5bc2ef414eb8 | note | Acceptance Criteria - Protect the concrete from extreme heat or cold and ensure temperatures do not drop below 5 degrees Wet cure all cast in place bridge decks and approach slabs or min. 72 hours after finishing, then follow approved curing regime. Ensure wet curing surfaces are completely covered in hessian with plastic sheeting A exposure classification requires 7 days wet curing Formwork to be stripped after 4 hours to allow finishing. Remove formwork in a way and time that achieves specified characteristics and prevents damage
176657fe-05d6-5b5e-8918-17a9fa7c7a05 | note | Frequency / Process Held - Once / prior to Concrete Sign off
0bb7cb69-c659-5eeb-85eb-9fd255495a56 | note | Inspection – ACPL - S
ee7f2cdc-7645-5b00-a18d-83cd951781d8 | note | Inspection – Client - S
e4d53423-0456-5d83-a1e4-58b00b63103f | note | Comments / Attachments / Records - Concrete Pour Record
| checkpoint | 2.4.11 - Assessment of Defects
10c09b3c-1f8c-5a9d-80fc-73a176cdf6ad | note | Requirements / Reference - B80 Cl 9.3
e00ec130-98ba-5bda-9864-751b8b342876 | note | Acceptance Criteria - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days Submit crack map to the principal with proposed remedial actions Non-conforming surface imperfections and defects also to be recorded and assessed.
c6c8f295-bddf-5c9d-a2ef-124ee5827ffa | note | Frequency / Process Held - Inspection following removal of formwork
2935de0d-d7fd-5db1-957d-160a507daca1 | note | Inspection – ACPL - S
c71c3efd-9d61-5603-8e72-c76b73621e5d | note | Inspection – Client - S
beee7eff-a609-5547-b67f-d0837b9d6926 | note | Comments / Attachments / Records - Crack Map
| checkpoint | 2.4.12 - Concrete Sign off
5c4965dc-9d96-5b97-8541-eefb3f8fd260 | note | Requirements / Reference - B80 Cl 8
9eaadaf4-0037-5305-a617-352e50f5b156 | note | Acceptance Criteria - Min 40mPa at 28 days
0caedfce-2461-50d7-b36b-241596713215 | note | Frequency / Process Held - Once / Stitch Pour
04832ecd-3533-5377-af52-eb988f1fefc8 | note | Inspection – ACPL - H
be66b81b-ae5a-5142-b8f3-c8d7b4a117c9 | note | Inspection – Client - H
13296b06-d5f7-5bf2-8be5-d8574ec04273 | note | Comments / Attachments / Records - Concrete Test Results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4.13 - As-Built Survey
2d052f79-79c1-5322-8e52-d1acb124321e | note | Requirements / Reference - B80 Cl 9
513e7380-1219-5681-bccf-4cac40a1a623 | note | Acceptance Criteria - Survey report of final as-builts Allowable Tolerances: Deviation in dimensions: -2.5, +2.5mm Deviation from plan position (at any level): 25mm Deviations in plan from straight or curved horizontal alignment: 5mm in 3m (1/600) Deviation from design grade: 3mm in 3m (1/1000) Deviation from vertical or specified batter: - Unexposed concrete: 12mm in 3m (1/250) - Exposed Concrete:6mm in 3m Deviation in height above deck slab: -5,+10mm Step anywhere on top or side surface: 5mm Front face flatness: 3mm in 3m (1/1000) Relative displacement between adjoining members: 10mm Deviation in barrier end posts dimensions: -5, +5
697fbe3f-f13c-5c14-9329-77dbede4bb85 | note | Frequency / Process Held - Once / Installation of Parapets
1de74783-e253-5d9c-a43f-d40c203461ca | note | Inspection – ACPL - S
9216f417-d184-5cf8-8cc9-f9850c40ff41 | note | Inspection – Client - S
d1bea8c7-bc9c-5f65-9ea8-ce5cd273b90b | note | Comments / Attachments / Records - As-Built Survey Report Cover Survey Report
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
7c5b253b-7b82-54f4-9c61-ff99e4964032 | button | Any non-conformances? | YES, NO
11918cb6-c8c0-5192-87aa-c88706ffbe2d | textbox | No's:
3a153eee-f620-50db-9db7-de1063506ca1 | button | Closed Out | YES, NO
90793fc8-22fd-55f1-9c20-7dc446a87077 | button | All work has been satisfactorily completed. | YES, NO
077e1c88-3b99-5852-ba16-4a4117d4f5e1 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
e9380114-55e3-5e6f-8e85-21dfc3b20585 | textbox | Lot Verified By:
39912f89-511a-5a0b-9441-e37b870ee296 | textbox | Lot Closed Date:
a414f0a9-e7e0-5c05-87d5-9d60bf8e545f | button | Submitted to Client | Yes, No, N/A
7d853130-2fcf-5934-84c2-cc7be6a1e55d | button | Reviewed by Client | Yes, No, N/A
a3ca90ea-c1f4-58e0-8656-6e93c9726ba8 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B4.P - Deck FRP Preliminary Works Rev 2 |  | ITP-B4.P - Deck FRP Preliminary Works Rev2 | ab1e5380-e447-4fd6-abf5-64a874fd00ba
| section | Lot Information
| checkpoint | Lot Information complete
f00ae8c3-f5da-4e3e-befe-c64d41ae1dcc | textbox | Lot Opened On
f96813ec-e3a3-4226-9105-2df9897311d5 | textbox | Date of Works
9820175d-ca20-4f7f-92f6-acc1fedc7a65 | textbox | Lot Type
205790f3-fb20-4523-abef-2b6c9e9e7d6c | textbox | Start Chainage
11a36a2f-7010-463c-a75f-9d708b574ceb | textbox | End Chainage
c34746ea-e412-48e9-930e-0e1d22c66289 | textbox | Offset
bcd59343-a6da-5d9f-9944-0a2d824d4c42 | textbox | Control Line
| section | 1. Prelims
| checkpoint | 1.1 - Safety Review
c972248a-7c22-5859-ab20-75f30d63fc3c | note | Requirements / Reference - Project Safety Plan
4001f2f6-31e8-5b79-bb4b-0b16d09962b7 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed. Subcontractor’s safety plan/procedure approved.
ebe27761-9ad4-572d-b450-86ca45a5e269 | note | Frequency / Process Held - Before Commencement of Works
35cfe48c-3e44-5341-9503-acf9146c16ac | note | Inspection – ACPL - W
d1c92722-3d64-543d-9213-66993f885d40 | note | Inspection – Client - S
04533893-4512-588b-ace0-ec0ca2fc3dbc | note | Comments / Attachments / Records - Signed SWMS
| checkpoint | 1.2 - Environment
f7312ebe-e6c8-5699-a014-22eff88823a9 | note | Requirements / Reference - Project Environment Plan
db837c76-3957-59c5-be76-7f8814d93f22 | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs. Air quality to be visually monitored for dust etc as a direct result of construction activities.
b09c218e-3640-5f22-bf14-b6826a2712ee | note | Frequency / Process Held - Before Commencement of Works
bdafca76-7380-545a-a7bb-46ed1b5f0e6a | note | Inspection – ACPL - W
df92cdc8-f3f4-5b93-96da-9c631fd81de2 | note | Inspection – Client - S
6c8c788e-466b-5a1c-a9a4-4c6acda3adf3 | note | Comments / Attachments / Records - SECP AQMP
| checkpoint | 1.3 - Submission of Nominated Mix Design
7cad9df9-f8a6-5607-ae08-6ef333942194 | note | Requirements / Reference - B80 Cl 3.9.1
368167b0-12a5-5736-a6a4-bb35b9344b25 | note | Acceptance Criteria - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
b5980be0-5644-5b6b-99ce-3b4f42757c88 | note | Frequency / Process Held - Prior to ordering concrete to site
6feba5eb-7e14-534f-967c-ef4ee5912b3a | note | Inspection – ACPL - H
d1c7e505-a497-5b4c-9358-26d8b90dcaa7 | note | Inspection – Client - H
3d57c174-97cb-5fc2-9c0d-3b9892eefe93 | note | Comments / Attachments / Records - Mix Design Submission
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Concreting Personnel
10bc22e6-e28c-5e1a-9772-ca3c03882dd5 | note | Requirements / Reference - B80 Cl 7.2.3
4dc43247-209d-554c-a2fe-8050b4c3aa35 | note | Acceptance Criteria - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
1034a52b-923b-549a-8494-b8339d04a708 | note | Frequency / Process Held - Prior to first concrete pour
9b7ff14d-900a-535a-97e6-0a9d649efd8b | note | Inspection – ACPL - H
220440f2-4dad-5c85-8d4b-7a91583ac603 | note | Inspection – Client - H
a6bb0c33-698f-5a07-a64b-2d860a163259 | note | Comments / Attachments / Records - Concreting Personnel Grey Cards
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Fabrication of Reinforcement
343a38cf-1ece-545e-91ed-9319214d1c58 | note | Requirements / Reference - B80 Cl 6
57ffc899-9792-59d3-8d57-cb109962c535 | note | Acceptance Criteria - Steel reinforcement must be certified by the ACRS for conformity of the reinforcement production and processing to the requirements of AS/NZS 4671 Chairs and Spacers must comply with AS/NZS 2425. The smallest chair or spacer dimensions must not be less than the specified cover, and the largest dimension must not exceed 1.8 times the cover. Fabrication tolerances must be as shown in Table B80.14
a65aaa35-93e8-591a-b8a5-d1b801306d86 | note | Frequency / Process Held - Once / Prior to FRP
215bfbd6-92d1-5b41-8e06-a7692ea4f285 | note | Inspection – ACPL - S
2ab60c14-09c6-506b-b578-61f7628ddf0c | note | Inspection – Client - S
eb77e89a-dcaa-5e24-b092-7be0553c57bc | note | Comments / Attachments / Records - Checklist ACRS Certificate
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
1b969290-9314-579e-9657-98d654a9a2c2 | button | Any non-conformances? | YES, NO
c01d1bd0-85c7-5df9-a25d-49b11e9cdfbd | textbox | No's:
ba286a97-d1b0-5533-b4ec-60c4f5ebf2c2 | button | Closed Out | YES, NO
868e959a-59b8-5e3b-923a-6399da4c8903 | button | All work has been satisfactorily completed. | YES, NO
34d95744-9ae3-57b9-95fd-5bcd30a830c7 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
2a71da31-562b-5970-bd95-ae3494e2742d | textbox | Lot Verified By:
a818e484-3379-5c68-baff-8a2e75ba04a4 | textbox | Lot Closed Date:
46b4040d-a48c-551f-bc9d-ca63c0bccfa0 | button | Submitted to Client | Yes, No, N/A
1777fe1b-c50f-5e6d-8299-2c011f3bb653 | button | Reviewed by Client | Yes, No, N/A
6ad0e924-ae1c-520e-a944-312c91617d59 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | ITP-B5.7 - Parapet Installation Span 7 Rev 2 | itp | ITP-B5.7 - Parapet Installation Span 7 Rev 2 | 6669e58e-d6cf-460b-bc28-e13643754743
| section | Lot Information
| checkpoint | Lot Information complete
22e5adb8-f7ca-4bf8-abd4-217a18cf59b5 | textbox | Lot Opened On
dac1df44-8930-49b8-82a5-ee4031f23d4d | textbox | Date of Works
8141b382-f898-42e2-aa03-98d56d4368ce | textbox | Lot Type
a8f7663f-9e23-41d5-89bb-c1a0f08c1b2a | textbox | Start Chainage
55dd982e-072f-4b4b-bd62-573ebf066d9f | textbox | End Chainage
1c284b0a-b418-4891-a407-39d81c7e533b | textbox | Offset
cd916635-cff4-5047-8299-7e5a0c45f249 | textbox | Control Line
| section | 1. Preliminary Works
| checkpoint | 1.1 - Preliminary Works ITP Signed off
44f80ae5-bd4a-5e77-9138-55d06c6c1cd4 | note | Requirements / Reference - Preliminary Works (FRP) ITP
faa9cb44-27fe-526f-97dc-811b154fe3b2 | note | Acceptance Criteria - Sign-off of ITP-B5.P FRP Preliminary Works ITP
0f6097b4-f98f-5785-b71a-ebb5fc003144 | note | Frequency / Process Held - Once / Prior to Construction
4c4c6398-f8d4-533e-af90-3d00a605cc53 | note | Inspection – ACPL - H
db7af8c9-936e-5e56-9a4b-b729014b3ce5 | note | Inspection – Client - H
c4124d63-5998-5c5b-96b5-932232c0e70b | note | Comments / Attachments / Records - ITP-B5.P
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Conformity of Supporting Member
6439c72f-f708-555e-9da1-6ee7863a1c7b | note | Requirements / Reference - B153 Cl 4.3
cdf22f20-a9b5-5c7a-a60c-48d6c7965380 | note | Acceptance Criteria - Concrete in supporting members has attained at least 80% of the specified strength (32mPa)
9e0f5094-77ef-57b2-9d28-a88872cfbb5c | note | Frequency / Process Held - Once / Prior to Erection
61e05daa-b40b-589c-97a1-2e08d17077ca | note | Inspection – ACPL - S
41dec016-c4e3-594b-8e36-90e6296a98bf | note | Inspection – Client - S
bcc43856-3b83-5f58-b9d6-3d8973d4787a | note | Comments / Attachments / Records - Concrete Test Results
| section | 2. Parapet Installation
| checkpoint | 2.1 - Pre-Alignment
0fb981c8-5db4-5a54-80f3-b6794db53c13 | note | Requirements / Reference - B153 Cl 4.4.1
f9849f67-2ffa-5745-b6d0-ce461c1120c7 | note | Acceptance Criteria - Submit a certificate verifying that the location of all permanent and temporary supports are in accordance with the profile shown on the drawing.
e79ab7dc-fbd9-54bd-b5ed-e8e117d21de2 | note | Frequency / Process Held - Once / one working day prior to erection
410db86d-846e-57bb-9659-30571a031ddd | note | Inspection – ACPL - S
d4d2b5f2-894c-56df-957d-d754969d9116 | note | Inspection – Client - S
f5c9b97b-f410-55c2-9a0c-f7c240cac994 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 2.2 - Verify Correct Parapet Type for Location
67c6dd34-1666-55e7-b08e-15f0e8df170f | note | Requirements / Reference - DRG-1071-73
d208c220-3eee-5331-93f5-2dbfa59cd242 | note | Acceptance Criteria - Ensure correct parapet type at placement location using bridge design drawings.
9477d951-8e5b-5bda-9f7d-0cf1498f42c9 | note | Frequency / Process Held - Once / prior to each placement
215cdd04-4922-50df-aa4b-c802bfc23cee | note | Inspection – ACPL - S
ea78c045-80ea-552b-ad61-dec277c587de | note | Inspection – Client - S
a5ea08e0-9268-5196-94de-85c76fc33516 | note | Comments / Attachments / Records - As-Built Record
| checkpoint | 2.3 - Erection of Parapets
424c97fb-4419-5901-9d50-acab1940ed71 | note | Requirements / Reference - B153 Cl 6.1,6.2,6.3
9a158e36-52da-5e19-a810-963737a51ef2 | note | Acceptance Criteria - Ensure that:
ff202a7e-b4a1-56ab-9ea9-29bf0d9fc66d | note | (a) each member is placed in position safely, without damage to the member or the structure; and
ee03b348-a1cb-56d6-9304-4899ff0f6a3c | note | (b) the intended permanent structural action of the member is not:
b4bb7c18-7b01-561e-9ebb-7550fd6a6d92 | note | (i) restrained; or otherwise
a8ae497b-dbad-582f-b23c-8d3726f67df7 | note | (ii) adversely affected by the process of erection or by movements which occur due to environmental or construction-related forces, before the member is finally integrated with the adjacent parts of the structure.
71af16db-a05d-594c-9b4e-f39cf10f78f4 | note | Give the Principal at least 2 working days' notice of the proposed date to commence erection.
250eb38c-4d44-5cb0-8bdc-9328f47d2566 | note | For the purpose of erection, lift members only by means of the inserts provided thereon and as specified on the Drawings. The angle of the sling must be within the specified range at all times.
74f5a4f1-e183-55bb-be9f-af5abf7bc83b | note | Submit a certificate specifying the safe lifting capacity of the equipment. Position the lifting equipment such that the turning radius, if any, does not endanger the stability of the equipment. Ensure the mass of the units to be lifted is within the capacity of the equipment.
35ace48b-c628-550c-a62c-b523b7a83423 | note | For non-light pole parapets: Hold down bolt to be secured prior to release of parapets.
8a6203b7-6749-5581-919a-fbe40af4cbee | note | For light pole parapets: Hold down bolt to be secured and welding of ligatures to be complete prior to release of parapets.
ee89654a-2ec8-5f97-a811-7ecc1414fc4f | note | Frequency / Process Held - Once / Following each placement
02e58789-2831-56a1-a0d9-764cf4411fd0 | note | Inspection – ACPL - S
7e54662c-4f94-57ee-ac76-7517fc69e2e3 | note | Inspection – Client - S
55d26a2e-50bf-51d5-948b-49982b2d79eb | note | Comments / Attachments / Records - SWMS
| checkpoint | 2.4 - Installation of Conduit Connection at Expansion Joint
00e7ff56-4a1f-5df0-b1e3-7a93b691128f | note | Requirements / Reference - BR-DRG-1076
05eb69ff-2a5f-5049-a837-055258308ba9 | note | Acceptance Criteria - Install conduit connection at expansion joint location as per detail on design drawings.
b1197a12-5edc-59fd-9ca5-2ea72c8ad49d | note | Frequency / Process Held - Once / Landing of subsequent parapet
0bad7425-8291-598b-ade8-cdcb681922c5 | note | Inspection – ACPL - S
a7a15cdb-661b-5612-b973-99268714499a | note | Inspection – Client - S
8df00815-6c06-52e5-a78d-94287b84b9a4 | note | Comments / Attachments / Records - Checklist
| section | 3. Position Verification
| checkpoint | 3.1 - Alignment and Tolerances
db39aaac-53e0-5aec-a561-571ef91cc2b1 | note | Requirements / Reference - B153 Cl 6.4 B80 Table B80.18
7f237b20-63aa-5ee3-aa7f-00a37b3a34ba | note | Acceptance Criteria - Place members in their correct position as shown on the Drawings. Properly align members placed in series adjacent to one another within specified tolerances. Check all alignment dimensions before finally fixing or grouting the units. The above tolerances apply to the as-cast formed surface prior to surface treatment, if any.
c8889711-c8a2-5050-b5ae-d7f0fcdaf5a4 | note | Frequency / Process Held - Once / Prior to landing next span
94d78327-2c8c-54d6-b16d-78b78f78c80c | note | Inspection – ACPL - S
8a99ee20-a10a-5c74-98c0-b6297578afb1 | note | Inspection – Client - S
8c583fe0-b612-5c38-a31a-f306debf7f45 | note | Comments / Attachments / Records - Survey Report
| checkpoint | 3.2 - Profile Diagram
bab41bb0-af69-55ac-9ed5-eeee9bd2fe81 | note | Requirements / Reference - B153 Cl 8
4b04a9df-d303-556d-a32f-38401745809c | note | Acceptance Criteria - Before placing of the cast-in-place concrete, or permanent fixing of precast units by any other means, submit a diagram that sets out the profile of the completed member(s) in relation to the profile specified on the Drawings.
8c13f450-e81d-53df-9d66-f2b55b60fab2 | note | Frequency / Process Held - Once / Prior to landing next span
26a9dbc3-2047-5a21-9f32-ff34622b058e | note | Inspection – ACPL - S
367fba12-dd6a-5f69-8782-d28000b8cf23 | note | Inspection – Client - S
e87b72f5-d085-55f8-a33b-e9fa3f008e89 | note | Comments / Attachments / Records - Survey Report
| section | Review by Project Manager
| checkpoint-no-value | Review by Project Manager
191cfb82-b72f-5325-9375-9d9bafe2b3d9 | button | Any non-conformances? | YES, NO
b70bed44-4b6d-5ee3-8a5e-12cb5be33417 | textbox | No's:
86c3e6b6-f99f-5b97-8169-ae0fe58d09c9 | button | Closed Out | YES, NO
f99ace6a-d047-5bbf-83dc-1e34b4ce0d2d | button | All work has been satisfactorily completed. | YES, NO
2d61d94b-33b9-5d7d-be22-534a97884f49 | textbox | Name:
| signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
688396e6-082c-5820-ac23-ce8dde6a010d | textbox | Lot Verified By:
88e1eed9-a73e-526c-9770-858f606d706c | textbox | Lot Closed Date:
13a5fbe4-3357-5a9f-bfe2-ebda0d8c3adf | button | Submitted to Client | Yes, No, N/A
155a2f75-2cab-5875-9b5a-ed4dd711586c | button | Reviewed by Client | Yes, No, N/A
c4515e31-dd12-5a37-9af5-1f77a7e738c7 | textbox | Submission Comments:
| section-nested-checklists | NCR
a3f21b9c-6052-40cc-866a-3f41b682f8d1 | checklist | ITP-B5.P - Parapet Installation Preliminary Works Rev 1 | itp | ITP-B5.P - Parapet Installation Preliminary Works Rev 1 | cbe28276-eb81-40c6-80a6-28aa78f0303b
| section | Lot Information
| checkpoint | Lot Information complete
ce70461f-8399-4117-a04b-805367e24315 | textbox | Lot Opened On
f4e3290a-8a19-47dc-bc28-1811ecd63418 | textbox | Date of Works
9ea517be-711d-4dc7-b4d0-6e02057c909e | textbox | Lot Type
f7bb2f2e-4e3e-4e71-a68a-9411a7e3894c | textbox | Start Chainage
a7e17e99-8065-4f6e-8870-6a8578ceb69b | textbox | End Chainage
45553de4-cf0b-4d3f-af37-565fe1f58bf9 | textbox | Offset
b7051b9c-50dc-50a5-8e12-e847c17a27d3 | textbox | Control Line
02dee1ed-949c-4281-b140-cde5661e11a2 | section | 1. Prelims
bad3bdd9-c50f-446f-ab08-baba7c88a9dc | checkpoint | 1.1 - Safety Review
06b56e66-6392-59d2-b099-a850cd50bbcf | note | Requirements / Reference - Project Safety Plan
8c1f57cf-977e-5a92-9fe2-cc7d0d65fe55 | note | Acceptance Criteria - All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements completed and signed.
d4285541-e86c-5b2c-9851-a8ac81aacf9f | note | Frequency / Process Held - Before Commencement of Works
e6e06155-0862-5370-ac02-98e9ae08bbd9 | note | Inspection - ACPL - W
ad41e2bd-fef4-55bd-aa9b-ad07bc0c29de | note | Inspection - Client - S
ea611e8a-d73f-5ed8-b16c-da33495b2412 | note | Comments / Attachments / Records - Signed SWMS
ffb5587e-e04f-427a-8ca7-b280740d47dd | checkpoint | 1.2 - Environment
ce5148e1-2c23-5f54-8e66-5a0adbf60aa1 | note | Requirements / Reference - Project Environment Plan
6494dc7e-8125-593e-892d-d810214dd41a | note | Acceptance Criteria - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
08672fc1-3226-56c9-a54d-c3c53304b01d | note | Frequency / Process Held - Before Commencement of Works
5f7ac755-d7fa-553c-8bc4-73a159065302 | note | Inspection - ACPL - W
0ab74746-735f-5246-991f-2cb0ab49c268 | note | Inspection - Client - S
bae11ea1-0e1f-5f55-9797-e95375f4850f | note | Comments / Attachments / Records - SECP AQMP
5e9c8553-a6c4-4298-a4a2-d0a2d0be8f20 | section | 2. Certification of Temporary Works
523cb8a8-8a9c-4805-bbf7-b9a4767c9903 | checkpoint | 2.1 - Certification of Lifting Equipment and Methodology (Platform Certification)
d9d5030b-3311-50d1-af7d-c1322ec4f44f | note | Requirements / Reference - G1 Cl 26
46d0d852-ef85-54b9-97ae-e0c57317a6f6 | note | Acceptance Criteria - Details of the proposed lifting equipment and method together with certification including calculations, by a Chartered Professional Engineer with membership of Engineers Australia practising in the field of geotechnical engineering that under the proposed set up and site conditions, the equipment nominated will be used within its safe working capacities.
481286c5-e02d-5df2-9c2d-2488fa98d39d | note | Frequency / Process Held - Once / Before setting up of Crane(s)
f7207cf1-16bf-5529-a3a9-ee5bd9a35d98 | note | Inspection - ACPL - H
47f3fac5-d664-5711-ac19-4afa86ceec2e | note | Inspection - Client - H
dac1ea96-2f3c-5366-b235-c12f60de4920 | note | Comments / Attachments / Records - Third Party Geotechnical Certification
f0af46e3-b669-4a5b-8a9a-276f640fb2f6 | signoff | AUTHORITY HOLDPOINT
9a65d1dc-4450-4847-9c58-d49bcb100de7 | checkpoint | 2.2 - Certification of Erection Methods
c631dfc4-a405-576e-8aa0-834a7f54ba55 | note | Requirements / Reference - B153 Cl 4.2 G1 Cl 26
8347397f-7d30-5949-880d-94f5b7a3232a | note | Acceptance Criteria - A certificate from an Engineer, certifying the structural adequacy and compliance of the proposed method of erection (including all supporting and bracing measures) with the Specification and design requirements, and compliance of the falsework with the relevant Australian Standards. The certificate must be accompanied by any drawings necessary to clearly describe the proposed method of erection including detailed drawings of any supporting and bracing measures.
2b35b97f-74c7-574d-b26e-1b0cf31acb51 | note | Frequency / Process Held - Once / Prior to erection of pretensioned precast concrete members.
679525db-352a-5964-a3b6-b213eabcf1ba | note | Inspection - ACPL - H
7ab12a8e-3d3f-5a1b-88b8-df4851f82cba | note | Inspection - Client - H
c200fb63-a02d-5aad-969c-c23507365ba4 | note | Comments / Attachments / Records - Structural Engineer Certification
e8e139d6-f2c4-41d7-a5f4-c56ad9f77918 | signoff | AUTHORITY HOLDPOINT
2fc6a48f-a136-4962-8059-a9ab5fb3cb63 | section | 3. Materials AND Approvals
ef17903e-7d16-44bd-8d22-d33113942427 | checkpoint | 3.1 - Mix Design Submission
8c92cbee-a9fa-5f1e-9293-ebc3d0ffb638 | note | Requirements / Reference - B80 Cl 3.9
d96bdc6e-1718-5591-9ca7-a6a626c6f7e3 | note | Acceptance Criteria - Submit to the Principal the following: (a) (i) all details in Clause 3.9.3; or (ii) mix ID and concrete mix design of a nominated mix from the Register of TfNSW Concrete Mixes; and (b) a statement stating that the mix conforms to this Specification and is suitable for its intended use.
0cb5e3e0-a29a-5e2a-8f89-bb0eb3813806 | note | Frequency / Process Held - Once / 4-weeks prior to proposed date of use
62a659f8-769e-559d-9eae-e0cdb2506d75 | note | Inspection - ACPL - H
50fe2aae-19ff-5747-9ff7-f3d9d34839a0 | note | Inspection - Client - H
fab47851-aa67-5c1a-9a71-07af881fc304 | note | Comments / Attachments / Records - Mix Design
27794fcc-06c8-46fa-885e-7e541cebc76b | signoff | AUTHORITY HOLDPOINT
169757cc-7546-471f-8882-1473f0d3e098 | checkpoint | 3.2 - Concreting Personnel
d0e8b384-6071-5318-a27d-28bfdc9a9f9c | note | Requirements / Reference - B80 Cl 7.2
0ba3d141-bb6b-552f-9ab5-620b8c621fb4 | note | Acceptance Criteria - Submit to the Principal the names of the personnel who will be involved in bridgeworks concreting operations; which of these persons hold a TfNSW Bridgeworks Concreting Grey Card; and corresponding evidence of this.
232be9ac-17ea-5417-b2c4-3e29bbeca2bf | note | Frequency / Process Held - Once at least 2 weeks prior to the first concrete pour
2548f321-00f8-52e4-83b2-20182b0d4015 | note | Inspection - ACPL - H
dc8e1b21-a829-5733-8960-8114cfd1c014 | note | Inspection - Client - H
7a18a430-4644-5498-822f-b7b4358419e2 | note | Comments / Attachments / Records - B80 Grey Cards
95876150-0790-402a-a48b-8084bf3f0233 | signoff | AUTHORITY HOLDPOINT
55a70338-99f3-44d4-bb9e-e404a4cc9059 | checkpoint | 3.3 - Certification Prior to Concreting
4d8b01c8-30e3-5903-9734-d5aecae2e6f0 | note | Requirements / Reference - B80 Cl 7.5
39c58a64-7459-5374-b67a-de243401b18b | note | Acceptance Criteria - Submit to the Principal checklists for verifying conformity of the nominated concrete mix, formwork, reinforcement, embedments and other relevant details.
5b991b96-93d8-5611-b1e6-03ebf3dad678 | note | Frequency / Process Held - Once / At Least two working days prior to commencement of production
a3160915-e664-5e5a-89c7-fd589f9378e0 | note | Inspection - ACPL - H
cc9bbe5d-2055-5cd5-96ec-3343060e31ac | note | Inspection - Client - H
445ef298-b0f5-545d-b600-09f9352599a6 | note | Comments / Attachments / Records - Pre-pour checklist
f11b9c50-7d8c-4cd0-ae69-9194c0fb05ef | signoff | AUTHORITY HOLDPOINT
0af77de4-458b-4663-9581-d12d21a81e92 | checkpoint | 3.4 - Steel Procurement
0622eee8-767e-53cc-9e18-77d3c73baf3c | note | Requirements / Reference - B201 Cl 5.2
dcd7e18a-8256-5565-95fa-d6562d4773ab | note | Acceptance Criteria - Valid certification of the steel manufacturer for the production of steel conforming to the applicable standard issued by either a JAS-ANZ or IAF accredited body, submitted no later than 10 working days before the steel is ordered.
648d8a32-ac2f-569e-9208-cd8ebcd1e806 | note | Frequency / Process Held - Once / 10 working days prior to ordering of steel
e780b765-a6a9-595b-a285-3da04549dfdc | note | Inspection - ACPL - H
167963ef-9e57-593c-9a6b-989edc0a1fff | note | Inspection - Client - H
be2f5ec3-1d7d-588c-b95d-c593982fec6a | note | Comments / Attachments / Records - Steel Certificates
7a19a573-6e2c-4e8a-a4a0-2c28b3a40c1a | signoff | AUTHORITY HOLDPOINT
623f6d7a-87e5-4f4c-9c9a-329e8100878e | checkpoint | 3.5 - Fabrication Work
f27199f1-6717-54f7-b3bd-d5d47ed7c2a7 | note | Requirements / Reference - B201 Cl 6.1
40b35c88-57ae-5d28-9acd-7aae755ffba0 | note | Acceptance Criteria - Shop drawings conforming to the Design Drawings approved and certified by the Designer in accordance with Clause 4.6.2, and procedures as detailed in Clause D1 of Annexure B201/D, items (b) to (v),
631c0cce-1768-53d2-b88c-2dcdca519ad5 | note | Frequency / Process Held - Once / 10 working days prior to ordering of steel
8c991241-35c2-5267-8219-40549d0b94cd | note | Inspection - ACPL - H
d7f20a9c-51e7-5c3c-b19a-7677e89a7e55 | note | Inspection - Client - H
b6cdfd86-acec-582f-b65f-ee614fc027f4 | note | Comments / Attachments / Records - Certified Shop Drawings
63ef8463-e8ca-46b9-b135-500cbda7e615 | signoff | AUTHORITY HOLDPOINT
bedaf148-57c5-47ac-ae2b-9aee78c39cd0 | checkpoint | 3.6 - Commencement of Fabrication
7e35b99c-40ef-552e-8792-604df650790a | note | Requirements / Reference - B201 Cl 6.1
5d32033e-34b7-52a1-bd7e-7b71a8c8f6e5 | note | Acceptance Criteria - Notification to client of commencement of fabrication
63fb2617-bc0a-5de7-847f-8d13c27082ab | note | Frequency / Process Held - Once / 10 working days
d1fb3ed9-0ea1-59bf-b26d-7622d8c216fa | note | Inspection - ACPL - W
7156b5b5-cf50-587f-ac43-4c0bed39428d | note | Inspection - Client - W
22ffef24-7e3f-5cee-914d-3a37e11063ea | note | Comments / Attachments / Records - WP Submission
3bc4319b-ece2-41e7-93cc-6484fcfd7944 | checkpoint | 3.7 - Completion of fabrication
8f939eb9-775f-5676-9be0-7b57fe472845 | note | Requirements / Reference - B201 Cl 15
14b283b7-8c9c-593e-b3a6-33762846af8f | note | Acceptance Criteria - The Fabricator’s Data Report must be submitted within four weeks of completion of fabrication.
b39b650b-7c83-5c02-8262-9802da668b5e | note | Frequency / Process Held - Once / 4 weeks from the completion of the fabrication.
f4e44394-e65a-50fc-a185-ecea0b991f3a | note | Inspection - ACPL - H
e1a384a9-32a7-51bf-870e-a6daf26d01c5 | note | Inspection - Client - H
7679d20c-ba32-57ff-81a9-da04047b68fd | note | Comments / Attachments / Records - Fabricator’s Data Report
73517afd-c320-4891-b2eb-f891985bb656 | signoff | AUTHORITY HOLDPOINT
cfbecbdc-e0ca-4be4-8bd5-ed397676d2e3 | section | 4. Welding Procedures
88527fc9-c162-49d4-acfb-d7fccc9ea9fd | checkpoint | 4.1 - Commencement of Welding
745c73f2-4140-50bd-91cf-1220a192d32d | note | Requirements / Reference - B203 Cl 4.1
16a27681-04c8-509a-aa63-94cca7dab3e7 | note | Acceptance Criteria - Prior to the commencement of welding of steel reinforcement for the Works, submit the following:
6dfb56f6-6fce-52c6-8149-6d32a7607e3a | note | (a) welding personnel names, roles, qualifications and experience;
f280116e-4af3-51af-b099-4a2f11acb59c | note | (b) welding procedure specifications (WPS) for the required welding;
9afe8e3e-851c-5944-9b42-74f4a3b22dfa | note | (c) welding procedure qualification records (PQR or WPQR) for the applicable WPS;
03bf8c48-edeb-5cf2-ba53-b25aac01fbe1 | note | (d) proof of conformity of proposed welding consumables to this Specification.
00c74151-e319-5149-82da-2c6f6acbf412 | note | Frequency / Process Held - Once / At least 5 days prior to commencement of welding
c209c5d5-104e-55d2-ac72-36bfc4ad219f | note | Inspection - ACPL - H
d9943f13-0ea2-54a0-a745-20c8092f5013 | note | Inspection - Client - H
18f15100-36cc-5d5f-88be-fa23366df8b7 | note | Comments / Attachments / Records - Welding Procedure Specification
4851b7b2-3b9d-4119-a189-37f1a452fe54 | signoff | AUTHORITY HOLDPOINT
b5451a60-287f-4d34-be5b-cf8fc971b26e | checkpoint | 4.2 - Weld Test Piece
73d7ee58-cfa5-539f-bac1-486f7f842d0e | note | Requirements / Reference - B201 Cl 7.4.1.1
a7a7b985-ee29-5669-9757-51fd570f7c48 | note | Acceptance Criteria - Manufacture of weld procedure qualification test piece
fdb843c5-5c9b-59e7-a37e-a5b9c31c6410 | note | Frequency / Process Held - Once / At least 3 working days notice prior to welding and testing of test piece
9e499ece-aa75-5833-9c98-e9e89eaa22e2 | note | Inspection - ACPL - W
c99fa350-cd5c-5642-b3e4-69a6eae9d8e1 | note | Inspection - Client - W
692aae99-0913-537a-9fa0-5cf3f2449431 | note | Comments / Attachments / Records - Welding Procedure Qualification Record
6df555c0-3592-4a75-b72d-c623d152be0c | section | 5. Production of Members
625220f3-35f2-4d18-a872-bb0bc318b4a0 | checkpoint | 5.1 - Certification of First Member Produced
54adb6cf-5522-5414-af34-bb51f48d23e5 | note | Requirements / Reference - B115 Cl 4.3
0a5193f9-83f6-5bcd-88ef-0b04b1c3dfe7 | note | Acceptance Criteria - Submit to the Principal a diagram showing the actual dimensions achieved for the first member compared to the specified dimensions and tolerances, prior to any further member being cast in the mould. The diagram must be accompanied with a certificate stating that: “The member dimensions, as anticipated at the age of 28 days, will be as shown on the Drawings and will be within the tolerances specified in Specification TfNSW B115.”
0c00b7f2-70e1-5f4b-9e63-e9e975d35a38 | note | Frequency / Process Held - Once per parapet type / casting further members
49caaaf5-2453-52a6-983f-a9dea9856993 | note | Inspection - ACPL - S
e047906c-d11c-5285-9b66-23ea19bd62b2 | note | Inspection - Client - S
536a4c10-475c-5266-8c03-1cda4886ab40 | note | Comments / Attachments / Records - As-Built Diagram
c9a1f440-03fb-462b-ba03-ab516408e831 | checkpoint | 5.2 - Casting of Further Members
bce4df94-36dd-596d-beb7-6e9ea5de69d6 | note | Requirements / Reference - B115 Cl 4.3
73f300c2-ff2f-5570-a736-124eb2569b92 | note | Acceptance Criteria - If any dimensions of the first member anticipated at the age of 28 days do not conform to the specified tolerances, deal with the nonconformity in accordance with TfNSW Q, and the following Hold Point applies: A certificate with supporting checklists verifying that the formwork will produce members conforming to the tolerances specified in Clause 4.2.
cb7f5278-b204-5568-8ee7-526146f2ddb5 | note | Frequency / Process Held - Once if necessary / Casting of Further Members
fd71102b-828d-52a0-b60a-44d28670bf65 | note | Inspection - ACPL - H
213f36b9-beab-5934-9fe1-6e1886cfeae6 | note | Inspection - Client - H
471fa1e9-74ca-5dd9-bfbf-9cadd99d0e08 | note | Comments / Attachments / Records - Formwork Certificate
8a096637-45e7-4a29-9464-0b724c9b6454 | signoff | AUTHORITY HOLDPOINT
1dcc9957-94aa-4120-950b-092aa52124b8 | checkpoint | 5.3 - Erection of Formwork
06144422-d4f2-5f63-8e85-89491e0051fa | note | Requirements / Reference - B80 Cl 5.2
27cde9e0-a14a-500e-9bc0-1d00ca327ec8 | note | Acceptance Criteria - Certification must state that the design of the formwork and the formwork documentation conform to AS 3610.1 and this Specification. Where multiple systems are combined to create the formwork, the design certification must cover the full extent of formwork used, including any interfaces and any required bracing and stiffeners. Submit to the Principal your formwork documentation and Engineer's design certification in accordance with Clause 5.2.
9ac4a9e2-be96-566f-8bde-0ea5af207e3e | note | Frequency / Process Held - Once at least ten working days before commencement of erection of formwork / Erection of Formwork
3358d4bb-8c2b-53e3-a13b-2929daaef6c5 | note | Inspection - ACPL - H
1220be14-0bb4-59ba-be35-4429d9070487 | note | Inspection - Client - H
d790263f-9bbc-5873-b682-a98942574119 | note | Comments / Attachments / Records - Formwork Certificate
e3f5011b-d0d3-4805-9e40-8fa8efe285d8 | signoff | AUTHORITY HOLDPOINT
98f84a46-b722-428b-827c-4ab46d3d459d | section | 6. Handling, Transport and Storage of Members
0c8e506c-9ad9-4e84-9e35-5da970ce3b1c | checkpoint | 6.1 - Ground Supports
f9b92ba9-f361-5f2e-b2f4-1ca4cf903b8e | note | Requirements / Reference - B115 Cl 5.1.2
0d20a601-9d07-5d95-869d-d15ad95b3c6f | note | Acceptance Criteria - Temporary supports on the ground must be of a size appropriate to the weight of the supported members and the bearing capacity of the ground, so that excessive settlement will not occur. Supports on the ground must not be less than 200 mm wide and 150 mm thick. Level the ground and clear the space between member supports to prevent accidental support being provided other than at the temporary supports. The minimum clearance from the ground to the underside of supported members must be 100 mm.
d528b449-4976-5649-b251-e4ed7fadf713 | note | Frequency / Process Held - Once / Prior to storage of members on site
6be591ec-592d-53a1-b5ba-c0ef23f06df3 | note | Inspection - ACPL - S
91886127-6e15-515a-9e31-f246a1d06916 | note | Inspection - Client - S
e1f8391a-e385-5bdf-8d38-24e6381ef8f0 | note | Comments / Attachments / Records - Temporary Storage Design
35d2e8c2-7f73-47b2-a044-ac29b9071cf5 | checkpoint | 6.2 - Certification of Support or Stacking Arrangement
fc6f1d52-3ff3-52c2-9918-8cf4c8e568ff | note | Requirements / Reference - B115 Cl 5.4
5565e868-5c3a-5e17-8614-fef4ec0b0559 | note | Acceptance Criteria - Provide a certificate to the Principal prior to storing or stacking the members and any rearrangement of stacked members, stating that the proposed storing or stacking arrangement will not overstress or damage any member, and that the stored or stacked members will be stable.
11614442-a459-561c-8b56-eea1b9ebd040 | note | Frequency / Process Held - Once / Prior to storage of members on site
9503d6b1-c8c1-50b9-a130-0dde4dc9d3e2 | note | Inspection - ACPL - S
f477b5c3-cb81-5deb-902c-78e6d5f47c9f | note | Inspection - Client - S
de5e1891-cda9-591b-bd40-e86ad24bc2db | note | Comments / Attachments / Records - Temporary Storage Design
e8e701c2-3b11-4001-91c4-efc5ee6793d8 | checkpoint | 6.3 - Transport of Members
1cea3fe3-e47a-535d-aaf8-c8cdc5f93b46 | note | Requirements / Reference - B115 Cl 5.5
7a796f83-35fa-5bea-935e-f9c3cdfca4cb | note | Acceptance Criteria - Do not transport any member to the Site until it is at least seven days old and the concrete has reached the specified 28 day strength. Prior to transport, submit to the Principal a certificate from a Structural Engineer stating that the proposed methods of support and transport of the member will be stable and secure and will not induce excessive stresses into the member.
ccc56c54-0485-5802-bb68-f186e57daa53 | note | Frequency / Process Held - Once / Prior to Transport to site
826428f1-1310-52ae-835d-8a9c936e5d2c | note | Inspection - ACPL - S
9560bc4d-d9d9-536f-b61e-e8e2fb354b82 | note | Inspection - Client - S
b7144687-9704-5bfe-a827-df66c4b8abaa | note | Comments / Attachments / Records - Concrete Strength Results Certificate of Conformity
b78b2c96-53f3-4ca1-b978-4c869db59b27 | section | Review by Project Manager
85bb5495-c102-4178-8c00-e43eb227f96a | checkpoint-no-value | Review by Project Manager
a3edd5e8-bcc1-5d44-85ec-69abf4acd462 | button | Any non-conformances? | YES, NO
9a41b0e5-36df-583b-a426-12207409145c | textbox | No's:
bbb89e91-0f49-59b3-bd9d-01aa8bceb6a7 | button | Closed Out | YES, NO
c58a9ab1-efbf-528f-8415-1ebf482a4dff | button | All work has been satisfactorily completed. | YES, NO
fbca4f18-5494-5d4a-b145-2300cdb4a568 | textbox | Name:
ed3adc9b-b8ab-4a2a-b900-a75be40c8554 | signoff | Add signature
| section | Lot Verification
| checkpoint | Lot Verification complete
4a025bef-8fae-5fa8-9a43-c4d9d50c1e72 | textbox | Lot Verified By:
74d0c13d-51d5-5bc7-9ce3-992c551c197c | textbox | Lot Closed Date:
3adc8d9c-fb30-580a-b9e8-9c31630e4572 | button | Submitted to Client | Yes, No, N/A
86588580-365d-5a94-b5b3-8bc96762354d | button | Reviewed by Client | Yes, No, N/A
0a9551a3-baf8-5661-b49c-7b848b819e24 | textbox | Submission Comments:
| section-nested-checklists | NCR
| checklist | Project Startup Hold Point |  | Project Startup Hold Point | 1bbb3619-f0db-4d7b-8af8-9fa989fc7f02
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Project Startup Hold Point
13a2ceed-9142-5446-a1f0-eaa6b3e83750 | note | Attach Hold Point details and any relevant documents, photos, etc.
e7395725-5637-57e6-a068-6f2f726c5ca6 | note | Issue to Client for their approval and sign off.
671c7abf-93c4-5abf-b1d8-67759621f3e5 | textbox | Hold Point number:
32969f13-66ad-59da-9555-5643e62e231b | textbox | Title:
1cd104df-af16-524d-b306-6bf36352ee1d | textbox | Specification / Clause Reference (if applicable):
6726f3c4-49ae-5122-976d-4bc3da6f5d6a | textbox | Work Start Date:
| signoff | HOLD POINT
| checklist | Project Startup Witness Point |  | Project Startup Witness Point | 56268ce4-be16-447c-896d-89bbd5a6ee30
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Project Startup Witness Point
a36a25f8-cb02-5b92-9643-8f98d2e7570e | note | Attach Witness Point details and any relevant documents, photos, etc.
c153a9fd-d68c-50a8-9e1c-f39ad2e58589 | note | Issue to Client for their approval and sign off.
d6ac7acc-8e9b-5aff-ade1-b390b7b1fec5 | textbox | Witness Point number:
5751a172-08d8-55cc-bda2-61a722ab850a | textbox | Title:
6cc753e7-e86d-5aa0-8dba-4928813e11f6 | textbox | Specification / Clause Reference (if applicable):
2ba0f484-3027-5d7f-bd20-42acf90fdd35 | textbox | Work Start Date:
| signoff | Witness POINT
| checklist | Submission of Management Plan |  | Submission of Management Plan | 44e131df-390b-4073-a81a-44530ab29b0f
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Submission of Management Plan
9151bae5-daf0-5402-9bef-8c4bf483e28c | note | Attach Management Plan and any relevant documents, photos, etc.
db71e6bb-fdef-5704-bf48-b41a6e458bf0 | note | Issue to Client for their approval and sign off
be47e92d-1578-5c55-aed5-e275bb529905 | textbox | Management Plan:
c20c62b5-b2f2-5b31-a1e5-412bab6f85d8 | textbox | Specification / Clause Reference (if applicable)
| signoff | Management Plan
| checklist | SURVEY REQUEST |  | SURVEY REQUEST | 0e9776a9-5a28-4c3c-933d-58e49b916126
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Complete the survey request details, then send the form to Surveyors to reply to
96c9af7d-9c0d-5dca-ac29-2b1f88240712 | textbox | Request #
bebb9889-bb85-5c94-ac64-e8e70a3f2516 | textbox | Lot #
bd414157-ccad-5b71-af3d-7de3b353d87f | textbox | Lot Details
21b79743-dcd6-5ac3-b5e6-52db00e1e83f | textbox | Any additional info
| signoff | SURVEY REQUEST
| checklist | TEST REQUEST |  | TEST REQUEST | a2b49c6b-5453-4a93-aa71-09e9f06a4f6c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Complete the test request details, attach the Test Request form, then send this to the Testers to reply to
b753b199-053d-5df0-8fbd-f7afd78b4aac | textbox | Request #
2a73cc19-5eae-5f3a-9a29-6b2757afa913 | textbox | Lot #
dac89885-d9cf-5d45-b954-ea55984498d8 | textbox | Lot Details
5db6f6d3-c57f-5781-852e-671755c22a78 | textbox | Any additional info
| signoff | TEST REQUEST