## Sheet1
1.1 | Treatment selection confirmed | — | — | Client approved treatment selection and variations including membrane seal design | — | DR | H | Client approval signature | — | 1.1 - Treatment selection confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - — | Criteria Notes - Client approved treatment selection and variations including membrane seal design | Site Lead - — | CM - DR | Client Rep - H | Records CHAR(AMP) Remarks - Client approval signature | Evidence - — | 1.1 - Treatment selection confirmed | SAMI Green A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ | NZTA M1A Performance Grade Testing - PG64….. | Completed PG64E compliant | SAMI Australia |  |  |  |  | Standard A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ
1.2 | Method of Work Plan | — | Pre site works | RQP Approved | — | DR | H | Client approval signature | — | 1.2 - Method of Work Plan | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - Pre site works | Criteria Notes - RQP Approved | Site Lead - — | CM - DR | Client Rep - H | Records CHAR(AMP) Remarks - Client approval signature | Evidence - — | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings | Will be completed during production | COLAS NZ |  |  |  |  | Test - NZTA M1A Performance Grade Testing - PG64…..
1.3 | Asphalt JMF confirmed | M10, Mix design report submitted to AT and is an approved JMF by AT while bitumen type will be different | — | Design meets specification requirements | — | DR | H | For this project the mix design JMF is AT approved AC14 PG64V/E while a different bitumen is used being SAMI Green A20E but the same JMF for BC and PSD will be followed | — | 1.3 - Asphalt JMF confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria - M10, Mix design report submitted to AT and is an approved JMF by AT while bitumen type will be different | Frequency - — | Criteria Notes - Design meets specification requirements | Site Lead - — | CM - DR | Client Rep - H | Records CHAR(AMP) Remarks - For this project the mix design JMF is AT approved AC14 PG64V/E while a different bitumen is used being SAMI Green A20E but the same JMF for BC and PSD will be followed | Evidence - — | Frequency - — | Site Testing - Field Airvoids Measured by NDM | Nuclear Density Meter used onsite to measure airvoids during construction | During paving | COLAS NZ |  |  |  |  | Notes - Completed PG64E compliant
1.4 | Underground and surface utilities identified and accounted for in design | — | — | Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. | — | DR | W | Client to confirm ok to mill 60mm on Ha Cresc and 200mm on repair areas at trench location and Manakau Quarry | — | 1.4 - Underground and surface utilities identified and accounted for in design | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - — | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Client to confirm ok to mill 60mm on Ha Cresc and 200mm on repair areas at trench location and Manakau Quarry | Evidence - — | Criteria Notes - Client approved treatment selection and variations including membrane seal design | Site Testing - Core Airvoids | NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint | After construction | COLAS NZ |  |  |  |  | Testing Provider - SAMI Australia
1.5 | Asphalt thickness check | Design, finished subbase levels with tolerances and kerb height will result in minimum LCV asphalt thickness to be achieved? | Pre site works | Agree with client minimum and average asphalt thickness to be achieved together with agreement on resulting asphalt volumes | — | W | W | Note that often the calculated and priced asphalt quantity is based on the specified thickness and area and this approach assumes the specified asphalt thickness is an average and due to subbase unevenness its expected the resulting asphalt thickness will be 5mm less in some areas and some cores less than the required minimum thickness in NZTA M10 thus upfront agreement in needed with client on targeted average asphalt thickness with allowable tolerances and resulting asphalt volume. | Meeting notes | 1.5 - Asphalt thickness check | Applicable Standard CHAR(AMP) Acceptance Criteria - Design, finished subbase levels with tolerances and kerb height will result in minimum LCV asphalt thickness to be achieved? | Frequency - Pre site works | Criteria Notes - Agree with client minimum and average asphalt thickness to be achieved together with agreement on resulting asphalt volumes | Site Lead - — | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Note that often the calculated and priced asphalt quantity is based on the specified thickness and area and this approach assumes the specified asphalt thickness is an average and due to subbase unevenness its expected the resulting asphalt thickness will be 5mm less in some areas and some cores less than the required minimum thickness in NZTA M10 thus upfront agreement in needed with client on targeted average asphalt thickness with allowable tolerances and resulting asphalt volume. | Evidence - Meeting notes | Site Lead - — | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | Performance Testing - Wheel Track Rutting as per NZTA M10 | After construction | Road Science |  |  |  |  | Asphalt Production Mix - AC14 PG64V/E A20E
1.6 | Pre-commencement/planning checklist completed | Neighbours and AT notified, TTM plan approved. Construction and testing planned both timing and resources plant and personnel. | — | This item is for planning the job to ensure everything is covered. And responsibilities allocated. | — | W | W | Pre-commencement Checklist and/or planning meeting notes | Email meeting notes - checklist and signed | 1.6 - Pre-commencement/planning checklist completed | Applicable Standard CHAR(AMP) Acceptance Criteria - Neighbours and AT notified, TTM plan approved. Construction and testing planned both timing and resources plant and personnel. | Frequency - — | Criteria Notes - This item is for planning the job to ensure everything is covered. And responsibilities allocated. | Site Lead - — | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Pre-commencement Checklist and/or planning meeting notes | Evidence - Email meeting notes - checklist and signed | CM - DR | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | Performance Testing - Resilient Modulus Test as per NZTA M10 | After construction | WSP |  |  |  |  | Test - NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings
2.1 | Milling Plans | Agreed by client and fits with traffic management plan | Every Day/Review as necessary | — | W | — | — | — | Photo of milling plan each day | 2.1 - Milling Plans | Applicable Standard CHAR(AMP) Acceptance Criteria - Agreed by client and fits with traffic management plan | Frequency - Every Day/Review as necessary | Criteria Notes - — | Site Lead - W | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Photo of milling plan each day | Client Rep - H | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | Mix Design Tensile Strength Ratio - TSR as per NZTA M10 | After construction | WSP |  |  |  |  | Notes - Will be completed during production
2.2 | Milled Surface Level | Spot checks with tape measure to achieve asphalt thickness requirements - only mill existing asphalt for 55mm | As necessary | Milling controlled on site - evidence when checking available space for asphalt prior to membrane seal | W | — | — | Milled depth to remove existing asphalt up to 55mm if less than 55mm road level raised with new asphalt to achieve 55mm | String across and photo and a check find spots that need to be corrected | 2.2 - Milled Surface Level | Applicable Standard CHAR(AMP) Acceptance Criteria - Spot checks with tape measure to achieve asphalt thickness requirements - only mill existing asphalt for 55mm | Frequency - As necessary | Criteria Notes - Milling controlled on site - evidence when checking available space for asphalt prior to membrane seal | Site Lead - W | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - Milled depth to remove existing asphalt up to 55mm if less than 55mm road level raised with new asphalt to achieve 55mm | Evidence - String across and photo and a check find spots that need to be corrected | Records CHAR(AMP) Remarks - Client approval signature | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain | After construction | Road Science |  |  |  |  | Testing Provider - COLAS NZ
2.3 | Deflection Testing | Not needed FWD testing has already been completed | — | FWD testing completed | — | DR | W | Height checked to ensure space for required membrane seal and asphalt | — | 2.3 - Deflection Testing | Applicable Standard CHAR(AMP) Acceptance Criteria - Not needed FWD testing has already been completed | Frequency - — | Criteria Notes - FWD testing completed | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Height checked to ensure space for required membrane seal and asphalt | Evidence - — | Evidence - — | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E | Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information | After construction | Road Science |  |  |  |  | Site Testing - Field Airvoids Measured by NDM
3.1 | Weather | The prior to and the day of sealing | Contractor visual on site and weather forecasts | Confirm the base temperature is greater than 4 degree Celsius | W | H | W |  | Screen shot of weather from phone - also action ok to proceed? | 3.1 - Weather | Applicable Standard CHAR(AMP) Acceptance Criteria - The prior to and the day of sealing | Frequency - Contractor visual on site and weather forecasts | Criteria Notes - Confirm the base temperature is greater than 4 degree Celsius | Site Lead - W | CM - H | Client Rep - W | Records CHAR(AMP) Remarks - | Evidence - Screen shot of weather from phone - also action ok to proceed? | 1.2 - Method of Work Plan | Existing Pavement Deflection Testing - Prior to Construction | Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | Completed on Ha Cres | Geosolve |  |  |  |  | Test - Nuclear Density Meter used onsite to measure airvoids during construction
3.2 | Surface suitable for sealing | 100% of area is tightly knitted | Areas compacted and free from loose surface | Surface should present a tight surface suitable for sealing | H | — | — | — | Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt | 3.2 - Surface suitable for sealing | Applicable Standard CHAR(AMP) Acceptance Criteria - 100% of area is tightly knitted | Frequency - Areas compacted and free from loose surface | Criteria Notes - Surface should present a tight surface suitable for sealing | Site Lead - H | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt | Applicable Standard CHAR(AMP) Acceptance Criteria - — | New Surfaced Pavement Deflection Testing - After Construction | Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | After construction | Geosolve |  |  |  |  | Notes - During paving
3.3 | Visual inspection of surface to be sealed | Tight surface suitable for sealing | Prior to sealing | Photos and fix areas observed that need fixing to comply | H | — | — | — | Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt | 3.3 - Visual inspection of surface to be sealed | Applicable Standard CHAR(AMP) Acceptance Criteria - Tight surface suitable for sealing | Frequency - Prior to sealing | Criteria Notes - Photos and fix areas observed that need fixing to comply | Site Lead - H | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt | Frequency - Pre site works | [8 empty] | Testing Provider - COLAS NZ
4.1 | Surface inspection | surface to be free of loose material prior to application of the membrane seal | Site Diary | Note covered in 3.3 above but this is an additional check on the day of sealing to ensure not damaged | H | — | — | — | Signed ITP and/or photos | 4.1 - Surface inspection | Applicable Standard CHAR(AMP) Acceptance Criteria - surface to be free of loose material prior to application of the membrane seal | Frequency - Site Diary | Criteria Notes - Note covered in 3.3 above but this is an additional check on the day of sealing to ensure not damaged | Site Lead - H | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Signed ITP and/or photos | Criteria Notes - RQP Approved | Standard A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ | NZTA M1A Performance Grade Testing - PG64….. | Completed PG64E compliant | SAMI Australia | Standard A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ | Test - NZTA M1A Performance Grade Testing - PG64….. | Notes - Completed PG64E compliant | Testing Provider - SAMI Australia | Site Testing - Core Airvoids
4.2 | Residual Bitumen Application Rate | 1.0l/m2 Residual Bitumen and Grade 6 or 1.4 l/m2 bitumen Grade 4 Chip | Spray Sheet | — | W | — | — | — | Photo from spray truck, bitumen usage, spray sheet | 4.2 - Residual Bitumen Application Rate | Applicable Standard CHAR(AMP) Acceptance Criteria - 1.0l/m2 Residual Bitumen and Grade 6 or 1.4 l/m2 bitumen Grade 4 Chip | Frequency - Spray Sheet | Criteria Notes - — | Site Lead - W | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Photo from spray truck, bitumen usage, spray sheet | Site Lead - — | Asphalt Production Mix - AC14 PG64V/E A20E | NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings | Will be completed during production | COLAS NZ | Asphalt Production Mix - AC14 PG64V/E A20E | Test - NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings | Notes - Will be completed during production | Testing Provider - COLAS NZ | Test - NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint
4.3 | Chip Application Rate | Visually ok no excess chip | Site diary/ Photos | — | W | — | — | — | Tonnage used versus area, dockets and rate calculated written in a spreadsheet | 4.3 - Chip Application Rate | Applicable Standard CHAR(AMP) Acceptance Criteria - Visually ok no excess chip | Frequency - Site diary/ Photos | Criteria Notes - — | Site Lead - W | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Tonnage used versus area, dockets and rate calculated written in a spreadsheet | CM - DR | Site Testing - Field Airvoids Measured by NDM | Nuclear Density Meter used onsite to measure airvoids during construction | During paving | COLAS NZ | Site Testing - Field Airvoids Measured by NDM | Test - Nuclear Density Meter used onsite to measure airvoids during construction | Notes - During paving | Testing Provider - COLAS NZ | Notes - After construction
5.1 | Sample Bitumen for PG 64 V/E testing | NZTA M1A - PG64V | Once per project per bitumen type (SAMI Green A20E and A20E) | This item is to sample SAMI Green A20E bitumen to conduct PG64V NZTA M1A testing to prove compliance after shipping and reheating. Note that original bitumen certificates sent when approving the JMF in item 1.0 | W | — | — | — | Sampling record signed | 5.1 - Sample Bitumen for PG 64 V/E testing | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M1A - PG64V | Frequency - Once per project per bitumen type (SAMI Green A20E and A20E) | Criteria Notes - This item is to sample SAMI Green A20E bitumen to conduct PG64V NZTA M1A testing to prove compliance after shipping and reheating. Note that original bitumen certificates sent when approving the JMF in item 1.0 | Site Lead - W | CM - — | Client Rep - — | Records CHAR(AMP) Remarks - — | Evidence - Sampling record signed | Client Rep - H | Site Testing - Core Airvoids | NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint | After construction | COLAS NZ | Site Testing - Core Airvoids | Test - NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint | Notes - After construction | Testing Provider - COLAS NZ | Testing Provider - COLAS NZ
6.1 | Binder content | IANZ accredited test cert | 1 per 200t at asphalt plant | NZTA M10: Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | — | DR | W | Sample from plant | — | 6.1 - Binder content | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert | Frequency - 1 per 200t at asphalt plant | Criteria Notes - NZTA M10: Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Sample from plant | Evidence - — | Records CHAR(AMP) Remarks - Client approval signature | Asphalt Production Mix - AC14 PG64V/E A20E | Performance Testing - Wheel Track Rutting as per NZTA M10 | Already completed from mix sampled on another site | Road Science | Asphalt Production Mix - AC14 PG64V/E A20E | Test - Performance Testing - Wheel Track Rutting as per NZTA M10 | Notes - Already completed from mix sampled on another site | Testing Provider - Road Science | Asphalt Production Mix - AC14 PG64V/E A20E
6.2 | Particle Size Distribution | IANZ accredited test cert | 1 per 200t at asphalt plant | NZTA M10: Refer to Table 5.3 | — | DR | W | Sample from plant | — | 6.2 - Particle Size Distribution | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert | Frequency - 1 per 200t at asphalt plant | Criteria Notes - NZTA M10: Refer to Table 5.3 | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Sample from plant | Evidence - — | Evidence - — | Asphalt Production Mix - AC14 PG64V/E A20E | Performance Testing - Resilient Modulus Test as per NZTA M10 | Already completed from mix sampled on another site | WSP | Asphalt Production Mix - AC14 PG64V/E A20E | Test - Performance Testing - Resilient Modulus Test as per NZTA M10 | Notes - Already completed from mix sampled on another site | Testing Provider - WSP | Test - Performance Testing - Wheel Track Rutting as per NZTA M10
6.3 | Max. Specific Gravity (MSG) of mix | IANZ accredited test cert | 1 per day or per 600t at asphalt plant | Report | — | DR | W | Sample from plant | — | 6.3 - Max. Specific Gravity (MSG) of mix | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert | Frequency - 1 per day or per 600t at asphalt plant | Criteria Notes - Report | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Sample from plant | Evidence - — | 1.3 - Asphalt JMF confirmed | Asphalt Production Mix - AC14 PG64V/E A20E | Mix Design Tensile Strength Ratio - TSR as per NZTA M10 | Already completed from mix sampled on another site | WSP | Asphalt Production Mix - AC14 PG64V/E A20E | Test - Mix Design Tensile Strength Ratio - TSR as per NZTA M10 | Notes - Already completed from mix sampled on another site | Testing Provider - WSP | Notes - Already completed from mix sampled on another site
6.4 | Air Voids at lab design compaction | IANZ accredited test cert | 1 per 600t at asphalt plant | NZTA M10: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | — | DR | W | Sample from plant | — | 6.4 - Air Voids at lab design compaction | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert | Frequency - 1 per 600t at asphalt plant | Criteria Notes - NZTA M10: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Sample from plant | Evidence - — | Applicable Standard CHAR(AMP) Acceptance Criteria - M10, Mix design report submitted to AT and is an approved JMF by AT while bitumen type will be different | Asphalt Production Mix - AC14 PG64V/E A20E | Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain | Already completed from mix sampled on another site | Road Science | Asphalt Production Mix - AC14 PG64V/E A20E | Test - Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain | Notes - Already completed from mix sampled on another site | Testing Provider - Road Science | Testing Provider - Road Science
6.5 | Sample and store for further performance testing | For research purposes comparing SAMI Green A20E with A20E | 20 boxes (10kg each) sampled on site per asphalt mix type | Modulus, Fatigue, Wheel Track Rutting to be tested after job completed for research purposes | — | DR | W | Sample on site and label | Sample record | 6.5 - Sample and store for further performance testing | Applicable Standard CHAR(AMP) Acceptance Criteria - For research purposes comparing SAMI Green A20E with A20E | Frequency - 20 boxes (10kg each) sampled on site per asphalt mix type | Criteria Notes - Modulus, Fatigue, Wheel Track Rutting to be tested after job completed for research purposes | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Sample on site and label | Evidence - Sample record | Frequency - — | Asphalt Production Mix - AC14 PG64V/E A20E | Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information | After construction | Road Science | Asphalt Production Mix - AC14 PG64V/E A20E | Test - Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information | Notes - After construction | Testing Provider - Road Science | Asphalt Production Mix - AC14 PG64V/E A20E
7.1 | Pre-AC Construction Site Checklist (week prior) | — | Prior to AC Construction on each site | No change from design report | W | W | — | Record any issues noted | Plan - | 7.1 - Pre-AC Construction Site Checklist (week prior) | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - Prior to AC Construction on each site | Criteria Notes - No change from design report | Site Lead - W | CM - W | Client Rep - — | Records CHAR(AMP) Remarks - Record any issues noted | Evidence - Plan - | Criteria Notes - Design meets specification requirements | Existing Pavement Deflection Testing - Prior to Construction | Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | Completed on Ha Cres | Geosolve | Existing Pavement Deflection Testing - Prior to Construction | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | Notes - Completed on Ha Cres | Testing Provider - Geosolve | Test - Performance Testing - Resilient Modulus Test as per NZTA M10
7.2 | Paving runs planned for joint locations not in wheel paths | — | Prior to AC Construction on each site |  | H | H | H | Pre-commencement checklist (i.e. pre-start reqs, by foreman/crew manager) | Joint location plan and meeting notes | 7.2 - Paving runs planned for joint locations not in wheel paths | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - Prior to AC Construction on each site | Criteria Notes - | Site Lead - H | CM - H | Client Rep - H | Records CHAR(AMP) Remarks - Pre-commencement checklist (i.e. pre-start reqs, by foreman/crew manager) | Evidence - Joint location plan and meeting notes | Site Lead - — | New Surfaced Pavement Deflection Testing - After Construction | Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | After construction | Geosolve | New Surfaced Pavement Deflection Testing - After Construction | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance | Notes - After construction | Testing Provider - Geosolve | Notes - Already completed from mix sampled on another site
7.3 | Space available to achieve specified asphalt thickness | Strings and survey | Prior to AC Construction on each site | Specified AC depth achievable | — | W | W | Site records | — | 7.3 - Space available to achieve specified asphalt thickness | Applicable Standard CHAR(AMP) Acceptance Criteria - Strings and survey | Frequency - Prior to AC Construction on each site | Criteria Notes - Specified AC depth achievable | Site Lead - — | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records | Evidence - — | CM - DR | [8 empty] | Testing Provider - WSP
7.4 | TAC / Membrane Seal | Visually ok to place asphalt | Each application pre paving | Membrane seal not damaged and ok to pave on | W | W | W | Site records | Sign off ITP membrane ok to proceed | 7.4 - TAC / Membrane Seal | Applicable Standard CHAR(AMP) Acceptance Criteria - Visually ok to place asphalt | Frequency - Each application pre paving | Criteria Notes - Membrane seal not damaged and ok to pave on | Site Lead - W | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records | Evidence - Sign off ITP membrane ok to proceed | Client Rep - H | [8 empty] | Asphalt Production Mix - AC14 PG64V/E A20E
7.5 | Asphalt temperature | M10 - 145 degrees minimum tipped into paver from truck | Every load on entry to site and again during compaction | Reference QMP for set temperatures | DR | W | W | Site records | — | 7.5 - Asphalt temperature | Applicable Standard CHAR(AMP) Acceptance Criteria - M10 - 145 degrees minimum tipped into paver from truck | Frequency - Every load on entry to site and again during compaction | Criteria Notes - Reference QMP for set temperatures | Site Lead - DR | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records | Evidence - — | Records CHAR(AMP) Remarks - For this project the mix design JMF is AT approved AC14 PG64V/E while a different bitumen is used being SAMI Green A20E but the same JMF for BC and PSD will be followed | [8 empty] | Test - Mix Design Tensile Strength Ratio - TSR as per NZTA M10
7.6 | Thickness Monitoring | Confirm Pavement height will allow thickness required to be achieved. | Calculated per load on field report. | Dipping on paver runs - Paving run check tonnage, width will calculate average thickness from field reports | DR | W | W | Site records paving run check | Premix field sheets tonnage vs area to determine average thickness | 7.6 - Thickness Monitoring | Applicable Standard CHAR(AMP) Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved. | Frequency - Calculated per load on field report. | Criteria Notes - Dipping on paver runs - Paving run check tonnage, width will calculate average thickness from field reports | Site Lead - DR | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records paving run check | Evidence - Premix field sheets tonnage vs area to determine average thickness | Evidence - — | [8 empty] | Notes - Already completed from mix sampled on another site
7.7 | Compaction | NZTA M10 section 9.9. NDM with correlated offset and prior days MTSG/Max Density, air voids 3 to 6% | Each paving run @ 20m centres and at core locations | Compact and change rollers and sequence until air voids achieved. At completion of compaction record NDM air voids and bulk density every 20 metres in centre of paving run | — | DR | W | Lab report on NDM measured on site | Suk after compaction 20m centre measurements to record in lab report and core locations | 7.7 - Compaction | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 section 9.9. NDM with correlated offset and prior days MTSG/Max Density, air voids 3 to 6% | Frequency - Each paving run @ 20m centres and at core locations | Criteria Notes - Compact and change rollers and sequence until air voids achieved. At completion of compaction record NDM air voids and bulk density every 20 metres in centre of paving run | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - Lab report on NDM measured on site | Evidence - Suk after compaction 20m centre measurements to record in lab report and core locations | 1.4 - Underground and surface utilities identified and accounted for in design | [8 empty] | Testing Provider - WSP
7.8 | Surface shape | Shape - NZTA M10 section 9.8. Levels - NZTA M10 section 10.2 | Post AC Construction on each site | Straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. | W | W | W | Site records and photos | Straight edge 3m - Suk and Greg - every 20m check and photos | 7.8 - Surface shape | Applicable Standard CHAR(AMP) Acceptance Criteria - Shape - NZTA M10 section 9.8. Levels - NZTA M10 section 10.2 | Frequency - Post AC Construction on each site | Criteria Notes - Straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. | Site Lead - W | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records and photos | Evidence - Straight edge 3m - Suk and Greg - every 20m check and photos | Applicable Standard CHAR(AMP) Acceptance Criteria - — | [8 empty] | Asphalt Production Mix - AC14 PG64V/E A20E
7.9 | Visual inspection minimal segregation, bleeding and joints nearly invisible | Visual inspection on surface and joint quality | Every 10 - 15 metres | Photos and fix areas observed that need fixing to comply | W | W | W | Site records | Photos as above and inspectiion Suk and Greg | 7.9 - Visual inspection minimal segregation, bleeding and joints nearly invisible | Applicable Standard CHAR(AMP) Acceptance Criteria - Visual inspection on surface and joint quality | Frequency - Every 10 - 15 metres | Criteria Notes - Photos and fix areas observed that need fixing to comply | Site Lead - W | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records | Evidence - Photos as above and inspectiion Suk and Greg | Frequency - — | [8 empty] | Test - Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain
7.1 | Road Marking Reinstated | Visual inspection on road marking location and quality | Every 40 metres | Photos and fix areas observed that need fixing to comply and paint and reflectivity complies with NZTA M7 specification | W | W | W | Site records | Melvin to check and take a few photos | 7.1 - Road Marking Reinstated | Applicable Standard CHAR(AMP) Acceptance Criteria - Visual inspection on road marking location and quality | Frequency - Every 40 metres | Criteria Notes - Photos and fix areas observed that need fixing to comply and paint and reflectivity complies with NZTA M7 specification | Site Lead - W | CM - W | Client Rep - W | Records CHAR(AMP) Remarks - Site records | Evidence - Melvin to check and take a few photos | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. | [8 empty] | Notes - Already completed from mix sampled on another site
8.1 | CORES | IANZ accredited test cert. NZTA M10 section 9.7 | — | Average Thickness > Specified Depth (Nominal) and thickness agreed as per item 1.5 | — | DR | W | — | — | 8.1 - CORES | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert. NZTA M10 section 9.7 | Frequency - — | Criteria Notes - Average Thickness > Specified Depth (Nominal) and thickness agreed as per item 1.5 | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - — | Evidence - — | Site Lead - — | [8 empty] | Testing Provider - Road Science
8.2 | Insitu density and air voids | NZTA M10 section 9.9 IANZ accredited test cert. | Per day 8 cores in mat and 3 near joints - Air voids mat LCV>2 and UCVCHAR(LESS)7; Joints LCV>2 and UCVCHAR(LESS)9 | NZTA M10 Air voids requirement | — | DR | W | — | — | 8.2 - Insitu density and air voids | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 section 9.9 IANZ accredited test cert. | Frequency - Per day 8 cores in mat and 3 near joints - Air voids mat LCV>2 and UCVCHAR(LESS)7; Joints LCV>2 and UCVCHAR(LESS)9 | Criteria Notes - NZTA M10 Air voids requirement | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - — | Evidence - — | CM - DR | [8 empty] | Asphalt Production Mix - AC14 PG64V/E A20E
8.3 | Falling Weigh Deflectometer Testing (FWD) | Conduct FWD tests at 20m intervals using Geosolve same testing as done prior | — | For research purposes | — | DR | W | — | — | 8.3 - Falling Weigh Deflectometer Testing (FWD) | Applicable Standard CHAR(AMP) Acceptance Criteria - Conduct FWD tests at 20m intervals using Geosolve same testing as done prior | Frequency - — | Criteria Notes - For research purposes | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - — | Evidence - — | Client Rep - W | [8 empty] | Test - Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information
8.4 | QA Handover and RAMM update | — | For each site on the project | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. RAMM update sheet | — | DR | W | — | — | 8.4 - QA Handover and RAMM update | Applicable Standard CHAR(AMP) Acceptance Criteria - — | Frequency - For each site on the project | Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. RAMM update sheet | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - — | Evidence - — | Records CHAR(AMP) Remarks - Client to confirm ok to mill 60mm on Ha Cresc and 200mm on repair areas at trench location and Manakau Quarry | [8 empty] | Notes - After construction
8.5 | Research Report | Final research report with performance test results comparing SAMI Green with Standard | — | For research purposes | — | DR | W | — | — | 8.5 - Research Report | Applicable Standard CHAR(AMP) Acceptance Criteria - Final research report with performance test results comparing SAMI Green with Standard | Frequency - — | Criteria Notes - For research purposes | Site Lead - — | CM - DR | Client Rep - W | Records CHAR(AMP) Remarks - — | Evidence - — | Evidence - — | [8 empty] | Testing Provider - Road Science
[19 empty] | 1.5 - Asphalt thickness check | [8 empty] | Existing Pavement Deflection Testing - Prior to Construction
[19 empty] | Applicable Standard CHAR(AMP) Acceptance Criteria - Design, finished subbase levels with tolerances and kerb height will result in minimum LCV asphalt thickness to be achieved? | [8 empty] | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
[19 empty] | Frequency - Pre site works | [8 empty] | Notes - Completed on Ha Cres
[19 empty] | Criteria Notes - Agree with client minimum and average asphalt thickness to be achieved together with agreement on resulting asphalt volumes | [8 empty] | Testing Provider - Geosolve
[19 empty] | Site Lead - — | [8 empty] | New Surfaced Pavement Deflection Testing - After Construction
[19 empty] | CM - W | [8 empty] | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
[19 empty] | Client Rep - W | [8 empty] | Notes - After construction
[19 empty] | Records CHAR(AMP) Remarks - Note that often the calculated and priced asphalt quantity is based on the specified thickness and area and this approach assumes the specified asphalt thickness is an average and due to subbase unevenness its expected the resulting asphalt thickness will be 5mm less in some areas and some cores less than the required minimum thickness in NZTA M10 thus upfront agreement in needed with client on targeted average asphalt thickness with allowable tolerances and resulting asphalt volume. | [8 empty] | Testing Provider - Geosolve
Evidence - Meeting notes
1.6 - Pre-commencement/planning checklist completed
Applicable Standard CHAR(AMP) Acceptance Criteria - Neighbours and AT notified, TTM plan approved. Construction and testing planned both timing and resources plant and personnel.
Frequency - —
Criteria Notes - This item is for planning the job to ensure everything is covered. And responsibilities allocated.
Site Lead - —
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Pre-commencement Checklist and/or planning meeting notes
Evidence - Email meeting notes - checklist and signed
2.1 - Milling Plans
Applicable Standard CHAR(AMP) Acceptance Criteria - Agreed by client and fits with traffic management plan
Frequency - Every Day/Review as necessary
Criteria Notes - —
Site Lead - W
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Photo of milling plan each day
2.2 - Milled Surface Level
Applicable Standard CHAR(AMP) Acceptance Criteria - Spot checks with tape measure to achieve asphalt thickness requirements - only mill existing asphalt for 55mm
Frequency - As necessary
Criteria Notes - Milling controlled on site - evidence when checking available space for asphalt prior to membrane seal
Site Lead - W
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - Milled depth to remove existing asphalt up to 55mm if less than 55mm road level raised with new asphalt to achieve 55mm
Evidence - String across and photo and a check find spots that need to be corrected
2.3 - Deflection Testing
Applicable Standard CHAR(AMP) Acceptance Criteria - Not needed FWD testing has already been completed
Frequency - —
Criteria Notes - FWD testing completed
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Height checked to ensure space for required membrane seal and asphalt
Evidence - —
3.1 - Weather
Applicable Standard CHAR(AMP) Acceptance Criteria - The prior to and the day of sealing
Frequency - Contractor visual on site and weather forecasts
Criteria Notes - Confirm the base temperature is greater than 4 degree Celsius
Site Lead - W
CM - H
Client Rep - W
Records CHAR(AMP) Remarks -
Evidence - Screen shot of weather from phone - also action ok to proceed?
3.2 - Surface suitable for sealing
Applicable Standard CHAR(AMP) Acceptance Criteria - 100% of area is tightly knitted
Frequency - Areas compacted and free from loose surface
Criteria Notes - Surface should present a tight surface suitable for sealing
Site Lead - H
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
3.3 - Visual inspection of surface to be sealed
Applicable Standard CHAR(AMP) Acceptance Criteria - Tight surface suitable for sealing
Frequency - Prior to sealing
Criteria Notes - Photos and fix areas observed that need fixing to comply
Site Lead - H
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
4.1 - Surface inspection
Applicable Standard CHAR(AMP) Acceptance Criteria - surface to be free of loose material prior to application of the membrane seal
Frequency - Site Diary
Criteria Notes - Note covered in 3.3 above but this is an additional check on the day of sealing to ensure not damaged
Site Lead - H
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Signed ITP and/or photos
4.2 - Residual Bitumen Application Rate
Applicable Standard CHAR(AMP) Acceptance Criteria - 1.0l/m2 Residual Bitumen and Grade 6 or 1.4 l/m2 bitumen Grade 4 Chip
Frequency - Spray Sheet
Criteria Notes - —
Site Lead - W
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Photo from spray truck, bitumen usage, spray sheet
4.3 - Chip Application Rate
Applicable Standard CHAR(AMP) Acceptance Criteria - Visually ok no excess chip
Frequency - Site diary/ Photos
Criteria Notes - —
Site Lead - W
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Tonnage used versus area, dockets and rate calculated written in a spreadsheet
5.1 - Sample Bitumen for PG 64 V/E testing
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M1A - PG64V
Frequency - Once per project per bitumen type (SAMI Green A20E and A20E)
Criteria Notes - This item is to sample SAMI Green A20E bitumen to conduct PG64V NZTA M1A testing to prove compliance after shipping and reheating. Note that original bitumen certificates sent when approving the JMF in item 1.0
Site Lead - W
CM - —
Client Rep - —
Records CHAR(AMP) Remarks - —
Evidence - Sampling record signed
6.1 - Binder content
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert
Frequency - 1 per 200t at asphalt plant
Criteria Notes - NZTA M10: Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Sample from plant
Evidence - —
6.2 - Particle Size Distribution
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert
Frequency - 1 per 200t at asphalt plant
Criteria Notes - NZTA M10: Refer to Table 5.3
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Sample from plant
Evidence - —
6.3 - Max. Specific Gravity (MSG) of mix
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert
Frequency - 1 per day or per 600t at asphalt plant
Criteria Notes - Report
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Sample from plant
Evidence - —
6.4 - Air Voids at lab design compaction
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert
Frequency - 1 per 600t at asphalt plant
Criteria Notes - NZTA M10: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Sample from plant
Evidence - —
6.5 - Sample and store for further performance testing
Applicable Standard CHAR(AMP) Acceptance Criteria - For research purposes comparing SAMI Green A20E with A20E
Frequency - 20 boxes (10kg each) sampled on site per asphalt mix type
Criteria Notes - Modulus, Fatigue, Wheel Track Rutting to be tested after job completed for research purposes
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Sample on site and label
Evidence - Sample record
7.1 - Pre-AC Construction Site Checklist (week prior)
Applicable Standard CHAR(AMP) Acceptance Criteria - —
Frequency - Prior to AC Construction on each site
Criteria Notes - No change from design report
Site Lead - W
CM - W
Client Rep - —
Records CHAR(AMP) Remarks - Record any issues noted
Evidence - Plan -
7.2 - Paving runs planned for joint locations not in wheel paths
Applicable Standard CHAR(AMP) Acceptance Criteria - —
Frequency - Prior to AC Construction on each site
Criteria Notes -
Site Lead - H
CM - H
Client Rep - H
Records CHAR(AMP) Remarks - Pre-commencement checklist (i.e. pre-start reqs, by foreman/crew manager)
Evidence - Joint location plan and meeting notes
7.3 - Space available to achieve specified asphalt thickness
Applicable Standard CHAR(AMP) Acceptance Criteria - Strings and survey
Frequency - Prior to AC Construction on each site
Criteria Notes - Specified AC depth achievable
Site Lead - —
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records
Evidence - —
7.4 - TAC / Membrane Seal
Applicable Standard CHAR(AMP) Acceptance Criteria - Visually ok to place asphalt
Frequency - Each application pre paving
Criteria Notes - Membrane seal not damaged and ok to pave on
Site Lead - W
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records
Evidence - Sign off ITP membrane ok to proceed
7.5 - Asphalt temperature
Applicable Standard CHAR(AMP) Acceptance Criteria - M10 - 145 degrees minimum tipped into paver from truck
Frequency - Every load on entry to site and again during compaction
Criteria Notes - Reference QMP for set temperatures
Site Lead - DR
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records
Evidence - —
7.6 - Thickness Monitoring
Applicable Standard CHAR(AMP) Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved.
Frequency - Calculated per load on field report.
Criteria Notes - Dipping on paver runs - Paving run check tonnage, width will calculate average thickness from field reports
Site Lead - DR
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records paving run check
Evidence - Premix field sheets tonnage vs area to determine average thickness
7.7 - Compaction
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 section 9.9. NDM with correlated offset and prior days MTSG/Max Density, air voids 3 to 6%
Frequency - Each paving run @ 20m centres and at core locations
Criteria Notes - Compact and change rollers and sequence until air voids achieved. At completion of compaction record NDM air voids and bulk density every 20 metres in centre of paving run
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - Lab report on NDM measured on site
Evidence - Suk after compaction 20m centre measurements to record in lab report and core locations
7.8 - Surface shape
Applicable Standard CHAR(AMP) Acceptance Criteria - Shape - NZTA M10 section 9.8. Levels - NZTA M10 section 10.2
Frequency - Post AC Construction on each site
Criteria Notes - Straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
Site Lead - W
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records and photos
Evidence - Straight edge 3m - Suk and Greg - every 20m check and photos
7.9 - Visual inspection minimal segregation, bleeding and joints nearly invisible
Applicable Standard CHAR(AMP) Acceptance Criteria - Visual inspection on surface and joint quality
Frequency - Every 10 - 15 metres
Criteria Notes - Photos and fix areas observed that need fixing to comply
Site Lead - W
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records
Evidence - Photos as above and inspectiion Suk and Greg
7.1 - Road Marking Reinstated
Applicable Standard CHAR(AMP) Acceptance Criteria - Visual inspection on road marking location and quality
Frequency - Every 40 metres
Criteria Notes - Photos and fix areas observed that need fixing to comply and paint and reflectivity complies with NZTA M7 specification
Site Lead - W
CM - W
Client Rep - W
Records CHAR(AMP) Remarks - Site records
Evidence - Melvin to check and take a few photos
8.1 - CORES
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert. NZTA M10 section 9.7
Frequency - —
Criteria Notes - Average Thickness > Specified Depth (Nominal) and thickness agreed as per item 1.5
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - —
Evidence - —
8.2 - Insitu density and air voids
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 section 9.9 IANZ accredited test cert.
Frequency - Per day 8 cores in mat and 3 near joints - Air voids mat LCV>2 and UCVCHAR(LESS)7; Joints LCV>2 and UCVCHAR(LESS)9
Criteria Notes - NZTA M10 Air voids requirement
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - —
Evidence - —
8.3 - Falling Weigh Deflectometer Testing (FWD)
Applicable Standard CHAR(AMP) Acceptance Criteria - Conduct FWD tests at 20m intervals using Geosolve same testing as done prior
Frequency - —
Criteria Notes - For research purposes
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - —
Evidence - —
8.4 - QA Handover and RAMM update
Applicable Standard CHAR(AMP) Acceptance Criteria - —
Frequency - For each site on the project
Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. RAMM update sheet
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - —
Evidence - —
8.5 - Research Report
Applicable Standard CHAR(AMP) Acceptance Criteria - Final research report with performance test results comparing SAMI Green with Standard
Frequency - —
Criteria Notes - For research purposes
Site Lead - —
CM - DR
Client Rep - W
Records CHAR(AMP) Remarks - —
Evidence - —