## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - MILL and FILL ASPHALT CONSTRUCTION | itp |  |  |  |  | ITP - MILL and FILL ASPHALT CONSTRUCTION
section | 2.0 Milling
checkpoint | 2.1 - Milling Plans
label | Applicable Standard & Acceptance Criteria - Agreed by client and fits with traffic management plan
label | Frequency - Every Day/Review as necessary
label | Site Lead - W
label | Evidence - Photo of milling plan each day
checkpoint | 2.2 - Milled Surface Level
label | Applicable Standard & Acceptance Criteria - Spot checks with tape measure to achieve asphalt thickness requirements - only mill existing asphalt for 55mm
label | Frequency - As necessary
label | Criteria Notes - Milling controlled on site - evidence when checking available space for asphalt prior to membrane seal
label | Site Lead - W
label | Evidence - String across and photo and a check find spots that need to be corrected
checkpoint | 2.3 - Deflection Testing
label | Applicable Standard & Acceptance Criteria - Not needed FWD testing has already been completed
label | Criteria Notes - FWD testing completed
label | CM - DR
label | Client Rep - W
section | 3.0 Presealing
checkpoint | 3.1 - Weather
label | Applicable Standard & Acceptance Criteria - The prior to and the day of sealing
label | Frequency - Contractor visual on site and weather forecasts
label | Criteria Notes - Confirm the base temperature is greater than 4 degree Celsius
label | Site Lead - W
label | CM - H
label | Client Rep - W
label | Evidence - Screen shot of weather from phone - also action ok to proceed?
holdpoint | HOLD POINT
checkpoint | 3.2 - Surface suitable for sealing
label | Applicable Standard & Acceptance Criteria - 100% of area is tightly knitted
label | Frequency - Areas compacted and free from loose surface
label | Criteria Notes - Surface should present a tight surface suitable for sealing
label | Site Lead - H
label | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
holdpoint | HOLD POINT
checkpoint | 3.3 - Visual inspection of surface to be sealed
label | Applicable Standard & Acceptance Criteria - Tight surface suitable for sealing
label | Frequency - Prior to sealing
label | Criteria Notes - Photos and fix areas observed that need fixing to comply
label | Site Lead - H
label | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
holdpoint | HOLD POINT
section | 4.0 Sealing
checkpoint | 4.1 - Surface inspection
label | Applicable Standard & Acceptance Criteria - surface to be free of loose material prior to application of the membrane seal
label | Frequency - Site Diary
label | Criteria Notes - Note covered in 3.3 above but this is an additional check on the day of sealing to ensure not damaged
label | Site Lead - H
label | Evidence - Signed ITP and/or photos
holdpoint | HOLD POINT
checkpoint | 4.2 - Residual Bitumen Application Rate
label | Applicable Standard & Acceptance Criteria - 1.0l/m2 Residual Bitumen and Grade 6 or 1.4 l/m2 bitumen Grade 4 Chip
label | Frequency - Spray Sheet
label | Site Lead - W
label | Evidence - Photo from spray truck, bitumen usage, spray sheet
checkpoint | 4.3 - Chip Application Rate
label | Applicable Standard & Acceptance Criteria - Visually ok no excess chip
label | Frequency - Site diary/ Photos
label | Site Lead - W
label | Evidence - Tonnage used versus area, dockets and rate calculated written in a spreadsheet
section | 7.0 Asphalt construction
checkpoint | 7.1 - Pre-AC Construction Site Checklist (week prior)
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - No change from design report
label | Site Lead - W
label | CM - W
label | Evidence - Plan -
checkpoint | 7.2 - Paving runs planned for joint locations not in wheel paths
label | Frequency - Prior to AC Construction on each site
label | Site Lead - H
label | CM - H
label | Client Rep - H
label | Evidence - Joint location plan and meeting notes
holdpoint | HOLD POINT
checkpoint | 7.3 - Space available to achieve specified asphalt thickness
label | Applicable Standard & Acceptance Criteria - Strings and survey
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - Specified AC depth achievable
label | CM - W
label | Client Rep - W
checkpoint | 7.4 - TAC / Membrane Seal
label | Applicable Standard & Acceptance Criteria - Visually ok to place asphalt
label | Frequency - Each application pre paving
label | Criteria Notes - Membrane seal not damaged and ok to pave on
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Evidence - Sign off ITP membrane ok to proceed
checkpoint | 7.5 - Asphalt temperature
label | Applicable Standard & Acceptance Criteria - M10 - 145 degrees minimum tipped into paver from truck
label | Frequency - Every load on entry to site and again during compaction
label | Criteria Notes - Reference QMP for set temperatures
label | Site Lead - DR
label | CM - W
label | Client Rep - W
checkpoint | 7.6 - Thickness Monitoring
label | Applicable Standard & Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved.
label | Frequency - Calculated per load on field report.
label | Criteria Notes - Dipping on paver runs - Paving run check tonnage, width will calculate average thickness from field reports
label | Site Lead - DR
label | CM - W
label | Client Rep - W
label | Evidence - Premix field sheets tonnage vs area to determine average thickness
checkpoint | 7.7 - Compaction
label | Applicable Standard & Acceptance Criteria - NZTA M10 section 9.9. NDM with correlated offset and prior days MTSG/Max Density, air voids 3 to 6%
label | Frequency - Each paving run @ 20m centres and at core locations
label | Criteria Notes - Compact and change rollers and sequence until air voids achieved. At completion of compaction record NDM air voids and bulk density every 20 metres in centre of paving run
label | CM - DR
label | Client Rep - W
label | Evidence - Suk after compaction 20m centre measurements to record in lab report and core locations
checkpoint | 7.8 - Surface shape
label | Applicable Standard & Acceptance Criteria - Shape - NZTA M10 section 9.8.
label | ○ Levels - NZTA M10 section 10.2
label | Frequency - Post AC Construction on each site
label | Criteria Notes - Straight edge can be used for checking the surface shape.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | ○ Level - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Evidence - Straight edge 3m - Suk and Greg - every 20m check and photos
checkpoint | 7.9 - Visual inspection minimal segregation, bleeding and joints nearly invisible
label | Applicable Standard & Acceptance Criteria - Visual inspection on surface and joint quality
label | Frequency - Every 10 - 15 metres
label | Criteria Notes - Photos and fix areas observed that need fixing to comply
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Evidence - Photos as above and inspectiion Suk and Greg
checkpoint | 7.10 - Road Marking Reinstated
label | Applicable Standard & Acceptance Criteria - Visual inspection on road marking location and quality
label | Frequency - Every 40 metres
label | Criteria Notes - Photos and fix areas observed that need fixing to comply and paint and reflectivity complies with NZTA M7 specification
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Evidence - Melvin to check and take a few photos
checkpoint | Quality Record Close Out:
textbox | Quality Manager Name:
date | Date:
signoff | Digital Signature
checklist | ITP - MILL and FILL THIN ASPHALT CONSTRUCTION | itp |  |  |  |  | ITP - MILL and FILL THIN ASPHALT CONSTRUCTION
section | 1.0 Pre-Commencement Activities
checkpoint | 1.1 - Treatment selection confirmed
label | Criteria Notes - Client approved treatment selection and variations including membrane seal design
label | CM - DR
label | Client Rep - H
label | Records & Remarks - Client approval signature
holdpoint | HOLD POINT
checkpoint | 1.2 - Method of Work Plan
label | Frequency - Pre site works
label | Criteria Notes - RQP Approved
label | CM - DR
label | Client Rep - H
label | Records & Remarks - Client approval signature
holdpoint | HOLD POINT
checkpoint | 1.3 - Asphalt JMF confirmed
label | Applicable Standard & Acceptance Criteria - M10, Mix design report submitted to AT and is an approved JMF by AT while bitumen type will be different
label | Criteria Notes - Design meets specification requirements
label | CM - DR
label | Client Rep - H
label | Records & Remarks - For this project the mix design JMF is AT approved AC14 PG64V/E while a different bitumen is used being SAMI Green A20E but the same JMF for BC and PSD will be followed
holdpoint | HOLD POINT
checkpoint | 1.4 - Underground and surface utilities identified and accounted for in design
label | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works.
label | ○ Service lid condition and levels confirmed suitable for proposed works.
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Client to confirm ok to mill 60mm on Ha Cresc and 200mm on repair areas at trench location and Manakau Quarry
checkpoint | 1.5 - Asphalt thickness check
label | Applicable Standard & Acceptance Criteria - Design, finished subbase levels with tolerances and kerb height will result in minimum LCV asphalt thickness to be achieved?
label | Frequency - Pre site works
label | Criteria Notes - Agree with client minimum and average asphalt thickness to be achieved together with agreement on resulting asphalt volumes
label | CM - W
label | Client Rep - W
label | Records & Remarks - Note that often the calculated and priced asphalt quantity is based on the specified thickness and area and this approach assumes the specified asphalt thickness is an average and due to subbase unevenness its expected the resulting asphalt thickness will be 5mm less in some areas and some cores less than the required minimum thickness in NZTA M10 thus upfront agreement in needed with client on targeted average asphalt thickness with allowable tolerances and resulting asphalt volume.
label | Evidence - Meeting notes
checkpoint | 1.6 - Pre-commencement/planning checklist completed
label | Applicable Standard & Acceptance Criteria - Neighbours and AT notified, TTM plan approved. Construction and testing planned both timing and resources plant and personnel.
label | Criteria Notes - This item is for planning the job to ensure everything is covered. And responsibilities allocated.
label | CM - W
label | Client Rep - W
label | Records & Remarks - Pre-commencement Checklist and/or planning meeting notes
label | Evidence - Email meeting notes - checklist and signed
section | 2.0 Milling
checkpoint | 2.1 - Milling Plans
label | Applicable Standard & Acceptance Criteria - Agreed by client and fits with traffic management plan
label | Frequency - Every Day/Review as necessary
label | Site Lead - W
label | Evidence - Photo of milling plan each day
checkpoint | 2.2 - Milled Surface Level
label | Applicable Standard & Acceptance Criteria - Spot checks with tape measure to achieve asphalt thickness requirements - only mill existing asphalt for 55mm
label | Frequency - As necessary
label | Criteria Notes - Milling controlled on site - evidence when checking available space for asphalt prior to membrane seal
label | Site Lead - W
label | Records & Remarks - Milled depth to remove existing asphalt up to 55mm if less than 55mm road level raised with new asphalt to achieve 55mm
label | Evidence - String across and photo and a check find spots that need to be corrected
checkpoint | 2.3 - Deflection Testing
label | Applicable Standard & Acceptance Criteria - Not needed FWD testing has already been completed
label | Criteria Notes - FWD testing completed
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Height checked to ensure space for required membrane seal and asphalt
section | 3.0 Presealing
checkpoint | 3.1 - Weather
label | Applicable Standard & Acceptance Criteria - The prior to and the day of sealing
label | Frequency - Contractor visual on site and weather forecasts
label | Criteria Notes - Confirm the base temperature is greater than 4 degree Celsius
label | Site Lead - W
label | CM - H
label | Client Rep - W
label | Records & Remarks -
label | Evidence - Screen shot of weather from phone - also action ok to proceed?
holdpoint | HOLD POINT
checkpoint | 3.2 - Surface suitable for sealing
label | Applicable Standard & Acceptance Criteria - 100% of area is tightly knitted
label | Frequency - Areas compacted and free from loose surface
label | Criteria Notes - Surface should present a tight surface suitable for sealing
label | Site Lead - H
label | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
holdpoint | HOLD POINT
checkpoint | 3.3 - Visual inspection of surface to be sealed
label | Applicable Standard & Acceptance Criteria - Tight surface suitable for sealing
label | Frequency - Prior to sealing
label | Criteria Notes - Photos and fix areas observed that need fixing to comply
label | Site Lead - H
label | Evidence - Every 20meters Suk and Greg - photos before sealing and after / before asphalt and again after asphalt
holdpoint | HOLD POINT
section | 4.0 Sealing
checkpoint | 4.1 - Surface inspection
label | Applicable Standard & Acceptance Criteria - surface to be free of loose material prior to application of the membrane seal
label | Frequency - Site Diary
label | Criteria Notes - Note covered in 3.3 above but this is an additional check on the day of sealing to ensure not damaged
label | Site Lead - H
label | Evidence - Signed ITP and/or photos
holdpoint | HOLD POINT
checkpoint | 4.2 - Residual Bitumen Application Rate
label | Applicable Standard & Acceptance Criteria - 1.0l/m2 Residual Bitumen and Grade 6 or 1.4 l/m2 bitumen Grade 4 Chip
label | Frequency - Spray Sheet
label | Site Lead - W
label | Evidence - Photo from spray truck, bitumen usage, spray sheet
checkpoint | 4.3 - Chip Application Rate
label | Applicable Standard & Acceptance Criteria - Visually ok no excess chip
label | Frequency - Site diary/ Photos
label | Site Lead - W
label | Evidence - Tonnage used versus area, dockets and rate calculated written in a spreadsheet
section | 5.0 Asphalt Bitumen
checkpoint | 5.1 - Sample Bitumen for PG 64 V/E testing
label | Applicable Standard & Acceptance Criteria - NZTA M1A - PG64V
label | Frequency - Once per project per bitumen type (SAMI Green A20E and A20E)
label | Criteria Notes - This item is to sample SAMI Green A20E bitumen to conduct PG64V NZTA M1A testing to prove compliance after shipping and reheating. Note that original bitumen certificates sent when approving the JMF in item 1.0
label | Site Lead - W
label | Evidence - Sampling record signed
section | 6.0 Asphalt Material Compliance Production at Asphalt Plant
checkpoint | 6.1 - Binder content
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert
label | Frequency - 1 per 200t at asphalt plant
label | Criteria Notes - NZTA M10:
label | ○ Individual Test Result: ± 0.5
label | ○ Mean of Three Test Results: ± 0.3
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Sample from plant
checkpoint | 6.2 - Particle Size Distribution
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert
label | Frequency - 1 per 200t at asphalt plant
label | Criteria Notes - NZTA M10: Refer to Table 5.3
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Sample from plant
checkpoint | 6.3 - Max. Specific Gravity (MSG) of mix
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert
label | Frequency - 1 per day or per 600t at asphalt plant
label | Criteria Notes - Report
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Sample from plant
checkpoint | 6.4 - Air Voids at lab design compaction
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert
label | Frequency - 1 per 600t at asphalt plant
label | Criteria Notes - NZTA M10:
label | ○ Individual Test Results: +2.0, -1.0
label | ○ Mean of Three Test Results: +1.2, -0.6
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Sample from plant
checkpoint | 6.5 - Sample and store for further performance testing
label | Applicable Standard & Acceptance Criteria - For research purposes comparing SAMI Green A20E with A20E
label | Frequency - 20 boxes (10kg each) sampled on site per asphalt mix type
label | Criteria Notes - Modulus, Fatigue, Wheel Track Rutting to be tested after job completed for research purposes
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Sample on site and label
label | Evidence - Sample record
section | 7.0 Asphalt construction
checkpoint | 7.1 - Pre-AC Construction Site Checklist (week prior)
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - No change from design report
label | Site Lead - W
label | CM - W
label | Records & Remarks - Record any issues noted
label | Evidence - Plan -
checkpoint | 7.2 - Paving runs planned for joint locations not in wheel paths
label | Frequency - Prior to AC Construction on each site
label | Site Lead - H
label | CM - H
label | Client Rep - H
label | Records & Remarks - Pre-commencement checklist (i.e. pre-start reqs, by foreman/crew manager)
label | Evidence - Joint location plan and meeting notes
holdpoint | HOLD POINT
checkpoint | 7.3 - Space available to achieve specified asphalt thickness
label | Applicable Standard & Acceptance Criteria - Strings and survey
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - Specified AC depth achievable
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records
checkpoint | 7.4 - TAC / Membrane Seal
label | Applicable Standard & Acceptance Criteria - Visually ok to place asphalt
label | Frequency - Each application pre paving
label | Criteria Notes - Membrane seal not damaged and ok to pave on
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records
label | Evidence - Sign off ITP membrane ok to proceed
checkpoint | 7.5 - Asphalt temperature
label | Applicable Standard & Acceptance Criteria - M10 - 145 degrees minimum tipped into paver from truck
label | Frequency - Every load on entry to site and again during compaction
label | Criteria Notes - Reference QMP for set temperatures
label | Site Lead - DR
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records
checkpoint | 7.6 - Thickness Monitoring
label | Applicable Standard & Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved.
label | Frequency - Calculated per load on field report.
label | Criteria Notes - Dipping on paver runs - Paving run check tonnage, width will calculate average thickness from field reports
label | Site Lead - DR
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records paving run check
label | Evidence - Premix field sheets tonnage vs area to determine average thickness
checkpoint | 7.7 - Compaction
label | Applicable Standard & Acceptance Criteria - NZTA M10 section 9.9. NDM with correlated offset and prior days MTSG/Max Density, air voids 3 to 6%
label | Frequency - Each paving run @ 20m centres and at core locations
label | Criteria Notes - Compact and change rollers and sequence until air voids achieved. At completion of compaction record NDM air voids and bulk density every 20 metres in centre of paving run
label | CM - DR
label | Client Rep - W
label | Records & Remarks - Lab report on NDM measured on site
label | Evidence - Suk after compaction 20m centre measurements to record in lab report and core locations
checkpoint | 7.8 - Surface shape
label | Applicable Standard & Acceptance Criteria - Shape - NZTA M10 section 9.8.
label | ○ Levels - NZTA M10 section 10.2
label | Frequency - Post AC Construction on each site
label | Criteria Notes - Straight edge can be used for checking the surface shape.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | ○ Level - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records and photos
label | Evidence - Straight edge 3m - Suk and Greg - every 20m check and photos
checkpoint | 7.9 - Visual inspection minimal segregation, bleeding and joints nearly invisible
label | Applicable Standard & Acceptance Criteria - Visual inspection on surface and joint quality
label | Frequency - Every 10 - 15 metres
label | Criteria Notes - Photos and fix areas observed that need fixing to comply
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records
label | Evidence - Photos as above and inspectiion Suk and Greg
checkpoint | 7.10 - Road Marking Reinstated
label | Applicable Standard & Acceptance Criteria - Visual inspection on road marking location and quality
label | Frequency - Every 40 metres
label | Criteria Notes - Photos and fix areas observed that need fixing to comply and paint and reflectivity complies with NZTA M7 specification
label | Site Lead - W
label | CM - W
label | Client Rep - W
label | Records & Remarks - Site records
label | Evidence - Melvin to check and take a few photos
section | 8.0 Post-Asphalt construction
checkpoint | 8.1 - CORES
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert.
label | ○ NZTA M10 section 9.7
label | Criteria Notes - Average Thickness > Specified Depth (Nominal) and thickness agreed as per item 1.5
label | CM - DR
label | Client Rep - W
checkpoint | 8.2 - Insitu density and air voids
label | Applicable Standard & Acceptance Criteria - NZTA M10 section 9.9
label | ○ IANZ accredited test cert.
label | Frequency - Per day 8 cores in mat and 3 near joints - Air voids mat LCV>2 and UCV<7; Joints LCV>2 and UCV<9
label | Criteria Notes - NZTA M10 Air voids requirement
label | CM - DR
label | Client Rep - W
checkpoint | 8.3 - Falling Weigh Deflectometer Testing (FWD)
label | Applicable Standard & Acceptance Criteria - Conduct FWD tests at 20m intervals using Geosolve same testing as done prior
label | Criteria Notes - For research purposes
label | CM - DR
label | Client Rep - W
checkpoint | 8.4 - QA Handover and RAMM update
label | Frequency - For each site on the project
label | Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | ○ RAMM update sheet
label | CM - DR
label | Client Rep - W
checkpoint | 8.5 - Research Report
label | Applicable Standard & Acceptance Criteria - Final research report with performance test results comparing SAMI Green with Standard
label | Criteria Notes - For research purposes
label | CM - DR
label | Client Rep - W
checkpoint | Quality Record Close Out:
textbox | Quality Manager Name:
date | Date:
signoff | Digital Signature
checklist | Testing for SAMI Green A20E Asphalt and Bitumen | [5 empty] | Testing for SAMI Green A20E Asphalt and Bitumen
section | Samples
checkpoint | SAMI Green A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ
label | Test - NZTA M1A Performance Grade Testing - PG64
label | Notes - Completed PG64E compliant
label | Testing Provider - SAMI Australia
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings
label | Notes - Will be completed during production
label | Testing Provider - COLAS NZ
checkpoint | Site Testing - Field Airvoids Measured by NDM
label | Test - Nuclear Density Meter used onsite to measure airvoids during construction
label | Notes - During paving
label | Testing Provider - COLAS NZ
checkpoint | Site Testing - Core Airvoids
label | Test - NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint
label | Notes - After construction
label | Testing Provider - COLAS NZ
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - Performance Testing - Wheel Track Rutting as per NZTA M10
label | Notes - After construction
label | Testing Provider - Road Science
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - Performance Testing - Resilient Modulus Test as per NZTA M10
label | Notes - After construction
label | Testing Provider - WSP
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - Mix Design Tensile Strength Ratio - TSR as per NZTA M10
label | Notes - After construction
label | Testing Provider - WSP
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain
label | Notes - After construction
label | Testing Provider - Road Science
checkpoint | Asphalt Production Mix - AC14 PG64V/E SAMI Green A20E
label | Test - Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information
label | Notes - After construction
label | Testing Provider - Road Science
checkpoint | Existing Pavement Deflection Testing - Prior to Construction
label | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
label | Notes - Completed on Ha Cres
label | Testing Provider - Geosolve
checkpoint | New Surfaced Pavement Deflection Testing - After Construction
label | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
label | Notes - After construction
label | Testing Provider - Geosolve
checklist | Testing for Standard A20E Asphalt and Bitumen | [5 empty] | Testing for Standard A20E Asphalt and Bitumen
section | Samples
checkpoint | Standard A20E - Modified Bitumen - immediately after blending by SAMI Australia prior to shipping to Colas NZ
label | Test - NZTA M1A Performance Grade Testing - PG64
label | Notes - Completed PG64E compliant
label | Testing Provider - SAMI Australia
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - NZTA M10 Testing Production Mix Lab Airvoids, TMSG and Bitumen Content and Gradings
label | Notes - Will be completed during production
label | Testing Provider - COLAS NZ
checkpoint | Site Testing - Field Airvoids Measured by NDM
label | Test - Nuclear Density Meter used onsite to measure airvoids during construction
label | Notes - During paving
label | Testing Provider - COLAS NZ
checkpoint | Site Testing - Core Airvoids
label | Test - NZTA M10 Core Airvoids - 8 on Mat and 3 on Joint
label | Notes - After construction
label | Testing Provider - COLAS NZ
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - Performance Testing - Wheel Track Rutting as per NZTA M10
label | Notes - Already completed from mix sampled on another site
label | Testing Provider - Road Science
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - Performance Testing - Resilient Modulus Test as per NZTA M10
label | Notes - Already completed from mix sampled on another site
label | Testing Provider - WSP
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - Mix Design Tensile Strength Ratio - TSR as per NZTA M10
label | Notes - Already completed from mix sampled on another site
label | Testing Provider - WSP
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - Performance Testing - Beam Fatigue Single Strain - ATM 274 - 200 micro-strain
label | Notes - Already completed from mix sampled on another site
label | Testing Provider - Road Science
checkpoint | Asphalt Production Mix - AC14 PG64V/E A20E
label | Test - Performance Testing - Beam Fatigue Full Set 18 Beams as per ATM 274 to obtain pavement design information
label | Notes - After construction
label | Testing Provider - Road Science
checkpoint | Existing Pavement Deflection Testing - Prior to Construction
label | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
label | Notes - Completed on Ha Cres
label | Testing Provider - Geosolve
checkpoint | New Surfaced Pavement Deflection Testing - After Construction
label | Test - Falling Weight Deflectometer Deflection Testing at 10m spacings to determine strains being exerted on asphalt mix to measure performance
label | Notes - After construction
label | Testing Provider - Geosolve