## Work Group
Similar ITP to be use in the below item grouping
SOP Number | Description
3711,3722,3725,3732,3741 | Stabilisation
3712 | FBS
3721, 3723, 3724, 3733, 3734, 3742 | Granular Overlay
3731 | Granular replacement (dig out)

## 3711_22_25_32_41 Stabilisat (hidden)
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | B | 0 - IFC | 1 - IFC | 2 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-08-12 | 2024-08-01 | 2024-11-24 | 2025-02-04
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-08-19 | 2024-09-02 | 2024-11-24 | 2025-02-04
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications: NZTA B/5: Specification for In-Situ Stabilisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Hansel Feliciano |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  | 2024-09-03 |  | 2025-02-04
[7 empty] | Issued by: Project Director |  | Chris Seath |  | 2024-09-03 |  | 2025-02-04
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve |  |  |  | IDC - RFT Schedule of Price | IDC specifications Frequency | Testing Type | Responsibility | Paid by: | Certification Type | Comments
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date
1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
1.01 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Crushing Resistance | H | 1 per 10,000 m3 | NZS4407:3.10 | < 10% passing 2.36mm sieve at 130kN | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.01 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Maximum Wet/Dry Strength | H | 1 per 10,000 m3 | NZS4407:3.10 & AS 1141.22 | — | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.02 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Weathering Quality Index | H | 1 per 10,000 m3 | NZS4407:3.11 | AA, AB, AC, BA, BB, CA | IANZ Report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.03 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Calfornia Bearing Ratio (CBR) | H | 1 per 10,000 m3 | NZS4402:4.1.3 NZS4407:3.15 | Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80% | IANZ Report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.04 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Quality of Fines, either PI or SE or CI | H | 1 per 1,000 m3 | NZS4407:3.4 - PI NZS4407:3.5 - CI | PI ≤ 5 CI ≤ 3 | IANZ Report | Contractor | NZTA M04: 2024 AP40 - Class 2 PI and CI applies | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.05 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Broken Faces Content | H | 1 per 1,000 m3 | NZS4407:3.14 | ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | IANZ Report | Contractor | Waived if aggregate is from crushed hard rock quarry | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.06 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
1.07 | Optimisation of Stabilising Agent(s) | Blend Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading. | Report using IANZ Reports for AP40 and TP PSDs | Designer | Designer to advise if "average" blend is acceptable. | R | A | I | dd/mm/yy | — | — | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing.
1.08 | Optimisation of Stabilising Agent(s) | Indirect Tensile Strength, ITS | H | 1 Optimisation test per aggregate type | NZTA T/19: 2020 | Testing at 1mm/min: BSM Dry ITS: 175 kPa to 400 kPa BSM Soaked ITS: 150 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 210 kPa to 480 kPa BSM Soaked ITS: 180 kPa to 450 kPa | IANZ Report | Designer | Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | R | A | I | dd/mm/yy | — | — | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing.
1.09 | Optimisation of Stabilising Agent(s) | Unconfined Compressive Strength, UCS | H | 1 Optimisation test per aggregate type | CCNZ / NPTG / CETANZ Industry Guide | UCS limits set by the design engineeer | IANZ Report | Designer | Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | R | A | I | dd/mm/yy | — | — | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing.
1.1 | Optimisation of Stabilising Agent(s) | Modified Maximum Dry Density | H | Single Point DD vs WC during optimisation test | NZS 4402.4.1.3 | To determine target density | IANZ Report | Designer | Required before Stabilisation commences | R | A | I | dd/mm/yy | — | — | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing.
2.0. BEFORE CEMENT STABILISATION STARTS
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor | — |  | I | R | dd/mm/yy | 3741 | — | sITE sURVEY | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape | — | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement |  | A | R | dd/mm/yy | 3741 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter | — | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions |  | A | R | dd/mm/yy | 3741 | self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3741 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.05 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3741 | 5000 m2 TNZ B/5: Section 7.7.1 NZTA B/7: Section 8.1 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.06 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3741 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. |  | I | R | dd/mm/yy | 3721 | — | Site survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
3.0. CEMENT STABILISATION OPERATION
3.01 | Stabilising Agents | Lime | M | Per Batch | TNZ M/15 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711 |  | Material Testing | Subcontractor (Physical Works) | Subcontractor | Supplier Certificate (Quality assurance testing) | Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
3.02 |  | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711 |  | Material Testing | Subcontractor (Physical Works) | Subcontractor
3.03 |  | Bitumen (130/150) | M | Per Batch | M/1 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711
3.03 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: Cement - 5°C, Lime - 10°C, Cement/Lime - 10°C | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.04 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed < 25 km/hr | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.05 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.06 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.07 | Spreading of powdered stabilising agent (Cement / Lime) | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.08 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711 |  | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.09 |  | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | Record usage from PCU at the end of each run | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711 |  | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.1 |  | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy | 3711 |  | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.08 | Injection & Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.09 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3711 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion.
3.1 | Cement/Lime Stabilisation material | Stabilised material strength - ITS | M | 3 soaked ITS + 3 dry ITS per Lot or when the material changes | NZTA T/19N: 2020 | Testing at 1mm/min: BSM Dry ITS: 150 kPa to 350 kPa BSM Soaked ITS: 100 kPa to 300 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 420 kPa BSM Soaked ITS: 120 kPa to 360 kPa | IANZ Report | Stabilising Contractor | ITS briquettes to be produced on site if travel time to lab > 30 minutes. | I | A | R | dd/mm/yy |  |  | Design Testing | Designer (Professional Services) | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing.
3.11 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3711 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.12 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3711 | 5000 m2 TNZ B/5: Section 7.7.1 NZTA B/7: Section 8.1 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.13 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.14 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 | — | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3711 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.15 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | I | A | R | dd/mm/yy | 3711 | ≤ 60% (Table 10: 3710 sub-base compliance amendments) | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.0. Testing and Sgnoff
4.01 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor | — |  | A | R | dd/mm/yy | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.02 | Finished Pavement | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor | — |  | A | R | dd/mm/yy | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.03 | Finished Pavement | Surface Shape | H | every 20m | Measurement | < 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory |  | A | R | dd/mm/yy | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.04 | Finished Pavement | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection |  | A | R | dd/mm/yy | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.05 | Finished Pavement | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor | — |  | A | R |  | 3711 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.06 | Pavement Layer Signoff | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineers Representative |  |  |  |  | dd/mm/yy |  |  | Final Signoff | Designer (Professional services) | Subcontractor | Engineer sign off record | In this case, professional services contractor to manage this scope of testing.
1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal. 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 3712_FBS (hidden)
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | B | 0 - IFC | 1 - IFC | 2 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-08-12 | 2024-08-01 | 2024-11-24 | 2025-02-04
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-08-19 | 2024-09-02 | 2024-11-24 | 2025-02-04
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications: NZTA B/5: Specification for In-Situ Stabilisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Hansel Feliciano |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  | 2024-09-03 |  | 2025-02-04
[7 empty] | Issued by: Project Director |  | Chris Seath |  | 2024-09-03 |  | 2025-02-04
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve |  |  |  | IDC - RFT Schedule of Price | IDC specifications Frequency | Testing Type | Testing Responsibility | Paid By: | Certification Type | Comments
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date
2.0. BEFORE BITUMEN STABILISATION STARTS
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor | — |  | I | R | dd/mm/yy | 3741 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | Electronic survey files (Quality Control Testing) | —
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape | — | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement |  | A | R | dd/mm/yy | 3741 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter | — | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions |  | A | R | dd/mm/yy | 3741 | self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | IDM specs
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3741 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | IDM specs
2.05 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3741 | 5000 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
2.06 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3741 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. |  | I | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
3.0. BITUMEN STABILISATION OPERATION
3.01 | Stabilising Agents | Lime (if applicable - check PI delete otherwise) | M | Per Batch | TNZ M/15 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy |  |  | Material Testing | Subcontractor (Physical Works) | Subcontractor | Supplier Certificate (Quality assurance testing) | Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
3.02 |  | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy |  |  | Material Testing | Subcontractor (Physical Works) | Subcontractor
3.03 |  | Bitumen (130/150) | M | Per Batch | M/1 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy |  |  | Material Testing | Subcontractor (Physical Works) | Subcontractor
3.04 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.05 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed < 25 km/hr | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.06 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.07 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | B5
3.08 | Spreading of powdered stabilising agent (Cement / Lime) | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | B5
3.09 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.1 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | Record usage from PCU at the end of each run | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.11 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.12 | Injection & Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.13 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor | — |  | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.14 | FBS material | Stabilised material strength - ITS | M | 3 soaked ITS + 3 dry ITS per Lot or when the material changes | NZTA T/19N: 2020 | Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa | IANZ Report | Stabilising Contractor | ITS briquettes to be produced on site if travel time to lab > 30 minutes. | I | A | R | dd/mm/yy |  | 1 SET PER DAY | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing. | T19
3.15 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3712 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | IDM specs
3.16 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3712 | 5000 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
3.17 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
3.18 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 | — | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3712 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.19 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | I | A | R | dd/mm/yy | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
4.0. Testing and Sgnoff
4.01 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor | — |  | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.02 | Finished Pavement | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor | — |  | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.03 | Finished Pavement | Surface Shape | H | every 20m | Measurement | < 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory |  | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.04 | Finished Pavement | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection |  | A | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
4.05 | Finished Pavement | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor | — |  | A | R |  | 3712 | 1 Test per Site | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.06 | Pavement Layer Signoff | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineers Representative |  |  |  |  | dd/mm/yy |  |  | Final Signoff | Designer (Professional services) | Subcontractor | Engineer sign off record | In this case, professional services contractor to manage this scope of testing.
1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal. The cost of the supply of bitumen is covered in Item 3211. 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.
Note on P34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to know what is the ideal area can be done in 1 day

## 3721_23_24_33_34_42 Overlay (hidden)
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | B | 0 - IFC | 1 - IFC | 2 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-08-12 | 2024-08-01 | 2024-11-24 | 2025-02-04
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-08-19 | 2024-09-02 | 2024-11-24 | 2025-02-04
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications: NZTA B/5: Specification for In-Situ Stabilisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Hansel Feliciano |  | 2024-09-02 |  | 2025-02-04
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  | 2024-09-03 |  | 2025-02-04
[7 empty] | Issued by: Project Director |  | Chris Seath |  | 2024-09-03 |  | 2025-02-04
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve |  |  |  | IDC - RFT Schedule of Price | IDC specifications Frequency | Testing Type | Testing Responsibility | Paid By: | Certification Type | Comments
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date
2.0. BEFORE BITUMEN STABILISATION STARTS
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor | — | — | I | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | Electronic survey files (Quality Control Testing) | —
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape | — | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement | — | A | R | dd/mm/yy | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter | — | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions | — | A | R | dd/mm/yy | 3721 | self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe. | IDM specs
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3721 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | IDM specs
2.05 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3721 | 5000 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
2.06 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. | — | I | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
3.0. BITUMEN STABILISATION OPERATION
3.01 | Stabilising Agents | Lime (if applicable - check PI delete otherwise) | M | Per Batch | TNZ M/15 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor | — | — | I | R | dd/mm/yy | — | — | Material Testing | Subcontractor (Physical Works) | Subcontractor | Supplier Certificate (Quality assurance testing) | Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
3.02 | Stabilising Agents | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor | — | — | I | R | dd/mm/yy | — | — | Material Testing | Subcontractor (Physical Works) | Subcontractor | Supplier Certificate (Quality assurance testing) | Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
3.03 | Stabilising Agents | Bitumen (130/150) | M | Per Batch | M/1 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor | — | — | I | R | dd/mm/yy | — | — | Material Testing | Subcontractor (Physical Works) | Subcontractor | Supplier Certificate (Quality assurance testing) | Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
3.04 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Daily work Log | Stabilsing Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.05 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed < 25 km/hr | Daily work Log | Stabilsing Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.06 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.07 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | B5
3.08 | Spreading of powdered stabilising agent (Cement / Lime) | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion. | B5
3.09 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.1 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | water | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.11 | Injection of bituminous stabilising agent (FBS or BE) | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.12 | Injection & Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.13 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² for stabilisastion.
3.14 | FBS material | Stabilised material strength - ITS | M | 3 soaked ITS + 3 dry ITS per Lot or when the material changes | NZTA T/19N: 2020 | Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa | IANZ Report | Stabilising Contractor | ITS briquettes to be produced on site if travel time to lab > 30 minutes. | I | A | R | dd/mm/yy | — | 1 SET PER DAY | Design Testing | Designer | Professional Services | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | In this case, professional services contractor to manage this scope of testing. | T19 | FBS - Not applicable
3.15 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3712 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | IDM specs | FBS - Not applicable
3.16 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3712 | 5000 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5 | FBS - Not applicable
3.17 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5 | FBS - Not applicable
3.18 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 | — | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3712 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. |  | FBS - Not applicable
3.19 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | I | A | R | dd/mm/yy | 3712 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing. | B5 | FBS - Not applicable
4.0. Testing and Sgnoff
4.01 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor | — | — | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.02 | Finished Pavement | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor | — | — | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.03 | Finished Pavement | Surface Shape | H | every 20m | Measurement | < 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory | — | A | R | dd/mm/yy | 3712 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² for stabilisastion.
4.04 | Finished Pavement | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection | — | A | R | dd/mm/yy | 3712 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
4.05 | Finished Pavement | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor | — | — | A | R | — | 3712 | 1 Test per Site | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Allowance to be made under a separate line item for m² rate for site testing.
4.06 | Pavement Layer Signoff | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineers Representative | — | — | — | — | dd/mm/yy | — | — | Final Signoff | Designer (Professional services) | Subcontractor | Engineer sign off record | In this case, professional services contractor to manage this scope of testing.
2.0. CONSTRUCTION - UNBOUND OVERLAY
2.01 | Material Placement | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout. | I | Continuous monitoring | TNZ B/02: 2005 - 5.1 | — | Survey/ Level checks | Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | —
2.02 | Layer Thickness | Sub-base Layer Thickness | W | 1 test per 20m | TNZ B/02: 2005 - 7.3 | The average uncompacted thickness of subbase layer shall not be less than 2.5 times the maximum particle size of the aggregate | Survey/ Level checks | Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | —
2.03 | Layer Thickness | Basecourse Layer Thickness | W | 1 test per 20m | TNZ B/02: 2005 - 7.3 | The average uncompacted thickness of basecourse layer shall not be more than 200 mm. | Survey/ Level checks | Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | —
2.04 | Overlay Sites Plateau density Tests | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC. | H | 1 test per 5,000m2 | TNZ B/02: 2005 - 7.5 (b) 7.6 | — | MDD and Plateau Reports | Contractor | The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction as required in clause 7.6 at OWC and make the information available to the Engineer. It shall be the responsibility of the Contractor to achieve the specification requirements. | — | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.05 | Compaction | Degree of Compaction (DoC) - Subbase | H | Min 5 Tests per lot (1000m2 max - lot size) | TNZ B/02:2005 - 7.6 | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Contractor | — | I | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
— | Compaction | Clegg Hammer Test | H | Min 5 Tests per lot (1000m2 max - lot size) | ASTM D5874 | ≥30 CIV | — | — | — | — | — | — | — | 3721 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
— | Compaction | Degree of Compaction (DoC) - Base course | H | Min 5 Tests per lot (1000m2 max - lot size) | TNZ B/02:2005 - 7.6 | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Contractor | — | I | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.06 | Compaction | Clegg Hammer Test | H | Min 5 Tests per lot (1000m2 max - lot size) | ASTM D5874 | ≥50 CIV | IANZ Report | Contractor | — | I | A | R | dd/mm/yy | 3721 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.0. TESTING & SIGNOFF - UNBOUND OVERLAY
3.01 | Fiinished Pavement | Crossfall | H | every 20m | TNZ B/02: 2005 - 5.1 | ± 0.5% of specified crossfall measure 2m apart | Survey | Contractor | — | — | A | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.02 | Fiinished Pavement | Width | H | every 20m | TNZ B/02: 2005 - 5.1 | -20mm, +100mm | Survey | Contractor | — | — | A | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.03 | Fiinished Pavement | Surface Shape | H | every 20m | TNZ B/02: 2005 - 7.8 | < 10mm using 3m straight edge | Survey | Contractor | Only required if the visual inspection appears unsatisfactory | — | A | R | dd/mm/yy | 3721 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made under a separate line item for m² rate for site testing.
3.04 | Fiinished Pavement | Holding Water | H | Prior to Sealing | TNZ B/02: 2005 - 7.7 | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | Survey | Contractor | — | — | A | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made under a separate line item for m² rate for site testing.
3.05 | Fiinished Pavement | Running Course | H | Prior to Sealing | TNZ B/02: 2005 - 10.1 | If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. | Site notes | Contractor | During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface. | — | I | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made under a separate line item for m² rate for site testing.
3.06 | Fiinished Pavement | Surface Finish post sweeping | H | Prior to Sealing | TNZ B/02: 2005 - 7.8 | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | Photos | Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On Site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made under a separate line item for m² rate for site testing.
3.07 | Fiinished Pavement | Roughness | H | Prior to Sealing | TNZ B/02: 2005 - 7.7 | The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. | Test Certificate | Contractor | — | — | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing. |  | Pre-seal NASRAA
3.08 | Fiinished Pavement | Degree of Saturation (DOS) | H | Min 5 Tests per lot (1000m2 max - lot size) | TNZ B/02:2005 - 12 | ≤ 60% (for design traffic load > 5x10⁶ ESAs) ≤ 65% (for design traffic load < 5x10⁶ ESAs) | IANZ Report | Contractor | Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (ie it has not rained or additional watering has not been applied to the pavement). | I | A | R | dd/mm/yy | 3721 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing) | Allowance to be made under a separate line item for m² rate for site testing.
2.0. BEFORE CEMENT STABILISATION STARTS
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor | — | — | I | R | dd/mm/yy | 3741 | — | Site Survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape | — | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement | — | A | R | dd/mm/yy | 3741 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
2.03 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Visual check or Vibratory Roller's response meter | — | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions | — | A | R | dd/mm/yy | 3741 | self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | 3741 | NZTA T23 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing. |  | Rip & Remake - Not applicable
2.05 | Compaction | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | 3741 | 5000 m2 TNZ B/5: Section 7.7.1 NZTA B/7: Section 8.1 | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing. |  | Rip & Remake - Not applicable
2.06 | Compaction | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor | — | I | A | R | dd/mm/yy | 3741 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made under a separate line item for m² rate for site testing. |  | Rip & Remake - Not applicable
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 Minimum: -5mm Maximum: +15mm | Drawing Showing levels and crossfalls | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. | — | I | R | dd/mm/yy | 3721 | — | Site survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor | — | — | I | R | dd/mm/yy | 3721 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
1. The contract rate must fully compensate for all plant, labour, transport costs and materials required to complete the work including ripping the existing seal layers, hoeing into the existing pavement material (where required), and the installation of a First Coat Seal except for the cost of the supply of bitumen which is covered in Item 3211. 2.The contract rate shall fully compensate for ripping and hoeing the existing seal, completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.
Note on P34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to know what is the ideal area can be done in 1 day

## 3731_Granular replacement (hidden)
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/2 Activity: Dig-out in Tie In Locations |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve |  |  |  | IDC - RFT Schedule of Price | IDM specifications Frequency | Testing Type | Responsibility | Paid By: | Certification Type | Comments
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.01 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Crushing Resistance | H | 1 per 10,000 m3 | NZS4407:3.10 | < 10% passing 2.36mm sieve at 130kN | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.02 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Weathering Quality Index | H | 1 per 10,000 m3 | NZS4407:3.11 | AA, AB, AC, BA, BB, CA | IANZ Report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.03 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Calfornia Bearing Ratio (CBR) | H | 1 per 10,000 m3 | NZS4402:4.1.3 NZS4407:3.15 | Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80% | IANZ Report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.04 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Quality of Fines, either PI or SE or CI | H | 1 per 1,000 m3 | NZS4407:3.4 - PI NZS4407:3.5 - CI | PI ≤ 5 CI ≤ 3 | IANZ Report | Contractor | NZTA M04: 2024 AP40 - Class 2 PI and CI applies | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.05 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Broken Faces Content | H | 1 per 1,000 m3 | NZS4407:3.14 | ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | IANZ Report | Contractor | Waived if aggregate is from crushed hard rock quarry | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.06 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.07 | AP40/ AP65 Aggregates used for overlay Notes: H = Hold point up to approval M = Monitor during production R = Review | Maximum Dry Density (MDD) | R | 1 per 5,000 m2 | NZS 4402.4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ report | Contractor | — | A | I | R | dd/mm/yy | 3721 and 3731 | — | Material Testing | Aggregate Supplier (Quarry) | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate. This might not be necessary since they will be covered by the FBS material testing.
1.0 Dig-out in Tie In Locations
1.01 | Excavation | Excavate from finish road level (FRL)/existing road level at a depth specified in the design drawing | M | In pavement tie In locations | Measure / Photo | Site Engineers Approval | Checksheet | Contractor | — | A | I | R | dd/mm/yy | 3731 | — | Site survey | Subcontractor (Physical Works) | Subcontractor | DWG File and drawing pdf (Quality Control Testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
1.02 | Geotextile | Geotextile material to be installed. | M | For each pavement tie In locations | Photo | - The geotextile must be non-woven - The geotextile must comply with Strength Class C of TNZ F/7 - The geotextile must comply with Filtration Class 2 of TNZ F/7 with the EOS requirement for cohesive soils -Jointing of geotextiles must be overlapped. Unless otherwise specified, the minimum overlap must be 500mm. | Certificate of Compliance | Contractor | As per IDM technical specification |  |  |  |  | 3731 | Product Compliance will not apply for sites less than or equal to 150m² of geotextile. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Subcontractor to visually confirm correct activity installation with photos and provide product compliance as per IDM technical specifications.
1.02 | Geogrid | Install geogrid (prosolve 30x30mm or similar approved) | M | For each pavement tie In locations | Photo | Site Engineers Approval | Certificate of Compliance | Contractor | Not specified in the Digout Repairs sections. Instead, geotextile fabric is to be used. | A | I | R | dd/mm/yy | 3731 | Certificate of Compliance will not apply for sites of area less than or equal to 130 m² of geogrid. | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Contractor must provide a Certificate of Compliance that is no more than 12 months old certifying that the geogrid complies with the requirements.
1.03 | Sub-base Backfilling Compaction | 1st layer backfill at a depth specified in the design drawing, use AP65/Stockedpiled material approved by the Engineer | M | — | Measure / Photo | Site Engineers Approval | Checksheet | Contractor | — | A | I | R | dd/mm/yy | 3731 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance Testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
1.04 | Sub-base Backfilling Compaction | AP65/AP40 2nd layer backfill at a depth specified in the design drawing | M | 5 per 1,000m2 | NZS 4407.4.2.1/Clegg | Average DoC ≥ 95% Minimum DoC ≥ 92% or CIV 30 | IANZ Report | Contractor | — | A | I | R | dd/mm/yy | 3731 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality Control Testing | Allowance to be made when building up a m² /ton rate for unbound overlay.
1.05 | Sub-base Backfilling Compaction | AP40 3rd layer backfill at a depth specified in the design drawing | M | 5 per 1,000m2 | NZS 4407.4.2.1 | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Contractor | Final backfill layer and testing will be done in FBS ITP | A | I | R | dd/mm/yy | 3731 | — | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made when building up a m² /ton rate for unbound overlay. ITP note: Final backfill layer and testing will be done in FBS ITP
1.06 | Compaction Requirements | Clegg Impact Value | H | Every 100mm depth compacted | Measure | Clegg Impact Value (CIV) ≥ 30 if NDM is not available on site TNZ B02:2005 | Carried out by competant operator, record results on digout Checksheet | Contractor | — | A | I | R | dd/mm/yy | 3731 | Not mentioned in IDM specs | Site Testing | Subcontractor (Physical Works) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Control testing) | Allowance to be made when building up a m² /ton rate for unbound overlay.
1. The contract rate must fully compensate for all plant, labour, transport costs and materials required to complete the work including the installation of a First Coat Seal except for the cost of the supply of bitumen which is covered in Item 3211. The contract rate must include for the reinstatement of the pavement markings. 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.
[16 empty] | Design Testing | Aggregate Supplier (Quarry) | Professional Services | DWG File and drawing pdf (Quality Control Testing)
[16 empty] | Final Signoff | Designer | Quarry | Engineer sign off record
[16 empty] | Material Testing | Designer (Professional Services) | Subcontractor | IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
[16 empty] | On site Inspections | Subcontractor (Physical Works) |  | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
[16 empty] | Site survey |  |  | IANZ Accerdiated laboratory test results reports - (Quality Control testing)
[16 empty] | Site Testing |  |  | In house inspection record - Quality assurance Testing
In house inspection record - Quality Control Testing
Supplier Certificate (Quality assurance testing)

## 3761_Subsoil
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL | [9 empty] | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | [7 empty] | dd/mm/yy
|  |  |  | Project Name: Project Name |  |  | Reviewed by Construction Manager: |  | PM name | [7 empty] | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | [7 empty] | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA F/2, F/5 & Regional Infrastructure technical specifications (RITS) |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | [7 empty] | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | [7 empty] | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | [7 empty] | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | IDC - RFT Schedule of Price | IDM specifications Frequency | Testing Type | Responsibility | Paid by: | Certification Type | Comments | Checked by
R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action | Minimum Test Frequency | Inspection / Test method | [11 empty] | Designer / PTG | Eng. Rep / NZTA | Contractor | Date
|  |  | (Hold, Monitor, Witness) | (Lot = 1 day’s production or 1,500m2)
1.0. AGGREGATE TESTING
1.01 | Drainage aggregate | Crushing Resistance | H | 1 Test per material per source | NZS4407:3.10 | > 100KN | IANZ report | Contractor | — | 3761 | — | Material Testing | Supplier | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Material source property test, cost is included in the supply of material | A | I | R | dd/mm/yy
1.02 | Drainage aggregate | Particle size distribution | H | 1 Test per material per source | NZS4407:3.8.1 | as per IFC drawing | IANZ report | Contractor | — | 3761 | — | Material Testing | Supplier | Quarry | IANZ Accerdiated laboratory test results reports - (Quality Assurance testing) | Material source property test, cost is included in the supply of material | A | I | R | dd/mm/yy
1.03 | Pipe | Subsoil Pipe Material | H | each delivery | Dockets for each delivery | Compliance with TNZ F/2 | Delivery Docket | Contractor | — | 3761 | — | Material Testing | Supplier | Supplier | Data Sheet compliance with TNZ F/2 | Material source property test, cost is included in the supply of material | A | I | R | dd/mm/yy
2.0. CONSTUCTION
3.12 | Alignment | Subsoils to be placed behind the Kerb line or as instructed by Engineer | H | For each site where subsoil is required | — | Engineers Approval | — | Engineers Representative | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
3.13 | Excavation | Excavtion of Trench should be within tolerances. | M | For each site where subsoil is required | Visual / Photo | Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified | Checksheet | Contractor | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
3.14 | Trench Lining | A29 A14 or other approved Bidim to be placed and wrapped around Trench. | M | For each site where subsoil is required | Visual / Photo | Minimum Width 300mm. | Checksheet | Contractor | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
3.15 | Pipe laying | Pipe must have Min. 100mm of Cushion. Drainage 60:40 Material to be used. | M | For each site where subsoil is required | Visual / Photo | Minimum 100mm | Checksheet | Contractor | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
3.16 | Pipe laying | 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge | M | For each site where subsoil is required | Visual / Photo | As Per IFC Drawings | Checksheet | Contractor | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
3.17 | Backfill | Drainage 60:40 Material to be used. | M | For each site where subsoil is required | Visual / Photo | As Per IFC Drawings | Checksheet | Contractor | — | 3761 | — | On site Inspections | Subcontractor (Physical Works) | Subcontractor | In house inspection record - Quality assurance testing | Allowance to be made when building up a m² for stabilisastion. | A | I | R | dd/mm/yy
1. The costs associated with subsoil supply and installation are included in the quantities under the relevant items in Section 5210 under ‘Drainage Renewal’. 2. 5211 - Payment will be made for each lineal metre completed, as specified. This rate shall include all plant, labour and materials to construct the subsoil drains to the specification (including connection to the downstream structure or outlet), reinstatement of pavement and shoulder the provision of any environmental controls, the disposal of excavated material, removing any material from the pavement surface, reinstating all signs, marker posts and culvert markers
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released
by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed
by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## Sealing CE (hidden)
sealing2020
Inspection and Test Plan - Chipsealing
| Site Location: |  |  |  |  | Sealing Date:
Contract:
ITP Prepared By: |  |  | ITP Approved By:
Date: |  |  | Date:
Activity Description | Verification Activity | Methods or Reference | Frequency | Acceptance Criteria | Hold / Witness Point | Records | Responsible Person | Completed?
Chipseal Surfacing
HOLD POINT: A mandatory verification point beyond which work cannot proceed without approval by the Client/Engineer. The work cannot proceed until one of these parties is able to verify acceptance and releases the Hold by means of approval. |  |  |  | Witness Point: An identified point in the process where the designated authority, typically the Contract Management team, Client / Engineer or Consultant or 3rd Party Inspector may review, witness, inspect method or process of work. The activities, however, may proceed provided the activity is documented and evidence gathered.
Design
Treatment Selection | Physical / Site video/photographic record | Asset Team - Base Preservation | Annually Pre-reseal | Documented approval from at time of Tender -Team/Client | Mandatory HOLD POINT - Client Approval | Approved Seal Designs | Sealing Contract Manager / Engineer
Chipseal Design | Peer review by Authorised Seal Design Approver | Chipsealing in NZ | One per design prior to commencing onsite | Design meets requirements of P17 | Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval | Peer Reviewed Seal Designs | Sealing Contract Manager / Engineer
Materials Testing
Size (Grades 2-5) & Shape (Grades 2-4) | Lab Test | NZTA M/6 | 1/500m3 | Size (ald mm) G2 9.5-12.0 G3 7.5-10.0 G4 5.5-8.0 G5 Report | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer
Shape AGD/ALD Ratio G2,3,4 = 2.25 max G2,3,4 = min 98% with 2+ broken faces
Cleanliness (Grades 2-6) | Lab Test | NZTA M/6 | 1/500m3 | Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 & G6 Report only | Witness Point
Compatibility (Multi Layered seals) | Comparison Of Chip ALD | Chipsealing in New Zealand NZTA (NZTA 2005) | 11.5 |  | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer
7.2
Bitumen Distributor | IANZ Lab E/2 Results | Code of Compliance | Annual | Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%) | Mandatory HOLD POINT - Client - Engineer Witness | RNZ E2 Certificate | Sealing Contract Manager / Engineer
Emulsion/PME Testing | Lab Testing | Manufacture Specification | Per Emulsion/Bitumen Production Batch | Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02 | Witness Point | IANZ Lab Reports | Road Science
Surface Inspection
Surface Texture - Measurement | Sandcircle Measurement | NZTA T/3 | At time of Seal Inspection | Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Witness Point | Sandcircle Data | Sealing Contract Manager / Engineer
| ARRB Hawkeye or |  |  |  |  | Hawkeye Data
| NZTA HSD |  |  |  |  | High Speed Data
Pre Seal Survey | Downer Survey or MS Forms Pre Reseal Inspection | Downer Survey or MS Forms Pre Reseal Inspection | At time of Seal Inspection | Record & any noted issues / Client | Witness Point | Lucidity | Sealing Contract Manager / Engineer
Construction Compliance testing |  |  | 24 hours in advance of seal construction commencement | Confirmation from renewals manager all testing has met requirements | Hold Point | Email Confirmation | Sealing Contract Manager / Engineer
Seal Construction
Go/No Go Survey | Visual, Zeus, Iris | Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager | Witness Point | Lucidity | Supervisor / Foreperson / QA
Pavement Markings/RRPMs | Tagging of existing Pavement Markings, Removal of RRPMs | Pavement Marking Set Out Sheet, CBP | Prior to sealing on each site | All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required | Witness Point | None | Foreperson / QA
Road Furniture & Sumps protected | Visual Inspection | Crew Breifing Plan / Visual | Prior to sealing on each site | Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps. | Witness Point | None | Foreperson
Surface Condition/Temp | Physical / Visual Inspection | Visual / NZTA T/3 | Prior to sealing on each site | Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing | Witness Point | None | Foreperson / QA
Stockpiles | Visual Inspection | CBP | Each Stockpile | Correct Source, Grade and quantity. Uniquely Identified. | Witness Point | Sealing Data Docket | Foreperson
Spraying | Paper Start and Finish all runs | Spray Runs | All Runs | Mark out start / Finish | Witness Point |  | Sealing Contract Engineer / QA
Sealing | Longitudinal Joints out side of wheel tracks | Spray Runs | All Runs | Mark out lane lines by construction team | Witness Point |  | Sealing Contract Engineer / QA
Binder Application Rate | Tank Level dips prior to and after spray run | Dipstick | At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading | Quantities used to be within the desired tolerance of design Spray Rate | Mandatory HOLD POINT | Spray Sheets | QA
Chip Spread Rate | Visual | Crew Briefing Plan/Visual | On going whilst seal being constructed | Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan | Witness Point | Data Docket | QA/Foreperson
Removal of Surplus Chip | Physical / Visual | Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection | At conclusion of positive traffication within 48 hours | All sump and road furniture protection removed. Meets requirements of P/17 Table 2. | Witness Point | Post Seal Inspection | Sealing Contract Engineer / QA
Post Seal Construction
Post Seal Traffic Management | Physical / Visual | As per TMP | Full length and width of carriageway | Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours | Hold Point | Zeus or suitable recorded weather data | Sealing Contract Manager / Engineer
Post Seal Inspection | On Site Visual | Lucidity Post Seal Inpsection | After sealing is complete | Engineers requirements. Any defects identified, repairs programmed and costs estimated | Witness Point | Post Seal Inpsection | Sealing Contract Engineer / Manager / QA
Asbuilts and RAMM data | RAMM Update Sheet | RAMM Database | After sealing is complete | RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete. | Witness Point | As built information / RAMM Update Sheet | Sealing Contract Manager/ QA/QE
Quality Record Close Out: |  |  | Date:
(digital signature)
(name)

## DATA (hidden)
Two Coat Seal Aggregate Compatibility
Upper Limit |  | Lower Limit
x | y | x | y
0 | -0.44 | 0 | -1.42
1 | 0.27 | 1 | -0.84
2 | 0.98 | 2 | -0.26
3 | 1.69 | 3 | 0.32
4 | 2.4 | 4 | 0.9
5 | 3.11 | 5 | 1.48
6 | 3.82 | 6 | 2.06
7 | 4.53 | 7 | 2.64
8 | 5.24 | 8 | 3.22
9 | 5.95 | 9 | 3.8
10 | 6.66 | 10 | 4.38
11 | 7.37 | 11 | 4.96
12 | 8.08 | 12 | 5.54
13 | 8.79 | 13 | 6.12
14 | 9.5 | 14 | 6.7
15 | 10.21 | 15 | 7.28
16 | 10.92 | 16 | 7.86
Compatibility Point
| x | y
| 11.5 | 7.2