## Project Checklist Templates
Type | Name | Values | Prompting Name
checklist | ITP - Pavement Renewal - FBS | itp | ITP - Pavement Renewal - FBS
section | 2.0. BEFORE BITUMEN STABILISATION STARTS
checkpoint | 2.01 - Setout section
note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Survey
note | Acceptance Criteria - Document existing furniture
note | Record documents (QCP - Quality Control Portal) - Electronic survey files
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - Electronic survey files (Quality Control Testing)
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Use grader's machine control and inspect shape
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Visual check or Vibratory Roller's response meter
note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
note | Responsibility - Stabiliisng Contractor
note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - 5000 m2
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Survey
note | Acceptance Criteria - As per NZTA Z/16
note | ○ Minimum: -5mm
note | ○ Maximum: +15mm
note | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
note | Responsibility - Stabilising Contractor with Main Contractor
note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
note | — overlay aggregate quality / consistency
note | — moisture content
note | — any concerns with shape and tie in
note | — etc.
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Daily Report
note | Acceptance Criteria - Points covered in NZTA B/5
note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
section | 3.0. BITUMEN STABILISATION OPERATION
checkpoint | 3.04 - Weather conditions
note | Detail of Activity / Test - Material behind stabiliser
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading
note | Inspection / Test method - Measurement
note | Acceptance Criteria - Material after stabilisation:
note | ○ BE: > 20°C, FB: > 20°C
note | ○ and Ambient: >5 deg.C
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.05 - Weather conditions
note | Detail of Activity / Test - Wind
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - Wind speed < 25 km/hr
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.06 - Weather conditions
note | Detail of Activity / Test - Rain
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - every 400 m2
note | ○ every 150m for a 2.4m width
note | Inspection / Test method - Weigh mat or tray
note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going measurement by computer/load cells
note | Inspection / Test method - Measurement each run
note | Acceptance Criteria - ± 2.5% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Flow meter and operator's display readings
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
note | Inspection / Test method - Visual display reading
note | Acceptance Criteria - ± 5% of specified rate
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Record usage from PCU at the end of each run
note | Inspection / Test method - Record readings at the end of each run
note | Acceptance Criteria - ± 3% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each bitumen tanker load
note | Inspection / Test method - Dip bitumen tanker before and after
note | Acceptance Criteria - ± 2.5% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.12 - Injection & Mixing of Water
note | Detail of Activity / Test - In-situ Stabilisation process
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going visual assessment
note | Inspection / Test method - Visual and hand squeeze test
note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.13 - Depth of stabilisation
note | Detail of Activity / Test - Depth of stabilisation
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Every 200m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - +15mm / -5mm from specified depth
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.15 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - 5000 m2
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 3.17 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 98%
note | ○ Minimum DoC ≥ 95%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
note | Detail of Activity / Test - Clegg Impact Value
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1000m2
note | Acceptance Criteria - CIV ≥ 50
note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
note | Detail of Activity / Test - Degree of Saturation, DOS
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 5 per 1000m2
note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
note | Acceptance Criteria - aim for DOS ≤ 80%
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Report only
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
note | Detail of Activity / Test - Crossfall
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - ± 0.5% of specified crossfall measure
note | ○ 2m apart
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
note | Detail of Activity / Test - Stabilised width
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - -20mm, +100mm
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
note | Detail of Activity / Test - Surface Shape
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - < 10mm using 3m straight edge
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
note | Detail of Activity / Test - Surface Finish
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Per Lot
note | Inspection / Test method - Visual
note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
note | 2. Smaller aggregate held in place by fine material
note | 3. matrix does not displace under normal trafficking and/or sweeping
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
note | Detail of Activity / Test - Roughness
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Before Sealing
note | Inspection / Test method - TNZ TM 7003 v1
note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
note | Record documents (QCP - Quality Control Portal) - Test Certificate
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - 1 Test per Site
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint-no-value | 1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal. The cost of the supply of bitumen is covered in Item 3211.
checkpoint-no-value | 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - Granular Replacement | itp | ITP - Pavement Renewal - Granular Replacement
section | 1.0 AP40/ AP65 Aggregates used for overlay
checkpoint | 1.01 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Crushing Resistance
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4407:3.10
note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.02 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Weathering Quality Index
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4407:3.11
note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.03 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
note | Acceptance Criteria - Compacted using NZ Vibe Hammer
note | ○ 4-day soaked CBR ≥ 80%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.04 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
note | Acceptance Criteria - PI ≤ 5
note | ○ CI ≤ 3
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - NZTA M04: 2024
note | ○ AP40 - Class 2
note | ○ PI and CI applies
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.05 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Broken Faces Content
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.14
note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.06 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Particle Size Distribution
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.8.1
note | Acceptance Criteria - NZTA M04:2024-Class 2
note | ○ Class 2 in Table 12 for PSD
note | ○ Table 13 for shape control
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.07 - AP40/ AP65 Aggregates used for overlay
note | Notes:
note | H = Hold point up to approval
note | M = Monitor during production
note | R = Review
note | Detail of Activity / Test - Maximum Dry Density (MDD)
note | Action (Hold, Monitor, Witness) - R
note | Minimum Test Frequency - 1 per 5,000 m2
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid By - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
note | ○ This might not be necessary since they will be covered by the FBS material testing.
section | 1.0 Dig-out in Tie In Locations
checkpoint | 1.01 - Excavation
note | Detail of Activity / Test - Excavate from finish road level (FRL)/existing road level at a depth specified in the design drawing
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - In pavement tie In locations
note | Inspection / Test method - Measure / Photo
note | Acceptance Criteria - Site Engineers Approval
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3731
note | Testing Type - Site survey
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
checkpoint | 1.02 - Geotextile
note | Detail of Activity / Test - Geotextile material to be installed.
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each pavement tie In locations
note | Inspection / Test method - Photo
note | Acceptance Criteria - The geotextile must be non-woven
note | — The geotextile must comply with Strength Class C of TNZ F/7
note | — The geotextile must comply with Filtration Class 2 of TNZ F/7 with the EOS requirement for cohesive soils
note | — Jointing of geotextiles must be overlapped. Unless otherwise specified, the minimum overlap must be 500mm.
note | Record documents (QCP - Quality Control Portal) - Certificate of Compliance
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - As per IDM technical specification
note | IDC - RFT Schedule of Price - 3731
note | IDM specifications Frequency - Product Compliance will not apply for sites less than or equal to 150m² of geotextile.
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Subcontractor to visually confirm correct activity installation with photos and provide product compliance as per IDM technical specifications.
checkpoint | 1.02 - Geogrid
note | Detail of Activity / Test - Install geogrid (prosolve 30x30mm or similar approved)
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each pavement tie In locations
note | Inspection / Test method - Photo
note | Acceptance Criteria - Site Engineers Approval
note | Record documents (QCP - Quality Control Portal) - Certificate of Compliance
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Not specified in the Digout Repairs sections. Instead, geotextile fabric is to be used.
note | IDC - RFT Schedule of Price - 3731
note | IDM specifications Frequency - Certificate of Compliance will not apply for sites of area less than or equal to 130 m² of geogrid.
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Contractor must provide a Certificate of Compliance that is no more than 12 months old certifying that the geogrid complies with the requirements.
checkpoint | 1.03 - Sub-base Backfilling Compaction
note | Detail of Activity / Test - 1st layer backfill at a depth specified in the design drawing, use AP65/Stockedpiled material approved by the Engineer
note | Action (Hold, Monitor, Witness) - M
note | Inspection / Test method - Measure / Photo
note | Acceptance Criteria - Site Engineers Approval
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3731
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
checkpoint | 1.04 - Sub-base Backfilling Compaction
note | Detail of Activity / Test - AP65/AP40 2nd layer backfill at a depth specified in the design drawing
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1/Clegg
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92% or CIV 30
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3731
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
checkpoint | 1.05 - Sub-base Backfilling Compaction
note | Detail of Activity / Test - AP40 3rd layer backfill at a depth specified in the design drawing
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Final backfill layer and testing will be done in FBS ITP
note | IDC - RFT Schedule of Price - 3731
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
note | ○ ITP note: Final backfill layer and testing will be done in FBS ITP
checkpoint | 1.06 - Compaction Requirements
note | Detail of Activity / Test - Clegg Impact Value
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Every 100mm depth compacted
note | Inspection / Test method - Measure
note | Acceptance Criteria - Clegg Impact Value (CIV)
note | ○ ≥ 30 if NDM is not available on site
note | ○ TNZ B02:2005
note | Record documents (QCP - Quality Control Portal) - Carried out by competant operator, record results on digout Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3731
note | IDM specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint-no-value | 1. The contract rate must fully compensate for all plant, labour, transport costs and materials required to complete the work including the installation of a First Coat Seal except for the cost of the supply of bitumen which is covered in Item 3211. The contract rate must include for the reinstatement of the pavement markings.
checkpoint-no-value | 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - Overlay | itp | ITP - Pavement Renewal - Overlay
section | 2.0. BEFORE BITUMEN STABILISATION STARTS
checkpoint | 2.01 - Setout section
note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Survey
note | Acceptance Criteria - Document existing furniture
note | Record documents (QCP - Quality Control Portal) - Electronic survey files
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - Electronic survey files (Quality Control Testing)
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Use grader's machine control and inspect shape
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Visual check or Vibratory Roller's response meter
note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
note | Responsibility - Stabiliisng Contractor
note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² rate for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | IDC specifications Frequency - 5000 m2
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Survey
note | Acceptance Criteria - As per NZTA Z/16
note | ○ Minimum: -5mm
note | ○ Maximum: +15mm
note | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
note | Responsibility - Stabilising Contractor with Main Contractor
note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
note | — overlay aggregate quality / consistency
note | — moisture content
note | — any concerns with shape and tie in
note | — etc.
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Daily Report
note | Acceptance Criteria - Points covered in NZTA B/5
note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
section | 3.0. BITUMEN STABILISATION OPERATION
checkpoint | 3.01 - Stabilising Agents
note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Per Batch
note | Inspection / Test method - TNZ M/15
note | Acceptance Criteria - Conform to Specification
note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | Testing Type - Material Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - Supplier Certificate (Quality assurance testing)
note | Comments - Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.02 - Stabilising Agents
note | Detail of Activity / Test - Cement, GP
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Per Batch
note | Inspection / Test method - NZS 3122
note | Acceptance Criteria - Conform to Specification
note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | Testing Type - Material Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - Supplier Certificate (Quality assurance testing)
note | Comments - Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.03 - Stabilising Agents
note | Detail of Activity / Test - Bitumen (130/150)
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Per Batch
note | Inspection / Test method - M/1
note | Acceptance Criteria - Conform to Specification
note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | Testing Type - Material Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - Supplier Certificate (Quality assurance testing)
note | Comments - Certificate to be submitted by the subcontractor. Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.04 - Weather conditions
note | Detail of Activity / Test - Material behind stabiliser
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading
note | Inspection / Test method - Measurement
note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.05 - Weather conditions
note | Detail of Activity / Test - Wind
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - Wind speed < 25 km/hr
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.06 - Weather conditions
note | Detail of Activity / Test - Rain
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - every 400 m2 every 150m for a 2.4m width
note | Inspection / Test method - Weigh mat or tray
note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going measurement by computer/load cells
note | Inspection / Test method - Measurement each run
note | Acceptance Criteria - ± 2.5% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Flow meter and operator's display readings
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
note | Inspection / Test method - Visual display reading
note | Acceptance Criteria - ± 5% of specified rate
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - water
note | Inspection / Test method - Record readings at the end of each run
note | Acceptance Criteria - ± 3% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each bitumen tanker load
note | Inspection / Test method - Dip bitumen tanker before and after
note | Acceptance Criteria - ± 2.5% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.12 - Injection & Mixing of Water
note | Detail of Activity / Test - In-situ Stabilisation process
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going visual assessment
note | Inspection / Test method - Visual and hand squeeze test
note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.13 - Depth of stabilisation
note | Detail of Activity / Test - Depth of stabilisation
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Every 200m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - +15mm / -5mm from specified depth
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.14 - FBS material
note | Detail of Activity / Test - Stabilised material strength - ITS
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
note | Inspection / Test method - NZTA T/19N: 2020
note | Acceptance Criteria - Testing at 1mm/min:
note | ○ BSM Dry ITS: 150 kPa to 400 kPa
note | ○ BSM Soaked ITS: 120 kPa to 350 kPa
note | Testing at 50.8mm/min:
note | ○ BSM Dry ITS: 180 kPa to 450 kPa
note | ○ BSM Soaked ITS: 150 kPa to 420 kPa
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC specifications Frequency - 1 SET PER DAY
note | Testing Type - Design Testing
note | Testing Responsibility - Designer
note | Paid By - Professional Services
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - In this case, professional services contractor to manage this scope of testing.
checkpoint | 3.15 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - 5000 m2
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 3.17 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 98%
note | ○ Minimum DoC ≥ 95%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Part of Pre-Seal Inspection
note | Detail of Activity / Test - Clegg Impact Value
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1000m2
note | Acceptance Criteria - CIV ≥ 50
note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
note | Responsibility - Stabilising Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Part of Pre-Seal Inspection
note | Detail of Activity / Test - Degree of Saturation, DOS
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 5 per 1000m2
note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
note | Acceptance Criteria - aim for DOS ≤ 80%
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Report only
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
note | Detail of Activity / Test - Crossfall
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - ± 0.5% of specified crossfall measure
note | ○ 2m apart
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
note | Detail of Activity / Test - Stabilised width
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - -20mm, +100mm
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
note | Detail of Activity / Test - Surface Shape
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - < 10mm using 3m straight edge
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
note | Detail of Activity / Test - Surface Finish
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Per Lot
note | Inspection / Test method - Visual
note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
note | 2. Smaller aggregate held in place by fine material
note | 3. matrix does not displace under normal trafficking and/or sweeping
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Downer Contract Rep, Sealing team rep and subcontractor rep to do this inspection together.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
note | Detail of Activity / Test - Roughness
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Before Sealing
note | Inspection / Test method - TNZ TM 7003 v1
note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
note | Record documents (QCP - Quality Control Portal) - Test Certificate
note | Responsibility - Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3712
note | IDC specifications Frequency - 1 Test per Site
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.06 - Pavement Layer Signoff
note | Detail of Activity / Test - Assessment of all test results for conformity
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Each Lot
note | Inspection / Test method - Site Inspection
note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
note | Record documents (QCP - Quality Control Portal) - NCR
note | Responsibility - Engineers Representative
date | Date -
note | Testing Type - Final Signoff
note | Testing Responsibility - Designer (Professional services)
note | Paid By - Subcontractor
note | Certification Type - Engineer sign off record
note | Comments - In this case, professional services contractor to manage this scope of testing.
signoff | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION - UNBOUND OVERLAY
checkpoint | 2.01 - Material Placement
note | Detail of Activity / Test - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout.
note | Action (Hold, Monitor, Witness) - I
note | Minimum Test Frequency - Continuous monitoring
note | Inspection / Test method - TNZ B/02: 2005 - 5.1
note | Record documents (QCP - Quality Control Portal) - Survey/ Level checks
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
checkpoint | 2.02 - Layer Thickness
note | Detail of Activity / Test - Sub-base Layer Thickness
note | Action (Hold, Monitor, Witness) - W
note | Minimum Test Frequency - 1 test per 20m
note | Inspection / Test method - TNZ B/02: 2005 - 7.3
note | Acceptance Criteria - The average uncompacted thickness of subbase layer shall not be less than 2.5 times the maximum particle size of the aggregate
note | Record documents (QCP - Quality Control Portal) - Survey/ Level checks
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
checkpoint | 2.03 - Layer Thickness
note | Detail of Activity / Test - Basecourse Layer Thickness
note | Action (Hold, Monitor, Witness) - W
note | Minimum Test Frequency - 1 test per 20m
note | Inspection / Test method - TNZ B/02: 2005 - 7.3
note | Acceptance Criteria - The average uncompacted thickness of basecourse layer shall not be more than 200 mm.
note | Record documents (QCP - Quality Control Portal) - Survey/ Level checks
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
checkpoint | 2.04 - Overlay Sites Plateau density Tests
note | Detail of Activity / Test - The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 test per 5,000m2
note | Inspection / Test method - TNZ B/02: 2005 - 7.5 (b), 7.6
note | Record documents (QCP - Quality Control Portal) - MDD and Plateau Reports
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction as required in clause 7.6 at OWC and make the information available to the Engineer. It shall be the responsibility of the Contractor to achieve the specification requirements.
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction (1)
note | Detail of Activity / Test - Degree of Compaction (DoC) - Subbase
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Min 5 Tests per lot (1000m2 max - lot size)
note | Inspection / Test method - TNZ B/02:2005 - 7.6
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction (2)
note | Detail of Activity / Test - Clegg Hammer Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Min 5 Tests per lot (1000m2 max - lot size)
note | Inspection / Test method - ASTM D5874
note | Acceptance Criteria - ≥30 CIV
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | IDC specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction (3)
note | Detail of Activity / Test - Degree of Compaction (DoC) - Base course
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Min 5 Tests per lot (1000m2 max - lot size)
note | Inspection / Test method - TNZ B/02:2005 - 7.6
note | Acceptance Criteria - Average DoC ≥ 98%
note | ○ Minimum DoC ≥ 95%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Compaction
note | Detail of Activity / Test - Clegg Hammer Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Min 5 Tests per lot (1000m2 max - lot size)
note | Inspection / Test method - ASTM D5874
note | Acceptance Criteria - ≥50 CIV
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | IDC specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
section | 3.0. TESTING & SIGNOFF - UNBOUND OVERLAY
checkpoint | 3.01 - Fiinished Pavement
note | Detail of Activity / Test - Crossfall
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - TNZ B/02: 2005 - 5.1
note | Acceptance Criteria - ± 0.5% of specified crossfall measure
note | ○ 2m apart
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.02 - Fiinished Pavement
note | Detail of Activity / Test - Width
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - TNZ B/02: 2005 - 5.1
note | Acceptance Criteria - -20mm, +100mm
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Fiinished Pavement
note | Detail of Activity / Test - Surface Shape
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - TNZ B/02: 2005 - 7.8
note | Acceptance Criteria - < 10mm using 3m straight edge
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Fiinished Pavement
note | Detail of Activity / Test - Holding Water
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to Sealing
note | Inspection / Test method - TNZ B/02: 2005 - 7.7
note | Acceptance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.05 - Fiinished Pavement
note | Detail of Activity / Test - Running Course
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to Sealing
note | Inspection / Test method - TNZ B/02: 2005 - 10.1
note | Acceptance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed.
note | Record documents (QCP - Quality Control Portal) - Site notes
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.06 - Fiinished Pavement
note | Detail of Activity / Test - Surface Finish post sweeping
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to Sealing
note | Inspection / Test method - TNZ B/02: 2005 - 7.8
note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
note | Record documents (QCP - Quality Control Portal) - Photos
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On Site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance Testing
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Fiinished Pavement
note | Detail of Activity / Test - Roughness
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to Sealing
note | Inspection / Test method - TNZ B/02: 2005 - 7.7
note | Acceptance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements.
note | Record documents (QCP - Quality Control Portal) - Test Certificate
note | Responsibility - Contractor
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.08 - Fiinished Pavement
note | Detail of Activity / Test - Degree of Saturation (DOS)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Min 5 Tests per lot (1000m2 max - lot size)
note | Inspection / Test method - TNZ B/02:2005 - 12
note | Acceptance Criteria - ≤ 60% (for design traffic load > 5x10^6 ESAs)
note | ○ ≤ 65% (for design traffic load < 5x10^6 ESAs)
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Pavement layer compaction test results may be used for this purpose where the Engineer is satisfied that the water content has not had a chance to rise between testing and sealing. (ie it has not rained or additional watering has not been applied to the pavement).
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accredited Laboratory Test Result Report - (Quality Assurance Testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
section | 2.0. BEFORE CEMENT STABILISATION STARTS
checkpoint | 2.01 - Setout section
note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Survey
note | Acceptance Criteria - Document existing furniture
note | Record documents (QCP - Quality Control Portal) - Electronic survey files
note | Responsibility - Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - Site Survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Use grader's machine control and inspect shape
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Visual check or Vibratory Roller's response meter
note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
note | Responsibility - Stabiliisng Contractor
note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - 5000 m2
note | ○ TNZ B/5: Section 7.7.1
note | ○ NZTA B/7: Section 8.1
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Designer - I
note | Eng. Rep - A
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - Site Testing
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Survey
note | Acceptance Criteria - As per NZTA Z/16
note | ○ Minimum: -5mm
note | ○ Maximum: +15mm
note | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
note | Responsibility - Stabilising Contractor with Main Contractor
note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
note | — overlay aggregate quality / consistency
note | — moisture content
note | — any concerns with shape and tie in
note | — etc.
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site survey
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Daily Report
note | Acceptance Criteria - Points covered in NZTA B/5
note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
note | Responsibility - Stabilising Contractor
note | Eng. Rep - I
note | Contractor - R
date | Date -
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On site Inspections
note | Testing Responsibility - Subcontractor (Physical Works)
note | Paid By - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
checkpoint-no-value | 1. The contract rate must fully compensate for all plant, labour, transport costs and materials required to complete the work including ripping the existing seal layers, hoeing into the existing pavement material (where required), and the installation of a First Coat Seal except for the cost of the supply of bitumen which is covered in Item 3211.
checkpoint-no-value | 2. The contract rate shall fully compensate for ripping and hoeing the existing seal, completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - Stabilisation | itp | ITP - Pavement Renewal - Stabilisation
section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Crushing Resistance
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4407:3.10
note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Maximum Wet/Dry Strength
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4407:3.10 & AS 1141.22
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Weathering Quality Index
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4407:3.11
note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 10,000 m3
note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
note | Acceptance Criteria - Compacted using NZ Vibe Hammer
note | ○ 4-day soaked CBR ≥ 80%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - NZTA M04: 2024
note | ○ AP40 - Class 2
note | ○ PI and CI applies
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Broken Faces Content
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.14
note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
note | Notes:
note | H = Hold point up to approval of Optimisation Testing
note | M = Monitor during production
note | Detail of Activity / Test - Particle Size Distribution
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.8.1
note | Acceptance Criteria - NZTA M04:2024-Class 2
note | ○ Class 2 in Table 12 for PSD
note | ○ Table 13 for shape control
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3721 and 3731
note | Testing Type - Material Testing
note | Responsibility - Aggregate Supplier (Quarry)
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Testing to be conducted as per NZTA M/4 requirements and all the testing cost to be included in aggregate supply and delivery rate.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
note | Detail of Activity / Test - Blend Particle Size Distribution
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 per 1,000 m3
note | Inspection / Test method - NZS4407:3.8.1
note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
note | Responsibility - Designer
note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
note | Testing Type - Design Testing
note | Responsibility - Designer
note | Paid by - Professional Services
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - In this case, professional services contractor to manage this scope of testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
note | Detail of Activity / Test - Indirect Tensile Strength, ITS
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 Optimisation test per aggregate type
note | Inspection / Test method - NZTA T/19: 2020
note | Acceptance Criteria - Testing at 1mm/min:
note | ○ BSM Dry ITS: 175 kPa to 400 kPa
note | ○ BSM Soaked ITS: 150 kPa to 350 kPa
note | Testing at 50.8mm/min:
note | ○ BSM Dry ITS: 210 kPa to 480 kPa
note | ○ BSM Soaked ITS: 180 kPa to 450 kPa
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Designer
note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
note | Testing Type - Design Testing
note | Responsibility - Designer
note | Paid by - Professional Services
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - In this case, professional services contractor to manage this scope of testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 Optimisation test per aggregate type
note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
note | Acceptance Criteria - UCS limits set by the design engineeer
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Designer
note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
note | Testing Type - Design Testing
note | Responsibility - Designer
note | Paid by - Professional Services
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - In this case, professional services contractor to manage this scope of testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
note | Detail of Activity / Test - Modified Maximum Dry Density
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Single Point DD vs WC during optimisation test
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - To determine target density
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Designer
note | Project Specific Notes / Instructions - Required before Stabilisation commences
note | Testing Type - Design Testing
note | Responsibility - Designer
note | Paid by - Professional Services
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - In this case, professional services contractor to manage this scope of testing.
signoff | AUTHORITY HOLDPOINT
section | 2.0. BEFORE CEMENT STABILISATION STARTS
checkpoint | 2.01 - Setout section
note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Survey
note | Acceptance Criteria - Document existing furniture
note | Record documents (QCP - Quality Control Portal) - Electronic survey files
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - sITE sURVEY
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Use grader's machine control and inspect shape
note | Record documents (QCP - Quality Control Portal) - N/A
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe, shape and proof roll
note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Visual check or Vibratory Roller's response meter
note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
note | Responsibility - Stabiliisng Contractor
note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - self-propelled pneumatic tyred roller with a minimum weight such that the weight on each tyre is least 2 tonnes, and a tyre pressure of minimum 250 kPa. Proof rolling must comprise at least 10 passes of the roller.
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality Control Testing
note | Comments - Subcontractor to conduct inspection with Engineer rep or Downer Rep. Allowance to be made when buiding up a m² for this pre-hoe.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | IDC - RFT Schedule of Price - 3741
note | IDC specifications Frequency - 5000 m2
note | ○ TNZ B/5: Section 7.7.1
note | ○ NZTA B/7: Section 8.1
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 2.06 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 95%
note | ○ Minimum DoC ≥ 92%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3741
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Overlay and check levels
note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Prior to stabilisation per section
note | Inspection / Test method - Survey
note | Acceptance Criteria - As per NZTA Z/16
note | ○ Minimum: -5mm
note | ○ Maximum: +15mm
note | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
note | Responsibility - Stabilising Contractor with Main Contractor
note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
note | — overlay aggregate quality / consistency
note | — moisture content
note | — any concerns with shape and tie in
note | — etc.
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - Site survey
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - DWG File and drawing pdf (Quality Control Testing)
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
signoff | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Production Plan
note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to each section
note | Inspection / Test method - Daily Report
note | Acceptance Criteria - Points covered in NZTA B/5
note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3721
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² /ton rate for unbound overlay.
section | 3.0. CEMENT STABILISATION OPERATION
checkpoint | 3.03 - Weather conditions
note | Detail of Activity / Test - Material behind stabiliser
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading
note | Inspection / Test method - Measurement
note | Acceptance Criteria - Material after stabilisation:
note | ○ Cement - 5°C, Lime - 10°C, Cement/Lime - 10°C
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.04 - Weather conditions
note | Detail of Activity / Test - Wind
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - Wind speed < 25 km/hr
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.05 - Weather conditions
note | Detail of Activity / Test - Rain
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Prior to spreading cement or lime
note | Inspection / Test method - Local weather stations
note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilsing Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.06 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - every 400 m2
note | ○ every 150m for a 2.4m width
note | Inspection / Test method - Weigh mat or tray
note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going measurement by computer/load cells
note | Inspection / Test method - Measurement each run
note | Acceptance Criteria - ± 2.5% of specified rate
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.08 - Injection & Mixing of Water
note | Detail of Activity / Test - In-situ Stabilisation process
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On-going visual assessment
note | Inspection / Test method - Visual and hand squeeze test
note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.09 - Depth of stabilisation
note | Detail of Activity / Test - Depth of stabilisation
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - Every 200m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - +15mm / -5mm from specified depth
note | Record documents (QCP - Quality Control Portal) - Daily work Log
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.11 - Compaction
note | Detail of Activity / Test - Plateau Density Test
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
note | ○ IANZ report when processed
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
note | IDC - RFT Schedule of Price - 3711
note | IDC specifications Frequency - NZTA T23
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Compaction
note | Detail of Activity / Test - Maximum Dry Density
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
note | Inspection / Test method - NZS 4402.4.1.3
note | Acceptance Criteria - For analysis of DoC
note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
note | IDC - RFT Schedule of Price - 3711
note | IDC specifications Frequency - 5000 m2
note | ○ TNZ B/5: Section 7.7.1
note | ○ NZTA B/7: Section 8.1
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
checkpoint | 3.13 - Compaction
note | Detail of Activity / Test - Degree of Compaction (DoC)
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1,000m2
note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
note | Acceptance Criteria - Average DoC ≥ 98%
note | ○ Minimum DoC ≥ 95%
note | Record documents (QCP - Quality Control Portal) - IANZ Report
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance & Control testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.14 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
note | Detail of Activity / Test - Clegg Impact Value
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 5 per 1000m2
note | Acceptance Criteria - CIV ≥ 50
note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | IDC specifications Frequency - Not mentioned in IDM specs
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.15 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
note | Detail of Activity / Test - Degree of Saturation, DOS
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - 5 per 1000m2
note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
note | Acceptance Criteria - aim for DOS ≤ 80%
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | Project Specific Notes / Instructions - Report only
note | IDC - RFT Schedule of Price - 3711
note | IDC specifications Frequency - ≤ 60% (Table 10: 3710 sub-base compliance amendments)
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
note | Detail of Activity / Test - Crossfall
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - ± 0.5% of specified crossfall measure
note | ○ 2m apart
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
note | Detail of Activity / Test - Stabilised width
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - -20mm, +100mm
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
note | Detail of Activity / Test - Surface Shape
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - every 20m
note | Inspection / Test method - Measurement
note | Acceptance Criteria - < 10mm using 3m straight edge
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
note | Detail of Activity / Test - Surface Finish
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Per Lot
note | Inspection / Test method - Visual
note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
note | 2. Smaller aggregate held in place by fine material
note | 3. matrix does not displace under normal trafficking and/or sweeping
note | Record documents (QCP - Quality Control Portal) - Survey
note | Responsibility - Stabilising Contractor
note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
note | Detail of Activity / Test - Roughness
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - Before Sealing
note | Inspection / Test method - TNZ TM 7003 v1
note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
note | Record documents (QCP - Quality Control Portal) - Test Certificate
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3711
note | Testing Type - Site Testing
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Allowance to be made under a separate line item for m² rate for site testing.
signoff | AUTHORITY HOLDPOINT
checkpoint-no-value | 1. The contract rate shall include allowance for mixing, compacting, trimming and finishing, to the specified tolerances, and the first coat seal.
checkpoint-no-value | 2. The contract rate shall fully compensate for completely constructing the repair, first coat seal, reinstating the shoulder, removal of surplus chip, and reinstating pavement markings, pavement markers or any other roadside furniture affected by the works, on a like for like basis (excluding any high performance, long life or specialist markings).
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement Renewal - Subsoil | itp | ITP - Pavement Renewal - Subsoil
section | 1.0 AP40/ AP65 Aggregates used for overlay
checkpoint | 1.01 - Drainage aggregate
note | Detail of Activity / Test - Crushing Resistance
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 Test per material per source
note | Inspection / Test method - NZS4407:3.10
note | Acceptance Criteria - > 100KN
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - Material Testing
note | Responsibility - Supplier
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Material source property test, cost is included in the supply of material
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Drainage aggregate
note | Detail of Activity / Test - Particle size distribution
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - 1 Test per material per source
note | Inspection / Test method - NZS4407:3.8.1
note | Acceptance Criteria - as per IFC drawing
note | Record documents (QCP - Quality Control Portal) - IANZ report
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - Material Testing
note | Responsibility - Supplier
note | Paid by - Quarry
note | Certification Type - IANZ Accerdiated laboratory test results reports - (Quality Assurance testing)
note | Comments - Material source property test, cost is included in the supply of material
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Pipe
note | Detail of Activity / Test - Subsoil Pipe Material
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - each delivery
note | Inspection / Test method - Dockets for each delivery
note | Acceptance Criteria - Compliance with TNZ F/2
note | Record documents (QCP - Quality Control Portal) - Delivery Docket
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - Material Testing
note | Responsibility - Supplier
note | Paid by - Supplier
note | Certification Type - Data Sheet compliance with TNZ F/2
note | Comments - Material source property test, cost is included in the supply of material
signoff | AUTHORITY HOLDPOINT
section | 2.0. CONSTUCTION
checkpoint | 3.12 - Alignment
note | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
note | Action (Hold, Monitor, Witness) - H
note | Minimum Test Frequency - For each site where subsoil is required
note | Acceptance Criteria - Engineers Approval
note | Responsibility - Engineers Representative
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
signoff | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Excavation
note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each site where subsoil is required
note | Inspection / Test method - Visual / Photo
note | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.14 - Trench Lining
note | Detail of Activity / Test - A29 A14 or other approved Bidim to be placed and wrapped around Trench.
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each site where subsoil is required
note | Inspection / Test method - Visual / Photo
note | Acceptance Criteria - Minimum Width 300mm.
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.15 - Pipe laying
note | Detail of Activity / Test - Pipe must have Min. 100mm of Cushion. Drainage 60:40 Material to be used.
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each site where subsoil is required
note | Inspection / Test method - Visual / Photo
note | Acceptance Criteria - Minimum 100mm
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.16 - Pipe laying
note | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each site where subsoil is required
note | Inspection / Test method - Visual / Photo
note | Acceptance Criteria - As Per IFC Drawings
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint | 3.17 - Backfill
note | Detail of Activity / Test - Drainage 60:40 Material to be used.
note | Action (Hold, Monitor, Witness) - M
note | Minimum Test Frequency - For each site where subsoil is required
note | Inspection / Test method - Visual / Photo
note | Acceptance Criteria - As Per IFC Drawings
note | Record documents (QCP - Quality Control Portal) - Checksheet
note | Responsibility - Contractor
note | IDC - RFT Schedule of Price - 3761
note | Testing Type - On site Inspections
note | Responsibility - Subcontractor (Physical Works)
note | Paid by - Subcontractor
note | Certification Type - In house inspection record - Quality assurance testing
note | Comments - Allowance to be made when building up a m² for stabilisastion.
checkpoint-no-value | 1. The costs associated with subsoil supply and installation are included in the quantities under the relevant items in Section 5210 under ‘Drainage Renewal’.
checkpoint-no-value | 2. 5211 - Payment will be made for each lineal metre completed, as specified. This rate shall include all plant, labour and materials to construct the subsoil drains to the specification (including connection to the downstream structure or outlet), reinstatement of pavement and shoulder the provision of any environmental controls, the disposal of excavated material, removing any material from the pavement surface, reinstating all signs, marker posts and culvert markers
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature