## Soak Pit
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 - IFC | 1 - IFC | 2 - IFC | 3 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Activity Soak Pit Installation |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved by: Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Director |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.0 Construction
1.01 | Excavation | Soakhole Depth is required to be minimum 1.5m below subsoil pipe invert or 200mm above water table. If this is not possible, an additional 200mm to the width required. Minimum width - 1.5m | H | Each site soak pit is installed | Measure / Photo | Site Engineers Approval | Measure / Photo | Contractor |  | A | I | R | dd/mm/yy
1.02 | Trench Lining | Install 500 Micron Polythene sheet wrapped around the trench. | M | Full length of soak pit | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.03 | Backfil - Gabrion Rock | Install clean gabion rock (300mm max size) | M | as per design drawing | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.04 | Geotextile | Install geotextile filter fabric | M | Full length of soak pit | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.05 | Backfill | Install clean gravel on top of filter fabric | M | Full length of soak pit | Visual / Photo | Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.