## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Soak Pit Installation | itp |  |  |  |  | ITP - Soak Pit Installation Rev 0
section | 1.0 Construction
checkpoint | 1.01 - Excavation
label | Detail of Activity / Test - Soakhole Depth is required to be minimum 1.5m below subsoil pipe invert or 200mm above water table. If this is not possible, an additional 200mm to the width required.
label | ○ Minimum width - 1.5m
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each site soak pit is installed
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Measure / Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Trench Lining
label | Detail of Activity / Test - Install 500 Micron Polythene sheet wrapped around the trench.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Full length of soak pit
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.03 - Backfil - Gabrion Rock
label | Detail of Activity / Test - Install clean gabion rock (300mm max size)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - as per design drawing
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.04 - Geotextile
label | Detail of Activity / Test - Install geotextile filter fabric
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Full length of soak pit
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.05 - Backfill
label | Detail of Activity / Test - Install clean gravel on top of filter fabric
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Full length of soak pit
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature