## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d7d58dae-2b82-4d10-81b5-b9c01d6b565c | checklist | FH-927-QU-ITP001 - Site Establishment - Rev 0 | itp | ITP001 - Site Establishment
7babd8cc-c8b9-46a3-ae60-ce22fda1a40f | section | 1 - Work and Site Arrangements
c33e8a06-7540-4604-998a-d5cca9129e76 | checkpoint | 1.1 - Dilapidation and Survey Report
43faea0a-4f02-5998-96d5-65158ceddf8a | note | Frequency - Not less than 2 weeks prior the commencement of the demolition
81557e9f-7638-503c-870b-ffec0a3f8322 | note | Acceptance Criteria - Dilapidation Report for all existing roads and tracks and any other areas utilised by the Contractor for the construction of the Works proposed for use by the Contractor in execution of the Works prior to commencement of physical works on site
d967e0a8-4f5b-5fff-9070-fd7eae32d9de | note | Reference Documents - Vol1: 1211-1 & 1211-2 HP
c62df700-8dd1-5549-aab0-69a871d6aa57 | note | Inspection/Test Method - Check
580ddac5-76b5-5fd8-993f-60eb2af2c84e | note | Record of conformity - Submission of Dilapidation Report
de23d31a-efb8-543a-a72c-6026fcea8552 | note | HP
0c614a86-05ef-548f-815b-deccc9332df6 | note | Responsibility - Project Manager / Quality Engineer
b4709456-aaab-534d-ab2b-17f6072b8a7a | date | Date Completed:
38db9133-2e8d-4469-9b05-aa6eefd62751 | signoff | AUTHORITY HOLDPOINT
fdabfcc2-8aa5-4a71-ba9b-0c9d51359e28 | checkpoint | 1.2 - Site Establishment Methodology Statement
22aea52d-05ec-53a0-824b-6bb0ee361ff8 | note | Frequency - Not more than three weeks after the award of the Contract
affd291e-c444-510c-a269-156ee1bd142c | note | Acceptance Criteria - The Contractor must submit a methodology statement describing all activities required for site establishment to the Contract Administrator for approval
205838a1-b3df-5457-b4da-1f7f40910b76 | note | Reference Documents - Vol1: 1220-1 HP
d5da910b-2cc8-5978-8c39-b83c1fe67ef8 | note | Inspection/Test Method - Check
071af4c1-2e58-568a-a159-d61fdc611e02 | note | Record of conformity - Submission of Site Establishment Methodology Statement
e622e8be-68f3-5592-82b2-ac3798e8d846 | note | HP
93245cde-02e3-55e2-8600-560405bd8109 | note | Responsibility - Quality Engineer
5637f41e-c867-5097-add4-aeedf93ab673 | date | Date Completed:
d794caab-d860-4ccb-a307-689af2ef1bec | signoff | AUTHORITY HOLDPOINT
9fbde557-6d20-40c0-ad15-7f7427715322 | checkpoint | 1.3 - Water Supply
0ff966c2-a661-5ab4-b3cf-167bded05182 | note | Frequency - Monthly
d0277fbe-874a-5395-9097-f2157bf47e6e | note | Acceptance Criteria - The Contractor is responsible for installation (and removal) of the metered water supply point, the supply of the meter and arranging for the reading of the meter, and submission of the readings, monthly. The Contractor must arrange for the Contract Administrator to be present for the initial and final readings.
2923b6cb-c2ae-598b-864f-b7a724ab02d5 | note | Reference Documents - Vol1: 1222-1 HP
429ee1aa-27cf-5f5e-ab4b-f0c074a5ced2 | note | Inspection/Test Method - Check
cccb6948-dd27-5961-91f4-8e9ee76b1d15 | note | Record of conformity - Picture or formal notification
909885a1-be55-51cc-b883-b030549e86e6 | note | HP
c3dc5427-3fe6-5280-83bd-95798acadd20 | note | Responsibility - Quality Engineer
93edaaf0-2535-52eb-a9c7-9f8c63cc8d58 | date | Date Completed:
799be748-2a65-4369-a149-bb3aebb0d256 | signoff | AUTHORITY HOLDPOINT
f278ab40-5686-45f8-a4e5-0747f66fc1b7 | checkpoint | 1.4 - Plant, Equipment and Tools
ba837a56-6539-50a4-b934-eea0b536705a | note | Frequency - Prior to bringing any on to the site
6614fb93-ca75-5da5-86d5-bdc81d4dd4e5 | note | Acceptance Criteria - List of each item of plant, equipment and tools to be used in the Works including type, maker, details of general configuration, weight, maximum wheel load, tyre pressure and maximum height
7585dd3d-ae5b-5c6a-9066-fe97a2fddcd7 | note | Reference Documents - Vol1: 1227-1 HP
2b0703d0-ca7c-5684-95c8-420ec5031390 | note | Inspection/Test Method - Check
e0d5a3ce-ed7b-5a89-93a8-a54646ca4629 | note | Record of conformity - Notification
d252d5e7-4ec6-57b1-9503-9911b787a968 | note | HP
416e4559-31d5-5588-a00b-b4c2976b49cf | note | Responsibility - Quality Engineer
125d69dd-c314-5847-90f4-2429210d4f69 | date | Date Completed:
cd6e3284-3548-42ad-936d-5fec02c00ced | signoff | AUTHORITY HOLDPOINT
4421b9df-c753-4702-9b94-259b4a4b1069 | checkpoint | 1.5 - Removal and Rehabilitation
286de53c-5081-526f-8f8e-870316d2b1ee | note | Frequency - Not less than 1 week prior to commencing removal
266af119-0d40-57b8-af03-2adaaea1d6b9 | note | Acceptance Criteria - When the Contractor's compound is no longer required for the Works being constructed under the Contract, the Contractor must remove from the compound area all sacrificial crushed rock layers and geotextile liners from the Contractor's compound.
a8760931-8711-51e4-8f2b-aea59d6f5b7c | note | Reference Documents - Vol1: 1220-2 HP
b7fe46ce-b294-5c87-81a0-40d457af52e4 | note | Inspection/Test Method - Check
441bb1bd-9095-57ef-9a9c-e7c86a0878b2 | note | Record of conformity - Notification
c31a5633-e218-5c3a-b30d-f276f7850d14 | note | HP
1b879858-7cf6-5e83-8b2a-d8d7f86d2502 | note | Responsibility - Quality Engineer
3cfbfaf0-2fb1-5be5-bd79-6af10d3db113 | date | Date Completed:
dc44ea27-2aa0-4543-9f9c-ee302ab3b2e8 | signoff | AUTHORITY HOLDPOINT
394ec1a5-83c5-458f-a2e4-b31d13bd95c1 | checkpoint | 1.6 - Stockpiles
0347d3d1-f2ee-5c58-95d7-2a762224e92f | note | Frequency - Prior to commencing asphalt works
3469004e-694c-5b44-8209-8ed38568f03a | note | Acceptance Criteria - Details of the location of proposed stockpile sites specifying the maximum dimensions (including height) of the proposed stockpile, material(s) to be stockpiled, proposed separation of stockpiles and methods of management of material(s) to be stockpiled
20ab32ee-066d-5516-b932-23c940fa40a7 | note | Reference Documents - Vol1: 1230-1 HP
7b981109-428a-56de-9b5e-feba37bb5bdd | note | Inspection/Test Method - Check
e9174231-9ff5-5545-8130-8db473c7bcc8 | note | Record of conformity - Notification
fe82fe36-3d67-5b7f-b4b2-8243d3da46c9 | note | HP
c4633004-dcf0-5a55-8690-416bd6fdb046 | note | Responsibility - Quality Engineer
732e157b-5dbc-5258-8e1d-afdc6fd15e32 | date | Date Completed:
e2f59e1a-1941-47f3-adae-f7e30db8adb4 | signoff | AUTHORITY HOLDPOINT
4f992f87-acd2-47c8-a3a9-9392c609af95 | checkpoint | 1.7 - Cold Planned Asphalt Stockpiles
5f085775-e7cc-5382-b9e4-136b467f4b01 | note | Frequency - Prior to commencing asphalt works
d9416cbc-a648-5c1f-aaf8-d94bfe1190de | note | Acceptance Criteria - The location of a temporary stockpile of cold planed asphalt must be proposed by the Contractor and approved by the Contract Administrator.
8c897f97-8f18-59e7-8935-78df9dc1f01d | note | Reference Documents - Vol1: 1230-2 HP
e369b714-64c5-55ce-8f7d-5034e93b000c | note | Inspection/Test Method - Check
4ef8f664-125f-5509-904f-1281b39804ce | note | Record of conformity - Notification
d2eb52a7-e6ad-5b79-baf5-eb06432bda2e | note | HP
92399a23-9a72-555a-9a7e-607316e6505d | note | Responsibility - Quality Engineer
c76a7ece-acdd-56f2-92bc-6163ab93a9c5 | date | Date Completed:
c6b817b9-cc46-4c96-a7f6-f8666d11c9dc | signoff | AUTHORITY HOLDPOINT
e4a12b03-46a5-4f73-9271-32e963600feb | checkpoint | 1.8 - Rehabilitation of stockpile sites
35292e9b-fdad-5f3f-8c82-2886f81f0076 | note | Frequency - Conclusion of works
4bc74673-5ab4-5394-8b57-2d134a09b3d8 | note | Acceptance Criteria - At the conclusion of the Works, the Contractor must dispose of surplus stockpiled material off-site and return the stockpile area to a condition similar to that which it was found, including regrading, replacement of topsoil and establishing grass to the satisfaction of the Contract Administrator.
3acd76ba-9de0-566a-8d7a-3099c12ed599 | note | Reference Documents - Vol1: 1230-3 HP
479fc997-13ab-5aaf-8f75-e6a1a9b1cbb6 | note | Inspection/Test Method - Check
b65a3c92-4747-559c-8bb6-c0a5744fd9a3 | note | Record of conformity - Notification
8f52cbd1-f383-588a-b8fa-7ded5cb67ea1 | note | WP
81468ba9-aa56-5a8d-b16d-aeedd35e9cfd | note | Responsibility - Quality Engineer
ee0ada4d-2631-5876-9328-c031ce4849d7 | date | Date Completed:
88e2e528-b421-47ff-ab84-a5da3950f819 | section | 2 - Quality Assurance and Environmental Management
9df74e3f-9621-403c-8cc3-eae1d707c9d5 | checkpoint | 2.1 - Appointment of Project Quality Representative
469fbc5e-560e-5f67-8283-653cb419e1b9 | note | Frequency - Prior to commencement of works
c03005d5-afaa-5609-bcbf-e76f874401c5 | note | Acceptance Criteria - Submission of Details and credentials of Project Quality Representative
252557fa-43e7-5957-a873-70cff898619a | note | Reference Documents - Vol1: 1303-1 HP
c3f3f718-cb96-57da-8027-86e5d5edc19b | note | Inspection/Test Method - Check
94e83a56-02dd-584d-b51d-d301f5ffe3ae | note | Record of conformity - Notification
327a9064-c8f5-5e2e-a674-7cd89a497755 | note | HP
0e3756dd-e7f8-5da5-beb3-4231a1cdd97c | note | Responsibility - Quality Engineer
2cffc075-1289-516b-a0c7-61b4d730825c | date | Date Completed:
c1285e43-2413-41b2-948a-ec10230ed37b | signoff | AUTHORITY HOLDPOINT
08ebb289-6bb2-4166-89ad-395fe515c9bc | checkpoint | 2.2 - Project Quality Plan
28ec0ec5-7d49-5cd8-b5e5-87e944c74793 | note | Frequency - Prior to commencement of works
b3290842-2c03-51a9-a4b4-9632ad6acca0 | note | Acceptance Criteria - Submission of Draft and final Project Quality Plan
6b3e65df-a8c0-59ff-bb26-d3c00e58a802 | note | Reference Documents - Vol1: 1304-1 HP
ad5dbecd-bef2-570f-85a3-8ce064c758b1 | note | Inspection/Test Method - Check
e3c9a24d-22df-5fc0-bef5-773361699b98 | note | Record of conformity - Notification
2a5af145-d5cc-5ea6-bfb2-a4be6c95c79b | note | HP
92bd11ff-36f4-5fdf-aa5b-849b99328f1b | note | Responsibility - Quality Engineer
9eee38dd-0c7e-5865-bf8e-345ef4b5caf3 | date | Date Completed:
ac7e6280-a9d5-4b35-99c8-2d10290344b8 | signoff | AUTHORITY HOLDPOINT
087e259e-210e-4c6d-8034-0c8b33b47580 | checkpoint | 2.3 - Changes to the Quality System
43fa60c5-745f-5b2b-aa48-31d46f859318 | note | Frequency - Within 24 hours of implementing the change
aaebf8ee-d3c3-5a34-a224-2a184134a339 | note | Acceptance Criteria - Changes to the Quality System may be made by the Contractor at any time. Such changes must comply with the requirements of the specification and must be subject to the prior written approval by the Contract Administrator.
b5514f61-b9b0-5fb5-9c54-879b8d3e1759 | note | Reference Documents - Vol1: 1305-1 HP
77a4dc47-4c4f-5cc9-8178-88af5d3695a8 | note | Inspection/Test Method - Check
4af4f7ef-e046-5f31-8948-0879bdea8ecf | note | Record of conformity - Notification
e6622e9a-a10c-52c6-9ac6-b2cf2ef3f16b | note | HP
90e5dafa-95d2-5b23-b9aa-ae5cc5ac48fb | note | Responsibility - Quality Engineer
436ad682-1428-5a59-9af1-32d63c1cec1b | date | Date Completed:
be242da4-ea30-4cb4-b30c-10dcbbf2f1e0 | signoff | AUTHORITY HOLDPOINT
f48a1da4-4917-43b4-8a46-cabac6187089 | checkpoint | 2.4 - CEMP
dab6a440-ec08-5acc-a23e-1e6d9a756095 | note | Frequency - Before the commencement of work
e3e6bbfe-f3a9-5268-b114-454e9a4fca7b | note | Acceptance Criteria - The Contractor must submit and finalise a Construction Environmental Management Plan (CEMP) in accordance with the requirements of the Contract.
3dbf197f-920a-5342-ae44-7fe14044b8f8 | note | Reference Documents - Vol1: 1404-1 HP
f38438e7-09e2-5cd4-ab1d-a2a99d6a8868 | note | Inspection/Test Method - Check
dd603cdc-b37e-57cb-9384-30d5b00d3963 | note | Record of conformity - Notification
a6ed602d-719a-5b5a-a42c-7750d3a9df1a | note | HP
3979b677-a578-54e3-885f-898950f48f0d | note | Responsibility - Quality Engineer
c280f9bb-2162-544e-9a57-aa99ee7abdfa | date | Date Completed:
c9e3ed87-6b3d-410d-98d0-791a75250df7 | signoff | AUTHORITY HOLDPOINT
a31ce71b-43b6-429c-86f5-bdd84faaca08 | checkpoint | 2.5 - Continuation of Works
feb63904-2179-58d5-b498-f3eea741d42f | note | Frequency - within five (5) working days after receipt of a notice for non- compliance.
a8bd7542-78f4-502a-8562-f6f996a38b0e | note | Acceptance Criteria - Submission of a written report to the Contract Administrator describing corrective actions required as a result of a non-compliance with the CEMP within five (5) working days after receipt of a notice for non-compliance.
82e8774e-4b14-5ba0-ab77-f13c0e233c53 | note | Reference Documents - Vol1: 1408-1 HP
45a75cf3-28ca-5484-9af5-b570f864679d | note | Inspection/Test Method - Check
768008f1-90fe-5fe1-ba99-e3505572b2cf | note | Record of conformity - Notification
ae958bb6-58f6-5d33-9acc-345cceb2b367 | note | HP
42912904-d880-5f82-b986-6252d40632bf | note | Responsibility - Quality Engineer
168142c2-734f-51ed-85e6-8c8b3c9ad6d9 | date | Date Completed:
f4e06a7c-286b-4668-861d-5e0c975c2674 | signoff | AUTHORITY HOLDPOINT
916b2337-1e2c-42a2-8426-9add3e693cf9 | checkpoint | 2.6 - Lot Closure
dc1c3bee-b3b2-59b5-bc34-182b0944d1aa | note | Frequency - Each Lot
630374a2-588a-5c76-99e7-fb45ccb88394 | note | Acceptance Criteria - Lot conforms to all required Technical Specifications. Any NCR's actioned and closed out and no further actions are required.
96329f10-cf81-589e-9d30-e6608a570601 | note | Reference Documents - Vol 1: 1300
50bcc07f-5cd5-509d-b22f-8a6095c51ddd | note | Inspection/Test Method - Verify
fffd1ddb-e3c2-5ecf-bc0d-e6cd10b72e03 | note | Record of conformity - ITP Sign Off
f1166447-8ca2-5156-82d8-a9e1f6d14795 | note | IP
9c62de04-f21a-5020-9e79-2ae113cb2e2e | note | Responsibility - Quality Engineer
517cc74a-ab63-5328-8132-10f862aea78f | date | Date Completed:
44cc34ec-aa33-42e6-9b9f-a32d7f18d0dd | checkpoint | Final Inspection
d9823b3c-e41f-517b-aaaf-aa6ec4aa07ed | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
c40eed90-56d7-5990-a07d-bda8c970ef5e | textbox | Print Name:
0da4dea0-baaf-5ed7-a6a1-abe3c73661e4 | textbox | Position:
e3a6bec8-1427-5e29-93c6-b19a812ccb89 | date | Work Completed On:
e7831767-5faa-5116-847d-965a26946e09 | date | Date:
6f5ac380-ba37-4785-a7b4-651b3379263e | checklist | FH-927-QU-ITP002 - Pavement Marking - Rev 0 | itp | ITP002 - Pavement Marking
9021e3bb-347a-4a4c-9b69-6a40f6e57b68 | section | 1 - Materials
5c0f7830-0aa8-4b52-8426-7945f4b6d820 | checkpoint | 1.1 - Supply of paints for pavement marking.
e1121e8e-bb46-5abc-9f99-cc140b7a08f9 | note | Frequency - Not less than 1 month prior to the commencement of pavement marking.
e34b338b-c944-576e-899b-4ced9362680c | note | Acceptance Criteria - Submission of conformance test reports for the proposed paints to the Contract Administrator which demonstrate compliance to Section 2 of this ITP.
9b3b5292-ff08-5a31-be09-36a88cd9b4bd | note | Reference Documents - Cl 7103(b), HP7103-1
407ede10-7cf2-54a0-93fb-5b5399a2fab6 | note | Inspection/Test Method - Document
7b4df792-1ee2-58f5-8c95-073ab19e5b33 | note | Record of conformity - Aconex Submission
f9e783a3-bc1a-5836-90bf-2a0c1a61560d | note | HP
a4506be2-225a-52b9-a51b-5a1a0b229268 | note | Responsibility - Site Engineer
3e82c557-21bd-5729-a028-43a33bbb71fe | date | Date Completed:
5afdf377-086d-4407-b81d-7814c5ae2c13 | signoff | AUTHORITY HOLDPOINT
ee507440-5527-4fbf-be79-4c000b656263 | section | 2 - Paint Properties
48c5af91-b240-4c26-a896-c3296cc67e1d | checkpoint | 2.1 - Runway marking paint and taxiway and apron marking paint type and packaging
d92c67d0-e904-56dd-a525-d3ab779fd59a | note | Frequency - Prior to the commencement of pavement marking works.
c63eb9eb-ffe6-5401-903d-f7b10e75f9c6 | note | Acceptance Criteria - Paint is pre-mixed acrylic co-polymer water-based paint, packaged in 20 L containers. Containers are of durable construction and labelled with manufacturer's name and a complete description of the contents. Paint is of a consistency suitable for application by brushing and spraying, and capable of being used as supplied or diluted with water.
9bb2477e-0dcb-528f-9be9-33a3ff2fdf39 | note | ○ Dilution information and coverage is stated by the manufacturer on the packaging.
3be5cd32-71a6-5842-82de-0f64d8511821 | note | Reference Documents - Cl 7103(a)(c)(d)(h)
2c98bfcf-7644-5406-a810-0b3a2f7c7089 | note | Inspection/Test Method - Inspection
faac731c-949d-5adb-b5dc-318cd8aeefb7 | note | Record of conformity - This ITP signed by Contractors Quality Representative
60e3dab6-76e2-5973-b5bd-21f16f88c3d8 | note | IP
724ec473-a627-572e-9d54-48eae7d0b6e0 | note | Responsibility - Site Engineer
755f33d9-1471-5aa7-a23e-4e461f3aa08b | date | Date Completed:
d233ca95-739d-4b21-95d4-3fb2bc55af06 | checkpoint | 2.2 - Condition upon delivery
9faef112-26e7-5c20-9d0c-e7f2a54c8277 | note | Frequency - Prior to the commencement of pavement marking works, at the time of delivery of paint.
c20b677c-51b3-57a2-8c80-28621ffacdd2 | note | Acceptance Criteria - Hand stirring of the paint readily produces a smooth uniform product.
3e786e2d-1bb9-5ea1-b565-1d0b5d60c09e | note | Reference Documents - Cl 7103(f)(g)(i)(j)(k)
de816b3b-fa7d-58fc-a0c9-497a44562b1d | note | Inspection/Test Method - Inspection
ef040c5f-de3d-56ec-88cf-4edc788de082 | note | Record of conformity - This ITP signed by Contractors Quality Representative
1274aaa2-f680-5f38-b2ce-2e330d79c5ee | note | IP
265058e5-47fc-5fb1-aa73-6ab802c5ecff | note | Responsibility - Site Engineer
9d210c0d-73b8-5903-8ce3-496a05e412cd | date | Date Completed:
3776d6c2-674f-468c-9084-08f14b41b474 | checkpoint | 2.3 - Paint Surface Finish
a2d2e530-ef5f-5b83-bfca-f05941eaa69d | note | Frequency - Prior to the commencement of pavement marking works.
d82ab70b-a118-5f99-a77a-759477a69b43 | note | Acceptance Criteria - The dried surface of painted areas on aircraft aprons is not slippery under foot. The surface finish of the dried film of paint is a non-gloss matte finish.
56ac6b53-5515-5103-9be6-194da6e17e6e | note | Reference Documents - Cl 7103(l)(m)
4dc3bc42-e8fb-51dd-a21f-51257e1c39ed | note | Inspection/Test Method - Inspection
4a45421c-c206-522c-9d3b-812d180881c4 | note | Record of conformity - This ITP signed by Contractors Quality Representative
d9b0375d-9dfc-5460-8ee0-0b818300c92e | note | IP
602fffad-afa7-5399-a4c0-d0f416cbf2ab | note | Responsibility - Site Engineer
f00cbd28-fdd0-5f48-9f4d-03c0977eac70 | date | Date Completed:
1566ffe2-ce47-40d3-8d24-5f6963940e75 | section | 3 - Trials
be6c6d5d-238c-4223-abe9-1a9078dc6a13 | checkpoint | 3.0 - Demonstration of process and equipment for removal of pavement paint markings.
7fd890f2-e66a-55d4-a4c8-ffc99991d8a8 | note | Frequency - Not less than 1 working day prior to the commencement of full-scale paint removal works. Prior notice (24 hours minimum) of trial to be given to Contract Administrator.
a65e6be2-e0a7-5bfc-bf75-256ffae03a13 | note | Acceptance Criteria - A trial conducted in an area agreed with the Contract Administrator of not less than 5 m2 demonstrates removal of pavement marking without chemical methods, without causing disintegration of the pavement surface and in compliance with the requirements of Section 4 of this ITP.
1ea04001-6641-54a3-bba9-9e9bce6ada87 | note | Reference Documents - Cl 7104(f), HP7104-1
140dc713-dd07-5825-afc0-1f533a173e22 | note | Inspection/Test Method - Inspection
67b74b49-b1d2-5ad1-b813-480e0e560d1f | note | Record of conformity - This ITP signed by Contract Administrator
cbf7587e-4a85-5ce6-a6a3-1e369a6689b6 | note | HP
21340322-efba-54c1-bb9c-0e8b4a75ad1d | note | Responsibility - Site Engineer
231def4b-093a-5505-a8c0-a3e80163ae19 | date | Date Completed:
2ea671f6-b46f-4e3f-b4b6-c24006ce8048 | signoff | AUTHORITY HOLDPOINT
a374aa73-66a6-48dd-aaaa-c4f5587642d1 | section | 4 - Removal of Pavement Paint Markings
f08ea855-23d4-4082-962a-5ef9938fed51 | checkpoint | 4.1 - Plant Performance Check
6fd6c66c-522c-521d-b43d-c555cb9ad7ae | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
aaec9f4e-f4fe-5a1e-a7ca-22d77206bd7d | note | Acceptance Criteria - All plant is in working order, free from leaks, and capable of removing all paint from the pavement surface without filling voids with debris, removing joint sealants or otherwise damaging the pavement surface.
8e2d74a6-3126-5406-800a-522ff9c5aaad | note | Reference Documents - Cl 7104(b)(c), WP7104- 1
2edb2795-aaf2-549c-a941-391b471f566e | note | Inspection/Test Method - Inspection
71436ee5-df44-5cb7-a6a4-8bae3057bd5e | note | Record of conformity - Daily Plant Verification Checklist / This ITP signed by Contract Administrator
6c2ed108-0918-511b-a2ef-9c3e0ddae5fd | note | WP
5527735a-e55b-5e58-9015-4ffa64cf3449 | note | Responsibility - Site Engineer
814d688b-95aa-5d76-94c7-85d7615c26af | date | Date Completed:
2a25c58b-53a4-4397-ac57-2a9b1993776e | checkpoint | 4.2 - Weather Conditions
e1ed1375-ef6d-5e08-9013-f3fec14f6c76 | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
3d7cab71-a4df-5d93-9e65-9570386346d5 | note | Acceptance Criteria - Pavement surface is free of snow, ice or slush, with a surface temperature of at least 5oC and rising at the beginning of operations (except for where shot- or sand- blasting is used for which a lower surface temperature may be accepted). Work is not occurring during a thunderstorm. Work is not occurring during rainfall, except for water-blasting and removal of previously applied chemicals.
d1526695-993b-5001-9ef0-bdab2471b4d0 | note | Reference Documents - Cl 7104(e)
a83c778e-7ff6-53f7-bda5-6d12e3ac57ca | note | Inspection/Test Method - Inspection
3a334b7a-56aa-520b-bd5f-bc4e3f735afc | note | Record of conformity - This ITP signed by Contractors Quality representative
de25f33f-5853-5bb4-8bf1-380ba0fae476 | note | IP
6415efe4-ed69-5407-bb31-3af986007cc3 | note | Responsibility - Site Engineer
22b31772-6cb9-595b-a9e0-a5c6eeeed00b | date | Date Completed:
f11e319b-72d9-4d3a-abc4-ab762f4c849d | checkpoint | 4.3 - Surface Texture
2f0194c1-3128-5167-bd97-36adff1f211f | note | Frequency - Prior to the commencement of paint marking removal work in each work period.
5e41bf13-54a9-5e3a-9b90-de3811965c89 | note | Acceptance Criteria - The surface texture of the cleaned removal area is comparable to a standard area of pavement in the removal trial area selected by the Contract Administrator.
56bf7701-f19c-5304-a15b-99c9853bcd57 | note | Reference Documents - Cl 7104(f)
b2e27adc-f548-5230-b711-e04eda40f4ca | note | Inspection/Test Method - Inspection
054f5682-fd2d-5dd5-ad8f-f91ba33d131b | note | Record of conformity - This ITP signed by Contractors Quality representative
c008bf20-529a-5138-9af5-18e672383547 | note | IP
4356a79a-546d-52e8-961d-043e7de317bd | note | Responsibility - Site Engineer
87093b31-de11-5f72-9b01-95b4b26f61d6 | date | Date Completed:
3fc108c7-e383-4d01-94ef-2b70eed8b90b | checkpoint | 4.4 - Clean up and waste disposal
0fd64ea0-e430-5a1e-bc31-961d4e42e0fc | note | Frequency - At the completion of paint marking removal work in each work period.
ba192bf8-cdd5-5e5a-bfd6-681f3611e528 | note | Acceptance Criteria - Debris and waste materials have been collected, removed from site and disposed of at an appropriately licensed waste disposal site.
e4751505-1cdf-58e6-8c66-099ec13790e1 | note | Reference Documents - Cl 7104(f)
2c9df90a-79a7-55b8-a1bf-b3433f1c31c7 | note | Inspection/Test Method - Inspection
ca18c8fd-b938-54aa-b6a1-ca03d65ab327 | note | Record of conformity - This ITP signed by Contractors Quality representative
b01c8491-2ca6-5841-bde6-08f3e09010fc | note | IP
bfebdaeb-ee1b-5539-9b3e-202e508af1f2 | note | Responsibility - Site Engineer
64a8b768-86ad-5d2a-a972-4796306486e4 | date | Date Completed:
73d85883-11ee-48bd-bcea-c767287049a6 | section | 5 - Application of Pavement Markings
b66fc8fe-7573-4b47-9d74-7990595f75a2 | checkpoint | 5.1 - Setting out of pavement markings
1254e53c-72a1-5b31-896a-d86cc279ddb8 | note | Frequency - At the completion of setting out and prior to application of pavement markings. Prior notice (minimum 24 hours) of commencement of setting out is given to the Contract Administrator.
a628cc16-a9e4-59fc-8cb2-22c3b1c76a00 | note | Acceptance Criteria - Survey for setting out new pavement markings has been completed as shown on the Drawings by a suitably qualified surveyor, to a horizontal accuracy of ± 25 mm. Spotting indicates the location and extent of new markings in sufficient detail for the painting of the required markings to the tolerances specified.
68dbe0be-89da-56ed-9eb6-75015e92f3b0 | note | Reference Documents - Cl 7105, HP7105-1
d4ac2d27-d024-527c-b575-dbc0bd0eeb5f | note | Inspection/Test Method - Inspection / Statement of complianc e by contractor s PQR
e56b0ef2-edda-5317-a148-d5ea781099e4 | note | Record of conformity - This ITP Signed by Contract Administrator
9ead7e50-d16f-5ffb-b143-ac75e53f179f | note | HP
a5ce3d8f-2c8e-55cd-b42b-81d46d92b67f | note | Responsibility - Site Engineer
f9fc8204-cb29-5cdc-81c5-4dbb2f484466 | date | Date Completed:
07e7c35f-a625-43d5-890c-6076c55e6122 | signoff | AUTHORITY HOLDPOINT
b84672dc-9474-4f48-bb2e-2cb25787fd05 | checkpoint | 5.2 - Surface preparation
d38a937d-e1e6-58b8-93e4-efc2ff759c03 | note | Frequency - Prior to the commencement of pavement marking in each work period. Prior notice (minimum 24 hours) of the commencement of pavement marking is given to the Contract Administrator.
e6d8cfe4-0a42-5eae-b510-71e61d940f2e | note | Acceptance Criteria - The surface to be painted has been thoroughly cleaned using vacuum sweepers, hand brooming, and/or high pressure water jetting as required, and all existing paint not strongly adhering to the pavement has been removed.
ab83bab6-0e5b-59cc-91ed-92a2d16564f4 | note | Reference Documents - Cl 7106(b), HP7106-1
cf66a919-2d94-5213-8bb0-e5f5a227cfda | note | Inspection/Test Method - Inspection / Statement of Complianc e by Contractor s PQR
59440c99-f69a-5b62-b05d-134cc9a2c4a5 | note | Record of conformity - This ITP Signed by Contract Administrator
25abbe96-b4f0-5db7-8a02-7b758fd0614f | note | HP
9e872a1c-e60e-5d8e-8b6b-55bed65a3c5c | note | Responsibility - Site Engineer
c64c28eb-50d0-5ec5-8d86-d49d56efe697 | date | Date Completed:
85c5ca23-797e-428e-9a12-b1a9a62980f7 | signoff | AUTHORITY HOLDPOINT
07d7d1c7-696e-41c6-a424-b79cd80ff294 | checkpoint | 5.3 - Weather conditions
98d48d6d-9469-5bfc-bce8-b69b74273873 | note | Frequency - Prior to the commencement of pavement marking in each work period.
d98e2c34-c3e5-5650-bcf4-d0e9ce4a3078 | note | Acceptance Criteria - The pavement surface is not wet and wet weather conditions are unlikely during the work period, the air and pavement temperatures are not less than 15oC, the relative humidity is not greater than 85%, the wind speed is not greater than 20km/hr, and wind conditions are unlikely to affect the application of the paint.
3606e0a8-6793-5aba-843a-b29b6e464de5 | note | Reference Documents - Cl 7106(c)
78b5db06-e8b5-51f9-919c-dde7de37335b | note | Inspection/Test Method - Inspection
f1b4b365-c955-55a0-9c2e-3d79d6162ce9 | note | Record of conformity - This ITP Signed by Contract Administrator
45cb75b5-110f-593f-ad93-061d8a7883c8 | note | IP
66f900ed-a9e1-5ed0-8394-dcb7b0e0b801 | note | Responsibility - Site Engineer
76172c38-a55f-5237-abd3-130dfa12131b | date | Date Completed:
fdb94963-0f14-4a4b-9a0a-a58e9e3ab121 | checkpoint | 5.4 - Pavement marking adjacent to in- pavement light fittings
44d5b57e-6b9e-5cce-955d-80cce72f4e11 | note | Frequency - During pavement marking works.
c48f1128-f027-529f-aba7-fa5d91b5e4cf | note | Acceptance Criteria - Any in-pavement light fittings in the vicinity of pavement marking works have been protected to avoid contamination with paint. Markings in line with light fittings extend to the edge of the fitting but not on to the fitting. The gap between the end of painted line and edge of a light fitting is not more than 25 mm.
22d6b35e-2633-52e1-ae9f-a3a1aeb926c9 | note | Reference Documents - Cl 7106(d)
e1b1eb9e-6f61-5d1c-85ce-90fb4ff92404 | note | Inspection/Test Method - Inspection
8bd6f016-6523-54f6-acd8-55fdad63ec9f | note | Record of conformity - This ITP signed by Contractor Quality representative
ab65aae3-6cf8-5a2e-99e8-5b3910990556 | note | IP
837506d2-15df-5c39-b5f9-4cd464f38eed | note | Responsibility - Site Engineer
673a4202-d0c7-5147-85eb-522edcdd7fe0 | date | Date Completed:
d55ea4a7-70a6-46ad-aacf-70b47e76e6fe | checkpoint | 5.5 - Application of Paint
0a53e44e-2f2f-518f-9159-8a62ec02a034 | note | Frequency - During Pavement works.
1b33b657-51e4-5de5-b349-c6853960fd58 | note | Acceptance Criteria - Paint is applied by spraying, except for small markings, isolated repairs, and stencilling of letters and numerals where brushing is permitted. Paint is applied in 2 even coats to give a minimum total dry film thickness of 120 µm. The edges of markings are straight or smooth even curves, with crisp even lines without side spatter at the edges and ends of markings.
bee329f3-683a-5bcf-ad50-28096441abcd | note | Reference Documents - Cl 7106(d)
e81732cb-f019-533c-abca-4953b29dedbc | note | Inspection/Test Method - Inspection
297eb5cd-ff3e-5667-9fba-6108e17e21f7 | note | Record of conformity - This ITP signed by Contractor Quality representative
b7da4b94-a0d0-5f51-bd40-d1a8b2d45371 | note | IP
c7ea825e-1938-56ca-9e06-f7c951c97f72 | note | Responsibility - Site Engineer
02f2039e-512d-5728-b519-ddcd6c9ccff7 | date | Date Completed:
8e24ba86-5355-4bd7-a707-62b64ba42d46 | checkpoint | 5.6 - Application of glass beads
c7ba8d42-eb1f-5a6a-a837-753b05d9f3c8 | note | Frequency - During Pavement Works.
3c6dbdd0-e160-54f6-97b9-8cb18868ba30 | note | Acceptance Criteria - Glass beads are not used on any pavements with the exception of areas specified within standard MAS- CVL-002 for Pavement & Pavement Markings (Airside). Where glass beads are specified on taxiway pavement markings, the minimum application rate is 300 g/m2.
2cdfa2ab-7768-57fd-b8e0-a783632edb7f | note | Reference Documents - Cl 7106(d), SP7103(n)
2661031b-569b-53d6-987a-316e0291fb13 | note | Inspection/Test Method - Inspection
4b6d42da-dcef-5bf5-a23d-e2d86ed3a132 | note | Record of conformity - This ITP signed by Contractor Quality representative
0dca6233-46bd-5b37-b02b-6b4af0d41382 | note | IP
1775200c-f43c-5b00-aee9-7d2c1dedde69 | note | Responsibility - Site Engineer
a5a06d77-9a9e-5766-9fb9-b69dccfe2372 | date | Date Completed:
bcc87495-a0c1-427f-916e-2d9df6c753e5 | checkpoint | 5.7 - Paint Application
892f6c06-0c3e-5764-b5fe-5ddc0450c780 | note | Frequency - At the completion of paint marking removal work in each work period.
740bb1f7-04ca-5782-bcb4-2624c8b3c286 | note | Acceptance Criteria - Paint usage and area of coverage for each work period are recorded.
46842592-312d-529a-ad05-f247adbcedf9 | note | Reference Documents - Cl 7107
b2b43e49-f396-5fca-8c8d-3c70bb2cb050 | note | Inspection/Test Method - Inspection
e1b0f966-4a0d-5549-a0c2-4479bb5163ad | note | Record of conformity - Daily Shift Report.
08e5ddac-52f1-5a43-9b80-f29c2ba26e45 | note | IP
e0524375-a145-51b3-84a8-98736e315a99 | note | Responsibility - Site Engineer
dd277837-dbc9-5e7f-924c-a2df4eb577be | date | Date Completed:
49ce66af-c0da-476f-8b74-ad76be6ff393 | checkpoint | 5.8 - Daily records of Paint Usage and Area covered.
5281a257-049c-58a4-a9af-8be23b828124 | note | Frequency - Each shift
0246511f-fbe2-52f0-8e6e-1451d3a3c793 | note | Acceptance Criteria - Daily records of paint usage and the area covered must be maintained by the Contractor to ensure that the specified application rate of the paint is being achieved consistently.
97dde519-66ca-55bc-bc5a-b810b55ccba5 | note | Reference Documents - CL7107
366b2cf9-f859-519d-9a23-1c310b245ad7 | note | Inspection/Test Method - Review of Daily Records.
5ed82264-d2c9-5300-8d99-1d754c993246 | note | Record of conformity - This ITP Signed by Contractors Quality representative.
9b557ef3-8df3-5a4b-9214-afb3305b251c | note | IP
faf3b611-99e6-5923-95c5-6f545cc66575 | note | Responsibility - Site Engineer
acef21dd-eee1-568a-a0b6-16ce7a3adf46 | date | Date Completed:
3f1c8687-750b-45a8-989a-1b94264d5998 | checkpoint | 5.9 - Lot Submission for Pavement Marking
85b4e7a6-aa53-5192-b32f-93a61816e0b7 | note | Frequency - Per shift
b14a8bed-b3fa-5e7a-9bbd-95045d84a3ee | note | Acceptance Criteria - Submit detailed information for each shift. Details include location, test certificates etc.
2d346bf1-ee85-5523-beec-a2e8fe3b287a | note | Reference Documents - Method Statement
e9af6895-92a5-5468-8764-b6954faec8f6 | note | Inspection/Test Method - Review of Lot Submission details
eb3f6070-1b11-565a-bd42-886aeb29648a | note | Record of conformity - Lot Submission documents submitted to Contract Administrator
15cacba1-e0b6-5c52-8728-949f6eb2cd21 | note | WP
84e227d5-0d97-511a-9abd-d40f7b4f0d52 | note | Responsibility - Site Engineer
f27075c9-a846-5328-ac2c-d54890832947 | date | Date Completed:
193f4b85-49c0-4362-9706-fae894f3f0fa | checkpoint | 5.10 - Removal of Non-conforming Pavement markings
032938c2-65c2-5ddb-b451-10953afdd1ad | note | Frequency - As required
9e42e32d-1d5a-5d67-b394-eaeb8f55c885 | note | Acceptance Criteria - Any pavement markings that do not comply with the requirements of this Specification must be deemed non- conforming and must be removed by the contractor in accordance with the requirements of Clause 7104 and reinstated.
ecfc8239-2a26-52b2-b2c5-7f021660ca58 | note | Reference Documents - CL7108
b44d3554-a993-5d71-a494-64c90b19ca2c | note | Inspection/Test Method - Verification of Removal
1ca70729-c1c7-55ef-81de-d733eaeacaa6 | note | Record of conformity - This ITP Signed by Contract Administrat or
c578c4ba-4c8d-5c17-ab5d-1beeb4db9f16 | note | WP
7578c95d-81ba-5f05-b92f-72a93e675ac6 | note | Responsibility - Site Engineer
2061de2a-a666-5030-af2f-872ed12f776d | date | Date Completed:
8b27fdf6-c363-401d-a9a0-9c83b419f012 | checkpoint | Final Inspection
ce8831f9-27db-5240-a899-378274ffc904 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
b6cd69c6-7965-5549-9e22-79a58662cf5a | textbox | Print Name:
867e8be6-fd99-5b00-b4d0-a7b0598312b3 | textbox | Position:
07819e95-5fda-5719-ae78-26e7cab46833 | date | Work Completed On:
51297cef-58c2-5e95-a656-ccdcb037d33e | date | Date:
9ce03912-5c9a-4f30-b0b6-4f5e09733cdb | checklist | FH-927-QU-ITP003 - Surface Rejuvenation - Rev 0 | itp | ITP003 - Surface Rejuvenation
9705a555-f101-4905-9708-e94c264880e8 | section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
abcf9e9f-e27e-4d3f-adc4-b69adb2e6713 | checkpoint | 1.1 - Check for correct documentation
85d0a6f6-1c70-5a64-ae0d-bd49a9d0c191 | note | Frequency - Prior to commencing any activity
faeab320-3ee7-5388-ae03-adea86fe30d7 | note | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy.
50e37505-28f3-5228-912a-54368f0265c4 | note | ○ Current revision to be obtained via Aconex.
81d4d525-a335-5569-a632-e4f73752b815 | note | Reference Documents - Drawings and drawing registers on Aconex
18ecd4d5-7f84-5bd0-84ad-c4fc5545edf4 | note | Inspection/Test Method - Visual inspection
29315a2f-a074-59e1-96df-b6bffcc3431f | note | Record of conformity - This ITP signed by contractors Quality Representative.
7887bf89-0d56-5984-9c9d-ad5dd248cdbe | note | HP*
e3ad0633-181b-5597-abfd-e437b5600e48 | note | Responsibility - Project Engineer
c616fbe2-6551-53eb-91cd-1327cc2088c4 | date | Date Completed:
1b8e8999-d59e-4eb7-9eb8-e89df03f4460 | checkpoint | 1.2 - Implementation of all measures and controls
1e7348ef-8e80-5df6-bb26-1537a38c5657 | note | Frequency - Prior to commencing any activity
d2b4acef-2ad5-5a5a-ba3d-bbd211a2b1a6 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
f7e4f864-3c44-578d-b90f-eee188f8d8a8 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
3780820d-dde9-587d-8e88-12762e84f2ee | note | Inspection/Test Method - Visual Inspection
600cef63-e3be-59b5-95f1-873ac7bb12c8 | note | Record of conformity - This ITP signed by contractors Quality Representative.
45766f02-c446-5ce9-8d96-469ecd686914 | note | HP*
dca29e69-229b-5f51-a94c-abc1fce79851 | note | Responsibility - Project Engineer
d9e56ec1-5d79-5e7d-9cbe-43b7196d6e96 | date | Date Completed:
fac222ce-2189-4215-9146-961821e8434c | checkpoint | 1.3 - Definition of the work area
c8b3bfaa-cd51-5e32-9609-48fae847be9a | note | Frequency - Prior to commencing any activity
0f816db6-f26b-5090-97b3-2175236ab47a | note | Acceptance Criteria - Work area has been cleared and limits of works defined on site.
d0fbd8a1-6156-504a-a66f-0acf1de218eb | note | Reference Documents - Drawings
6c5c7773-bb65-5c62-913e-6e7388256be2 | note | Inspection/Test Method - Visual Inspection
d3deb857-ec54-5ff4-b372-2d1c7550a744 | note | Record of conformity - This ITP signed by contractors Quality Representative.
08445fb9-ac0e-5b98-acb5-ddee96bb3727 | note | HP*
dd55079d-9325-56c3-88a6-70af477d18fa | note | Responsibility - Project Engineer
de1b3b25-d65b-5a3e-8f1b-5f6f956bb766 | date | Date Completed:
2dbaa836-4882-42a3-8d69-56a60d3525f7 | section | 2.0 - Plant, Tools Equipment
2a54c27f-e103-4279-89a2-fb14750aa0d1 | checkpoint | 2.1 - Plant, Equipment and Tools
45fbe457-ad87-5aa5-9099-8bdcd77489ac | note | Frequency - Prior to commencement.
fab5695c-26e6-5e2e-b29d-21c9a61c85fb | note | Acceptance Criteria - List of all plant, equipment and tools to Contract Administrator prior to commencement of Works.
3a88df02-09e2-51b3-baaf-4c42caf72d4b | note | Reference Documents - Cl 5605-1, WP5605-1
6b6e16cb-fd45-50c8-9418-4fb3f8417481 | note | Inspection/Test Method - Visual Inspection.
081a18bc-d607-5f04-bb48-6c9c6f3bbe18 | note | Record of conformity - List of all plant equipment and tools to be submitted to Contract administrator.
b3168d70-a02e-5c22-92b5-28f20f0e4059 | note | WP
813df316-8e55-57f5-90fb-a5ed24c29c88 | note | Responsibility - Site Engineer
014ff7e0-debe-59c6-9d68-5fc611610a47 | date | Date Completed:
c7634c78-f084-4cc2-b29e-f28593d0911b | checkpoint | 2.2 - Stabilised Calibration and demonstration of spraying equipment
871d072a-33a2-59a9-b8d5-5933f17294af | note | Frequency - 7 days Prior to commencement.
007d38a4-1898-56f0-92be-9c614dcd49cc | note | Acceptance Criteria - The Contractor must demonstrate to the Contract Administrator prior to the commencement of work that the spraying equipment complies with the Specifications.
cc9c406c-d5ac-5ed3-8985-24b82e24398b | note | Reference Documents - Cl 5605-1, HP5605-1
8dbebdb4-435c-52f3-8bd7-14fec3da38a6 | note | Inspection/Test Method - Verify
96fd43bb-ac12-52fe-a399-2cd919b20b60 | note | Record of conformity - Aconex Submission/This ITP signed by Contract administrator.
de301d42-3389-5842-9a9a-90c684419786 | note | HP
1c06fd08-e845-551c-b93b-f10d554541e1 | note | Responsibility - Site Engineer
c94e6401-7a53-556f-a2f1-73cb3949f208 | date | Date Completed:
0fa59cfa-feec-4b27-9c7b-92803ce70e31 | signoff | AUTHORITY HOLDPOINT
1fbe42d1-ec5a-4721-996e-1522a8b235d7 | section | 3.0 - Weather Limitations
71284bcb-1e23-42ad-b51e-364a0e3453e1 | checkpoint | 3.1 - Intention to proceed with works
d72eeb4a-5bad-5417-8bbb-a70a2a47efc0 | note | Frequency - 24 hours prior to commencement of works
61a19d8a-e887-54ec-a5b0-da5cc05cca36 | note | Acceptance Criteria - Written intention to proceed with the Works and on what basis this decision has been made, at least 24 hours prior to commencement of works.
3cb4477d-72e4-5470-8856-56fb04d1d7d4 | note | ○ Application of the rejuvenation material must only proceed when the pavement temperature is above 15 °C and rising.
06259747-5e07-5ebc-80c2-bb700a2064be | note | Reference Documents - Cl 5606-1, WP5606-1
82d3dd21-e36a-54ca-a311-4fb50962674d | note | Inspection/Test Method - Notificatio n
ce0889e9-32cf-5fbc-b58c-a81754b2fb2b | note | Record of conformity - This ITP signed by contractors Quality Representative.
560b1b11-431b-5cf6-8a85-3277d8baac50 | note | WP
0375a004-1c19-523d-8b0b-6dd352d1ea68 | note | Responsibility - Site Engineer
8efe1e37-fb30-5976-bf29-9b0f590377b3 | date | Date Completed:
f4c8328c-3b16-4428-aa5e-40c19459ce3f | section | 4.0 - Preparation of Surface
27cd2ea9-f648-419e-a708-e7658bc1f841 | checkpoint | 4.1 - Inspection of Surface
490edd98-1b8c-53a8-a6a4-92fda5929517 | note | Frequency - 24hours notice prior to commencement of works
75ce3441-355f-5230-b0c4-eacaee5a75e2 | note | Acceptance Criteria - 24 hours’ notice to the Contract Administrator for inspection of the surface to be rejuvenated.
24ddd71c-4825-5978-bb90-76d47aeaee07 | note | ○ Prior to applying the Rejuvenating Material, the Contractor must prepare the pavements surface. This preparation may include but not be limited to:
c786cde6-dbe9-5d2c-b897-2ba45ad414cc | note | — Sweeping those areas of the surface contaminated with accumulations of soil, silt or other foreign and/or loose material.
70029f8d-5585-5b50-b53c-8c8aa1413c28 | note | — Protecting all airfield light fittings and other structures and abutting concrete by suitable means.
2a6fd62f-5b3a-5352-b9d9-01b6d42720be | note | — Protecting all pavement markings by suitable means unless stated otherwise on the drawings.
7e1a24a4-047a-5529-8423-dfb2bdf67d6d | note | Reference Documents - Cl 5607-1, WP5607-1
92a37058-bf3e-5a4a-805e-93b9cbb5d4fe | note | Inspection/Test Method - Verify
7dc2ab5d-a41d-50a0-9e75-56c2013c3620 | note | Record of conformity - This ITP signed by all parties present including contractors administrator
58fa861e-0958-57a8-8d0d-0ea108eb4315 | note | WP
8e1b42fa-ab4f-5528-87a9-5aea927e8310 | note | Responsibility - Site Engineer
2e710d58-b05c-5c03-b26c-440eb3d5140b | date | Date Completed:
35a1927d-2a7a-43b7-bb99-5b07ffa531de | section | 5.0 - Application of Rejuvenating Materials
acc9c28c-3b00-42e6-86a9-431ab8ec0275 | checkpoint | 5.1 - Transport and Storage of Rejuvenating material to site
e15ab493-190a-5717-824d-7cf844f04289 | note | Frequency - 7 days prior to transporting rejuvenating material to site
ecfd8145-b7bc-571a-8153-425a16290494 | note | Acceptance Criteria - During construction, the contractor must submit records on the transport and storage of the material on request by the Contract Administrator.
9ac75f65-37ec-55ae-b54f-95d2e45bad56 | note | Reference Documents - Cl 5608-1, HP5608-1
460d763b-91d0-584a-9f4e-0a5c99342244 | note | Inspection/Test Method - Check
17458c45-8faf-5a57-aa8c-298a9e50e09a | note | Record of conformity - This ITP signed by contractors administrator
e2e65d0b-059d-5c81-92b7-2e85f0e12468 | note | HP
6506edd1-ad3c-570a-9e5c-8814f8c26d75 | note | Responsibility - Site Engineer
5ba3cb1e-6eff-5ddb-a214-6eea772b8e4e | date | Date Completed:
e225fa32-a316-46bf-a7b0-bb99e5739d5b | signoff | AUTHORITY HOLDPOINT
54667830-26d7-43f6-930a-fd5b6b7ea60f | checkpoint | 5.2 - Application of Rejuvenating Material
b3483d85-4bb5-525f-a69c-feb7af5c9c5f | note | Frequency - 24hours notice prior to commencement of works
78437f0c-f0fb-539f-997b-ac487f3061c7 | note | Acceptance Criteria - The Rejuvenating Material must be applied only in the presence of the Contract Administrator. Rejuvenating Material must only be applied using a suitably calibrated sprayer/applicator.
c247450b-bee8-52ce-848c-99c11edb43b0 | note | ○ Before each run is applied, the Contractor must mark out the pavement with removable markings to guide the sprayer when applying the Rejuvenating Material to ensure correct application.
797df7bb-a507-5247-8ace-a11c8c2f8724 | note | Reference Documents - Cl 5608-1, WP5608-1
95685c65-b25b-5855-b3da-4b1785410410 | note | Inspection/Test Method - Verify
8e918f34-7585-5dd4-a110-fe69e254de1b | note | Record of conformity - This ITP signed by all parties present including contractors administrator
9a9f7a3a-a36b-545a-bbff-ac1b9c07a12e | note | WP
6e862f0d-d221-58aa-9346-52d7e24caf43 | note | Responsibility - Site Engineer
79b46588-f5a7-59cd-9da3-b3902c1f72f0 | date | Date Completed:
a3cd644c-52f7-4fbc-85f4-b3e75753ddc7 | checkpoint | 5.3 - Application rate
50b08a10-dc88-5044-96a7-2b39c0df17e4 | note | Frequency - During
3dd11fe5-9a01-5920-8f5f-87cde213da14 | note | Acceptance Criteria - The Rejuvenating Material must be applied at the application rates indicated as per the specification.
650a0efb-19a9-5f85-a6f7-f70300fe8ff7 | note | ○ Application rates will be included in daily record sheets.
18630409-8d68-5e05-9598-c52d6f1f66bf | note | Reference Documents - Cl 5608-1
005fe0ad-a8ca-5145-aae5-779eb42af6ce | note | Inspection/Test Method - Verify
283ea1ec-8458-568d-adbc-b9141dcb567b | note | Record of conformity - This ITP signed by Contract administrator / Daily Spray Record Sheets
bc2cf652-3b4c-5efc-a216-a4082ad83e2f | note | WP
1633ca06-aa21-5a13-9f80-198a61e5af67 | note | Responsibility - Site Engineer
1197930e-5d15-50c3-b2fd-11f4e91b3a55 | date | Date Completed:
b5a3b387-caea-43f8-acc1-b1b685831ab8 | section | 6.0 - Quality Control
8a6105ed-680f-487a-89ff-5c333614d3ab | checkpoint | 6.1 - Application of fuel resistant surface treatment
6bf96c2b-19af-53dd-9857-eae644ef9edf | note | Frequency - Prior to commencement of works
080250d6-6a3c-5179-bedc-b815c3027fb5 | note | Acceptance Criteria - Proposed production and process control testing programme.
2ddb3a1d-654e-540d-aef6-7cf08064181c | note | Reference Documents - Cl 5612-1, HP5612-1
8b19e1e0-97ad-5e45-89cc-4d28a1560b9a | note | Inspection/Test Method - Verify
5c9e1235-30f8-5065-b25b-1d58402b5ef6 | note | Record of conformity - Aconex Submission of PQP / This ITP signed by Contract administrator
8ac4a915-bb11-54b1-86be-b5bb71063066 | note | HP
5150a210-06c0-5234-beb7-5302c511266e | note | Responsibility - Quality Engineer/ Site Engineer
5572d6df-92ec-5bcd-a830-08a2ec89fcfd | date | Date Completed:
b54681f9-0fb6-47ae-a36c-8922e6d45dca | signoff | AUTHORITY HOLDPOINT
572b5d9c-c4ad-4db1-9860-0657808f608b | checkpoint | 6.2 - Test Certificates
3144d9e6-9e62-508b-be8e-8d54fce19566 | note | Frequency - During surface treatment works
43d6ead8-b143-5f1a-bf61-789d7fd09a27 | note | Acceptance Criteria - Reference samples, test certificates, MSDS and technical data as specified for component materials and previous usage of the Rejuvenating Material and sand
8101511f-9a60-5020-9e71-de21717f2a8c | note | Reference Documents - Cl 5612-2, HP5612-2
0d20e940-27f3-56dd-8a35-5c11095bc002 | note | Inspection/Test Method - Verify
d23651b8-1eee-553e-83e9-7cb5acf557f2 | note | Record of conformity - Test Certificate s / Reference Samples / This ITP signed by Contract administrator
14fa980b-7dda-50c1-be0e-91937069a982 | note | HP
476faf2d-5170-59ba-9d20-c2c2b3069f5c | note | Responsibility - Site Engineer
1e41c429-958a-5b5f-b9d6-cacd87e2c77d | date | Date Completed:
5a0d8e8b-52fd-4546-bbc1-641011fd6b0e | signoff | AUTHORITY HOLDPOINT
05c91fc0-2d4d-4a27-9be8-40585c2654fa | checkpoint | 6.3 - Work Method Statement
efa44936-8e93-55f0-955d-3ccc252a78b8 | note | Frequency - Prior to commencement of works
437e9942-2b4f-5d7a-acf5-2bf623790a66 | note | Acceptance Criteria - The Contractor’s work method statement for the processes to be used for the application of the Rejuvenating Material, including surface cleaning/preparation, priming (as required), number of coats to be applied and curing time must be submitted with the reference samples.
aef6b93b-5df6-5c1f-9325-623fc3ce1fbb | note | Reference Documents - Cl 5612-3, HP5612-3
bbd605b1-6ada-59c2-bb41-485d08e92a37 | note | Inspection/Test Method - Verify
e9065638-7be1-5f7d-95d0-c746aae3c93d | note | Record of conformity - Aconex Submission / Reference samples / This ITP signed by Contract administrator
9b32c4e4-bc69-5f3b-b38b-593580b89f85 | note | HP
754eb856-9edf-55ad-9320-8fc9b2315bbf | note | Responsibility - Site Engineer
7a9493a9-e4ba-591b-995c-7ae1229b9fc5 | date | Date Completed:
e0b835b4-38e9-4e0c-9441-bd3be308ffdf | signoff | AUTHORITY HOLDPOINT
8e4cb35b-251f-46dd-b8d9-58d726d6a39e | checkpoint | 6.4 - Lot Submission for Surface Rejuvenation
6a7b1959-b3c7-5bd5-b8a1-5261789408c6 | note | Frequency - Per shift
8c5b9fa4-df2f-5240-93dc-8494cf2c0a3c | note | Acceptance Criteria - Submit detailed information for each shift. Details include application rate, location, test certificates and daily spray records etc.
8af9f627-c199-5b18-b275-337155cd53b8 | note | Reference Documents - Method Statement
2df2e1e5-bafd-5d77-a483-5af42923851a | note | Inspection/Test Method - Review of Lot Submission details
d8a5985b-2913-5d1c-95fb-9d9baeb7d4e5 | note | Record of conformity - Lot Submission document s submitted to Contract administrator
78b593b0-98bb-51eb-870c-37d1a763ec28 | note | WP
dbe9fbf5-dedd-56dd-bad0-0d166985e244 | note | Responsibility - Site Engineer
3d09ab66-4549-5848-b6a9-d19eba69a461 | date | Date Completed:
04838dca-2600-41aa-b896-48edb497fdc9 | checkpoint | 6.5 - Rejected materials and work
c192ba66-14e3-5431-986b-55895ea7e547 | note | Frequency - As required
e3c40430-e3b5-56b2-b8f9-e37f3cdcef3a | note | Acceptance Criteria - Non-conforming materials or areas must be repaired or rectified by the contractor to comply fully with the specification.
85b732f6-30ad-59cd-8f98-57c9457849c5 | note | Reference Documents - Cl 5613
18738f00-41fe-5043-9966-05ddb5b9b50a | note | Inspection/Test Method - Review and verification
506f4256-881a-5759-8544-ed5788ef4157 | note | Record of conformity - This ITP signed by Contract administrator
963de4a7-c07b-59d6-a881-7ad177240d60 | note | HP
6f4725b0-33ae-5cd6-bbb2-b7a4a7938ba1 | note | Responsibility - Site Engineer
16fc5edf-f971-5c8d-92c1-90eddd56a35f | date | Date Completed:
283a4d62-8424-4e09-b5ea-2367ab50b088 | signoff | AUTHORITY HOLDPOINT
cf8d008f-2c8d-4a1b-991e-0136f670cd11 | checkpoint | Final Inspection
3d805f06-8133-54b2-9f12-65e0fcad152e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
649aae02-b8bf-5738-9e39-6657bcaa815c | textbox | Print Name:
ae8c5e26-50ed-5142-9437-79e22b0ed75d | textbox | Position:
86055197-3639-5950-8aad-748648a9633d | date | Work Completed On:
c98ef87d-a187-5e6e-814c-eef67a92d4f9 | date | Date:
6ac3586a-d0b9-4472-843a-6ea3623e3f78 | checklist | FH-927-QU-ITP004 - Cold Planing - Rev 0 | itp | ITP004 - Cold Planing
ea029470-4a5d-4c21-b2f0-396c75b7ad9e | section | 1.0 - Plant and equipment
56ece968-9288-4e27-86af-14e903ac1736 | checkpoint | 1.1 - All cold planing works
65b986b8-e70f-5a95-8ac1-d6dde08b9331 | note | Frequency - At least ten (10) working days prior to commencement of cold planing operations
e824c2a9-6d4c-5303-a23c-40f6378aff0c | note | Acceptance Criteria - List, including details, of all plant and equipment to be used for the cold planing work.
124f3684-64ca-564d-9b52-c9272f486064 | note | Reference Documents - Volume 1: HP3903-1
d74bb5df-2517-5191-ac62-0be20b7ee2e5 | note | Inspection/Test Method - Notification
407a9563-a09d-572c-849e-bed68788bb44 | note | Record of conformity - Aconex Submission / This ITP signed by Contract Administrator
5c2c1cc7-40cf-5b47-b6ea-a2a847868e66 | note | HP
9767e0d1-3265-5aa2-a29a-a64c6f5e9647 | note | Responsibility - Quality Engineer
d77976d3-37a9-5917-8703-e521e048da12 | date | Date Completed:
3223ee95-af92-47b7-8a88-950fed3e5b7b | signoff | AUTHORITY HOLDPOINT
97fc56f9-57fa-4647-81c0-6f958610ebeb | checkpoint | 1.2 - Contractor's check that cold planing plant in full working order
2f6dbeff-6fec-5777-81f3-6ddf4f1e593a | note | Frequency - Prior (60 minutes)
41e33686-3e6c-5951-83e8-2cb6ff312df8 | note | Acceptance Criteria - 1. Notice of the commencement time of the Contractor's cold planing plant verification process
8b4a0ca7-565d-5d2a-b78f-550f04703b48 | note | Reference Documents - Volume 1: HP3903- 2.1
f5e53ac0-a528-5ac5-a5c5-fc66e39aa0b8 | note | Inspection/Test Method - Verify
9d825650-d6a9-5936-8430-bc0cbcb31e73 | note | Record of conformity - This ITP signed by Contract Administrator
8827771b-8cc2-55dd-b86c-a3c1e7af07ea | note | HP
25a1e1bd-8859-5456-a924-9e68d7109acb | note | Responsibility - Quality Engineer
560fa061-5e5f-5488-a3ca-52f8c420b390 | date | Date Completed:
ecb50d83-4133-4a2d-ab99-0aedc9f92bde | signoff | AUTHORITY HOLDPOINT
e5671e29-7e9b-409d-8c89-37d4d6230931 | checkpoint | 1.3 - Cold planing plant in full working order
f86f26f7-dff1-56f7-893a-40d24f2c2442 | note | Frequency - Prior (60 minutes)
dceb69fe-0843-5693-bb9c-4b5d5c1423fe | note | Acceptance Criteria - 2. Copy of Contractors’ cold planing verification checklist at the completion of check prior to commencement of each work period
8e1e7111-051e-51c1-8698-e2206c905d0a | note | Reference Documents - Volume 1: HP3903- 2.2
21a33649-6f47-5977-959b-c68b12ad1eff | note | Inspection/Test Method - Notification
c74edf1d-7953-5317-afba-cb5419302335 | note | Record of conformity - Submission of Daily Prestart Records / This ITP signed by Contract Administrator
79100767-fab4-56ce-8459-3c5578a02fb7 | note | HP
b664c168-d148-5f57-bd28-5ef3b1e63986 | note | Responsibility - Quality Engineer
438d4dad-a561-563c-98e7-444ebe489b25 | date | Date Completed:
dd5ae327-44d1-489b-b347-de1443e0ca9e | signoff | AUTHORITY HOLDPOINT
dc8ae8a9-0542-459e-98a1-28ba4f7a1268 | section | 2.0 - Cold Planing in Advance of Asphalt Work
83c45c77-f43e-482d-a76c-6833aebe3e11 | checkpoint | 2.1 - Cold planing in advance of asphalt overlay work: Area closed to aircraft traffic.
afc7eee6-bd3a-5b84-b2a8-014a226a39ee | note | Frequency - Prior (10 working days) to commencement of planing works
7b359933-00a9-5443-a36c-c77477a62081 | note | Acceptance Criteria - Proposal to Contract Administrator to texture, profile and mill in advance of asphalt work including complete program and plan of texturing, profiling and milling and asphalt overlay work proposed in the work area.
8423a013-0170-50ee-8c5d-1296553e2ca5 | note | Reference Documents - Volume 1: HP3904-1
915a47c9-7696-56b0-afe8-749868919af1 | note | Inspection/Test Method - Notification
4a1bdd4f-d778-57a7-be78-0088aa4174ea | note | Record of conformity - Submission of Shift Plan / This ITP signed by Contract Administrator
aac5be45-0894-52c0-bbcf-aa49cced4c84 | note | HP
73f14a28-7d9f-5049-b0f8-83551a4008c0 | note | Responsibility - Quality Engineer
8dd1f1be-06bc-579e-87ad-bd9601e083e9 | date | Date Completed:
05ce69ab-40db-4c79-a7ae-b6b3a364aef9 | signoff | AUTHORITY HOLDPOINT
2c90c988-8f58-4e36-be4e-614c06a81dd9 | checkpoint | 2.2 - Cold planning in advance of asphalt overlay work: Area open to aircraft traffic.
89ea38ed-30c5-5d58-a294-9c8d3ac19d78 | note | Frequency - Prior (10 working days) to commencement of planing works
5dc87b4f-681a-58ad-a782-e1028bd5fa6b | note | Acceptance Criteria - 1. Proposal to Contract Administrator to texture in advance of asphalt overlay work including date of demonstration and detailed program of texturing and asphalt overlay work in the work area
40c48bb7-98a9-5480-ab6d-79446473350f | note | Reference Documents - Volume 1: HP3904- 2.1
bfb7d62c-a43c-5237-b0b5-8b4f252296cb | note | Inspection/Test Method - Notification
18736951-116d-5391-81f7-303bed724d3b | note | Record of conformity - This ITP signed by Contract Administrator
ba21795c-f16f-55fe-b30f-e9184329954e | note | HP
56967bc8-d6e8-5eba-86f0-8f202b3ae6fe | note | Responsibility - Quality Engineer
22362919-b47d-5000-a50c-ec7a9419faf6 | date | Date Completed:
0e3cd6d5-c769-4514-b1e0-a49b3328b356 | signoff | AUTHORITY HOLDPOINT
8278a25d-d885-4027-94e4-222d54a174ef | checkpoint | 2.3 - Removal of cold planing and asphalt paving equipment from work area
a24d689b-5041-5275-9d13-9a195d3738bf | note | Frequency - Before textured surface is opened to aircraft traffic
d0e81f79-a9d3-5323-af75-658d77502ce2 | note | Acceptance Criteria - Inspection between Contractor and Contract Administrator of textured area.
228d95c7-2042-5142-8247-6054495269ca | note | Reference Documents - Volume 1: HP3904-3
7b8350e9-1ccf-5254-a98e-31b062fdc8ba | note | Inspection/Test Method - Verify
bc47a563-32d5-5d49-a72b-89c106018eb0 | note | Record of conformity - This ITP signed by Contract Administrator
0bea37cf-ff56-5b79-a3f4-05d296bb3214 | note | HP
adeadbc7-a313-5baf-90d7-e85c56af052d | note | Responsibility - Quality Engineer
7a4fa75d-cec6-58b6-b534-d9c4aaf8454b | date | Date Completed:
f0ae4694-2975-4945-998a-53052144e820 | signoff | AUTHORITY HOLDPOINT
06633a22-78c7-4102-a0f5-4592efc6923d | section | 3.0 - Restrictions on Cold Planing
e7e8b6b2-8cbf-4790-89a8-255bfd96ab97 | checkpoint | 3.1 - Commencement of cold planing works
61c54e79-13e5-5d77-aff9-b1ec55aac8e7 | note | Frequency - Before the commencement of each working period
404df789-5422-5814-9444-2eede388e00c | note | Acceptance Criteria - Written notification to the Contract Administrator that all plant, equipment and labour, including that required for the placing, compaction and finish of asphalt, are available and ready on-site and supply of asphalt for the work is confirmed even in the event of an unexpected breakdown of the asphalt mixing plant.
913d21e0-7077-54eb-bc12-6ab181818ea9 | note | Reference Documents - Volume 1: HP3905-1
31cc9cb6-92f8-5cdf-8e36-d39a2f664e8e | note | Inspection/Test Method - Notification
63557213-04a0-5c4d-aef9-f2bcf695b0f3 | note | Record of conformity - This ITP signed by Contract Administrator
589e7315-793d-5889-9422-ce19f0db3383 | note | HP
20002462-f467-5f40-94c3-9fe7bce0735a | note | Responsibility - Quality Engineer
84210763-bc1d-5211-9197-447148b39293 | date | Date Completed:
33ab8b22-ac22-46b1-9465-a355dec9a635 | signoff | AUTHORITY HOLDPOINT
52dd7f7a-1bc2-45b1-9c4c-c08e623bb0a1 | section | 4.0 - Performance Check at Commencement of Work Period
5c8a7a09-7e5d-4aab-b6a0-eff6745d46ba | checkpoint | 4.1 - Check that planing machines producing compliant surface
0441768f-767e-5593-9d1f-9c1145fd662f | note | Frequency - Prior (30 minutes)
d94375ee-2a0f-519b-a189-87bc5556533a | note | Acceptance Criteria - Notice to the Contract Administrator of the commencement time of cold planning
a2296c43-b838-5d17-9a90-15f93065d73f | note | Reference Documents - Volume 1: WP3906-1
7f9b6b4a-2d31-5286-950a-877485fb93c6 | note | Inspection/Test Method - Notification
eef1bf63-b7f4-523a-afde-61505c30e0f3 | note | Record of conformity - Submission
88107878-4967-5c69-a57f-eb6d99b0d9fa | note | WP
2047fb4e-0eca-5a2a-bbf2-ddb2251e9700 | note | Responsibility - Quality Engineer
fd96eeb3-ef39-558b-b27c-08040ea24d5b | date | Date Completed:
410b78ad-f109-4ea3-a393-0d553724b2b4 | section | 5.0 - Texturing
03c726e1-57d5-441c-a88f-0d473e462398 | checkpoint | 4.1 - Commencement of application of tack coat and asphalt paving
f93380da-3c60-5779-b230-fe9008af490a | note | Frequency - Prior (30 minutes)
f0c0e942-ff74-54c4-9de0-00d86755e99f | note | Acceptance Criteria - 1. Notice to the contract Administrator of the scheduled commencement time of Contractor's inspection and checking of the textured surface of the texturing trial.
8b6a2303-6b5d-5de8-9dde-f47b58daef0d | note | 2. Statement of compliance signed by the Contractors’ PQR that the textured surface in the texturing trial complies with the specified requirements
6132b647-e024-5884-8db4-aec0b8c4af4d | note | Reference Documents - Volume 1: HP3907- 2.1
064d0583-bfae-58eb-ab5f-d224297652c6 | note | Inspection/Test Method - Notification
5090beb4-57af-509c-94bb-3457da606774 | note | Record of conformity - This ITP signed by Contract administrator
946468c5-b805-5c9a-aab6-abb3bf9283ed | note | HP
c7c755a0-851b-5a18-bcbb-a7ac68ae53b8 | note | Responsibility - Quality Engineer
0a90d577-4188-552d-a9db-33a456af2c48 | date | Date Completed:
fd1e1ec4-73b8-41bb-ad57-8a6d1e8a9d74 | signoff | AUTHORITY HOLDPOINT
f71d867d-cf58-47a8-b28c-fc9a4294e438 | checkpoint | 4.2 - Commencement of application of tack coat and asphalt paving
d679ad3d-a3da-5c94-ab87-d4a80f66482a | note | Frequency - Prior to application of tack coat
81a5a226-7131-50c2-adcc-65a1915b47c6 | note | Acceptance Criteria - Written agreement by Contractor, including photograph and typical measurements of the Texture Reference Area
41b81d1f-02ff-5d4a-be79-f7a9b198081e | note | Reference Documents - Volume 1: HP3907-3
377134ca-449f-53da-93fe-e22388f582c4 | note | Inspection/Test Method - Notification
cdcad977-6820-5d3c-9429-6973861b468e | note | Record of conformity - This ITP signed by Contract administrator
469bf1fb-f839-5c38-b9d8-27e68fa046c9 | note | HP
b595edca-ed0b-5a54-96b6-ed7b15a05dd7 | note | Responsibility - Quality Engineer
7a36fbb3-d0f7-5c16-a547-ceaef23acf45 | date | Date Completed:
79bdd867-cb3f-42c9-997b-70e117fc607a | signoff | AUTHORITY HOLDPOINT
74b0a6ed-057a-4d18-9bd6-64502df531f1 | checkpoint | 4.3 - Removal of application of cold planing and asphalt paving equipment from work area
caaed5c4-0260-5dd8-9382-fedbb9f4254f | note | Frequency - Prior (minimum 60 minutes)
f0206aa9-aa01-5710-9782-d51387c179a3 | note | Acceptance Criteria - Notice to the Contract Administrator of Contractor's Inspection of completed textured surface and, statement of compliance of textured surface with specified requirements signed by contractor’s PQR
2b04079d-8443-5f86-a5f3-eaa65ab5e25a | note | Reference Documents - Volume 1: HP3907-4
6702a828-bbb7-5f75-892e-9711631de67d | note | Inspection/Test Method - Notification
471eaeff-82ba-513b-9748-c1cf98d76c35 | note | Record of conformity - This ITP signed by Contract administrator
d817cddc-2127-5cdf-9052-380239065d45 | note | HP
765da35b-7441-51ff-bc99-97884964538d | note | Responsibility - Quality Engineer
0fffa46f-c4a8-5d85-85c7-055a6626e86c | date | Date Completed:
9c4a3592-ba77-47f2-981d-887434523bdb | signoff | AUTHORITY HOLDPOINT
39acdceb-d1d3-4805-96b3-8aaf4a5cc051 | section | 5.0 - Profiling, Miling and Cleaning of Cold Planed Surfaces
9792884e-4b23-4a6c-a61c-161de0346b97 | checkpoint | 5.1 - Removal of planing and cleaning equipment from site
55a8927b-3789-5e43-9d32-d570d5ddad57 | note | Frequency - Prior (minimum 60 minutes)
a172cef5-d831-5f40-9295-8acd3eae9c6f | note | Acceptance Criteria - Notice to the Contract Administrator of Contractor's Inspection of completed profiled surface and, statement of compliance of profiled surface with specified requirements signed by contractor’s PQR
7d6bb1cb-f325-5c9f-a9ef-086f0abb6b55 | note | Reference Documents - Volume 1: HP3908- 1
d8fbd496-3b74-515d-868e-521046aa6ce6 | note | Inspection/Test Method - Notification
80ae0136-6f30-5176-b43d-9fcc91a21ef3 | note | Record of conformity - This ITP signed by Contract administrator
c70f912a-1023-5787-9b9d-82eb4951f25f | note | HP
5177fce9-1ba4-5045-a32e-6e64a1176da6 | note | Responsibility - Quality Engineer
0fdc9785-a0a7-5ebc-9b95-a83c2d9931fe | date | Date Completed:
e24d278f-944e-4101-af43-0e8135b9def3 | signoff | AUTHORITY HOLDPOINT
f90aaa04-6a52-4c8d-9720-3b774f166056 | checkpoint | 5.2 - Removal of cold planing and asphalt paving equipment from work area
fc24761e-6832-5563-84d4-00b4fc3c53a7 | note | Frequency - Prior (minimum 60 minutes)
80bf26a3-ec6f-5479-a5c8-e62566246d2c | note | Acceptance Criteria - Notice to the Contract Administrator of Contractor's Inspection of completed milled surface and, statement of compliance of milled surface with specified requirements signed by contactor’s PQR
610e4946-97c5-5001-bc90-4bce28b83374 | note | Reference Documents - Volume 1: HP3909- 1
d85a27ec-80cf-5ea6-9e81-7c232892f14e | note | Inspection/Test Method - Notification
831781d5-cb79-59ca-9d0f-36e096ce52ae | note | Record of conformity - This ITP signed by Contract administrator
31decac4-f5c5-5c22-8b33-5c3119913c36 | note | HP
5a9e79b6-6268-508d-b6ff-2f83cf642d3b | note | Responsibility - Quality Engineer
a084521c-9cbb-57dd-934d-4257abae560d | date | Date Completed:
e64d7dbe-7279-413f-a872-0a3114834ef1 | signoff | AUTHORITY HOLDPOINT
318ed062-024e-4266-b405-6ee486a4f63b | checkpoint | 5.3 - Cleaning of entire cold planned surfaces of asphalt
1e0fb155-7b9c-58e1-a135-6c47b45176fb | note | Frequency - Prior (minimum 30 minutes)
46e0f679-6278-57a3-b350-a97e7fc2e9ad | note | Acceptance Criteria - Notice to the contract Administrator of commencement of cleaning of cold planed surfaces of asphalt
b8572e6c-c17f-5a92-a839-6829c3953f51 | note | Reference Documents - Volume 1: WP3911-1
88bad2f4-e16c-5ee9-a454-a2225877e051 | note | Inspection/Test Method - Notification
21885a12-e9af-59e6-bbd9-4d9e192980a7 | note | Record of conformity - This ITP signed by Contractor
7bfd38ab-2bea-5518-8d2e-b550062b6563 | note | WP
692a0649-fd2b-56c7-9453-f63a6eac5ac8 | note | Responsibility - Quality Engineer
b4fed396-863a-5c15-ae8d-e992a968abe7 | date | Date Completed:
8c23502f-e5e9-4e89-b27a-af1f98b6f0da | checkpoint | 5.4 - Tack coat and placement of asphalt over cold planed surfaces of asphalt
77d56dd5-8997-5668-8713-4210d61ffa99 | note | Frequency - At completion of each cleaning working period
d0d42760-ddcd-5a73-b6db-c53ae5cac733 | note | Acceptance Criteria - Statement signed by the Contractor's PQR that the whole of the cold planed surfaces of asphalt have been cleaned as specified
36ecb701-e283-59e9-8324-1c0f34010cbe | note | Reference Documents - Volume 1: HP3911-1
7a32c944-8717-5084-b2ef-2964a9dcab73 | note | Inspection/Test Method - Notification
45d8380e-da23-5c83-8bdd-3578c8853a0c | note | Record of conformity - This ITP signed by Contract Administrator
1d662f22-a43f-5e94-97b9-f85f3dbaa3bc | note | HP
546617c6-89f2-5b1f-9781-b79bdecfe852 | note | Responsibility - Quality Engineer
30d3998d-a47e-51f7-914a-a87153b8bb1b | date | Date Completed:
b4fdc53e-2cc2-43ac-aa53-5386d54bc15e | signoff | AUTHORITY HOLDPOINT
353bb9a4-6f49-46ef-b977-12c6cf6d9578 | checkpoint | 5.5 - Removal of Waste
d79ef7a5-099e-5455-897b-953a8a9cb632 | note | Frequency - As required
a4a7f09b-6380-5940-99fd-2409f00d8691 | note | Acceptance Criteria - All asphalt removed from pavements by cold planing will become the property of the Contractor and must be removed from the site and disposed of by the Contractor.
f32b54a1-0f19-5fd3-8c7e-15dc20e7bb9b | note | ○ Stockpiling and material disposal requirements to be confirmed and authorised with Contract Administrator
54380ef5-2c2f-5c4f-b773-02c446df6c55 | note | Reference Documents - Volume 1: 3912 and Volume 2 SP3912
faeb0094-65be-5600-a29c-e7938fe0d7ec | note | Inspection/Test Method - Inspection
6f8abbe4-ce64-5765-92e4-82dcd3b92cd0 | note | Record of conformity - This ITP signed by Contractor
0fe53466-a516-587f-9fd4-7284e350987e | note | IP
e7d0b7cd-03e1-506d-9146-e09ff1a564d9 | note | Responsibility - Quality Engineer
ecde1828-5f24-5bbd-84bb-2b31e74633d4 | date | Date Completed:
b8be134e-5369-4858-82de-26c9da7bee8b | section | 7.0 - Survey of Cold Planed Asphalt Surfaces
69b234bf-e9b5-4d24-a2e7-fed67db76276 | checkpoint | 7.1 - Placing of asphalt over cold- planed asphalt surfaces
8614325e-71b2-57d6-ba8a-a836f3811bed | note | Frequency - Prior (30 minutes)
076db706-e5f4-5903-91ba-755521bac87e | note | Acceptance Criteria - Survey of cold planed asphalt surfaces and determination of overlay thicknesses for asphalt thickness control, and Notice to the contract Administrator of commencement of survey
63b35289-2d9e-55b2-be20-c131a232fcbb | note | Reference Documents - Volume 1: HP3913- 1
33c5343f-214f-5e09-9a27-6258ca39ea07 | note | Inspection/Test Method - Notification
1d2aa705-71e5-59ae-b51f-7536c4752aa1 | note | Record of conformity - This ITP signed by Contract Administrator / Submission of Survey Records.
e6c17ec6-70bb-5bfc-bb1b-a71edb0ef8e3 | note | HP
e8237c23-41b2-5e07-8436-8049456954d9 | note | Responsibility - Quality Engineer
e4a50348-683a-5a02-867f-23d146c6361b | date | Date Completed:
c2e6ab1d-2960-47bf-92ec-733757904456 | signoff | AUTHORITY HOLDPOINT
76b0e715-3585-44dc-af70-328c5c97917e | checkpoint | 5.9 - Lot Submission for Cold Planning
10211427-3e9d-51a2-afdc-722c1bd40097 | note | Frequency - Per shift
b132dc1d-6739-5018-9570-cdd729489683 | note | Acceptance Criteria - Submit detailed information for each shift. Details include location, test certificates etc.
2b12618a-eb92-59b3-8f85-4cd056e35442 | note | Reference Documents - Method Stateme nt
d0018771-3d04-5e58-9c12-ed1b24b35937 | note | Inspection/Test Method - Review of Lot Submission details
7b815e96-3bc6-5c86-8b7e-a89b9d6eee7e | note | Record of conformity - Lot Submission documents submitted to Contract Administrator
c38ae2ce-18e4-516e-9b78-f12a2ee777a2 | note | WP
c4534f59-2ff6-5779-84e4-b1babec74c5c | note | Responsibility - Site Engineer
fd82f616-bede-553a-b046-bc60ee4e6365 | date | Date Completed:
5c2fcf7f-b2fb-4ae1-9d2c-993ad41b80a2 | checkpoint | Final Inspection
e4caba04-50d9-5589-a881-ad25c79c07a3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
20150ecf-6d69-52e6-89be-e6c773c07833 | textbox | Print Name:
9fa1377d-7366-5391-8c79-d02e38beceae | textbox | Position:
e177c2b4-30f3-5273-b7de-1eb4550a6c91 | date | Work Completed On:
90c1a333-6205-54cb-a4a9-48adc4939b56 | date | Date:
0d4674af-433d-46a6-802f-437927cda28e | checklist | FH-927-QU-ITP005 - Asphalt Placement - Rev 0 | itp | ITP005 - Asphalt Placement
d46d1d67-272d-4888-8ad0-c5677477d87c | section | 1.0 - Paving Plant, Tools and Equipment
a984a4ea-f28e-4b9e-b50e-037420cf6455 | checkpoint | 1.1 - Commencement of any work period
191cf676-f3b6-5857-844d-92a6bc17fddb | note | Frequency - Prior to commencement of any work period
56f65278-b585-5ae8-8169-84a747d46054 | note | Acceptance Criteria - Prior to movement of any plant on to site of works, submission of daily plant inspection verification checklist
3348fe40-9fab-5c41-a5d9-c622709e5c24 | note | Reference Documents - Volume 1: HP-5113-1
3de3727a-e383-5ca4-b0fb-f58e7b83bd47 | note | Inspection/Test Method - Submission
7875e704-22a0-521b-a60d-fedfb02e83e9 | note | Record of conformity - Plant Inspection verification Checklist
8558d2a7-c8ad-5be0-b634-ea3390f17f10 | note | HP
d8ae45fb-2264-5e0b-abf4-5da52f8e2712 | note | Responsibility - Construction Manager
93fa0da0-ff90-5fb1-9e65-75468202e7dd | date | Date Completed:
899641eb-eed8-4f11-8ddc-d09da21895b6 | signoff | AUTHORITY HOLDPOINT
955692d1-5b37-42d2-8cd1-6209db456a13 | checkpoint | 1.2 - Asphalt Haul Trucks
cdc93efa-710d-5b41-a2a4-2e8d88e35928 | note | Frequency - Each Lot
377088f8-3cdb-5319-bbd7-41444e5b8003 | note | Acceptance Criteria - All asphalt haul trucks must be suitably equipped to avoid spilling the mix in front of the asphalt spreaders. The internal surfaces of the truck bodies must be smooth, clean and uniformly coated with a suitable release agent (nonpetroleum based material) to prevent adhesion of the mixture to the bodies.
7e478f08-6f79-5487-bec5-9f582cdca6be | note | Reference Documents - Volume 1: Clause 5113 (e)
49d9b6a7-202d-54c3-8d88-2a72fed802d0 | note | Inspection/Test Method - Verify
cb2ebe31-3ba5-5c66-919f-67727188bf3e | note | Record of conformity - This ITP signed by Contractor
5f1bd9d2-6b23-5398-9db1-374626e310c0 | note | IP
8752d358-fbfb-5251-9ca5-aeb86cf8b835 | note | Responsibility - Construction Manager
9644b783-c4c0-5ed9-bf38-34724a24f1f0 | date | Date Completed:
5e1f5c0c-8ead-49c7-875a-6ee366a6d63d | checkpoint | 1.3 - Asphalt Spreaders
522cbcca-f300-583f-b336-660340b7cd37 | note | Frequency - Each Lot
484961f8-356e-5505-88c5-a46c98b1ef7a | note | Acceptance Criteria - The spreaders must be a self- propelled mechanical device designed for spreading, screeding and compacting hot asphalt and having a capacity to complete the planned works within the time available in a paving shift. Specific details are shown in clause 5113 (f)
4b4cc7a5-0ec1-5371-b3be-f05345cccb05 | note | Reference Documents - Volume 1: Clause 5113 (f)
99d9ead6-48ea-5aca-9b10-1746dba7ac4d | note | Inspection/Test Method - Verify
206493b0-643d-5589-af0d-a9f04d414f3c | note | Record of conformity - This ITP signed by Contractor
4a1e9777-f68a-5103-9aed-01b35cb6bdf1 | note | IP
aea2b36c-dd78-516f-9233-6eb23c8171f5 | note | Responsibility - Construction Manager
7ae8d1f8-b271-566c-ab42-287d9c99cbd7 | date | Date Completed:
ceaae0b5-3920-462d-868e-667592a9eeef | checkpoint | 1.4 - Steel Wheel Rollers
cedf9219-b91e-5273-83e6-980ceabd8533 | note | Frequency - Each Lot
5f3377a0-4174-5687-a577-7aa1bf37407c | note | Acceptance Criteria - Steel wheel rollers must have an all up mass between 6 and 11 t.Vibrating steel wheel rollers must have two (2) vibrating drums each of which must have a roll diameter and width of not less than 1.00 m and 1.37 m respectively, a static mass of at least 2.8 t per lineal m of width of drum, and a dynamic loading intensity under operating conditions of between 4.2 t and 6.8 t per lineal metre of width of drum. When operating in the vibrating mode the amplitude must not exceed 0.5 mm and the frequency of vibration must not be less than 2700 cycles per minute
b849ec28-38f8-53cb-8301-56b7c70a5141 | note | Reference Documents - Volume 1: Clause 5113 (h)
1286a14d-4267-52d7-9a74-170944880452 | note | Inspection/Test Method - Verify
74d42838-f488-5af6-aaa9-5a266797974c | note | Record of conformity - This ITP signed by Contractor
831730a3-c15a-57fb-a261-74313b1f8d21 | note | IP
2886094f-edb7-5868-830f-0c2a3f93e287 | note | Responsibility - Construction Manager
85217231-3fa2-5668-be82-722b6aba7a51 | date | Date Completed:
7a3036a6-3b0b-4658-947b-faa82381cd36 | checkpoint | 1.5 - Pneumatic Tyre Rollers
51e0a4a9-2a77-5bb1-b740-2f068e7bd720 | note | Frequency - Each Lot
22261c52-9ea1-5722-84ae-da68ac2bc8eb | note | Acceptance Criteria - Medium pneumatic tyred rollers must be rollers having an all up mass of not less than 18 t and wheel loads of not less than 2.5 t. The tyre pressure must not be less than 850 kPa.
efe1a935-9489-519f-bf48-6dbdf006b924 | note | ○ The application of water, soaps or propriety additives to the tyres must be the minimum necessary to prevent adhesion /pick- up of the mix.
2701af06-9745-53d3-81e8-864b573bd338 | note | Reference Documents - Volume 1: Clause 5113 (i)
d9125568-ca1e-5cb9-a2cb-18d869197bc5 | note | Inspection/Test Method - Verify
90349019-10ae-5666-9a6d-7cda0a9f631f | note | Record of conformity - This ITP signed by Contractor
09d2d22c-e790-56ef-acdf-86d42214e03d | note | IP
2d5d71ab-36d1-5ec8-b524-f74858cc2f8c | note | Responsibility - Construction Manager
2a219c36-0e88-5168-85c9-f76313692b51 | date | Date Completed:
d3572c83-146b-4025-aa94-09315690f987 | checkpoint | 1.6 - Edge Compactor
28b89179-abb0-59e9-a3ee-7270333289af | note | Frequency - Each Lot
2c723179-1f40-58ee-b398-df734bd86b3d | note | Acceptance Criteria - At least one steel wheel roller must be fitted with an edge compactor capable of compacting joints and edges of newly placed asphalt between vertical and 45° to the vertical, without dislodging or disturbing the material forming the joint or edge.
5f06dd43-49b5-5095-be58-000548d3cda4 | note | Reference Documents - Volume 1: Clause 5113 (j)
11e664c7-5c02-5bf8-9c19-362e9473872f | note | Inspection/Test Method - Verify
72c04a0a-8029-5c39-b1b0-c42075a8e79b | note | Record of conformity - This ITP signed by Contractor
f172fdd8-2c85-5e48-88db-ab4e73383a8e | note | IP
6af27d6c-09d0-5372-9f97-29f74b6a4de7 | note | Responsibility - Construction Manager
ddc49bf7-ba80-526e-bc4e-2fb5c41d2c13 | date | Date Completed:
f98c9dee-69a6-46d0-97ee-f81553f02b61 | checkpoint | 1.7 - Mechanical Brooms
07cddbe8-ad64-50ff-838c-17f8081a98df | note | Frequency - Each Lot
d57e6c7a-5217-5104-92f8-c2aeaf65d658 | note | Acceptance Criteria - Mechanical brooms may be skid steer loaders capable of being fitted with both a bucket and a broom/bucket combination.
8afb672b-5e6c-5b47-b6be-4785e309cb36 | note | ○ All brooms/broom stocks must have non-metallic bristles.
a3b7ae33-ced8-5618-b62e-5f9c7cd01227 | note | Reference Documents - Volume 1: Clause 5113 (l)(ii)
57ce0d9b-2439-5a6c-bd92-7efe2f93f8ea | note | Inspection/Test Method - Verify
1098f787-7f2d-55e2-8814-4618f8fe2d89 | note | Record of conformity - This ITP signed by Contractor
2b20818e-a90d-5592-a215-c6e1ca18a73c | note | IP
ea39445d-358f-5426-b014-7c6f9d21d392 | note | Responsibility - Construction Manager
af38b45a-2a30-5de3-a656-c8c025716c68 | date | Date Completed:
d72e773b-7061-422d-8eb3-fc1a51a7d8b0 | checkpoint | 1.10 - Vacuum Sweepers
eb063583-ffd5-5730-9e86-06eac72d1f39 | note | Frequency - Each Lot
8b10722a-4799-5278-8ac9-f298a7f45795 | note | Acceptance Criteria - At least one (1) vacuum sweeper must be a machine purpose built to vacuum clean a width of pavement of at least two metres per pass with no reliance on brooming for lateral collection of material. Airfield Schwarze sweepers manufactured by Schwarze Industries Australia, or similar approved, are suitable.
b2fa5093-03af-5873-b9c0-15e5f3c6a62e | note | Reference Documents - Volume 1: Clause 5113 (l)(iii)
bec6c791-2257-5d47-9132-bd1f3161c64c | note | Inspection/Test Method - Verify
ed064d0e-a51f-5829-ac4d-0007aef3c396 | note | Record of conformity - This ITP signed by Contractor
27bd828c-3da0-5fc9-9738-95fe14835e22 | note | IP
fb9c97e3-9a88-5114-b571-04d26ed15af5 | note | Responsibility - Construction Manager
0be0fd31-b4bd-5e05-8865-12a972034c6b | date | Date Completed:
d6601552-5e81-44c9-9355-0061320cfeeb | checkpoint | 1.11 - Coring machine
59acdfab-9393-5c52-9d54-a784e0d3217c | note | Frequency - Each Lot
d47c75bb-8114-535c-8fde-ccabdaf7994d | note | Acceptance Criteria - The coring machine must be easily portable and capable of rapidly cutting clean 100 mm or 150 mm diameter cores from the finished courses of asphalt in accordance with the requirements of AS 2891.1.2. The core drills fitted to the machine must be either diamond tipped or carborundum types.
240c1c71-65c1-52e4-927b-63dd7206b62a | note | Reference Documents - Volume 1: Clause 5113 (n)
2a189e7d-80c6-53f7-9ed0-b3ac7cc38e86 | note | Inspection/Test Method - Verify
c1d2fe5e-d93c-5248-8846-42ee978981c7 | note | Record of conformity - This ITP signed by Contractor
91598aa9-093c-5578-ac79-61966dac4215 | note | IP
ef667fc9-1b5c-50b4-9b62-498b3ade0079 | note | Responsibility - Construction Manager
77220eee-e5f4-5124-8781-d6cd8c100c4c | date | Date Completed:
3c9b1c9c-cba7-42c6-8445-3137563afd0f | checkpoint | 1.12 - Manual Straight Edge
ecaf0f3f-2bda-5f25-846d-8cfd2804cdad | note | Frequency - Each Lot
ce300aec-b05d-58bf-8f56-975483c7e2da | note | Acceptance Criteria - Not less than 1 hand held straight edge must be provided for each operating paver to facilitate the location of defects in the smoothness of the finished surface. Straight edges must be constructed of a material and in a manner that ensures rigidity and accuracy, and must be 3.5m long and must be placed directly onto the mat.
43888188-7465-56a9-b49c-2b76c20c7594 | note | Reference Documents - Volume 1: Clause 5113 (o)(i)
97b43e25-6c09-524a-8d7b-0a52865d4dc2 | note | Inspection/Test Method - Verify
74fd8f98-d003-5c3b-bc1e-bd632fddb9e4 | note | Record of conformity - This ITP signed by Contractor
d415b926-6445-5510-8c3c-44b6ff15b34c | note | IP
b6dd71d5-673b-5f00-be66-55b0efa51484 | note | Responsibility - Construction Manager
cbc780a9-aa24-5764-9d78-0bded4e9c81c | date | Date Completed:
6b7c9172-b6b0-4b43-9987-f2804019ea06 | checkpoint | 1.13 - Hand tools
37dd9ff0-e261-593e-aba1-e3ba308033fb | note | Frequency - Each Lot
ebeacdc3-f430-5669-8cc8-92d900853d00 | note | Acceptance Criteria - Hand tools must consist of wooden spreaders, shovels, steel lutes and tampers, hand brooms, a portable heater for heating tampers, hand held blowers and any other hand tools as may be required.
5708113c-9b95-51cd-b338-203e1f29e05a | note | Reference Documents - Volume 1: Clause 5113 (p)
a4d85563-875e-5fad-b34e-538a866be9f3 | note | Inspection/Test Method - Verify
67a907e9-df90-5119-8ba4-d97a4aa55767 | note | Record of conformity - This ITP signed by Contractor
6e737f17-6878-5083-ab0b-1a35de072964 | note | IP
ee4e3149-1c8d-574b-a88d-ed5ba5adc437 | note | Responsibility - Construction Manager
0e19f23d-dcc4-5618-897b-72e5f3ef725c | date | Date Completed:
9efb9778-561e-49c0-b398-bee0d282335c | checkpoint | 1.14 - Thermometers
82ea6767-9242-5bcd-9faf-8002a38799ce | note | Frequency - Each Lot
f01d270c-e600-5be2-a902-d11bc0451c13 | note | Acceptance Criteria - The Contractor must provide one calibrated immersion stem thermometer (0 - 200 °C) and one calibrated pavement surface thermometer (bi-metal or infra-red), (0 - 200 °C), with each operating spreader. The thermometers must be held on site at all times when asphalt is being placed.
4f34b5d6-c01c-53ab-80d4-ac5ed573c388 | note | Reference Documents - Volume 1: Clause 5113 (q)
7d72b759-a946-59b9-949e-747a73c93ee6 | note | Inspection/Test Method - Verify
b97e5341-5fe1-5f5b-a597-249fa9096f29 | note | Record of conformity - This ITP signed by Contractor
84b33dfa-fe14-53ae-b21d-9784a16029f9 | note | IP
ab9f1977-9df4-5270-ab42-862f1e0d3782 | note | Responsibility - Quality Engineer
17593f6a-a5f7-5e76-ac1d-987e7b3667ef | date | Date Completed:
e32d09e0-a223-4ddb-911a-5c1d3c4ca003 | section | 2.0 - Weather Restrictions
153efa1a-8a88-43d4-bed4-18d3f4aa1442 | checkpoint | 2.1 - Weather Restrictions
c6a461ae-ce44-5f10-98e8-17f69cd6fc3c | note | Frequency - Each Lot
01649fe6-9b36-50dc-9ee9-d16c418b159f | note | Acceptance Criteria - The surface on which the asphalt is to be placed must be essentially dry and free of any surface water.
dd552549-7b7b-5907-923e-7482e01e7a46 | note | ○ Asphalt must not be placed during periods of rain or when rain is imminent. Any asphalt placed during rain must be removed from the Works and replaced, unless otherwise determined by the Contract Administrator.
6f183fc0-0d83-5e98-9ab1-7491f33eb486 | note | ○ Asphalt must not be placed if the surface temperature falls below the minimum surface temperature as specified in Table 5115-1
446eb026-c9ab-5490-bf8a-5a9227ebba31 | note | Reference Documents - Volume 1: Clause 5115 Table 5115-1
29088ac4-49d6-5186-9a61-977b2cdbf858 | note | Inspection/Test Method - Verify
c6ccf82a-6b88-5cc5-8bfb-26c8a73921a6 | note | Record of conformity - This ITP signed by Contractor
b91abcb6-e80e-5080-9295-ba3c75ae7f7e | note | IP
c00c7912-167e-5b0f-9e08-f469e191be29 | note | Responsibility - Quality Engineer
35d700b7-484d-50e6-853d-9c12d45765cb | date | Date Completed:
751e92e8-3788-490f-ab86-39fe058e4e54 | section | 3.0 - Transport and Delivery of Asphalt
9c52bf6e-d1f8-408c-b4d4-561938d749d2 | checkpoint | 3.1 - General
1dc78aa4-22fd-5006-981d-7af77e102b0d | note | Frequency - Each Lot
93b457ae-f57d-5d31-9d8c-63405e133eab | note | Acceptance Criteria - Asphalt delivery must adhere to AS 2150 standards, ensuring completion of spreading and compaction by the work period's end. Each truckload requires a docket with details such as truck number, dispatch time, temperature, and mix specifications. Delivery vehicles cannot access freshly laid asphalt, and loads must be covered with heavy canvas and insulated to maintain temperature.
dc1c16fc-9564-5b88-88db-c4f088fadf8f | note | Reference Documents - Volume 1: Clause 5117 (a)
80bad2c9-5793-5a48-8157-a9b4dd65be47 | note | Inspection/Test Method - Verify
e93de50c-dbf0-5b4e-ac90-b203a40f6493 | note | Record of conformity - This ITP signed by Contractor
d0aaf64a-64c4-5bcd-b7c5-6eee33912f01 | note | IP
61d2e93b-bc3e-5cbb-8abb-e6283a8006f6 | note | Responsibility - Quality Engineer
261367f1-d7d7-5506-ad1b-ea4f7778b4e7 | date | Date Completed:
b241f366-8506-40a4-a408-0e0d8735f272 | checkpoint | 3.2 - Delivery Temperature
3fa9baea-0142-5e43-b947-60bcdebb9438 | note | Frequency - Each Lot
46379788-2c90-5ff7-871f-aac5123c2209 | note | Acceptance Criteria - The asphalt mix must be delivered at the minimum temperature specified in Table 5117-1 for the bitumen and must allow for initial compaction before cooling. Loads below this temperature, with cold crusts, wet from rain, or contaminated, must be rejected.
d8060428-8d19-53dc-aa43-2d865cf1c506 | note | ○ Miinimum asphalt temperature for compaction are indicated inTable 5121-1
d81ae9c4-34ab-520a-b2ac-77196c6b48ad | note | Reference Documents - Volume 1: Clause 5117 (c), Table 5117-1 and Table 5121-1
9da80f03-ae7c-5bb6-b36a-58ce7bc26e62 | note | Inspection/Test Method - Verify
6b438444-b37d-56f2-ba0f-c568a7f4b3af | note | Record of conformity - This ITP signed by Contractor
91dbded9-868e-5fe0-88ff-e7ee228a6595 | note | IP
4d5ba716-a0cb-5cbe-b399-114b2f88e1ae | note | Responsibility - Quality Engineer
a0e37f2b-0562-549d-b102-d404a21e7fa0 | date | Date Completed:
81b77859-abcf-408d-996c-8053465f31cf | section | 4.0 - Surface Preparation and Tack Coat
fc64ab7c-f1d1-4ad1-898f-3cae7a718363 | checkpoint | 4.1 - Surface Preparation
74a6e020-e624-57e8-9a75-562f3bb0a9da | note | Frequency - Each Lot
86a9c19e-bc5b-5d0d-8ea4-734b7e1a71e2 | note | Acceptance Criteria - Before applying the tack coat, remove loose materials within a 300 mm buffer, using power brooms or hand sweeping if needed. Clean oil spills with detergent and let the area dry. Ensure the surface is dry, debris-free, and mostly dust-free.
d457cf16-5557-57ea-acf8-220825f2b782 | note | Reference Documents - Volume 1: Clause 5118
3fb6d26e-45f8-5caf-af46-630f148f36b4 | note | Inspection/Test Method - Verify
ef852801-cb9e-54c5-8041-28f77a44de3a | note | Record of conformity - This ITP signed by Contractor
48fc05ec-57a0-59c0-803f-e6b32c8a41e4 | note | IP
67ecf7ad-f149-5637-8034-146451d4e820 | note | Responsibility - Quality Engineer
f183f32e-1399-55a8-86f2-382fb040cd59 | date | Date Completed:
e0212ba0-15a5-447c-9eca-57012218521f | checkpoint | 4.2 - Application of Tack Coat
8b68765b-c718-5d39-8d11-122e9d2a8214 | note | Frequency - Each Lot
852c0721-cd51-58cf-8e56-f09a61302758 | note | Acceptance Criteria - Tack coat must be applied to the prepared surfaces such that a uniform cover at the specified application rate over the full surface is achieved.
fc2ef4f6-e58d-5f6c-bbf2-f8148601b846 | note | ○ The residual bitumen application rate of emulsion tack coat must be between 0.15 ℓ/m2 and 0.25 ℓ/m2.
f0ead906-7a51-5cc6-aaf9-8a8af2d7ea8e | note | Reference Documents - Volume 1: Clause 5119
fc6e0e8d-5411-5a19-857b-1e2108067c33 | note | Inspection/Test Method - Verify
5a2be890-e53a-5aec-92cd-8a396fc5671a | note | Record of conformity - This ITP signed by Contractor
845cc706-8811-5cf5-8f3d-5a398a7aa925 | note | HP*
d7bbac37-8b7c-5b32-a7f3-5f194842b64a | note | Responsibility - Quality Engineer
30380e00-6a03-5694-8277-68f818cd7fa3 | date | Date Completed:
af937f1c-b174-471d-99ef-9795e1278897 | section | 5.0 - Placing Asphalt
c7758bcd-39ab-4280-84d6-d4373b470f8e | checkpoint | 5.1 - Placing of Asphalt
6ab40d70-e0c3-5670-baf3-6227bf531774 | note | Frequency - Each Lot
d9b046bd-6748-5e91-be10-e84491ae94b0 | note | Acceptance Criteria - Asphalt placing must not commence until all of the treatments within the paving lane and adjacent paving lane are completed and inspected by the Contract Administrator.
1ed51b87-ece1-5333-96c0-eaeafd27ca69 | note | Reference Documents - Volume 1: HP 5120-1
28ab9820-7794-5d92-bde6-89b872109ff1 | note | Inspection/Test Method - Submission
03d5c593-c9ef-571d-a749-f84e62575abf | note | Record of conformity - This ITP signed by Contract Adminstrato r
45ce2baf-882d-52d0-aa59-caf2cbda9602 | note | HP
d9a12b0d-49a3-5086-a208-29a4a2d4f188 | note | Responsibility - Quality Engineer
f852df76-4dd7-57a2-8bd4-32b51a70e836 | date | Date Completed:
776e5d3f-d07f-44cd-bc58-b50f92b7ed19 | signoff | AUTHORITY HOLDPOINT
f9e09c64-0ff9-4fe5-bffc-4df99931aff5 | checkpoint | 5.2 - Layer Thickness
f8ae547d-77bf-5fc6-82a3-2134709bcbf6 | note | Frequency - Each Lot
6a9a8e7b-5b5c-54c2-b306-8a284f2d93c8 | note | Acceptance Criteria - The minimum and maximum layer thicknesses for different nominal asphalt sizes must be in accordance with Table 5120-1.
d9a63def-0ed9-5cbe-98ac-3c870373d739 | note | Reference Documents - Volume 1: Clause 5120 (b)(i)
37d0fe30-bd2e-594a-a1e5-fa7ed8fe8a0c | note | Inspection/Test Method - Verify
8dd3885e-95ed-50ae-b96c-3ddf7a81d629 | note | Record of conformity - This ITP signed by Contractor
ae826fb8-899f-59d1-b5a0-c0775738ca37 | note | IP
678f7cbb-ea0e-5594-82e7-03405ec9acaa | note | Responsibility - Quality Engineer
6756ed3c-1190-56d5-b7b3-0f0635134f0f | date | Date Completed:
acb74ade-5d51-475f-9015-901e05031023 | section | 6.0 - Compaction of Asphalt
c0af65a3-16b1-422f-8f99-0258caae90c8 | checkpoint | 6.1 - Compaction temperature Requirements
0361d7cb-f0cc-5bc8-9d7a-d4e242cedfa9 | note | Frequency - Each Lot
93ead0d2-bd68-5115-874b-4405d0c89c9f | note | Acceptance Criteria - The asphalt must be compacted while the mix temperature is above the respective minimum values specified in Table 5121-1 for the relevant bitumen used in the production of the mix and roller type, unless otherwise determined and approved during the construction trials. The asphalt must be compacted with rollers meeting the requirements of Technical Specs, Volume 1
2e5554cb-db5d-5efb-a85f-7805ae825166 | note | Reference Documents - Volume 1: Clause 5121 (b), Table 5121-1
7a4435c8-d8d0-5b21-b3ba-560039b6da30 | note | Inspection/Test Method - Verify
2c49cba3-0489-5571-be02-24ae5c97bb40 | note | Record of conformity - This ITP signed by Contractor
208b151f-296e-59bd-bad0-4634567cc158 | note | IP
397fb876-1489-566d-bfb5-c8ba8bcb9346 | note | Responsibility - Quality Engineer
2c297e41-a97a-5645-946b-3e942ae772fe | date | Date Completed:
c3299f6a-de74-448f-908b-5815283e8004 | checkpoint | 6.2 - Compaction temperature Requirements
5a6abb14-a6b3-5163-8662-dcaf79dafd24 | note | Frequency - Each Lot
ce6caa5f-8261-5de6-97fc-88c3f2c00113 | note | Acceptance Criteria - The contractor must maintain detailed records of the temperatures of the asphalt mix during delivery, placement and compaction and must submit these records as part of the lot submission
ffa2f8dc-7b81-5d53-8006-2fc343fb74ed | note | Reference Documents - Volume 1: Clause 5121 (b)
dd9f078c-8e90-55fe-891c-64398edc719d | note | Inspection/Test Method - Submission
9a55dabc-b0d3-5e70-9c10-5f84e1da2b68 | note | Record of conformity - Asphalt Temperature Records (Delivery, placement and Compaction)
a3eb3e67-00f0-587f-9a97-917bc9dcd562 | note | IP
b3ca7c0f-992c-534d-9dd4-948f7db2f63a | note | Responsibility - Quality Engineer
de523c36-b18b-55ac-b142-f69589d79cfc | date | Date Completed:
f153ef5e-6256-4947-b8a7-3885e4b824d1 | checkpoint | 6.3 - Compaction Requirements
23c78c06-9787-588f-aebc-e09696ec918b | note | Frequency - Each Lot
d677b604-d285-51c2-9c8c-74d1d14f45ff | note | Acceptance Criteria - All of the rolling must be performed in a definite pattern previously determined by the Contractor and must be supervised continuously by the Contractor for the duration of the work.
0a369cd4-2958-500b-977a-d813feadc3ad | note | ○ The in-situ voids requirements for the asphalt must comply with the requirements of Table 5121-2.
e61d3f57-bb6e-5c6e-8e57-958b464a1dba | note | Reference Documents - Volume 1: Clause 5121 (c)
62a20483-6b1f-559b-b611-1dcf95c6731c | note | Inspection/Test Method - Verify
438b0f2c-2512-51a2-930b-f8e69d37c6bd | note | Record of conformity - This ITP signed by Contractor
d897c822-56bd-56e0-91a1-036003136c60 | note | IP
47595685-7610-5415-abc7-a39db8bcedd5 | note | Responsibility - Quality Engineer
dbeee951-4ba0-5278-b5b9-22e5e068d96d | date | Date Completed:
b14dfdd7-0b5d-4bbf-9650-4f20f5519838 | checkpoint | 6.4 - Breakdown rolling
f458a677-ab55-51a6-b4eb-f0afeec0ecd0 | note | Frequency - Each Lot
4bd6c5cd-c887-508f-9281-61d5d9617360 | note | Acceptance Criteria - Breakdown rolling requires a non-vibrating steel wheel roller with up to two passes. Start at the lower edge, overlap the lane edges by 200 mm, and progress across, overlapping previous tracks by 100 mm to 200 mm and extending 6 m beyond. For subsequent lanes, start at the free edge and overlap about 100 mm onto the previous lane.
2b896a7b-ea5e-5e4d-baf5-d9cee2144a70 | note | Reference Documents - Volume 1: Clause 5121 (d)
543b3ae1-6535-51c1-aa3a-9c6a15e1283d | note | Inspection/Test Method - Verify
9ecc5e79-0287-5aa9-a168-14bf8cb2e4f4 | note | Record of conformity - This ITP signed by Contractor
d1bd8ff8-74e8-5e2e-b9df-170e110b6904 | note | IP
359810bb-dd6a-53ba-8c12-7648b483840c | note | Responsibility - Quality Engineer
2a5ab849-cf03-5114-ae29-43fe116e3296 | date | Date Completed:
9a446b63-eb04-4b96-bd5c-b80812ba2bfb | checkpoint | 6.5 - Vibrating rolling
692cbec0-408d-5340-9c7e-0fbdab81e683 | note | Frequency - Each Lot
a426c6d7-3cac-5c42-ad26-f5822338d693 | note | Acceptance Criteria - Vibrating rolling follows breakdown rolling. For vibrating steel-wheeled rollers, keep vibration amplitude at or below 0.5 mm, unless the layer thickness exceeds 50 mm, allowing for greater amplitude at the Contractor's discretion.
78fb4a96-2845-5caf-bc6b-dd5fbddef6c4 | note | Reference Documents - Volume 1: Clause 5121 (e)
4e08a400-484a-5c5a-bff9-5575d052980c | note | Inspection/Test Method - Verify
49805d46-e4cd-589d-b605-3fc8bf880bf5 | note | Record of conformity - This ITP signed by Contractor
44b706cc-2d48-5d20-a4ea-25397daf47a4 | note | IP
98672449-752a-548c-ade6-bcd413f2f5bb | note | Responsibility - Quality Engineer
a60cbe93-4e91-54b2-9dd9-b2c342887e37 | date | Date Completed:
08676da5-e74a-452b-86dd-173222d24df7 | checkpoint | 6.6 - Pneumatic Tyre Rolling
0705dad3-1f23-51ad-ba26-f4cbe20fca76 | note | Frequency - Each Lot
a27c00a5-14bc-5c65-b942-312ed86c6185 | note | Acceptance Criteria - Pneumatic tyred rolling must follow vibrating rolling, requiring at least six passes before the asphalt cools below the specified temperature showed in Table 5121-1 to ensure a tightly bonded surface.
e1ca5e15-2900-5b66-baae-bf0f46220d7f | note | Reference Documents - Volume 1: Clause 5121 (f)
c9a056f0-6bc9-5830-905c-84f791da72cd | note | Inspection/Test Method - Verify
a979aa2c-51d2-5f7e-bfe0-b98652988be9 | note | Record of conformity - This ITP signed by Contractor
cd4a4f08-7e91-52e4-a736-0c867533c8be | note | IP
8cae2149-3157-5ad0-9111-60b2122fe2a0 | note | Responsibility - Quality Engineer
0486b2d3-01dc-5ea9-a5e9-9b2588622d15 | date | Date Completed:
5834265a-dc81-484a-963c-608504836a3a | section | 7.0 - Joints
6a7c16f5-5d56-40fd-ae59-5983ab51ae4c | checkpoint | 7.1 - General
3c7e4d16-79af-544f-86b6-056d1e9ea5b6 | note | Frequency - Each Lot
82dd6091-ca3c-54ca-9c67-ccdc0e650d08 | note | Acceptance Criteria - All paving joints must match the surrounding surface's texture, density and smoothness.
d395c689-d014-5d9a-974d-e46ed5368e40 | note | ○ Longitudinal joints between lanes need to ensure a continuous bond and minimized cold joints. If the surface finish is below standard, a non-conformance report must be issued. Longitudinal joints in overlays must be offset by at least 200 mm.
d3049320-464e-54ab-926d-483ce419b5f3 | note | Reference Documents - Volume 1: Clause 5122 (a)
1499f217-9a82-5e2b-a46b-2d790d90ff59 | note | Inspection/Test Method - Verify
dc866f15-791f-56bb-a888-a6eddf790344 | note | Record of conformity - This ITP signed by Contractor
21b84239-5baf-5f42-b0c4-822fbf046f53 | note | IP
445b90e3-6889-57a0-81e7-3c2e0951fbe0 | note | Responsibility - Quality Engineer
b2d28fe6-238a-5039-84e1-ff112d8fd7b0 | date | Date Completed:
6a8fbfa2-8b60-467f-94fa-e6ae63a91b53 | checkpoint | 7.2 - Longitudinal Joints – Warm Joints
4fc861c5-e890-585e-ad5c-cac633269154 | note | Frequency - Each Lot
7f1c5e81-e9dd-559b-b370-c343a32a27f4 | note | Acceptance Criteria - To treat the joint between asphalt lanes as a warm joint, place the adjoining lane within 1 hour while maintaining the required compaction temperature specified in Table 5121-1. Procedure is detailled in Clause 5122 (b)(ii)
ce677d45-7cb6-561f-8519-3fc7cc8429e9 | note | Reference Documents - Volume 1: Clause 5122 (b)(ii)
88777d09-d638-540a-a86e-ac8740ee70d4 | note | Inspection/Test Method - Verify
389f5b46-5ed2-5142-984b-186d9071695d | note | Record of conformity - This ITP signed by Contractor
7df01de0-384a-50dc-8eaa-5a4663b2d032 | note | IP
08d465d2-3ffb-5298-a8ee-1c306ffc06ff | note | Responsibility - Quality Engineer
7df6258f-aa83-5419-82c0-bf7f550c81b2 | date | Date Completed:
a0894a68-4fce-4bd2-9d76-cec04a7e7018 | checkpoint | 7.3 - Transverse Joints
5209e2bc-b8c9-52f9-9e5e-c6fcdfc9efdb | note | Frequency - Each Lot
2f7cca94-b5fe-594e-adea-b85f9f3cbaa5 | note | Acceptance Criteria - Transverse joints must be at right angles to the direction of placing and must be cut to a straight face between vertical and 45° to the vertical to the full depth of the course. Procedure is detailed in Clause 5122 (c)
85654d44-f65f-592b-8ff2-a7ec165d4af3 | note | Reference Documents - Volume 1: Clause 5122 (c)
3cceb58a-9601-52f4-8081-144fe572efb6 | note | Inspection/Test Method - Verify
226114da-23cc-5b86-b4ed-6bcf3f508ab0 | note | Record of conformity - This ITP signed by Contractor
927a4480-8e3a-5343-97b4-d5c6754e6e37 | note | IP
a41182e8-0812-5ff2-a5fb-789ed95f8d9f | note | Responsibility - Quality Engineer
92a7fd51-7d75-5031-a054-8a656e65cd0b | date | Date Completed:
df51edb5-12cd-473c-b65d-f721ca1134c6 | section | 8.0 - Finished Surface Level, Surface Smoothnes and Finish
31b5cafe-fd9f-404b-bf0b-9636ea0f3a21 | checkpoint | 8.1 - Thickness and Surface Level Tolerances
ad4fa3ef-3c3e-5d6c-a6bc-812e7a55ec49 | note | Frequency - Within one working day of completion of the survey
c364ad81-fcd9-56fb-9efb-d64158a342f8 | note | Acceptance Criteria - The Contractor must provide the Contract Administrator with a record of the finished surface levels together with a summary indicating the magnitude of the departures from the specified finished surface levels shown on the drawings within one(1) working day of completion of the survey
c5cdec3c-ba41-5414-8543-21a99f328093 | note | Reference Documents - Volume 1: HP5124-1 & Clause 5124 (b )
b26d8c7e-6f8e-5072-82d5-100072e5fbb5 | note | Inspection/Test Method - Submission
8e977416-b42d-513c-8016-c72f80ab2daa | note | Record of conformity - Survey Report
5f92282a-60e3-54f1-adfd-d6c9e299189d | note | HP/ SCP
9951ee19-3278-5696-959f-f03ea51a5739 | note | Responsibility - Quality Engineer
089c47e4-a720-55bb-8d1a-7a3b0d2c18d7 | date | Date Completed:
a1f25ebd-2206-4fb1-b162-46d2de0226bb | signoff | AUTHORITY HOLDPOINT
2c60f94a-4d27-4678-b65b-f0e59aa19c6c | checkpoint | 8.2 - Surface Smoothness Tolerances
97287aac-3952-58e8-a819-8a1cd51e1be4 | note | Frequency - Each Lot
bec09b96-62b1-585f-a62d-3659d4f697c0 | note | Acceptance Criteria - The finished surface of all asphalt surfacing courses must not deviate from the testing edge of an approved 3.5 m straight edge by more the requirements in Table 5124-1
4a0afbee-ed29-55d6-9ff2-a726f844b5ee | note | Reference Documents - Volume 1: Clause 5124 (c)
d9509180-7902-5c41-9268-04ba6836c3f7 | note | Inspection/Test Method - Verify
7f542e25-6c58-5df2-8568-16384f29e261 | note | Record of conformity - This ITP signed by Contractor
7030fc37-78db-5bb0-9155-24d71d7bd401 | note | HP*
f6bc4b55-7bdf-56e8-a564-ec9df0c97551 | note | Responsibility -
c90db453-a3f3-54c1-b188-da9307f3f53c | date | Date Completed:
c04cf879-83b2-4692-bb91-e55bc3c8f140 | checkpoint | 8.3 - Pavement Cleanliness
e543a0a0-8551-5aa9-a13a-8773d995109d | note | Frequency - Each Lot
72d87f48-8bb2-5759-90ab-b52fc0f9e4c7 | note | Acceptance Criteria - Inspection of completed pavement with the Contract Administrator
d5e82e2a-16e8-5830-9e6d-51354e4f03cd | note | Reference Documents - Volume 1: WP 5126-1 & Clause 5126
c1d678a5-e88c-51dd-8dba-e97c80577e2d | note | Inspection/Test Method - Notificatio n
56f6a07d-ea69-5eb2-82d3-70a343ade743 | note | Record of conformity - This ITP signed by Contractor
292610ff-c4af-5adf-a1d1-620f8890fb32 | note | WP
7f6d7635-96af-5758-9398-f86faf48d9b7 | note | Responsibility - Quality Engineer
45e35063-8bf1-553c-b4d5-edbf622d5ac1 | date | Date Completed:
4c7cab25-7c04-4def-a61d-846715132e3f | section | 9.0 - Quality Assurance – Construction
8054b4f8-0ba5-4aaf-853e-f9e1f5017398 | checkpoint | 9.1 - Assigned Maximum Density of a lot of Asphalt
149353aa-f8d4-5019-ae87-af7edeb52d79 | note | Frequency - Each Lot
53f3ff72-0071-5857-98c2-49b7d896e845 | note | Acceptance Criteria - The assigned maximum density for use in the determination of the in- situ voids of an asphalt must be the as defined in Clause 5132(a) of this specification, using cores cut as per Clause 5132(b)
c1920bc6-d655-54ae-bbfd-ba23185d165a | note | Reference Documents - Volume 1: Clause 5132 (a)-(c)
f955e875-fb19-5f92-9d0f-f4750cc81599 | note | Inspection/Test Method - Verify
4e2954c9-e74c-5d0e-83a4-d88370858177 | note | Record of conformity - This ITP signed by Contractor
e25b96c3-7dc9-5047-8720-8e50277f347e | note | IP
137520dd-cfb8-5e07-8b13-b65ee56c5e52 | note | Responsibility - Quality Engineer
822bdaa7-ac5d-5f71-96af-d8e59fa2ea82 | date | Date Completed:
4e18aaac-3553-4b59-b2bb-6549ab4397bf | checkpoint | 9.2 - Thickness Determination
7342fc8b-f592-5a43-bf5e-fa2247db1f4b | note | Frequency - Within one working day of completion of the asphalt work
b31d52fe-44e0-5da0-8c40-db8acc16d669 | note | Acceptance Criteria - Copy of the thickness determinations indicating the magnitude of the depature from the specified thickness, immediately on completion of the determination or within one-working day of completion of the asphalt work and statement of conformance (or non- conformance report and proposed disposition if applicable)
d21f65b3-7bfe-5696-961d-08d401ed5f80 | note | Reference Documents - Volume 1: HP 5132-1 & Clause 5132 (e) Volume 2: Clause SP5132 (e)(iv)
d89f7b1f-d84d-5e36-af06-a6998cf138ff | note | Inspection/Test Method - Submission
5a19d011-f8f8-5ec0-9a7e-844714b5dcac | note | Record of conformity - Core Thickness
515a3441-ce42-5f7b-9139-8c9ad903b908 | note | HP/ TP
560cef25-df1c-5ab7-a06c-a1fd0477d0a2 | note | Responsibility - Quality Engineer
37207b42-2f77-5d4d-a796-fb353c6bb5e9 | date | Date Completed:
31488329-6150-48d6-89f2-7205d441c1ff | signoff | AUTHORITY HOLDPOINT
cd0a31f7-1981-4f19-9bba-b32b84763973 | checkpoint | 9.3 - Compacted Asphalt - Finished Surface Levels
9bf26edc-23f0-5039-b54d-e0bdf546dfb9 | note | Frequency - Within one (1) working day of conformance
25d90672-a365-5327-a5e8-3512f97facd0 | note | Acceptance Criteria - Record of the finished surface levels together with a summary indicating the magnitude of the departures from the specified finished surface levels shown on the drawings within one (1) working day of conformance (or non-conformance report and proposed disposition if applicable)
05bc34b3-6645-5ccb-8215-7aa176e00ea4 | note | Reference Documents - Volume 1: HP 5132-2 & Clause 5132 (f)
a49765d5-09b1-5a82-895f-d332679230c6 | note | Inspection/Test Method - Submission
f61b4b87-5077-5d8f-a056-c08de256e909 | note | Record of conformity - Survey Report
92d82d3f-d895-5df0-b83d-2bf401ee7039 | note | HP/ SCP
34aa7762-e236-5442-8ecc-a14e1a3230a7 | note | Responsibility - Quality Engineer
fe0e2b4a-bfec-5802-8fd8-ee008182f1af | date | Date Completed:
ff70a887-8940-46ea-a7a9-c6b0ba8a81f7 | signoff | AUTHORITY HOLDPOINT
7d6fe474-2e9e-45e3-9564-a98f20923a74 | checkpoint | 9.4 - Compacted Asphalt - Surface Smoothness
39e47690-1a10-5e36-ad02-1a18b13e3ff8 | note | Frequency - Within one (1) working day of completion of testing
3376b45e-4449-5ee6-b38c-0f0a3b113574 | note | Acceptance Criteria - Statement of conformance or record and plan of location and extend of surface irregularities that depart from testing edge by more than the tolerances specified within one (1) working day of completion of the surface smoothness testing and non-conformance report and proposed disposition as applicable.
85bb08a8-9d3a-5629-815c-5db1efe80562 | note | Reference Documents - Volume 1: HP 5132-3 & Clause 5132 (g)
2697dd61-b7f4-5134-965e-58cef1b9068e | note | Inspection/Test Method - Submission
79ccce3a-5bba-57f0-b19a-d49447eac871 | note | Record of conformity - Straight Edge Testing
b1e90ba0-889f-5cdd-bc33-1b9f142dff55 | note | HP/ TP
745b8f84-99d6-5596-8b1a-651e6a6b3ab0 | note | Responsibility - Quality Engineer
da38909f-4142-595f-bbf9-f125b887760b | date | Date Completed:
3fa4a8cd-b331-4d55-9153-cdd0386d49d6 | signoff | AUTHORITY HOLDPOINT
323b9d3b-3c61-40f9-9253-d1b4b54a3857 | checkpoint | Final Inspection
1501278e-fbf4-5a9a-b9f2-60cfedbf2003 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
959b311b-1609-5ac9-847f-c811130b2e86 | textbox | Print Name:
16bf4c64-42cd-50d0-b2e2-da70bde482be | textbox | Position:
d8fdf9db-8af5-5da3-9755-ed578f7f13ed | date | Work Completed On:
62e06bec-de87-5b2f-9690-2b99055d20a6 | date | Date:
ee016b77-3e02-41ac-8175-cb913f00c70d | checklist | FH-927-QU-ITP006 - Asphalt Production - Rev 0 | itp | ITP006 - Asphalt Production
33ccfd01-5132-4e49-b5b2-aee913366718 | section | 1.0 - Paving Plant, Tools and Equipment
498f71e8-e3b3-4125-bfc7-c25cd9e6193d | checkpoint | 1.1 - Minimum Requirements
d7b61c68-fd54-5f19-b76d-fd38dc7f71c7 | note | Frequency - Each Lot
c8b5d74d-3e66-5164-bc24-d4aae434127d | note | Acceptance Criteria - The plant must be calibrated by the Contractor prior to the commencement of production trials in accordance with Clause 5112(i) and the calibration checked and reliably maintained throughout the entire production for the Works.
65a2fcc5-a864-503b-93a3-f3e4a8b65871 | note | Reference Documents - Volume 1: Clause 5112 (a)
9ba7f55d-ff35-518a-87cd-09d839be7516 | note | Inspection/Test Method - Verify
03379e6f-824a-5303-a32a-29f13cc7f58a | note | Record of conformity - This ITP signed by Contractor
7f75603c-1faa-5e6d-99e9-fff2a2a0ed64 | note | IP
1ac82db3-d139-503d-b585-59a348536c04 | note | Responsibility - Construction Manager
5a303c8d-856f-5e10-a12a-f5e31759a842 | date | Date Completed:
3abb1288-adbe-4d76-8b1a-775afcf2908d | checkpoint | 1.2 - Bitumen Usage
501bdf09-cdaf-5341-87d9-b7b35c2090ff | note | Frequency - Each Lot
5efc18e8-fa52-5e9b-9943-7354a2a7adcb | note | Acceptance Criteria - Submission of results of verification testing of asphalt mixing plant devices against direct measuring of bitumen tank with mix/trial mix test results
31695f66-d497-56d1-a37a-9de6f790643e | note | Reference Documents - Volume 1: HP 5112-1
36b4945c-1594-50fd-a82e-05c4fc0eabdf | note | Inspection/Test Method - Submission
14559176-6a55-5da1-b1fc-c8a0defa07dc | note | Record of conformity - Bitumen Usage Record
e3ff46f3-4916-537c-bd07-33c5d406ee4e | note | HP
bce06722-eca7-5592-bb52-a3de95c2fe00 | note | Responsibility - Quality Engineer
8c6a4980-2d50-5336-baf1-1b72d11caf10 | date | Date Completed:
7166dfa2-7438-48ce-983d-3b8b024b5b71 | signoff | AUTHORITY HOLDPOINT
c4b51b25-4ba6-4129-8ace-67ac496c62a3 | section | 2.0 - Storage and Handling of Aggregates, Added Filler and Bituminous materials
bc17508a-a246-49f0-8be6-d6fa758067ac | checkpoint | 2.1 - Storage and Handling of Aggregates
3e2076d5-4b6a-5c1c-a2bd-2deda5218c8e | note | Frequency - Each Lot
a85bc6ee-89ee-5cd1-a482-70cac61b6eb9 | note | Acceptance Criteria - Aggregates must be tested for compliance and compliance confirmed before delivery on site. The aggregates must be stockpiled separately at the quarry or mixing plant, stored to prevent contamination and segregation. Each size should be stored with at least 6 m of space between them or a wall to avoid mixing. Aggregates up to 10 mm must stay in free-draining stockpiles for at least 72 hours before use, with waterproof covers used during wet weather when the plant isn’t operating.
966874f4-4ad5-5713-8297-2f9e3c83c587 | note | Reference Documents - Volume 1: Clause 5114 (a), 5131 (a)(i)
810d2649-b9fc-599e-8044-12778c82427a | note | Inspection/Test Method - Verify
31e71d2c-b42e-51d6-aa09-078ba176c470 | note | Record of conformity - This ITP signed by Contractor
a9d34f0e-fe06-5e82-9201-c00377f8e290 | note | IP
7523b39b-1877-5fdf-a9b4-630ed29de204 | note | Responsibility - Plant Operator
21638f1c-25e2-5646-a9da-2882cfd0d382 | date | Date Completed:
87804086-360d-4838-a6ed-da2937d1fa63 | checkpoint | 2.2 - Storage of Added Filler
06598b96-5e9a-5752-b7af-60a8566b01a9 | note | Frequency - Each Lot
44db3327-22b2-5fc8-a8f6-e366b966e1da | note | Acceptance Criteria - Added filler must be stored in weatherproof storage bins or silos to prevent moisture absorption and the formation of lumps.
0a83d6ec-7f65-583b-9e8d-34d9f92e1b8d | note | Reference Documents - Volume 1: Clause 5114
4017e13b-34cf-55d2-b81e-5608b5c5103c | note | Inspection/Test Method - Verify
8a2d107d-9d75-571e-a4c8-8614f4d56cc8 | note | Record of conformity - This ITP signed by Contractor
a572544a-a9ef-5cf1-ac27-0bbd488007b6 | note | IP
020ebe95-34ea-5c3b-bba0-47b6194fc16c | note | Responsibility - Plant operator
32c388c8-938c-59dd-9fdb-19765acd1bed | date | Date Completed:
3f89c631-c4e6-42d1-867d-12b7b9b6ba83 | checkpoint | 2.3 - Storage and Handling of Bitumen
8bc8111c-0916-593d-88ec-1ed1293e2381 | note | Frequency - Each Lot
5f655bd3-9fb1-5498-b986-a48032e65a49 | note | Acceptance Criteria - Bitumen must be stored in clean tanks and not reheated above specified temperatures or stored longer than showed in Table 5114-1.
bf0351b0-c295-50a9-9ff5-c909819c6532 | note | ○ The Contractor should keep records of heating and storage; if there are not records, bitumen must be used within 24 hours of delivery.
236859ef-1465-51a6-a139-65ad95adc4e4 | note | ○ Contaminated bitumen cannot be used for asphalt.
ba9fd0c6-d187-540c-ad7a-c570d2c3afaa | note | Reference Documents - Volume 1: Clause 5114 (c) and Table 5114-1
c52bd20d-c858-5962-af2e-4978f0ef4199 | note | Inspection/Test Method - Verify
aa2c7d6c-0444-5eef-ab3f-fda06b116617 | note | Record of conformity - This ITP signed by Contractor
9f967ca4-12b2-580a-9228-08d297e31fe3 | note | IP
45a106aa-805c-5cfa-9eef-96128195e550 | note | Responsibility - Plant Operator
bfd11a6b-4f0c-545e-82e3-5035b0c57e12 | date | Date Completed:
27ce9938-22b9-497f-9768-e4bfa065a295 | section | 3.0 - Mix Production Requirements
f1109095-a0ef-4519-8416-868f16a49c2e | checkpoint | 3.1 - Moisture Content of Aggregate
b0e3ddd3-0d9c-52df-9bd1-e1edaef97cb0 | note | Frequency - Each Lot
de492511-ad21-5f49-8d41-e621ba9d345f | note | Acceptance Criteria - Moisture content must be determined in accordance with the requirements of Clause 5129(c).
a29d553d-eb13-54fc-883f-123637e57fea | note | Reference Documents - Volume 1: Clause 5116 (b)
59e68647-eda1-565d-9295-ef98d2d317e3 | note | Inspection/Test Method - Verify
8b7d8c73-e2bd-5bd9-ad47-21716b45bf51 | note | Record of conformity - Moisture Test Report
db8cb7c7-0a87-58f9-ad7b-ef4a55429064 | note | TP
22ebf353-8eeb-50d1-839a-b3a86dd92ceb | note | Responsibility - Quality Engineer
b1017e86-c10b-51d1-8c76-5f6327cf1ec8 | date | Date Completed:
9b143e81-8007-43fc-9c2d-1882443a7192 | checkpoint | 3.2 - Particle Size Distribution Tolerance
a0156c06-ca50-51eb-9850-1844dc388a4f | note | Frequency - Each Lot
a9238d7a-c2c6-56b9-8524-dfa884a68c4f | note | Acceptance Criteria - Individual samples of aggregate from stockpiles, deliveries, cold bins, or feeders must maintain consistent particle size distribution. This ensures that the overall particle size distribution of asphalt remains within specified limits defined by job requirements and production tolerances outlined in tables for coarse and fine aggregates.
5beb5fa6-0db9-5b05-8884-a9ea830a733d | note | Reference Documents - Volume 1: Clause 5116 (c)
ffbad884-91c9-52fc-9b68-cdb8acbc8b2b | note | Inspection/Test Method - Verify
86c901eb-fc37-5f66-ad70-58cb5c570630 | note | Record of conformity - PSD Test Report
73132174-c006-5b5c-a818-c891bbf196d4 | note | TP
201e46bc-b080-5b75-8c33-b0206603fddb | note | Responsibility - Quality Engineer
d3aa8ff3-517b-5b93-a399-22c8623dfcde | date | Date Completed:
67719429-4a4a-44f2-b470-235299f68384 | checkpoint | 3.3 - Commencement of production of asphalt in each working period
f6a448d2-47e2-5e84-9266-4023e40cf2e2 | note | Frequency - Not less than 48 hours prior to the commencement of a work period
135ed056-9fbd-53d7-932c-f687a91dee5c | note | Acceptance Criteria - Submission of production plan which must demonstrate that the hot storage capacity and the production capacity of the mixing plant is capable of suppling asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown
2e1d8e6d-3795-585c-adee-18d3ea8f0c30 | note | Reference Documents - Volume 1: HP 5116-1
7e87fc7f-2362-5aad-9a6c-a60319fe6b72 | note | Inspection/Test Method - Submission
90453849-1b8b-55d2-8ae4-448133c224fc | note | Record of conformity - Production Plan
9ed347a1-a134-5fc8-9d88-abc9d07f8d0a | note | HP
e1ccbb26-e874-5104-a1ad-582b1997d569 | note | Responsibility - Quality Engineer
54ebb15f-233a-594d-b35a-b8be9598a7ce | date | Date Completed:
df41e6d5-7310-4cd8-ab46-279ad9036108 | signoff | AUTHORITY HOLDPOINT
a025b698-b6b0-426e-9c15-b52e83247c37 | checkpoint | 3.4 - Mixing Temperature Requirements
4a728ea8-e49f-5968-956c-0135a01f6593 | note | Frequency - Each Lot
2bc2996d-bdf8-5d6c-9133-b6f304417c23 | note | Acceptance Criteria - Tolerances of bitumen temperature, temperature of aggregates and Asphalt temperature when introduced into the mix are shown in Clause 5116 (f)
80f86711-ef2b-5d9a-9302-341168d05a6a | note | Reference Documents - Volume 1: Clause 5116 (f)
eb30f737-175e-5004-a8d7-3c84c092e1d4 | note | Inspection/Test Method - Verify
af613631-f4bf-5387-8c52-f445f2492898 | note | Record of conformity - Asphalt Production Records
80763018-9dd7-5a05-a962-db06611192b1 | note | IP
9a128f36-296d-56c6-bfeb-709f132fb0e6 | note | Responsibility - Quality Engineer
a28b8d3c-7bb8-5e57-b4e8-7b51e389f9ca | date | Date Completed:
16ee8284-299c-48a5-aa47-3a488137b0e0 | checkpoint | 3.5 - Mixing Efficiency
640c8ae3-414a-5860-8e3b-331b45be9338 | note | Frequency - Each Lot
f2eda4fd-8cdd-5578-a7ff-5d118dfcfc7f | note | Acceptance Criteria - For asphalt production, hot aggregate, filler, and bitumen must be mixed until particles are at least 97% coated, ensuring a homogeneous mixture per ASTM D2489.
6d2e92d3-ba47-5dff-be9c-fb2c9ed87423 | note | Reference Documents - Volume 1: Clause 5116 (g)
fdaaac3f-1d55-51e8-a8fe-41f2b1f28709 | note | Inspection/Test Method - Verify
ada9ac0b-53e9-57ca-962e-3aa3ca962132 | note | Record of conformity - This ITP Signed
d4893023-2d62-57e8-af00-1e0470d0d8e8 | note | IP
b6675927-b251-51a6-9c22-5d1fe5cef4ab | note | Responsibility - Plant Operator
79cdabef-ce13-5fe0-871a-afa1d1d4f2df | date | Date Completed:
8d967ff0-807a-4223-90d1-b823bccd84e8 | checkpoint | 3.6 - Mixing Times
c02a2241-c89a-5c0a-b00a-9b13708fe4d5 | note | Frequency - Each Lot
6e793693-c045-5181-a929-17a20b2fd525 | note | Acceptance Criteria - Mixing time for asphalt should balance efficiency and prevent bitumen hardening. Dry mixing must last at least 10 seconds, while wet mixing should include bitumen addition (max 10 seconds) and ensure complete coating of all particles.
c08c3fc2-3710-55d4-ae16-5fa30d0413db | note | Reference Documents - Volume 1: Clause 5116 (h)
d9537352-b51b-50f4-9c7a-7510aa2916a0 | note | Inspection/Test Method - Verify
079e3a5d-872b-554c-906a-4427d643eeca | note | Record of conformity - This ITP Signed
1f0f43e7-b760-5d83-a7f1-993a3f759bd9 | note | IP
82e14adc-5754-5c47-9484-c5ec6b1579cc | note | Responsibility - Plant Operator
98aa7f48-b669-5d96-825a-bdbf6c9735c5 | date | Date Completed:
8649d592-7918-4b78-b17a-a443b954407f | checkpoint | 3.7 - Production Tolerances
6ba8dc52-f287-5a38-9450-8b033334c417 | note | Frequency - Each Lot
b2c72d5a-d74c-57cb-8621-38610b39dbd9 | note | Acceptance Criteria - All asphalt produced in accordance with the 'job mix' must comply with the properties specified in Tables 5116-4, 5116-5, 5116-6, & 5116-7
a21ac71d-bbde-5de2-bf3b-33042705c8f3 | note | Reference Documents - Volume 1: Clause 5116 (j)
53bd7640-1b76-5e9f-8297-6a7326bdcc6f | note | Inspection/Test Method - Verify
50da24ff-fdfd-56b0-ab35-76415050e105 | note | Record of conformity - Asphalt Mix Test Report
ee979a08-ee9e-562b-b58a-fd06ec56d97e | note | TP
83a5f842-e452-570c-aeb9-cca3ed265a21 | note | Responsibility - Quality Engineer
744331bf-be5d-5d89-bd90-ae10699c95d5 | date | Date Completed:
7bf9b2e9-ff73-435b-85b6-e2db28ba8644 | checkpoint | 3.8 - Non-Conformed Production of Asphalt
3b11f7c5-8764-586d-b8af-2e961a57508b | note | Frequency - As required
06460e9d-7720-513a-a71b-60ce4b7289a6 | note | Acceptance Criteria - If during the progress of the Works asphalt produced, with an aggregate particle size distribution and bitumen content within the tolerances specified in Table 5116-7, a non- conformance report and proposed disposition must be recorded and submitted
4b2cb4d3-2a3b-5d3a-8137-7ff2eca2adee | note | Reference Documents - Volume 1: HP 5116-2 and Table 5116-7
a91903c7-f0ad-5f33-a822-74f89143c78a | note | Inspection/Test Method - Notification
13766e57-6827-5dd8-9c40-e72e6bb3cb1a | note | Record of conformity - NCR
aea2d90b-17f4-50ab-af1a-c1dee552c496 | note | HP
75da77b1-5dd9-579c-ae7b-e3b667d65b88 | note | Responsibility - Quality Enginer
bab99fc0-8e00-5139-b73e-29637e5a419d | date | Date Completed:
a531a18a-07c5-45d7-9352-e828e48f7e2a | signoff | AUTHORITY HOLDPOINT
90770881-b34f-42f1-91f3-ac422a72ae72 | checkpoint | 3.9 - Non-Conforming Material
e48c027c-4b1b-582a-b88c-6c694fb1f393 | note | Frequency - As required
4f5d2aba-3fb9-5d63-ad80-3f6a54374a94 | note | Acceptance Criteria - Asphalt that is overheated, inadequately mixed, contains moisture, or does not meet specifications is deemed nonconforming and must be removed from the site.
089358e3-b049-5130-88ca-4be7d6106dac | note | Reference Documents - Volume 1: Clause 5116 (k)
eb88e0ec-09dd-54ad-84cc-8d6f3d616715 | note | Inspection/Test Method - Verify
ecb6eaef-97bf-513c-96bb-c90ec303ba09 | note | Record of conformity - This ITP signed by Contractor
dbe3d991-d9a9-5070-8bfc-4ea7d671002c | note | TP
342c4fea-34c8-58f7-8c28-e936cffd5f68 | note | Responsibility - Quality Engineer
e278af1b-fa87-5712-bc9b-e3bc46e4f54d | date | Date Completed:
3c78655e-65cd-427a-963f-d4b807eb8476 | section | 4.0 - Quality Assurance – Production
42759d85-ba0b-4be2-aebb-e6e3f689a1e6 | checkpoint | 4.1 - Sampling and Testing – Coarse Aggregates and Fine Aggregates
864996ec-8a0b-53a4-a29c-151d2502d67b | note | Frequency - Not less than 5 days prior the use of the aggregate in production of asphalt
c93f9791-ba71-5228-a192-a08afeb559b4 | note | Acceptance Criteria - The minimum frequency of sampling and testing for each coarse aggregate fraction must comply with the requirements of Table 5131-1.
8d2a79d9-dbe2-56c4-ba0a-d4ed6e34b26d | note | ○ The minimum frequency of sampling and testing for each fine aggregate fraction must comply with the requirements of Table 5131-2.
5f6cc60e-dbe6-5027-bd9e-c0e54cfd4d2c | note | Reference Documents - Volume 1: HP 5131-1
b73e856f-13ab-5f8a-a579-88844bee42e3 | note | Inspection/Test Method - Submission
7d2f44aa-1911-55e7-a3e9-112502c6a9c0 | note | Record of conformity - Aggregate Test Reports
d6c2f7b7-5ca3-50f7-8079-955e360b5584 | note | HP/ TP
564cae2a-6d6d-533b-8dc7-0974f6721b83 | note | Responsibility - Quality Engineer
ff8f8dd1-9ecf-5973-a5dd-807a13736ff8 | date | Date Completed:
27f703dd-0569-4f8a-bf16-605a51b3c771 | signoff | AUTHORITY HOLDPOINT
f4407eea-6b58-48f6-bdef-bd4dec8e77f9 | checkpoint | 4.2 - Added Filler
23057b94-4263-5d83-abe7-f0158731e728 | note | Frequency - Not later than 24 hours after each delivery
167188b4-3639-512b-adf5-14b3efbff29d | note | Acceptance Criteria - A test certificate confirming that the hydrated lime meets 5106 must be included with each delivery to the asphalt mixing plant. This certificate, along with the delivery docket, must be submitted to the Contract Administrator
a0387c1b-ca3a-5fa7-b0eb-ee37a3c25a86 | note | Reference Documents - Volume 1: Clause 5131 (b)
a5f59d19-87e6-5695-a430-e4d82e9c2b49 | note | Inspection/Test Method - Submission
deaab8bc-03a1-5642-b04d-fbeafe090617 | note | Record of conformity - Added filler Certificate and docket
fc01f41e-d05c-55dc-82e1-353ee644a874 | note | IP
bf432dfe-c165-5cb9-a3e8-95d58cc7996b | note | Responsibility - Quality Engineer
d63f5bdd-bc59-56cd-9a44-19e066896c5e | date | Date Completed:
562f9a1a-2520-4904-b98e-76afc3d121cd | checkpoint | 4.3 - Bitumen Test Certificates
6f40ea66-0c82-5c75-a6f7-a31b9ab78fc0 | note | Frequency - Not later than 24 hours after each delivery.
75c26f09-687c-53e1-b3cd-602c5342dc86 | note | Acceptance Criteria - Each delivery of bitumen to the asphalt mixing plant must include a test certificate verifying compliance with specifications and corresponding to the delivered lot. The delivery docket, detailing quantity and delivery time, must be submitted to the Contract Administrator, along with a testing certificate for each new batch.
65fc2659-829c-520b-8cc4-80fe1f1f7d4e | note | Reference Documents - Volume 1: Clause 5131 (e)(i)
fde215c2-6ba5-5fd2-b145-264e867a9c2c | note | Inspection/Test Method - Submission
37ac0581-7857-5eb8-a6b1-345ab8b826f9 | note | Record of conformity - Bitumen Certificate and docket
778e77a2-533e-53e7-b3ae-c3d02c90bfa3 | note | IP
2cb4bbcf-288b-5694-9651-b9fab9e89c82 | note | Responsibility - Quality Engineer
79178805-5400-5ecd-9027-a41260428f7f | date | Date Completed:
d0e7f3ae-b676-44aa-80c4-6dcc48574c2a | checkpoint | 4.4 - Sampling of bitumen from delivery vehicle at mixing plant
358d2f63-99f2-5b5b-9e21-49ff51360c3d | note | Frequency - 24 hours prior
c95c4b33-8740-51cd-af90-d5119a39330b | note | Acceptance Criteria - Notice (24 hours prior) of time of bitumen delivery to mixing plant and taking of bitumen samples.
13ac8573-e79c-5408-aafd-bd7eb2218a05 | note | ○ Samples must be at least two (2) litres in sealed, 6ubmitte airtight steel cans with removable tops. They should be traceable to supplier records and handed to the Contract Administrator immediately after sampling.
df3d422d-532c-5781-a7a4-f887b0dec9f1 | note | Reference Documents - Volume 1: WP 5131-1 and Clause 5131 (e)(ii)
b5b528e4-2568-58b8-8064-752fad3e023e | note | Inspection/Test Method - Notification
ba6edc9b-0b62-5b43-a7b5-8ef564d84846 | note | Record of conformity - This ITP signed by Contractor
3b51bc67-492f-5aa3-8cbb-bebc8c48edd2 | note | WP
b0259b15-7c6f-5e42-ad9f-e2796169e323 | note | Responsibility - Quality Engineer
5ab9c3e2-e828-50b0-a5c6-7a97a5283485 | date | Date Completed:
04eac989-535a-4dee-af37-c1196cb9935f | checkpoint | 4.5 - Non-Conforming Bitumen
0dbe6b31-63ee-57e1-9b46-85b34c9938a4 | note | Frequency - As required
0bf1c28b-c3e7-5ffb-8849-27eb34c06e40 | note | Acceptance Criteria - If the test results indicate that the bitumen in the tank does not comply with the requirements of the Specification, the bitumen represented by the sample tested must be deemed to be non- conforming and must not be used to manufacture asphalt for the Works. A non-conformance report must be recorded and submitted immediately
c16d5279-24e1-5d23-a6b5-3353bd3b4638 | note | Reference Documents - Volume 1: HP 5131-3
2bdbdcf3-f4b3-5e37-8d80-4052309d0f3b | note | Inspection/Test Method - Submission
2b1edd8a-457a-50ee-bf0b-8c4d89d66fa8 | note | Record of conformity - NCR / This ITP signed by Contract Administrato r
a8194884-ca54-59bc-9af6-0c14d63666f9 | note | HP
84f596ab-2e96-5a4c-ae64-6101d6f33914 | note | Responsibility - Quality Engineer
f04ef2d8-f9c8-5f04-a97d-3bdf9aaf6143 | date | Date Completed:
350f7473-22df-404a-ac9e-63d8921b6571 | signoff | AUTHORITY HOLDPOINT
1c661a3b-92e1-4f4c-994a-387c919c7bb2 | checkpoint | 4.6 - Bitumen Emulsion and propriety products – Test Certificates
20e3dbad-d4a0-5790-a6e1-5f8c4a9308e9 | note | Frequency - Not later than 24 hours after each delivery
010222e4-92fe-540c-b4d3-9497a802c237 | note | Acceptance Criteria - Each bitumen emulsion delivery must include a compliance test certificate and a delivery docket detailing the quantity, time, and date, both submitted to the Contract Administrator.
8edc6d7e-b26e-5f04-8443-ddb072c4f3f5 | note | Reference Documents - Volume 1: Clause 5131 (d)(i)
20ea7f38-fdd3-5247-83c4-a90ab47de03f | note | Inspection/Test Method - Submission
b5118143-ca5c-5f02-b85b-9e85e837bb20 | note | Record of conformity - Bitumen Emulsion Certificate and docket
47520994-8e60-5d7a-a896-b3576235ae1f | note | IP
7b9c5e3c-bc74-5c8e-8680-d252b1189908 | note | Responsibility - Quality Engineer
f1a761a2-ed57-5b56-a609-681532112a9a | date | Date Completed:
d404bc50-738a-415d-a5b8-dc8af8a8a7cc | checkpoint | 4.7 - Asphalt Production – Sampling & Testing
1744631f-af97-57a2-9401-e15235af81f0 | note | Frequency - Each Lot
401fd518-66fc-5d47-8c50-1da7ad57e243 | note | Acceptance Criteria - The number of samples and sets of tests on each nominal size of asphalt produced in the work period must not be less than that specified in Table 5131-4
4fdae860-3576-5488-9526-447567e3b04c | note | Reference Documents - Volume 1: Clause 5131 (e) (ii)
bb51a2a4-3056-59dc-9a96-05d903458ea6 | note | Inspection/Test Method - Verify
0f0d4946-62d8-5fe7-a2d6-2a8f217a9e9b | note | Record of conformity - Test Report
2e7cf40b-7776-5431-91a7-32a5fb90b7c6 | note | TP
a96724c5-d0db-556a-bedb-ec1c45c6f427 | note | Responsibility - Quality Engineer
631f0198-327e-55f6-bb11-2f6cdb9fc064 | date | Date Completed:
3916fad0-d354-4f43-9261-f4485ec9b1eb | checkpoint | 4.8 - Daily Bitumen Usage
591ecf81-86db-5ae0-b1b9-8ed6a57144ac | note | Frequency - Each Lot
75b7a3c5-680d-5969-b972-efd367374b62 | note | Acceptance Criteria - During each work period, the quantity of bitumen used in each production run for each nominal size of asphalt mix must be accurately recorded by dipping the bitumen storage tank or by recording the plant digital read- outs before and after each production run. The recorder bitumen usage must be included in the lot submission.
66102c70-2267-5a48-bd83-8bef0306c955 | note | Reference Documents - Volume 1: Clause 5131 (e)(iii)
68f67cdd-3af3-540e-92ee-02125cb70363 | note | Inspection/Test Method - Verify
b5f1670e-73bb-5858-9eba-5175494dcbe3 | note | Record of conformity - Asphalt Production Records
d68d8d0b-60a9-54e2-acb3-dedc27ca7cb9 | note | IP
dd8c11db-6aaa-5e25-b778-f7f3db13b2a6 | note | Responsibility - Quality Engineer
0a48c419-b821-56a8-855b-d7e3aae811f9 | date | Date Completed:
765e66d8-ed86-4290-a9eb-c35082da578d | checkpoint | 4.9 - Mass of Asphalt
eb6947a3-9bbc-5f35-8b7e-0a512bb11199 | note | Frequency - Each Lot
16125fe3-0a32-549e-9222-07263858b104 | note | Acceptance Criteria - The mass of each nominal size of asphalt mix produced in each work period must be determined, recorded and included in the lot submissions.
5698bb77-7c1a-5101-937b-f9c395dbd0eb | note | Reference Documents - Volume 1: Clause 5131 (e)(iv)
218925e5-a208-54a8-8619-85cd9b54cdc0 | note | Inspection/Test Method - Verify
570111aa-8ebc-56c4-8fef-21b3affbf5ae | note | Record of conformity - Asphalt Production Records
88f49786-d100-5eb8-93ef-45d5eb122f4e | note | IP
6b4b1eca-bc4d-5c25-a435-46b5e2c38a16 | note | Responsibility - Quality Engineer
575a1aba-d3c5-5e91-80f9-adef8c9edeb1 | date | Date Completed:
f3ee4ec7-bf1e-414a-a5d3-8ae7e8d3132d | checkpoint | 4.10 - Supplementary Bitumen Content Determination
a4c63226-e37b-5e27-bf16-0864249df0e4 | note | Frequency - Each Lot
a1777ec5-496e-54fa-abda-ae8cd5a7e009 | note | Acceptance Criteria - Calculate and report the average bitumen content for each nominal size of asphalt based on the total bitumen used and asphalt mass produced, and include it in the lot submissions.
3677b7c0-c68f-57b3-a7f0-0393bd5f814c | note | Reference Documents - Volume 1: Clause 5131 (e)(v)
4686db1a-fbbe-5cad-b381-ff9bc405d77c | note | Inspection/Test Method - Verify
df9c350b-e8a7-504b-9428-d64d77c5fc70 | note | Record of conformity - Asphalt Production Records
a2c827d3-c631-519b-b485-0991663fa9f5 | note | IP
a1875806-a271-5ee7-b048-65551cf489c0 | note | Responsibility - Quality Engineer
98a49ecc-66e3-5ef1-945f-472160645c9d | date | Date Completed:
6cd95be2-26cc-4f6a-98fb-855c4aa31fa3 | checkpoint | 4.11 - Bitumen Temperature Recording
d527300a-973e-5101-ab36-28bafb13cdc7 | note | Frequency - Each Lot
5fe943b9-4b02-55fc-bdb2-e644fc1038fd | note | Acceptance Criteria - The temperature of the bitumen in the storage tank must be recorded at the time of taking every bitumen volumetric reading and at intervals of not less than once every work period.
4235aa0c-cb35-5344-97ed-6e16b105ecd1 | note | Reference Documents - Volume 1: Clause 5131 (e)(vi)
107ba21c-6143-5361-ad04-f36bf33b3d26 | note | Inspection/Test Method - Verify
2ef0f96c-491d-560d-85e5-6d62549743cc | note | Record of conformity - This ITP Signed
85a7b2e0-2395-5af5-acc5-ed3b57ec166a | note | IP
4fec78a2-4f00-5405-ba3e-299c76b3b878 | note | Responsibility - Quality Engineer
610acd96-6bf6-5088-883a-2005e82281bf | date | Date Completed:
4a2d51d3-a83b-417a-8db1-faf392649452 | checkpoint | 4.12 - Asphalt moisture content
e2a08b45-5455-538a-9755-a7e7c63ed4a9 | note | Frequency - Each Lot
90a829f2-7eb2-5e88-af39-b617682c7057 | note | Acceptance Criteria - Asphalt moisture content must be determined at least once per lot when approximately 50% of the asphalt for the planned shift has been manufactured.
5c2a0bb9-ae52-5fa7-9078-8ddcfd47406b | note | Reference Documents - Volume 1: Clause 5131 (e)(vii)
0c6de3dd-e8c8-5d70-a1de-0072140c8d94 | note | Inspection/Test Method - Verify
9c07772b-eb1b-5041-b050-c2f22d4e281c | note | Record of conformity - Asphalt Production Records
e358eab5-0468-59d7-955c-a7b173ea022c | note | IP
e89068c9-ab77-5109-b74e-fadc4fcf33e2 | note | Responsibility - Quality Engineer
e7272ea3-b74c-5565-8dde-0adef5cd2a67 | date | Date Completed:
f525e115-867f-4d36-ad52-b78b9f8bcd3f | checkpoint | Final Inspection
37666f9c-de0b-59a0-aa2b-f28b0da904a7 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
d1615c0e-2a0d-5609-a2d0-612dcff92339 | textbox | Print Name:
b8b6dc22-5622-58f4-8740-e31355adbc06 | textbox | Position:
26ab37e2-27fd-5824-a321-18cef782d831 | date | Work Completed On:
2811771b-610c-5bd2-a16f-ef915e3fe4ff | date | Date:
628f9dae-9459-4865-83dd-e26d17be8a1e | checklist | FH-927-QU-ITP007 - AGL Removal of Luminaire, Installation of Shallow Cans and Luminaire Installation - Rev 0 | itp | ITP007 - AGL Removal of Luminaire, Installation of Shallow Cans and Luminaire Installation
2e23dfbf-e1b2-4a0d-b840-f6712aab3e22 | section | 1.0 - Preliminary Works
a5fa1837-c6bb-4191-9285-c8e44e503d16 | checkpoint | 1.1 - Check for correct documentation
9eb56052-dfe5-595e-8f8e-dca27dcdcc2d | note | Frequency - Prior to commencing any activity
cec55df0-0ec8-5e34-bbaa-f32880896656 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
bacd0f75-a3b9-5730-99f3-fb7c811d260d | note | Reference Documents - IFC Drawings Appendix K - AGL Specification
ee073e91-16ea-588b-87a5-e1dc0b47c0b5 | note | Inspection/Test Method - Verify
741bb28f-e437-50be-806c-6d8c26b63e05 | note | Record of conformity - Drawings
eb6340e5-8ebd-56fb-875a-80560d2c23c8 | note | IP
f754570a-9aac-5c10-94c5-b2c6112cf8f4 | note | Responsibility - Subcontractor Representative
b5381803-cdbd-5227-9498-a05e791454ac | date | Date Completed:
532bb790-d791-4d58-bd52-8dd2b6e7eef5 | checkpoint | 1.2 - Implementation of all measures and controls
4cd7de30-1bf9-51cd-8841-66dd5f64df39 | note | Frequency - Prior to commencing any activities
b739ca80-a32c-5bdb-af07-ccd155382854 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
6e160ce6-918b-59fd-be4c-b82249c2e61e | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
5b1fbd15-19d3-57e7-aae5-fbb97973e2d0 | note | Inspection/Test Method - Verify
7afa6138-0844-5a9d-9fa2-25429da05d9e | note | Record of conformity - Site and Office Inspection
c92fcd35-a766-5788-aa94-46ea20ffb9e0 | note | HP*
4c83abe7-4e80-5924-8b6f-8747d1d1690e | note | Responsibility - Site Engineer / Site Supervisor
21280251-5085-55e6-8781-95ddf3000725 | date | Date Completed:
61e58180-f743-4a64-b2d1-71c65ddfa598 | checkpoint | 1.3 - Material/Equipment Approvals and Certification
cf51fe3b-d719-5a09-919d-40e719c9f67d | note | Frequency - Prior to Start
b0222ab4-0b02-5b00-afc5-fed0043f5794 | note | Acceptance Criteria - All materials shall be proven to meet contractual requirements prior to acceptance.
6b85f21a-f987-5f55-91df-bcf41b61538b | note | Reference Documents - GHD-DD-SPC- 002 Section 2.4, Section 2.5
707d030b-7f0a-5636-90bb-a96bd974d07d | note | Inspection/Test Method - Verify
b7b2704c-f7dc-5f4e-b097-5a09bfa20039 | note | Record of conformity - Datasheet/ Material Submission
80e24163-a2a9-5f94-9fb4-1a35a41a46f2 | note | HP*
ac72aaff-c29c-5610-aa71-4b85172789f9 | note | Responsibility - Site Engineer
a35effc9-8c92-54ff-9c9c-23bd4b9662e9 | date | Date Completed:
909219f6-2fc4-4da6-b00d-fdcefde58b2e | section | 2.0 - Removal of AGL Luminaires and installation of Foundation (All light types)
5b7c36da-6ba1-4835-a7c1-f047ae835a8c | checkpoint | 2.1 - Setting out of Airfield Luminaires
90603e7b-95ea-54a8-b234-04e27d1e0696 | note | Frequency - Each Lot
57cc76fb-1b54-5f7b-a845-4f98ade52751 | note | Acceptance Criteria - Surveyor to confirm location of AGL with IFC drawings and confirm alignment of luminaires.
638270d5-08d1-5aa8-9026-a61b7411725b | note | ○ Existing lights shall be reinstated following the overlay works in their existing location and at their existing orientation utilising the survey data captured prior to their removal before the overlay works commencing.
a09d8175-b3a1-5121-ac61-0741ec8b8b1c | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.1
ca28b3f6-b4bd-5ad7-9441-04a0cdf6bb8a | note | Inspection/Test Method - Verify
c88f2ee5-63bb-5abe-8da2-4861c9b768d6 | note | Record of conformity - SCP
5b56b763-196b-54f8-a6c2-16724c9eea50 | note | IP
2738e6da-2791-50b6-be56-203678f3d8a5 | note | Responsibility - Site Engineer / Surveyor
62f5df29-e202-51ee-9b33-223fb306819e | date | Date Completed:
17abdbf9-33ef-4c6c-aecc-970516d50009 | checkpoint | 2.2 - Confirmation of pre- works
5094f88a-f790-5a54-b58a-948c51d4a009 | note | Frequency - Each Lot
3942dd6e-3836-5589-8360-d7c877074db4 | note | Acceptance Criteria - Ensure that the light to be removed corresponds to project drawings and documentation.
96932986-66b7-57e5-9223-a42e3153103d | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
81a92ec5-2fc4-55ea-b4dd-2ebf56a7a864 | note | Inspection/Test Method - Verify
6bdd2a2f-653c-558b-a755-d87ae169cf55 | note | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
1e1e3bbb-4825-5906-82da-b53576197074 | note | IP
7327319a-5dad-570b-8de0-11f408b94b78 | note | Responsibility - Site Engineer / Site Supervisor
0f5baf93-8eb0-5ffc-a0c7-312fb3d80f45 | date | Date Completed:
bd384c3e-cf5d-421b-97ca-17e005b730f4 | checkpoint | 2.3 - Light removal
3eb75e54-a2a7-5697-98fd-b6c0888dc04d | note | Frequency - Each Lot
5f939ccc-b625-591b-a31d-f85b059f9245 | note | Acceptance Criteria - Remove existing light and AGL cables from conduits as per Sub-Contractor ITC for the Methods 1 and 2.
2a801e11-b7f0-58ab-8044-453806f9ffd9 | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 Sub-Contractor ITC
696f5b6b-bfd9-5b88-8f04-5ae92b547fae | note | Inspection/Test Method - Verify
1c6b4bfc-06c2-55ce-b79e-b1e42394f250 | note | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
af7c23aa-5c13-5ab7-bd91-5dcce50d1489 | note | IP
37797d21-efe1-596d-a8b8-bd835340356e | note | Responsibility - Site Engineer / Site Supervisor
8be72e6a-9cb3-5320-b491-a54dc028f8a9 | date | Date Completed:
efa51d29-7757-45d2-a980-c80c0c56bd06 | checkpoint | 2.4 - Isolation of lights
52816959-2feb-51f4-8137-1b4fd40305b2 | note | Frequency - Each Lot
2ddeafdd-9c31-554b-b515-ec55d27fb984 | note | Acceptance Criteria - Prior to commencement of removal, the subcontractor shall ensure that the light has been isolated from power.
5ad0c991-d7f1-5595-a568-1789cc9d81c3 | note | Reference Documents - APAM Electrical Isolation Standards
579025af-129d-5f97-a444-86bb7ab57694 | note | Inspection/Test Method - Verify
1a2d9bd4-814c-52c2-88ce-e3cb4fd5a7df | note | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
23aa684a-0260-57a8-b525-8f37d162f38a | note | IP
dcda2334-2cd5-5581-9ecd-51fbd7a9f313 | note | Responsibility - Site Engineer / Site Supervisor
c50b2614-f11a-56bc-bae2-7ec551781a9c | date | Date Completed:
0e352a1c-74b5-470f-bf3a-e9749366ddc7 | checkpoint | 2.5 - Coring
6b060a8f-d869-5bed-a33d-dfbfa191bc9e | note | Frequency - Each Lot
1f234ec1-2343-5563-945d-b7e79fadf1b5 | note | Acceptance Criteria - Core pavement to required depth as per subcontractor ITC for relevant Method.
45dc76e3-1f3c-58a4-b038-cbb8123eff48 | note | ○ Remove base and clean void.
f79924cb-d9b4-545e-96b7-ce9e17434e96 | note | ○ Existing AGL secondary cables removed after coring.
78e7f663-f0e7-5088-a769-a74fa14140af | note | Reference Documents - AGL Subcontractor ITC CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
5dc78a55-9f43-597d-a057-79caec9a47ac | note | Inspection/Test Method - Verify
060126e3-85e0-5c66-9ff5-28f57b01606b | note | Record of conformity - This ITP Signed & AGL Subcontractor ITC
98b59741-fcda-53c3-a1f1-55b92affaa57 | note | IP
edcee0db-3772-5b4c-8b5f-742fe30abe2b | note | Responsibility - Site Engineer / Site Supervisor
34095f50-298d-5d3e-a030-edf13ee9fc65 | date | Date Completed:
81917d29-6e35-4c5b-b9d1-6ae4d942667c | checkpoint | 2.6 - Blanking Plate
e84ad726-9809-5b5a-b2ed-d10bcd0a3335 | note | Frequency - Each Lot
3ef6da7c-0ac3-5ba8-a16e-84461e8a0c18 | note | Acceptance Criteria - As required, core holes and luminaires to be safeguarded to allow for placement of asphalt with a Blanking plate.
87a7bbd7-5887-54be-9651-d74ec1cb1d63 | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
be0970cf-7668-5f95-a2fb-d380960472ae | note | Inspection/Test Method - Verify
db441785-c248-5942-81bc-7c1a0820a525 | note | Record of conformity - This Signed ITP & AGL Sub-Contractor ITC
eebda4fe-2d2b-5afc-90ac-0ec86b147287 | note | IP
38927bce-2861-5b69-a39c-85e5260ea548 | note | Responsibility - Site Engineer / Site Supervisor
7e5b6fed-2045-5f47-8ffb-0746fa6fe90c | date | Date Completed:
c7740bb6-a871-4bd9-9d8d-afe95094638b | checkpoint | 2.7 - Light storage
49ca107b-d401-566e-b61a-1b879a94d1e8 | note | Frequency - Each Lot
90def926-b77b-58e2-a157-acdad4fc780b | note | Acceptance Criteria - After removal of the light, the subcontractor must ensure that the light number and position is recorded and stored accordingly for re-installation.
4bfcab98-4ca1-5df5-a8dd-94352dbdc917 | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031
cbafc7d2-32fe-5f12-bb27-0de57b991436 | note | Inspection/Test Method - Verify
44cbdba3-db54-53c2-8bd5-768d5cbe2168 | note | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
baba23f4-6485-55a0-9575-3cdb0047eee6 | note | IP
57413cd8-4039-5159-a6ac-687ee3191d8c | note | Responsibility - Site Engineer / Site Supervisor
690e54b2-e7e8-5a60-afa2-26fe600990c7 | date | Date Completed:
79674210-6eac-4fa5-8cca-bb4eab57fa30 | section | 3.0 - Installation of Light Foundation
445bc731-d292-4c5a-a3bc-51dcb54bc8c9 | checkpoint | 3.1 - Setting out of Airfield Luminaires
60bf8443-96b0-51a5-b1db-7f3f7d7131bb | note | Frequency - Each Lot
e56241d4-ea31-51fe-bf7e-3cfabe1f09f7 | note | Acceptance Criteria - Existing lights shall be reinstated following the overlay works in their existing location and at their existing orientation utilising the survey data captured prior to their removal before the overlay works commencing.
85e6547a-b1d9-5d8c-af5f-3e4fc32b7a9c | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.1
31150bad-36a7-502b-9217-786272da8b06 | note | Inspection/Test Method - Verify
f17a3fe2-061a-5ea9-a5fa-bc153be73ee7 | note | Record of conformity - SCP
f22f389a-c4ff-5088-a976-87a124e4f013 | note | IP
530b162d-9fdf-55fa-8aff-7e6dc4248fa6 | note | Responsibility - Site Engineer / Surveyor
cf1dd12c-9f6b-5558-8b4a-bb9b4a0ae809 | date | Date Completed:
c1dfca71-68bf-4644-a200-fa757f1b697b | checkpoint | 3.2 - Coring
9ec66ecb-d413-558f-b27b-05effa0e2f85 | note | Frequency - Each Lot
dd0355f6-8036-5f31-b9ab-40c0b43552f3 | note | Acceptance Criteria - Core pavement to required depth as per subcontractor ITC for relevant Method and Section 3.19.3 of Specifications GHD-DD-SPC-002.
50d80f39-5c98-5a05-b78d-be2511f2d806 | note | ○ Remove asphalt core and remove blanking plate.
61d7ce28-b03b-54c2-a6b8-3ecae3179dce | note | Reference Documents - AGL Subcontractor ITC CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC- 002
037b2813-192e-5c04-900d-3a42175ff5a1 | note | Inspection/Test Method - Verify
61f60495-c036-5c81-ad08-5449db247e06 | note | Record of conformity - This ITP Signed & AGL Subcontractor ITC
ba42180e-8b43-5c2f-b2af-63152788fd19 | note | IP
09ab6817-ce9a-5203-9cb9-4bb2726ef090 | note | Responsibility - Site Engineer / Site Supervisor
386e5eed-58f2-54b5-a350-d84ffc5c0000 | date | Date Completed:
43aa15f2-72c7-49aa-af65-c1f89919cf0c | checkpoint | 3.3 - Installation of Light Base
f328c3f2-684b-525f-a9ea-4b0e3f374ffa | note | Frequency - Each Lot
fc8dc1e7-c1ea-5829-ba5f-0ad82518d731 | note | Acceptance Criteria - Method 1:
3e94b54a-9c40-50c5-acbd-e2cb164bbf22 | note | 1) Re-instated Light Location is to be picked up by survey as per Section 3.19.1 of Specifications GHD-DD-SPC-002
806c8508-104a-5580-9923-f4107f8b73e6 | note | 2) Secondary cable and earthing are to be places in Slot cuts
794c8fc4-56a2-5c4d-a05d-bcd815960ac3 | note | 3) Reinstall existing light and reconnect secondary cable and terminate earth on light base as per Sections 3.12.4 and 3.19.3 of Specifications GHD-DD-SPC-002
2577b90f-6617-5488-89e7-a82aa782e365 | note | Method 2:
a44ba48a-55dd-5d18-9f31-de154f1d3e52 | note | 1) Re-instated Light Location is to be picked up by survey as per Section 3.19.1 of Specifications GHD-DD-SPC-002
caa36e01-04b1-5d67-877b-4b502c3aa6ee | note | 2) Reinstall existing light and reconnect the existing secondary cable and connector as per Sections 3.12.4 and 3.19.3 of Specifications GHD-DD-SPC-002
3566743d-3ca4-58ed-942d-f44ddfde991b | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 Sub-Contractor ITC
93e2206f-b260-590d-a0a7-135a62fd6ad9 | note | Inspection/Test Method - Verify
e3415636-a45e-596e-9359-47a91afca756 | note | Record of conformity - This ITP Signed & AGL Sub-Contractor ITC
3c9b7ce5-d0f6-5b5c-99d4-a55018c910d4 | note | IP
aebaf6c7-7826-5054-be9b-d04f5156951f | note | Responsibility - Site Engineer / Site Supervisor
3a58bb80-e9df-59af-bcaa-c09f4553ba7b | date | Date Completed:
a37fd2f4-af02-49a9-92f8-0421591e4c13 | section | 4.0 - Installation of AGL Luminaires
81962dfe-df1f-4936-9530-34bdd3d25e69 | checkpoint | 4.1 - Installation of Inset light
c38b0d4d-464d-514a-b284-e93b50b90e9a | note | Frequency - Each Lot
7c612a6c-702c-585b-b1a8-7df2dff96a16 | note | Acceptance Criteria - A jig must be used to install, locate and level the inset light unit base in position in the core hole and maintain the base in position during the curing of the epoxy grout.
c020d1d6-6c5d-55a0-907f-28d2d78bb1c2 | note | ○ Ensure correct light is installed in correct position and rotation as per the IFC drawings, this ITP and ITC
dd63f666-2d1d-5346-8e9d-ceba1e1cf5a2 | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.6
344c60ae-c78e-5e70-b3b4-a708fcb34084 | note | Inspection/Test Method - Verify
baafcfd7-2a23-527f-acfd-ee16d49ca60d | note | Record of conformity - This ITP Signed & Sub- contractor ITC
5f1969ba-a6d0-58dc-95fb-7e15f237b3a3 | note | IP
92d03496-fabe-5665-92fa-6654bfff97be | note | Responsibility - Site Engineer / Site Supervisor
a67db9cf-8375-527a-b03a-1b054a25f20b | date | Date Completed:
3d817f07-fcf3-412d-8ad9-fab5f4e3bdec | checkpoint | 4.2 - Light Fitting Functional Check
952f5c4c-4319-59c7-8baf-f7eee7790677 | note | Frequency - Each Lot
98629ad4-fb60-5ed3-835e-862d75e8793b | note | Acceptance Criteria - Light illuminates correctly (aiming, orientation, existing colour) as per existing photometric specs
369c719c-5983-5149-b9fa-a742e64c77f0 | note | Reference Documents - CP1024-GHD- AD-L00-DR- EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031 GHD-DD-SPC-002 Section 3.19.6 MOS 139
e164a8c9-cb40-54a5-9903-3645767120d9 | note | Inspection/Test Method - Verify
6e5d34f2-b21e-5fe1-8485-95f2e75f1067 | note | Record of conformity - This ITP Signed & Sub- contractor ITC
227377d6-d826-5994-acae-46636f0756c8 | note | IP
b6e08a1c-cee8-53ce-a14f-365ed7887fdc | note | Responsibility - Site Engineer / Site Supervisor
5e59fb8d-8f24-506e-ae9b-f69ba944b5f8 | date | Date Completed:
734ff8d0-ece8-4272-a79d-341452ee80e1 | checkpoint | 4.3 - Cabling and Earth Bond Verification
2f62ae11-b7c5-5992-96fc-c1ca7ee0b245 | note | Frequency - Each Lot
d127b8c0-3331-579e-9266-00c69e8bffd1 | note | Acceptance Criteria - Termination as per IFC and testing requirements of AS/NZ 3000
8593d4c2-bca4-5920-8c5a-74a6e26941b8 | note | Reference Documents - CP1024-GHD-AD-L00-DR-EE-0003 to CP1024-GHD-AD-L00-DR-EE-0031, GHD-DD-SPC-002 Section 3.19.6 AS/NZ 3000
36290b83-b28a-5dc6-ab9e-152e23caff3d | note | Inspection/Test Method - Verify
0e25c909-d09e-512a-a4c0-b852800a3546 | note | Record of conformity - This ITP Signed & Sub-contractor ITC
bd50e7ca-03ee-59cb-9fc2-a63ee2e56569 | note | IP
28200766-2d0c-5bf4-9b1e-fb0c9debcb8b | note | Responsibility - Site Engineer / Site Supervisor
4f51083e-e17b-5bdb-8e56-b58201bc7f99 | date | Date Completed:
0140bac2-0cef-476c-88cf-c4fe08778a19 | checkpoint | Final Inspection
4750e419-f93e-53a8-b2e6-0545be98912a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
32cf1118-97c0-51d9-b7b3-0cd6b9929a93 | textbox | Print Name:
5572b201-45bd-5edb-9fe6-c47a7cb10cac | textbox | Position:
ac5af606-7739-544d-a02d-325ec0d75d4f | date | Work Completed On:
7e813865-d01a-5dc1-a0d1-be93de3286b7 | date | Date:
ade14335-82c9-4754-8934-d6cfe4a7e265 | checklist | FH-927-QU-ITP008 - Runway Grooving of Asphalt Surfacing - Rev 0 | itp | ITP008 - Runway Grooving of Asphalt Surfacing
689fb04b-45ac-44e8-b8e6-32cbbc2b5715 | section | 1.0 - Trials
89068953-1628-4da6-b630-470f11268ef9 | checkpoint | 1.1 - Trial section of grooving in new asphalt surfacing
85370a73-a8fa-59bf-bb63-1acb315e5a68 | note | Frequency - Prior to the commencement of grooving works.
e0e88bc1-daaa-52dc-918a-a2f82d278422 | note | Acceptance Criteria - Construction of a trial section of grooving that complies with the requirements of Sections 2 and 3 of this ITP.
45033f1a-33a2-5989-a98f-c9284fe2c09d | note | Reference Documents - GHD-SPC-001 7005, HP 7005-1
50ee7d49-29fb-55b2-b67c-95ea07b4c1ea | note | Inspection/Test Method - Inspection
dc95e2e2-4c6b-557e-a684-b3afb43a345a | note | Record of conformity - This signed ITP
5020b356-5673-527a-a326-7e84453f0872 | note | HP
f57f8102-7a67-564a-88ca-395483a6892c | note | Responsibility - Quality Manager
245ac754-95f0-50ce-b271-957b91257e28 | date | Date Completed:
7f4440ef-5e2b-429f-aadc-12a948bf9c4a | signoff | AUTHORITY HOLDPOINT
c7473b90-ecbf-4e26-b910-67d8a9eb6565 | section | 2.0 - Grooving
71ced464-9e1d-4933-9b06-ce6a05fbd816 | checkpoint | 2.1 - Commencement of grooving in new asphalt surfacing.
54520e62-dc1c-521c-8697-264fcd06ae05 | note | Frequency - Prior to the commencement of grooving works.
6a3bf879-35d4-5abd-ba9b-7c50155abd40 | note | Acceptance Criteria - Grooving of asphalt surfacing commenced no less than 8 weeks after the completion of the construction of the asphalt surfacing.
2d27c563-b893-54dd-9a00-837ec0f2bbaa | note | Reference Documents - GHD-SPC-001 7004(a)
84a45a6f-e12d-58ac-9321-3070bb222de2 | note | Inspection/Test Method - Inspection
38626c72-e94d-5d2c-be70-24e8ca672696 | note | Record of conformity - This signed ITP
933c6ffc-4e79-5fe8-bd5f-b4d39073c9ee | note | IP
9daaeb6b-f28a-5775-93ec-8c04301d2c77 | note | Responsibility - Site Engineer
59adbd10-6880-5900-966e-c17095017486 | date | Date Completed:
68cf2183-e9b2-49af-b7a5-c20e192a9e31 | checkpoint | 2.2 - Grooving of new asphalt surfacing as per specified dimensions, length, extent and shape.
7287731f-2a7e-5523-bc30-d903c4fe1216 | note | Frequency - During grooving works, on at least 15 randomly selected grooves within a lot. Submission of groove lots to be within 48 hours of completion of a lot.
add71c52-a9d0-5cd3-ba93-89f227ee865f | note | Acceptance Criteria - Width, depth and spacing of grooves are as indicated on Drawings. Floor of grooves are parallel to the finished surface of the pavement. Square grooves are square with sides perpendicular to the surface of the runway; trapezoidal grooves are a consistent trapezoidal shape and not round or semi-circle. The deviation from specified groove shape is not more than specified in Note 1.
6d039e12-7a2c-5da7-bb9b-5ac2cb6b6ef3 | note | ○ Grooves are cut continuously across the width of the pavement and are cut to extend over the length of the pavement, as shown on the Drawings.
3eb350e0-3496-59fb-bc30-77d6cef6846f | note | Reference Documents - GHD-SPC-001 7004(c)(d)(f)(g), Table 7007-1, WP 7007-1
9197a377-8b6b-5c4a-9018-b946e6dbeecd | note | Inspection/Test Method - Inspection; random selection in accordance with AS 1289.1.4.2
e3a6dc61-1943-5def-b51f-a582366e7cc6 | note | Record of conformity - This signed ITP
d8873b9d-fe14-5d78-9c27-6d7b6af58354 | note | WP
e7bdcc1c-def2-573d-8165-7ffbda2cab07 | note | Responsibility - Site Engineer
93a476dc-8efa-52aa-9935-6f5451c5d3d4 | date | Date Completed:
73b9427b-94cb-403e-b532-1071a5ae81bf | checkpoint | 2.3 - Grooving of new asphalt surfacing as per specified alignment.
3584b706-e387-5e51-b2dc-1b58f8e823ba | note | Frequency - During grooving works, on at least 15 randomly selected grooves within a lot. Submission of groove lots to be within 48 hours of completion of a lot.
927182af-7b7a-5a14-b708-54834cc37c5f | note | Acceptance Criteria - Alignment of grooves reset to truly perpendicular to the runway centreline at 150 m intervals along the runway.
4398f927-e743-5b02-9a0e-55681af2c786 | note | ○ Grooves are cut in parallel straight lines perpendicular to the runway centreline and comply with the requirements of Note 1.
0354bf0b-0478-501f-b52e-7fdf523dbc5b | note | ○ Grooves on rapid exit taxiways are in straight lines and oriented as indicated on Drawings.
2d338016-3f65-53d2-8b61-f1b91aab468e | note | Reference Documents - GHD-SPC-001 7004(e), Table 7007-1, WP 7007-1
7629b990-b247-5441-8068-049ff405a105 | note | Inspection/Test Method - Inspection; random selection in accordance with AS 1289.1.4.2
0a898d05-1e0a-5e7b-83b0-898295bc51d2 | note | Record of conformity - This signed ITP
f641b53d-1825-51e3-8062-4ec2276894a7 | note | WP
b86e7acc-a88c-56f7-8183-d3f93b23591b | note | Responsibility - Site Engineer
c85d189f-9e87-5f0b-8d1f-3241761010b4 | date | Date Completed:
2f51d1b2-e5ea-42fd-9676-e06f616a9fb1 | checkpoint | 2.4 - Grooving of new asphalt surfacing near inset light fittings.
15918721-3b4a-5748-8ac0-b53606ed7544 | note | Frequency - During grooving works adjacent to inset light fittings.
08836870-ca0d-5c29-885b-ba3462e8e141 | note | Acceptance Criteria - Grooving is stopped to leave a regular (rectangular or square) ungrooved area symmetrically surrounding the light fitting. Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any inset light.
f732bc6a-bfeb-5b61-a648-2f447d38dc6a | note | Reference Documents - GHD-SPC-001 7004(h)
9ea1e305-9dd5-5bb4-8b24-f34abbc6ea9e | note | Inspection/Test Method - Inspection
370c10e5-8eab-5bdc-ba61-890798da015b | note | Record of conformity - This signed ITP
905d3fca-f3c7-5bb8-8387-766226c47aed | note | IP
dc698b8f-7c8d-5889-a4b8-c6aef1c7da27 | note | Responsibility - Site Engineer
84eab9cf-5445-5926-860b-bed2ca409de7 | date | Date Completed:
d1c6e6ae-b277-4c44-bab9-db991b1665ca | checkpoint | 2.5 - Grooving of new asphalt surfacing near cable slots.
78207ba8-4256-5b08-8d34-7b42d38b9a3c | note | Frequency - During grooving works adjacent to cable slots.
713a9d37-6700-51ce-a441-c127621698ec | note | Acceptance Criteria - Grooves are not sawn closer than 150 mm and not more than 900 mm from the edge of any cable slots.
d480ad65-2e96-51a5-8d0b-a079bd2eed6d | note | Reference Documents - GHD-SPC-001 7004(i)
236495e3-c495-53d6-9898-6426df2f5a74 | note | Inspection/Test Method - Inspection
80c16b78-898b-59f0-8c46-a63583c3bfe9 | note | Record of conformity - This signed ITP
6d5d91aa-6ab3-5b41-867d-7e4574eb6c35 | note | IP
d00af3ac-ff83-5d03-907d-af2f591c9dcf | note | Responsibility - Site Engineer
5151d0b4-de70-5b59-9b9c-7103509ee288 | date | Date Completed:
f87a22e9-2717-4737-bffa-1e0505d58400 | checkpoint | 2.6 - Grooving of new asphalt surfacing near cable arrestors.
bfaef363-6038-5b2f-89cb-65b831fd4f9e | note | Frequency - During grooving works adjacent to cable arrestors.
d97226d2-8e14-5a05-9dfa-626c3e834c9d | note | Acceptance Criteria - Grooves are not sawn closer than 3,000 mm each side of a cable arrestor system.
120c61b0-1c7f-563c-b923-4a41da009b2b | note | Reference Documents - GHD-SPC-001 7004(j)
86d37de4-9784-5193-b447-f7d820343066 | note | Inspection/Test Method - Inspection
1ad67d07-ebab-520a-b767-87b45a016e45 | note | Record of conformity - This signed ITP
538fbacc-ba32-5805-b102-46ca02c5b9d6 | note | IP
9e2aa1c1-fa0b-51e6-8d9f-6a8d3602cf11 | note | Responsibility - Site Engineer
0d119c26-5380-5003-9660-51c7d892dacf | date | Date Completed:
3821e847-66a1-44e7-a497-cd0d2ae05116 | section | 3.0 - Slurry Removal
1b9f312f-94c4-4d8b-b737-99a1ad75bbca | checkpoint | 3.1 - Cleaning of grooved surface.
9c11d751-be42-56f1-96ad-d5dcf454db91 | note | Frequency - Progressively during grooving and at the completion of grooving works.
2487c66f-bbef-5f82-ac19-aeada09cea2c | note | Acceptance Criteria - Slurry produced by grooving equipment is flushed from grooves as it is produced and removed by suction into a mobile container. Residual slurry is removed to produce a clean pavement free from all material arising from the cutting of grooves.
4432e2b8-53a6-51ae-a08d-929e374d69e5 | note | Reference Documents - GHD-SPC-001 7006
9076c046-e0a9-5639-b9d9-a17f92c1bf05 | note | Inspection/Test Method - Inspection
19e01e09-d672-590d-9fda-1dedad411d3b | note | Record of conformity - This signed ITP
e880bf1a-6063-5e01-9be4-1f8575a4a775 | note | IP
4b105b8b-dd76-59a6-92be-ceb402942f31 | note | Responsibility - Site Engineer
9f6eee9f-777c-5c1e-8ab4-4955fda2e0ed | date | Date Completed:
a41f440c-85c2-4456-aad3-37bc5f1545f3 | checkpoint | 3.2 - Notification of completion of cleaning of pavement surface.
e3d013ac-f3c7-5f16-a6d6-8fae26d338ae | note | Frequency - At the end of each work period in which grooving works have been undertaken.
34d883d8-8e1a-5e67-9298-39d91d807715 | note | Acceptance Criteria - Contract Administor is notified of completion of cleaning of pavement surface.
8dbbed4c-8eeb-57c3-9ce7-fcf12dc94175 | note | Reference Documents - GHD-SPC-001 7006, WP 7006-1
29069c86-2604-5f60-828f-c3617a8c8e21 | note | Inspection/Test Method - Inspection
fddb18ef-0986-550f-8f68-93ebe6632006 | note | Record of conformity - This signed ITP
99d33dfa-75b0-5e0b-9400-6fcc9ab375d8 | note | WP
6fd66d81-c91c-502d-9554-650ff2de72b2 | note | Responsibility - Site Engineer
833f9d60-94a7-5846-a21b-a0092da3b4d0 | date | Date Completed:
bc29e60d-8e66-47e5-bcee-2c14dd83b497 | section | 4.0 - Quality Assurance
fe11b69a-f326-4d2b-b68a-2ec1286d94ee | checkpoint | 4.1 - Compliance
980aed18-e864-5766-ae49-8b4e0ce21a1d | note | Frequency - Lot information to be submitted within two weeks of completing works.
d15b0da8-27f0-5847-a9b7-7c1939f60a4b | note | Acceptance Criteria - The Contractor must measure the requirements for grooves specified in subclauses 7004(c) to 7004(g) on at least 15 randomly selected grooves within a lot. Random selection must be in accordance with AS 1289.1.4.2. Lot submissions must be within 2 weeks of completing works.
9716af25-dd42-5418-bf62-17efef2d3ed5 | note | Reference Documents - GHD-SPC-001 7007(B), WP 7007-1
3e7998cf-2f12-55f4-8a4a-2e565ce42546 | note | Inspection/Test Method - Review of Lot Submission details
76667453-d101-5b24-9921-42cd98d08d55 | note | Record of conformity - This signed ITP
30328097-eb0a-5909-962b-ad763f8e4b32 | note | WP
88cff047-a9b4-59d5-bf36-a923acf1c002 | note | Responsibility - Site Engineer
19a17d06-4578-56c9-b548-11314fba1609 | date | Date Completed:
30a0741d-9fe5-4bcd-a812-6e1441383808 | checkpoint | 4.2 - Non-conforming work
bd292cd5-3af6-541e-bd97-eb8858c85e31 | note | Frequency - As required throughout the completion of works
9a1c0162-c72d-5ae1-9690-d6ce6fb062dd | note | Acceptance Criteria - Any grooves that do not meet all the requirements of the specification must be deemed nonconforming and the work must be rectified to comply with all requirements of the specification. Where rectification requires the removal and replacement of asphalt or concrete, all requirements of the specifications must apply.
8a9ef6f6-3bbb-510a-afcf-f8e68f4e01f1 | note | ○ Any damage to other infrastructure (lights fittings, drains, manholes, adjacent pavements, etc.) shall be recorded as a non-conformance and the damage made good by the Contractor to the satisfaction of the Contract Administrator at no additional cost to the Principal.
5f243c42-bf43-5285-9ae0-96582270310d | note | Reference Documents - GHD-SPC-001 7008
f969ecaa-b933-50c0-934e-ffe1e85a6067 | note | Inspection/Test Method - Verfication of Remediation method.
34b12699-0f4c-5338-8249-077944574def | note | Record of conformity - This ITP signed by Contract Adminstrator
f7ceda83-a3f9-5f74-80fa-9a255a7872ac | note | HP
7e5fd112-61e6-53da-ba37-e0e6cdfa1acb | note | Responsibility - Site Engineer
136ec89c-ec5a-5993-803a-8c69b77d6990 | date | Date Completed:
d7112cd0-9ab2-4f86-ae85-b42fb4f7018d | signoff | AUTHORITY HOLDPOINT
de92510c-7922-4de9-ade7-22642c4d139e | checkpoint | Final Inspection
d0eefab8-2a1e-5994-b7c2-64a300bd6499 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
148fae91-9851-5cd1-a2af-b82b59bc334a | textbox | Print Name:
37aac08f-e861-5ce1-9326-3abb674b4efa | textbox | Position:
a53e9f6a-4c6c-5bab-8907-17210b843f94 | date | Work Completed On:
a7fa989e-b875-56bf-bc51-09bfd0441f4a | date | Date: