## Master List Templates
Id | Type | Name | Values | Prompting Name
d5edd73c-b54a-41c5-b43a-75fa11528a09 | checklist | 1. Prepour (Secondary and Primary cage inspections) |  | Cage:
da4f98a0-8614-4fd6-ac43-c17351e2a819 | section | Reinforcement Cage Inspection (Secondary Welding)
28f6aee5-36b0-4966-afe5-1908ae388d44 | checkpoint-no-value | Cage inspection details
a12aee59-fab4-58f1-bdb2-874f033d3898 | textbox | Cage Length (+/- 50mm)
7b0dfeec-da61-4e92-ac5e-5a6e8cae9fb8 | checkpoint-no-value | Pole Cap
6212ee1b-480b-5604-a0ae-056383a6be76 | textbox | Size
7f6f320c-f0cf-58cd-ac7f-61be61c5d2e0 | button | 4No. Welds | Y, N
9d6c7a70-adb1-5158-be4f-5cbe86cad4d4 | button | Seated Square (+/- 2mm) | Y, N
d5954709-d4f9-4551-89d0-9212a42a2cd6 | checkpoint-no-value | Fittings Drawing Number
6eba38d5-f80d-5ed9-8ee9-37feb02595fb | textbox | No.
de2cf11a-067d-4729-bbb1-0fb4215c4020 | checkpoint | Correct Type & Number of Studs
6bf02e81-5131-4d1d-960a-0b6df2e18bbb | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
a87d756e-647f-547f-88d2-637ddfb53f2c | textbox | - Tubes & Hole Formers (±3 mm)
3c1424fe-8465-5756-9138-eaeb96de0e62 | textbox | - Earths (+/-10 mm)
d683c163-cc26-5504-a29e-8877fd5239b4 | textbox | - Steps (+/-10 mm)
5a57e313-8cf4-5f91-8c58-5230622f7de5 | textbox | - Others (+/-10 mm)
af8ed886-0c16-5302-b47c-e9b1648bd32e | textbox | - Splice Wires (+/- 0mm)
a6a6fda3-8a28-555c-a298-31f6255f6b04 | textbox | FWB (+/- 0mm)
70258266-c588-42b9-961c-4b42d47702fb | checkpoint | ANTI-ACCESS Wires
0e02dabe-41a6-4077-91f4-3ba1474ddab0 | signoff | Accepted? (Y / N) (Initial)
99119a72-7096-4fd2-86ed-39ee4cb1b2c8 | section | Reinforcement Primary Cage Inspection
2b4ac30a-2a87-41c0-99f9-68abce086380 | checkpoint | Cage Diameter Check (mm)
246e84c8-5882-5d42-9037-f5ab9cd8c341 | note | Distance from Tip (m)
56f69229-0ca4-5ead-b400-48bf7c36207a | textbox | Tip
bd15674c-050d-5870-a456-371361a81dab | textbox | 1
1a803f76-9c3f-5ff4-bba2-c558721c6994 | textbox | 2
b10e1562-25f6-537c-ba2f-c7d9408de1ec | textbox | 3
f3510cd1-caf0-5173-9bd2-f801e9c9d1c2 | textbox | 4
9fdc6569-5419-5d30-8e38-332ccfce09a8 | textbox | 5
7f6cb4b7-ffb4-5324-87f0-c5e84461164f | textbox | 6
af9dbf0d-592a-5496-a281-62451733764e | textbox | 7
0f28fe46-52f8-5cac-8e24-57ca60433de1 | textbox | 8
297160b4-985e-5acd-b3de-b0779316b452 | textbox | 9
3cedc558-7262-5c7a-ad55-b3bf7a0e7e11 | textbox | 10
abb9bb95-e4cd-5610-aa29-6024422be967 | textbox | 11
2da01ae3-35ad-5b1f-9b9e-9f20dfcb471e | textbox | 12
9c113825-8d2c-5312-8a64-23637ad7a2ff | textbox | 13
3d8aff04-3871-5a32-8516-f97f2c0cf30f | textbox | 14
74f160e8-0d0d-53c8-901b-09774790e4e8 | textbox | 15
a8bb4efc-839a-531b-a804-587e5e720c54 | textbox | 16
64853837-d54b-5d67-bbc9-e74b43f52388 | textbox | 17
9bd573c9-5850-5db7-a0bb-ffe688e143c6 | textbox | 18
07a26924-6b71-560c-b7c5-dccbfc76365b | textbox | 19
8d9d5255-c74e-5cbc-a87a-b7e9a7e19c4b | textbox | 20
37377c22-2ca6-5db3-9ec7-f7c5676e0661 | textbox | 21
8e37db82-1a65-55a2-ab0b-b7244ecdcfc2 | textbox | 22
8a507c0a-faa7-5e93-8b5c-117f9c48902e | textbox | 23
22db83f3-b6f4-5370-8c48-6783ffdb557b | textbox | 24
79567ae8-8540-4817-a3fd-36e5abc40f5b | checkpoint | Check Pitch Finish - Distance from Tip
50b25b8c-fcbd-5429-9219-654d0f2ee038 | textbox | 40 tip
2b355bc4-1f3b-5289-8c30-8f03aa1cccc4 | textbox | 80 tip
626cdb5e-0b4e-552c-82dd-47b1a051e020 | textbox | 160
a011abcd-46db-5669-b576-ac1ba0caf7e1 | textbox | 80 butt
94aa81e5-4468-5036-993e-34bc9289d42f | textbox | 40 butt
8e039770-6d8e-5d36-b2cf-797da9a1d1db | textbox | Other
957bee6e-c8f8-4a20-a985-93afe4502c8e | checkpoint | Check Longitudinal Start Distance from Cage Tip
d8114925-f7e4-58e9-9d8e-422d53b85316 | note | Number of longitudinals
3f1cac91-34df-5d6d-8e3c-d3f800382bad | textbox | 4
5f932ad2-b3c4-5120-a046-94ef5de088a0 | textbox | 8
50c832ed-6e75-5799-902b-e0e7da925401 | textbox | 12
06ac7afd-aa67-57f3-81d0-a9f69cf3cdee | textbox | 16
f1f955d0-75e6-5137-a1cb-c2492c71df1e | textbox | 20
691de0bc-83e7-5c2d-ae68-eadeb63cd9fb | textbox | 24
89218e4f-396a-5799-ac54-b6907608bc06 | textbox | 28
9f7cc304-08a7-57eb-978e-c0e66d138fd3 | textbox | 32
85f46b13-3daf-5140-ac64-cbafe6e46e0e | textbox | 36
7721c84a-6c2a-5957-a0c9-0c16a050772f | textbox | 40
aaa10200-b777-5322-af1d-1f8ec0cb9f47 | textbox | 44
8f9ede12-ae1a-57e7-9521-3cdda9fe6512 | textbox | 48
192aab2f-3fc4-4d0a-b930-88a878fc1e03 | signoff | Accepted? (Y / N) (Initial)
fd927f6c-a38c-48ed-bc37-60b54723bf78 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3246 |  | 11/16 P/COR - Cage:
7a837aa2-c13c-4ddb-8dab-a824b39a7790 | section | Reinforcement Cage Inspection (Secondary Welding)
053acf10-b4e1-4feb-af01-725d657e76b1 | checkpoint-no-value | Cage inspection details
f77ea5fe-f44b-5ac3-a3bf-16699f8bf203 | note | Fittings Drawing Number: 3246
e3a078d6-6173-5775-a959-727a13d5490e | textbox | Cage Length (+/- 50mm)
1c0cdd38-4b92-4c90-938d-2cc7d2b052b3 | checkpoint | Correct Type & Number of Studs
b0767ab1-3ed0-4df0-863b-79931f297934 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
839220b0-d1b0-5317-a014-72a5a444e9d1 | note | 6
c4079d1b-38cb-458a-884f-8ccbc47001c2 | checkpoint | - Earths (+/-10 mm)
194de852-f62c-58ee-8858-0662b7074d27 | note | 3
1d4db3ac-4b38-4f62-9d47-d0201c7e9ed4 | checkpoint | - Others (+/-10 mm)
bc1a13b3-0e25-57f6-80b2-6355ca545aa5 | note | 1
bcd23654-171e-4dfa-9481-570eb6f08879 | checkpoint | - Splice Wires (+/- 0mm)
892b48d1-6dfb-557f-9550-fd4492c75a0d | note | 2
3e45d487-78fa-49fd-89cf-ee75053f4808 | checkpoint | ANTI-ACCESS Wires
8bc67854-501e-4554-95aa-2a49f083d59f | section | Cage Diameter Check
4608a904-a9af-4b53-9081-75c02782b3de | checkpoint | Cage Details
f71a9c05-9493-58b8-bbd2-681a41ed8941 | note | Primary Reingocement Drawign No.: 1765
3a3bfd27-bf9e-5432-aa2d-3a7a3b35b142 | note | Longotudinal Size: 9.88
511c6212-4c68-50f5-a01b-6b880d929152 | note | Circumferential Size: 5.55
838a722f-5759-4932-ab06-cbefd8da7b9f | checkpoint-no-value | Distance from Tip (m) Min - Max
cda872cc-1518-5a57-9092-d113502d9a96 | tickbox | TIP 195 - 200
96be274a-c49f-5f3a-8d66-fd0d7ca94359 | tickbox | 1m 210 - 215
b79e0cbb-3329-542f-8177-0736eaafe36b | tickbox | 2m 225 - 230
cd335cfe-8945-5658-a4b9-37a0d12a2d11 | tickbox | 3m 240 - 245
7deed267-ffd5-5a75-a840-eb1914e2efa9 | tickbox | 4m 255 - 260
1cd75a2f-71c8-5e52-be8d-1d242b9cd028 | tickbox | 5m 270 - 275
baa63306-b74b-5ec4-bd0d-6d43ce77798b | tickbox | 6m 285 - 290
2beb4560-d988-5089-b8a6-0fbe59e9eedd | tickbox | 7m 300 - 305
37202374-74c6-5c25-8c58-140eefb6c35b | tickbox | 8m 315 - 320
7c55f8cf-d131-567f-8886-22bc8f2596ba | tickbox | 9m 330 - 335
0cdb0909-f6fa-55e3-aa71-0af74276213c | tickbox | 10m 345 - 350
dee42c0c-aeac-5c66-811c-b8dc4612cf54 | tickbox | 11m 360 - 365
b0691bd5-c229-4482-8ee7-4c06725dea69 | section | Check Pitch Finish - Distance from Tip
53680034-e9f9-498e-a230-9bdbec24a309 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fa09eb79-10e4-42b9-b554-f991a9fb11ce | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
3e930b34-795c-4104-9828-f45bc0827dd2 | section | Longitudinals
430a8bd6-fbb7-463c-9a30-6b7fd6625ddf | checkpoint-no-value | Longitudinals Details
0bee6f51-ebd6-5a5f-a619-ba1317a6791a | note | Number of Longitudinal
bb1329f9-27e6-5be7-87c1-878c120c6ada | note | Longitudinal introduction Min (m)
f29580c8-de76-5d0c-b2e8-49b344d8d072 | note | Longitudinal introduction Max (m)
11e9f38e-5400-4915-82da-a71ee1fde362 | checkpoint | 12 (1.4m -1.6m)
e67e494f-3591-4637-860f-1af611cafbfc | checkpoint | 16 (4.4m - 4.6m)
4fdc290b-e6f3-4ea7-80e7-6f7f27c63f86 | checkpoint | 20 (6.9m - 7.1m)
3975ae13-fc9d-4447-8226-ede21d0ec1c4 | checkpoint | 24 (9.9m - 10.1m)
03615099-d038-4f6d-8cbc-459250fcffaf | checkpoint | 28 (13.9m - 14.1m)
517361fb-7b23-42cb-b975-b6f691338a0e | checkpoint | Acceptance
e844d2fd-8332-427a-bae9-cea313a22ea4 | signoff | Accepted? (Y / N) (Initial)
138297f0-5dfe-4523-9d4f-f881585602c4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3248 |  | 12.5/16 P/COR - Cage:
a088705a-9487-4e9f-9475-435e7697cc4c | section | Reinforcement Cage Inspection (Secondary Welding)
e1a7128f-1f69-4178-846c-740bb4adf8ab | checkpoint-no-value | Cage inspection details
24e31726-fcb4-57ba-92c4-b91217809e6b | note | Fittings Drawing Number: 3248
64bf3951-4ce4-57e3-9d2e-48a3156fcf96 | textbox | Cage Length (+/- 50mm)
b86ec3e4-5366-417b-b4d6-a4adf22407ba | checkpoint | Pole Cap - M24
33502014-257a-5163-9fb2-268cf5e59c7a | button | 4No. Welds | Y, N
614ad8fe-f806-5997-99b1-342fdc76b601 | button | Seated Square (+/- 2mm) | Y, N
a2fd89d1-c529-4055-a7d0-6ee4dfd0af75 | checkpoint | Correct Type & Number of Studs
141c3e37-b01c-4c60-a6a9-d306f9acc1f1 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
e3ab6daf-dd41-580a-8202-eee901266c54 | note | 6
22714eaa-7082-49f6-be40-73dca55d7f6d | checkpoint | - Earths (+/-10 mm)
59b49db2-6b14-558a-a0bf-fec37382f4fe | note | 4
7ff025c8-febf-4f85-a1c1-7a5bb86a4c7a | checkpoint | - Others (+/-10 mm)
6feb116f-f872-531c-88c6-e887fc25af7a | note | 1
68b4ed1e-a61f-4b30-a00c-98dd705a9113 | checkpoint | - Splice Wires (+/- 0mm)
7372c2f5-b5b6-521b-8c9f-15908de774c8 | note | 6
4165988c-0375-48d3-8153-3eb5ba065137 | checkpoint | ANTI-ACCESS Wires
76f40190-da91-4173-9136-3ce06a6404cd | section | Cage Diameter Check
dee40e2f-2bf5-4edd-9498-f70fb6dffd9e | checkpoint | Cage Details
10eac8bd-9bf3-5b9e-99ef-6072f6bbf77c | note | Primary Reingocement Drawign No.: 1764
587059be-acb4-533b-9540-34622b785507 | note | Longotudinal Size: 9.88
b7f08c9a-5ef8-547c-b77c-efea5b281ee4 | note | Circumferential Size: 5.55
f2b6b6b5-6d57-472b-8fd6-2475a8dfdfd8 | checkpoint-no-value | Distance from Tip (m) Min - Max
3d5376be-62cf-5894-9cfc-451d16387cef | tickbox | TIP 195 - 200
792c62bf-42de-58f8-b8ee-e83539f9a409 | tickbox | 1m 210 - 215
cf9ffd66-6c03-5314-a7ee-8b44ffd5c994 | tickbox | 2m 225 - 230
18bae7b4-1095-51e9-aaa0-93df7db97fce | tickbox | 3m 240 - 245
58f4c681-4d17-5cd1-a313-8e2c683fa048 | tickbox | 4m 255 - 260
1c5513c1-294a-5576-bcf2-e141a464b79f | tickbox | 5m 270 - 275
1ebdbb8b-9246-5cee-a8d5-491a9ea558ac | tickbox | 6m 285 - 290
e6f0f8f7-1705-53f6-85ad-35511d59030c | tickbox | 7m 300 - 305
a033b60f-9ac4-5577-b5e9-836511ab1194 | tickbox | 8m 315 - 320
2c05e30e-4290-52c3-bcf2-8b2e73d749b5 | tickbox | 9m 330 - 335
e77910ad-9e35-59b7-9210-e01ac7a0cb5a | tickbox | 10m 345 - 350
ae538cb7-f871-5a6f-b3e7-d2fce792a788 | tickbox | 11m 360 - 365
1bfd4180-559d-5ad5-b58d-a87e8d094539 | tickbox | 12m 375 - 380
807be7ef-9698-54e8-b9f3-a7ac278161f3 | tickbox | 13m 390 - 395
b3ed21f7-f0ae-4fc3-90dd-d4fdb0455bab | section | Check Pitch Finish - Distance from Tip
1e398136-6c14-4e7f-81c5-a66a2210cf52 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
763485db-35e6-4ecb-8c75-6417e57f3e4d | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
32185a4c-7db7-463c-82dd-2f177f2884a8 | section | Longitudinals
41a6da3a-dab1-460c-b3ed-aaf2a593bd10 | checkpoint-no-value | Longitudinals Details
5e52dbc5-9fc3-56a4-83d7-18deae539f1e | note | Number of Longitudinal
3fb431c9-694c-5954-9371-c1e1b93fd3f3 | note | Longitudinal introduction Min (m)
5fd75918-263c-569d-81a2-0e13baf41176 | note | Longitudinal introduction Max (m)
7717066d-31d5-4184-a8de-1bd945dc6e23 | checkpoint | 12 (1.4m -1.6m)
726b599f-b209-43a3-871f-6c30eefd1a94 | checkpoint | 16 (4.4m - 4.6m)
389d4e9c-294e-439c-a013-13e18025a199 | checkpoint | 20 (6.9m - 7.1m)
b07f0fde-f29a-4bd3-98e9-0fd0030f8b58 | checkpoint | 24 (9.9m - 10.1m)
dd8dcfdf-3d1c-42cc-a7c9-79f342ed65d4 | checkpoint | 28 (13.9m - 14.1m)
777313bb-29f5-43ed-b22d-85a5a3379532 | checkpoint | Acceptance
1a3ff9e5-9e70-4e2f-be6e-708dc5a969b2 | signoff | Accepted? (Y / N) (Initial)
d2973624-523a-4fed-8cfe-d187a49bac85 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3249 |  | 12.5/24 P/COR - Cage:
56cd6fe7-e17b-4b2f-8f50-19108b3e9dec | section | Reinforcement Cage Inspection (Secondary Welding)
af8e7a41-30a9-4a70-806e-38239d677707 | checkpoint-no-value | Cage inspection details
9b0fb319-d7aa-599b-b41b-e163f6e4f407 | note | Fittings Drawing Number: 3249
2837cbd5-4c17-51af-bd12-eb5e426ac114 | textbox | Cage Length (+/- 50mm)
1a331a1c-a72d-496e-9160-eecd31103c72 | checkpoint | Pole Cap - M24
af5b0609-87e9-5c07-a456-8653672e39ba | button | 4No. Welds | Y, N
e2e1fca4-be35-5b55-b23f-a2ac0d248edf | button | Seated Square (+/- 2mm) | Y, N
ac40409e-5703-4f84-b99b-490d8085e905 | checkpoint | Correct Type & Number of Studs
712dcc76-bb8c-46f3-8a2a-1cff7215b160 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
de7b03b6-2f33-5af8-acd5-853bc065b94c | note | 6
af57ba30-0d0a-4b49-8978-2c2949a3b2fb | checkpoint | - Earths (+/-10 mm)
6997d620-e698-53aa-8ae6-7aa547479cb5 | note | 5
86b336f4-32ee-46e7-acab-dd8dfa41dc4d | checkpoint | - Others (+/-10 mm)
437eaf52-17e4-5eee-b96f-f2de4da0d242 | note | 1
fc4c84c9-6b0e-4dbd-ab08-5497c6fc8165 | checkpoint | - Splice Wires (+/- 0mm)
9f10eaa1-ed09-53f3-80d2-282b09299a27 | note | 6
bf2c230f-cde2-4ec2-8e4e-9b5e2276d58c | checkpoint | ANTI-ACCESS Wires
754da598-b2f8-4679-82ff-3716815bc9dc | section | Cage Diameter Check
5c39e25c-5693-474f-869a-7b14397a4689 | checkpoint | Cage Details
e27e8997-ad02-572d-8249-08cd74aeda2e | note | Primary Reingocement Drawign No.: 1766
7a6e558e-4cc5-5fff-8126-93fdf23ac970 | note | Longotudinal Size: 9.88
a8d01f3f-0285-57ce-b348-9414e44b0d85 | note | Circumferential Size: 5.55
cc46df13-3d55-4db6-bc1e-54544d46339a | checkpoint-no-value | Distance from Tip (m) Min - Max
faacdad0-4b22-53cc-92b3-d40876949044 | tickbox | TIP 195 - 200
d727cb5c-339a-5b78-97db-581408513ef7 | tickbox | 1m 210 - 215
3afaa058-66d3-5e6a-86a7-391502cf5804 | tickbox | 2m 225 - 230
f03113be-75bb-52df-ad59-ba74d220b079 | tickbox | 3m 240 - 245
17d671f2-0309-5770-b1b0-479d36fd64f4 | tickbox | 4m 255 - 260
7d5f0825-185f-58be-9931-74e102ba35b2 | tickbox | 5m 270 - 275
417a9109-4549-55db-901d-bde109ad662a | tickbox | 6m 285 - 290
9c60a0e0-58ec-5555-9c07-1d2395dddd81 | tickbox | 7m 300 - 305
2d257d7b-a776-51c1-97ae-bd05bf127c4b | tickbox | 8m 315 - 320
cfc0bc64-cca4-5f23-a24c-23b2de4ff77c | tickbox | 9m 330 - 335
c91f8c39-f61f-5d1c-9a2d-f792e2582eed | tickbox | 10m 345 - 350
20d6efc8-4e04-559e-9208-17b2ccaa86cc | tickbox | 11m 360 - 365
6ef3ac7f-d6ef-59ad-961f-fd510faa996b | tickbox | 12m 375 - 380
389440f0-8515-5a67-8cb3-bc3dd096da49 | tickbox | 13m 390 - 395
de5abeb3-68da-430f-8c91-bb94cae39fae | section | Check Pitch Finish - Distance from Tip
069bc1fe-e4b5-479a-a4f8-1ccfd9890c52 | checkpoint | Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
39a54ecb-27b8-4de3-817b-8f84789e8652 | checkpoint | Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
d9847f2a-1563-4326-966b-6676545089cc | checkpoint | Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
f096bb37-f70b-4c93-85a5-3958a9161d60 | section | Longitudinals
4c28218a-9486-4f5d-9f2c-d36b28febd47 | checkpoint-no-value | Longitudinals Details
c9d63758-4882-53d5-9496-6f77d442a0d8 | note | Number of Longitudinal
9bc1b02d-03d7-554b-aad5-f76cd25b76ac | note | Longitudinal introduction Min (m)
5a6ba63c-ac26-5c1b-8d8f-604d6c28fe70 | note | Longitudinal introduction Max (m)
1f648762-8d1b-4ce1-b570-a030450aa474 | checkpoint | 16 (1.4m - 1.6m)
86bd4edb-39e8-4a65-9e28-c440cfd96552 | checkpoint | 20 (2.4m - 2.6m)
72ac5c43-ef6d-4a3c-9d89-70fc25e675a9 | checkpoint | 24 (4.4m - 4.6m)
07e49ec5-4a67-4194-936f-a4fde0e7d212 | checkpoint | 28 (8.4m - 8.6m)
ad56e298-2cdc-4093-b928-b4278008d93a | checkpoint | Acceptance
8991065c-cf4e-4b8d-aa4c-14ff8efe357d | signoff | Accepted? (Y / N) (Initial)
26756598-5be8-4a0f-9038-e7e32419dcc4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5589 |  | 11/16 SPAN - Cage:
c73bdafb-b7d4-4d09-8093-f1112a3791cd | section | Reinforcement Cage Inspection (Secondary Welding)
e667259d-007b-4e2f-afa5-33712c87571c | checkpoint-no-value | Cage inspection details
0736ec19-ee30-536d-b6d9-d32259a99d81 | note | Fittings Drawing Number: 5589
a92bde2a-e9c1-51c5-8ccb-1b084e00731e | textbox | Cage Length (+/- 50mm)
a0adf7c0-6298-45bc-8e58-6f66a18bcdef | checkpoint | Correct Type & Number of Studs
1f1fa794-d0e2-46b5-b550-ea99275900e4 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
2705fc95-abad-5ad7-913b-9cbf55a426fb | note | 6
902e6167-42f0-41cd-8778-d71bd56bb9ab | checkpoint | - Earths (+/-10 mm)
cf8e75d4-db1a-5ae9-b646-838f82bacc6f | note | 2
7ddb9318-e6d6-4f4f-8aa0-f522e74b9f50 | checkpoint | - Splice Wires (+/- 0mm)
a9351838-f772-5389-8410-715bd7f696cb | note | 2
1ae766a8-e6ce-4050-aac8-18a2e6e2afa0 | checkpoint | ANTI-ACCESS Wires
d35c27b5-315a-41ae-9e19-c368ccf522c4 | section | Cage Diameter Check
4a5cd9b9-ef53-4dfa-837c-a4aacf7a61bf | checkpoint | Cage Details
add99e13-f631-55a2-8ea9-3c4cf10dd74d | note | Primary Reingocement Drawign No.: 1765
0737e1d7-e2de-5525-b0b1-5e56d1dbe5fe | note | Longotudinal Size: 9.88
a96a1e4f-837d-566b-8fa1-afdea66f2f0e | note | Circumferential Size: 5.55
574a5595-e205-4d77-9bf6-2cd671c3f960 | checkpoint-no-value | Distance from Tip (m) Min - Max
e23a42e2-82e6-5be9-9309-49a11d7ad42b | tickbox | TIP 195 - 200
98347156-321f-5391-bdb3-ab280f5f1e5f | tickbox | 1m 210 - 215
ea206c6d-ea1b-5194-affc-c33e54439a42 | tickbox | 2m 225 - 230
81ca6c86-9554-5767-ba6a-bd5814738930 | tickbox | 3m 240 - 245
99130bf9-72b9-54f9-b5ee-efeef559bbad | tickbox | 4m 255 - 260
e317324f-a784-53fd-bccb-00e2ec1cf2f5 | tickbox | 5m 270 - 275
c64bb5ee-7572-5da7-8ade-3c5c010f72dc | tickbox | 6m 285 - 290
ed8538f4-2190-511c-994c-19c63adcbba8 | tickbox | 7m 300 - 305
50805332-a2fd-53a9-a85e-bb86303411b1 | tickbox | 8m 315 - 320
208de21d-5489-5e97-8e1d-88d16179fe3b | tickbox | 9m 330 - 335
052ea74d-1b9c-5f59-9c4f-b02b59899b7d | tickbox | 10m 345 - 350
28cbde63-f4f7-514b-a75e-4114861c4bff | tickbox | 11m 360 - 365
26e4ac03-51ca-4cd6-b26f-760a07733f87 | section | Check Pitch Finish - Distance from Tip
d112fc3f-6072-4a18-9fc6-8196b250b9a0 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
c562b6cf-3532-4a14-9d88-db0ef999ae2e | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
9d5c4848-49e2-4217-9372-d187caf964c3 | section | Longitudinals
bc0e8581-f220-495c-b876-e6511d41a161 | checkpoint-no-value | Longitudinals Details
6d332a3a-b59b-5d65-ac68-c8c4519218d4 | note | Number of Longitudinal
ab77be31-c5fb-5877-a547-4cc5410139d4 | note | Longitudinal introduction Min (m)
415c962c-5e0d-58ec-bca4-94fe387c027d | note | Longitudinal introduction Max (m)
eb3dd763-b117-49d5-b0e3-b81f887a253b | checkpoint | 12 (1.4m -1.6m)
1fe0024f-5ad8-4851-a36f-dcdd1564f4ef | checkpoint | 16 (4.4m - 4.6m)
b92925fd-090d-409e-9cdd-f6218e711429 | checkpoint | 20 (6.9m - 7.1m)
a97905f2-ed13-40fd-9dac-e18f5291c4f3 | checkpoint | 24 (9.9m - 10.1m)
5dd1cf85-a976-46db-acb9-8f33a680c3d2 | checkpoint | 28 (13.9m - 14.1m)
aa8793b9-f554-4c02-8192-834db141f1c1 | checkpoint | Acceptance
0d29615a-fd36-4330-b185-b7c269608c49 | signoff | Accepted? (Y / N) (Initial)
6fef6a68-0533-4108-999a-346725b445a8 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5593 |  | 12.5/24 SPAN W/S - Cage:
f6e5c00e-0df8-41ae-ba2c-c4e4307b33e1 | section | Reinforcement Cage Inspection (Secondary Welding)
473baf41-a997-495b-beb0-a3569f440bc0 | checkpoint-no-value | Cage inspection details
7e3fd408-4e86-5ac0-865a-942d43fffef6 | note | Fittings Drawing Number: 5593
64af15b4-50d5-59ab-82ba-5b89e35efabe | textbox | Cage Length (+/- 50mm)
fb91c63f-8889-4bc2-909a-5f06b01ab3aa | checkpoint | Pole Cap - M24
f8c5324d-7d58-586f-b6c0-1f02f301fcfc | button | 4No. Welds | Y, N
36a1435f-1c6f-5e99-98fa-dc3d713ead03 | button | Seated Square (+/- 2mm) | Y, N
04396cf2-6475-41ae-bc50-2c23c706c252 | checkpoint | Correct Type & Number of Studs
5a15b685-79b4-493c-a2fe-d730af92baea | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
b8f7c6ff-82bb-5190-bc90-c67272eaf8dd | note | 6
ff262906-4fef-4d7f-893b-16a894346e25 | checkpoint | - Earths (+/-10 mm)
430b5dbb-9081-5956-870c-dbd6a9b1ebf0 | note | 4
188fdc77-cb73-417c-bebb-4e418f10c8b0 | checkpoint | - Steps (+/-10 mm)
11b01569-b0a8-5886-ac94-9bd0ea285b2d | note | 7
786d51ea-67bf-46f2-99c2-64009cea5451 | checkpoint | - Splice Wires (+/- 0mm)
f23877e7-8384-5f7f-92b2-23048e18295d | note | 6
51f95ff4-15fe-48cc-aa2e-fb2b6a83f6a4 | checkpoint | ANTI-ACCESS Wires
f3b71e3d-82ae-4c9e-bdf6-8e605f09925b | section | Cage Diameter Check
49b5d406-dd32-488e-8603-62bb0e0ecd27 | checkpoint | Cage Details
7619ffec-d23e-547d-9e95-f0b474368bc1 | note | Primary Reingocement Drawign No.: 1766
57842c89-65f9-50e1-8d48-a4ad52942cdf | note | Longotudinal Size: 9.88
386600b5-12c2-5025-a743-bc13e816fe0f | note | Circumferential Size: 5.55
16806b2b-3e43-47d0-81df-b2c4170aa9ab | checkpoint-no-value | Distance from Tip (m) Min - Max
b99148c5-d341-5353-922a-3bd0762b0811 | tickbox | TIP 195 - 200
f3276907-c684-50c6-b91a-eb2d82a93ed4 | tickbox | 1m 210 - 215
d3cb9ece-c6d1-55f2-adb2-fe2f9ed905ca | tickbox | 2m 225 - 230
e27cf682-1db8-588b-a7a1-675cc26f5dd1 | tickbox | 3m 240 - 245
5c587646-4535-545f-ae58-d4085f183cb9 | tickbox | 4m 255 - 260
a6dc6021-db74-52f1-b054-bad0362ace65 | tickbox | 5m 270 - 275
64f7fb61-2461-56c5-ae52-6e28cd43d0fe | tickbox | 6m 285 - 290
98cc8c9c-6342-5e47-bbdf-9b83e3edf606 | tickbox | 7m 300 - 305
be81092d-5e94-5b03-bae1-da6d73c911bb | tickbox | 8m 315 - 320
b6175cdc-549a-5742-8caf-cb5f1fd78ca3 | tickbox | 9m 330 - 335
b5661983-932b-57a1-ad89-22bb5f5eee7c | tickbox | 10m 345 - 350
372bcd54-5c52-5292-b78b-c73171113546 | tickbox | 11m 360 - 365
cbaf8199-ff16-5e70-918a-54fb5219e836 | tickbox | 12m 375 - 380
0d44584e-0def-5224-9b43-78e559d42d80 | tickbox | 13m 390 - 395
dac2dab2-82a5-47e5-85b2-9bbadfece30d | section | Check Pitch Finish - Distance from Tip
ec08196c-fe37-4134-b1fc-e1a5f2a82a63 | checkpoint | Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
479d886c-88e2-4252-8661-2eeb2b7ca121 | checkpoint | Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
c151c6ef-211f-48e6-a77c-7227b62d1d8f | checkpoint | Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
33b6ad9b-2737-4434-8794-a8ece11ed45e | section | Longitudinals
355411e9-fec6-4e59-a19b-1f915fb47944 | checkpoint-no-value | Longitudinals Details
36536db3-92d3-5d20-b913-0ca98f133704 | note | Number of Longitudinal
8d434f0d-b28e-5e1d-a305-91c54a6332ca | note | Longitudinal introduction Min (m)
a3d060bc-8e94-5e8e-81fb-269dadb7c964 | note | Longitudinal introduction Max (m)
43715909-72e6-4e4a-a8ab-cd6a276c275e | checkpoint | 16 (1.4m - 1.6m)
c31a6fc8-e106-4041-9d3b-9a9ecf513393 | checkpoint | 20 (2.4m - 2.6m)
2ad4962d-08ff-4d15-9f37-aa2938bc9faf | checkpoint | 24 (4.4m - 4.6m)
fbed1f1e-1537-49d5-8118-7833160652aa | checkpoint | 28 (8.4m - 8.6m)
ea35251d-1072-445e-a4df-ebd8a2c88020 | checkpoint | Acceptance
cacf9107-ba24-43c1-947b-62c9e62245c4 | signoff | Accepted? (Y / N) (Initial)
3828ab13-7bfd-4733-b2e5-df918d0d74fc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5594 |  | 12.5/16 SPAN W/S - Cage:
f27c050b-d801-4714-aa38-9eb7252e707f | section | Reinforcement Cage Inspection (Secondary Welding)
93b0b319-f988-4ae7-987f-a9a2a69b131e | checkpoint-no-value | Cage inspection details
82fe3052-cbab-573f-8902-3cf1df87385a | note | Fittings Drawing Number: 5594
de3b377a-8ef4-5326-a155-3eb2d442c07b | textbox | Cage Length (+/- 50mm)
64c0d07f-e62c-4795-8469-f394208052bd | checkpoint | Pole Cap - M24
6a4073ab-791f-5207-843e-044fe07ba069 | button | 4No. Welds | Y, N
9d71c366-dc28-5ed3-8207-b3fc1b12f7bb | button | Seated Square (+/- 2mm) | Y, N
b293f3c7-3ebf-442d-8f21-ef30f82d7fe5 | checkpoint | Correct Type & Number of Studs
a7f7a90e-d2d8-46da-ac6c-831153cca327 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
f9426846-a7b1-556b-9cea-40f4b22c9173 | note | 6
93b84c79-49e7-4949-8554-1359bae45ead | checkpoint | - Earths (+/-10 mm)
f384b6c0-abaa-5ea7-a33b-bfef4c432e75 | note | 4
c6e7e469-a033-4341-99f9-e70a568f765d | checkpoint | - Steps (+/-10 mm)
2cb18d18-c74c-589e-bf8e-f0c67833cd22 | note | 7
ca05cb3c-10af-4725-8688-772cafb0e459 | checkpoint | - Splice Wires (+/- 0mm)
3423f176-3591-5354-a994-7ea372bf3bc6 | note | 6
485a3147-50e4-482d-8e18-fe95ab4e9163 | checkpoint | ANTI-ACCESS Wires
07f43247-01ee-4969-881e-8b006f82ac4d | section | Cage Diameter Check
ef9fd327-576a-4c15-a08d-b68367e206c0 | checkpoint | Cage Details
1f273cb3-abb1-5d2a-86bf-f6c0c39f9487 | note | Primary Reingocement Drawign No.: 1764
a6df44d1-f3ed-505c-a7fe-4ff272708895 | note | Longotudinal Size: 9.88
78595ebf-ecb9-56e2-baba-0e2e49c2eba4 | note | Circumferential Size: 5.55
a1f50101-bad8-471e-a7e1-93e3ec2430c1 | checkpoint-no-value | Distance from Tip (m) Min - Max
683918bd-c4fd-5900-8e21-fe54ababc2e2 | tickbox | TIP 195 - 200
c444b7a7-bbe4-587a-8824-9251123da8a9 | tickbox | 1m 210 - 215
4e4b9dd5-15e1-5cd2-af34-7fb268c3f91f | tickbox | 2m 225 - 230
969d8b4d-7c88-54da-a880-aca0a5afa08e | tickbox | 3m 240 - 245
8d7a53da-2a94-58fa-ac66-0859ce957b45 | tickbox | 4m 255 - 260
6736d553-9051-5889-bf16-a5f0e2cb6248 | tickbox | 5m 270 - 275
bde09ee6-5e07-59aa-ae97-1bb9fd84a7bc | tickbox | 6m 285 - 290
a098e223-8197-595c-b85f-e61901cf62f6 | tickbox | 7m 300 - 305
aedfeaaa-0e16-5340-b389-626600868d84 | tickbox | 8m 315 - 320
b161811c-c0f4-5fc1-80b0-ceabe55b3bc2 | tickbox | 9m 330 - 335
72c6f837-432a-5cd2-aa40-7913d9242a53 | tickbox | 10m 345 - 350
265ae906-bbf4-5fad-a8f4-0c090c999800 | tickbox | 11m 360 - 365
fbc272f5-a6bb-5d40-9787-4b80cfee5a01 | tickbox | 12m 375 - 380
724e74c0-b9e4-5616-92f4-34c2e665b82f | tickbox | 13m 390 - 395
159040f8-7a45-40cf-a3a4-41f4d65f783a | section | Check Pitch Finish - Distance from Tip
a7e49f18-a1ee-4840-84d5-583ce21aa245 | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fea45de1-aabf-4a19-af19-f2dc68fb637f | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
438146ba-a2a3-4bcb-a79f-35e11531bbc4 | section | Longitudinals
c6844705-1892-4494-80d2-530df6a57f8e | checkpoint-no-value | Longitudinals Details
897d632b-de8a-58f7-afeb-6cb75967e86c | note | Number of Longitudinal
93568b1e-75ae-5c33-8087-2304db809802 | note | Longitudinal introduction Min (m)
e4ab5efb-a53e-5289-bd01-bb6ec40e5730 | note | Longitudinal introduction Max (m)
b71ad0df-5ab9-42e7-8ab4-3733622496b8 | checkpoint | 12 (1.4m -1.6m)
0fa21303-81ec-4800-bf17-9006e85c98b1 | checkpoint | 16 (4.4m - 4.6m)
07d89d18-f5fb-4ed1-b7d4-39e6a0fbedf5 | checkpoint | 20 (6.9m - 7.1m)
bfa3ea27-d8e0-4b34-97b5-1f4cfd93703f | checkpoint | 24 (9.9m - 10.1m)
705b1420-66bf-4239-ad6f-d8cbaadbcf00 | checkpoint | 28 (13.9m - 14.1m)
ece5c504-995f-4392-9257-0f8a21401d75 | checkpoint | Acceptance
6780aac2-d3cf-4c8f-915e-0bf2d544a45a | signoff | Accepted? (Y / N) (Initial)
b9751522-4e1a-4492-bcd9-a58a054eb4dc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5595 |  | 12.5/16 SPAN N/S - Cage:
db9cb702-e411-4189-ba04-ee6bdd5be38f | section | Reinforcement Cage Inspection (Secondary Welding)
2882432a-1787-43df-9949-fff00850bd50 | checkpoint-no-value | Cage inspection details
148cc336-3e14-528f-bdc8-3247d60083e0 | note | Fittings Drawing Number: 5595
63c9460c-cb46-5a5f-9671-1b39bb49724c | textbox | Cage Length (+/- 50mm)
42ef8c96-dd04-423a-9233-2351a673522e | checkpoint | Pole Cap - M24
e1dd98ae-0cff-597b-8fde-3cbf9c6b9a08 | button | 4No. Welds | Y, N
c10ae6de-af67-51b5-8678-c12b74eab35a | button | Seated Square (+/- 2mm) | Y, N
011545f4-c4d0-4ae9-99b5-7ed1be4d2f1a | checkpoint | Correct Type & Number of Studs
c4978b4e-8c5c-4e66-961c-e714a60f7c65 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
1e0c14c9-be0e-5e9d-9727-fa43eaebae64 | note | 6
e7c74590-5f01-467d-be37-ef105c830cd2 | checkpoint | - Earths (+/-10 mm)
c4754220-b7a5-501b-8240-291dd9e797af | note | 4
0329b24f-8489-4d1e-869d-fdd658b3dc20 | checkpoint | - Splice Wires (+/- 0mm)
20884513-df4e-5e0a-853e-472364ee65fa | note | 6
603a23b6-988d-4737-acef-c98d0cb8549b | checkpoint | ANTI-ACCESS Wires
b35a9d04-41a4-4efc-af30-33e5795bbf91 | section | Cage Diameter Check
ce0f7c09-5143-4325-b718-302807762da9 | checkpoint | Cage Details
6238ae9d-2024-5f93-824a-c31a7eeaceca | note | Primary Reingocement Drawign No.: 1764
c8e7149b-16df-5c0b-b2c3-097f59931de0 | note | Longotudinal Size: 9.88
2c77af15-819a-5dc3-b370-9ee61b6553a0 | note | Circumferential Size: 5.55
7fe2d4ba-e2df-48c0-8a54-c592ac55678b | checkpoint-no-value | Distance from Tip (m) Min - Max
d5d4f296-d494-56b6-b534-70752af7ec04 | tickbox | TIP 195 - 200
89ce744f-6c26-5188-8eee-b05f4d127639 | tickbox | 1m 210 - 215
3379899a-e358-5e39-85b9-75728d1d815d | tickbox | 2m 225 - 230
16d0d4a3-0385-57a4-b47b-a014ed484efb | tickbox | 3m 240 - 245
57fc1a3d-1fcd-5d84-867d-421abd1021bd | tickbox | 4m 255 - 260
96131855-56c2-59d8-abb8-56601fc997fa | tickbox | 5m 270 - 275
f3491eca-cd87-527e-97a5-51b0f0ebae4b | tickbox | 6m 285 - 290
d1d755b0-54ac-5a02-983a-28a722a19c61 | tickbox | 7m 300 - 305
cce3ab02-2268-503d-9e92-adaba83f2337 | tickbox | 8m 315 - 320
887aeb15-ecc3-518b-9aed-dac2920653b6 | tickbox | 9m 330 - 335
3e65f8c8-d9e5-5387-9de5-b50f91ee3eb9 | tickbox | 10m 345 - 350
cd9f06e1-cd1a-5e23-9c58-d1c44351df16 | tickbox | 11m 360 - 365
1c1a5005-92a6-5e3f-8149-b37c8a3d50dd | tickbox | 12m 375 - 380
8eca0c86-bf43-56a3-8439-04fe6e8dd03f | tickbox | 13m 390 - 395
a263e59c-83b0-4353-856a-123ef3c75e34 | section | Check Pitch Finish - Distance from Tip
a8827e6d-2eb0-41b0-a3f1-9d1905f810ef | checkpoint | Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
0871f9b3-f385-4dd3-9dfd-0e62fb8dce6d | checkpoint | Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
ae881694-b8d5-4821-9207-4d39a3af0e57 | section | Longitudinals
cd8974b2-0e0d-4a41-8507-ef701b7a49d2 | checkpoint-no-value | Longitudinals Details
331109f1-e8d3-5d09-884c-2b2a5bf057c7 | note | Number of Longitudinal
26fd10ca-e0a8-5322-a945-5433f3432062 | note | Longitudinal introduction Min (m)
efcaa250-af69-555b-8aef-4b4b5965fae5 | note | Longitudinal introduction Max (m)
c355aec6-f15b-49e1-8a3e-1ce21be9ae77 | checkpoint | 12 (1.4m -1.6m)
3258cd4a-4872-44c2-909f-afc1000a3baa | checkpoint | 16 (4.4m - 4.6m)
691fb529-0e78-4f31-a806-fe5a87d817ed | checkpoint | 20 (6.9m - 7.1m)
77bdac51-7691-47b2-b435-a4992f474c37 | checkpoint | 24 (9.9m - 10.1m)
47c9df14-425d-4c8c-a2c1-6c1542e4e3a5 | checkpoint | 28 (13.9m - 14.1m)
87a1af3a-135f-479f-a68d-3d18ee0ff339 | checkpoint | Acceptance
32bef75f-d20d-4287-8e22-8e4e6e919968 | signoff | Accepted? (Y / N) (Initial)
70ac589e-ab75-4655-8661-2e059dcefbba | checklist | 2. Postpour (Visual Quality and Finished product inspections) |  | Product Number:
c2856e22-fed6-4e75-b6dc-d0bd31137c44 | section | Finished Product inspection
c685d966-84a2-48eb-80ac-bafea08dac5f | checkpoint-no-value | Details
d22bcb4e-39c1-5a60-8820-07214df4aa6c | textbox | Product Size and Type
e2201ce3-821e-5bf7-ab85-a8920ef55a02 | number | Mould Number
31a70758-5787-5481-921f-d66a7696b350 | textbox | Drawing Number
d3355cf4-e096-4528-aa89-6175f6f65fbb | checkpoint-no-value | Inspection
d665f2eb-576c-55e3-9fea-41cd86723148 | textbox | PRODUCT LENGTH (±50 mm)
c094f088-9c11-5210-a46c-5e5d14580f94 | button | CAPS TAPPED & PLUGGED? (Y / N) | Y,N
1aa3f5ef-b462-52c0-95d4-6b8f426a9a91 | button | FITTINGS TAPPED & PLUGGED? (Y / N) | Y,N
6d106673-da28-5ae0-a260-1236e1b4ecda | button | Joint configuration & PCD check - Result passed check (Y / N) | Y,N
0f35aff7-f203-5cf7-8e62-201e9fba647a | textbox | WALL THICKNESS - TIP
f77e18e8-80d1-547a-8472-df9379cba854 | textbox | WALL THICKNESS - BUTT
0f35ad16-e216-46cd-81f3-a20f5418af05 | checkpoint-no-value | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS (record amount visually inspected)
af75e346-45ce-5b21-a049-6011a721a5d8 | textbox | - Tubes & Hole Formers (±3 mm)
b1352b62-e84e-5611-ad51-25de53716efe | textbox | - Earths (±10 mm)
4f2fd9ba-1f31-5614-8371-f3e1dd902e52 | textbox | - Steps (±10 mm)
650396a6-e10e-5acb-a9b1-475a5879cd14 | textbox | - Others (±10 mm)
e5aa6f2c-6ee7-4c1d-ae2d-65e12d7eb87e | checkpoint | ANTI-ACCESS WIRES (Y / N / NR)
c8c86378-982a-4751-986a-9f39ec606849 | checkpoint | INTERNAL CLEAN - DEBRIS CLEANED FROM COMMS POLES (Y / N)
5ae10731-3cd0-4b76-b2e0-4a5b0867db18 | signoff | ACCEPTED? (Y / N) (Initial)
a9c7f156-1c01-43bf-ae69-7306ea239a03 | section | Visual Quality
49a54f8c-fd67-4e13-b0cd-d778f4d4a384 | checkpoint | Visual inspection
dd43bcab-04e8-5327-8116-7a7d171bc7f9 | note | RAISE ISSUE FOR EACH OCCURRENCE
64388d55-91db-5c2b-a5be-10caafdbfc68 | note | 1. Exposed reinforcement
2c981b1f-667d-51ae-80e7-451947b7d672 | note | 2. Squareness of ends
daeaa09a-3bdb-589c-acb1-5fdf8a4bab27 | note | 3. External finish
4439f630-2ad2-5d75-8030-46c7ff2003c5 | note | 4. Bulges or dents
3a06e9d1-d47f-5da3-9b82-684d550e04e1 | note | 5. Chips / Hammer marks
7b8076e5-f8fb-5c42-9292-7f6ea0c18c15 | note | 6. Flexural / Longitudinal Cracks
7f3783b6-5e00-5694-9c31-5e553087aaf8 | note | 7. Stud / Lug / Tip Ferrules incorrect
49678347-7666-5f2f-81fe-62a39bcd26a2 | note | 8. Deep fittings
d82be945-f8d5-5b4b-97fd-aa617f9000f9 | note | 9. Plastic Plugs missing
3a2aa2b3-1e71-56bd-a03a-38f4fd28f228 | note | 10. Slumps / Fall-ins
d49921dd-b4fd-50a0-afd3-65bed932addd | note | 11. Seams not washed-in
768b0aa0-811c-52c6-ba60-68a6be43f11a | note | 12. Mould Stick
e53ac214-fb3c-53cf-8472-9392de8d26f5 | note | 13. Product Identification incorrect
915de46a-ef74-5ebf-a093-a21d4cec517b | note | 14. Internal Finish
1424209a-ff67-5a65-b332-6ce5d1bd3ef4 | note | 15. Branding Incorrect
cefe7a66-dd35-5882-99ef-8d7c3d39300d | note | 16. Depth Marker incorrect location
bbce09f3-51da-578d-a12f-9de137268c79 | note | 17. Seam Bleeds
cc2c231d-0d9f-5ce7-bd77-a72371842005 | note | 18. Tip / Butt Bleed
6dab859c-255f-56c9-96ce-612a3f1a9612 | note | 19. Fitting Datum incorrect
7e9c553a-0a8a-5af2-8335-1e4991875b5c | note | 20. Class (Strength) incorrect
2f298ec4-c853-540f-b447-010115c0cb9d | note | Total Faults
994155f5-7588-5776-b68d-6905fafca203 | note | Action taken to rectify
fb88e286-73f5-438e-bedb-82121222ef1e | signoff | Inspected by
952573a6-db98-454c-a564-b6c29f5e9f50 | checklist | QA - 001 - Cement Records V1 |  | QA - 001 - Cement Records
7c7b2d6b-98e8-468f-bf77-499699d3f691 | section | Cement Records
729d5db7-2e22-4405-8340-8beb2f67fb48 | checkpoint-no-value | Details
60368e20-2fa9-5b48-894d-fd6449bb3661 | note | Procedure
5fd88907-4f9d-5e8f-b961-c404f218cb85 | note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
d6bc5a75-4174-523d-8fc5-93fd0655b9f4 | note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
ff5e4594-3564-5ca3-a416-16fb99d37b5f | note | 2. Record details and compare to minimum acceptable specifications.
b1ef194c-042d-5ad1-bd00-190166deb5ed | note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
ee1e4f32-33f6-572d-96a3-5b24bd081619 | note | If non-conforming do the following:
6266ae67-1be1-5a00-868d-8c917ea29dbd | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
c2e80835-2c54-5c4c-bf2d-d8fb032a5666 | note | b. Identify unused cement on site, reject if outside minimum specification.
225c5990-f586-58bb-8639-7eedeacef456 | note | c. Notify supplier of non-conformance.
88c824f3-2939-5366-95e6-37396f5eca9c | note | d. Examine test performance of completed products/cylinders to identify potential production defects.
f734497e-0776-5752-b89f-d83d1b7408fb | date | QUARTER ENDING:
6f055d20-7d89-52b4-94de-988530b2d182 | tickbox | Or, new supplier or new type
c05ae3b9-894b-55ac-922b-f2d2813a6ed0 | date | DATE
90dd9c50-f6d5-5bea-942a-151a77670bd2 | textbox | SUPPLIER
55b907a8-227f-5c09-8a13-bbbe098ef275 | textbox | DOCKET No.
0a21d3e1-6d44-51ee-bfb1-04dcd406ed9f | textbox | CERTIFICATE No.
9d3dd8de-3506-5cf1-b6b8-e5fd4ceda689 | textbox | CEMENT TYPE
a36722d7-0eaa-41a4-aa63-c0eb4ba8f216 | checkpoint | Properties meet AS3972
2ab9799b-54c8-4f46-97c1-a427b5cdaff5 | checkpoint | Cement meets Civilmart Poles Spec.
78f90b1c-5acd-5a32-965d-92eafeaba161 | note | Poles Cement Specification
cba6a794-2135-50ab-b2ef-f4b1c2ccfcd7 | note | — — — — — — — — — — — — —
4e923395-5e44-52c9-82ff-69fa8c18ad6e | note | TYPE ¦¦ **C3S content ¦¦ Fineness Index * ¦¦ Initial Set - Hrs. ¦¦ Total Alkali NA20 equivalent ¦¦ SO3 content ¦¦ C3A (informative)
115de9de-08a4-503d-8d46-0e4b5c55006b | note | — — — — — — — — — — — — —
f3bb8a9a-a4b1-530b-967e-7e350f389739 | note | GP ¦¦ > 55% ¦¦  350 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
fec9827a-c6ad-50e0-a93d-62da3e9c88f3 | note | GB ¦¦ ≥ 55% ¦¦ Max.15% on 45m sieve ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
2aabd5e9-38aa-5b6a-8496-ae754ba5ca04 | note | HE ¦¦ ≥ 50% ¦¦ > 380 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
86c77c77-e253-5cff-be8c-c6111dec4d04 | note | SR ¦¦ > 55% ¦¦ > 330 ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
af22a899-66b9-5c8a-9934-f88e4bfd42de | note | — — — — — — — — — — — — —
87e4dbeb-04b3-578a-8a2c-d4d6184e497c | note | All cements shall comply with the relevant clauses of AS3972 table 1, except that:
c34297f1-0a72-5f8b-9699-b938f9529d2a | note | a. All types (except GB) shall contain no mineral additions without prior written agreement from Civilmart Poles.
caaab089-1d4c-5aa7-96d2-c1b2e825116a | note | b. The following restrictions shall apply:
6dd00535-7ede-5ed2-bf22-879dacb0448c | note | Particular cements which do not comply with these latter requirements can be used but only after gaining written approval from the Regional/Area or Manufacturing Manager.
dc4672f8-e650-5982-817e-ee48d83d175c | note | Certain products, contracts or processes may require individual specifications.
cea58245-fe1e-5624-87b7-a5208b9a982b | note | * Minimum fineness indices should be agreed with individual suppliers during contract negotiations but should not be less than these values.
ad9a0b43-fc71-5494-893e-eb438f40643b | note | ** It is recommended that the clinker or OPC used to make the blend have a C3S as indicated for GB. Ideally the blend should contain at least 75% by mass of OPC.
bf21c7f2-e484-4b53-9f25-4c7bc9eac7e9 | checkpoint | INSPECTED BY
0c486dcf-d15b-483f-b485-f185af64aa33 | signoff | Signoff
7f96aa46-6c65-4a6f-96db-a825017125c0 | checklist | QA - 002 - Fly Ash and Admixtures Record V1 |  | QA - 002 - Fly Ash and Admixtures Record
593bdd89-9963-4604-94a2-94815c22053d | section | Fly Ash and Admixtures Record
68cb878e-9a71-4641-8ebc-e17fc3fe5cf1 | checkpoint-no-value | Details
b2588d04-fa3d-5a32-8af9-5ff7f3ed24d1 | note | Procedure
eabc7066-58e2-5c2d-9dd0-08ca7fa75077 | note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
b530bd4a-30c4-5b5f-b2e1-660bf1e827ef | note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
f9cb1efb-1119-5de2-b1ad-4d4491350070 | note | 2. Record details and compare to minimum acceptable specifications.
05781f39-ec67-5de7-bc84-fc50e2d5c85d | note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
702cb4ed-d532-5a5a-ad51-d822662b5c93 | note | If non-conforming do the following:
a7271165-27d1-597e-866a-a332f57839bd | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form.
1cf49d8d-b7b8-5c38-9dbc-861adf8b9cfa | note | b. Identify unused fly ash/admixture on site, reject if outside minimum specification.
6bffb44a-bada-5079-97aa-db6798a223f0 | note | c. Notify supplier of non-conformance.
99798fab-44a4-5cb8-b01f-2b916397c979 | note | d. Examine test performance of completed products/cylinders to identify potential production defects.
98cab6b8-14d1-5f23-8a0b-f22f8b1c5fcb | date | QUARTER ENDING:
ad195689-c612-59f8-9494-f7c1a4c00bcc | tickbox | Or, new supplier or new type
75f4bd75-3319-521c-aff5-6bed3c665c75 | tickbox | Review / approval from Engineering Department
453e3c45-35d7-4a2a-b2b3-b35c994d1609 | section | PART 1 - FLY ASH
452f21c1-f41a-4829-85cd-38f700444d9b | checkpoint-no-value | Details
3f881ef3-2238-585b-8b53-b630ac52da42 | date | DATE
589442b2-82b4-5c4f-8109-921b5d9abb16 | textbox | SUPPLIER
3a90779e-4f37-553e-a5f1-29109a2c230b | textbox | DOCKET No.
e6d61c05-a98f-52e0-b167-bfc02e9a817a | textbox | CERTIFICATE No.
51753b7c-b318-5eb0-9cb3-83688fa58a10 | textbox | FLY ASH TYPE
5459f5ef-2b9d-4291-b107-666565113b90 | checkpoint | Remaining properties meet AS3582.1
8fda78bf-fa2e-4878-aa6c-99731038f914 | checkpoint | Meets Civilmart Poles Spec.
1501db86-a1fa-5124-a8c8-417338207b60 | note | Civilmart Poles Minimum Acceptable Specification:
34a455ce-601b-5bc1-a282-c2660de8e83b | note | Moisture 1% max, >75% passing 45μm sieve, loss on ignition <4%
fd9ea64b-957b-5f31-9ec9-7265067ad861 | note | Density and available alkali must be reported
a26c9a07-2a1e-5756-b3c2-23379c7178f8 | note | i.e. apart from these Civilmart Poles requirements, all other properties must meet AS 3582.1 Grade "Fine" (refer to fly ash certificate)
1daaec9d-a9ee-4260-b210-c4214b3fb90b | section | PART 2 - ADMIXTURES
4eafc774-32ed-42fa-8440-22c9f150ac92 | checkpoint-no-value | Details
901f3faf-e0e2-59db-a008-b49f9ae5f9b5 | note | Certificate of Analysis (CoA) to be obtain to provide records for investigative/comparison purposes. Refer to ITP for required frequency.
a80215e2-0cb5-597b-a708-fb1e0f08c03c | date | DATE
619053d0-12c7-58b0-b9fc-a739ad8920f1 | textbox | SUPPLIER
3fe35740-7ffd-55c9-8cc3-1fe469e55b3b | textbox | DOCKET No.
d4696dce-970f-5e1f-b249-e532ab72ce92 | textbox | CERTIFICATE No.
e180b7e6-4694-5290-a0aa-82f30abe793a | textbox | ADMIXTURE TYPE
2418440b-19ab-5b8c-ac50-f2ee925a356b | textbox | BRAND NAME
63cbe85a-1692-4c98-adf5-675dd9a976c9 | checkpoint | INSPECTED BY
893d4a40-8f18-4c76-a977-7b01d828ca08 | signoff | Signoff
ae8a9049-ab04-468d-bfd2-6e5f2eaba12c | checklist | QA - 003 - Aggregates Visual Inspection V1 |  | QA - 003 - Aggregates Visual Inspection
deda7b58-f1fe-4d4f-9213-b3d6102d8f16 | section | Aggregates Visual Inspection
b42fa1da-6da7-49ad-9e4e-e76938046445 | checkpoint-no-value | Details
632a5159-0bc5-5046-9b05-59fd6447b4d2 | note | Procedure
0c908d0c-3af7-5457-ac2b-a47ecaa80c2f | note | Minimum Frequency - QEC - none except new supplier
14d60fd8-31d8-5dcd-9823-6185659b001c | note | Non-QEC - 1 Delivery / Week / Type / Supplier OR Where non-conformance is found from daily check.
cfc4550c-8c17-583a-b1b7-685709d10e8c | note | 1. Visually inspect all aggregates.
0e8b82a7-f6fd-56c8-9826-2e04913cf0a7 | note | 2. Maintain an agreed reference sample (from initial supply) for comparison with supplied aggregates.
40508e27-90b7-5c0c-b51b-213e894b3301 | note | 3. Record visual inspection details as follows:
4bfe655f-0264-5b2b-a786-c0aefd281c10 | note | C = Conforming. MV = Minor Variation. SD = Serious Deficiency
ba54afae-ad4d-5e5f-ac65-59b3c5433a33 | note | 4. Initial the ‘INSPECTED BY’ box.
9f524532-4138-5b28-a5e5-6d3e642d83a1 | note | Note: Fire ants check applicable in Queensland only.
50eacd85-1967-5541-aaba-400ae723596f | note | If non-conforming do the following:
ad179767-a984-513f-ab97-1f992eba4847 | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form – NCR shall be raised.
9ae82db5-7ce3-59db-86c9-bec11347d85d | note | b. If either visual inspection is SD isolate material (flag) and remove - investigate with supplier, then closely monitor supplies untilresolved, or
20266c9e-c598-5d95-9a48-6a4250397164 | note | c. If either visual inspection is MV consult with supplier, do additional testing to check degree of variation.
cc9d727d-15a3-5a88-8512-8ebc4fc370ca | date | DATE
7fdca3b1-b291-5b53-991f-ee1ee8577e7d | textbox | TIME
ce8a436d-3977-599c-915f-0128770a7252 | textbox | SUPPLIER
fa4fcea2-a445-515f-b693-557a49a3233a | textbox | AGG. SIZE
5acf4ff0-30a2-56fb-8e85-c59e9938f11c | button | VISUAL: SHAPE | C,MV,SD
6ef1a225-065a-51ec-963b-5c3e4883fbfd | button | VISUAL: FOREIGN MATTER | C,MV,SD
526a2106-16f8-47f1-9036-2a98cb4c2018 | checkpoint | FIRE ANTS CHECK
767fefd0-79e8-4202-ac7a-c6c437b26fd7 | checkpoint | INSPECTED BY
5644990d-355e-4094-8e29-32587a813f76 | signoff | Signoff
72e2e387-9c34-414d-a825-efb287d0e3a6 | checklist | QA - 007 - Reinforcement Inspection V3 |  | QA - 007 - Reinforcement Inspection
c9f353c1-8c5c-48ee-a6ae-912544dfcebf | section | REINFORCEMENT INSPECTION
02a747b2-cae7-4852-95f1-26b8533c1f96 | checkpoint | Details
cdabaad2-9dee-5934-84af-58906e8ecc11 | note | Procedure
714e480b-7ce5-5aa3-8645-578924b70f29 | note | Minimum Frequency - EACH DELIVERY
035d4dd0-490f-5af9-8a25-ccdcdf809b7c | note | 1. Check 1 in 50 (min 1 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
733cf5af-aa07-58ea-ac08-8587038b2c24 | note | 2. Visually inspect wire and record details below as follows
0ce52aa0-d407-5d49-8d11-d04f421b1b89 | note | C = Conforming MD = Minor Deficiency SD = Serious Deficiency
8cbe266a-7e15-5083-88a3-c0f45beaa2f4 | note | 4. Inspect all reinforcement in the delivery to ensure it is compliant with specified on site mass limits
2a5aca1d-96b5-5cba-a9a2-b7d4330b051e | note | (i.e., Wodonga mass limit = 1900kg) and record details below as follows C = Conforming NC = Non-conforming.
6bdb8c1c-a8a5-596e-ab39-53f8903fb876 | note | 5. Initial PASS or FAIL box, THEN:
77ad0736-701b-5ada-9c66-5b85a6324bf9 | note | Minimum Frequency - ANUALLY
05e20a57-1bcf-5850-b5fe-0421cc93b13f | note | 6. Obtain 3 of NATA Test Certificates from Manufacturers indicating breaking stress values for Annual UTS results. Average results and record
e03c8bcf-7e4e-5ffb-b3b9-7d8011bf3fc8 | note | If non-conforming do the following:
3b5a8ba8-9bbe-5954-83eb-ebbaabe44396 | note | a. If visual inspection has SD or continuing MD then:
d3a9c5ae-3627-5849-9fc4-f4418d94b0a6 | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
e33b35fa-91d7-5f79-bbd6-38895f6c67db | note | — Quarantine coil and follow up with supplier.
75a236dd-aff8-57d5-a33b-74706a0b0140 | note | b. If mass limit is NC then:
0dd2ea62-eaf5-51b1-b40a-302ccda2cf77 | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
2c795287-c8ab-5e64-bcdd-ca612be08ccc | note | c. If UTS result outside AS4671-2019 or AS4672-2007
97a38725-cc42-5ab2-874b-6a72001f2a5b | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
7943049e-426f-5ee2-a40d-436a279db79b | note | — Reject further coils and follow up with supplier.
1064e8e8-8de1-5373-94d0-5206908e168e | note | — Follow up on representative final product testing.
b03c87dd-62ac-5bc0-b0d3-77a5969a7789 | dropdown | Reinforcement Size | 5.55,7.02,9.88,12.33,15FWB,20FWB,N20,N24,12.7 STRAND,9.5 STRAND
d689ce7d-b453-5989-8bc1-78f4c00c17ad | textbox | Delivery Docket No.
e2d46c35-d335-551a-a921-cb79db216756 | textbox | Coil/Batch No.
f71de0df-dc9b-519e-8f8f-6474513557e0 | date | DATE: Delivered
fcb3a7b3-29ac-54ce-a897-36fe5795af84 | date | DATE: Inspected or Tested
37ea6b65-2b31-5661-b0d0-575d8bbeb6c1 | button | Visual inspections: Dimensions | C,MD,SD
f676edf1-e55f-5ef2-bf2a-205acbc2c8f4 | button | Visual inspections: Rust | C,MD,SD
e74f4520-88d7-5ec4-8d1b-548bbc2d4bbb | button | Visual inspections: Surface oil | C,MD,SD
7dc538d9-087c-5933-abd5-5df9cffbd3f5 | button | Compliant with specified on site mass limits? | CONFORMING,NON-CONFORMING
bd98ae33-4bb2-40df-ba2b-093c0ec21995 | checkpoint | INSPECTED BY
c878f383-9a84-45fe-8356-94a3a9f7af71 | signoff | Signoff
721b5495-8500-4c93-a675-93d07fa38110 | checklist | QA - 008 - Fabricated Reinforcement Inspection V1 |  | QA - 008 - Fabricated Reinforcement Inspection
5a21347d-cd45-4b06-be08-8d57d7261442 | section | Fabricated Reinforcement Inspection
0ede2eb3-9945-483a-9a35-461f658f48d3 | checkpoint | Details
cf38403a-0ad7-5f97-8264-64759ff20147 | note | Procedure
ad2fadf1-002b-5f38-89d9-40ff71d83769 | note | Minimum Frequency - EACH DELIVERY
2b78f3a9-85ef-5792-b11d-42218f2b7a35 | note | 1. Review delivery docket to confirm quantity and other specific information.
5cd1af35-2e56-5213-9584-3b716b8a899c | note | 2. Check each delivery conforms to the relevant drawing or specific requirements including relevant AS (i.e., AS 4671, AS 3679, AS 4291 etc).
64314b32-8f75-5693-a65a-3b6c3e2f3b2e | note | 3. Check at rate of 1 in 50 (min 2 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
e1aa1da1-5e67-5c93-b7d1-6ab76743ece4 | note | 4. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended).
6b494e34-337f-5fdf-966d-34fde8c33bcc | note | If non-conforming do the following:
9e64dddf-84fc-50df-b54f-ee3bd6a952a2 | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
dfd7abf9-1991-5828-a175-65e916ee13df | note | b. Check a further 2 items (in the sample size).
d0932050-6f28-5679-a127-262b0a2dc131 | note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
23e74b30-ff88-5e57-be70-08cdd0a6f4e5 | note | d. Isolate and identify all defective reinforcing or batches of reinforcing.
57744ff4-0122-5899-abc9-e9645577f8f6 | textbox | ITEM DESCRIPTION
824ccc59-a090-559e-a149-54db0ef37381 | textbox | SUPPLIER
0c737b63-1783-59c4-8f40-d127d59bcfdb | button | Supplier QEC | Yes,No
948f6b86-205c-52b8-ba3c-9222b3b523f2 | note | DELIVERY DETAILS
619e7aa5-de0c-531f-a33d-23663cc75459 | textbox | Delivery Docket No.
ae6e1964-27e9-5516-8162-577e5e4a5945 | date | Date Received
69f88f9c-cbb2-5032-865d-c15c839f6b86 | textbox | Quantity Received
d6c01785-0665-5451-87a9-93d66bbc6554 | textbox | Sample Size
e265a04e-44d2-5c58-a4b7-61f93830a99b | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
58c1f459-fa25-44b7-af7e-48398ac97064 | checkpoint | INSPECTED BY
45687411-4fe6-4ad4-aacc-18ca223186b7 | signoff | Signoff
640b5e42-d654-43ef-b2d6-7b0dc78b5704 | checklist | QA - 009 - Fittings Inspection V1 |  | QA - 009 - Fittings Inspection
4283c580-b43f-42b4-985d-47cecc69a0a7 | section | Fittings Inspection
8c0b3e2c-5a46-47b6-8bd8-4e6cfda076fd | checkpoint | Details
31cc0cdb-2d29-58e3-855d-6acd6ffff43d | note | Procedure
1dc354e4-9d29-5ae7-bebc-9371b5a4ea28 | note | Minimum Frequency - EACH DELIVERY
be1e8c5d-1cc7-5124-afa5-a889d33bde49 | note | 1. Check fittings: Mass produced (extruded, cast, machine fabricated) at the rate of 2 per container of same items, or if the supplier is a Quality Endorsed Company (QEC) as recorded on the approved suppliers list, a minimum inspection of 2 items per delivery.
475cfd8c-d5f9-52e9-a1c1-f113e67f4f5a | note | 2. Note whether the supplier is a Quality Endorsed Company.
fdad35a6-3232-55b4-8415-b00800115195 | note | 3. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended)
78ea4562-1853-53a0-b9c3-e6545a884d42 | note | If non-conforming do the following:
bb5dc947-5938-5f30-b543-f4e9e2ffa73d | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
0e5aef8b-9637-5c74-a0cf-405ea9f2832b | note | b. Check a further 2 items (in the sample size).
ddab41bb-b85e-5157-874e-b75f0718d0fe | note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
1ab82ef2-dd98-56d9-b989-529d68633595 | note | d. Isolate and identify all defective fittings or batches of fittings.
9ba5127a-6ec8-5bad-b023-6fddfdf2a53b | textbox | ITEM DESCRIPTION
70967962-cfa6-5104-8ab6-d62f82cdb059 | textbox | SUPPLIER
e4373743-ad0c-57f3-b4dd-e076fced9cfc | button | Supplier QEC | Yes,No
09a05859-555a-5571-9fef-ba90ce7553df | note | DELIVERY DETAILS
67433f20-4103-5461-a555-4d310c54ecb9 | textbox | Delivery Docket No.
12dd4c80-6d2f-537a-9a2f-385e3a1e468f | date | Date Received
66dfa29b-cee1-51aa-b243-964e9422ab02 | textbox | Quantity Received
795baee1-cd2e-57b6-a93a-ca274b414532 | textbox | Sample Size
0a4538ff-41fc-5209-bf03-39f2a39a9026 | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
6c2686ad-7d91-4251-9214-2ce5f8dac7e1 | checkpoint | INSPECTED BY
26933cf2-5552-4b0b-9d4b-043033597b23 | signoff | Signoff
bcabbb4c-79f6-4e6d-9052-cec0b38dc7b3 | checklist | QA - 016 - Assembled Product Inspection V1 |  | QA - 016 - Assembled Product Inspection
f3ad3f8b-9349-4870-89c8-1e1fd402143e | section | Assembled Product Inspection
e1d96f70-8bf7-48d2-9825-234d25f30f15 | checkpoint | CHECKED
9a685ce2-0942-585a-9de0-4f9f4b758085 | textbox | CAGE SIZE / TYPE
182d87b5-35a0-5c9d-9c0a-8dc5f51806f4 | textbox | CAGE TAG #
4e8bc008-7ff2-51a1-ae7e-ce171bc5f1ed | textbox | MOULD #
c52ba43f-faa5-5014-b1b6-aec39f6475e5 | textbox | DRAWING #
d5193a18-1fc6-5adc-b120-8c8759e3dc60 | textbox | REVISION NUMBER
b4ca4392-2ed2-5a1f-a533-5ecf9ca0a63a | textbox | # STUDS / TIP FERRULES
7ad9404c-bb0a-5c99-a68d-5bf9293d562c | button | ANTI-ACCESS BARS | Yes,No
83d4a479-77b4-5049-9f38-b47c7252f400 | textbox | # LUGS / BUTT-EARTHS
4cd93123-e9d0-52ed-a85d-3d6ed31c5194 | textbox | # STRANDS
0a365049-1cca-5047-8b23-d5b66b2f68e3 | button | CHECK FOR CROSSED STRANDS | Yes,No
370e7c70-4c54-5e86-931a-1664135aa842 | button | ALL JOINT BARS WELDED | Yes,No
865185c2-323d-5d02-aa72-eb7a78493ab9 | button | STUD/LUG AS PER DESIGN | Yes,No
a8797400-13dc-524c-bad2-6a92a58f2cb6 | button | JOINT RING | Yes,No
43545a93-f399-5749-8ae2-1f9411fc647a | button | LIFT TUBES CHECKED | Yes,No
950d29ca-b09f-5ede-b393-59e1a39e6ce8 | button | SEEMS SCRAPED | Yes,No
8c0fa1d7-f424-55d0-830d-0e32f5dac415 | button | MOULD OILED | Yes,No
d04c8780-b406-5592-9e6c-343d0e6427ec | button | PLATES OILED | Yes,No
38902269-42ac-5d5f-ad18-00298bd247b3 | button | BARREL/WEDGES SEATED | Yes,No
ac27c6ec-7d35-5ed1-bfe1-94d1ed3157bd | button | CLEARANCE CHECK | Yes,No
64eb4fd7-6052-5835-9792-9a9750f622aa | textbox | COIL # ON PACKAGE
5b0934da-78fe-4fec-a37d-dcdaa03263cb | checkpoint | PRODUCT ACCEPTED
bec814de-c1a4-4fb3-a1ab-f28c174648d7 | checkpoint | INSPECTED BY
74de8def-88df-4051-9eac-ab7d78a89569 | signoff | Signoff
c7061147-b18c-45f0-beed-98f6805f93b9 | checklist | QA - 028 - Load Visual Inspection V1 |  | QA - 028 - Load Visual Inspection
1d0d6bcd-16b8-49bb-82ae-b68ba2fc9d82 | section | Load Visual Inspection
d1930446-13bb-421a-946e-9e3a07238aaa | checkpoint | Load
7a1c1ce2-5d76-51c2-8b94-5653ef21cda4 | note | Procedure
95debc8e-64b3-5a37-a220-c1c9dbd57885 | note | Minimum Frequency - 1(i) LOAD / WEEK
e5adfd5f-60e2-582c-b5fc-be1b4de632da | note | 1. Observe the loading of product to ensure compliance with established procedures and relevant Work Instructions.
c5dbcbfc-2586-5239-8ab6-5c606993982b | note | 2. Observe load for product damage (compared with conveniently located, correctly branded product sample of customer / specification)
0b19f323-60fa-5ab4-bbe0-6a6723b9d4fe | note | 3. Check load for all items against the details on the loading slip. Confirm that correct products and quantity are present.
7e235426-11bd-58fb-a193-ea0c3bbfa2d2 | note | 4. Confirm Quality Checks & Chain of Responsibility Checks (CoR) are completed by the loader.
0d910843-30d4-5642-84a4-62220ba14a35 | note | 5. Record all observations.
504c44d2-b9a4-5b62-aa95-60f504ca18b0 | note | Notes:
8784115b-975c-5644-8801-903702350854 | note | (i) Increased frequency may be required where high output occurs or non-conformance has occurred.
031451ab-f4ac-5fc6-b209-a60ea3a3f8a1 | note | (ii) Fire Ants check applicable in Queensland only.
8eea6e1e-401e-5733-96a5-947aba26c1ed | note | (iii) Deviation from established procedure is regarded as non-conformance.
14ef1ee3-3457-5715-854f-d7e8d0230743 | date | Date
233a77c9-4c5b-5a03-987f-f337b4a64bbc | textbox | Carrier
ff39f8ad-d7d0-5f25-8511-f01c25bf040e | textbox | Client
e35da9cc-c366-5cb6-99b2-49b1b06e4111 | textbox | Loading Docket No.
0c330066-5977-5a9b-b715-46cf76daae83 | textbox | Loaded by (Loader & Dogman Initials)
0d0c83c2-65e2-4514-9a0b-5575a81ed669 | checkpoint | Observation:
8631e487-1aa6-59c8-ae42-43fb94a6b890 | button | Exclusion zone established? | Yes,No
608529b2-67a1-541d-9e99-72855ebd57a2 | button | Platform ladders in place and used? | Yes,No
7ad0069d-4971-5722-adf9-fca340cbeb46 | button | Work crew wearing all required PPE? | Yes,No
bd4aebd8-5aa9-50d8-992d-be2a3fcf166c | button | Lifting equipment positively attached? | Yes,No
8c9b91ec-c1cf-5930-a1af-47e3fb47daab | button | Tagline used at all times? | Yes,No
6111e7fb-0698-5695-b2f5-84f8f0e5e3a6 | button | Lifting and shifting completed as per SOP? | Yes,No
1ca27a87-3077-5cd5-936c-20d8bbd8e499 | button | Any unsafe practices or deviations observed? | Yes,No
3f183ac0-7ae8-5149-aa51-52ac377e4d77 | button | Quality Checks completed by the loader? | Yes,No
f98ea210-3af8-55c9-be1d-ebd2aaaa686f | button | Chain of Responsibility Checks (CoR) completed? | Yes,No
bec2e18c-f687-5cc6-856f-4e8419893453 | button | Any product damage identified? | Yes,No
014fda89-7d71-5a21-a523-fe5db903eee6 | button | Products, items, and quantity, correct? | Yes,No
2ecb94b0-9791-42d5-b2dd-0fc7e3ca7cf7 | checkpoint | Fire Ants Check (QLD only)
0d0e9b31-8387-4e95-a090-dcc4ab88bbca | checkpoint | INSPECTED BY
1581afd1-34cb-492f-a97e-f238e0dc42ec | signoff | Signoff
e09b7aa8-9794-42bc-8afb-f6cb895dfff0 | checklist | QA - 060 - First Up Product Mould Inspection V1 |  | QA - 060 - First Up Product Mould Inspection
cfef7878-6269-40ee-acea-d0d19a37843d | section | First Up Product Mould Inspection
e99663d6-8e28-4095-8e1a-ad5bd880b0c6 | checkpoint-no-value | Details
2cbe521f-510f-5ca2-be8b-52de15b258be | date | Date:
5adfecdb-8871-50a8-8db1-dd36b7368dfc | textbox | Worker Completing Mould Inspection:
e54b58a3-3499-56ff-9100-9d1812645177 | textbox | Pole Type / Size:
97795e48-9950-57c7-8aff-b4ac473148a8 | textbox | Mould No.:
9371148b-a3de-5e7a-bac3-22d48c285692 | tickbox | New Mould
1cf3bf27-d07a-5098-867d-703f90e58fb5 | tickbox | Mould from repair
c78fcf9e-80ab-5911-ba68-b428d8c5af8c | tickbox | Mould From Storage
332392d3-0301-4027-92a4-dd2cab72fcd0 | section | DIMENSIONAL CHECKS
28f8ff42-c18d-482b-8602-5e43a7cd0d69 | checkpoint | Tip Diameter
a28cfaf8-6be9-5f67-b98b-17c73551543c | textbox | DESIGN
db202ee6-90b0-5397-ab87-5eb672dd070c | textbox | ACTUAL
4c263ec5-9b86-51ef-92f9-56a5cb0eede0 | note | TOLERANCE
1f232032-f0fb-53aa-93ec-3297b39cffa3 | note | POLES: ± 2 mm
da10dca6-3853-5a58-83c7-9b6f4ec1ef36 | note | PILES: + 10 mm, - 5 mm
7a634c83-a21d-4c6c-bf33-505a5e8368a1 | checkpoint | Butt Diameter
d81622f5-1468-5c4f-9953-2423a9508d26 | textbox | DESIGN
e0545981-ce28-5dcc-ae30-8dce649ed63f | textbox | ACTUAL
609d34d5-f53f-5843-a666-dde26294732f | note | TOLERANCE
c34a9a84-9284-5ec6-83c3-3fe56ac30044 | note | POLES: ± 2 mm
60129f9c-04ec-52b7-a879-943092c7f843 | note | PILES: + 10 mm, - 5 mm
aa808996-6eb2-446e-a8a6-8a77c6f2bee3 | checkpoint | Distance from butt to depth marker
b9eb723c-4d19-5f0f-b711-42bfa6a4ab61 | textbox | DESIGN
12dc2024-8d5a-5835-84aa-5cde4910b751 | textbox | ACTUAL
a9ddef7f-64fa-5507-9fe3-3ffabd8aa979 | note | TOLERANCE
9222f48c-d3b3-534a-939b-f085eb0f7f29 | note | POLES: ± 100mm
67efc7c8-10af-5561-acc5-4cde5cbf14fd | note | PILES: N/A
dcd8eed2-db1f-4dcb-b885-cb6e3190a1c8 | checkpoint | Distance from butt to Name plate location
39849a31-78e9-5270-964f-0381bb029927 | textbox | DESIGN
6c4dbc76-c4be-5087-a118-3440fa3829aa | textbox | ACTUAL
28811510-147f-5aed-90d9-c97f215db7b1 | note | TOLERANCE
a0fc47ca-6edf-5977-acf5-e4f11ee43e9d | note | POLES: ± 100mm (Unless interference occurs)
aa23a87b-69b4-5e88-a421-82935737b630 | note | PILES: N/A
d6efb28a-1ec1-403c-bf19-9010ebf5c8cb | checkpoint | Specified Product Length
5239450d-39e4-5416-9b91-c83267de7ae5 | textbox | DESIGN
53edb291-f399-5f85-a1e6-1a3287299936 | textbox | ACTUAL
83f649ec-48b9-5e89-af7e-d987dff7de62 | note | TOLERANCE
ed4670be-fb79-5540-9cb8-5cc67aecab38 | note | POLES: ± 50mm Poles
e1ca172a-6a7e-5bf1-bf56-01c33816b708 | note | PILES: + 50mm, - 0mm
40d42edc-8b00-4044-ab0a-ca6db2ab9166 | section | MOULD CHECKS
f829e5c4-276d-459c-9938-fc14dc1f9e57 | checkpoint | Does the mould have all locating pins
98e13503-4498-46c0-9939-1d426912bd45 | checkpoint | Has the mould been clean thoroughly including weld spatter?
314528ae-1a9b-49f3-92d0-7d08042c6494 | checkpoint | Have all unused locating holes been filled
b88511fe-4481-443d-bb88-2fa0608582af | checkpoint | Have the seams been scraped
42043672-2e06-4b1b-b4ff-82aff3fc245d | checkpoint | Are there any cracks in the mould
83e4bd08-ee09-4eda-b738-4a142ede6a60 | checkpoint | Have running rings been secured correctly?
2ad2b5c6-e1fc-48b5-9456-7cb2dbb40e28 | checkpoint | Have mould sections been sealed with silicone and secured correctly?
9181338a-b4de-4f18-960c-0e75dcae2ff5 | section | FINISHED PRODUCT VISUAL CHECKS
7c723feb-1e3a-4970-aeae-54fd32b45d74 | checkpoint-no-value | Details
92fb1df2-9ba1-521e-9c20-3f24a55904a9 | date | Date:
5a3d73d2-3a18-5321-b4b7-c66883d889bc | textbox | Product No.:
4f5ef9c3-bc85-4ad9-b43b-400847890d5d | checkpoint | IS THE FOLLOWING NOTICEABLE?
4e2d5b39-3767-5b6b-a748-a2342c516220 | note | BULGES, INDENTS, HOLES, SEEM BLEEDS, RUST MARKS, DIRT MARKS, FOREIGN MATTER OR SILICONE
d64d7385-9d07-4606-980b-c9adf008c286 | checkpoint | INSPECTED BY
f90bcea3-eaf4-4e7a-a039-048fbdec5cae | signoff | Signoff