## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
952573a6-db98-454c-a564-b6c29f5e9f50 | checklist | QA - 001 - Cement Records V1 |  | QA - 001 - Cement Records
7c7b2d6b-98e8-468f-bf77-499699d3f691 | section | Cement Records
729d5db7-2e22-4405-8340-8beb2f67fb48 | checkpoint-no-value | Details
| note | Procedure
| note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
| note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
| note | 2. Record details and compare to minimum acceptable specifications.
| note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
| note | If non-conforming do the following:
| note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | b. Identify unused cement on site, reject if outside minimum specification.
| note | c. Notify supplier of non-conformance.
| note | d. Examine test performance of completed products/cylinders to identify potential production defects.
f734497e-0776-5752-b89f-d83d1b7408fb | date | QUARTER ENDING:
6f055d20-7d89-52b4-94de-988530b2d182 | tickbox | Or, new supplier or new type
c05ae3b9-894b-55ac-922b-f2d2813a6ed0 | date | DATE
90dd9c50-f6d5-5bea-942a-151a77670bd2 | textbox | SUPPLIER
55b907a8-227f-5c09-8a13-bbbe098ef275 | textbox | DOCKET No.
0a21d3e1-6d44-51ee-bfb1-04dcd406ed9f | textbox | CERTIFICATE No.
9d3dd8de-3506-5cf1-b6b8-e5fd4ceda689 | textbox | CEMENT TYPE
a36722d7-0eaa-41a4-aa63-c0eb4ba8f216 | checkpoint | Properties meet AS3972
2ab9799b-54c8-4f46-97c1-a427b5cdaff5 | checkpoint | Cement meets Civilmart Poles Spec.
| note | Poles Cement Specification
| note | — — — — — — — — — — — — —
| note | TYPE ¦¦ **C3S content ¦¦ Fineness Index * ¦¦ Initial Set - Hrs. ¦¦ Total Alkali NA20 equivalent ¦¦ SO3 content ¦¦ C3A (informative)
| note | — — — — — — — — — — — — —
| note | GP ¦¦ > 55% ¦¦  350 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
| note | GB ¦¦ ≥ 55% ¦¦ Max.15% on 45m sieve ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
| note | HE ¦¦ ≥ 50% ¦¦ > 380 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
| note | SR ¦¦ > 55% ¦¦ > 330 ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
| note | — — — — — — — — — — — — —
| note | All cements shall comply with the relevant clauses of AS3972 table 1, except that:
| note | a. All types (except GB) shall contain no mineral additions without prior written agreement from Civilmart Poles.
| note | b. The following restrictions shall apply:
| note | Particular cements which do not comply with these latter requirements can be used but only after gaining written approval from the Regional/Area or Manufacturing Manager.
| note | Certain products, contracts or processes may require individual specifications.
| note | * Minimum fineness indices should be agreed with individual suppliers during contract negotiations but should not be less than these values.
| note | ** It is recommended that the clinker or OPC used to make the blend have a C3S as indicated for GB. Ideally the blend should contain at least 75% by mass of OPC.
7f96aa46-6c65-4a6f-96db-a825017125c0 | checklist | QA - 002 - Fly Ash and Admixtures Record V1 |  | QA - 002 - Fly Ash and Admixtures Record
593bdd89-9963-4604-94a2-94815c22053d | section | Fly Ash and Admixtures Record
68cb878e-9a71-4641-8ebc-e17fc3fe5cf1 | checkpoint-no-value | Details
| note | Procedure
| note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
| note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
| note | 2. Record details and compare to minimum acceptable specifications.
| note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
| note | If non-conforming do the following:
| note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form.
| note | b. Identify unused fly ash/admixture on site, reject if outside minimum specification.
| note | c. Notify supplier of non-conformance.
| note | d. Examine test performance of completed products/cylinders to identify potential production defects.
98cab6b8-14d1-5f23-8a0b-f22f8b1c5fcb | date | QUARTER ENDING:
ad195689-c612-59f8-9494-f7c1a4c00bcc | tickbox | Or, new supplier or new type
75f4bd75-3319-521c-aff5-6bed3c665c75 | tickbox | Review / approval from Engineering Department
453e3c45-35d7-4a2a-b2b3-b35c994d1609 | section | PART 1 - FLY ASH
452f21c1-f41a-4829-85cd-38f700444d9b | checkpoint-no-value | Details
3f881ef3-2238-585b-8b53-b630ac52da42 | date | DATE
589442b2-82b4-5c4f-8109-921b5d9abb16 | textbox | SUPPLIER
3a90779e-4f37-553e-a5f1-29109a2c230b | textbox | DOCKET No.
e6d61c05-a98f-52e0-b167-bfc02e9a817a | textbox | CERTIFICATE No.
51753b7c-b318-5eb0-9cb3-83688fa58a10 | textbox | FLY ASH TYPE
5459f5ef-2b9d-4291-b107-666565113b90 | checkpoint | Remaining properties meet AS3582.1
8fda78bf-fa2e-4878-aa6c-99731038f914 | checkpoint | Meets Civilmart Poles Spec.
1501db86-a1fa-5124-a8c8-417338207b60 | note | Civilmart Poles Minimum Acceptable Specification:
34a455ce-601b-5bc1-a282-c2660de8e83b | note | Moisture 1% max, >75% passing 45μm sieve, loss on ignition <4%
fd9ea64b-957b-5f31-9ec9-7265067ad861 | note | Density and available alkali must be reported
a26c9a07-2a1e-5756-b3c2-23379c7178f8 | note | i.e. apart from these Civilmart Poles requirements, all other properties must meet AS 3582.1 Grade "Fine" (refer to fly ash certificate)
1daaec9d-a9ee-4260-b210-c4214b3fb90b | section | PART 2 - ADMIXTURES
4eafc774-32ed-42fa-8440-22c9f150ac92 | checkpoint-no-value | Details
901f3faf-e0e2-59db-a008-b49f9ae5f9b5 | note | Certificate of Analysis (CoA) to be obtain to provide records for investigative/comparison purposes. Refer to ITP for required frequency.
a80215e2-0cb5-597b-a708-fb1e0f08c03c | date | DATE
619053d0-12c7-58b0-b9fc-a739ad8920f1 | textbox | SUPPLIER
3fe35740-7ffd-55c9-8cc3-1fe469e55b3b | textbox | DOCKET No.
d4696dce-970f-5e1f-b249-e532ab72ce92 | textbox | CERTIFICATE No.
e180b7e6-4694-5290-a0aa-82f30abe793a | textbox | ADMIXTURE TYPE
2418440b-19ab-5b8c-ac50-f2ee925a356b | textbox | BRAND NAME
ae8a9049-ab04-468d-bfd2-6e5f2eaba12c | checklist | QA - 003 - Aggregates Visual Inspection V1 |  | QA - 003 - Aggregates Visual Inspection
deda7b58-f1fe-4d4f-9213-b3d6102d8f16 | section | Aggregates Visual Inspection
b42fa1da-6da7-49ad-9e4e-e76938046445 | checkpoint-no-value | Details
| note | Procedure
| note | Minimum Frequency - QEC - none except new supplier
| note | Non-QEC - 1 Delivery / Week / Type / Supplier OR Where non-conformance is found from daily check.
| note | 1. Visually inspect all aggregates.
| note | 2. Maintain an agreed reference sample (from initial supply) for comparison with supplied aggregates.
| note | 3. Record visual inspection details as follows:
| note | C = Conforming. MV = Minor Variation. SD = Serious Deficiency
| note | 4. Initial the ‘INSPECTED BY’ box.
| note | Note: Fire ants check applicable in Queensland only.
| note | If non-conforming do the following:
| note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form – NCR shall be raised.
| note | b. If either visual inspection is SD isolate material (flag) and remove - investigate with supplier, then closely monitor supplies untilresolved, or
| note | c. If either visual inspection is MV consult with supplier, do additional testing to check degree of variation.
cc9d727d-15a3-5a88-8512-8ebc4fc370ca | date | DATE
7fdca3b1-b291-5b53-991f-ee1ee8577e7d | textbox | TIME
ce8a436d-3977-599c-915f-0128770a7252 | textbox | SUPPLIER
fa4fcea2-a445-515f-b693-557a49a3233a | textbox | AGG. SIZE
| button | VISUAL: SHAPE | C,MV,SD
| button | VISUAL: FOREIGN MATTER | C,MV,SD
526a2106-16f8-47f1-9036-2a98cb4c2018 | checkpoint | FIRE ANTS CHECK
72e2e387-9c34-414d-a825-efb287d0e3a6 | checklist | QA - 007 - Reinforcement Inspection V3 |  | QA - 007 - Reinforcement Inspection
c9f353c1-8c5c-48ee-a6ae-912544dfcebf | section | REINFORCEMENT INSPECTION
02a747b2-cae7-4852-95f1-26b8533c1f96 | checkpoint | Details
| note | Procedure
| note | Minimum Frequency - EACH DELIVERY
| note | 1. Check 1 in 50 (min 1 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
| note | 2. Visually inspect wire and record details below as follows
| note | C = Conforming MD = Minor Deficiency SD = Serious Deficiency
| note | 4. Inspect all reinforcement in the delivery to ensure it is compliant with specified on site mass limits
| note | (i.e., Wodonga mass limit = 1900kg) and record details below as follows C = Conforming NC = Non-conforming.
| note | 5. Initial PASS or FAIL box, THEN:
| note | Minimum Frequency - ANUALLY
| note | 6. Obtain 3 of NATA Test Certificates from Manufacturers indicating breaking stress values for Annual UTS results. Average results and record
| note | If non-conforming do the following:
| note | a. If visual inspection has SD or continuing MD then:
| note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | — Quarantine coil and follow up with supplier.
| note | b. If mass limit is NC then:
| note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | c. If UTS result outside AS4671-2019 or AS4672-2007
| note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | — Reject further coils and follow up with supplier.
| note | — Follow up on representative final product testing.
| dropdown | Reinforcement Size | 5.55,7.02,9.88,12.33,15FWB,20FWB,N20,N24,12.7 STRAND,9.5 STRAND
| textbox | Delivery Docket No.
e2d46c35-d335-551a-a921-cb79db216756 | textbox | Coil/Batch No.
f71de0df-dc9b-519e-8f8f-6474513557e0 | date | DATE: Delivered
fcb3a7b3-29ac-54ce-a897-36fe5795af84 | date | DATE: Inspected or Tested
| button | Visual inspections: Dimensions | C,MD,SD
| button | Visual inspections: Rust | C,MD,SD
| button | Visual inspections: Surface oil | C,MD,SD
7dc538d9-087c-5933-abd5-5df9cffbd3f5 | button | Compliant with specified on site mass limits? | CONFORMING,NON-CONFORMING
721b5495-8500-4c93-a675-93d07fa38110 | checklist | QA - 008 - Fabricated Reinforcement Inspection V1 |  | QA - 008 - Fabricated Reinforcement Inspection
5a21347d-cd45-4b06-be08-8d57d7261442 | section | Fabricated Reinforcement Inspection
0ede2eb3-9945-483a-9a35-461f658f48d3 | checkpoint | Details
| note | Procedure
| note | Minimum Frequency - EACH DELIVERY
| note | 1. Review delivery docket to confirm quantity and other specific information.
| note | 2. Check each delivery conforms to the relevant drawing or specific requirements including relevant AS (i.e., AS 4671, AS 3679, AS 4291 etc).
| note | 3. Check at rate of 1 in 50 (min 2 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
| note | 4. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended).
| note | If non-conforming do the following:
| note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | b. Check a further 2 items (in the sample size).
| note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
| note | d. Isolate and identify all defective reinforcing or batches of reinforcing.
57744ff4-0122-5899-abc9-e9645577f8f6 | textbox | ITEM DESCRIPTION
| textbox | SUPPLIER
0c737b63-1783-59c4-8f40-d127d59bcfdb | button | Supplier QEC | Yes,No
948f6b86-205c-52b8-ba3c-9222b3b523f2 | note | DELIVERY DETAILS
| textbox | Delivery Docket No.
ae6e1964-27e9-5516-8162-577e5e4a5945 | date | Date Received
69f88f9c-cbb2-5032-865d-c15c839f6b86 | textbox | Quantity Received
d6c01785-0665-5451-87a9-93d66bbc6554 | textbox | Sample Size
e265a04e-44d2-5c58-a4b7-61f93830a99b | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
640b5e42-d654-43ef-b2d6-7b0dc78b5704 | checklist | QA - 009 - Fittings Inspection V1 |  | QA - 009 - Fittings Inspection
4283c580-b43f-42b4-985d-47cecc69a0a7 | section | Fittings Inspection
8c0b3e2c-5a46-47b6-8bd8-4e6cfda076fd | checkpoint | Details
| note | Procedure
| note | Minimum Frequency - EACH DELIVERY
| note | 1. Check fittings: Mass produced (extruded, cast, machine fabricated) at the rate of 2 per container of same items, or if the supplier is a Quality Endorsed Company (QEC) as recorded on the approved suppliers list, a minimum inspection of 2 items per delivery.
| note | 2. Note whether the supplier is a Quality Endorsed Company.
| note | 3. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended)
| note | If non-conforming do the following:
| note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
| note | b. Check a further 2 items (in the sample size).
| note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
| note | d. Isolate and identify all defective fittings or batches of fittings.
9ba5127a-6ec8-5bad-b023-6fddfdf2a53b | textbox | ITEM DESCRIPTION
| textbox | SUPPLIER
e4373743-ad0c-57f3-b4dd-e076fced9cfc | button | Supplier QEC | Yes,No
09a05859-555a-5571-9fef-ba90ce7553df | note | DELIVERY DETAILS
| textbox | Delivery Docket No.
12dd4c80-6d2f-537a-9a2f-385e3a1e468f | date | Date Received
66dfa29b-cee1-51aa-b243-964e9422ab02 | textbox | Quantity Received
795baee1-cd2e-57b6-a93a-ca274b414532 | textbox | Sample Size
0a4538ff-41fc-5209-bf03-39f2a39a9026 | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
c7061147-b18c-45f0-beed-98f6805f93b9 | checklist | QA - 028 - Load Visual Inspection V1 |  | QA - 028 - Load Visual Inspection
1d0d6bcd-16b8-49bb-82ae-b68ba2fc9d82 | section | Load Visual Inspection
d1930446-13bb-421a-946e-9e3a07238aaa | checkpoint | Load
| note | Procedure
| note | Minimum Frequency - 1(i) LOAD / WEEK
| note | 1. Observe the loading of product to ensure compliance with established procedures and relevant Work Instructions.
| note | 2. Observe load for product damage (compared with conveniently located, correctly branded product sample of customer / specification)
| note | 3. Check load for all items against the details on the loading slip. Confirm that correct products and quantity are present.
| note | 4. Confirm Quality Checks & Chain of Responsibility Checks (CoR) are completed by the loader.
| note | 5. Record all observations.
| note | Notes:
| note | (i) Increased frequency may be required where high output occurs or non-conformance has occurred.
| note | (ii) Fire Ants check applicable in Queensland only.
| note | (iii) Deviation from established procedure is regarded as non-conformance.
14ef1ee3-3457-5715-854f-d7e8d0230743 | date | Date
233a77c9-4c5b-5a03-987f-f337b4a64bbc | textbox | Carrier
ff39f8ad-d7d0-5f25-8511-f01c25bf040e | textbox | Client
e35da9cc-c366-5cb6-99b2-49b1b06e4111 | textbox | Loading Docket No.
0c330066-5977-5a9b-b715-46cf76daae83 | textbox | Loaded by (Loader & Dogman Initials)
| checkpoint | Observation:
| button | Exclusion zone established? | Yes,No
| button | Platform ladders in place and used? | Yes,No
| button | Work crew wearing all required PPE? | Yes,No
| button | Lifting equipment positively attached? | Yes,No
| button | Tagline used at all times? | Yes,No
| button | Lifting and shifting completed as per SOP? | Yes,No
| button | Any unsafe practices or deviations observed? | Yes,No
| button | Quality Checks completed by the loader? | Yes,No
| button | Chain of Responsibility Checks (CoR) completed? | Yes,No
| button | Any product damage identified? | Yes,No
| button | Products, items, and quantity, correct? | Yes,No
2ecb94b0-9791-42d5-b2dd-0fc7e3ca7cf7 | checkpoint | Fire Ants Check (QLD only)