## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
952573a6-db98-454c-a564-b6c29f5e9f50 | checklist | QA - 001 - Cement Records V1 |  | QA - 001 - Cement Records
7c7b2d6b-98e8-468f-bf77-499699d3f691 | section | Cement Records
729d5db7-2e22-4405-8340-8beb2f67fb48 | checkpoint-no-value | Details
60368e20-2fa9-5b48-894d-fd6449bb3661 | note | Procedure
5fd88907-4f9d-5e8f-b961-c404f218cb85 | note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
d6bc5a75-4174-523d-8fc5-93fd0655b9f4 | note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
ff5e4594-3564-5ca3-a416-16fb99d37b5f | note | 2. Record details and compare to minimum acceptable specifications.
b1ef194c-042d-5ad1-bd00-190166deb5ed | note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
ee1e4f32-33f6-572d-96a3-5b24bd081619 | note | If non-conforming do the following:
6266ae67-1be1-5a00-868d-8c917ea29dbd | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
c2e80835-2c54-5c4c-bf2d-d8fb032a5666 | note | b. Identify unused cement on site, reject if outside minimum specification.
225c5990-f586-58bb-8639-7eedeacef456 | note | c. Notify supplier of non-conformance.
88c824f3-2939-5366-95e6-37396f5eca9c | note | d. Examine test performance of completed products/cylinders to identify potential production defects.
f734497e-0776-5752-b89f-d83d1b7408fb | date | QUARTER ENDING:
6f055d20-7d89-52b4-94de-988530b2d182 | tickbox | Or, new supplier or new type
c05ae3b9-894b-55ac-922b-f2d2813a6ed0 | date | DATE
90dd9c50-f6d5-5bea-942a-151a77670bd2 | textbox | SUPPLIER
55b907a8-227f-5c09-8a13-bbbe098ef275 | textbox | DOCKET No.
0a21d3e1-6d44-51ee-bfb1-04dcd406ed9f | textbox | CERTIFICATE No.
9d3dd8de-3506-5cf1-b6b8-e5fd4ceda689 | textbox | CEMENT TYPE
a36722d7-0eaa-41a4-aa63-c0eb4ba8f216 | checkpoint | Properties meet AS3972
2ab9799b-54c8-4f46-97c1-a427b5cdaff5 | checkpoint | Cement meets Civilmart Poles Spec.
78f90b1c-5acd-5a32-965d-92eafeaba161 | note | Poles Cement Specification
cba6a794-2135-50ab-b2ef-f4b1c2ccfcd7 | note | — — — — — — — — — — — — —
4e923395-5e44-52c9-82ff-69fa8c18ad6e | note | TYPE ¦¦ **C3S content ¦¦ Fineness Index * ¦¦ Initial Set - Hrs. ¦¦ Total Alkali NA20 equivalent ¦¦ SO3 content ¦¦ C3A (informative)
115de9de-08a4-503d-8d46-0e4b5c55006b | note | — — — — — — — — — — — — —
f3bb8a9a-a4b1-530b-967e-7e350f389739 | note | GP ¦¦ > 55% ¦¦  350 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
fec9827a-c6ad-50e0-a93d-62da3e9c88f3 | note | GB ¦¦ ≥ 55% ¦¦ Max.15% on 45m sieve ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
2aabd5e9-38aa-5b6a-8496-ae754ba5ca04 | note | HE ¦¦ ≥ 50% ¦¦ > 380 ¦¦ < 2.5 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
86c77c77-e253-5cff-be8c-c6111dec4d04 | note | SR ¦¦ > 55% ¦¦ > 330 ¦¦ < 3.0 ¦¦ < 0.8% ¦¦ < 3.0 % ¦¦ Record Result to 0.1%
af22a899-66b9-5c8a-9934-f88e4bfd42de | note | — — — — — — — — — — — — —
87e4dbeb-04b3-578a-8a2c-d4d6184e497c | note | All cements shall comply with the relevant clauses of AS3972 table 1, except that:
c34297f1-0a72-5f8b-9699-b938f9529d2a | note | a. All types (except GB) shall contain no mineral additions without prior written agreement from Civilmart Poles.
caaab089-1d4c-5aa7-96d2-c1b2e825116a | note | b. The following restrictions shall apply:
6dd00535-7ede-5ed2-bf22-879dacb0448c | note | Particular cements which do not comply with these latter requirements can be used but only after gaining written approval from the Regional/Area or Manufacturing Manager.
dc4672f8-e650-5982-817e-ee48d83d175c | note | Certain products, contracts or processes may require individual specifications.
cea58245-fe1e-5624-87b7-a5208b9a982b | note | * Minimum fineness indices should be agreed with individual suppliers during contract negotiations but should not be less than these values.
ad9a0b43-fc71-5494-893e-eb438f40643b | note | ** It is recommended that the clinker or OPC used to make the blend have a C3S as indicated for GB. Ideally the blend should contain at least 75% by mass of OPC.
| checkpoint | INSPECTED BY
| signoff | Signoff
7f96aa46-6c65-4a6f-96db-a825017125c0 | checklist | QA - 002 - Fly Ash and Admixtures Record V1 |  | QA - 002 - Fly Ash and Admixtures Record
593bdd89-9963-4604-94a2-94815c22053d | section | Fly Ash and Admixtures Record
68cb878e-9a71-4641-8ebc-e17fc3fe5cf1 | checkpoint-no-value | Details
b2588d04-fa3d-5a32-8af9-5ff7f3ed24d1 | note | Procedure
eabc7066-58e2-5c2d-9dd0-08ca7fa75077 | note | Minimum Frequency - QUARTERLY / TYPE / SUPPLIER.
b530bd4a-30c4-5b5f-b2e1-660bf1e827ef | note | 1. Retain a manufacturer's test certificate for each Type per Supplier per Quarter.
f9cb1efb-1119-5de2-b1ad-4d4491350070 | note | 2. Record details and compare to minimum acceptable specifications.
05781f39-ec67-5de7-bc84-fc50e2d5c85d | note | Note: This form shall also be completed for a new supplier or new type prior to or upon delivery.
702cb4ed-d532-5a5a-ad51-d822662b5c93 | note | If non-conforming do the following:
a7271165-27d1-597e-866a-a332f57839bd | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form.
1cf49d8d-b7b8-5c38-9dbc-861adf8b9cfa | note | b. Identify unused fly ash/admixture on site, reject if outside minimum specification.
6bffb44a-bada-5079-97aa-db6798a223f0 | note | c. Notify supplier of non-conformance.
99798fab-44a4-5cb8-b01f-2b916397c979 | note | d. Examine test performance of completed products/cylinders to identify potential production defects.
98cab6b8-14d1-5f23-8a0b-f22f8b1c5fcb | date | QUARTER ENDING:
ad195689-c612-59f8-9494-f7c1a4c00bcc | tickbox | Or, new supplier or new type
75f4bd75-3319-521c-aff5-6bed3c665c75 | tickbox | Review / approval from Engineering Department
453e3c45-35d7-4a2a-b2b3-b35c994d1609 | section | PART 1 - FLY ASH
452f21c1-f41a-4829-85cd-38f700444d9b | checkpoint-no-value | Details
3f881ef3-2238-585b-8b53-b630ac52da42 | date | DATE
589442b2-82b4-5c4f-8109-921b5d9abb16 | textbox | SUPPLIER
3a90779e-4f37-553e-a5f1-29109a2c230b | textbox | DOCKET No.
e6d61c05-a98f-52e0-b167-bfc02e9a817a | textbox | CERTIFICATE No.
51753b7c-b318-5eb0-9cb3-83688fa58a10 | textbox | FLY ASH TYPE
5459f5ef-2b9d-4291-b107-666565113b90 | checkpoint | Remaining properties meet AS3582.1
8fda78bf-fa2e-4878-aa6c-99731038f914 | checkpoint | Meets Civilmart Poles Spec.
1501db86-a1fa-5124-a8c8-417338207b60 | note | Civilmart Poles Minimum Acceptable Specification:
34a455ce-601b-5bc1-a282-c2660de8e83b | note | Moisture 1% max, >75% passing 45μm sieve, loss on ignition <4%
fd9ea64b-957b-5f31-9ec9-7265067ad861 | note | Density and available alkali must be reported
a26c9a07-2a1e-5756-b3c2-23379c7178f8 | note | i.e. apart from these Civilmart Poles requirements, all other properties must meet AS 3582.1 Grade "Fine" (refer to fly ash certificate)
1daaec9d-a9ee-4260-b210-c4214b3fb90b | section | PART 2 - ADMIXTURES
4eafc774-32ed-42fa-8440-22c9f150ac92 | checkpoint-no-value | Details
901f3faf-e0e2-59db-a008-b49f9ae5f9b5 | note | Certificate of Analysis (CoA) to be obtain to provide records for investigative/comparison purposes. Refer to ITP for required frequency.
a80215e2-0cb5-597b-a708-fb1e0f08c03c | date | DATE
619053d0-12c7-58b0-b9fc-a739ad8920f1 | textbox | SUPPLIER
3fe35740-7ffd-55c9-8cc3-1fe469e55b3b | textbox | DOCKET No.
d4696dce-970f-5e1f-b249-e532ab72ce92 | textbox | CERTIFICATE No.
e180b7e6-4694-5290-a0aa-82f30abe793a | textbox | ADMIXTURE TYPE
2418440b-19ab-5b8c-ac50-f2ee925a356b | textbox | BRAND NAME
| checkpoint | INSPECTED BY
| signoff | Signoff
ae8a9049-ab04-468d-bfd2-6e5f2eaba12c | checklist | QA - 003 - Aggregates Visual Inspection V1 |  | QA - 003 - Aggregates Visual Inspection
deda7b58-f1fe-4d4f-9213-b3d6102d8f16 | section | Aggregates Visual Inspection
b42fa1da-6da7-49ad-9e4e-e76938046445 | checkpoint-no-value | Details
632a5159-0bc5-5046-9b05-59fd6447b4d2 | note | Procedure
0c908d0c-3af7-5457-ac2b-a47ecaa80c2f | note | Minimum Frequency - QEC - none except new supplier
14d60fd8-31d8-5dcd-9823-6185659b001c | note | Non-QEC - 1 Delivery / Week / Type / Supplier OR Where non-conformance is found from daily check.
cfc4550c-8c17-583a-b1b7-685709d10e8c | note | 1. Visually inspect all aggregates.
0e8b82a7-f6fd-56c8-9826-2e04913cf0a7 | note | 2. Maintain an agreed reference sample (from initial supply) for comparison with supplied aggregates.
40508e27-90b7-5c0c-b51b-213e894b3301 | note | 3. Record visual inspection details as follows:
4bfe655f-0264-5b2b-a786-c0aefd281c10 | note | C = Conforming. MV = Minor Variation. SD = Serious Deficiency
ba54afae-ad4d-5e5f-ac65-59b3c5433a33 | note | 4. Initial the ‘INSPECTED BY’ box.
9f524532-4138-5b28-a5e5-6d3e642d83a1 | note | Note: Fire ants check applicable in Queensland only.
50eacd85-1967-5541-aaba-400ae723596f | note | If non-conforming do the following:
ad179767-a984-513f-ab97-1f992eba4847 | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form – NCR shall be raised.
9ae82db5-7ce3-59db-86c9-bec11347d85d | note | b. If either visual inspection is SD isolate material (flag) and remove - investigate with supplier, then closely monitor supplies untilresolved, or
20266c9e-c598-5d95-9a48-6a4250397164 | note | c. If either visual inspection is MV consult with supplier, do additional testing to check degree of variation.
cc9d727d-15a3-5a88-8512-8ebc4fc370ca | date | DATE
7fdca3b1-b291-5b53-991f-ee1ee8577e7d | textbox | TIME
ce8a436d-3977-599c-915f-0128770a7252 | textbox | SUPPLIER
fa4fcea2-a445-515f-b693-557a49a3233a | textbox | AGG. SIZE
5acf4ff0-30a2-56fb-8e85-c59e9938f11c | button | VISUAL: SHAPE | C,MV,SD
6ef1a225-065a-51ec-963b-5c3e4883fbfd | button | VISUAL: FOREIGN MATTER | C,MV,SD
526a2106-16f8-47f1-9036-2a98cb4c2018 | checkpoint | FIRE ANTS CHECK
| checkpoint | INSPECTED BY
| signoff | Signoff
72e2e387-9c34-414d-a825-efb287d0e3a6 | checklist | QA - 007 - Reinforcement Inspection V3 |  | QA - 007 - Reinforcement Inspection
c9f353c1-8c5c-48ee-a6ae-912544dfcebf | section | REINFORCEMENT INSPECTION
02a747b2-cae7-4852-95f1-26b8533c1f96 | checkpoint | Details
cdabaad2-9dee-5934-84af-58906e8ecc11 | note | Procedure
714e480b-7ce5-5aa3-8645-578924b70f29 | note | Minimum Frequency - EACH DELIVERY
035d4dd0-490f-5af9-8a25-ccdcdf809b7c | note | 1. Check 1 in 50 (min 1 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
733cf5af-aa07-58ea-ac08-8587038b2c24 | note | 2. Visually inspect wire and record details below as follows
0ce52aa0-d407-5d49-8d11-d04f421b1b89 | note | C = Conforming MD = Minor Deficiency SD = Serious Deficiency
8cbe266a-7e15-5083-88a3-c0f45beaa2f4 | note | 4. Inspect all reinforcement in the delivery to ensure it is compliant with specified on site mass limits
2a5aca1d-96b5-5cba-a9a2-b7d4330b051e | note | (i.e., Wodonga mass limit = 1900kg) and record details below as follows C = Conforming NC = Non-conforming.
6bdb8c1c-a8a5-596e-ab39-53f8903fb876 | note | 5. Initial PASS or FAIL box, THEN:
77ad0736-701b-5ada-9c66-5b85a6324bf9 | note | Minimum Frequency - ANUALLY
05e20a57-1bcf-5850-b5fe-0421cc93b13f | note | 6. Obtain 3 of NATA Test Certificates from Manufacturers indicating breaking stress values for Annual UTS results. Average results and record
e03c8bcf-7e4e-5ffb-b3b9-7d8011bf3fc8 | note | If non-conforming do the following:
3b5a8ba8-9bbe-5954-83eb-ebbaabe44396 | note | a. If visual inspection has SD or continuing MD then:
d3a9c5ae-3627-5849-9fc4-f4418d94b0a6 | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
e33b35fa-91d7-5f79-bbd6-38895f6c67db | note | — Quarantine coil and follow up with supplier.
75a236dd-aff8-57d5-a33b-74706a0b0140 | note | b. If mass limit is NC then:
0dd2ea62-eaf5-51b1-b40a-302ccda2cf77 | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
2c795287-c8ab-5e64-bcdd-ca612be08ccc | note | c. If UTS result outside AS4671-2019 or AS4672-2007
97a38725-cc42-5ab2-874b-6a72001f2a5b | note | — Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
7943049e-426f-5ee2-a40d-436a279db79b | note | — Reject further coils and follow up with supplier.
1064e8e8-8de1-5373-94d0-5206908e168e | note | — Follow up on representative final product testing.
b03c87dd-62ac-5bc0-b0d3-77a5969a7789 | dropdown | Reinforcement Size | 5.55,7.02,9.88,12.33,15FWB,20FWB,N20,N24,12.7 STRAND,9.5 STRAND
d689ce7d-b453-5989-8bc1-78f4c00c17ad | textbox | Delivery Docket No.
e2d46c35-d335-551a-a921-cb79db216756 | textbox | Coil/Batch No.
f71de0df-dc9b-519e-8f8f-6474513557e0 | date | DATE: Delivered
fcb3a7b3-29ac-54ce-a897-36fe5795af84 | date | DATE: Inspected or Tested
37ea6b65-2b31-5661-b0d0-575d8bbeb6c1 | button | Visual inspections: Dimensions | C,MD,SD
f676edf1-e55f-5ef2-bf2a-205acbc2c8f4 | button | Visual inspections: Rust | C,MD,SD
e74f4520-88d7-5ec4-8d1b-548bbc2d4bbb | button | Visual inspections: Surface oil | C,MD,SD
7dc538d9-087c-5933-abd5-5df9cffbd3f5 | button | Compliant with specified on site mass limits? | CONFORMING,NON-CONFORMING
| checkpoint | INSPECTED BY
| signoff | Signoff
721b5495-8500-4c93-a675-93d07fa38110 | checklist | QA - 008 - Fabricated Reinforcement Inspection V1 |  | QA - 008 - Fabricated Reinforcement Inspection
5a21347d-cd45-4b06-be08-8d57d7261442 | section | Fabricated Reinforcement Inspection
0ede2eb3-9945-483a-9a35-461f658f48d3 | checkpoint | Details
cf38403a-0ad7-5f97-8264-64759ff20147 | note | Procedure
ad2fadf1-002b-5f38-89d9-40ff71d83769 | note | Minimum Frequency - EACH DELIVERY
2b78f3a9-85ef-5792-b11d-42218f2b7a35 | note | 1. Review delivery docket to confirm quantity and other specific information.
5cd1af35-2e56-5213-9584-3b716b8a899c | note | 2. Check each delivery conforms to the relevant drawing or specific requirements including relevant AS (i.e., AS 4671, AS 3679, AS 4291 etc).
64314b32-8f75-5693-a65a-3b6c3e2f3b2e | note | 3. Check at rate of 1 in 50 (min 2 per type, per delivery) or 1 in 200 (min 1 per type, per delivery) if supplier is a Quality Endorsed Company.
e1aa1da1-5e67-5c93-b7d1-6ab76743ece4 | note | 4. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended).
6b494e34-337f-5fdf-966d-34fde8c33bcc | note | If non-conforming do the following:
9e64dddf-84fc-50df-b54f-ee3bd6a952a2 | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
dfd7abf9-1991-5828-a175-65e916ee13df | note | b. Check a further 2 items (in the sample size).
d0932050-6f28-5679-a127-262b0a2dc131 | note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
23e74b30-ff88-5e57-be70-08cdd0a6f4e5 | note | d. Isolate and identify all defective reinforcing or batches of reinforcing.
57744ff4-0122-5899-abc9-e9645577f8f6 | textbox | ITEM DESCRIPTION
824ccc59-a090-559e-a149-54db0ef37381 | textbox | SUPPLIER
0c737b63-1783-59c4-8f40-d127d59bcfdb | button | Supplier QEC | Yes,No
948f6b86-205c-52b8-ba3c-9222b3b523f2 | note | DELIVERY DETAILS
619e7aa5-de0c-531f-a33d-23663cc75459 | textbox | Delivery Docket No.
ae6e1964-27e9-5516-8162-577e5e4a5945 | date | Date Received
69f88f9c-cbb2-5032-865d-c15c839f6b86 | textbox | Quantity Received
d6c01785-0665-5451-87a9-93d66bbc6554 | textbox | Sample Size
e265a04e-44d2-5c58-a4b7-61f93830a99b | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
| checkpoint | INSPECTED BY
| signoff | Signoff
640b5e42-d654-43ef-b2d6-7b0dc78b5704 | checklist | QA - 009 - Fittings Inspection V1 |  | QA - 009 - Fittings Inspection
4283c580-b43f-42b4-985d-47cecc69a0a7 | section | Fittings Inspection
8c0b3e2c-5a46-47b6-8bd8-4e6cfda076fd | checkpoint | Details
31cc0cdb-2d29-58e3-855d-6acd6ffff43d | note | Procedure
1dc354e4-9d29-5ae7-bebc-9371b5a4ea28 | note | Minimum Frequency - EACH DELIVERY
be1e8c5d-1cc7-5124-afa5-a889d33bde49 | note | 1. Check fittings: Mass produced (extruded, cast, machine fabricated) at the rate of 2 per container of same items, or if the supplier is a Quality Endorsed Company (QEC) as recorded on the approved suppliers list, a minimum inspection of 2 items per delivery.
475cfd8c-d5f9-52e9-a1c1-f113e67f4f5a | note | 2. Note whether the supplier is a Quality Endorsed Company.
fdad35a6-3232-55b4-8415-b00800115195 | note | 3. Check all critical dimensions and features as specified. (Visual comparison to existing sample is recommended)
78ea4562-1853-53a0-b9c3-e6545a884d42 | note | If non-conforming do the following:
bb5dc947-5938-5f30-b543-f4e9e2ffa73d | note | a. Advise the designated quality coordinator of non-conformance and provide them with a copy of this form. – NCR shall be raised.
0e5aef8b-9637-5c74-a0cf-405ea9f2832b | note | b. Check a further 2 items (in the sample size).
ddab41bb-b85e-5157-874e-b75f0718d0fe | note | c. If any of these samples do not conform reject the delivery - or test 100% and accept all satisfactory items.
1ab82ef2-dd98-56d9-b989-529d68633595 | note | d. Isolate and identify all defective fittings or batches of fittings.
9ba5127a-6ec8-5bad-b023-6fddfdf2a53b | textbox | ITEM DESCRIPTION
70967962-cfa6-5104-8ab6-d62f82cdb059 | textbox | SUPPLIER
e4373743-ad0c-57f3-b4dd-e076fced9cfc | button | Supplier QEC | Yes,No
09a05859-555a-5571-9fef-ba90ce7553df | note | DELIVERY DETAILS
67433f20-4103-5461-a555-4d310c54ecb9 | textbox | Delivery Docket No.
12dd4c80-6d2f-537a-9a2f-385e3a1e468f | date | Date Received
66dfa29b-cee1-51aa-b243-964e9422ab02 | textbox | Quantity Received
795baee1-cd2e-57b6-a93a-ca274b414532 | textbox | Sample Size
0a4538ff-41fc-5209-bf03-39f2a39a9026 | textbox | RELEVANT DRAWING OR SPECIFICATION (or sample)
| checkpoint | INSPECTED BY
| signoff | Signoff
bcabbb4c-79f6-4e6d-9052-cec0b38dc7b3 | checklist | QA - 016 - Assembled Product Inspection V1 |  | QA - 016 - Assembled Product Inspection
f3ad3f8b-9349-4870-89c8-1e1fd402143e | section | Assembled Product Inspection
e1d96f70-8bf7-48d2-9825-234d25f30f15 | checkpoint | CHECKED
9a685ce2-0942-585a-9de0-4f9f4b758085 | textbox | CAGE SIZE / TYPE
182d87b5-35a0-5c9d-9c0a-8dc5f51806f4 | textbox | CAGE TAG #
4e8bc008-7ff2-51a1-ae7e-ce171bc5f1ed | textbox | MOULD #
c52ba43f-faa5-5014-b1b6-aec39f6475e5 | textbox | DRAWING #
d5193a18-1fc6-5adc-b120-8c8759e3dc60 | textbox | REVISION NUMBER
b4ca4392-2ed2-5a1f-a533-5ecf9ca0a63a | textbox | # STUDS / TIP FERRULES
7ad9404c-bb0a-5c99-a68d-5bf9293d562c | button | ANTI-ACCESS BARS | Yes,No
83d4a479-77b4-5049-9f38-b47c7252f400 | textbox | # LUGS / BUTT-EARTHS
4cd93123-e9d0-52ed-a85d-3d6ed31c5194 | textbox | # STRANDS
0a365049-1cca-5047-8b23-d5b66b2f68e3 | button | CHECK FOR CROSSED STRANDS | Yes,No
370e7c70-4c54-5e86-931a-1664135aa842 | button | ALL JOINT BARS WELDED | Yes,No
865185c2-323d-5d02-aa72-eb7a78493ab9 | button | STUD/LUG AS PER DESIGN | Yes,No
a8797400-13dc-524c-bad2-6a92a58f2cb6 | button | JOINT RING | Yes,No
43545a93-f399-5749-8ae2-1f9411fc647a | button | LIFT TUBES CHECKED | Yes,No
950d29ca-b09f-5ede-b393-59e1a39e6ce8 | button | SEEMS SCRAPED | Yes,No
8c0fa1d7-f424-55d0-830d-0e32f5dac415 | button | MOULD OILED | Yes,No
d04c8780-b406-5592-9e6c-343d0e6427ec | button | PLATES OILED | Yes,No
38902269-42ac-5d5f-ad18-00298bd247b3 | button | BARREL/WEDGES SEATED | Yes,No
ac27c6ec-7d35-5ed1-bfe1-94d1ed3157bd | button | CLEARANCE CHECK | Yes,No
64eb4fd7-6052-5835-9792-9a9750f622aa | textbox | COIL # ON PACKAGE
5b0934da-78fe-4fec-a37d-dcdaa03263cb | checkpoint | PRODUCT ACCEPTED
| checkpoint | INSPECTED BY
| signoff | Signoff
c7061147-b18c-45f0-beed-98f6805f93b9 | checklist | QA - 028 - Load Visual Inspection V1 |  | QA - 028 - Load Visual Inspection
1d0d6bcd-16b8-49bb-82ae-b68ba2fc9d82 | section | Load Visual Inspection
d1930446-13bb-421a-946e-9e3a07238aaa | checkpoint | Load
7a1c1ce2-5d76-51c2-8b94-5653ef21cda4 | note | Procedure
95debc8e-64b3-5a37-a220-c1c9dbd57885 | note | Minimum Frequency - 1(i) LOAD / WEEK
e5adfd5f-60e2-582c-b5fc-be1b4de632da | note | 1. Observe the loading of product to ensure compliance with established procedures and relevant Work Instructions.
c5dbcbfc-2586-5239-8ab6-5c606993982b | note | 2. Observe load for product damage (compared with conveniently located, correctly branded product sample of customer / specification)
0b19f323-60fa-5ab4-bbe0-6a6723b9d4fe | note | 3. Check load for all items against the details on the loading slip. Confirm that correct products and quantity are present.
7e235426-11bd-58fb-a193-ea0c3bbfa2d2 | note | 4. Confirm Quality Checks & Chain of Responsibility Checks (CoR) are completed by the loader.
0d910843-30d4-5642-84a4-62220ba14a35 | note | 5. Record all observations.
504c44d2-b9a4-5b62-aa95-60f504ca18b0 | note | Notes:
8784115b-975c-5644-8801-903702350854 | note | (i) Increased frequency may be required where high output occurs or non-conformance has occurred.
031451ab-f4ac-5fc6-b209-a60ea3a3f8a1 | note | (ii) Fire Ants check applicable in Queensland only.
8eea6e1e-401e-5733-96a5-947aba26c1ed | note | (iii) Deviation from established procedure is regarded as non-conformance.
14ef1ee3-3457-5715-854f-d7e8d0230743 | date | Date
233a77c9-4c5b-5a03-987f-f337b4a64bbc | textbox | Carrier
ff39f8ad-d7d0-5f25-8511-f01c25bf040e | textbox | Client
e35da9cc-c366-5cb6-99b2-49b1b06e4111 | textbox | Loading Docket No.
0c330066-5977-5a9b-b715-46cf76daae83 | textbox | Loaded by (Loader & Dogman Initials)
0d0c83c2-65e2-4514-9a0b-5575a81ed669 | checkpoint | Observation:
8631e487-1aa6-59c8-ae42-43fb94a6b890 | button | Exclusion zone established? | Yes,No
608529b2-67a1-541d-9e99-72855ebd57a2 | button | Platform ladders in place and used? | Yes,No
7ad0069d-4971-5722-adf9-fca340cbeb46 | button | Work crew wearing all required PPE? | Yes,No
bd4aebd8-5aa9-50d8-992d-be2a3fcf166c | button | Lifting equipment positively attached? | Yes,No
8c9b91ec-c1cf-5930-a1af-47e3fb47daab | button | Tagline used at all times? | Yes,No
6111e7fb-0698-5695-b2f5-84f8f0e5e3a6 | button | Lifting and shifting completed as per SOP? | Yes,No
1ca27a87-3077-5cd5-936c-20d8bbd8e499 | button | Any unsafe practices or deviations observed? | Yes,No
3f183ac0-7ae8-5149-aa51-52ac377e4d77 | button | Quality Checks completed by the loader? | Yes,No
f98ea210-3af8-55c9-be1d-ebd2aaaa686f | button | Chain of Responsibility Checks (CoR) completed? | Yes,No
bec2e18c-f687-5cc6-856f-4e8419893453 | button | Any product damage identified? | Yes,No
014fda89-7d71-5a21-a523-fe5db903eee6 | button | Products, items, and quantity, correct? | Yes,No
2ecb94b0-9791-42d5-b2dd-0fc7e3ca7cf7 | checkpoint | Fire Ants Check (QLD only)
| checkpoint | INSPECTED BY
| signoff | Signoff
e09b7aa8-9794-42bc-8afb-f6cb895dfff0 | checklist | QA - 060 - First Up Product Mould Inspection V1 |  | QA - 060 - First Up Product Mould Inspection
cfef7878-6269-40ee-acea-d0d19a37843d | section | First Up Product Mould Inspection
e99663d6-8e28-4095-8e1a-ad5bd880b0c6 | checkpoint-no-value | Details
2cbe521f-510f-5ca2-be8b-52de15b258be | date | Date:
5adfecdb-8871-50a8-8db1-dd36b7368dfc | textbox | Worker Completing Mould Inspection:
e54b58a3-3499-56ff-9100-9d1812645177 | textbox | Pole Type / Size:
97795e48-9950-57c7-8aff-b4ac473148a8 | textbox | Mould No.:
9371148b-a3de-5e7a-bac3-22d48c285692 | tickbox | New Mould
1cf3bf27-d07a-5098-867d-703f90e58fb5 | tickbox | Mould from repair
c78fcf9e-80ab-5911-ba68-b428d8c5af8c | tickbox | Mould From Storage
332392d3-0301-4027-92a4-dd2cab72fcd0 | section | DIMENSIONAL CHECKS
28f8ff42-c18d-482b-8602-5e43a7cd0d69 | checkpoint | Tip Diameter
a28cfaf8-6be9-5f67-b98b-17c73551543c | textbox | DESIGN
db202ee6-90b0-5397-ab87-5eb672dd070c | textbox | ACTUAL
4c263ec5-9b86-51ef-92f9-56a5cb0eede0 | note | TOLERANCE
1f232032-f0fb-53aa-93ec-3297b39cffa3 | note | POLES: ± 2 mm
da10dca6-3853-5a58-83c7-9b6f4ec1ef36 | note | PILES: + 10 mm, - 5 mm
7a634c83-a21d-4c6c-bf33-505a5e8368a1 | checkpoint | Butt Diameter
d81622f5-1468-5c4f-9953-2423a9508d26 | textbox | DESIGN
e0545981-ce28-5dcc-ae30-8dce649ed63f | textbox | ACTUAL
609d34d5-f53f-5843-a666-dde26294732f | note | TOLERANCE
c34a9a84-9284-5ec6-83c3-3fe56ac30044 | note | POLES: ± 2 mm
60129f9c-04ec-52b7-a879-943092c7f843 | note | PILES: + 10 mm, - 5 mm
aa808996-6eb2-446e-a8a6-8a77c6f2bee3 | checkpoint | Distance from butt to depth marker
b9eb723c-4d19-5f0f-b711-42bfa6a4ab61 | textbox | DESIGN
12dc2024-8d5a-5835-84aa-5cde4910b751 | textbox | ACTUAL
a9ddef7f-64fa-5507-9fe3-3ffabd8aa979 | note | TOLERANCE
9222f48c-d3b3-534a-939b-f085eb0f7f29 | note | POLES: ± 100mm
67efc7c8-10af-5561-acc5-4cde5cbf14fd | note | PILES: N/A
dcd8eed2-db1f-4dcb-b885-cb6e3190a1c8 | checkpoint | Distance from butt to Name plate location
39849a31-78e9-5270-964f-0381bb029927 | textbox | DESIGN
6c4dbc76-c4be-5087-a118-3440fa3829aa | textbox | ACTUAL
28811510-147f-5aed-90d9-c97f215db7b1 | note | TOLERANCE
a0fc47ca-6edf-5977-acf5-e4f11ee43e9d | note | POLES: ± 100mm (Unless interference occurs)
aa23a87b-69b4-5e88-a421-82935737b630 | note | PILES: N/A
d6efb28a-1ec1-403c-bf19-9010ebf5c8cb | checkpoint | Specified Product Length
5239450d-39e4-5416-9b91-c83267de7ae5 | textbox | DESIGN
53edb291-f399-5f85-a1e6-1a3287299936 | textbox | ACTUAL
83f649ec-48b9-5e89-af7e-d987dff7de62 | note | TOLERANCE
ed4670be-fb79-5540-9cb8-5cc67aecab38 | note | POLES: ± 50mm Poles
e1ca172a-6a7e-5bf1-bf56-01c33816b708 | note | PILES: + 50mm, - 0mm
40d42edc-8b00-4044-ab0a-ca6db2ab9166 | section | MOULD CHECKS
f829e5c4-276d-459c-9938-fc14dc1f9e57 | checkpoint | Does the mould have all locating pins
98e13503-4498-46c0-9939-1d426912bd45 | checkpoint | Has the mould been clean thoroughly including weld spatter?
314528ae-1a9b-49f3-92d0-7d08042c6494 | checkpoint | Have all unused locating holes been filled
b88511fe-4481-443d-bb88-2fa0608582af | checkpoint | Have the seams been scraped
42043672-2e06-4b1b-b4ff-82aff3fc245d | checkpoint | Are there any cracks in the mould
83e4bd08-ee09-4eda-b738-4a142ede6a60 | checkpoint | Have running rings been secured correctly?
2ad2b5c6-e1fc-48b5-9456-7cb2dbb40e28 | checkpoint | Have mould sections been sealed with silicone and secured correctly?
9181338a-b4de-4f18-960c-0e75dcae2ff5 | section | FINISHED PRODUCT VISUAL CHECKS
7c723feb-1e3a-4970-aeae-54fd32b45d74 | checkpoint-no-value | Details
92fb1df2-9ba1-521e-9c20-3f24a55904a9 | date | Date:
5a3d73d2-3a18-5321-b4b7-c66883d889bc | textbox | Product No.:
4f5ef9c3-bc85-4ad9-b43b-400847890d5d | checkpoint | IS THE FOLLOWING NOTICEABLE?
4e2d5b39-3767-5b6b-a748-a2342c516220 | note | BULGES, INDENTS, HOLES, SEEM BLEEDS, RUST MARKS, DIRT MARKS, FOREIGN MATTER OR SILICONE
| checkpoint | INSPECTED BY
| signoff | Signoff