## ITP Summary
Project | 2025-21 Lake Innes House - Built by CC | Values | Check list | Options
checklist-sectioned | Precast Components ITP
section | Job Aproval Documents/Construction Documents
checkpoint | Received Construction drawings from Client |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "For Construction" |  | Pass/Fail/NA | attachments/photos/comments
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | FormWork |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Items and their placement correct (ferrules, lifters, grout tubes etc). |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lift Procedure |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concreting (mix design N40) |  | Pass/Fail/NA | attachments/photos/comments
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Test Schedule and Test Results |  | Pass/Fail/NA | attachments/photos/comments
section | Transport
Sub section 01 | Transport 01
| Any Lifting,Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/comments
| Transport Vehicle Approvals (registration, transit insurance for goods) |  | Pass/Fail/NA | attachments/photos/comments
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/comments
Sub section 02 | Transport 02
| Any Lifting,Loading, TransportInstructions from Client |  | Pass/Fail/NA | attachments/photos/comments
| Transport Vehicle Approvals (registration, transit insurance for goods) |  | Pass/Fail/NA | attachments/photos/comments
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/comments
Sub section 03 | Transport 03
| Any Lifting,Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/comments
| Transport Vehicle Approvals (registration, transit insurance for goods) |  | Pass/Fail/NA | attachments/photos/comments
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/comments
Sub section 04 | Transport 04
| Any Lifting,Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/comments
| Transport Vehicle Approvals (registration, transit insurance for goods) |  | Pass/Fail/NA | attachments/photos/comments
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/comments
Sub section 05 | Transport 05
| Any Lifting,Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/comments
| Transport Vehicle Approvals (registration, transit insurance for goods) |  | Pass/Fail/NA | attachments/photos/comments
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/comments
section | Other Documentations
checkpoint | Special Instructions |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Other |  | Pass/Fail/NA | attachments/photos/comments
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete. |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | All personnel site inducted
checkpoint | SWMS on hand, all personnel signed onto SWMS
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location |  | Pass/Fail/NA | attachments/photos/comments | Repeating items
tickbox | Set out |  | Pass/Fail/NA | attachments/photos/comments
tickbox | Core Holes |  | Pass/Fail/NA | attachments/photos/comments
tickbox | Dowels |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings. |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Grouting and sealing |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | Remove backpropping when instructed by consulting Engineers. |  | Pass/Fail/NA | attachments/photos/comments
section | Final Inspection |  | Pass/Fail/NA | attachments/photos/comments
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  | Pass/Fail/NA | attachments/photos/comments

## Panels
2025-21 Lake Innes House - Built by CC
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/comments
checkpoint | Availability of updated lift plan drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Availability of updated panel dimensions drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Availability of updated reinforcing steel drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation Checked | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item - Lifters Correct - Position, Size, Orientation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover check (40mm) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check (150mm) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel length check, allignment check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Void(s) for windows - dimensional and location check completed (if applicable) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Recesses checked as per drawings | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Grout Tubes / dowels firmly fixed & alligned - Check
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo(s) Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist
section | Job Aproval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item - Lifters - as per lift drawing - Position,Size,Orientation - NS / FS | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Items - as per drawings - Ferrules - Position,Size,Orientation - NS / FS | Pass/Fail/NA | attachments/photos/comments
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check - Panel Dimensions (length, width, thickness) & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents - bond breaker or wax | Pass/Fail/NA | attachments/photos/comments
checkpoint | Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould,Supports,Ties | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Drawing(s) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Dowels / Grout Tubes Fixed Firm & alligned - Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - (min cover 40mm) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Recesses checked as per drawings | Pass/Fail/NA | attachments/photos/comments
checkpoint | Void(s) for windows - dimensional check and location check completed (if applicable) | Pass/Fail/NA | attachments/photos/comments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations %, adjustments %,mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirements to do Concreting - DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/comments
section | Other Arrangements
checkpoint | Concrete surface finish (good all faces) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
Repeating items
P1
P2
P3
P4
P5
P6
P7
P8
P9
P10

## Instaler CheckList PL Panels (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - Pinhead Lifter Galvanised 5Ton x 180mm (LA05180) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 0
dropdown |  | 4
dropdown |  | 6
dropdown |  | 7
dropdown |  | 8
dropdown |  | 9
dropdown |  | other
checkpoint | Embeded Item - Ferrules -M16x96 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 2
dropdown |  | 6
dropdown |  | 8
dropdown |  | 9
dropdown |  | 10
dropdown |  | 12
dropdown |  | other
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (top min cov30mm, Bottom Min Cov 25mm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (Fine Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | SP1
SP2
SP3
SP4
SP5
SP6
SP7
SP8
SP9
SP10
SP11
SP12
SP13
SP14

## Instaler CheckList ST(steps) (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Constrction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item -Lifters -XXXXXX - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules -M12x50 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (min cov XXmm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (BROOM\SPONGE Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | STD1-1
STD1-2
STD1-3
STD1-4
STD1-5
STD1-6
STD1-7
STD1-8
STD1-9
STD1-10
STD1-11

## Sheet1 (hidden)
Repeating items | SP1 | STD1-1
| SP2 | STD1-2
| SP3 | STD1-3
| SP4 | STD1-4
| SP5 | STD1-5
| SP6 | STD1-6
| SP7 | STD1-7
| SP8 | STD1-8
| SP9 | STD1-9
| SP10 | STD1-10
| SP11 | STD1-11
SP12
SP13
SP14

## Sheet2 (hidden)
Repeating items |  | Ferrule (M16x96) | Holes | Thk | Length (Max) | Width (Max) | Weight | Volume | Con .Grade | Min:Cover (Top) | Min:Cover (Bot) | Test Freeq: | Con Grade
| SP1 | 2 | 8 | 200 | 1580 | 5695 | 4.26 | 1.72 | S32 | 30 | 25 | 1 test- 3 cylinders- 7days & 28days | 40
| SP2 | 10 | 8 | 200 | 1100 | 5979 | 3.96 | 1.6 | S32 | 30 | 25
| SP3 | 10 | 9 | 200 | 1100 | 6263 | 4.16 | 1.68 | S32 | 30 | 25
| SP4 | 12 | 0 | 200 | 890 | 6480 | 2.8 | 1.13 | S32 | 30 | 25
| SP5 | 2 | 4 | 200 | 1100 | 2909 | 1.88 | 0.76 | S32 | 30 | 25
| SP6 | 6 | 7 | 200 | 1580 | 5226 | 3.53 | 1.42 | S32 | 30 | 25
| SP7 | 9 | 8 | 200 | 1100 | 5793 | 3.74 | 1.51 | S32 | 30 | 25
| SP8 | 10 | 9 | 200 | 1100 | 6361 | 4.13 | 1.66 | S32 | 30 | 25
| SP9 | 12 | 0 | 200 | 890 | 6796 | 2.89 | 1.16 | S32 | 30 | 25
| SP10 | 2 | 6 | 200 | 1100 | 4311 | 2.83 | 1.14 | S32 | 30 | 25
| SP11 | 8 | 6 | 200 | 1100 | 4595 | 3.02 | 1.22 | S32 | 30 | 25
| SP12 | 9 | 7 | 200 | 1100 | 4878 | 3.21 | 1.3 | S32 | 30 | 25
| SP13 | 9 | 7 | 200 | 1100 | 5162 | 3.41 | 1.38 | S32 | 30 | 25
| SP14 | 10 | 0 | 200 | 890 | 5380 | 2.31 | 0.93 | S32 | 30 | 25
| STD1-1 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-2 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-3 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-4 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-5 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-6 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-7 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-8 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-9 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-10 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
| STD1-11 | 2 |  |  | 1200 |  |  |  | S32 | 30 | 25
xx
xx
SLUMP AT TIME OF POURING TO BE WITHIN THE PERMISSIBLE TOLERANCE IN AS1379-2007 FOR NOMINAL
SLUMP SPECIFIED.
- AT LEAST 1 SAMPLE FOR EVERY 50m³ SHALL BE TAKEN AT THE SITE, BUT NOT LESS THAN 3 SAMPLES
SHALL BE TAKEN PER POUR. FIRST AND LAST BATCH PER DAY TO BE SAMPLED, THE OTHER TAKEN
PROGRESSIVELY DURING THE POUR, RECORDING LOCATION IN POUR WHERE SAMPLE WAS TAKEN.
- IT IS PERMISSIBLE TO REDUCE THE NUMBER OF SAMPLES TO 2 FOR POURS OF LESS THAN 30m³, AND 1
FOR POURS OF LESS THAN 10m³, SAMPLE CONSISTS OF AT LEAST 3 CYLINDERS. ONE CYLINDER SHALL BE
TESTED AT 7 DAYS. TWO CYLINDERS SHALL BE TESTED AT 28 DAYS. 7 & 28 DAY TEST RESULTS TO BE
SENT IMMEDIATELY TO NORTHROP CONSULTING ENGINEERS.
PC12. COLOUR AND FINISH SAMPLES OF PRECAST ELEMENTS SHALL BE SUBMITTED TO THE ARCHITECT FOR
APPROVAL BEFORE ELEMENTS ARE CAST.
Pinhead Lifters
Plastic Solutions Australia
https://www.psa.com.au › psa-products › pinhead-lifters
LA05180. Description: *Capacity x length (L) 5 Series Pinhead Lifter Galvanised x 180mm. Box30. CodeLA05240. Description: *Capacity x length (L) 5 Series ..
Pinhead Lifter Galvanised 5Ton x 180mm (LA05180)

## old doc (hidden)
BP-01 | Bridge Plank | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Testing
section | Transport
Checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
|  |  |  | 0.8 | 0.6 | 0.1 | 0.048 | 0.1152
checklist | Checkers Checklist
checkpoint | Overall Measurements | [5 empty] | 0.804 | 1.9296
checkpoint | Void Correct Position
checkpoint | Ferrules - Measurements & Size - NS / FS
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown |  | 150mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Eye Anchor - 2.5T | 4
textbox | Ferrules - M20 x 96mm | 10
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Broom
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?