## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Aproval Documents/Construction Documents
checkpoint | Received Construction drawings from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | FormWork
checkpoint | Reinforcement (Reo)
checkpoint | Embedded Items and their placement correct (ferrules, lifters, grout tubes etc).
checkpoint | Embedded Item - Wall Brace, Floor Brace and Strongback Inserts installed as per the drawings if required
checkpoint | Lift Procedure
checkpoint | Concreting (mix design N40)
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client
checkpoint | Test Schedule and Test Results
section | Transport 01
checkpoint | Any Lifting,Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals (registration, transit insurance for goods)
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting,Loading, TransportInstructions from Client
checkpoint | Transport Vehicle Approvals (registration, transit insurance for goods)
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 03
checkpoint | Any Lifting,Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals (registration, transit insurance for goods)
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 04
checkpoint | Any Lifting,Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals (registration, transit insurance for goods)
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 05
checkpoint | Any Lifting,Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals (registration, transit insurance for goods)
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint | Special Instructions
checkpoint | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint-no-status | All personnel site inducted
checkpoint-no-status | SWMS on hand, all personnel signed onto SWMS
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
tickbox | Set out
tickbox | Core Holes
tickbox | Dowels
checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove backpropping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
section | Details
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated lift plan drawing
checkpoint | Availability of updated panel dimensions drawing
checkpoint | Availability of updated reinforcing steel drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation Checked
checkpoint | Embedded Item - Lifters Correct - Position, Size, Orientation
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Embedded Item - Wall Brace, Floor Brace and Strongback Inserts installed as per the drawings if required
checkpoint | Concrete cover check (40mm)
checkpoint | Panel Thickness check,allignment check (150mm)
checkpoint | Panel length check, allignment check
checkpoint | Void(s) for windows - dimensional and location check completed (if applicable)
checkpoint | Recesses checked as per drawings
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint-no-status | Grout Tubes / dowels firmly fixed & alligned - Check
checkpoint | Curing Procedure arranged
checkpoint | Photo(s) Taken
checklist | Installers Checklist
section | Job Aproval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item - Lifters - as per lift drawing - Position,Size,Orientation - NS / FS
checkpoint | Embedded Items - as per drawings - Ferrules - Position,Size,Orientation - NS / FS
checkpoint-no-status | ID Plate
section | Pre-Pour Check Approvals
checkpoint | Formwork Check - Panel Dimensions (length, width, thickness) & DOUBLE CHECK
checkpoint | Apply Debonding agents - bond breaker or wax
checkpoint | Fix ID Plate to Formwork
checkpoint | Use Required Mould,Supports,Ties
checkpoint | Reinforcement Check - Reo as-per Drawing(s)
checkpoint | Lifters, Ferrules, Dowels / Grout Tubes Fixed Firm & alligned - Check
checkpoint | Embedded Item - Wall Brace, Floor Brace and Strongback Inserts installed as per the drawings if required
checkpoint | Concrete cover Check - (min cover 40mm)
checkpoint | Recesses checked as per drawings
checkpoint | Void(s) for windows - dimensional check and location check completed (if applicable)
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations %, adjustments %,mix time
checkpoint | QA - All main & other requirements to do Concreting - DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface finish (good all faces)
checkpoint | Curing Procedure arranged