## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
63e54f5b-282c-4af6-aecf-876e5c12c379 | checklist | QA 8_Below Ground Pipework Checklist - Sewer - NMH |  | Below Ground Pipework Checklist - Sewer
91bcd7ac-18ab-4180-b87f-58ddea93fc34 | section | Details
ebfc9db2-a6a1-4f7d-b589-14c64700266f | checkpoint | LendLease Permits Issued
9f4630ac-f1a2-4601-bdfd-b2f01ee4f19b | checkpoint | Set out pits depths and trench runs.
5e98f1b0-8b66-5eec-b278-6e2be52e762d | note | As per DRG#
73b36896-6cb2-50c5-8adc-893cd50612ad | textbox | Drawing No.:
2a9cdea1-8703-40dd-8510-fbe283cc69d7 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
bdd6b96d-73f5-5832-974d-4f81061a60bc | note | Spec#: AS3500
c3c27ccc-fe26-5b00-894d-4b3758379289 | textbox | Material used
e391c9b6-194a-425f-8acc-7ee75ac58edc | checkpoint | Bedding placement and compaction and material meets specification.
40051253-be0c-572d-8853-82346b1b5076 | note | Spec#: AS3500 and Hydraulic Specification
db9241d5-83d0-4c3f-a31a-d30ff73a41ee | checkpoint | Laying and jointing of pipes R.Ls and falls
5c2ec4cc-071c-5af3-95d4-2503e6f647f8 | note | AS3500
299b4869-2488-5b37-9f51-f823430f580e | note | RLs as per hyd drgs
af7f5841-0f53-42d2-aa94-9660a2ff194a | checkpoint | Connections to pits and existing services
937f0538-6438-458d-9866-2a30840640a7 | checkpoint | Hydrostatic tests are carried out as required.
3ac827b6-11f4-58b5-ad6c-bd40730197bb | button | Air or Water? | Water,Air
4279fd4e-8d50-5ad9-a835-fe2b17b0e768 | note | Inspected and recorded by Independent Certifier or PIC (See attached)
eb7b06ef-f1f7-4394-b54a-dcba673c26ac | checkpoint | Mirror tests are completed if required.
2c087100-f618-4c56-9d1f-c9d75b1a4f18 | checkpoint | Placement and compaction of backfill and material meets spec.
630d9e6c-9aa8-4488-8246-d77e174f26b2 | checkpoint | Temporary cover provided to open drain.
ae0c0310-ea1c-41bb-ae98-e4c17ff01cff | checkpoint | PVC/ Plastic caps to open ends
ad0cafdf-36c5-4406-be47-0322b8ca4636 | checkpoint | As built information updated onto drawings
c03dba40-4097-5e4c-a633-10ed5f6eae6e | note | Ongoing
b7c235d7-a332-582e-be3a-2a41809c7490 | note | To be provided
9bdd10e3-9d29-486d-befc-704efd0c8ba1 | checkpoint | Sign Off
876148c5-f961-58b0-9514-53fa5decab58 | button | Geschke Group Signature added below | Yes,No,N/A
44df2575-9ed7-52c1-aa52-f48beb40d559 | button | LendLease Signature added below | Yes,No,N/A
10105dbd-f030-52cf-9783-3d34fcc9d941 | button | ARUP Group Signature added below | Yes,No,N/A