## NMH Project Template
Type | Name | Values | Prompting Name
checklist | QA 8_Below Ground Pipework Checklist - Sewer - NMH |  | Below Ground Pipework Checklist - Sewer
checkpoint | LendLease Permits Issued
checkpoint | Set out pits depths and trench runs.
note | As per DRG#
textbox | Drawing No.:
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
note | Spec#: AS3500
textbox | Material used
checkpoint | Bedding placement and compaction and material meets specification.
note | Spec#: AS3500 and Hydraulic Specification
note | 75mm Q-Minus Bedding and Encasement to top of pipe
checkpoint | Laying and jointing of pipes R.Ls and falls
note | PVC solvent welded
note | 1:60 fall
note | AS3500
note | RLs as per hyd drgs
checkpoint | Connections to pits and existing services
checkpoint | Hydrostatic tests are carried out as required.
button | Air or Water? | Water,Air
note | Inspected and recorded by Independent Certifier or PIC (See attached)
checkpoint | Mirror tests are completed if required.
checkpoint | Placement and compaction of backfill and material meets spec.
note | Compacted crushed rock backfill 80% to 100% compaction
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
note | Ongoing
note | To be provided
checkpoint | Sign Off
button | Geschke Group Signature added below | Yes,No,N/A
button | LendLease Signature added below | Yes,No,N/A
button | ARUP Group Signature added below | Yes,No,N/A